## 880
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
CB393 | SGBM12 | Jan 19 2016 6:30PM | Jan 21 2016 11:16AM | 39.360 | 37.775 | 6, 8, 14 | 26.521 | 39.360 | 11.254 |  | 0.0 | 9.5 | 10T25 | T10-150 | 12.254 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055426 | 8.5
CB394 | SGBM12 | Jan 15 2016 5:00PM | Jan 18 2016 11:26AM | 39.690 | 37.775 | 0.25, 7, 11, 13.8 | 26.625 | 39.690 | 11.150 |  | 0.0 | 9.0 | 10T25 | T10-150 | 12.15 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045276 | 8.5
CB395 | SGBM12 | Jan 23 2016 9:00AM | Jan 26 2016 4:05PM | 39.675 | 37.775 | 5, 6, 9, 11, 13 | 26.598 | 39.675 | 11.177 |  | 0.0 | 9.9 | 10T25 | T10-150 | 12.177 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045489 | 8.5
CB396 | SGBM12 | Jan 29 2016 8:15AM | Jan 30 2016 5:05PM | 39.850 | 37.775 | 0.25, 5, 7, 11, 13 | 26.645 | 39.850 | 11.130 |  | 0.0 | 9.9 | 10T25 | T10-150 | 12.13 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045745 | 9
CB397 | SGBM12 | Jan 12 2016 4:10PM | Jan 14 2016 2:40PM | 39.840 | 37.775 | 6, 8, 12, 14.15 | 26.655 | 39.840 | 11.120 |  | 0.0 | 9.9 | 10T25 | T10-150 | 12.12 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055243 | 8.5
CB398 | SGBM12 | Jan 21 2016 2:12PM | Jan 22 2016 7:35PM | 39.650 | 37.775 | 0.25, 6, 9, 11 | 26.585 | 39.650 | 11.190 |  | 0.0 | 9.9 | 10T25 | T10-150 | 12.19 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045417 | 8.5
CB399 | SGBM12 | Jan 27 2016 8:15AM | Jan 28 2016 8:30PM | 39.800 | 37.775 | 5, 6, 10 | 26.456 | 39.800 | 11.319 |  | 0.0 | 10.2 | 10T25 | T10-150 | 12.319 | 6.9 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045602 | 8.5
CB400 | SGBM12 | Feb 12 2016 8:00AM | Feb 15 2016 10:00AM | 39.920 | 37.775 | 6, 7, 10, 12, 14.598 | 26.602 | 39.920 | 11.173 |  | 0.0 | 9.9 | 10T25 | T10-150 | 12.137 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046268 | 8.5
CB401 | SGBM12 | Feb 2 2016 8:30AM | Feb 3 2016 8:55PM | 39.880 | 37.775 | 6, 7, 11, 13 | 26.507 | 39.880 | 11.268 |  | 0.0 | 10.0 | 10T25 | T10-150 | 12.268 | 6.9 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046009 | 8.5
CB402 | SGBM12 | Feb 25 2016 2:30PM | Feb 27 2016 2:30PM | 39.660 | 37.775 | 6, 8, 10, 13 | 26.990 | 39.660 | 10.785 |  | 0.0 | 9.8 | 10T25 | T10-150 | 12.218 | 6.6 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047067 | 10
CB403 | SGBM12 | Mar 2 2016 2:00PM | Mar 4 2016 4:56PM | 39.600 | 37.775 | 6, 8, 10, 12.5 | 26.655 | 39.600 | 11.120 |  | 0.0 | 9.9 | 10T25 | T10-150 | 12.12 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201047403 | 8.5
CB404 | SGBM12 | Mar 9 2016 8:00AM | Mar 11 2016 12:19PM | 39.570 | 37.775 | 6, 8, 10.5, 12, 14 | 26.626 | 39.570 | 11.149 |  | 0.0 | 9.3 | 10T25 | T10-150 | 12.149 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201047763 | 8.5
CB405 | SGBM12 | Mar 15 2016 8:00AM | Mar 16 2016 11:30AM | 39.640 | 37.775 | 7, 9, 14 | 26.698 | 39.640 | 11.077 |  | 0.0 | 9.8 | 10T25 | T10-150 | 12.077 | 6.7 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P101055644 | 8.5
CB406 | SGBM12 | Mar 12 2016 8:00AM | Mar 14 2016 1:55PM | 39.550 | 37.775 | 6, 8, 12, 14.45 | 26.560 | 39.550 | 11.215 |  | 0.0 | 10.4 | 10T25 | T10-150 | 12.215 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P101055611 | 8.5
CB407 | SGBM12 | Mar 5 2016 8:30AM | Mar 8 2016 5:10PM | 39.600 | 37.775 | 6, 8, 10, 12, 14 | 26.532 | 39.600 | 11.243 |  | 0.0 | 10.4 | 10T25 | T10-150 | 12.240 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201047606 | 8.5
CB408 | SGBM12 | Feb 29 2016 8:00AM | Mar 2 2016 12:45PM | 39.500 | 37.775 | 6, 7, 10, 12, 14.5 | 26.575 | 39.500 | 11.200 |  | 0.0 | 10.1 | 10T25 | T10-150 | 12.2 | 6.8 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047244 | 10
CB409 | SGBM12 | Jan 18 2016 4:10PM | Jan 19 2016 6:01PM | 39.836 | 38.425 | 6, 8, 12 | 26.554 | 39.836 | 11.871 |  | 0.0 | 10.1 | 10T25 | T10-150 | 12.221 | 7.2 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | Pending | 8.5
CB410 | SGBM12 | Dec 18 2015 3:30PM | Dec 21 2015 11:35AM | 39.770 | 37.775 | 6, 8, 12, 14.025 | 26.672 | 39.770 | 11.103 |  | 8.0 | 9.8 | 10T25 | T10-150 | 12.103 | 6.8 | 8.5 | 25.9 | 30 TREMIE 2 (JKR) | P100054073 | 8.5
CB412 | SGBM12 | Dec 28 2015 8:00AM | Dec 29 2015 6:55PM | 39.770 | 37.775 | 6, 8, 12, 14.23 | 26.652 | 39.770 | 11.123 |  | 8.2 | 10.0 | 10T25 | T10-150 | 12.123 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054453 | 8
CB413 | SGBM12 | Dec 31 2015 10:35AM | Jan 2 2016 6:26PM | 39.715 | 37.775 | 5, 6.5, 11, 13 | 26.663 | 39.715 | 11.112 |  | 0.0 | 9.8 | 10T25 | T10-150 | 12.112 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054671 | 8.5
CB414 | SGBM12 | Jan 6 2016 9:00AM | Jan 7 2016 2:40PM | 39.734 | 37.775 | 6, 8, 12 | 26.603 | 39.734 | 11.172 |  | 0.0 | 9.6 | 10T25 | T10-150 | 12.172 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054918 | 8.5
CB411 | SGBM10 | Dec 10 2015 5:10PM | Dec 15 2015 4:08PM | 39.715 | 37.775 | 5, 7.5, 8.5, 10, 12, 13.595 | 26.625 | 39.715 | 11.150 |  | 8.6 | 10.1 | 10T25 | T10-150 | 12.15 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053838 | 8
CB415 | SGBM12 | Jan 14 2016 3:30PM | Jan 15 2016 3:44PM | 39.674 | 37.775 | 6, 10 | 26.577 | 39.674 | 11.198 |  | 0.0 | 8.6 | 10T25 | T10-150 | 12.189 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045210 | 8.5
CB416 | SGBM12 | Dec 23 2015 9:30AM | Dec 26 2015 10:45PM | 39.974 | 37.775 | 5, 6, 10.9, 12.3 | 26.630 | 39.974 | 11.145 |  | 8.5 | 9.2 | 10T25 | T10-150 | 12.145 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054337 | 8
CB417 | SGBM10 | Dec 15 2015 8:00AM | Dec 17 2015 3:35PM | 39.745 | 37.775 | 6, 7, 11, 14.5 | 26.556 | 39.745 | 11.219 |  | 8.6 | 10.5 | 10T25 | T10-150 | 12.219 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053930 | 8
CB418 | SGBM10 | Dec 9 2015 10:30AM | Dec 10 2015 7:30PM | 39.768 | 37.775 | 6, 10.5, 13 | 26.580 | 39.768 | 11.195 |  | 8.4 | 10.2 | 10T25 | T10-150 | 12.195 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053624 | 8
CB419 | SGBM12 | Jan 9 2016 6:10PM | Jan 12 2016 4:58PM | 39.830 | 37.775 | 6, 9, 13 | 26.656 | 39.830 | 11.119 |  | 0.0 | 9.8 | 10T25 | T10-150 | 12.119 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055150 | 8.5
CB420 | SGBM12 | Jan 4 2016 10:00AM | Jan 5 2016 2:56PM | 39.885 | 37.775 | 4.5, 6, 12, 14.5 | 26.565 | 39.885 | 11.210 |  | 0.0 | 10.4 | 10T25 | T10-150 | 12.21 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054786 | 8.5
CB421 | SGBM12 | Dec 29 2015 11:00AM | Dec 31 2015 4:16PM | 40.006 | 37.775 | 6, 7.5, 10, 14.4 | 26.601 | 40.006 | 11.174 |  | 8.5 | 9.8 | 10T25 | T10-150 | 12.175 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054604 | 8
CB422 | SGBM12 | Dec 21 2015 11:50AM | Dec 23 2015 9:50AM | 40.651 | 37.775 | 6, 9.2, 11, 14.4 | 26.603 | 40.651 | 11.172 |  | 8.4 | 10.2 | 10T25 | T10-150 | 12.172 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054204 | 8.5
CB423 | SGBM10 | Dec 9 2015 6:00PM | Dec 12 2015 6:00PM | 40.666 | 37.775 | 5, 6.5, 8, 13.5, 14.8 | 26.546 | 40.666 | 11.229 |  | 9.9 | 10.3 | 10T25 | T10-150 | 12.229 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053771 | 8
CB424 | SGBM32 | Oct 23 2015 10:55AM | Oct 26 2015 2:55PM | 40.670 | 37.775 | 7, 9, 12, 14.6 | 26.519 | 2.895 | 11.256 |  | 7.7 | 10.6 | 10T25 | T10-150 | 12.6 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051088 | 9
CB425 | SGBM32 | Oct 6 2015 1:10PM | Dec 7 2015 9:20PM | 40.675 | 37.775 | 5.7, 7.5, 12 | 26.488 | 2.900 | 11.287 |  | 9.9 | 9.8 | 10T25 | T10-150 | 12.287 | 6.9 | 9.0 | 31.1 | 30 TREMIE 2 (JKR) | 1 | 9
CB426 | SGBM32 | Oct 15 2015 8:00AM | Oct 16 2015 6:00PM | 40.680 | 37.775 | 4.255, 6, 11, 13 | 26.620 | 2.905 | 11.155 |  | 10.6 | 10.5 | 10T25 | T10-150 | 12.155 | 6.8 | 9.0 | 32.6 | 30 TREMIE 2 (JKR) | P100050567 | 9
CB427 | SGBM32 | Oct 19 2015 9:15AM | Oct 21 2015 8:20PM | 40.690 | 37.775 | 4.194, 4.2, 5, 10 | 26.600 | 40.690 | 11.175 |  | 10.4 | 10.4 | 10T25 | T10-150 | 12.6 | 6.8 | 9.0 | 32.4 | 30 TREMIE 2 (JKR) | P100050814 | 9
CB428 | SGBM32 | Oct 28 2015 11:15AM | Oct 29 2015 6:55PM | 40.620 | 37.775 | 7, 9, 13 | 26.552 | 40.620 | 11.223 |  | 9.3 | 9.9 | 10T25 | T10-150 | 12.5 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051339 | 8
CB429 | SGBM32 | Oct 10 2015 2:30PM | Oct 12 2015 9:42PM | 40.694 | 37.775 | 7.11, 9, 13.6 | 26.454 | 2.919 | 11.321 |  | 8.4 | 8.6 | 10T25 | T10-150 | 12.325 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050336 | 9
CB430 | SGBM32 | Oct 3 2015 8:45AM | Oct 5 2015 2:30PM | 40.680 | 37.775 | 8.2, 15.4 | 26.270 | 40.680 | 11.505 |  | 7.3 | 7.4 | 18T32 | T12-200 | 12.65 | 7.0 | 10.0 | 42.9 | 30 TREMIE 2 (JKR) | 1 | 10
CB431 |  | Oct 22 2015 8:00AM | Oct 23 2015 5:45PM | 40.640 | 37.775 | 9.145, 10.5, 15.4 | 26.123 | 40.640 | 11.652 |  | 6.6 | 7.2 | 18T32 | T12-200 | 13.2 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050909 | 9
CB432 | SGBM32 | Oct 26 2015 8:50AM | Oct 27 2015 5:05PM | 40.570 | 37.775 | 7.843, 13 | 26.163 | 40.570 | 11.612 |  | 6.9 | 6.9 | 18T32 | T12-200 | 13.2 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051162 | 9
CB433 | SGBM32 | Oct 8 2015 9:00AM | Oct 10 2015 5:05PM | 40.651 | 37.775 | 10.585, 12.6, 14, 15.8 | 26.046 | 2.876 | 11.729 |  | 5.4 | 5.4 | 18T32 | T12-200 | 13.029 | 7.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050234 | 10
CB434 | SGBM32 | Oct 13 2015 8:00AM | Oct 13 2015 9:00PM | 40.650 | 37.775 | 11.33 | 25.980 | 40.650 | 11.795 |  | 4.5 | 4.5 | 18T32 | T12-200 | 13.745 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050379 | 10
CB435 | SGBM32 | Oct 1 2015 5:00PM | Oct 2 2015 9:50PM | 40.660 | 37.775 | 12.64 | 26.105 | 40.660 | 11.670 |  | 2.8 | 2.8 | 18T32 | T12-200 | 12.97 | 7.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049787 | 10
CB436 | SGBM32 | Oct 5 2015 11:10AM | Oct 6 2015 7:15PM | 40.635 | 37.775 | 18.21 | 21.555 | 40.635 | 16.220 |  | 2.0 | 16.2 | 18T32 | T12-200 | 17.7 | 9.9 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049983, P100049987 | 7, 7
CB437 | SGBM32 | Oct 27 2015 11:30AM | Oct 28 2015 8:35PM | 40.620 | 37.775 | 18 | 22.582 | 2.845 | 15.193 |  | 0.8 | 3.4 | 18T32 | T12-200 | 18.7 | 9.2 | 13.0 | -9.2 | 30 TREMIE 2 (JKR) | P100051265, P100051266 | 7, 6
CB438 | SGBM32 | Nov 2 2015 5:50PM | Nov 3 2015 8:26PM | 40.640 | 37.775 | 4.88, 7.6, 9, 19.2 | 16.504 | 40.640 | 21.271 |  | 5.3 | 19.6 | 18T32 | T12-200 | 22.571 | 12.9 | 19.0 | -280.9 | 30 TREMIE 2 (JKR) | P100051579, P100051580 | 10, 9
CB439 | SGBM32 | Oct 16 2015 5:15PM | Oct 19 2015 7:05PM | 40.660 | 37.775 | 5.5, 6.5, 21.768, 23.5 | 17.652 | 40.660 | 20.123 |  | 2.1 | 18.8 | 18T32 | T12-200 | 20.8 | 12.2 | 15.0 | 22.5 | 30 TREMIE 2 (JKR) | P100050685, P100050686 | 9, 6
CB440 | SGBM32 | Sep 29 2015 9:00AM | Oct 2 2015 4:20PM | 40.660 | 37.775 | 5.32, 6, 8.6, 9.5, 11, 19.8, 25 | 16.540 | 40.660 | 21.235 |  | 19.8 | 2.1 | 18T32 | T12-200 | 22.532 | 12.9 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049752, P100049753 | 9, 9
CB441 | SGBM32 | Oct 29 2015 6:20PM | Oct 31 2015 6:20PM | 40.640 | 37.775 | 6.155, 7.5 | 16.477 | 40.640 | 21.298 |  | 7.3 | 18.4 | 18T32 | T12-200 | 22.7 | 13.0 | 18.0 | 10.5 | 30 TREMIE 2 (JKR) | P100051469, P100051473 | 9, 9
CB442 | SGBM32 | Nov 4 2015 8:30AM | Nov 5 2015 5:50PM | 40.640 | 37.775 | 6.317, 8, 15, 16.6 | 22.846 | 40.640 | 14.929 |  | 3.3 | 11.0 | 18T32 | T12-200 | 16.229 | 9.1 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051665 | 12
CB443 | SGBM32 | Nov 12 2015 8:00AM | Nov 20 2015 5:42PM | 40.610 | 37.775 | 6.215, 9, 13 | 26.492 | 40.610 | 11.283 |  | 8.2 | 8.2 | 10T25 | T10-150 | 12.3 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052485 | 9
CB444 | SGBM10 | Nov 26 2015 8:30AM | Nov 28 2015 3:13PM | 40.590 | 37.775 | 6.112, 8, 12 | 26.463 | 40.590 | 11.312 |  | 8.8 | 8.8 | 10T25 | T10-150 | 12.312 | 6.9 | 9.0 | 30.8 | 30 TREMIE 2 (JKR) | P100052883 | 9
CB445 | SGBM10 | Nov 21 2015 4:45PM | Nov 24 2015 3:40PM | 40.620 | 37.775 | 6.24, 8, 10, 12.8, 14.6 | 26.269 | 40.620 | 11.506 |  | 8.5 | 8.5 | 10T25 | T10-150 | 12.506 | 7.0 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052702 | 8
CB446 | SGBM10 | Nov 11 2015 5:30PM | Nov 17 2015 6:22PM | 40.670 | 37.775 | 4.24, 6, 10 | 26.350 | 40.670 | 11.425 |  | 10.3 | 10.3 | 10T25 | T10-150 | 13.4 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052291 | 9
CB447 | SGBM12 | Oct 1 2015 8:00AM | Oct 2 2015 7:40PM | 40.660 | 37.775 | 5.188, 10.5, 11.2, 13.6, 14.4 | 26.410 | 40.660 | 11.365 |  | 9.9 | 10.2 | 18T32 | T12-200 | 13.02 | 6.9 | 10.0 | -6.9 | 30 TREMIE 2 (JKR) | P100049774 | 10
CB448 | SGBM32 | Nov 4 2015 7:40PM | Nov 6 2015 8:35PM | 40.640 | 38.425 | 4.265, 7, 10, 12 | 26.638 | 40.640 | 11.787 |  | 10.0 | 10.0 | 10T25 | T10-150 | 12.787 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | 1 | 9
CB449 | SGBM12 | Oct 12 2015 4:30PM | Oct 15 2015 4:45PM | 40.670 | 38.425 | 5.55, 7, 9.5, 12.8, 14.5 | 26.370 | 40.670 | 12.055 |  | 9.4 | 9.4 | 10T25 | T10-150 | 13.055 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050514 | 9
CB450 | SGBM12 | Oct 19 2015 8:55AM | Oct 22 2015 3:30PM | 40.660 | 38.425 | 4.5, 5.5, 8, 12.5, 14.7 | 26.350 | 40.660 | 12.075 |  | 10.6 | 0.0 | 10T25 | T10-150 | 13.1 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050844 | 9
CB451 | SGBM32 | Oct 31 2015 2:00PM | Nov 2 2015 7:00PM | 40.665 | 38.425 | 4.5, 8, 12 | 26.606 | 40.665 | 11.819 |  | 9.8 | 9.8 | 10T25 | T10-150 | 13.1 | 7.2 | 9.0 | -7.2 | 30 TREMIE 2 (JKR) | P100051553 | 9
CB452 | SGBM12 | Oct 5 2015 12:10PM | Oct 6 2015 9:10PM | 40.660 | 38.425 | 4.875, 7.3, 9, 10.5 | 26.675 | 2.235 | 11.750 |  | 9.7 | 9.7 | 10T25 | T10-150 | 12.75 | 7.1 | 10.0 | -7.1 | 30 TREMIE 2 (JKR) | P100049989 | 10
CB454 |  | Oct 7 2015 8:45AM | Oct 9 2015 3:20PM | 40.670 | 38.425 | 5.02, 7.7, 10, 12.8, 15 | 26.585 | 40.670 | 11.840 |  | 10.1 | 10.1 | 10T25 | T10-150 | 12.835 | 7.2 | 10.0 | -7.2 | 30 TREMIE 2 (JKR) | P100050170 | 10
CB455 | SGBM12 | Sep 23 2015 10:00AM | Sep 26 2015 9:06PM | 40.680 | 38.425 | 4.297, 5, 8, 9.2, 11.2, 13 | 26.700 | 40.680 | 11.725 |  | 10.3 | 9.5 | 10T25 | T10-150 | 12.725 | 7.1 | 10.0 | 17.0 | 30 TREMIE 2 (JKR) | P100049420 | 10
CB453 | SGBM12 | Sep 28 2015 9:35AM | Sep 30 2015 8:50PM | 40.680 | 38.425 | 4.97, 6, 11.8, 13.5, 14.5, 15 | 26.600 | 40.680 | 11.825 |  | 10.0 | 10.3 | 10T25 | T10-150 | 13.05 | 7.2 | 12.0 | -7.2 | 30 TREMIE 2 (JKR) | P100049657 | 12
CB456 | SGBM12 | Oct 22 2015 2:00PM | Oct 28 2015 4:15PM | 40.620 | 38.425 | 4.28, 7.3, 9.4, 11, 11.8, 13.8, 14.5 | 26.586 | 40.620 | 11.839 |  | 10.3 | 0.0 | 10T25 | T10-150 | 13.1 | 7.2 | 9.0 | -7.2 | 30 TREMIE 2 (JKR) | P100051246 | 9
CB457 | SGBM12 | Oct 15 2015 3:50PM | Oct 17 2015 7:25PM | 40.630 | 38.425 | 5.2, 6.5, 11, 13.1 | 26.613 | 40.630 | 11.812 |  | 10.3 | 0.0 | 10T25 | T10-150 | 12.812 | 7.2 | 9.0 | -7.2 | 30 TREMIE 2 (JKR) | P100050618 | 9
CB458 | SGBM12 | Sep 28 2015 8:00AM | Sep 29 2015 6:58PM | 40.690 | 38.425 | 6, 9, 14.2 | 26.599 | 2.265 | 11.826 |  | 10.0 | 10.0 | 10T25 | T10-150 | 12.826 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049541 | 10
CB459 | SGBM12 | Oct 3 2015 9:15AM | Oct 5 2015 2:00PM | 40.690 | 38.425 | 5.02, 6.5, 13.5 | 26.520 | 40.690 | 11.905 |  | 10.1 | 10.1 | 10T25 | T10-150 | 12.947 | 7.2 | 10.0 | -7.2 | 30 TREMIE 2 (JKR) | 1 | 10
CB460 | SGBM12 | Sep 22 2015 3:30PM | Sep 25 2015 8:57PM | 40.685 | 38.425 | 5.5, 7.5, 9, 10.2 | 26.713 | 40.685 | 11.712 |  | 9.4 | 9.4 | 10T25 | T10-150 | 12.712 | 7.1 | 13.0 | 17.0 | 30 TREMIE 2 (JKR) | P100049356, P100049358 | 6.5, 6.5
CB461 | SGBM12 | Oct 7 2015 6:00PM | Oct 12 2015 9:00PM | 40.670 | 38.425 | 4.755, 7, 8.5, 10, 13 | 26.580 | 40.670 | 11.845 |  | 9.7 | 9.7 | 10T25 | T10-150 | 12.852 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050331 | 10
CB462 | SGBM12 | Oct 16 2015 5:30PM | Oct 20 2015 5:40PM | 40.680 | 38.425 | 6.5, 10.3, 14.5 | 26.560 | 40.680 | 11.865 |  | 9.2 | 0.0 | 10T25 | T10-150 | 13 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050734 | 9
CB463 | SGBM12 | Oct 28 2015 10:35AM | Oct 29 2015 8:00PM | 40.730 | 38.425 | 6.5, 10.5, 12.5 | 26.485 | 40.730 | 11.940 |  | 9.5 | 0.0 | 10T25 | T10-150 | 13.1 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051345 | 9
CB464 |  | Nov 2 2015 4:15PM | Nov 4 2015 2:23PM | 40.680 | 38.425 | 6.258, 8.2, 10.9, 14 | 26.841 | 40.680 | 11.584 |  | 8.6 | 0.0 | 10T25 | T10-150 | 12.887 | 7.0 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051596 | 9
CB465 | SGBM32 | Nov 12 2015 9:35AM | Nov 19 2015 6:45PM | 40.501 | 38.425 | 5.45, 7, 8.6, 11, 12 | 26.680 | 40.501 | 11.745 |  | 8.8 | 8.8 | 10T25 | T10-150 | 12.8 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052433 | 9
CB466 | SGBM10 | Nov 24 2015 8:30AM | Nov 25 2015 2:52PM | 40.500 | 38.425 | 6.49, 9, 13, 15.145 | 26.577 | 40.500 | 11.848 |  | 8.7 | 8.7 | 10T25 | T10-150 | 12.845 | 7.2 | 10.0 | -7.2 | 30 TREMIE 2 (JKR) | P100052762 | 10
CB467 | SGBM10 | Nov 28 2015 3:45PM | Nov 30 2015 11:49PM | 40.450 | 38.425 | 9.2, 12 | 26.695 | 40.450 | 11.730 |  | 5.4 | 7.4 | 10T25 | T10-150 | 12.73 | 7.1 | 10.0 | -7.1 | 30 TREMIE 2 (JKR) | P100053019 | 10
CB468 | SGBM10 | Dec 4 2015 5:30PM | Dec 5 2015 12:15AM | 40.440 | 38.425 | 7.675, 9, 12 | 26.484 | 40.440 | 11.941 |  | 6.8 | 6.8 | 10T25 | T10-150 | 12.941 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053412 | 9
CB469 | SGBM10 | Nov 25 2015 8:30AM | Nov 27 2015 2:09PM | 40.447 | 38.425 | 9.023, 14.6 | 26.640 | 40.447 | 11.785 |  | 5.8 | 5.8 | 10T25 | T10-150 | 12.785 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052833 | 10
CB471 | SGBM12 | Oct 31 2015 2:50PM | Nov 2 2015 5:05PM | 40.430 | 38.425 | 7.13, 10.5, 13 | 26.645 | 40.430 | 11.780 |  | 7.1 | 7.1 | 10T25 | T10-150 | 13.1 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051545 | 9
CB472 | SGBM10 | Nov 19 2015 6:30PM | Nov 21 2015 11:20PM | 40.510 | 38.425 | 6, 11.7, 13.3 | 26.672 | 40.510 | 11.753 |  | 8.2 | 8.2 | 10T25 | T10-150 | 12.753 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | 1 | 9
CB474 | SGBM32 | Nov 7 2015 10:15AM | Nov 9 2015 6:00PM | 40.530 | 38.425 | 6.335, 10, 13 | 26.655 | 40.530 | 11.770 |  | 8.1 | 7.8 | 10T25 | T10-150 | 12.77 | 7.2 | 9.0 | 25.7 | 30 TREMIE 2 (JKR) | P100051902 | 9
CB475 | SGBM12 | Oct 30 2015 8:00AM | Oct 31 2015 4:30PM | 40.470 | 38.425 | 8, 9, 11.8, 14.7 | 26.420 | 2.045 | 12.005 |  | 7.3 | 7.6 | 10T25 | T10-150 | 13.2 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051456 | 9
CB476 |  | Nov 3 2015 7:00PM | Nov 5 2015 5:50PM | 40.540 | 38.425 | 7.62, 8, 11.9, 14.7 | 26.468 | 40.540 | 11.957 |  | 7.6 | 0.0 | 10T25 | T10-150 | 22.957 | 7.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051673 | 10
CB477 | SGBM10 | Nov 25 2015 8:00AM | Nov 28 2015 4:09PM | 40.527 | 38.425 | 7.207, 8.3, 12, 13.6 | 26.483 | 40.527 | 11.942 |  | 7.4 | 7.4 | 10T25 | T10-150 | 12.935 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052885 | 9
CB478 | SGBM10 | Dec 1 2015 8:00AM | Dec 4 2015 7:30PM | 40.469 | 38.425 | 7.128, 8, 11, 13.5, 14.6 | 26.643 | 40.469 | 11.782 |  | 7.6 | 7.6 | 10T25 | T10-150 | 12.783 | 7.2 | 9.0 | 25.6 | 30 TREMIE 2 (JKR) | P100053290 | 9
CB479 | SGBM10 | Dec 22 2015 8:00AM | Dec 23 2015 5:53PM | 40.580 | 38.425 | 9, 12, 14.8 | 26.630 | 40.580 | 11.795 |  | 5.9 | 7.7 | 10T25 | T10-150 | 12.795 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054220 | 9
CB480 | SGBM10 | Dec 26 2015 6:10PM | Dec 29 2015 8:12PM | 40.597 | 38.425 | 9, 10.5, 14, 15.238 | 26.672 | 40.597 | 11.753 |  | 6.2 | 7.7 | 10T25 | T10-150 | 12.753 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054464 | 9
CB481 | SGBM10 | Jan 6 2016 10:45AM | Jan 7 2016 6:34PM | 40.600 | 38.425 | 9, 12 | 26.679 | 40.600 | 11.746 |  | 0.0 | 7.1 | 10T25 | T10-150 | 12.75 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054952 | 9
CB482 | SGBM10 | Jan 13 2016 8:15AM | Jan 15 2016 10:10AM | 40.452 | 38.425 | 8, 9, 11.2, 12.5, 14.65 | 26.600 | 40.452 | 11.825 |  | 0.0 | 6.8 | 10T25 | T10-150 | 12.825 | 7.2 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055295 | 8.5
CB483 | SGBM10 | Dec 7 2015 8:00AM | Dec 8 2015 1:27PM | 40.690 | 38.425 | 9.273, 13 | 26.613 | 40.690 | 11.812 |  | 5.3 | 5.3 | 10T25 | T10-150 | 12.812 | 7.2 | 9.0 | 25.3 | 30 TREMIE 2 (JKR) | P100053487 | 9
CB484 | SGBM12 | Dec 11 2015 11:15AM | Dec 15 2015 1:40PM | 40.690 | 38.425 | 11.5 | 27.312 | 40.690 | 11.113 |  | 2.4 | 4.2 | 12T25 | T12-150 | 12.113 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | 28066400 | 9
CB485 | SGBM10 | Dec 23 2015 4:15PM | Dec 26 2015 2:40PM | 40.610 | 38.425 | 11 | 27.410 | 40.610 | 11.015 |  | 2.9 | 3.5 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054286 | 9
CB486 | SGBM10 | Dec 30 2015 10:00AM | Dec 30 2015 5:55PM | 40.730 | 38.425 | 13 | 27.453 | 40.730 | 10.972 |  | 1.0 | 2.7 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054547 | 9
CB487 | SGBM10 | Nov 28 2015 8:30AM | Dec 2 2015 9:52PM | 40.700 | 38.425 | 12.16, 16, 19.5, 21 | 20.230 | 40.700 | 18.195 |  | 9.0 | 9.9 | 12T25 | T10-150 | 20.423 | 11.1 | 15.0 | -27.7 | 30 TREMIE 2 (JKR) | P100053146, P100053148 | 8, 7
CB488 | SGBM12 | Dec 9 2015 10:00AM | Dec 10 2015 7:56PM | 40.740 | 38.425 | 0.25, 15.278 | 24.770 | 40.740 | 13.655 |  | 1.1 | 1.1 | 12T25 | T10-150 | 14.655 | 8.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053626 | 10
CB489 | SGBM12 | Dec 15 2015 3:40PM | Dec 18 2015 6:25PM | 40.597 | 38.425 | 11, 12 | 27.423 | 40.597 | 11.002 |  | 2.5 | 3.8 | 12T25 | T12-150 | 9 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054018 | 9
CB491 | SGBM10 | Jan 9 2016 5:00PM | Jan 11 2016 7:52PM | 40.635 | 38.425 | 10.5, 13.5 | 27.451 | 40.635 | 10.974 |  | 0.0 | 4.3 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055107 | 9
CB492 | SGBM10 | Jan 4 2016 4:00PM | Jan 5 2016 4:13PM | 40.692 | 38.425 | 11.5, 13.8 | 27.464 | 40.692 | 10.961 |  | 0.0 | 3.9 | 12T25 | T10-150 | 12 | 6.7 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054791 | 8.5
CB493 | SGBM10 | Dec 31 2015 4:40PM | Jan 2 2016 5:00PM | 40.627 | 38.425 | 12, 14 | 27.407 | 40.627 | 11.018 |  | 2.1 | 3.1 | 12T25 | T10-150 | 12 | 6.7 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054665 | 8.5
CB494 | SGBM10 | Jan 8 2016 8:00AM | Jan 8 2016 5:06PM | 40.600 | 38.425 | 12, 12.6 | 27.487 | 40.600 | 10.938 |  | 0.0 | 2.3 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054969 | 9
CB495 | SGBM10 | Jan 12 2016 4:34PM | Jan 13 2016 7:45PM | 40.685 | 38 | 10.5, 12 | 27.370 | 40.685 | 10.630 |  | 0.0 | 4.4 | 12T25 | T10-150 | 12 | 6.5 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055196 | 9
CB496 | SGBM10 | Dec 19 2015 8:00AM | Dec 21 2015 5:50PM | 40.625 | 38.425 | 13, 14.2 | 27.339 | 40.625 | 11.086 |  | 1.3 | 2.1 | 12T25 | T10-150 | 12.086 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054097 | 9
CB497 | SGBM10 | Dec 8 2015 9:50AM | Dec 8 2015 6:39PM | 40.660 | 38.425 | 13 | 27.122 | 2.235 | 11.303 |  | 2.2 | 2.2 | 12T25 | T10-150 | 12.303 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053503 | 9
CB498 | SGBM10 | Jan 12 2016 8:00AM | Jan 12 2016 5:39PM | 40.770 | 38.425 | 4, 13 | 27.260 | 40.770 | 11.165 |  | 0.0 | 2.6 | 12T25 | T10-150 | 12.162 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055151 | 9
CB499 | SGBM10 | Jan 2 2016 5:30PM | Jan 4 2016 4:42PM | 40.831 | 38.425 | 11, 12.5 | 27.420 | 40.831 | 11.005 |  | 0.0 | 5.1 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054747 | 9
CB500 | SGBM10 | Dec 29 2015 3:00PM | Dec 30 2015 3:02PM | 40.760 | 38.425 | 11.6, 13 | 27.440 | 40.760 | 10.985 |  | 2.7 | 3.3 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054533 | 9
CB501 | SGBM10 | Jan 8 2016 6:00PM | Jan 9 2016 6:11PM | 40.580 | 38.425 | 12, 13 | 27.186 | 40.580 | 11.239 |  | 0.0 | 2.5 | 12T25 | T10-150 | 12.239 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055035 | 9
CB502 | SGBM10 | Jan 19 2016 4:45PM | Jan 20 2016 6:45PM | 40.738 | 38.425 | 11, 14.4 | 27.324 | 40.738 | 11.101 |  | 0.0 | 5.0 | 12T25 | T10-150 | 12.102 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045375 | 9
CB503 | SGBM10 | Dec 21 2015 8:00AM | Dec 21 2015 7:08PM | 40.674 | 38.425 | 11, 13 | 27.200 | 40.674 | 11.225 |  | 3.3 | 4.4 | 12T25 | T10-150 | 12.225 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054103 | 9
CB504 | SGBM12 | Dec 14 2015 6:20PM | Dec 15 2015 3:55PM | 40.680 | 38.425 | 13, 14.4 | 27.292 | 40.680 | 11.133 |  | 1.5 | 2.2 | 12T25 | T12-150 | 12 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053837 | 9
CB505 | SGBM10 | Jan 5 2016 3:30PM | Jan 6 2016 3:14PM | 40.760 | 38.425 | 10.5, 11.5 | 27.405 | 40.760 | 11.020 |  | 0.0 | 4.9 | 12T25 | T10-150 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054837 | 9
CB506 | SGBM10 | Dec 30 2015 5:30PM | Dec 31 2015 7:48PM | 40.700 | 38.425 | 11, 14 | 27.383 | 40.700 | 11.042 |  | 3.3 | 5.0 | 12T25 | T10-150 | 12.042 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054622 | 9
CB507 | SGBM10 | Dec 26 2015 1:00PM | Dec 26 2015 10:00PM | 40.770 | 38 | 12 | 27.436 | 40.770 | 10.564 |  | 2.1 | 4.2 | 12T25 | T10-150 | 12 | 6.4 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054333 | 8
CB508 | SGBM10 | Dec 17 2015 3:25PM | Dec 18 2015 11:50AM | 40.705 | 38.425 | 10, 12 | 27.355 | 40.705 | 11.070 |  | 4.3 | 4.8 | 12T25 | T12-150 | 12.07 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054065 | 9
CB509 | SGBM12 | Dec 9 2015 2:15PM | Dec 11 2015 6:40PM | 40.920 | 38.425 | 18 | 27.528 | 40.920 | 10.897 |  | 1.2 | 1.2 | 12T25 | T10-150 | 15.462 | 6.6 | 12.0 | 27.6 | 30 TREMIE 2 (JKR) | P100053692 | 12
CB510 | SGBM12 | Dec 3 2015 8:00AM | Dec 3 2015 7:10PM | 40.925 | 38.425 | 16.815 | 23.660 | 40.925 | 14.765 |  | 1.2 | 1.2 | 12T25 | T10-150 | 15.765 | 9.0 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053224, P100053224 | 6, 6
CB511 | SGBM12 | Nov 6 2015 8:00AM | Nov 7 2015 5:10PM | 40.915 | 38.425 | 17.65, 20.5, 24 | 16.515 | 40.915 | 21.910 |  | 8.2 | 8.2 | 10T25 | T10-150 | 22.51 | 13.3 | 22.0 | -147.6 | 30 TREMIE 2 (JKR) | P100051815, P100051820 | 5, 17
CB512 | SGBM12 | Nov 21 2015 8:00AM | Nov 21 2015 11:25PM | 40.000 | 38.425 | 17.053 | 23.451 | 40.000 | 14.974 |  | 1.1 | 1.1 | 12T25 | T10-150 | 15.974 | 9.1 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052591 | 12
CB513 | SGBM12 | Nov 30 2015 8:00AM | Nov 30 2015 8:25PM | 41.005 | 38.425 | 16.392 | 24.385 | 41.005 | 14.040 |  | 1.1 | 1.1 | 12T25 | T10-150 | 15.04 | 8.5 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052991 | 12
CB514 | SGBM12 | Dec 4 2015 9:34AM | Dec 4 2015 9:06PM | 41.005 | 38.425 | 17 | 24.177 | 41.005 | 14.248 |  | 0.6 | 1.2 | 12T25 | T10-150 | 15.248 | 8.7 | 13.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053307, P100053308 | 7, 6
CB515 | SGBM12 | Dec 8 2015 8:00AM | Dec 8 2015 8:30PM | 41.188 | 38.425 | 16.7 | 24.021 | 41.188 | 14.404 |  | 1.1 | 1.1 | 12T25 | T10-150 | 15.404 | 8.8 | 11.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053512 | 11
CB516 | SGBM10 | Nov 14 2015 8:00AM | Nov 16 2015 4:40PM | 40.950 | 38.425 | 16.6 | 25.208 | 40.950 | 13.217 |  | 0.3 | 1.1 | 12T25 | T10-150 | 12 | 8.0 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052243 | 10
CB517 | SGBM12 | Nov 25 2015 8:30AM | Nov 27 2015 10:00PM | 40.965 | 38.425 | 17.5 | 24.305 | 40.965 | 14.120 |  | 0.6 | 1.3 | 12T25 | T10-150 | 15.113 | 8.6 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052866 | 12
CB518 | SGBM12 | Dec 1 2015 4:30PM | Dec 2 2015 7:20PM | 41.101 | 38.425 | 14.61 | 26.104 | 41.101 | 12.321 |  | 1.1 | 1.1 | 12T25 | T10-150 | 13.322 | 7.5 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053127 | 10
CB519 | SGBM12 | Dec 5 2015 2:59PM | Dec 7 2015 5:00PM | 41.250 | 38.425 | 14.145 | 26.499 | 41.250 | 11.926 |  | 1.1 | 1.1 | 12T25 | T10-150 | 12.926 | 7.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053412 | 10
CB520 | SGBM12 | Nov 23 2015 8:00AM | Nov 23 2015 9:53PM | 41.060 | 38.425 | 14.4, 15 | 26.338 | 41.060 | 12.087 |  | 1.2 | 1.2 | 12T25 | T10-150 | 13.087 | 7.4 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052668 | 10
CB521 | SGBM10 | Nov 12 2015 4:00PM | Nov 16 2015 6:05PM | 40.970 | 38.425 | 14.005 | 26.374 | 40.970 | 12.051 |  | 1.1 | 1.1 | 12T25 | T10-150 | 13.051 | 7.3 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052252, P100052259 | 9, 3
CB522 | SGBM12 | Dec 5 2015 8:00AM | Dec 5 2015 10:45PM | 41.220 | 38.425 | 14.41, 15 | 26.422 | 41.220 | 12.003 |  | 1.1 | 1.1 | 12T25 | T10-150 | 13.003 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053435 | 9
CB523 | SGBM12 | Nov 30 2015 5:00PM | Dec 1 2015 8:28PM | 41.143 | 38.425 | 15.78 | 24.870 | 41.143 | 13.555 |  | 1.0 | 1.0 | 12T25 | T10-150 | 14.565 | 8.2 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053073 | 12
CB524 |  | Nov 23 2015 10:00AM | Nov 23 2015 11:45PM | 41.142 | 38.425 | 14.215 | 26.375 | 41.142 | 12.050 |  | 1.1 | 1.1 | 12T25 | T10-150 | 13.05 | 7.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052675 | 10
CB525 | SGBM12 | Nov 19 2015 2:00PM | Nov 20 2015 10:03PM | 41.140 | 38.425 | 13.707 | 26.942 | 41.140 | 11.483 |  | 1.1 | 1.1 | 12T25 | T10-150 | 12.5 | 7.0 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052507 | 10
CB526 | SGBM12 | Dec 7 2015 8:00AM | Dec 7 2015 6:50PM | 41.310 | 38.425 | 14.163 | 27.095 | 41.310 | 11.330 |  | 1.1 | 1.1 | 12T25 | T12-150 | 12.33 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053445 | 9
CB527 | SGBM12 | Dec 3 2015 8:00AM | Dec 4 2015 6:25PM | 41.140 | 38.425 | 14 | 27.211 | 41.140 | 11.214 |  | 0.7 | 1.2 | 12T25 | T10-150 | 12.214 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053286 | 9
CB528 | SGBM12 | Nov 28 2015 8:00AM | Nov 30 2015 12:59PM | 41.022 | 38.425 | 14.357 | 27.002 | 41.022 | 11.423 |  | 1.1 | 1.1 | 12T25 | T10-150 | 12.423 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052961 | 9
CB529 | SGBM12 | Nov 24 2015 8:00AM | Nov 24 2015 7:35PM | 41.280 | 38.425 | 16.063 | 25.660 | 41.280 | 12.765 |  | 1.1 | 1.1 | 12T25 | T10-150 | 13.765 | 7.8 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052716 | 10
CB392 | SGBM12 | Jan 7 2016 1:15PM | Jan 9 2016 3:12PM | 39.753 | 37.775 | 6, 9, 11.3, 14.3 | 26.680 | 1.978 | 11.095 |  | 10.3 | 10.3 | 10T25 | T10-150 | 12.095 | 6.7 | 8.5 | -6.7 | 30 TREMIE 2 (JKR) | P100055012 | 8.5

## 900
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
CB470 | SGBM32 | Nov 7 2015 8:15AM | Nov 11 2015 6:20PM | 40.440 | 38.425 | 8, 10, 12.5 | 26.591 | 40.440 | 11.834 |  | 6.6 | 0.0 | 10T25 | T10-150 | 12.834 | 7.5 | 9.0 | 19.5 | 30 TREMIE 2 (JKR) | P100051965 | 9
CB473 | SGBM32 | Nov 12 2015 11:15AM | Nov 13 2015 6:45PM | 40.535 | 38.425 | 6.7, 10, 12.5 | 26.625 | 40.535 | 11.800 |  | 7.6 | 7.6 | 10T25 | T10-150 | 12.8 | 7.5 | 9.0 | 19.9 | 30 TREMIE 2 (JKR) | P100052109 | 9
CB490 | SGBM10 | Dec 22 2015 9:30AM | Dec 22 2015 6:30PM | 40.705 | 38.425 | 11 | 27.337 | 2.280 | 11.088 |  | 3.1 | 4.4 | 12T25 | T10-150 | 12.088 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054176 | 9
CB530 | SGBM12 | Nov 19 2015 5:30PM | Nov 20 2015 8:15PM | 41.190 | 0 | 15.737 | 24.608 | 41.190 | -24.608 |  | 0.0 | 1.0 |  |  | 14.8 | -15.7 | 12.0 | -176.6 | 30 TREMIE 2 (JKR) | P100052498 | 12

## 1050
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
17.1/K2 | SGBM10 | Jan 15 2016 2:00PM | Jan 19 2016 4:45PM | 40.464 | 28.575 | 8, 9, 11, 12.1, 15, 15.8 | 25.291 | 11.889 | 3.284 |  | 8.2 | 8.2 | 9T25 | T10-150 | 4.285 | 2.8 | 4.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045344 | 4
18.1/K2 | SGBM12 | Feb 15 2016 9:30AM | Feb 16 2016 5:50PM | 40.540 | 28.575 | 9, 14 | 25.265 | 11.965 | 3.310 |  | 8.4 | 8.4 | 9T25 | T10-150 | 4.31 | 2.9 | 4.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046405 | 4.5
18.1a/K2 | SGBM10 | Jan 21 2016 8:00AM | Jan 22 2016 8:08PM | 40.610 | 35.525 | 17, 18.5, 20 | 19.993 | 5.085 | 15.532 |  | 6.9 | 6.9 | 9T25 | T10-150 | 12 | 13.5 | 16.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045417, P201045419 | 8, 8
19.1/K2 | SGBM10 | Jan 23 2016 8:30AM | Jan 27 2016 11:24PM | 40.590 | 35.525 | 13, 14, 15, 16, 18.5, 20, 21.3 | 19.951 | 5.065 | 15.574 |  | 10.1 | 10.1 | 9T25 | T10-150 | 12 | 13.5 | 16.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045597, P201045602 | 8, 8
20.1/K2 | SGBM10 | Jan 30 2016 8:30AM | Feb 12 2016 9:55AM | 40.780 | 35.525 | 12, 14.5, 16, 18.5, 20, 21.5, 22.2 | 19.570 | 5.255 | 15.955 |  | 12.1 | 12.1 | 9T25 | T10-150 | 12 | 13.8 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046236, P201046237 | 9, 9
21.1/K2 | SGBM10 | Jan 28 2016 8:30AM | Jan 29 2016 6:55PM | 40.850 | 35.525 | 11, 16, 18 | 19.847 | 5.325 | 15.678 |  | 13.3 | 13.3 | 9T25 | T10-150 | 12 | 13.6 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045744, P201045745 | 9, 9

## 1500
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
10.1/H2/1 | SGBM28 | Feb 2 2016 3:30PM | Feb 5 2016 4:05PM | 39.100 | 28.275 | 5.5, 7, 10, 12, 16, 16.25 | 23.700 | 10.825 | 4.575 |  | 11.3 | 11.3 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.575 | 8.1 | 10.0 | 1.9 | 30 TREMIE 2 (JKR) | P201046174 | 10
10.1/H2/2 | SGBM28 | Feb 23 2016 1:00PM | Feb 29 2016 3:45PM | 39.405 | 28.275 | 5, 6, 8, 9, 11, 11.5, 13, 13.6, 15, 15.5, 16.4 | 23.690 | 11.130 | 4.585 |  | 13.6 | 13.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.585 | 8.1 | 10.0 | 1.9 | 30 TREMIE 2 (JKR) | P101055556 | 10
10.1/H2/3 | SGBM30 | Mar 5 2016 8:30AM | Mar 7 2016 8:05PM | 39.530 | 28.275 | 6, 9, 12 | 23.720 | 11.255 | 4.555 |  | 12.3 | 12.3 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.6 | 8.1 | 10.0 | 24.2 | 30 TREMIE 2 (JKR) | P201047538 | 10
10.1/H2/4 | SGBM28 | Mar 1 2016 8:00AM | Mar 3 2016 8:45PM | 39.550 | 28.275 | 7.5, 9, 13, 14.5, 16.8 | 23.730 | 11.275 | 4.545 |  | 11.9 | 11.9 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.545 | 8.0 | 10.0 | 24.5 | 30 TREMIE 2 (JKR) | P201047380 | 10
10.1/K2/1 | SGBM28 | Feb 15 2016 10:00AM | Feb 20 2016 4:35PM | 39.390 | 28.075 | 5.3, 6, 7, 8, 9, 10, 10.5, 12, 13, 15, 16.5, 16.78 | 23.310 | 11.315 | 4.765 |  | 11.8 | 11.8 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.765 | 8.4 | 10.0 | 18.7 | 30 TREMIE 2 (JKR) | P201046663 | 10
10.1/K2/2 | SGBM28 | Jan 28 2016 8:00AM | Feb 2 2016 2:30PM | 39.520 | 28.075 | 3, 4, 6.5, 9.3, 11, 13.5, 15, 17.65 | 23.427 | 11.445 | 4.648 |  | 15.7 | 15.7 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 8.648 | 8.2 | 10.5 | 27.8 | 30 TREMIE 2 (JKR) | P201046013 | 10.5
11.1/H2/1 | SGBM28 | Feb 20 2016 4:30PM | Feb 23 2016 2:13PM | 39.650 | 28.275 | 7, 9, 12, 16.5 | 23.622 | 11.375 | 4.653 |  | 11.1 | 11.1 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.653 | 8.2 | 12.0 | 45.9 | 30 TREMIE 2 (JKR) | P201046815 | 12
11.1/H2/2 | SGBM25 | Jan 14 2016 8:15AM | Jan 16 2016 12:20PM | 40.680 | 28.275 | 6, 8, 12.5, 14.5, 17.6 | 23.740 | 12.405 | 4.535 |  | 11.9 | 4.5 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.535 | 8.0 | 10.0 | 24.8 | 30 TREMIE 2 (JKR) | P201045237 | 10
11.1/H2/3 | SGBM32 | Jan 6 2016 10:30AM | Jan 8 2016 4:46PM | 40.660 | 28.275 | 7, 10.5, 12.6, 17.6 | 23.565 | 12.385 | 4.710 |  | 12.2 | 4.7 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.71 | 8.3 | 10.0 | 20.1 | 30 TREMIE 2 (JKR) | P100054968 | 10
11.1/H2/4 | SGBM30 | Dec 5 2015 5:30PM | Dec 8 2015 1:40PM | 40.580 | 28.275 | 6, 9.5, 12, 17.1 | 23.653 | 12.305 | 4.622 |  | 11.7 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.622 | 8.2 | 10.0 | 22.4 | 30 TREMIE 2 (JKR) | P100053486 | 10
11.1/K2/1 | SGBM28 | Dec 17 2015 11:00AM | Dec 21 2015 4:55PM | 40.580 | 28.075 | 7, 8.5, 10, 13, 14.5, 17.6 | 23.504 | 12.505 | 4.571 |  | 11.9 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.571 | 8.1 | 12.0 | 48.5 | 30 TREMIE 2 (JKR) | P100054092 | 12
11.1/K2/2 | SGBM30 | Dec 10 2015 4:20PM | Dec 12 2015 10:40AM | 40.614 | 28.075 | 6, 8, 13, 17.7 | 23.514 | 12.539 | 4.561 |  | 13.1 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.561 | 8.1 | 10.0 | 24.1 | 30 TREMIE 2 (JKR) | P100053732 | 10
16.1/H2/1 | SGBM30 | Nov 25 2015 11:30AM | Nov 27 2015 7:40PM | 40.547 | 28.075 | 6, 8, 13.5, 18.2 | 23.520 | 12.472 | 4.555 |  | 13.1 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.555 | 8.1 | 11.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052858 | 11
16.1/H2/2 | SGBM30 | Nov 30 2015 6:30PM | Dec 2 2015 8:25PM | 40.571 | 28.075 | 6.5, 8.5, 12.5, 15 | 23.442 | 12.496 | 4.633 |  | 13.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.633 | 8.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053136 | 10
16.1/H2/3 | SGBM25 | Jan 23 2016 11:00AM | Jan 27 2016 4:05PM | 40.460 | 28.075 | 8, 9, 12, 13, 15, 18 | 23.535 | 12.385 | 4.540 |  | 12.9 | 12.9 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.54 | 8.0 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045545 | 10
16.1/H2/4 | SGBM32 | Dec 21 2015 6:30PM | Dec 28 2015 1:56PM | 40.599 | 28.075 | 6, 7, 9, 10.3, 11, 12.5, 14, 16, 17.7 | 23.490 | 12.524 | 4.585 |  | 12.8 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.585 | 8.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054353 | 10
16.1/H2/5 | SGBM25 | Jan 9 2016 1:30PM | Jan 13 2016 10:15PM | 40.514 | 28.075 | 5, 7, 9.6, 11, 14, 16, 18.6 | 22.460 | 12.439 | 5.615 |  | 14.3 | 5.5 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 6.615 | 9.9 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055213 | 12
17.1/H2/3 | SGBM12 | Feb 19 2016 3:40PM | Feb 24 2016 11:13AM | 40.450 | 25.775 | 9, 10, 12, 13, 15, 16, 18.5, 19.8 | 21.174 | 14.675 | 4.601 |  | 11.5 | 11.5 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.601 | 8.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046876 | 10
17.1/H2/4 | SGBM25 | Feb 24 2016 8:15AM | Mar 1 2016 6:30PM | 40.413 | 25.775 | 8.5, 10, 12, 13, 15, 15.6, 17, 17.6, 19, 19.8, 20 | 20.982 | 14.638 | 4.793 |  | 12.6 | 12.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.793 | 8.5 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047200 | 10
17.1/H2/5 | SGBM25 | Mar 11 2016 1:00PM | Mar 15 2016 12:35PM | 40.340 | 25.775 | 9, 10, 11.5, 14.5, 16.5, 19.7 | 21.050 | 14.565 | 4.725 |  | 11.1 | 4.7 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.725 | 8.4 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P101055620 | 10
17.1/H2/6 | SGBM25 | Mar 2 2016 8:00AM | Mar 7 2016 11:30AM | 40.470 | 25.775 | 10.5, 12, 14, 15, 16, 17, 19.7, 19.81 | 21.163 | 14.695 | 4.612 |  | 11.4 | 11.4 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.606 | 8.2 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P101055589 | 12
17.1/J2/1 | SGBM25 | Feb 2 2016 2:30PM | Feb 5 2016 7:33PM | 40.420 | 25.875 | 7, 8.3, 10, 13, 16.5, 19.6 | 21.220 | 14.545 | 4.655 |  | 14.6 | 14.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.555 | 8.2 | 10.0 | -8.2 | 30 TREMIE 2 (JKR) | P201046181 | 10
17.1/J2/2 | SGBM25 | Feb 11 2016 11:30AM | Feb 15 2016 8:05PM | 40.500 | 25.875 | 8, 9.2, 10.5, 13.5, 14.5, 17.5, 18.5 | 21.205 | 14.625 | 4.670 |  | 13.0 | 13.0 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.57 | 8.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046332 | 10
17.1/J2/3 | SGBM25 | Jan 28 2016 8:00AM | Feb 2 2016 4:25PM | 40.490 | 25.875 | 6, 7, 9, 10.5, 12.5, 13.2, 15, 17, 18.5 | 21.192 | 14.615 | 4.683 |  | 14.4 | 14.4 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.583 | 8.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045924 | 10
17.1/J2/4 | SGBM32 | Dec 31 2015 5:00PM | Jan 6 2016 4:45PM | 40.535 | 25.875 | 8, 9.5, 12.5, 14, 17, 19.8, 19.95 | 21.094 | 14.660 | 4.781 |  | 13.5 | 4.8 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.781 | 8.4 | 11.0 | -100.0 | 30 TREMIE 2 (JKR) | P100047290 | 11
17.1/J2/5 | SGBM25 | Jan 16 2016 10:30AM | Jan 19 2016 5:55PM | 40.464 | 25.875 | 7.5, 12, 14.2, 18, 19.8 | 21.291 | 14.589 | 4.584 |  | 14.6 | 14.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.514 | 8.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045348 | 10
17.1/J2/6 | SGBM32 | Dec 28 2015 1:00PM | Dec 31 2015 7:25PM | 40.522 | 25.875 | 6.427, 10.052, 8.752, 6.452, 13.452, 13.952, 18.952 | 21.826 | 14.647 | 4.049 |  | 33.9 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.597 | 7.2 | 11.0 | 53.7 | 30 TREMIE 2 (JKR) | P100054619 | 11
17.1/J2/7 | SGBM25 | Jan 20 2016 10:00AM | Jan 23 2016 1:56PM | 40.440 | 25.875 | 9, 11, 14, 15, 17, 19.7 | 21.120 | 14.565 | 4.755 |  | 13.4 | 13.4 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.655 | 8.4 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055515 | 10
17.1/J2/8 | SGBM32 | Jan 8 2016 1:30PM | Jan 12 2016 4:20PM | 40.485 | 25.875 | 7.5, 9, 11, 14, 16.5, 21, 21.278 | 19.780 | 14.610 | 6.095 |  | 14.4 | 4.5 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.497 | 10.8 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055141 | 10

## 1650
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
11.1/F2 | SGBM32 | Dec 18 2015 2:30PM | Dec 21 2015 2:29PM | 30.740 | 28.575 | 5.5, 7, 9, 12.1 | 19.601 | 2.165 | 8.974 |  | 7.2 | 7.2 | 24T25 | T10-150 | 9.974 | 19.2 | 24.0 | 25.1 | 30 TREMIE 2 (JKR) | P100054079, P100054080, P100054083 | 8, 8, 8
12.1/K2/1 | SGBM28 | Nov 30 2015 10:00AM | Dec 2 2015 5:16PM | 40.582 | 27.775 | 8, 9, 11, 13, 17, 19.5 | 21.533 | 12.807 | 6.242 |  | 13.3 | 6.2 | 24T25 | T10-150 | 7.242 | 13.3 | 16.0 | 19.9 | 30 TREMIE 2 (JKR) | P100053117, P100053118 | 8, 8
12.1/K2/2 | SGBM28 | Nov 21 2015 6:30PM | Nov 25 2015 5:22PM | 40.550 | 27.775 | 9.5, 12, 15, 19.8 | 21.400 | 12.775 | 6.375 |  | 11.2 | 6.4 | 24T25 | T10-150 | 7.375 | 13.6 | 16.0 | 17.4 | 30 TREMIE 2 (JKR) | P100052773, P100052775 | 8, 8
13.1/K2/1 | SGBM28 | Dec 4 2015 1:00PM | Dec 8 2015 3:45PM | 40.600 | 27.775 | 6.5, 9, 12.5, 18, 21, 26.4 | 14.833 | 12.825 | 12.942 |  | 21.4 | 12.9 | 24T25 | T10-150 | 13.942 | 27.7 | 36.0 | 30.1 | 30 TREMIE 2 (JKR) | P100053493, P100053494, P100053495, P100053497 | 9, 9, 9, 9
13.1/K2/2 | SGBM28 | Dec 11 2015 3:30PM | Dec 15 2015 2:20PM | 40.612 | 27.775 | 7, 9, 12, 18, 23 | 14.843 | 12.837 | 12.932 |  | 21.7 | 12.9 | 24T25 | T10-150 | 13.932 | 27.7 | 34.0 | 22.9 | 30 TREMIE 2 (JKR) | 28066409, 28066410, 28066415, 28066427 | 8, 6, 10, 10
14.1/K2/1 | SGBM28 | Dec 2 2015 3:30PM | Dec 4 2015 3:15PM | 40.600 | 27.775 | 5.265, 7, 10, 13, 18.7 | 22.720 | 12.825 | 5.055 |  | 18.8 | 5.0 | 24T25 | T10-150 | 6.05 | 10.8 | 13.0 | 20.3 | 30 TREMIE 2 (JKR) | P100053267, P100053272 | 7, 6
14.1/K2/2 | SGBM28 | Dec 21 2015 1:00PM | Dec 23 2015 11:10PM | 40.599 | 27.775 | 5.25, 6, 9, 13.4, 15 | 22.650 | 12.824 | 5.125 |  | 8.9 | 5.1 | 24T25 | T10-150 | 6.125 | 11.0 | 14.0 | 27.7 | 30 TREMIE 2 (JKR) | Pending, Pending | 7, 7
15.1/K2/1 | SGBM28 | Dec 29 2015 2:30PM | Jan 4 2016 11:20PM | 40.574 | 27.775 | 5.5, 6.5, 8.6, 9.5, 11.5, 12.4, 15, 16.5, 19 | 20.977 | 12.799 | 6.798 |  | 15.5 | 6.8 | 24T25 | T10-150 | 7.798 | 14.5 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054770, P100054773 | 9, 9
15.1/K2/2 | SGBM28 | Nov 25 2015 1:00PM | Nov 30 2015 12:32PM | 40.620 | 27.775 | 8, 9.5, 11.5, 13, 15, 16.5, 18.5, 19.4 | 22.773 | 12.845 | 5.002 |  | 14.4 | 14.4 | 24T25 | T10-150 | 6 | 10.7 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052959, P100052960 | 7, 7
16.1/K2/1 | SGBM28 | Dec 8 2015 8:15AM | Dec 11 2015 4:45PM | 40.600 | 27.775 | 5.5, 8, 11.5, 12.5, 14.3, 15, 17.5, 18.6 | 22.713 | 12.825 | 5.062 |  | 13.9 | 5.1 | 24T25 | T10-150 | 6.063 | 10.8 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053679 | 12
16.1/K2/2 | SGBM28 | Jan 5 2016 8:15AM | Jan 8 2016 6:40PM | 40.510 | 27.775 | 7, 9, 12, 13.5, 15.5, 17, 18.4 | 22.710 | 12.735 | 5.065 |  | 13.5 | 5.1 | 24T25 | T10-150 | 6.065 | 10.8 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054981, P100054980 | 7, 7
17.1/H2/1 | SGBM30 | Mar 3 2016 3:00PM | Mar 4 2016 7:55PM | 40.450 | 25.775 | 11, 14, 16 | 20.645 | 14.675 | 5.130 |  | 12.3 | 12.3 | 24T25 | T10-150 | 6.2 | 11.0 | 15.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047414, P201047417 | 8, 7
17.1/H2/2 | SGBM25 | Mar 8 2016 8:30AM | Mar 10 2016 8:15PM | 40.444 | 25.775 | 10.5, 14, 16.2, 18, 20.3 | 20.725 | 14.669 | 5.050 |  | 11.7 | 5.0 | 24T25 | T10-150 | 6.05 | 10.8 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047754, P201047757 | 7, 7

## 1800
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
12.1/H2/1 | SGBM28 | Dec 14 2015 7:15PM | Dec 17 2015 11:17AM | 40.625 | 27.775 | 5, 7.5, 13, 15, 18.6 | 22.363 | 12.850 | 5.412 |  | 15.1 | 5.4 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.412 | 13.8 | 17.0 | 23.4 | 30 TREMIE 2 (JKR) | P100053921, P100053923 | 9, 8
12.1/H2/2 | SGBM28 | Dec 26 2015 8:30AM | Dec 29 2015 5:05PM | 40.660 | 27.775 | 6.5, 8.5, 12.5, 14.5, 19, 19.125 | 22.152 | 12.885 | 5.623 |  | 13.8 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.623 | 14.3 | 18.0 | 25.8 | 30 TREMIE 2 (JKR) | P100054440, P100054441 | 9, 9
12.1/J2/1 | SGBM28 | Nov 13 2015 1:00PM | Nov 18 2015 5:48PM | 40.595 | 27.775 | 9, 11, 12.5, 16, 17.5, 21, 22.5, 25.4, 25.5 | 16.412 | 12.820 | 11.363 |  | 18.3 | 11.4 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 12.365 | 28.9 | 34.0 | 17.6 | 30 TREMIE 2 (JKR) | P100052371, P100052372, P100052373 | 12, 10, 12
12.1/J2/2 | SGBM28 | Oct 31 2015 1:30PM | Nov 5 2015 9:20PM | 40.660 | 27.775 | 8, 10, 12, 12.5, 17, 18, 23, 25 | 16.430 | 12.885 | 11.345 |  | 17.3 | 11.3 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 12.345 | 28.9 | 32.0 | 10.8 | 30 TREMIE 2 (JKR) | P100051678, P100051679, P100051680, P100051681 | 8, 8, 8, 8
13.1/G2/1 | SGBM25 | Mar 15 2016 4:50PM | Mar 18 2016 3:49PM | 32.010 | 27.775 | 2, 3.5, 4.3, 6.5, 8.5, 9.9 | -10.050 | 4.235 | 37.825 |  | 10.1 | 5.8 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.815 | 96.3 | 18.0 | -81.3 | 30 TREMIE 2 (JKR) | P201048048, P201048049 | 9, 9
13.1/G2/2 | SGBM30 | Dec 2 2015 7:00PM | Dec 5 2015 8:30PM | 40.585 | 27.775 | 5, 9, 17, 19.1 | 22.295 | 12.810 | 5.480 |  | 15.3 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.48 | 13.9 | 17.0 | 21.9 | 30 TREMIE 2 (JKR) | P100053393, P100053397 | 9, 8
13.1/H2/1 | SGBM25 | Feb 20 2016 11:00AM | Feb 27 2016 12:10PM | 40.610 | 27.775 | 7, 10.5, 12.5, 15.6, 17.8, 21, 22.3, 26, 27.5, 30, 31.3 | 12.013 | 12.835 | 15.762 |  | 26.4 | 26.4 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.212 | 40.1 | 49.0 | 11.9 | 30 TREMIE 2 (JKR) | P201047058, P201047059, P201047060, P201047061, P201047062 | 10, 10, 10, 10, 9
13.1/H2/2 | SGBM30 | Jan 16 2016 10:30AM | Jan 20 2016 3:30PM | 40.600 | 27.775 | 7, 10, 14, 21, 24, 30.4 | 10.665 | 12.825 | 17.110 |  | 26.0 | 26.0 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 19.07 | 43.5 | 51.0 | 17.1 | 30 TREMIE 2 (JKR) | P201045364, P201045365, P100055415, P100055417, P201045368 | 9, 12, 12, 9, 9
13.1/J2/1 | SGBM28 | Nov 18 2015 3:00PM | Nov 21 2015 11:20PM | 40.640 | 27.775 | 7, 10, 12.5, 18, 20.5, 26, 29 | 10.794 | 12.865 | 16.981 |  | 26.2 | 26.2 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 17.981 | 43.2 | 50.0 | 15.7 | 30 TREMIE 2 (JKR) | P100052590, P100052594, P100052598, P100052604, P100052605 | 10, 10, 10, 10, 10
13.1/J2/2 | SGBM28 | Nov 6 2015 9:00AM | Nov 13 2015 5:05PM | 40.666 | 27.775 | 6, 8, 11.5, 13, 16.5, 18, 20, 22, 24, 25, 27, 28.5, 31 | 11.000 | 12.891 | 16.775 |  | 26.2 | 16.8 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 17.775 | 42.7 | 46.0 | 7.7 | 30 TREMIE 2 (JKR) | P100052102, P100052103, P100052104, P100052105, P100052107 | 9, 10, 9, 9, 9
14.1/G2/1 | SGBM30 | Dec 8 2015 11:30AM | Dec 10 2015 5:59PM | 40.550 | 27.775 | 7, 10, 13, 17, 18.8 | 22.251 | 12.775 | 5.524 |  | 13.1 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.524 | 14.1 | 18.0 | 28.0 | 30 TREMIE 2 (JKR) | P100053614, P100053615 | 9, 9
14.1/G2/2 | SGBM30 | Nov 27 2015 9:30AM | Nov 30 2015 10:30PM | 40.530 | 27.775 | 6, 10, 12, 16, 17.5 | 22.285 | 12.755 | 5.490 |  | 14.9 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.490 | 14.0 | 18.0 | 28.8 | 30 TREMIE 2 (JKR) | P100053009, P100053013 | 9, 9
14.1/H2/1 | SGBM30 | Nov 9 2015 2:00PM | Nov 14 2015 1:30PM | 40.675 | 27.775 | 5.107, 7, 8, 9, 11, 13, 14, 16, 17, 19, 19.9 | 22.300 | 12.900 | 5.475 |  | 20.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.475 | 13.9 | 18.0 | 29.2 | 30 TREMIE 2 (JKR) | P100052120, P100052121 | 9, 9
14.1/H2/2 | SGBM30 | Nov 18 2015 9:30AM | Nov 20 2015 10:25PM | 40.630 | 27.775 | 6, 8, 10, 14, 16 | 22.220 | 12.855 | 5.555 |  | 15.1 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.555 | 14.1 | 16.0 | 13.2 | 30 TREMIE 2 (JKR) | P100052509, P100052510 | 8, 8
14.1/J2/1 | SGBM30 | Oct 23 2015 3:00PM | Oct 28 2015 6:55PM | 40.640 | 27.775 | 6, 8.5, 9.3, 12.5, 14, 16, 18, 19.4 | 22.288 | 12.865 | 5.487 |  | 14.6 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.5 | 14.0 | 18.0 | 28.9 | 30 TREMIE 2 (JKR) | P100051256, P100051258 | 9, 9
14.1/J2/2 | SGBM30 | Oct 12 2015 3:00PM | Oct 19 2015 4:05PM | 40.700 | 27.775 | 7, 7.6, 9, 9.5, 11, 11.7, 13, 13.5, 15, 15.5, 17.2, 20 | 20.510 | 12.925 | 7.265 |  | 15.2 | 15.2 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 8.3 | 18.5 | 24.0 | 29.8 | 30 TREMIE 2 (JKR) | P100050669, P100050674, P100050675 | 8, 8, 8
15.1/G2/1 | SGBM30 | Nov 21 2015 1:00PM | Nov 25 2015 4:15PM | 40.540 | 27.775 | 5.5, 7.5, 9, 13, 15, 18.4, 18.59 | 22.330 | 12.765 | 5.445 |  | 13.7 | 5.4 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.445 | 13.9 | 18.0 | 29.9 | 30 TREMIE 2 (JKR) | P100052767, P100052770 | 9, 9
15.1/G2/2 | SGBM28 | Oct 27 2015 9:30AM | Oct 31 2015 3:40PM | 40.550 | 27.775 | 6, 7, 9.5, 10.7, 12, 15, 17, 19.9 | 22.238 | 12.775 | 5.537 |  | 15.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.1 | 18.0 | 27.7 | 30 TREMIE 2 (JKR) | P100051447, P100051449 | 9, 9
15.1/H2/1 | SGBM30 | Oct 6 2015 4:30PM | Oct 12 2015 2:55PM | 40.500 | 27.775 | 6.2, 9, 10, 12, 13, 15, 16.2, 18.6, 19.8 | 22.260 | 12.725 | 5.515 |  | 14.9 | 14.9 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 7 | 14.0 | 18.0 | 28.2 | 30 TREMIE 2 (JKR) | P100050278, P100050281 | 9, 9
15.1/H2/2 | SGBM30 | Oct 19 2015 2:20PM | Oct 23 2015 6:00PM | 40.500 | 27.775 | 5.5, 7, 9.3, 10.5, 13, 14.5, 19 | 22.210 | 12.725 | 5.565 |  | 15.1 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.2 | 20.0 | 41.2 | 30 TREMIE 2 (JKR) | P100050910, P100050912 | 10, 10
15.1/J2/1 | SGBM30 | Nov 5 2015 1:30PM | Nov 9 2015 4:00PM | 40.675 | 27.775 | 6, 8, 10, 14, 15.5, 19.8, 20.047 | 20.493 | 12.900 | 7.282 |  | 16.5 | 7.3 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 8.252 | 18.5 | 21.0 | 13.3 | 30 TREMIE 2 (JKR) | P100051892, P100051893 | 10, 11
15.1/J2/2 | SGBM30 | Oct 28 2015 4:00PM | Nov 2 2015 2:30PM | 40.680 | 27.775 | 4, 5.5, 7, 9.5, 11.2, 14, 16, 18.4 | 22.239 | 12.905 | 5.536 |  | 14.9 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.1 | 19.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051530, P100051531 | 9.5, 9.5
16.1/G2/1 | SGBM30 | Nov 14 2015 2:30PM | Nov 18 2015 12:30PM | 40.540 | 27.775 | 7, 9, 11, 15, 17, 19.8 | 22.263 | 12.765 | 5.512 |  | 14.6 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.512 | 14.0 | 19.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052353, P100052354 | 9, 10
16.1/G2/2 | SGBM30 | Nov 2 2015 11:30AM | Nov 5 2015 4:03PM | 40.550 | 27.775 | 7, 9, 10.5, 14, 16.5, 19, 19.6 | 22.243 | 12.775 | 5.532 |  | 14.7 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.1 | 19.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051656, P100051658 | 10, 9
17.1/G2/1 | SGBM30 | Dec 29 2015 11:30AM | Jan 2 2016 3:00PM | 40.488 | 27.775 | 8, 10, 12, 15.5, 19 | 22.249 | 12.713 | 5.526 |  | 12.9 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.526 | 14.1 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054653, P100054657 | 9, 9
17.1/G2/2 | SGBM30 | Jan 6 2016 8:30AM | Jan 13 2016 4:35PM | 40.666 | 27.775 | 9.5, 10.5, 11.5, 12.2, 13.4, 14.3, 15.3, 16, 17.2, 18.8 | 22.276 | 12.891 | 5.499 |  | 11.1 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.499 | 14.0 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055180, P100055183 | 9, 9
18.1/G2/1 | SGBM30 | Dec 12 2015 9:30AM | Dec 15 2015 11:25AM | 40.725 | 27.775 | 7, 14, 16.5, 18 | 22.223 | 12.950 | 5.552 |  | 15.1 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.552 | 14.1 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | 28066396, 28066397 | 9, 9
18.1/G2/2 | SGBM28 | Jan 18 2016 9:30AM | Jan 20 2016 5:35PM | 40.730 | 27.775 | 10.687, 13, 14.5, 18.5, 19.1 | 22.128 | 12.955 | 5.647 |  | 8.3 | 8.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.647 | 14.4 | 19.0 | 32.2 | 30 TREMIE 2 (JKR) | P201045370, P100055418 | 9, 10
18.1/H2/1 | SGBM30 | Feb 3 2016 9:30AM | Feb 5 2016 2:59PM | 40.640 | 27.775 | 11, 13.5, 15, 18.8 | 22.220 | 12.865 | 5.555 |  | 8.9 | 8.9 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.555 | 14.1 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046171, P201046172 | 10, 8
18.1/H2/2 | SGBM30 | Jan 22 2016 3:00PM | Jan 27 2016 5:35PM | 40.640 | 27.775 | 10, 11.5, 13, 16, 18, 19, 19.28 | 22.120 | 12.865 | 5.655 |  | 11.2 | 11.2 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.655 | 14.4 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045557, P201045558 | 9, 9
18.1a/G2/1 | SGBM30 | Dec 22 2015 9:00AM | Dec 23 2015 8:25PM | 40.855 | 34.025 | 14, 17, 18 | 22.016 | 6.830 | 12.009 |  | 8.6 | 8.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.009 | 30.6 | 38.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054237, P100054238, P100054239, P100054241 | 9, 10, 9, 10
18.1a/G2/2 | SGBM30 | Jan 5 2016 9:30AM | Jan 7 2016 4:47PM | 40.750 | 34.025 | 15, 16, 18, 19.2, 19.377 | 21.973 | 6.725 | 12.052 |  | 6.3 | 6.3 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.052 | 30.7 | 37.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054929, P100054933, P100054938, P100054939 | 9, 9, 9, 10
18.1a/H2/1 | SGBM30 | Feb 5 2016 1:00PM | Feb 16 2016 2:50PM | 40.640 | 34.025 | 12, 13, 14, 15, 15.5, 16.5, 17.5, 18, 19, 19.41 | 21.969 | 6.615 | 12.056 |  | 8.6 | 8.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.056 | 30.7 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046385, P201046386, P201046389, P201046393 | 9, 9, 9, 9
18.1a/H2/2 | SGBM30 | Jan 27 2016 2:30PM | Jan 29 2016 4:55PM | 40.690 | 34.025 | 13, 14.5, 16, 19, 19.33 | 21.963 | 6.665 | 12.062 |  | 6.8 | 6.8 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.062 | 30.7 | 36.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045733, P201045735, P201045736, P201045737 | 9, 9, 9, 9
19.1/G2/1 | SGBM30 | Dec 14 2015 6:45PM | Dec 18 2015 3:30PM | 40.974 | 34.025 | 14, 16, 17.5, 21, 22.5, 24.6 | 16.898 | 6.949 | 17.127 |  | 13.4 | 13.4 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.127 | 43.6 | 50.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053997, P100053998, P100054005, P100054011, P100054012 | 10, 10, 10, 10, 10
19.1/G2/2 | SGBM28 | Jan 13 2016 9:00AM | Jan 18 2016 1:20PM | 40.750 | 34.025 | 11, 13.5, 15.5, 16.6, 18, 19, 24, 24.7 | 16.905 | 6.725 | 17.120 |  | 13.4 | 14.9 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.12 | 43.6 | 49.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045279, P201045280, P201045283, P201045285, P100055339 | 10, 10, 9, 10, 10
19.1/H2/1 | SGBM25 | Feb 17 2016 9:00AM | Feb 20 2016 12:59PM | 40.740 | 34.025 | 16, 16.6, 17.5, 19, 21, 24.6 | 16.915 | 6.715 | 17.110 |  | 7.6 | 9.6 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 17.11 | 43.5 | 53.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046647, P201046648, P201046649, P201046650, P201046652, P201046653, P201046657 | 8, 8, 9, 9, 8, 8, 3
19.1/H2/2 | SGBM30 | Jan 29 2016 11:00AM | Feb 3 2016 6:23PM | 40.700 | 34.025 | 12, 13.2, 14, 16.5, 18, 20, 21, 24.6, 24.7 | 16.780 | 6.675 | 17.245 |  | 14.0 | 14.0 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.245 | 43.9 | 50.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045993, P201045995, P201045996, P201046005, P201046006, P201046013 | 9, 9, 9, 8, 8, 7
21.1/J2/1 | SGBM10 | Feb 3 2016 8:40AM | Feb 16 2016 6:05PM | 40.820 | 34.025 | 10, 11.3, 13.2, 14.2, 17, 18, 20, 21, 22 | 19.515 | 6.795 | 14.510 |  | 13.5 | 13.5 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 16.51 | 36.9 | 44.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045211, P201045845, P201045501, P201045503, P201045504 | 4.5, 9, 9, 12, 10
21.1/J2/2 | SGBM28 | Jan 22 2016 8:30AM | Jan 27 2016 9:06PM | 40.875 | 34.025 | 11, 12, 15, 16, 18, 18.5, 20.5, 21.8, 22.04 | 19.448 | 6.850 | 14.577 |  | 11.7 | 11.7 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 15.577 | 37.1 | 44.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045580, P201045583, P201045587, P201045590 | 12, 10, 10, 12

## 2000
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
18.1a/J2/1 | SGBM30 | Feb 16 2016 1:00PM | Feb 18 2016 5:35PM | 40.644 | 33.725 | 12, 14, 17, 23, 26 | 14.779 | 6.919 | 18.946 |  | 17.2 | 17.2 | 34T25 | T10-150 | 12 | 59.5 | 66.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046532, P201046534, P201046536, P201046538, P201046544, P201046545, P201046548 | 8, 9, 9, 12, 12, 8, 8
18.1a/J2/2 | SGBM30 | Feb 20 2016 5:30PM | Feb 23 2016 5:00PM | 40.490 | 33.725 | 13, 16, 24 | 14.616 | 6.765 | 19.109 |  | 14.7 | 14.7 | 34T25 | T10-150 | 12 | 60.0 | 69.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046828, P201046829, P201046831, P201046834, P201046839, P201046841 | 12, 9, 12, 12, 12, 12
19.1/J2/1 | SGBM30 | Feb 25 2016 2:30PM | Feb 29 2016 11:05AM | 40.570 | 33.725 | 11, 13, 16, 20.6 | 20.375 | 6.845 | 13.350 |  | 11.6 | 11.6 | 34T25 | T10-150 | 12 | 41.9 | 50.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047100, P201047101, P201047102, P201047104, P201047103 | 12, 8, 10, 9, 11
19.1/J2/2 | SGBM30 | Mar 1 2016 8:00AM | Mar 3 2016 4:35PM | 40.770 | 33.725 | 11, 15.5, 18.5, 20.4, 20.697 | 20.603 | 7.045 | 13.122 |  | 12.0 | 12.0 | 34T25 | T10-150 | 14.2 | 41.2 | 48.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047350, P201047352, P201047354, P201047356 | 12, 12, 12, 12
20.1/J2/1 | SGBM30 | Feb 23 2016 2:00PM | Feb 26 2016 10:40AM | 40.825 | 33.725 | 13, 15, 17.5, 18.2 | 23.258 | 7.100 | 10.467 |  | 7.3 | 7.3 | 34T25 | T10-150 | 11.467 | 32.9 | 38.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046988, P201046989, P201046990, P201046992 | 12, 9, 9, 8
20.1/J2/2 | SGBM30 | Feb 18 2016 3:00PM | Feb 22 2016 2:15PM | 40.825 | 33.725 | 11, 12, 14, 17, 18.2 | 23.237 | 7.100 | 10.488 |  | 8.2 | 8.2 | 34T25 | T10-150 | 11.5 | 33.0 | 40.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046723, Pending, P201046727, P201046732 | 9, 10, 12, 9.5

## 2200
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
20.1/G2/1 | SGBM30 | Jan 7 2016 2:00PM | Jan 11 2016 2:20PM | 40.945 | 33.325 | 11.21, 13, 15, 16.5, 19, 21, 22 | 18.370 | 7.620 | 14.955 |  | 17.3 | 12.0 | 40T25 | T10-150 | 12 | 56.9 | 68.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055085, P100055088, P100055092, P100055093, P100055094, P100055099, P100055102 | 12, 10, 9, 10, 10, 10, 7
20.1/G2/2 | SGBM30 | Dec 26 2015 8:15AM | Dec 29 2015 3:00PM | 41.080 | 33.325 | 12, 16, 18, 23.1 | 18.364 | 7.755 | 14.961 |  | 12.5 | 12.5 | 40T25 | T10-150 | 12 | 56.9 | 70.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054427, P100054428, P100054429, P100054431, P100054433, P100054435, P100054436 | 10, 10, 10, 9, 10, 10, 11
20.1/G2/3 | SGBM30 | Dec 18 2015 9:00AM | Dec 22 2015 11:10AM | 40.995 | 33.325 | 13, 14, 18, 20 | 18.368 | 7.670 | 14.957 |  | 10.7 | 10.7 | 40T25 | T10-150 | 12 | 56.9 | 68.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054143, P100054144, P100054146, P100054148, P100054149, P100054150, P100054151 | 10, 9, 12, 10, 9, 9, 9
20.1/H2/1 | SGBM30 | Jan 20 2016 11:00AM | Jan 26 2016 1:30PM | 40.920 | 33.325 | 11, 13.5, 17, 19, 23.4 | 18.171 | 7.595 | 15.154 |  | 14.1 | 14.1 | 40T25 | T10-150 | 12 | 57.6 | 65.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045489, P201045490, P201045491, P201045492, P201045496, P201045499, P201045500 | 9, 9, 9, 9, 12, 9, 8
20.1/H2/2 | SGBM30 | Jan 13 2016 2:30PM | Jan 16 2016 3:17PM | 40.945 | 33.325 | 11.108, 14, 16, 19.5, 22.5, 23.4 | 18.349 | 7.620 | 14.976 |  | 17.6 | 12.4 | 40T25 | T10-150 | 12 | 56.9 | 65.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045243, P201045244, P201045246, P201045247, P201045250, P201045253 | 12, 12, 10, 12, 10, 9
20.1/H2/3 | SGBM30 | Dec 31 2015 1:00PM | Jan 6 2016 9:40PM | 41.000 | 33.325 | 14, 15.5, 17.5, 18.8, 21, 22.5, 23.2 | 18.442 | 7.675 | 14.883 |  | 10.5 | 10.5 | 40T25 | T10-150 | 12 | 56.6 | 68.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054871, P100054873, P100054875, P100054881, P100054884, P100054890, P100054892 | 9, 12, 10, 9, 10, 9, 9