## 750
Summary List for 1891651800-Parcel F
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
V/27-1 | SGBM08 | Sep 11 2015 4:00PM | Sep 14 2015 6:45PM | 49.817 | 48.775 | 8, 11 | 31.246 | 1.042 | 17.529 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.7 | 9.0 | -7.7 | G35T2 | 1 | 9
W/27-1 | SGBM16 | Aug 11 2015 8:30AM | Aug 13 2015 4:30PM | 49.655 | 49.075 | 9 | 32.385 | 0.580 | 16.690 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.4 | 8.0 | -7.4 | G35T2 | 1 | 8
X1/Y2-1 | SGBM09 | Oct 21 2015 8:00AM | Oct 21 2015 5:33PM | 55.760 | 55.075 |  | 29.878 | 0.685 | 25.197 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 5, 4
X1/Y3-1 | SGBM21 | Dec 3 2015 8:00AM | Dec 10 2015 8:10PM | 55.766 | 55.075 | 9, 16 | 30.866 | 0.691 | 24.209 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 8, 2, 1
X1/Y4-1 | SGBM09 | Oct 20 2015 10:00AM | Oct 20 2015 4:26PM | 55.690 | 55.075 |  | 31.803 | 0.615 | 23.272 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
X1/Y5-1 | SGBM09 | Oct 17 2015 9:00AM | Oct 17 2015 3:41PM | 55.677 | 55.075 |  | 31.988 | 0.602 | 23.087 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 16.0 | 56.8 | G45T2 | 1, 2, 3 | 7, 6, 3
X1/Y6-1 | SGBM09 | Oct 12 2015 8:40AM | Oct 12 2015 7:38PM | 55.731 | 55.075 |  | 31.965 | 0.656 | 23.110 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 13.0 | -100.0 | G45T2 | 1, 2 | 6, 7
L/33-1 | SGBM20 | Sep 30 2015 5:00PM | Oct 1 2015 2:38PM | 52.100 | 50.225 | 9 | 29.774 | 1.025 | 20.451 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.0 | 16.0 | 7.0 | G45T2 | 1, 2 | 8, 8
K/33-1 | SGBM20 | Sep 21 2015 6:00PM | Sep 22 2015 12:15PM | 51.957 | 50.225 | 9, 18 | 30.724 | 0.582 | 19.501 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 15.0 | -100.0 | G45T2 | c480009015, c480009018, c480009019 | 2, 11, 2
H/59-1 | SGBM01 | Oct 21 2015 3:15PM | Oct 30 2015 7:00PM | 51.950 | 50.575 | 8, 27 | 9.848 | 1.375 | 40.727 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 18.0 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 8, 7
H/59-2 | SGBM08 | Oct 31 2015 5:35PM | Nov 3 2015 8:50PM | 51.923 | 50.575 | 9, 16 | 10.223 | 1.348 | 40.352 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.8 | 22.0 | -100.0 | G45T2 | 1, 2 | 10, 12
H/59-3 | SGBM08 | Nov 2 2015 9:35AM | Nov 6 2015 10:25PM | 51.990 | 50.575 | 9, 15, 28 | 10.510 | 1.415 | 40.065 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.7 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
H/59-4 | SGBM01 | Oct 26 2015 10:55AM | Oct 28 2015 9:33PM | 51.910 | 50.575 | 8, 18 | 10.388 | 1.335 | 40.187 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.8 | 24.0 | -17.8 | G45T2 | 1, 2 | 12, 12
H/59-5 | SGBM01 | Oct 26 2015 10:25AM | Oct 31 2015 1:31PM | 51.940 | 50.575 | 8, 15, 23, 25, 30 | 9.830 | 1.365 | 40.745 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 18.0 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
H/59-6 | SGBM08 | Nov 2 2015 8:50AM | Nov 7 2015 6:20PM | 52.000 | 50.575 | 9, 27.5, 35 | 10.291 | 1.425 | 40.284 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.8 | 18.0 | -17.8 | G45T2 | PJ 1376, PJ 1377, PJ 1378 | 6, 6, 6
H/59-7 | SGBM08 | Nov 2 2015 8:26AM | Nov 5 2015 12:35PM | 51.930 | 50.575 | 9, 23.6 | 10.311 | -50.575 | 40.264 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.8 | 22.5 | 26.5 | G45T2 | C480011361, C480011364 | 11.5, 11
H/59-8 | SGBM17 | Oct 26 2015 11:35AM | Oct 28 2015 10:00PM | 51.953 | 50.575 | 9, 19.2 | 10.132 | 1.378 | 40.443 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.9 | 20.0 | -100.0 | G45T2 | 1, 2 | 11, 9
Y/26a-1 | SGBM22 | Sep 22 2015 4:40PM | Sep 23 2015 1:53AM | 49.896 | 46.525 |  | 26.834 | 3.371 | 19.691 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 14.5 | -100.0 | G45T2 | 1, 2 | 11.5, 3
Y/26a-2 | SGBM22 | Sep 28 2015 4:00PM | Sep 29 2015 11:27PM | 49.794 | 46.525 |  | 26.748 | 3.269 | 19.777 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 12.0 | -100.0 | G45T2 | 1, 2 | 9, 3
Y/26a-3 | SGBM16 | Sep 18 2015 8:00AM | Sep 18 2015 8:00PM | 49.867 | 46.525 |  | 26.783 | 3.342 | 19.742 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 12.0 | -100.0 | G45T2 | 1, 2 | 11, 1
Y/26a-4 | SGBM22 | Sep 23 2015 11:00AM | Sep 23 2015 7:47PM | 49.931 | 46.525 |  | 27.089 | 3.406 | 19.436 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/26a-5 | SGBM22 | Sep 24 2015 12:45PM | Sep 25 2015 5:40PM | 49.819 | 46.525 |  | 27.241 | 3.294 | 19.284 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/26a-6 | SGBM22 | Sep 28 2015 4:30PM | Sep 29 2015 12:59PM | 49.791 | 46.525 |  | 27.116 | 3.266 | 19.409 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/26a-7 | SGBM22 | Sep 17 2015 8:00AM | Sep 17 2015 8:55PM | 49.798 | 46.525 |  | 27.244 | 3.273 | 19.281 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/26a-8 | SGBM22 | Sep 21 2015 8:45AM | Sep 21 2015 6:00PM | 49.745 | 46.525 |  | 27.135 | 3.220 | 19.390 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 15.0 | -100.0 | G45T2 | 1, 2 | 4, 11
Y/27a-1 | SGBM22 | Sep 25 2015 11:00AM | Sep 26 2015 2:05PM | 49.972 | 46.525 |  | 27.349 | 3.447 | 19.176 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 11.0 | -100.0 | G45T2 | 1 | 11
Y/27a-2 | SGBM22 | Sep 21 2015 3:00PM | Sep 22 2015 5:52PM | 49.897 | 46.525 |  | 27.147 | 3.372 | 19.378 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 17.0 | -100.0 | G45T2 | 1 | 17
Y/27a-3 | SGBM22 | Sep 30 2015 10:10AM | Sep 30 2015 11:07PM | 49.926 | 46.525 |  | 27.161 | 3.401 | 19.364 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 12.0 | -100.0 | G45T2 | 1, 2 | 9, 3
Y/27a-4 | SGBM16 | Sep 18 2015 8:00AM | Sep 18 2015 7:17PM | 49.871 | 46.525 |  | 27.247 | 3.346 | 19.278 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 12.0 | -100.0 | G45T2 | 1 | 12
Y/27a-5 | SGBM22 | Oct 1 2015 8:20AM | Oct 2 2015 7:05PM | 49.915 | 46.525 |  | 27.075 | 3.390 | 19.450 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 11.0 | -100.0 | G45T2 | 1 | 11
Y/27a-6 | SGBM22 | Sep 25 2015 1:00PM | Sep 28 2015 7:16PM | 49.812 | 46.525 |  | 27.135 | 3.287 | 19.390 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 12.0 | -100.0 | G45T2 | 1, 2 | 10, 2
Y/27a-7 | SGBM22 | Sep 29 2015 8:20AM | Sep 30 2015 1:21PM | 49.814 | 46.525 |  | 26.760 | 3.289 | 19.765 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 10.0 | -100.0 | G45T2 | 1, 2 | 4, 6
Y/27a-8 | SGBM16 | Sep 17 2015 8:00AM | Sep 17 2015 9:13PM | 49.801 | 46.525 |  | 27.124 | 3.276 | 19.401 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 12.0 | -100.0 | G45T2 | 1 | 12
G/31-2 | SGBM20 | Nov 5 2015 12:08PM | Nov 5 2015 10:28PM | 52.162 | 48.175 | 9 | 30.663 | -48.175 | 17.512 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.7 | 12.0 | -7.7 | G45T2 | Pending, 2 | 6, 6
G/31-3 | SGBM22 | Nov 7 2015 11:05AM | Nov 7 2015 11:05PM | 52.100 | 48.175 | 9 | 30.490 | 3.925 | 17.685 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.8 | 11.0 | -7.8 | G45T2 | 1, 2 | 6, 5
G/31-4 | SGBM20 | Nov 12 2015 5:05PM | Nov 11 2015 11:50PM | 52.241 | 48.175 | 9 | 30.226 | 4.066 | 17.949 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.9 | 11.0 | -100.0 | G45T2 | 1, 2 | 5.5, 5.5
G/31-5 | SGBM20 | Nov 11 2015 8:00AM | Nov 11 2015 8:45PM | 52.185 | 48.175 | 9 | 30.570 | -48.175 | 17.605 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.8 | 11.0 | -7.8 | G45T2 | 1, 2 | 7, 4
G/31-6 | SGBM20 | Nov 3 2015 9:40AM | Nov 3 2015 8:19PM | 52.148 | 48.175 | 9 | 30.563 | -48.175 | 17.612 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.8 | 12.0 | -100.0 | G45T2 | 1, 2 | 5, 7
G/31-7 | SGBM20 | Nov 6 2015 2:30PM | Nov 6 2015 7:00PM | 52.134 | 48.175 | 9 | 30.320 | -48.175 | 17.855 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.9 | 12.0 | -7.9 | G45T2 | 1, 2, 3 | 5, 5, 2
G/31-8 | SGBM20 | Nov 15 2015 10:10AM | Nov 16 2015 7:12PM | 52.128 | 48.175 | 9 | 30.248 | 3.953 | 17.927 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.9 | 11.0 | 38.9 | G45T2 | 1, 2 | 7, 4
G/31-9 | SGBM20 | Nov 4 2015 11:17AM | Nov 4 2015 11:08PM | 52.220 | 48.175 | 9 | 30.245 | -48.175 | 17.930 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.9 | 11.0 | -7.9 | G45T2 | 1, 2 | 7, 4
G/33-1 | SGBM20 | Nov 2 2015 5:58PM | Nov 2 2015 10:04PM | 52.211 | 50.775 | 9 | 37.563 | -50.775 | 13.212 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.8 | 9.0 | 54.2 | G35T2 | 1, 2 | 8, 1
G/33-2 | SGBM20 | Nov 6 2015 8:30AM | Nov 6 2015 11:37AM | 52.273 | 50.775 | 9 | 37.832 | -50.775 | 12.943 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.7 | 8.0 | -100.0 | G35T2 | 1 | 8
G/33-3 | SGBM22 | Nov 7 2015 6:30PM | Nov 7 2015 11:55PM | 52.205 | 50.775 | 9 | 37.985 | 1.430 | 12.790 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.7 | 10.0 | -100.0 | G35T2 | 1, 2 | 6, 4
G/33-4 | SGBM20 | Oct 31 2015 3:55PM | Oct 31 2015 7:56PM | 52.244 | 50.775 | 9 | 37.763 | -50.775 | 13.012 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.7 | 10.0 | -100.0 | G45T2 | 1, 2 | 7, 3
Fa/31-1 | SGBM20 | Nov 12 2015 7:20PM | Nov 14 2015 9:12PM | 52.235 | 50.775 | 9 | 29.560 | -50.775 | 21.215 |  | 0.0 | 0.0 | 11T16 | T12-225 | 12 | 9.4 | 8.0 | -100.0 | G35T2 | 1 | 8
Fa/32-1 | SGBM20 | Nov 14 2015 9:00AM | Nov 14 2015 6:55PM | 52.222 | 50.775 | 9 | 37.700 | -50.775 | 13.075 |  | 0.0 | 0.0 | 11T16 | T12-225 | 12 | 5.8 | 8.0 | -100.0 | G45T2 | 1 | 8
Fa/33-1 | SGBM20 | Nov 15 2015 9:30AM | Nov 16 2015 12:19PM | 52.348 | 50.775 | 9 | 38.084 | 1.573 | 12.691 |  | 0.0 | 0.0 | 11T16 | T12-225 | 12 | 5.6 | 8.0 | -100.0 | G45T2 | 1 | 8
X1/Y1-1 | SGBM18 | Dec 8 2015 4:00PM | Dec 14 2015 7:36PM | 55.742 | 54.475 | 9, 14, 16 | 24.898 | 1.267 | 29.577 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.1 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
X1/Y7-1 | SGBM09 | Oct 13 2015 12:00PM | Oct 13 2015 10:10PM | 55.709 | 55.075 |  | 28.882 | 0.634 | 26.193 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.6 | 13.0 | -11.6 | G45T2 | 1, 2 | 7, 6
X2/Y1-1 | SGBM18 | Nov 25 2015 9:00AM | Nov 25 2015 8:49PM | 55.675 | 54.375 |  | 23.363 | 1.300 | 31.012 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.7 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 5, 6
X2/Y2-1 | SGBM09 | Oct 15 2015 9:00AM | Oct 15 2015 5:11PM | 55.831 | 55.075 |  | 31.021 | 0.756 | 24.054 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 14.0 | -10.6 | G45T2 | 1, 2 | 7, 7
X2/Y3-1 | SGBM09 | Oct 16 2015 9:00AM | Oct 16 2015 3:56PM | 55.851 | 55.075 |  | 31.911 | 0.776 | 23.164 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
X2/Y4-1 | SGBM09 | Oct 7 2015 12:00PM | Oct 7 2015 9:03PM | 55.701 | 55.075 |  | 31.776 | 0.626 | 23.299 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 14.0 | -10.3 | G35T2 | 1, 2 | 7, 7
X2/Y5-1 | SGBM09 | Oct 16 2015 2:00PM | Oct 16 2015 8:12PM | 55.633 | 55.075 |  | 32.942 | 0.558 | 22.133 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
X2/Y6-1 | SGBM09 | Oct 3 2015 6:00PM | Oct 3 2015 11:30PM | 55.618 | 55.075 |  | 47.418 | 0.543 | 7.657 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 3.4 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 9, 5
X2/Y7-1 | SGBM20 | Nov 6 2015 7:30PM | Nov 7 2015 2:41PM | 55.768 | 55.075 | 9 | 30.982 | 0.693 | 24.093 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
X3/Y2-1 | SGBM21 | Nov 12 2015 7:00PM | Nov 13 2015 6:57PM | 55.772 | 55.075 | 9, 20, 28.5 | 25.146 | 0.697 | 29.929 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.2 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
X3/Y3-1 | SGBM21 | Nov 7 2015 7:30PM | Nov 11 2015 3:40PM | 55.908 | 55.075 | 9 | 26.786 | -55.075 | 28.289 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 15.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 7, 2
X3/Y6-1 | SGBM21 | Nov 2 2015 5:46PM | Nov 3 2015 12:05PM | 55.707 | 55.075 | 9, 24 | 30.842 | 0.632 | 24.233 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
X3/Y7-1 | SGBM21 | Nov 4 2015 11:15AM | Nov 4 2015 9:30PM | 55.712 | 55.075 | 9, 14 | 31.966 | 0.637 | 23.109 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
X4/Y2-1 | SGBM21 | Nov 5 2015 12:30PM | Nov 6 2015 9:00PM | 55.702 | 55.075 | 9, 13.5 | 24.925 | 0.627 | 30.150 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.3 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 9, 2
X4/Y3-1 | SGBM21 | Nov 4 2015 5:52PM | Nov 5 2015 12:52PM | 55.909 | 55.075 | 9, 19.3 | 27.022 | 0.834 | 28.053 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
X4/Y7-1 | SGBM21 | Nov 5 2015 7:00PM | Nov 6 2015 9:11PM | 55.704 | 55.075 | 9 | 32.815 | -55.075 | 22.260 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
X5/Y6-1 | SGBM21 | Oct 31 2015 2:45PM | Nov 2 2015 12:10PM | 55.720 | 55.075 | 9, 20.9 | 31.700 | -55.075 | 23.375 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
X5/Y7-1 | SGBM21 | Nov 3 2015 7:12PM | Nov 4 2015 12:40PM | 55.739 | 55.075 | 9, 15.4 | 32.570 | -55.075 | 22.505 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
X6/Y7-1 | SGBM03 | Nov 7 2015 7:52PM | Nov 12 2015 3:07PM | 55.639 | 55.075 | 9 | 32.961 | 0.564 | 22.114 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 15.0 | -100.0 | G45T2 | 1, 2 | 5, 10
X6a/Y4-1 | SGBM05 | Nov 20 2015 7:00PM | Nov 21 2015 2:46PM | 55.662 | 51.075 | 9 | 25.702 | 4.587 | 25.373 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 14.0 | 24.9 | G45T2 | 1, 2 | 7, 7
X6a/Y4-2 | SGBM21 | Nov 9 2015 5:30PM | Nov 12 2015 8:28PM | 55.722 | 51.075 | 9 | 25.869 | 4.647 | 25.206 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 2, 7
X6a/Y4-3 | SGBM21 | Oct 30 2015 5:15PM | Oct 31 2015 12:00PM | 55.857 | 51.075 | 9, 21 | 25.745 | -51.075 | 25.330 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
X6a/Y4-4 | SGBM21 | Oct 24 2015 5:40PM | Oct 26 2015 2:54PM | 55.839 | 51.075 | 9 | 26.002 | 4.764 | 25.073 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -11.1 | G45T2 | 1, 2 | 7.5, 7.5
X6a/Y4-5 | SGBM21 | Nov 18 2015 10:00AM | Nov 18 2015 4:55PM | 55.787 | 51.075 |  | 25.902 | 4.712 | 25.173 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 14.0 | -11.1 | G45T2 | 1, 2 | 7, 7
X6a/Y4-6 | SGBM21 | Nov 2 2015 10:04AM | Nov 2 2015 9:11PM | 55.864 | 51.075 | 9 | 25.906 | -51.075 | 25.169 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
X6a/Y4-7 | SGBM21 | Oct 28 2015 5:45PM | Oct 28 2015 9:57PM | 55.797 | 51.075 | 9 | 26.022 | 4.722 | 25.053 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
X6a/Y4-8 | SGBM09 | Oct 10 2015 9:00AM | Oct 10 2015 5:10PM | 55.824 | 51.075 |  | 25.799 | 4.749 | 25.276 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 14.0 | -11.2 | G45T2 | 1, 2 | 7, 7
X7/Y7-1 | SGBM21 | Nov 11 2015 6:50PM | Nov 14 2015 8:49PM | 55.537 | 55.075 | 9 | 32.777 | 0.462 | 22.298 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
X9/Y2-1 | SGBM21 | Nov 17 2015 8:00AM | Nov 17 2015 8:30PM | 55.631 | 55.075 | 9 | 24.939 | 0.556 | 30.136 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.3 | 16.0 | -13.3 | G45T2 | 1, 2 | 8, 8
X10/Y7-1 | SGBM03 | Nov 11 2015 9:37AM | Nov 13 2015 10:54PM | 55.700 | 55.075 | 9 | 36.144 | 0.625 | 18.931 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
ABa/21-1 | SGBM22 | Oct 20 2015 11:10AM | Oct 20 2015 7:32PM | 49.732 | 48.475 |  | 28.938 | 1.257 | 19.537 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 12.0 | 39.0 | G45T2 | 1, 2 | 6, 6
ABa/22-1 | SGBM03 | Oct 19 2015 3:20PM | Oct 20 2015 2:30AM | 49.721 | 48.475 |  | 28.753 | 1.246 | 19.722 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
ABa/23-1 | SGBM03 | Oct 19 2015 6:00PM | Oct 20 2015 1:00AM | 49.683 | 48.475 |  | 28.846 | 1.208 | 19.629 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
ABa/24-1 | SGBM22 | Oct 19 2015 6:00PM | Oct 19 2015 11:39PM | 49.772 | 48.475 |  | 34.924 | 1.297 | 13.551 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.0 | 9.0 | -100.0 | G45T2 | 1, 2 | 4.5, 4.5
AB/24a-1 | SGBM22 | Oct 20 2015 5:30PM | Oct 20 2015 11:18PM | 49.630 | 48.475 |  | 34.280 | 1.155 | 14.195 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.3 | 10.0 | -100.0 | G35T2 | 1, 2 | 5, 5
AB/25-1 | SGBM22 | Oct 21 2015 12:30PM | Oct 21 2015 7:09PM | 49.891 | 48.475 |  | 27.835 | 1.416 | 20.640 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.1 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
AB/31-1 | SGBM22 | Oct 23 2015 6:00PM | Oct 24 2015 2:52AM | 50.144 | 48.475 |  | 27.567 | 1.669 | 20.908 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.2 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
AA/22-1 | SGBM20 | Oct 9 2015 2:00PM | Oct 10 2015 10:40PM | 49.816 | 49.075 |  | 29.635 | 0.741 | 19.440 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 10.0 | -8.6 | G35T2 | 1 | 10
AA/23-1 | SGBM19 | Oct 10 2015 8:00AM | Oct 10 2015 6:26PM | 49.898 | 49.075 |  | 29.730 | 0.823 | 19.345 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 10.0 | -100.0 | G35T2 | 1, 2 | 7, 3
AA/24-1 | SGBM22 | Oct 12 2015 8:00AM | Oct 12 2015 8:12PM | 49.686 | 49.075 |  | 29.233 | 0.611 | 19.842 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.8 | 13.0 | -100.0 | G35T2 | 1, 2 | 6, 7
AA/26-1 | SGBM22 | Oct 13 2015 8:00AM | Oct 13 2015 8:08PM | 49.789 | 49.075 |  | 34.608 | 0.714 | 14.467 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.4 | 9.0 | -100.0 | G35T2 | 1, 2 | 7, 2
AA/27-1 | SGBM20 | Oct 9 2015 7:15PM | Oct 10 2015 5:45PM | 49.815 | 49.075 |  | 34.134 | 0.740 | 14.941 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.6 | 10.0 | 51.5 | G35T2 | 1, 2 | 7, 3
AA/28-1 | SGBM19 | Oct 9 2015 8:00AM | Oct 10 2015 12:29AM | 50.036 | 49.075 |  | 34.449 | 0.961 | 14.626 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.5 | 10.0 | -100.0 | G35T2 | 1 | 10
AA/29-1 | SGBM19 | Oct 9 2015 9:00PM | Oct 10 2015 12:39AM | 49.957 | 49.075 |  | 34.526 | 0.882 | 14.549 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.4 | 10.0 | -100.0 | G35T2 | 1 | 10
AA/31-1 | SGBM22 | Oct 13 2015 10:10AM | Oct 13 2015 5:16PM | 49.812 | 47.825 |  | 27.849 | 1.987 | 19.976 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.8 | 13.0 | -100.0 | G35T2 | 1, 2 | 6, 7
AA/31-2 | SGBM03 | Oct 19 2015 11:00AM | Oct 19 2015 4:47PM | 50.065 | 47.825 |  | 27.287 | 2.240 | 20.538 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.1 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
Za/20-1 | SGBM22 | Oct 20 2015 2:20PM | Oct 20 2015 6:59PM | 49.786 | 48.475 |  | 29.416 | 1.311 | 19.059 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
V/20-1 | SGBM03 | Oct 15 2015 8:10AM | Oct 15 2015 7:48PM | 49.831 | 48.475 |  | 26.244 | 1.356 | 22.231 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 10, 2
T/22-1 | SGBM22 | Oct 7 2015 8:00AM | Oct 7 2015 6:50PM | 49.837 | 49.075 |  | 29.954 | 0.762 | 19.121 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 10.0 | -100.0 | G45T2 | 1, 2 | 3, 7
AF/31a-1 | SGBM22 | Nov 18 2015 5:20PM | Nov 19 2015 2:22AM | 49.351 | 48.475 |  | 30.222 | 0.876 | 18.253 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
AF/32a-1 | SGBM22 | Nov 23 2015 5:30PM | Nov 23 2015 9:25PM | 49.462 | 48.475 | 9 | 30.119 | 0.987 | 18.356 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 11.0 | -8.1 | G45T2 | 1, 2 | 5.5, 5.5
AF/35-1 | SGBM22 | Nov 24 2015 8:00AM | Nov 24 2015 2:30PM | 49.465 | 48.475 |  | 30.158 | 0.990 | 18.317 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 11.0 | -8.1 | G45T2 | 1, 2 | 6, 5
AF/36-1 | SGBM22 | Nov 23 2015 10:10AM | Nov 23 2015 11:00PM | 49.470 | 48.475 | 9 | 24.047 | 0.995 | 24.428 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.8 | 15.0 | -10.8 | G45T2 | 1, 2 | 7, 8
AF/37-1 | SGBM19 | Nov 25 2015 1:42PM | Nov 25 2015 11:59PM | 49.317 | 48.475 | 9 | 23.475 | 0.842 | 25.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.0 | 17.0 | -100.0 | G45T2 | 2157, 2162, 2169 | 7, 7, 3
AF/38-1 | SGBM22 | Nov 25 2015 2:43PM | Nov 25 2015 11:08PM | 49.364 | 48.475 | 9 | 22.436 | 0.889 | 26.039 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 14.0 | -11.5 | G45T2 | 2152, 2153 | 7, 7
AF/39-1 | SGBM22 | Nov 24 2015 7:49PM | Nov 25 2015 10:23PM | 49.406 | 48.475 | 9, 13.4 | 26.475 | 0.931 | 22.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.7 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
AF/40-1 | SGBM22 | Nov 26 2015 9:20AM | Nov 27 2015 12:08AM | 49.492 | 48.475 |  | 25.837 | 1.017 | 22.638 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.0 | 13.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 5, 1
AF/41-1 | SGBM22 | Nov 26 2015 11:35AM | Nov 26 2015 10:19PM | 49.561 | 48.475 |  | 25.548 | 1.086 | 22.927 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.1 | 12.0 | 18.5 | G35T2 | 1, 2 | 6, 6
AF/42-1 | SGBM22 | Nov 28 2015 8:30AM | Nov 28 2015 4:57PM | 49.776 | 48.475 | 9 | 25.153 | 1.301 | 23.322 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
AF/43-1 | SGBM22 | Nov 29 2015 10:05AM | Nov 30 2015 9:13PM | 49.663 | 48.475 | 9, 16.2 | 25.412 | 1.188 | 23.063 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
AF/44-1 | SGBM22 | Nov 30 2015 10:06AM | Nov 30 2015 7:24PM | 49.834 | 48.475 | 9 | 25.466 | 1.359 | 23.009 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
AF/45-1 | SGBM22 | Dec 3 2015 8:30AM | Dec 3 2015 4:50PM | 49.263 | 48.475 | 9 | 24.224 | 0.788 | 24.251 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
AE/35a-1 | SGBM22 | Nov 17 2015 1:00PM | Nov 18 2015 1:51AM | 49.632 | 48.775 |  | 24.684 | 0.857 | 24.091 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 15.0 | 40.9 | G45T2 | 1, 2 | 8, 7
AE/37-1 | SGBM19 | Nov 17 2015 3:20PM | Nov 18 2015 1:02AM | 49.576 | 48.775 |  | 23.690 | 0.801 | 25.085 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -11.1 | G45T2 | 1, 2 | 8, 7
AE/38-1 | SGBM19 | Nov 17 2015 4:10PM | Nov 18 2015 3:40AM | 49.520 | 48.775 |  | 22.774 | 0.745 | 26.001 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 15.0 | -11.5 | G45T2 | 1, 2 | 8, 7
AEa/38-1 | SGBM19 | Nov 26 2015 11:10AM | Nov 27 2015 3:13AM | 49.539 | 49.075 | 9 | 26.923 | 0.464 | 22.152 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 4, 6, 5
AE/39-1 | SGBM22 | Nov 20 2015 6:00PM | Nov 21 2015 2:50PM | 49.502 | 48.775 |  | 22.582 | 0.727 | 26.193 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.6 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
AEa/39-1 | SGBM19 | Nov 26 2015 9:25AM | Nov 27 2015 1:49AM | 49.477 | 49.075 | 9 | 27.038 | 0.402 | 22.037 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.7 | 13.0 | -100.0 | G35T2 | 1, 2, 3 | 5, 6, 2
AE/40-1 | SGBM22 | Nov 28 2015 3:00PM | Nov 28 2015 11:03PM | 49.532 | 48.475 | 9 | 20.907 | 1.057 | 27.568 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 15.0 | -100.0 | G45T2 | PJ 2328, PJ 2330 | 7, 8
AEa/40-1 | SGBM22 | Nov 27 2015 11:15AM | Nov 28 2015 12:44AM | 49.411 | 49.075 | 9 | 26.889 | 0.336 | 22.186 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
AE/41-1 | SGBM22 | Dec 1 2015 4:00PM | Dec 2 2015 11:01PM | 49.317 | 48.475 |  | 20.972 | 0.842 | 27.503 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
AEa/41-1 | SGBM22 | Nov 27 2015 2:20PM | Nov 28 2015 12:44AM | 49.465 | 49.075 |  | 26.589 | 0.390 | 22.486 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 13.0 | -9.9 | G35T2 | 1, 2 | 7, 6
AE/42-1 | SGBM22 | Dec 2 2015 8:30AM | Dec 2 2015 6:40PM | 49.177 | 48.475 |  | 20.991 | 0.702 | 27.484 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.1 | 15.0 | -12.1 | G45T2 | 1, 2 | 7, 8
AEa/42-1 | SGBM22 | Dec 1 2015 9:30AM | Dec 2 2015 1:29AM | 49.393 | 49.075 | 9 | 26.958 | 0.318 | 22.117 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 13.0 | -9.8 | G45T2 | 1, 2 | 7, 6
AE/43-1 | SGBM22 | Dec 3 2015 4:10PM | Dec 3 2015 10:50PM | 49.192 | 48.475 | 9 | 20.193 | 0.717 | 28.282 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 18.0 | -12.5 | G45T2 | PJ 2560, PJ 2562, PJ 2563, PJ 2565 | 6, 5, 5, 2
AE/44-1 | SGBM22 | Dec 4 2015 8:00AM | Dec 4 2015 4:59PM | 49.239 | 48.475 |  | 19.721 | 0.764 | 28.754 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.7 | 16.0 | -12.7 | G45T2 | 1, 2 | 8, 8
AE/45-1 | SGBM22 | Dec 29 2015 7:10PM | Jan 31 2016 1:35AM | 49.282 | 48.475 |  | 19.381 | 0.807 | 29.094 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.9 | 16.0 | -100.0 | G45T2 | PJ3760, PJ 3762 | 8, 8
AE/46-1 | SGBM22 | Dec 26 2015 8:40AM | Dec 28 2015 1:30PM | 50.013 | 48.475 |  | 23.852 | 1.538 | 24.623 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.9 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
AD/31a-1 | SGBM19 | Nov 18 2015 6:25PM | Nov 19 2015 3:43AM | 49.475 | 48.475 | 9 | 30.895 | 1.000 | 17.580 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.8 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
AD/35-1 | SGBM19 | Nov 11 2015 8:14AM | Nov 11 2015 7:27PM | 49.650 | 49.075 | 9 | 30.293 | 0.575 | 18.782 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.3 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
AD/36-1 | SGBM19 | Nov 9 2015 3:10PM | Nov 12 2015 4:40PM | 49.581 | 49.075 | 9 | 29.588 | 0.506 | 19.487 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 14.0 | -100.0 | G35T2 | 1, 2 | 6, 8
AD/37-1 | SGBM22 | Nov 9 2015 2:50PM | Nov 11 2015 6:05PM | 49.492 | 49.075 | 9 | 28.764 | 0.417 | 20.311 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.0 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
AD/38-1 | SGBM22 | Nov 10 2015 1:35PM | Nov 11 2015 11:10AM | 49.453 | 49.075 |  | 27.847 | 0.378 | 21.228 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.4 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
AD/39-1 | SGBM22 | Nov 2 2015 8:40AM | Nov 2 2015 4:21PM | 49.530 | 49.075 | 9 | 27.525 | 0.455 | 21.550 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.5 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
AD/40-1 | SGBM22 | Nov 1 2015 3:15PM | Nov 2 2015 5:13PM | 49.590 | 49.075 | 9, 18 | 26.998 | 0.515 | 22.077 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
AD/41-1 | SGBM22 | Oct 30 2015 2:40PM | Nov 2 2015 9:14PM | 49.635 | 49.075 | 9 | 27.577 | 0.560 | 21.498 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.5 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
AD/42-1 | SGBM22 | Nov 4 2015 12:20PM | Nov 4 2015 9:54PM | 49.566 | 49.075 |  | 26.998 | 0.491 | 22.077 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 13.0 | -100.0 | G45T2 | 1, 2 | 6, 7
AD/43-1 | SGBM02 | Nov 5 2015 9:20AM | Nov 6 2015 2:40AM | 49.592 | 49.075 |  | 26.844 | 0.517 | 22.231 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
AD/44-1 | SGBM22 | Nov 5 2015 3:50PM | Nov 6 2015 1:00AM | 49.516 | 49.075 |  | 26.718 | 0.441 | 22.357 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 14.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 2
AD/45-1 | SGBM22 | Nov 5 2015 12:20PM | Nov 6 2015 1:00AM | 49.420 | 49.075 |  | 25.555 | 0.345 | 23.520 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.4 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
AD/46-1 | SGBM19 | Nov 13 2015 10:30AM | Nov 14 2015 2:43PM | 43.370 | 49.075 | 9, 24 | 20.811 | -5.705 | 28.264 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 16.0 | -12.5 | G45T2 | 1, 2, 3 | 6, 6, 4
Aca/31a-1 | SGBM22 | Nov 19 2015 8:10AM | Nov 19 2015 3:12PM | 49.539 | 48.475 |  | 27.028 | 1.064 | 21.447 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.5 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
Aca/46-1 | SGBM22 | Nov 6 2015 2:00PM | Nov 6 2015 11:58PM | 49.454 | 49.075 |  | 26.030 | 0.379 | 23.045 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
Aba/35-1 | SGBM19 | Nov 12 2015 12:36PM | Nov 12 2015 8:12PM | 49.653 | 48.775 | 9 | 32.511 | 0.878 | 16.264 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.2 | 12.0 | -16.5 | G35T2 | 1, 2 | 6, 6
AB/36-1 | SGBM19 | Oct 29 2015 6:40PM | Oct 30 2015 1:13AM | 49.598 | 48.275 |  | 26.198 | 1.323 | 22.077 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 11.0 | -100.0 | G35T2 | 1 | 11
AB/36-2 | SGBM19 | Oct 27 2015 4:20PM | Oct 27 2015 10:30PM | 49.598 | 48.275 |  | 26.176 | 1.323 | 22.099 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 4, 7, 4
Aba/36-1 | SGBM08 | Oct 25 2015 8:00PM | Oct 26 2015 1:13PM | 49.649 | 49.075 |  | 27.062 | 0.574 | 22.013 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.7 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
Aba/37-1 | SGBM08 | Oct 21 2015 12:00PM | Oct 22 2015 2:14AM | 49.630 | 49.075 |  | 29.982 | 0.555 | 19.093 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
AB/38-1 | SGBM19 | Oct 28 2015 4:10PM | Oct 29 2015 12:10AM | 49.552 | 48.275 |  | 23.273 | 1.277 | 25.002 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.0 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 2
AB/38-2 | SGBM19 | Oct 27 2015 1:00PM | Oct 27 2015 9:39PM | 49.598 | 48.275 |  | 23.235 | 1.323 | 25.040 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Aba/38-1 | SGBM08 | Oct 24 2015 3:50PM | Oct 24 2015 10:08PM | 49.591 | 49.075 |  | 27.982 | 0.516 | 21.093 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 12.0 | -100.0 | G45T2 | 1, 2 | 5, 7
AB/39-1 | SGBM19 | Oct 28 2015 1:45PM | Oct 28 2015 11:13PM | 49.558 | 48.275 |  | 23.202 | 1.283 | 25.073 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 13.0 | -100.0 | G35T2 | 1, 2 | 6, 7
AB/39-2 | SGBM19 | Oct 30 2015 4:10PM | Oct 31 2015 1:50AM | 49.641 | 48.275 |  | 23.180 | 1.366 | 25.095 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 5, 5, 5
Aba/39-1 | SGBM08 | Oct 21 2015 5:50PM | Oct 22 2015 3:00AM | 49.505 | 49.075 |  | 28.003 | 0.430 | 21.072 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 11.0 | 18.1 | G45T2 | 1, 2 | 5.5, 5.5
AB/40-1 | SGBM19 | Oct 28 2015 11:45AM | Oct 28 2015 9:09PM | 49.526 | 48.275 |  | 23.204 | 1.251 | 25.071 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 6, 3
AB/40-2 | SGBM19 | Oct 30 2015 6:30PM | Oct 31 2015 4:20AM | 49.535 | 48.275 |  | 23.252 | 1.260 | 25.023 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Aba/40-1 | SGBM08 | Oct 24 2015 12:00PM | Oct 24 2015 9:05PM | 49.498 | 49.075 |  | 27.856 | 0.423 | 21.219 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.4 | 14.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 2
AB/41-1 | SGBM19 | Oct 30 2015 8:00AM | Oct 31 2015 5:18AM | 49.495 | 48.275 |  | 23.208 | 1.220 | 25.067 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 2
AB/41-2 | SGBM19 | Oct 29 2015 3:20PM | Oct 30 2015 4:08AM | 49.489 | 48.275 |  | 23.246 | 1.214 | 25.029 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 16.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 2
Aba/41-1 | SGBM08 | Oct 16 2015 11:30AM | Oct 16 2015 6:20PM | 49.813 | 49.075 |  | 27.984 | 0.738 | 21.091 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 13.0 | -100.0 | G45T2 | 1, 2, 3 | 3, 7, 3
AB/42-1 | SGBM08 | Oct 19 2015 8:50AM | Oct 19 2015 7:25PM | 49.780 | 48.275 |  | 23.245 | 1.505 | 25.030 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
AB/42-2 | SGBM19 | Oct 29 2015 3:00PM | Oct 30 2015 6:39AM | 49.496 | 48.275 |  | 22.999 | 1.221 | 25.276 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 15.0 | -100.0 | G35T2 | 1, 2, 3 | 5, 8, 2
Aba/42-1 | SGBM19 | Nov 3 2015 11:20AM | Nov 4 2015 1:09AM | 49.468 | 49.075 | 9 | 30.573 | 0.393 | 18.502 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.2 | 15.0 | -100.0 | G45T2 | 1, 2, 3 | 4, 6, 5
AB/43-1 | SGBM19 | Nov 2 2015 6:00PM | Nov 3 2015 2:38PM | 49.445 | 48.275 | 9, 15 | 25.279 | 1.170 | 22.996 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 3
AB/43-2 | SGBM22 | Nov 4 2015 10:45AM | Nov 4 2015 11:40PM | 49.582 | 48.275 |  | 23.259 | 1.307 | 25.016 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 4
Aba/43-1 | SGBM22 | Nov 6 2015 8:45AM | Nov 6 2015 6:44PM | 49.553 | 49.075 |  | 28.005 | 0.478 | 21.070 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 14.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 5, 3
AB/44-1 | SGBM22 | Nov 2 2015 5:20PM | Nov 3 2015 4:33PM | 49.707 | 48.275 | 9, 21 | 24.179 | 1.432 | 24.096 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 4, 7, 6
AB/44-2 | SGBM19 | Oct 30 2015 11:00AM | Oct 30 2015 6:08PM | 49.607 | 48.275 |  | 22.236 | 1.332 | 26.039 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 16.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 3
Aba/44-1 | SGBM19 | Nov 4 2015 8:00AM | Nov 4 2015 1:58PM | 49.663 | 49.075 | 8 | 27.983 | -5.412 | 21.092 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 12.0 | 28.8 | G35T2 | 1, 2 | 6, 6
AB/45-1 | SGBM19 | Nov 2 2015 5:40PM | Nov 4 2015 3:40AM | 49.531 | 48.275 | 9, 18, 21 | 23.339 | 1.256 | 24.936 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.0 | 14.0 | -11.0 | G45T2 | 1, 2 | 7, 7
AB/45-2 | SGBM02 | Nov 4 2015 7:15PM | Nov 5 2015 3:43PM | 49.538 | 48.275 |  | 20.655 | 1.263 | 27.620 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
AA/36-1 | SGBM21 | Oct 6 2015 8:45PM | Oct 7 2015 11:01AM | 49.625 | 49.075 |  | 29.540 | 0.550 | 19.535 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.6 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
AA/37-1 | SGBM21 | Oct 6 2015 8:45PM | Oct 7 2015 11:50AM | 49.619 | 49.075 |  | 29.346 | 0.544 | 19.729 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
AA/38-1 | SGBM21 | Oct 6 2015 8:45PM | Oct 7 2015 3:32PM | 49.653 | 49.075 |  | 29.491 | 0.578 | 19.584 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 11.0 | -100.0 | G35T2 | 1 | 11
AA/39-1 | SGBM21 | Oct 7 2015 8:00AM | Oct 7 2015 4:35PM | 49.635 | 49.075 |  | 28.947 | 0.560 | 20.128 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.9 | 12.0 | -100.0 | G35T2 | 1, 2 | 5, 7
AA/40-1 | SGBM19 | Oct 13 2015 2:20PM | Oct 13 2015 9:58PM | 49.830 | 49.075 |  | 25.065 | 0.755 | 24.010 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 16.0 | -100.0 | G35T2 | 1, 2 | 10, 6
AA/43-1 | SGBM08 | Oct 13 2015 1:00PM | Oct 13 2015 7:34PM | 49.646 | 49.075 |  | 30.025 | 0.571 | 19.050 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 10.0 | -100.0 | G35T2 | 1, 2 | 7, 3
AA/44-1 | SGBM08 | Oct 13 2015 1:00PM | Oct 13 2015 10:44PM | 49.712 | 49.075 |  | 29.019 | 0.637 | 20.056 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.9 | 10.0 | -100.0 | G35T2 | 1, 2 | 7, 3
AA/45-1 | SGBM08 | Oct 15 2015 2:50PM | Oct 16 2015 12:36AM | 49.643 | 49.075 |  | 28.031 | 0.568 | 21.044 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
AA/46-1 | SGBM02 | Nov 6 2015 4:00PM | Nov 7 2015 2:15AM | 49.419 | 49.075 |  | 27.025 | 0.344 | 22.050 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.7 | 13.0 | -100.0 | G35T2 | 1, 2 | 6, 7
Ta/40-1 | SGBM03 | Jan 11 2016 10:30AM | Jan 11 2016 9:05PM | 52.171 | 51.325 |  | 27.360 | 0.846 | 23.965 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
Aba/45-1 | SGBM22 | Nov 6 2015 3:00PM | Nov 7 2015 12:15AM | 49.512 | 49.075 |  | 26.812 | 0.437 | 22.263 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 13.0 | 32.2 | G45T2 | 1, 2 | 5, 8
U/34-1 | SGBM03 | Jan 12 2016 8:10AM | Jan 12 2016 8:00PM | 52.393 | 51.325 |  | 36.783 | 1.068 | 14.542 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.4 | 9.0 | -100.0 | G45T2 | 1 | 9
U/35-1 | SGBM20 | Jan 8 2016 8:40AM | Jan 8 2016 9:27PM | 52.306 | 51.375 |  | 29.689 | 0.931 | 21.686 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.6 | 12.0 | -9.6 | G45T2 | 1, 2 | 6, 6
U/36a-1 | SGBM20 | Jan 16 2016 8:30AM | Jan 16 2016 2:35PM | 52.213 | 51.325 |  | -18.500 | 0.888 | 69.825 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 30.9 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
U/37a-1 | SGBM20 | Jan 15 2016 9:00AM | Jan 15 2016 5:00PM | 52.329 | 51.325 |  | -19.100 | 1.004 | 70.425 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 31.1 | 10.0 | -100.0 | G45T2 | 1 | 10
U/37-1 | SGBM03 | Jan 11 2016 8:30AM | Jan 11 2016 7:40PM | 52.386 | 51.375 |  | 30.239 | 1.011 | 21.136 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 13.0 | -100.0 | G45T2 | 1, 2 | 7, 6
U/38a-1 | SGBM03 | Jan 13 2016 5:00PM | Jan 15 2016 1:00AM | 52.345 | 51.325 |  | 33.247 | 1.020 | 18.078 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 12.0 | 50.2 | G45T2 | 1, 2 | 5, 7
S/31-1 | SGBM01 | Dec 17 2015 10:00AM | Dec 18 2015 5:09PM | 52.055 | 51.375 |  | 33.106 | 0.680 | 18.269 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
Sa/40-1 | SGBM21 | Oct 9 2015 2:00PM | Oct 9 2015 5:42PM | 52.450 | 50.775 |  | 32.775 | 1.675 | 18.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 10.0 | -100.0 | G45T2 | 1, 2 | 7, 3
S/40-1 | SGBM21 | Oct 7 2015 8:00AM | Oct 7 2015 12:20PM | 52.498 | 50.775 |  | 32.775 | 1.723 | 18.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 10.0 | -100.0 | G45T2 | 1 | 10
R/40-1 | SGBM21 | Oct 7 2015 6:00PM | Oct 8 2015 11:45AM | 52.436 | 50.775 |  | 33.775 | 1.661 | 17.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.5 | 10.0 | -7.5 | G45T2 | 1 | 10
Q/31-1 | SGBM20 | Dec 15 2015 8:00AM | Dec 15 2015 10:58PM | 52.075 | 51.375 |  | 33.156 | 0.700 | 18.219 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 11.0 | -100.0 | G45T2 | 1 | 11
Q/40-1 | SGBM21 | Oct 7 2015 12:00PM | Oct 7 2015 8:12PM | 52.253 | 50.775 |  | 29.775 | 1.478 | 21.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 14.0 | -9.3 | G45T2 | 1, 2 | 7, 7
P/40-1 | SGBM08 | Oct 5 2015 7:00PM | Oct 6 2015 2:32PM | 52.080 | 50.775 |  | 29.775 | 1.305 | 21.000 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 12.0 | -100.0 | G45T2 | 1, 2 | 8, 4
N/30-1 | SGBM20 | Dec 14 2015 2:30PM | Dec 16 2015 12:05PM | 52.038 | 51.375 |  | 33.255 | 0.663 | 18.120 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 10.0 | -100.0 | G45T2 | 1, 2 | 5, 5
N/31-1 | SGBM20 | Dec 28 2015 6:00PM | Dec 28 2015 10:14PM | 52.082 | 51.375 |  | 35.232 | 0.707 | 16.143 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.1 | 11.0 | -7.1 | G45T2 | 1, 2 | 6, 5
T/15-1 | SGBM03 | Dec 11 2015 5:00PM | Dec 12 2015 3:10AM | 55.805 | 54.475 |  | 34.180 | 1.330 | 20.295 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.0 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
R/23-1 | SGBM21 | Dec 1 2015 8:00AM | Dec 1 2015 4:34PM | 50.242 | 48.275 | 9 | 30.102 | 1.967 | 18.173 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
R/23-2 | SGBM21 | Dec 7 2015 8:00AM | Dec 7 2015 9:43PM | 50.346 | 48.275 | 9 | 30.114 | 2.071 | 18.161 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 10.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 3, 1
Q/17-1 | SGBM20 | Dec 1 2015 8:00AM | Dec 2 2015 12:41PM | 55.765 | 55.075 | 9 | -15.700 | 0.690 | 70.775 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 31.3 | 8.0 | -100.0 | G45T2 | 1, 2 | 6, 2
Q/18-1 | SGBM20 | Dec 1 2015 8:00AM | Dec 2 2015 3:17PM | 55.820 | 55.075 | 9 | 41.770 | -55.075 | 13.305 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.9 | 9.0 | -100.0 | G45T2 | 1, 2 | 7, 2
Q/22-1 | SGBM21 | Nov 19 2015 6:20PM | Nov 21 2015 3:07PM | 53.605 | 52.775 | 9 | 36.735 | 0.830 | 16.040 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.1 | 9.0 | -100.0 | G35T2 | 1, 2 | 5, 4
P/22-1 | SGBM05 | Nov 14 2015 12:00PM | Nov 17 2015 5:30PM | 53.493 | 52.775 | 9 | 36.801 | -52.775 | 15.974 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.1 | 8.0 | -100.0 | G45T2 | 1 | 8
N/23-1 | SGBM21 | Nov 18 2015 6:10PM | Nov 19 2015 4:05PM | 53.169 | 52.775 | 9 | 32.602 | 0.394 | 20.173 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.9 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
M/18a-1 | SGBM05 | Nov 14 2015 4:22PM | Nov 17 2015 12:25PM | 55.559 | 52.175 | 9 | 39.739 | 3.384 | 12.436 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.5 | 8.0 | -100.0 | G35T2 | 1 | 8
Ma/22a-1 | SGBM16 | Jan 2 2016 8:30AM | Jan 2 2016 12:10PM | 53.362 | 52.775 |  | 36.491 | 0.587 | 16.284 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.2 | 10.0 | -100.0 | G45T2 | 1 | 10
H/35-1 | SGBM20 | Nov 6 2015 8:00AM | Nov 6 2015 9:15PM | 52.178 | 51.375 | 9 | 32.874 | 1.000 | 18.501 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.2 | 12.0 | -8.2 | G45T2 | 1, 2 | 6, 6
L/18a-1 | SGBM20 | Nov 14 2015 6:22PM | Nov 17 2015 1:35PM | 53.648 | 52.175 | 9 | 39.894 | 1.473 | 12.281 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.4 | 8.0 | -100.0 | G45T2 | 1, 2 | 5, 3
J/18-1 | SGBM19 | Mar 26 2016 11:10AM | Mar 29 2016 12:45AM | 55.336 | 51.375 |  | 24.582 | 3.961 | 26.793 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 13.0 | -100.0 | G45T2 | pj7372, pj7373 | 7, 6
J/18-2 | SGBM31 | Apr 2 2016 8:00AM | Apr 4 2016 6:50PM | 55.290 | 51.375 |  | 24.638 | 3.915 | 26.737 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 13.0 | -100.0 | G45T2 | pj7582, pj7583 | 7, 6
H/18-1 | SGBM19 | Apr 1 2016 6:00AM | Apr 2 2016 3:00PM | 55.160 | 50.575 |  | 23.586 | 4.585 | 26.989 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 14.0 | -100.0 | G45T2 | pj7541, pj7543 | 7, 7
H/18-2 | SGBM20 | Nov 9 2015 11:00AM | Nov 9 2015 8:33PM | 53.676 | 50.575 | 9 | 23.926 | 3.101 | 26.649 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 15.0 | -11.8 | G45T2 | 1, 2 | 8, 7
H/18-3 | SGBM19 | Mar 28 2016 9:40AM | Mar 29 2016 3:20PM | 54.943 | 50.575 |  | 23.692 | 4.368 | 26.883 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 16.0 | -100.0 | G45T2 | pj7377, pj7378 | 8, 8
H/18-4 | SGBM20 | Nov 11 2015 4:25PM | Nov 11 2015 3:17PM | 53.671 | 50.575 | 9 | 23.970 | 3.096 | 26.605 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 14.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 5, 4
G/18-1 | SGBM19 | Mar 26 2016 10:30AM | Mar 26 2016 9:20PM | 54.644 | 51.375 |  | 23.652 | 3.269 | 27.723 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 18.0 | -100.0 | G45T2 | pj7298, pj7299 | 9, 9
G/18-2 | SGBM19 | Apr 1 2016 5:20PM | Apr 2 2016 4:35PM | 54.660 | 51.375 |  | 24.486 | 3.285 | 26.889 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 13.0 | -100.0 | G45T2 | pj7549, pj7551 | 7, 6
Ka/64-1 | SGBM02 | Dec 5 2015 9:58AM | Dec 10 2015 11:41AM | 52.241 | 49.775 | 11 | 19.690 | 2.466 | 30.085 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.3 | 21.0 | 58.0 | G35T2 | 1, 2, 3 | 7, 7, 7
H/53-1 | SGBM01 | Oct 27 2015 8:00PM | Oct 28 2015 1:54PM | 51.945 | 51.375 |  | 16.237 | 0.570 | 35.138 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.5 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
E/63-1 | SGBM23 | Nov 9 2015 3:36PM | Nov 11 2015 6:30PM | 51.760 | 51.375 | 9 | 15.165 | 0.385 | 36.210 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.0 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 2
D/63-1 | SGBM17 | Oct 31 2015 12:40PM | Nov 9 2015 6:20PM | 51.890 | 51.375 | 9, 23 | 17.031 | 0.515 | 34.344 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.2 | 20.0 | 4.8 | G45T2 | PJ 1376, PJ 1377, PJ 1378, PJ 1383 | 6, 6, 6, 2
C/52-1 | SGBM02 | Nov 18 2015 6:01PM | Nov 19 2015 10:30PM | 51.560 | 51.275 | 12, 22 | 11.056 | -51.275 | 40.219 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.8 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
C/54-1 | SGBM02 | Nov 21 2015 8:40AM | Nov 21 2015 7:31PM | 51.515 | 51.375 | 12 | 12.319 | -51.375 | 39.056 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.3 | 24.0 | -17.3 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 4
C/63-1 | SGBM02 | Nov 14 2015 12:00PM | Nov 14 2015 10:09PM | 51.710 | 51.375 | 14 | 18.058 | 0.335 | 33.317 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
Ba/53-1 | SGBM08 | Nov 13 2015 9:20AM | Nov 14 2015 12:27AM | 51.760 | 51.075 | 15 | 18.060 | 0.685 | 33.015 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.6 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 7
Ba/54-1 | SGBM02 | Nov 17 2015 8:30AM | Nov 18 2015 6:27PM | 51.751 | 51.275 | 9, 15 | 13.194 | 0.456 | 38.081 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.8 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
B/55-1 | SGBM18 | Nov 14 2015 1:25PM | Nov 15 2015 12:30AM | 51.707 | 51.275 |  | 13.507 | 0.432 | 37.768 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.7 | 22.0 | -100.0 | G45T2 | 1, 2 | 10, 12
B/57-1 | SGBM08 | Nov 17 2015 9:15AM | Nov 18 2015 12:35PM | 51.713 | 51.275 | 9, 13.5, 31 | 14.698 | 0.438 | 36.577 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.2 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
B/58-1 | SGBM02 | Nov 20 2015 9:25AM | Nov 21 2015 1:21PM | 51.483 | 51.275 | 12, 19.5, 30 | 16.211 | 0.208 | 35.064 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.5 | 22.0 | 6.5 | G45T2 | 1, 2, 3 | 8, 7, 7
B/59-1 | SGBM02 | Nov 21 2015 5:50PM | Nov 23 2015 6:23PM | 51.460 | 51.275 | 12, 32 | 16.970 | 0.185 | 34.305 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.2 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
B/60-1 | SGBM08 | Nov 18 2015 12:50PM | Nov 19 2015 7:25PM | 51.600 | 51.275 | 12, 24 | 18.074 | 0.325 | 33.201 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.7 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 4
B/62-1 | SGBM02 | Nov 19 2015 2:54PM | Nov 20 2015 4:44PM | 51.430 | 51.075 | 9 | 19.003 | 0.355 | 32.072 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.2 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 5
B/63-1 | SGBM02 | Nov 15 2015 8:30AM | Nov 17 2015 10:27AM | 51.668 | 51.075 | 9 | 23.850 | 0.593 | 27.225 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 6, 5
Aa/58-1 | SGBM08 | Nov 9 2015 7:15PM | Nov 12 2015 4:00PM | 51.646 | 51.275 | 9, 35 | 15.942 | 0.371 | 35.333 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.6 | 23.0 | 13.4 | G45T2 | C520123284, C480011635 | 12, 11
Aa/59-1 | SGBM08 | Nov 15 2015 2:00PM | Nov 16 2015 10:22PM | 51.535 | 51.275 | 9, 24 | 16.881 | -51.275 | 34.394 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.2 | 17.0 | 11.9 | G45T2 | 1, 2, 3 | 6, 6, 5
Aa/60-1 | SGBM02 | Nov 9 2015 6:15PM | Nov 15 2015 7:57PM | 51.690 | 51.275 | 15, 18, 23.5 | 23.179 | 0.415 | 28.096 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 18.0 | 45.0 | G35T2 | 1, 2, 3 | 6, 6, 6
Aa/62-1 | SGBM02 | Nov 12 2015 6:15PM | Nov 13 2015 10:40PM | 51.640 | 51.375 | 9, 15 | 19.175 | 0.265 | 32.200 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.2 | 20.0 | -100.0 | G45T2 | 1, 2 | 11, 9
Aa/63-1 | SGBM18 | Nov 9 2015 12:05PM | Nov 9 2015 5:22PM | 51.750 | 50.775 |  | 23.713 | 0.975 | 27.062 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 4
Ca/52-1 | SGBM02 | Nov 11 2015 11:10AM | Nov 12 2015 12:40PM | 51.895 | 51.275 | 9 | 11.245 | 0.620 | 40.030 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.7 | 29.0 | -17.7 | G45T2 | C480011623, C480011625, C480011626 | 9, 10, 10
J/55-2a | SGBM23 | Nov 6 2015 8:10AM | Nov 6 2015 6:05PM | 51.880 | 49.375 | 9, 27 | 14.974 | 2.505 | 34.401 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.2 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 8
J/55-2b | SGBM15 | Nov 4 2015 5:00PM | Nov 5 2015 3:02PM | 51.882 | 49.375 | 9, 15 | 15.232 | 2.507 | 34.143 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.1 | 23.0 | 52.5 | G45T2 | PJ 1253, PJ 1255, PJ 1258 | 8, 8, 7
M/41-1 | SGBM01 | Jan 4 2016 12:26PM | Jan 4 2016 10:10PM | 51.896 | 50.575 |  | 27.134 | 1.321 | 23.441 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.4 | 13.0 | -10.3 | G45T2 | PJ 3945, PJ 3948 | 7, 6
M/45-1 | SGBM08 | Dec 31 2015 2:00PM | Jan 2 2016 8:00PM | 51.833 | 50.575 |  | 23.437 | 1.258 | 27.138 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
M/46-1 | SGBM08 | Dec 23 2015 11:00AM | Dec 26 2015 8:21PM | 51.587 | 50.575 |  | 22.505 | 1.012 | 28.070 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 15.0 | -12.4 | G45T2 | PJ 3551, PJ 3554 | 8, 7
N/41-1 | SGBM01 | Jan 4 2016 3:10PM | Jan 4 2016 11:30PM | 52.033 | 50.575 |  | 32.260 | 1.458 | 18.315 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 10.0 | -8.1 | G45T2 | PJ 3951 | 10
N/42-1 | SGBM08 | Dec 21 2015 5:35PM | Dec 23 2015 8:41PM | 51.820 | 50.575 |  | 24.046 | 1.245 | 26.529 |  | 0.0 | 0.0 | 16T20+8T20 | T10-225 | 12 | 11.7 | 20.0 | -100.0 | G35T2 | C520124352, C520124354 | 10, 10
N/43-1 | SGBM08 | Dec 21 2015 4:40PM | Dec 22 2015 9:29PM | 51.871 | 50.575 |  | 23.573 | 1.296 | 27.002 |  | 0.0 | 0.0 | 16T20+8T20 | T10-225 | 12 | 11.9 | 20.0 | -100.0 | G35T2 | 1, 2 | 12, 8
N/44-1 | SGBM08 | Jan 4 2016 1:28PM | Jan 5 2016 3:20PM | 52.060 | 50.575 |  | 24.093 | 1.485 | 26.482 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.7 | 14.0 | -11.7 | G45T2 | PJ 3973, PJ 3975 | 7, 7
N/45-1 | SGBM08 | Jan 2 2016 4:45PM | Jan 4 2016 1:00PM | 51.888 | 50.575 |  | 23.524 | 1.313 | 27.051 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 15.0 | -11.9 | G45T2 | PJ 3899, PJ 3903 | 8, 7
N/46-1 | SGBM08 | Dec 29 2015 2:35PM | Dec 29 2015 7:52PM | 51.643 | 50.575 |  | 22.165 | 1.068 | 28.410 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.6 | 16.0 | 27.5 | G45T2 | PJ 3684, PJ 3688 | 8, 8
N/47-1 | SGBM08 | Dec 23 2015 1:15PM | Dec 24 2015 1:51AM | 51.690 | 50.575 |  | 22.206 | 1.115 | 28.369 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 23.0 | -12.5 | G45T2 | C520124371, C520124375, C520124376 | 6, 10, 7
H/37-1 | SGBM08 | Dec 10 2015 3:46PM | Dec 11 2015 4:33PM | 52.056 | 51.075 |  | 29.629 | 0.981 | 21.446 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.5 | 13.0 | 37.2 | G45T2 | PJ 2952, PJ 2955 | 7, 6
F/40-1 | SGBM08 | Dec 17 2015 4:20PM | Dec 18 2015 1:58AM | 52.000 | 51.375 |  | 25.790 | 0.625 | 25.585 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 15.0 | 32.7 | G45T2 | 1, 2 | 7, 8
F/41-1 | SGBM08 | Dec 11 2015 11:32AM | Dec 12 2015 5:08PM | 52.008 | 51.375 |  | 25.090 | 0.633 | 26.285 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.6 | 16.0 | 37.8 | G45T2 | 1, 2 | 8, 8
F/48-1 | SGBM08 | Nov 28 2015 10:29AM | Nov 30 2015 4:23PM | 51.493 | 51.075 | 16, 27 | 14.719 | 0.418 | 36.356 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.1 | 22.0 | 5.9 | G45T2 | 1, 2, 3 | 7, 8, 7
F/49-1 | SGBM08 | Nov 30 2015 11:46AM | Dec 2 2015 2:06AM | 51.809 | 51.075 | 9, 26, 27 | 14.750 | 0.734 | 36.325 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.1 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
Ea/40-1 | SGBM08 | Dec 11 2015 11:35AM | Dec 12 2015 2:42PM | 51.976 | 51.375 |  | 26.192 | 0.601 | 25.183 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | 34.8 | G45T2 | 1, 2 | 8, 7
Ea/41-1 | SGBM08 | Dec 10 2015 9:53AM | Dec 10 2015 8:09PM | 51.940 | 51.375 | 11 | 23.952 | 0.565 | 27.423 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.1 | 18.0 | 48.6 | G45T2 | 1, 2, 3 | 9, 7, 2
Ea/42-1 | SGBM08 | Dec 9 2015 9:10AM | Dec 9 2015 7:58PM | 51.825 | 50.775 |  | 28.666 | 1.050 | 22.109 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
E/46-1 | SGBM08 | Nov 26 2015 7:30PM | Nov 28 2015 6:03PM | 51.575 | 50.775 | 12 | 15.576 | 0.800 | 35.199 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.6 | 22.0 | 6.4 | G35T2 | 1, 2 | 11, 11
Da/46-1 | SGBM08 | Dec 7 2015 2:25PM | Dec 8 2015 6:00PM | 51.700 | 50.775 | 9, 29 | 15.648 | 0.925 | 35.127 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.5 | 22.0 | 41.7 | G45T2 | PJ 2767, PJ 2769, PJ 2771 | 8, 7, 7
Da/47-1 | SGBM08 | Dec 4 2015 5:43PM | Dec 7 2015 7:12PM | 51.760 | 50.775 | 11, 27, 30.2 | 14.314 | 0.985 | 36.461 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 16.1 | 22.0 | -100.0 | G45T2 | PJ 2719, PJ 2721, PJ 2727 | 8, 7, 7
Ca/50-1 | SGBM15 | Nov 25 2015 8:00AM | Nov 26 2015 5:14PM | 51.581 | 50.775 |  | 17.561 | 0.806 | 33.214 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.7 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 6
Ca/51-1 | SGBM08 | Nov 23 2015 12:36PM | Nov 24 2015 9:12PM | 51.566 | 50.775 | 12, 25 | 10.741 | 0.791 | 40.034 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 17.7 | 24.0 | -17.7 | G45T2 | 1, 2, 3 | 8, 8, 8
T/49a-1 | SGBM23 | Feb 26 2016 4:20PM | Feb 27 2016 2:15PM | 51.947 | 51.375 |  | -29.300 | 0.572 | 80.675 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 35.6 | 16.0 | -32.7 | G45T2 | pj6107, pj6112 | 8, 8
T/60a-1 | SGBM23 | Feb 23 2016 9:25AM | Feb 23 2016 7:45PM | 52.062 | 50.375 |  | 26.097 | 1.687 | 24.278 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 14.0 | -100.0 | G45T2 | PJ5911, PJ5913 | 7, 7
S/49a-1 | SGBM08 | Feb 19 2016 10:00AM | Feb 22 2016 6:20PM | 52.029 | 51.375 |  | 22.899 | 0.654 | 28.476 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.6 | 15.0 | 19.2 | G45T2 | PJ5851, PJ5855 | 8, 7
S/60a-1 | SGBM23 | Feb 23 2016 10:10AM | Feb 23 2016 9:20PM | 52.043 | 51.375 |  | 32.281 | 0.668 | 19.094 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 12.0 | 3.6 | G45T2 | 1, 2 | 6, 6
R/49a-1 | SGBM08 | Feb 19 2016 8:15AM | Feb 20 2016 8:30PM | 52.042 | 51.375 |  | 21.821 | 0.667 | 29.554 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.1 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
R/58-1 | SGBM05 | Jan 16 2016 2:05PM | Feb 15 2016 7:15PM | 51.923 | 51.375 |  | 23.810 | 0.548 | 27.565 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 13.0 | 6.7 | G45T2 | 1, 2 | 7, 6
R/62-1 | SGBM31 | Feb 20 2016 5:25PM | Feb 23 2016 11:15PM | 50.568 | 49.925 |  | -22.600 | 0.643 | 72.525 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 32.0 | 12.0 | -62.6 | G45T2 | 1, 2 | 6, 6
Q/49a-1 | SGBM08 | Feb 22 2016 3:00PM | Feb 23 2016 6:40PM | 51.931 | 51.375 |  | 26.253 | 0.556 | 25.122 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 17.0 | -100.0 | G45T2 | pj5910, pj5906, pj5919 | 7, 8, 2
Q/49-1 | SGBM05 | Feb 4 2016 12:55PM | Feb 10 2016 8:00PM | 51.880 | 51.375 |  | 22.160 | 0.505 | 29.215 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.9 | 18.0 | -12.9 | G45T2 | 1, 2 | 8, 10
Q/58-1 | SGBM19 | Nov 30 2015 8:40AM | Nov 30 2015 8:28PM | 52.265 | 51.375 | 9 | 22.772 | 0.890 | 28.603 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.6 | 26.0 | -100.0 | G45T2 | PJ 2380, PJ 2381, PJ 2384, PJ 2393 | 7, 7, 6, 6
Q/62-1 | SGBM31 | Feb 24 2016 9:40AM | Feb 24 2016 4:10PM | 50.744 | 49.925 |  | 27.650 | 0.819 | 22.275 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 12.0 | -100.0 | G45T2 | PJ5946, PJ5949 | 6, 6
P/60a-1 | SGBM23 | Feb 23 2016 5:30PM | Feb 24 2016 7:25PM | 52.273 | 51.375 |  | 28.995 | 0.898 | 22.380 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 12.0 | 2.1 | G45T2 | PJ5957, PJ5958 | 6, 6
Na/41-1 | SGBM31 | Mar 9 2016 10:40AM | Mar 10 2016 12:25AM | 51.992 | 51.375 |  | 30.624 | 0.617 | 20.751 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.2 | 13.0 | -9.2 | G45T2 | 1, 2 | 6, 7
Na/42-1 | SGBM31 | Mar 9 2016 9:00AM | Mar 9 2016 10:55PM | 52.091 | 51.375 |  | 30.914 | 0.716 | 20.461 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.0 | 13.0 | -9.0 | G45T2 | pj6531, Pending | 7, 6
Na/43-1 | SGBM31 | Mar 8 2016 1:15PM | Mar 9 2016 12:05AM | 52.058 | 51.375 |  | 29.706 | 0.683 | 21.669 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.6 | 14.0 | -100.0 | G45T2 | 1, 2 | 8, 6
Na/44-1 | SGBM31 | Mar 7 2016 2:15PM | Mar 7 2016 11:40PM | 52.176 | 51.375 |  | 28.843 | 0.801 | 22.532 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.0 | 13.0 | -100.0 | G45T2 | pj6423, pj6424 | 7, 6
Na/45-1 | SGBM31 | Mar 7 2016 1:25PM | Mar 8 2016 9:08PM | 52.088 | 51.375 |  | 27.933 | 0.713 | 23.442 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
Na/46-1 | SGBM01 | Jan 26 2016 12:00PM | Jan 27 2016 6:25PM | 51.809 | 50.575 |  | 27.463 | 0.434 | 23.112 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
N/49-1 | SGBM08 | Feb 11 2016 4:15PM | Feb 13 2016 2:55PM | 51.696 | 51.375 |  | 22.062 | 0.321 | 29.313 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.0 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
N/60a-1 | SGBM31 | Mar 2 2016 10:35AM | Mar 3 2016 12:20AM | 51.951 | 51.375 |  | -30.000 | 0.576 | 81.375 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 36.0 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 2
M7/52-1 | SGBM08 | Jan 20 2016 1:30PM | Jan 22 2016 4:50PM | 52.020 | 51.375 |  | 20.155 | 0.645 | 31.220 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 18.0 | -100.0 | G45T2 | 1, 2 | 8, 10
M7/54-1 | SGBM08 | Jan 22 2016 4:15PM | Jan 26 2016 2:15PM | 52.084 | 50.925 |  | 19.607 | 1.159 | 31.318 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
M5/60a-1 | SGBM08 | Jan 5 2016 1:45PM | Jan 7 2016 9:40PM | 51.786 | 51.375 |  | 24.287 | 0.411 | 27.088 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
M4/60-1 | SGBM08 | Jan 5 2016 2:50PM | Jan 6 2016 9:40PM | 51.860 | 51.375 |  | 20.003 | 0.485 | 31.372 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.9 | 15.0 | -100.0 | G45T2 | 1, 2 | 7, 8
M3/60a-1 | SGBM08 | Jan 5 2016 1:00PM | Jan 7 2016 9:40PM | 51.835 | 51.375 |  | 24.314 | 0.460 | 27.061 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 16.0 | 33.8 | G45T2 | 1, 2 | 8, 8
Tb/62a-1 | SGBM08 | Jan 26 2016 11:45AM | Jan 27 2016 3:30PM | 50.502 | 48.5 |  | 30.246 | -0.273 | 18.254 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
Ta/62a-1 | SGBM08 | Jan 29 2016 3:30PM | Jan 30 2016 10:45PM | 50.937 | 48.5 |  | 30.077 | 1.162 | 18.423 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 12.0 | -100.0 | G45T2 | 1, 2 | 10, 2
T/62a-1 | SGBM08 | Feb 2 2016 11:35AM | Feb 3 2016 8:30PM | 50.569 | 48.5 |  | 30.145 | 0.794 | 18.355 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
S/62a-1 | SGBM05 | Feb 10 2016 8:30AM | Feb 11 2016 10:45PM | 50.531 | 49.775 |  | 22.671 | 0.756 | 27.104 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
R/62a-1 | SGBM05 | Feb 16 2016 9:15AM | Feb 17 2016 11:30PM | 50.514 | 50.775 |  | 22.390 | -0.261 | 28.385 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
Q/62a-1 | SGBM05 | Feb 20 2016 8:45AM | Feb 20 2016 11:45PM | 50.709 | 50.775 |  | 22.064 | -0.066 | 28.711 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.7 | 14.0 | -12.7 | G45T2 | 1, 2 | 7, 7
P/62a-1 | SGBM05 | Feb 18 2016 2:00PM | Feb 19 2016 11:10PM | 50.516 | 50.775 |  | 20.216 | -0.259 | 30.559 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.5 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/62a-1 | SGBM08 | Feb 13 2016 1:15PM | Feb 15 2016 11:20PM | 51.323 | 50.775 |  | 26.179 | 0.548 | 24.596 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.9 | 13.0 | -10.9 | G45T2 | 1, 2 | 7, 6
M7b/62a-1 | SGBM08 | Feb 2 2016 9:45AM | Feb 4 2016 4:55PM | 51.273 | 48.5 |  | 24.723 | 0.498 | 23.777 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.5 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
M7a/62b-1 | SGBM08 | Jan 27 2016 1:30PM | Jan 30 2016 8:10PM | 51.542 | 48.5 |  | 25.462 | 0.767 | 23.038 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | 25.2 | G45T2 | 1, 2 | 11, 3
AE/52-1 | SGBM20 | Feb 17 2016 10:10AM | Feb 18 2016 6:40PM | 49.956 | 48.475 |  | 23.440 | 1.481 | 25.035 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 16.0 | -100.0 | G45T2 | PJ 5702, PJ 5709 | 8, 8
AE/53-1 | SGBM31 | Feb 18 2016 9:15AM | Feb 18 2016 3:50PM | 49.925 | 49.075 |  | 23.518 | 0.850 | 25.557 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 15.0 | -100.0 | G45T2 | PJ 5687, PJ 5690 | 8, 7
AE/54-1 | SGBM31 | Feb 17 2016 10:20AM | Feb 17 2016 4:40PM | 49.824 | 48.475 |  | 23.447 | 1.349 | 25.028 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G45T2 | PJ5638, PJ 5642 | 8, 7
AE/55-1 | SGBM31 | Feb 19 2016 9:25AM | Feb 19 2016 5:50PM | 49.608 | 48.475 |  | 23.405 | 1.133 | 25.070 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G45T2 | PJ 5746, PJ 5750 | 8, 7
AE/56-1 | SGBM31 | Feb 22 2016 9:37AM | Feb 22 2016 4:25PM | 49.581 | 48.475 |  | 23.430 | 3.480 | 25.045 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 16.0 | -100.0 | G45T2 | PJ 5842, PJ 5847 | 8, 8
AE/57-1 | SGBM31 | Feb 10 2016 5:30PM | Feb 11 2016 2:30PM | 49.626 | 48.475 |  | 22.835 | 1.151 | 25.640 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
AE/57a-1 | SGBM31 | Jan 23 2016 3:20PM | Jan 26 2016 10:55AM | 49.590 | 48.475 |  | 23.396 | 1.115 | 25.079 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 19.0 | 71.5 | G45T2 | PJ 4873, PJ 4874, PJ 4876 | 8, 7, 4
AE/58-1 | SGBM31 | Jan 22 2016 8:45AM | Jan 22 2016 6:55PM | 49.577 | 48.475 |  | 17.342 | 1.102 | 31.133 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 7, 3
AAa/59-1 | SGBM22 | Jan 16 2016 8:39AM | Jan 15 2016 7:15PM | 49.680 | 48.475 |  | 17.058 | 1.205 | 31.417 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.9 | 18.0 | -100.0 | G35T2 | PJ 4502, PJ 4507 | 8, 10
AAa/60-1 | SGBM22 | Jan 11 2016 10:40AM | Jan 12 2016 5:40PM | 49.632 | 47.075 |  | 15.896 | 2.557 | 31.179 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 17.0 | -100.0 | G35T2 | 1, 2 | 8, 9
AAa/61-1 | SGBM22 | Jan 13 2016 3:59PM | Jan 14 2016 11:25PM | 49.365 | 47.075 |  | 15.890 | 2.290 | 31.185 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 17.0 | -100.0 | G35T2 | 1, 2 | 8, 9
AAa/62-1 | SGBM31 | Feb 2 2016 3:05PM | Feb 3 2016 2:30PM | 49.297 | 47.075 |  | 23.038 | 2.222 | 24.037 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.6 | 15.0 | -100.0 | G35T2 | PJ 5219, PJ 5222 | 7, 8
AD/52-1 | SGBM20 | Feb 19 2016 9:15AM | Feb 19 2016 5:05PM | 49.796 | 49.075 |  | 23.811 | 0.721 | 25.264 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 15.0 | -100.0 | G45T2 | PJ 5741, PJ 5745 | 8, 7
AD/53-1 | SGBM20 | Feb 20 2016 10:00AM | Feb 20 2016 2:25PM | 49.905 | 49.075 |  | 23.867 | 0.830 | 25.208 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G45T2 | PJ 5781, PJ 5783 | 7, 8
ACa/46a-1 | SGBM19 | Nov 13 2015 2:45PM | Nov 13 2015 7:42PM | 49.340 | 49.075 | 9 | 25.900 | 0.265 | 23.175 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
AC/52-1 | SGBM22 | Nov 11 2015 4:30PM | Nov 12 2015 4:20PM | 49.329 | 49.075 | 9, 21 | 25.668 | 0.254 | 23.407 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
AC/53-1 | SGBM22 | Nov 14 2015 3:10PM | Nov 14 2015 9:25PM | 49.310 | 49.075 | 9 | 25.709 | 0.235 | 23.366 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
AC/54-1 | SGBM31 | Feb 13 2016 8:20AM | Feb 13 2016 4:55PM | 49.592 | 49.075 |  | 23.336 | 0.517 | 25.739 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.4 | 13.0 | -100.0 | G45T2 | PJ 5483, PJ 5487 | 7, 6
AC/55-1 | SGBM31 | Feb 20 2016 10:25AM | Feb 20 2016 5:15PM | 49.617 | 49.075 |  | 23.994 | 0.542 | 25.081 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 15.0 | -100.0 | G45T2 | PJ 5797, PJ 5802 | 8, 7
AB/57-1 | SGBM31 | Jan 28 2016 8:10AM | Jan 28 2016 3:35PM | 49.521 | 49.075 |  | 23.104 | 0.446 | 25.971 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 15.0 | -100.0 | G45T2 | PJ5011, PJ 5012 | 8, 7
AA/52-1 | SGBM19 | Nov 16 2015 8:00AM | Nov 16 2015 4:59PM | 49.372 | 49.075 |  | 25.756 | 0.297 | 23.319 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 16.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 2
AA/62a-1 | SGBM31 | Feb 15 2016 3:35PM | Feb 16 2016 7:45PM | 48.568 | 47.855 |  | 23.364 | 0.713 | 24.491 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.8 | 14.0 | -100.0 | G35T2 | PJ 5605, PJ 5608 | 7, 7
Y/63-1 | SGBM31 | Jan 26 2016 8:22AM | Jan 26 2016 11:40PM | 49.650 | 49.075 |  | 18.890 | 0.575 | 30.185 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.3 | 15.0 | -100.0 | G45T2 | PJ 4928, PJ 4934 | 7, 8
X/63-1 | SGBM22 | Jan 18 2016 9:13AM | Jan 18 2016 8:00PM | 49.940 | 49.075 |  | 20.788 | 0.865 | 28.287 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
W/63-1 | SGBM31 | Jan 20 2016 8:43AM | Jan 20 2016 9:05PM | 49.843 | 49.075 |  | 22.113 | 0.768 | 26.962 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
V/63-1 | SGBM31 | Jan 20 2016 8:29AM | Jan 20 2016 6:55PM | 50.491 | 49.075 |  | 23.832 | 1.416 | 25.243 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
U/63-1 | SGBM20 | Feb 12 2016 9:40AM | Feb 12 2016 5:30PM | 50.429 | 51.375 |  | 30.915 | -0.946 | 20.460 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.0 | 12.0 | -9.0 | G45T2 | 1, 2 | 6, 6
T2a/62-1 | SGBM20 | Feb 11 2016 3:05PM | Feb 11 2016 6:30PM | 51.399 | 51.375 |  | 33.411 | 0.024 | 17.964 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.9 | 10.0 | -100.0 | G45T2 | 1 | 10
Ea/43-1 | SGBM08 | Dec 8 2015 3:06PM | Dec 9 2015 6:32PM | 51.760 | 50.775 | 9 | 27.623 | 0.985 | 23.152 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
Ea/44-1 | SGBM08 | Dec 3 2015 3:30PM | Dec 4 2015 12:13AM | 51.816 | 50.775 |  | 25.434 | 1.041 | 25.341 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
E/45-1 | SGBM08 | Dec 3 2015 11:19AM | Dec 5 2015 1:31AM | 51.673 | 50.775 | 10, 30 | 16.502 | 0.898 | 34.273 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.1 | 20.0 | -100.0 | G45T2 | PJ 2624, PJ 2625, PJ 2628 | 8, 6, 6
Da/45-1 | SGBM08 | Dec 2 2015 1:10PM | Dec 3 2015 12:13AM | 51.733 | 50.775 |  | 23.283 | 0.958 | 27.492 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.1 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 5, 4
T/16-1 | SGBM03 | Dec 7 2015 8:00AM | Dec 10 2015 7:57PM | 55.827 | 54.475 | 9, 19.3 | 35.186 | 1.352 | 19.289 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
T/17-1 | SGBM03 | Dec 4 2015 5:30PM | Dec 5 2015 6:04PM | 55.798 | 54.475 | 9 | 36.350 | 1.323 | 18.125 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
T/18-1 | SGBM20 | Dec 8 2015 10:15AM | Dec 8 2015 10:10PM | 55.664 | 54.475 | 9 | 36.162 | 1.189 | 18.313 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 9.0 | 0.9 | G45T2 | 1, 2 | 7, 2
T/19-1 | SGBM03 | Dec 10 2015 6:30PM | Dec 11 2015 7:45PM | 55.920 | 54.475 | 9 | 36.231 | 1.445 | 18.244 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.1 | 11.0 | -100.0 | G45T2 | 1, 2 | 6, 5
M6a/54-1 | SGBM08 | Jan 19 2016 11:35AM | Jan 20 2016 7:55PM | 51.948 | 51.275 |  | 20.160 | 0.673 | 31.115 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.7 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
N/59-1 | SGBM31 | Mar 1 2016 2:40PM | Mar 2 2016 7:30PM | 52.140 | 49.075 |  | 17.547 | 3.065 | 31.528 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.9 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
N/59-2 | SGBM31 | Feb 29 2016 11:20AM | Feb 29 2016 8:40PM | 52.138 | 49.075 |  | 17.908 | 3.063 | 31.167 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
N/59-3 | SGBM31 | Mar 2 2016 9:30AM | Mar 2 2016 9:50PM | 52.136 | 49.075 |  | 17.134 | 3.061 | 31.941 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.1 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 7, 2
N/59-4 | SGBM31 | Feb 25 2016 10:50AM | Feb 25 2016 9:30PM | 52.039 | 49.075 |  | 17.794 | 2.964 | 31.281 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.8 | 17.0 | -100.0 | G45T2 | pj6024, pj6027 | 9, 8
N/59-5 | SGBM31 | Feb 25 2016 11:30AM | Feb 26 2016 4:30PM | 52.081 | 49.075 |  | 17.469 | 3.006 | 31.606 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.0 | 19.0 | -14.0 | G45T2 | pj6045, pj6050 | 10, 9
N/59-6 | SGBM31 | Mar 4 2016 8:30AM | Mar 7 2016 10:10PM | 52.038 | 49.075 |  | 17.261 | 2.963 | 31.814 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.1 | 17.0 | 20.9 | G45T2 | pj6416, pj6419 | 8, 9
N/59-7 | SGBM31 | Mar 4 2016 9:15AM | Mar 4 2016 8:10PM | 52.062 | 49.075 |  | 17.440 | 2.987 | 31.635 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.0 | 18.0 | 28.8 | G45T2 | 1, 2 | 8, 10
N/59-8 | SGBM31 | Feb 29 2016 11:45AM | Mar 1 2016 9:55PM | 51.994 | 49.075 |  | 17.607 | 2.919 | 31.468 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.9 | 17.0 | -100.0 | G45T2 | pj6226, pj6228 | 8, 9
T/59-1 | SGBM31 | Feb 26 2016 11:00AM | Feb 27 2016 2:30AM | 51.950 | 49.075 |  | 23.309 | 2.875 | 25.766 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.4 | 16.0 | -11.4 | G45T2 | 1, 2 | 8, 8
T/59-2 | SGBM15 | Feb 29 2016 2:40PM | Mar 2 2016 12:00AM | 52.041 | 49.075 |  | 23.671 | 2.966 | 25.404 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T/59-3 | SGBM31 | Mar 3 2016 8:30AM | Mar 3 2016 8:15PM | 52.031 | 49.075 |  | 23.380 | 2.956 | 25.695 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T/59-4 | SGBM31 | Feb 24 2016 11:30AM | Feb 25 2016 6:15PM | 52.078 | 49.075 |  | 23.709 | 3.003 | 25.366 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 15.0 | -11.2 | G45T2 | pj6008, pj6009 | 8, 7
T/59-5 | SGBM31 | Feb 24 2016 10:40AM | Feb 24 2016 10:40PM | 52.014 | 49.075 |  | 23.768 | 2.939 | 25.307 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.2 | 16.0 | 4.8 | G45T2 | 1, 2 | 6, 10
T/59-6 | SGBM31 | Mar 3 2016 11:50AM | Mar 3 2016 6:55PM | 52.011 | 49.075 |  | 23.297 | 2.936 | 25.778 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T/59-7 | SGBM31 | Feb 26 2016 10:30AM | Feb 27 2016 2:30AM | 52.073 | 49.075 |  | 23.575 | 2.998 | 25.500 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 16.0 | -11.3 | G45T2 | 1, 2 | 8, 8
T/59-8 | SGBM15 | Feb 29 2016 2:15PM | Mar 1 2016 2:45PM | 52.073 | 49.075 |  | 23.167 | 2.998 | 25.908 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.4 | 15.0 | -100.0 | G45T2 | pj6206, pj6207 | 8, 7
T1b/49-1 | SGBM31 | Mar 14 2016 2:00PM | Mar 14 2016 9:35PM | 51.777 | 51.175 |  | 24.926 | 0.602 | 26.249 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.6 | 15.0 | 29.3 | G45T2 | 1, 2 | 8, 7
T1b/50-1 | SGBM31 | Mar 15 2016 9:30AM | Mar 15 2016 6:30PM | 51.777 | 51.175 |  | 25.189 | 0.602 | 25.986 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 15.0 | 30.6 | G45T2 | pj6748, pj6750 | 7, 8
T1b/51-1 | SGBM15 | Mar 3 2016 9:30AM | Mar 3 2016 10:00PM | 51.899 | 51.375 |  | 24.391 | 0.524 | 26.984 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T1b/52-1 | SGBM23 | Mar 1 2016 5:00PM | Mar 2 2016 3:15PM | 51.934 | 51.375 |  | 24.322 | 0.559 | 27.053 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T1b/53-1 | SGBM23 | Feb 29 2016 5:25PM | Mar 1 2016 4:20PM | 51.983 | 51.375 |  | 24.995 | 0.608 | 26.380 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.7 | 15.0 | -100.0 | G45T2 | pj6211, pj6214 | 8, 7
T1b/54-1 | SGBM31 | Feb 27 2016 8:30AM | Feb 27 2016 3:50PM | 51.950 | 51.075 |  | 24.324 | 0.875 | 26.751 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 15.0 | -100.0 | G45T2 | pj6117, pj6126 | 8, 7
T1b/56-1 | SGBM08 | Feb 23 2016 10:00AM | Feb 23 2016 11:50PM | 51.922 | 51.375 |  | 26.231 | 0.547 | 25.144 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 12.0 | -100.0 | G45T2 | 1, 2 | 7, 5
T1b/57-1 | SGBM05 | Feb 17 2016 2:15PM | Feb 18 2016 8:50PM | 51.914 | 51.375 |  | 25.342 | 0.539 | 26.033 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
T1b/61-1 | SGBM31 | Feb 22 2016 4:00PM | Feb 22 2016 11:00PM | 51.996 | 50.775 |  | 32.255 | 1.221 | 18.520 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.2 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
T2a/53-1 | SGBM20 | Jan 27 2016 10:16AM | Jan 27 2016 7:45PM | 51.920 | 51.375 |  | 27.001 | 0.545 | 24.374 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.8 | 16.0 | -100.0 | G45T2 | PJ 4971, PJ 4974 | 8, 8
T2a/54-1 | SGBM20 | Feb 4 2016 10:03AM | Feb 4 2016 5:25PM | 51.852 | 51.375 |  | 24.761 | 0.477 | 26.614 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 15.0 | -100.0 | G45T2 | 5287, 5291 | 8, 7
T2a/57-1 | SGBM20 | Jan 29 2016 4:50PM | Jan 30 2016 5:45PM | 51.833 | 51.375 |  | 26.591 | 0.458 | 24.784 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.0 | 15.0 | -100.0 | G45T2 | PJ 5132, PJ 5139 | 8, 7
T2a/61-1 | SGBM20 | Feb 10 2016 4:25PM | Feb 11 2016 12:25PM | 51.908 | 51.375 |  | 28.182 | 0.533 | 23.193 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
U/33a-1 | SGBM20 | Jan 13 2016 3:00PM | Jan 14 2016 9:35PM | 52.345 | 51.325 |  | 36.047 | 1.015 | 15.278 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 6.8 | 9.0 | -100.0 | G45T2 | PJ 4404 | 9
Ua/41-1 | SGBM22 | Jan 4 2016 5:20PM | Jan 6 2016 2:15PM | 52.102 | 50.525 |  | 24.491 | 1.577 | 26.034 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 14.0 | -100.0 | G45T2 | PJ 4028, PJ 4031 | 7, 7
Ua/41-2 | SGBM22 | Jan 9 2016 9:35AM | Jan 9 2016 8:05PM | 52.034 | 50.525 |  | 24.433 | 1.509 | 26.092 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.5 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
AB/32-1 | SGBM22 | Dec 19 2015 8:30AM | Dec 18 2015 4:17PM | 49.658 | 48.475 |  | 32.169 | 1.183 | 16.306 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 7.2 | 11.0 | -100.0 | G35T2 | 1 | 11
Ma/61-1 | SGBM08 | Dec 30 2015 4:00PM | Dec 31 2015 7:00PM | 51.900 | 50.075 |  | 21.780 | 1.825 | 28.295 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.5 | 16.0 | -12.5 | G45T2 | PJ 3807, PJ 3810 | 8, 8
Ma/62-1 | SGBM08 | Dec 19 2015 5:21PM | Dec 21 2015 8:26PM | 52.356 | 50.075 |  | 20.156 | 2.281 | 29.919 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.2 | 18.0 | 36.2 | G45T2 | 1, 2 | 8, 10
Ma/63-1 | SGBM02 | Dec 12 2015 5:01PM | Dec 14 2015 10:46PM | 52.279 | 50.075 |  | 20.652 | 2.204 | 29.423 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.0 | 17.0 | 30.8 | G45T2 | 1, 2, 3 | 6, 6, 5
Ma/64-1 | SGBM02 | Dec 12 2015 5:05PM | Dec 13 2015 12:58AM | 52.154 | 50.075 |  | 20.724 | 2.079 | 29.351 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.0 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
M/53-1 | SGBM02 | Dec 2 2015 8:35AM | Dec 3 2015 2:11AM | 51.857 | 51.375 | 9 | 24.528 | -51.375 | 26.847 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 16.0 | 34.9 | G45T2 | 1, 2 | 8, 8
M/54-1 | SGBM02 | Dec 1 2015 1:00PM | Dec 2 2015 3:25AM | 51.645 | 51.375 |  | 24.684 | 0.270 | 26.691 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
M/55-1 | SGBM02 | Dec 1 2015 8:00AM | Dec 1 2015 9:30PM | 51.625 | 51.375 |  | 24.398 | 0.250 | 26.977 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 2
La/62-1 | SGBM02 | Dec 4 2015 4:34PM | Dec 5 2015 7:40PM | 52.166 | 50.075 | 10 | 15.660 | 2.091 | 34.415 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 15.2 | 20.0 | -100.0 | G45T2 | PJ 2654, PJ 2657 | 12, 8
La/63-1 | SGBM02 | Dec 10 2015 8:05PM | Dec 11 2015 9:45PM | 52.343 | 50.075 |  | 20.943 | 2.268 | 29.132 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.9 | 17.0 | 4.1 | G45T2 | 1, 2 | 10, 7
La/64-1 | SGBM02 | Dec 10 2015 1:20PM | Dec 10 2015 8:30PM | 52.334 | 50.075 | 11 | 20.834 | 2.259 | 29.241 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.9 | 21.0 | -100.0 | G45T2 | PJ 2913, PJ 2917, PJN2924 | 9, 8, 4
M4/59-1 | SGBM08 | Jan 7 2016 5:45PM | Jan 8 2016 6:03PM | 51.765 | 51.075 |  | 19.124 | 0.690 | 31.951 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.1 | 17.0 | 20.4 | G45T2 | 1, 2, 3 | 7, 5, 5
X8/Y6a-1 | SGBM18 | Nov 19 2015 1:00PM | Nov 19 2015 9:44PM | 55.576 | 54.625 |  | 47.281 | 0.951 | 7.344 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 3.2 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
X1/Y8-1 | SGBM18 | Dec 4 2015 4:00PM | Dec 5 2015 9:32PM | 55.748 | 55.075 | 9 | 30.195 | 0.673 | 24.880 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.0 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
X2/Y8-1 | SGBM18 | Dec 4 2015 4:45PM | Dec 7 2015 12:05PM | 55.708 | 55.075 | 9 | 31.766 | 0.633 | 23.309 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
X0/Y1-1 | SGBM21 | Dec 26 2015 8:00AM | Dec 26 2015 5:29PM | 56.316 | 54.475 |  | 23.448 | 1.841 | 31.027 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.7 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 5, 4
X0/Y2-1 | SGBM21 | Dec 21 2015 8:45PM | Dec 22 2015 10:38PM | 55.636 | 55.075 |  | 29.926 | 0.561 | 25.149 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 18.0 | -100.0 | G35T2 | 1, 2 | 11, 7
X0/Y3-1 | SGBM21 | Dec 23 2015 8:00AM | Dec 23 2015 10:36PM | 55.610 | 55.075 |  | 30.963 | 0.535 | 24.112 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 3, 5
X0/Y4-1 | SGBM21 | Dec 19 2015 2:45PM | Dec 22 2015 3:57PM | 55.695 | 54.625 |  | 25.593 | -54.625 | 29.032 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.8 | 20.0 | 55.9 | G35T2 | 1, 2, 3 | 7, 7, 6
X0/Y5-1 | SGBM21 | Dec 19 2015 2:00PM | Dec 21 2015 6:14PM | 55.749 | 54.625 |  | 25.841 | 1.124 | 28.784 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.7 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 3
X0/Y6-1 | SGBM03 | Dec 17 2015 2:15PM | Dec 18 2015 8:19PM | 55.761 | 54.625 |  | 29.579 | 1.136 | 25.046 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 9, 3
X0/Y7-1 | SGBM03 | Dec 17 2015 2:55PM | Dec 18 2015 1:04AM | 55.747 | 55.075 |  | 27.014 | 0.672 | 28.061 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 20.0 | 61.3 | G35T2 | 1, 2, 3 | 8, 8, 4
X0/Y8-1 | SGBM03 | Dec 17 2015 3:35PM | Dec 18 2015 4:52PM | 55.933 | 55.075 |  | 26.956 | -55.075 | 28.119 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 17.0 | -100.0 | G35T2 | Pending, 2 | 9, 8
X0/Y9-1 | SGBM21 | Dec 18 2015 7:15PM | Dec 19 2015 8:12PM | 56.246 | 54.475 |  | -24.400 | 1.771 | 78.875 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 34.9 | 12.0 | -100.0 | G35T2 | 1 | 12
X1/Y9-1 | SGBM21 | Dec 11 2015 8:00AM | Dec 12 2015 1:10AM | 55.998 | 54.475 | 9 | 33.313 | -54.475 | 21.162 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.4 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
X2/Y9-1 | SGBM21 | Dec 10 2015 7:30PM | Dec 11 2015 10:30PM | 55.730 | 54.475 | 9 | -21.100 | -54.475 | 75.575 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 33.4 | 11.0 | -100.0 | G35T2 | 1, 2 | 6, 5
X3/Y9-1 | SGBM21 | Dec 14 2015 1:00PM | Dec 14 2015 11:30PM | 55.727 | 54.475 |  | 32.198 | 1.252 | 22.277 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
X4/Y9-1 | SGBM21 | Dec 14 2015 1:35PM | Dec 15 2015 1:45AM | 55.756 | 54.475 |  | 33.317 | 1.281 | 21.158 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 11.5 | -100.0 | G35T2 | 1 | 11.5
X5/Y9-1 | SGBM21 | Jan 23 2016 10:30AM | Jan 23 2016 4:10PM | 55.967 | 54.475 |  | 33.035 | 1.492 | 21.440 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.5 | 11.0 | -100.0 | G35T2 | 1, 2 | 6, 5
X6/Y8-1 | SGBM21 | Dec 7 2015 3:10PM | Dec 8 2015 3:22PM | 55.583 | 55.075 | 9 | 32.742 | 0.508 | 22.333 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 12.0 | -9.9 | G35T2 | 1, 2 | 6, 6
X6/Y8a-1 | SGBM21 | Jan 9 2016 3:00PM | Jan 9 2016 9:30PM | 55.787 | 55.075 |  | 33.923 | 0.712 | 21.152 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.3 | 11.5 | -100.0 | G35T2 | 1 | 11.5
X6/Y9-1 | SGBM21 | Dec 15 2015 8:00AM | Dec 15 2015 6:43PM | 55.799 | 54.475 |  | -19.300 | 1.324 | 73.775 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 32.6 | 11.0 | -100.0 | G35T2 | 1, 2 | 6, 5
X7/Y8-1 | SGBM21 | Dec 7 2015 3:55PM | Dec 8 2015 10:52AM | 55.324 | 54.975 | 9, 18.3 | 32.719 | 0.349 | 22.256 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 12.0 | 2.2 | G35T2 | 1, 2 | 6, 6
X7/Y9-1 | SGBM21 | Dec 15 2015 2:00PM | Dec 15 2015 9:07PM | 55.979 | 54.475 |  | 32.372 | -54.475 | 22.103 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
X8/Y8-1 | SGBM21 | Dec 8 2015 3:05PM | Dec 8 2015 8:07PM | 55.420 | 54.975 | 9 | 32.900 | 0.445 | 22.075 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.8 | 12.0 | 2.2 | G35T2 | 1 | 12
X8/Y9-1 | SGBM21 | Dec 16 2015 8:00AM | Dec 16 2015 8:47PM | 55.138 | 54.475 |  | 35.138 | 0.663 | 19.337 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 11.0 | -100.0 | G35T2 | 1, 2 | 6, 5
X9/Y9-1 | SGBM21 | Dec 16 2015 10:00AM | Dec 16 2015 5:36PM | 55.682 | 54.475 |  | 36.338 | 1.207 | 18.137 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.0 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
X10/Y8-1 | SGBM21 | Dec 9 2015 1:15PM | Dec 10 2015 1:08PM | 55.758 | 55.075 | 9 | 31.899 | 0.683 | 23.176 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 12.0 | 17.2 | G35T2 | 1, 2 | 6, 6
X10/Y9-1 | SGBM21 | Dec 16 2015 9:10AM | Dec 16 2015 3:37PM | 55.525 | 54.475 |  | 35.833 | 1.050 | 18.642 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.2 | 10.0 | -100.0 | G35T2 | 1, 2 | 5, 5
X6/Y1-1 | SGBM18 | Dec 10 2015 4:22PM | Dec 12 2015 3:00PM | 55.505 | 55.075 |  | 21.901 | 0.430 | 33.174 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.7 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 6, 6
X7/Y1-1 | SGBM21 | Dec 17 2015 9:30AM | Dec 17 2015 6:00PM | 55.519 | 55.075 |  | 21.895 | 0.444 | 33.180 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.7 | 21.0 | -100.0 | G35T2 | 3281, 3282, 3289 | 6, 8, 7
X8/Y1-1 | SGBM21 | Dec 17 2015 5:00PM | Dec 18 2015 3:37PM | 55.428 | 54.975 |  | -33.200 | 0.453 | 88.175 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 39.0 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 6
X9/Y1-1 | SGBM21 | Dec 17 2015 4:19PM | Dec 20 2015 1:16AM | 55.557 | 55.075 |  | 23.703 | 0.482 | 31.372 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.9 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 9, 10, 2
X10/Y1-1 | SGBM20 | Dec 22 2015 9:00PM | Dec 24 2015 12:23AM | 55.749 | 55.075 |  | 24.781 | 0.674 | 30.294 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.4 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 9, 3
R/6-1 | SGBM21 | Dec 28 2015 10:00PM | Dec 29 2015 11:07AM | 55.741 | 55.075 |  | 35.933 | 0.666 | 19.142 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 12.0 | -100.0 | G35T2 | 1, 2 | 6, 6
ER-1 | SGBM03 | Dec 30 2015 10:00PM | Dec 31 2015 2:25PM | 59.498 | 57.375 |  | 29.238 | 2.123 | 28.137 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 6, 5
ER-2 | SGBM03 | Jan 4 2016 3:00PM | Jan 4 2016 7:20PM | 59.407 | 57.375 |  | 29.578 | 2.032 | 27.797 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 19.0 | 54.7 | G35T2 | 1, 2, 3 | 8, 7, 4
ER-3 | SGBM03 | Jan 5 2016 2:00PM | Jan 5 2016 11:40PM | 59.447 | 57.375 |  | 29.627 | 2.072 | 27.748 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 9, 4
ER-4 | SGBM03 | Jan 8 2016 9:00AM | Jan 8 2016 4:22PM | 59.362 | 57.375 |  | 29.222 | 1.987 | 28.153 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 2
ER-5 | SGBM03 | Jan 2 2016 12:00PM | Jan 2 2016 5:45PM | 59.528 | 57.375 |  | 29.703 | 2.153 | 27.672 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 21.0 | 71.8 | G35T2 | 1, 2, 3 | 10, 7, 4
ER-6 | SGBM03 | Jan 7 2016 9:25AM | Jan 7 2016 5:55PM | 59.440 | 57.375 |  | 29.935 | 2.065 | 27.440 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.1 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 2
ER-7 | SGBM03 | Jan 8 2016 9:00AM | Jan 9 2016 2:02PM | 60.324 | 57.375 |  | 29.724 | 2.949 | 27.651 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 9, 2
ER-8 | SGBM21 | Dec 31 2015 9:00AM | Dec 31 2015 3:00PM | 59.450 | 57.375 |  | 29.725 | 2.075 | 27.650 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 16.0 | 31.0 | G35T2 | 1, 2, 3 | 6, 5, 5
ER-9 | SGBM21 | Jan 7 2016 9:30AM | Jan 7 2016 4:09PM | 59.358 | 57.375 |  | 29.731 | 1.983 | 27.644 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
ER-10 | SGBM21 | Jan 8 2016 11:00AM | Jan 8 2016 7:40PM | 59.524 | 57.375 |  | -30.300 | 2.149 | 87.675 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 38.7 | 23.0 | -53.5 | G35T2 | 1, 2, 3 | 8, 10, 5
ER-11 | SGBM03 | Dec 31 2015 3:00PM | Dec 31 2015 11:10PM | 59.568 | 57.375 |  | 29.695 | 2.193 | 27.680 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 18.0 | -100.0 | G35T2 | 1, 2 | 10, 8
ER-12 | SGBM03 | Jan 2 2016 4:00PM | Jan 2 2016 11:45PM | 59.762 | 57.375 |  | 29.785 | 2.387 | 27.590 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 17.0 | -100.0 | G35T2 | 1, 2 | 8, 9
ER-13 | SGBM03 | Jan 5 2016 9:00AM | Jan 5 2016 2:00PM | 59.585 | 57.375 |  | 29.610 | 2.210 | 27.765 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 17.0 | -100.0 | G35T2 | 1, 2 | 9, 8
ER-14 | SGBM03 | Jan 6 2016 9:00AM | Jan 6 2016 3:38PM | 59.593 | 57.375 |  | 29.643 | 2.218 | 27.732 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 17.0 | -100.0 | G35T2 | 1, 2 | 8, 9
ER-15 | SGBM21 | Dec 31 2015 9:00AM | Dec 31 2015 8:25PM | 59.600 | 57.375 |  | 29.650 | 2.225 | 27.725 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
ER-16 | SGBM21 | Jan 4 2016 3:00PM | Jan 4 2016 9:45PM | 59.454 | 57.375 |  | 29.598 | 2.079 | 27.777 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 18.0 | 46.7 | G35T2 | 1, 2 | 10, 8
ER-17 | SGBM21 | Jan 5 2016 1:00PM | Jan 5 2016 8:15PM | 59.500 | 57.375 |  | 29.348 | 2.125 | 28.027 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
ER-18 | SGBM21 | Jan 2 2016 1:00PM | Jan 2 2016 9:35PM | 59.500 | 57.375 |  | 29.742 | 2.125 | 27.633 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 17.0 | -100.0 | G35T2 | 1, 2 | 8, 9
ER-19 | SGBM03 | Jan 6 2016 1:00PM | Jan 6 2016 10:37PM | 59.358 | 57.375 |  | 29.205 | 1.983 | 28.170 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 4
ER-20 | SGBM21 | Jan 2 2016 12:00PM | Jan 2 2016 4:05PM | 59.429 | 57.375 |  | 29.659 | 2.054 | 27.716 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 17.0 | -100.0 | G35T2 | PJ 3857, PJ 3859 | 9, 8
Xa/Y8-1 | SGBM21 | Jan 13 2016 9:00AM | Jan 14 2016 10:50AM | 55.797 | 54.275 |  | 30.107 | 1.522 | 24.168 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 13.0 | -10.7 | G35T2 | 1, 2 | 7, 6
Xa/Y9-1 | SGBM21 | Jan 13 2016 9:50AM | Jan 14 2016 5:10PM | 55.859 | 54.275 |  | 31.241 | 1.584 | 23.034 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.2 | 12.0 | -10.2 | G35T2 | 1, 2 | 6, 6
Xa/Y7-1 | SGBM03 | Jan 16 2016 8:00AM | Jan 16 2016 3:30PM | 55.756 | 54.275 |  | 30.072 | 1.481 | 24.203 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Xa/Y6-1 | SGBM03 | Jan 14 2016 4:45PM | Jan 15 2016 6:35PM | 55.837 | 54.275 |  | 30.011 | 1.562 | 24.264 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 13.0 | 21.3 | G35T2 | 1, 2 | 7, 6
Xa/Y5-1 | SGBM21 | Jan 21 2016 12:00PM | Jan 21 2016 7:00PM | 55.746 | 54.275 |  | 29.879 | 1.471 | 24.396 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.8 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 2
Xa/Y8-2 | SGBM21 | Jan 18 2016 8:40AM | Jan 20 2016 10:40PM | 55.885 | 54.275 |  | 30.081 | 1.610 | 24.194 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.7 | 17.0 | 59.0 | G35T2 | 1, 2 | 12, 5
Xa/Y9-2 | SGBM20 | Jan 18 2016 8:00AM | Jan 18 2016 10:00PM | 55.870 | 54.275 |  | 31.213 | 1.565 | 23.062 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.2 | 18.0 | -10.2 | G35T2 | 1, 2, 3, 4 | 6, 6, 3, 3
Xa/Ya-1 | SGBM21 | Feb 11 2016 9:32AM | Feb 11 2016 8:50PM | 56.215 | 54.175 |  | 27.923 | 2.040 | 26.252 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 21.0 | -100.0 | G35T2 | PJ 5412, PJ 5418, PJ 5421 | 8, 8, 5
Xa/Ya-2 | SGBM21 | Feb 13 2016 8:15AM | Feb 13 2016 3:05PM | 56.016 | 54.175 |  | 27.716 | 1.841 | 26.459 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.7 | 19.0 | -11.7 | G35T2 | PJ 5473, PJ 5475, PJ 5482 | 8, 8, 3
Xa/Y0-1 | SGBM21 | Feb 3 2016 10:05AM | Feb 3 2016 9:00PM | 56.167 | 54.175 |  | 28.022 | 1.992 | 26.153 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 16.0 | -100.0 | G35T2 | PJ 5349, PJ 5252 | 8, 8
Xa/Y0-2 | SGBM21 | Feb 10 2016 8:18AM | Feb 10 2016 4:45PM | 55.208 | 54.175 |  | 27.894 | 1.033 | 26.281 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 16.0 | -100.0 | G35T2 | PJ5345, PJ 5350 | 8, 8
Xa/Y1-1 | SGBM21 | Feb 2 2016 11:00AM | Feb 2 2016 8:05PM | 55.961 | 54.175 |  | 27.860 | 1.786 | 26.315 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
Xa/Y1-2 | SGBM21 | Feb 4 2016 11:05AM | Feb 4 2016 10:00PM | 56.110 | 54.175 |  | 28.061 | 1.935 | 26.114 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.5 | 16.0 | -100.0 | G35T2 | PJ 5309, PJ 5314 | 8, 8
Xa/Y2-1 | SGBM21 | Jan 29 2016 9:00AM | Jan 29 2016 5:30PM | 55.961 | 54.275 |  | 29.030 | 1.686 | 25.245 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.2 | 19.0 | 70.3 | G35T2 | 1, 2, 3 | 8, 7, 4
Xa/Y2-2 | SGBM21 | Jan 30 2016 9:00AM | Jan 30 2016 8:20PM | 55.839 | 54.275 |  | 28.933 | -54.275 | 25.342 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.2 | 21.0 | 87.6 | G35T2 | 1, 2 | 11, 10
Xa/Y3-1 | SGBM21 | Jan 27 2016 12:00PM | Jan 27 2016 8:00PM | 55.818 | 54.275 |  | 29.083 | 1.543 | 25.192 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.1 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 5
Xa/Y3-2 | SGBM21 | Jan 29 2016 1:30PM | Jan 29 2016 10:40PM | 55.904 | 54.275 |  | 29.140 | 1.629 | 25.135 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.1 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 5
Xa/Y4-1 | SGBM21 | Jan 27 2016 9:00AM | Jan 27 2016 1:45PM | 55.915 | 54.275 |  | 29.793 | 1.640 | 24.482 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.8 | 16.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 3
Xa/Y4-2 | SGBM21 | Jan 20 2016 10:00AM | Jan 20 2016 5:45PM | 55.787 | 54.275 |  | 30.013 | 1.512 | 24.262 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.7 | 17.0 | 58.6 | G35T2 | 1, 2 | 11, 6
Xa/Y5-2 | SGBM19 | Jan 26 2016 11:00AM | Jan 26 2016 7:05PM | 55.720 | 54.275 |  | 29.754 | 1.445 | 24.521 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.8 | 17.0 | -100.0 | G35T2 | 1, 2 | 8, 9
Xa/Y6-2 | SGBM21 | Jan 22 2016 2:00PM | Jan 23 2016 12:45AM | 55.771 | 54.275 |  | 30.160 | 1.496 | 24.115 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.7 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
Xa/Y7-2 | SGBM21 | Jan 21 2016 1:00PM | Jan 22 2016 10:25AM | 55.715 | 54.275 |  | 30.128 | 1.440 | 24.147 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 10.7 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
X0/Ya-1 | SGBM21 | Feb 12 2016 9:32AM | Feb 12 2016 7:35PM | 55.879 | 54.175 |  | 27.465 | 1.704 | 26.710 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.8 | 18.0 | -100.0 | G35T2 | PJ 5446, PJ 5449 | 10, 8
X0/Ya-2 | SGBM21 | Feb 17 2016 10:10AM | Feb 17 2016 11:05PM | 56.099 | 54.175 |  | 28.154 | 1.924 | 26.021 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.5 | 17.0 | -100.0 | G35T2 | PJ 5661, PJ 5668 | 8, 9
X1/Ya-1 | SGBM21 | Feb 15 2016 8:39AM | Feb 15 2016 4:10PM | 55.949 | 54.175 |  | 28.115 | 1.774 | 26.060 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.5 | 17.0 | -11.5 | G35T2 | PJ 5523, PJ 5528 | 8, 9
X1/Ya-2 | SGBM21 | Feb 22 2016 3:40PM | Feb 22 2016 7:10PM | 55.999 | 54.175 |  | 27.891 | 1.824 | 26.284 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 17.0 | -11.6 | G35T2 | PJ 5858, PJ 5861 | 9, 8
X2/Ya-1 | SGBM17 | Feb 16 2016 10:35AM | Feb 16 2016 9:35PM | 55.865 | 54.175 |  | 27.895 | 1.690 | 26.280 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 20.0 | -100.0 | G35T2 | PJ 5617, PJ5619, PJ 5626 | 8, 8, 4
X3/Ya-1 | SGBM21 | Feb 18 2016 8:15AM | Feb 18 2016 5:45PM | 55.694 | 54.175 |  | 27.959 | 1.519 | 26.216 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 11.6 | 16.0 | -100.0 | G35T2 | PJ5696, PJ 5703 | 8, 8
X3/Ya-2 | SGBM21 | Feb 20 2016 9:12AM | Feb 20 2016 7:05PM | 55.698 | 54.175 |  | 47.513 | 1.523 | 6.662 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 2.9 | 22.0 | -100.0 | G35T2 | PJ5809, PJ5818, PJ 5825 | 10, 7, 5
N/1-1 | SGBM19 | Jan 21 2016 9:10AM | Jan 21 2016 6:45PM | 55.680 | 55.075 |  | 27.012 | 0.605 | 28.063 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 16.0 | 29.0 | G35T2 | 1, 2 | 8, 8
N/2-1 | SGBM19 | Jan 26 2016 1:00PM | Jan 26 2016 11:50PM | 55.763 | 55.075 |  | 24.795 | 0.688 | 30.280 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.4 | 17.0 | -100.0 | G35T2 | 1, 2 | 9, 8
M/1-1 | SGBM19 | Jan 22 2016 11:00AM | Jan 23 2016 12:10AM | 55.696 | 55.075 |  | 27.290 | 0.621 | 27.785 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 15.0 | -12.3 | G35T2 | 1, 2 | 8, 7
M/2-1 | SGBM19 | Jan 28 2016 9:00AM | Jan 28 2016 7:35PM | 55.722 | 55.075 |  | 24.694 | 0.647 | 30.381 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 13.4 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 4
M/3-1 | SGBM19 | Jan 23 2016 7:40AM | Jan 23 2016 6:15PM | 55.733 | 55.075 |  | 27.116 | 0.658 | 27.959 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 15.0 | -100.0 | G35T2 | 1, 2 | 8, 7
M/4-1 | SGBM17 | Feb 4 2016 12:00PM | Feb 4 2016 8:30PM | 55.783 | 55.075 |  | 26.541 | 0.708 | 28.534 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.6 | 17.0 | -100.0 | G35T2 | PJ5302, PJ5307 | 8, 9
M/5-1 | SGBM17 | Feb 11 2016 10:00AM | Feb 11 2016 5:35PM | 55.615 | 55.075 |  | 27.115 | 0.540 | 27.960 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 17.0 | -100.0 | G35T2 | PJ5401, PJ5405 | 10, 7
M/6-1 | SGBM31 | Mar 29 2016 10:40AM | Mar 29 2016 11:15PM | 55.860 | 55.075 |  | 28.460 | 0.785 | 26.615 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 17.0 | -100.0 | G35T2 | pj7428, pj7431 | 10, 7
M/7-1 | SGBM22 | Feb 23 2016 12:05PM | Feb 23 2016 10:20PM | 55.896 | 55.075 |  | 28.315 | 0.821 | 26.760 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 16.0 | -100.0 | G35T2 | PJ 5927, PJ 5930 | 8, 8
M/8-1 | SGBM22 | Feb 27 2016 10:00AM | Feb 27 2016 7:45PM | 55.936 | 55.075 |  | 28.372 | 0.861 | 26.703 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 20.0 | -100.0 | G35T2 | PJ6140, PJ6146 | 10, 10
K/18-2 | SGBM20 | Nov 12 2015 2:00PM | Nov 12 2015 7:15PM | 53.735 | 51.375 |  | 24.617 | 2.360 | 26.758 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 14.0 | 18.4 | G45T2 | 1, 2 | 8, 6
Fa/33-1a | SGBM03 | Jan 9 2016 1:00PM | Jan 9 2016 8:10PM | 52.460 | 50.175 |  | 37.304 | 2.285 | 12.871 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.7 | 9.0 | -100.0 | G35T2 | 1 | 9
Fa/33-1b | SGBM16 | Jan 9 2016 8:00AM | Jan 9 2016 8:10PM | 52.392 | 50.175 |  | 37.492 | 2.217 | 12.683 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 5.6 | 8.0 | -100.0 | G35T2 | 1, 2 | 2, 6
Na/20a-1 | SGBM05 | Nov 18 2015 8:00AM | Nov 18 2015 11:29AM | 53.735 | 53.675 |  | 38.234 | 0.060 | 15.441 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 6.8 | 8.0 | -100.0 | G35T2 | 1 | 8
Ua/40-1 | SGBM23 | Jan 7 2016 11:00AM | Jan 7 2016 8:10PM | 52.106 | 51.325 |  | 26.267 | 0.781 | 25.058 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.1 | 14.0 | -100.0 | G35T2 | 1, 2 | 7, 7
Aa/56-1 | SGBM02 | Nov 17 2015 11:55AM | Nov 17 2015 8:55PM | 51.770 | 50.775 |  | 18.650 | 0.995 | 32.125 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 14.2 | 20.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 6, 6, 6, 2
Aa/57-1 | SGBM02 | Nov 20 2015 7:50AM | Nov 20 2015 9:01PM | 51.714 | 51.275 |  | 43.374 | 0.439 | 7.901 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 3.5 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 5
Aa/61-1 | SGBM02 | Nov 21 2015 7:30PM | Nov 22 2015 3:20PM | 51.468 | 51.075 |  | 23.710 | 0.393 | 27.365 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.1 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 6, 5
AAa/62a-1 | SGBM31 | Feb 10 2016 8:00AM | Feb 10 2016 6:10PM | 48.563 | 46.475 |  | 22.239 | 2.088 | 24.236 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.7 | 15.0 | -100.0 | G35T2 | 5354, 5358 | 8, 7
P/2-1 | SGBM31 | Mar 18 2016 11:00AM | Mar 19 2016 9:00PM | 55.674 | 55.075 |  | 27.524 | 0.599 | 27.551 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 16.0 | -100.0 | G35T2 | pj6960, pj6961 | 8, 8
P/7-1 | SGBM20 | Mar 16 2016 5:55PM | Mar 17 2016 5:10PM | 55.980 | 55.075 |  | 28.108 | 0.905 | 26.967 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 15.0 | 25.9 | G35T2 | c480018578, c480018581 | 10, 5
P/8-1 | SGBM20 | Mar 12 2016 8:00AM | Mar 12 2016 8:30PM | 55.884 | 55.075 |  | 29.413 | 0.809 | 25.662 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 16.0 | -100.0 | G35T2 | pj6672, pj6675 | 8, 8
P/9-1 | SGBM20 | Mar 14 2016 4:00PM | Mar 15 2016 2:30PM | 55.780 | 55.075 |  | 28.906 | 0.705 | 26.169 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.6 | 15.0 | -100.0 | G35T2 | pj6732, pj6738 | 8, 7
P/10-1 | SGBM23 | Mar 17 2016 2:00PM | Mar 18 2016 8:50PM | 55.900 | 51.075 |  | 23.896 | -51.075 | 27.179 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 20.0 | -12.0 | G35T2 | pj6923, pj6926 | 10, 10
R/8a-1 | SGBM19 | Mar 29 2016 2:30PM | Mar 30 2016 9:00PM | 55.930 | 55.075 |  | 28.306 | 0.855 | 26.769 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 16.0 | -100.0 | G35T2 | pj7462, pj7463 | 8, 8
R/9-1 | SGBM19 | Mar 29 2016 1:00PM | Mar 30 2016 6:10PM | 55.781 | 54.475 |  | 27.619 | 1.306 | 26.856 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 16.0 | -100.0 | G35T2 | pj7449, pj7451 | 8, 8
R/10-1 | SGBM31 | Mar 26 2016 4:15PM | Mar 28 2016 1:40PM | 55.823 | 54.475 |  | 27.174 | 1.348 | 27.301 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.1 | 14.0 | -100.0 | G35T2 | pj7334, pj7335 | 7, 7
R/11-1 | SGBM31 | Mar 24 2016 8:10PM | Mar 26 2016 3:20PM | 55.705 | 54.475 |  | 26.975 | 1.230 | 27.500 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 14.0 | 15.2 | G35T2 | pj7268, pj7269 | 7, 7
R/12-1 | SGBM31 | Mar 25 2016 8:00AM | Mar 26 2016 7:30PM | 55.720 | 54.475 |  | 27.483 | 1.245 | 26.992 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.9 | 14.0 | -100.0 | G35T2 | pj7287, pj7295 | 7, 7
R/13-1 | SGBM22 | Mar 25 2016 8:40AM | Mar 25 2016 11:30PM | 55.780 | 54.475 |  | 27.336 | 1.305 | 27.139 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.0 | 14.0 | -12.0 | G35T2 | pj7233, pj7238 | 7, 7
Q/13a-1 | SGBM23 | Mar 19 2016 3:15PM | Mar 19 2016 9:15PM | 55.855 | 55.075 |  | 28.283 | 0.780 | 26.792 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 14.0 | 18.3 | G35T2 | pj6962, pj6963 | 7, 7
L/2-1 | SGBM19 | Mar 17 2016 11:00AM | Mar 18 2016 5:10PM | 55.580 | 55.075 |  | -29.200 | 0.505 | 84.275 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 37.2 | 17.0 | -100.0 | G35T2 | pj6907, pj6912 | 8, 9
K/2-1 | SGBM31 | Mar 16 2016 1:00PM | Mar 17 2016 1:30PM | 55.508 | 55.075 |  | 27.125 | 0.433 | 27.950 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 16.0 | -100.0 | G35T2 | pj6853, pj6857 | 8, 8
J/2-1 | SGBM31 | Mar 17 2016 1:00PM | Mar 18 2016 3:15PM | 55.470 | 55.075 |  | 27.137 | 0.395 | 27.938 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 16.0 | -100.0 | G35T2 | pj6903, pj6904 | 8, 8
J/4-1 | SGBM22 | Mar 1 2016 8:10AM | Mar 1 2016 5:55PM | 55.540 | 54.275 |  | 26.459 | 1.265 | 27.816 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 17.0 | -100.0 | G35T2 | C480017647, C520125652 | 7, 10
J/4-2 | SGBM22 | Feb 26 2016 12:05PM | Feb 26 2016 7:05PM | 55.510 | 54.275 |  | 26.329 | 1.235 | 27.946 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 19.0 | -100.0 | G35T2 | PJ6060, PJ 6064, PJ 6074 | 8, 9, 2
J/4-3 | SGBM22 | Feb 25 2016 10:00AM | Feb 25 2016 9:40PM | 55.550 | 54.275 |  | 26.429 | 1.275 | 27.846 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 17.0 | -100.0 | G35T2 | PJ6025, PJ6028 | 8, 9
J/4-5 | SGBM22 | Mar 2 2016 11:15AM | Mar 2 2016 8:45PM | 55.480 | 54.275 |  | 26.196 | 1.205 | 28.079 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 17.0 | -12.4 | G35T2 | PJ 6264, PJ 6266 | 9, 8
J/4-6 | SGBM22 | Mar 1 2016 1:10PM | Mar 1 2016 6:50PM | 55.530 | 54.275 |  | 26.363 | 1.255 | 27.912 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 17.0 | -100.0 | G35T2 | C520125653, C480017657 | 7, 10
J/4-7 | SGBM22 | Mar 5 2016 8:12AM | Mar 5 2016 1:25PM | 55.555 | 54.275 |  | 26.279 | 1.280 | 27.996 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.4 | 18.0 | -100.0 | G35T2 | C480017867, C480017870 | 10, 8
J/4-9 | SGBM22 | Mar 3 2016 8:11AM | Mar 3 2016 3:00PM | 55.500 | 54.275 |  | 26.700 | 1.225 | 27.575 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.2 | 17.0 | -100.0 | G35T2 | PJ 6290, PJ 6292 | 9, 8
J/4-11 | SGBM22 | Mar 8 2016 1:00PM | Mar 8 2016 6:37PM | 55.490 | 54.275 |  | 47.379 | 1.215 | 6.896 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 3.0 | 18.0 | -100.0 | G35T2 | PJ 7756, PJ7789 | 8, 10
J/4-12 | SGBM22 | Mar 4 2016 8:10AM | Mar 4 2016 4:25PM | 55.524 | 54.275 |  | 26.433 | 1.249 | 27.842 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 12.3 | 17.0 | -100.0 | G35T2 | PJ 6336, PJ 6338 | 9, 8
H/2-1 | SGBM22 | Mar 16 2016 11:10AM | Mar 17 2016 11:00AM | 55.450 | 55.075 |  | -29.200 | 0.375 | 84.275 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 37.2 | 16.0 | -100.0 | G35T2 | pj6850, pj6851 | 8, 8
P/49a-1 | SGBM15 | Mar 2 2016 8:40AM | Mar 2 2016 7:45PM | 51.943 | 50.575 |  | 25.101 | 1.368 | 25.474 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 14.0 | -100.0 | G35T2 | pj 6258, pj6262 | 7, 7
Ta/45-1 | SGBM15 | Mar 4 2016 10:00AM | Mar 5 2016 8:20PM | 51.923 | 50.575 |  | 23.899 | 1.348 | 26.676 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 15.0 | -100.0 | G35T2 | 1, 2 | 8, 7
Ta/44-1 | SGBM31 | Mar 4 2016 10:30AM | Mar 5 2016 4:25PM | 51.963 | 50.575 |  | 30.071 | 1.388 | 20.504 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.1 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Ta/43-1 | SGBM31 | Mar 4 2016 11:15AM | Mar 5 2016 5:25PM | 52.120 | 50.575 |  | 29.959 | 1.545 | 20.616 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.1 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Tb/41-1 | SGBM31 | Mar 9 2016 10:15AM | Mar 10 2016 9:50PM | 52.289 | 50.575 |  | 31.535 | 1.714 | 19.040 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.4 | 15.0 | -100.0 | G35T2 | 1, 2 | 9, 6
Tb/42-1 | SGBM31 | Mar 12 2016 11:20AM | Mar 12 2016 8:50PM | 52.230 | 50.575 |  | 30.841 | 1.655 | 19.734 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Tb/43-1 | SGBM31 | Mar 12 2016 9:00AM | Mar 12 2016 9:55PM | 52.062 | 50.575 |  | 29.910 | 1.487 | 20.665 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.1 | 13.0 | -9.1 | G35T2 | 1, 2 | 7, 6
Tb/44-1 | SGBM31 | Mar 12 2016 10:00AM | Mar 12 2016 10:55PM | 51.972 | 50.575 |  | 31.297 | 1.397 | 19.278 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.5 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Tb/45-1 | SGBM31 | Mar 14 2016 8:30AM | Mar 14 2016 8:25PM | 51.827 | 50.575 |  | 25.077 | 1.252 | 25.498 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.3 | 15.0 | -100.0 | G35T2 | 1, 2 | 8, 7
Ta/41-1 | SGBM15 | Mar 7 2016 9:45AM | Mar 8 2016 7:54PM | 52.477 | 50.575 |  | 30.860 | 1.902 | 19.715 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.7 | 12.0 | -100.0 | G35T2 | pj6462, pj6465 | 6, 6
Ta/42-1 | SGBM31 | Mar 11 2016 8:30AM | Mar 11 2016 9:20PM | 52.273 | 50.575 |  | 30.420 | 1.698 | 20.155 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 8.9 | 13.0 | -8.9 | G35T2 | 1, 2 | 7, 6
Na/47-1 | SGBM31 | Mar 10 2016 10:00AM | Mar 10 2016 7:25PM | 51.937 | 50.175 |  | 25.612 | 1.762 | 24.563 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.9 | 14.0 | -10.8 | G35T2 | PJ 6566, PJ 6569 | 7, 7
M/Yb-1 | SGBM31 | Mar 23 2016 2:00PM | Mar 23 2016 9:05PM | 55.720 | 55.075 |  | 31.440 | 0.645 | 23.635 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.4 | 13.0 | 24.5 | G35T2 | pj7122, pj7123 | 7, 6
L/Yb-1 | SGBM31 | Mar 23 2016 5:00PM | Mar 23 2016 10:30PM | 55.578 | 54.475 |  | 31.091 | 1.103 | 23.384 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.3 | 13.0 | -100.0 | G35T2 | pj7124, pj7125 | 7, 6
K/Yb-1 | SGBM31 | Mar 22 2016 3:30PM | Mar 23 2016 3:15PM | 55.699 | 54.475 |  | 31.425 | 1.224 | 23.050 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | -100.0 | G35T2 | pj7102, pj7103 | 7, 7
J/Yb-1 | SGBM31 | Mar 21 2016 11:00AM | Mar 22 2016 10:00PM | 55.730 | 54.475 |  | 32.169 | 1.255 | 22.306 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.9 | 17.0 | 72.5 | G35T2 | pj7070, pj7071 | 8, 9
H/Yb-1 | SGBM31 | Mar 24 2016 2:30PM | Mar 24 2016 10:30PM | 55.605 | 54.475 |  | 31.395 | 1.130 | 23.080 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 15.0 | -100.0 | G35T2 | pj7173, pj7174 | 8, 7
Ga/Yb-1 | SGBM31 | Mar 24 2016 3:00PM | Mar 25 2016 4:20PM | 55.456 | 54.475 |  | 31.349 | 0.981 | 23.126 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 10.2 | 14.0 | -100.0 | G35T2 | pj7194, pj7198 | 7, 7
L/18-1 | SGBM31 | Mar 28 2016 9:00AM | Mar 29 2016 6:00PM | 55.773 | 52.175 |  | 31.787 | 3.598 | 20.388 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.0 | 13.0 | -100.0 | G35T2 | pj7389, pj7392 | 7, 6
Ka/18-1 | SGBM19 | Apr 1 2016 4:30PM | Apr 4 2016 5:05PM | 55.675 | 51.375 |  | 47.555 | 4.300 | 3.820 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 1.7 | 13.0 | -100.0 | G35T2 | pj7575, pj7576 | 7, 6
Ka/18-2 | SGBM19 | Apr 2 2016 9:20AM | Apr 4 2016 6:00PM | 55.940 | 51.375 |  | 24.637 | 4.565 | 26.738 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 11.8 | 13.0 | -100.0 | G35T2 | pj7579, pj7581 | 7, 6
K/18-1 |  |  |  | 0.000 | 51.375 |  | 0.000 | 0.000 | 51.375 |  | 0.0 | 0.0 | 11T16 | T10-225 |  | 22.7 | 0.0 | 0.0 | G35T2
Na/42-1a | SGBM20 | Apr 11 2016 10:20AM | Apr 11 2016 7:21PM | 52.027 | 50.575 |  | 43.891 | 1.452 | 6.684 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 3.0 | 12.0 | 6.3 | G35T2 | pj7745, pj7746 | 8, 4
Na/42-1b | SGBM20 | Apr 11 2016 10:55AM | Apr 11 2016 8:25PM | 52.897 | 50.575 |  | 30.064 | 2.322 | 20.511 |  | 0.0 | 0.0 | 11T16 | T10-225 | 12 | 9.1 | 12.0 | -100.0 | G35T2 | pj7749, pj7750 | 7, 5

## 900
Summary List for 1891651800-Parcel F
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
F/59-1 | SGBM17 | Aug 4 2015 8:00AM | Aug 5 2015 9:50PM | 51.980 | 50.375 | 8 | 8.335 | 1.605 | 42.040 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.7 | 38.0 | -100.0 | G45T2 | c480006473, c480006470, c480006475, c480006476 | 11, 5, 11, 11
F/59-2 | SGBM23 | Aug 25 2015 3:20PM | Sep 11 2015 11:15AM | 51.942 | 50.375 | 5.5, 40.5 | 8.310 | 1.567 | 42.065 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.8 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 8, 11, 2
F/59-3 | SGBM17 | Sep 12 2015 10:30AM | Sep 17 2015 10:00PM | 51.935 | 50.375 | 6, 31.8 | 8.372 | 1.560 | 42.003 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.7 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 10, 9, 9
K/26-1 |  | Aug 19 2015 4:00PM | Aug 21 2015 6:15AM | 53.497 | 51.425 | 9, 18, 25.3 | 28.963 | 2.422 | 22.462 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.3 | 22.0 | -100.0 | G45T2 | c480007386, c480007387 | 11, 11
K/26-2 | SGBM15 | Aug 14 2015 12:10PM | Aug 15 2015 6:15PM | 53.489 | 51.425 | 9 | 29.059 | 2.414 | 22.366 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 22.0 | -100.0 | G45T2 | c480007117, c480007115, c480007115 | 4, 12, 6
K/27-1 | SGBM20 | Aug 18 2015 5:00PM | Aug 19 2015 10:24AM | 53.517 | 51.425 | 9 | 28.728 | 2.442 | 22.697 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.4 | 22.0 | -100.0 | G45T2 | C170012392, C170012391, C480007284 | 8, 10, 4
K/27-2 | SGBM15 | Aug 21 2015 8:00AM | Aug 22 2015 3:30PM | 53.500 | 51.425 | 9, 17 | 29.700 | 2.075 | 21.725 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.8 | 23.0 | -13.8 | G45T2 | 1, 2, 3 | 5, 11, 7
L/22-1 | SGBM15 | Aug 12 2015 5:15PM | Aug 13 2015 10:30AM | 53.395 | 51.275 | 9, 20 | 31.430 | 2.120 | 19.845 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.6 | 17.0 | -100.0 | G35T2 | c480006949, c480006950 | 10, 7
L/22-2 | SGBM15 | Aug 18 2015 3:30PM | Aug 19 2015 3:00PM | 53.384 | 51.275 | 9, 17 | 31.544 | 2.109 | 19.731 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.6 | 16.0 | 27.4 | G35T2 | 1, 2, 3 | 11, 3, 2
L/23-1 | SGBM20 | Aug 14 2015 12:10PM | Aug 15 2015 3:40PM | 53.394 | 51.275 | 9, 22.4 | 31.614 | 2.119 | 19.661 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.5 | 17.0 | -100.0 | G35T2 | c480007103, c480007110 | 11.5, 5.5
L/23-2 | SGBM20 | Aug 20 2015 4:00PM | Aug 21 2015 11:40AM | 53.378 | 51.275 |  | 31.548 | 2.103 | 19.727 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.6 | 17.0 | -100.0 | G35T2 | 1, 2 | 11, 6
L/24-1 | SGBM20 | Aug 13 2015 4:00PM | Aug 14 2015 3:30PM | 53.407 | 50.975 | 9 | 31.155 | 2.432 | 19.820 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.6 | 15.0 | -100.0 | G35T2 | c480007004, c480007008 | 11, 4
L/24-2 | SGBM15 | Aug 18 2015 6:00PM | Aug 19 2015 1:44PM | 53.394 | 50.975 | 9 | 31.452 | 2.419 | 19.523 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.4 | 15.0 | -100.0 | G35T2 | C480007292, C480007293 | 11, 4
L/25-1 | SGBM15 | Aug 17 2015 5:45PM | Aug 18 2015 10:15AM | 53.414 | 50.975 | 9, 22 | 31.289 | 2.439 | 19.686 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.5 | 15.0 | -100.0 | G35T2 | c480007216, c480007217 | 11.5, 3.5
L/25-2 | SGBM15 | Aug 20 2015 6:00PM | Aug 22 2015 11:50AM | 53.445 | 50.975 | 9, 21 | 32.011 | 2.470 | 18.964 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.1 | 19.0 | -12.1 | G35T2 | 1, 2 | 11, 8
V/26-1 | SGBM16 | Aug 20 2015 2:00PM | Aug 21 2015 10:25AM | 49.778 | 47.575 |  | 28.196 | 2.203 | 19.379 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.3 | 19.0 | -100.0 | G35T2 | 1, 2 | 11, 8
V/26-2 | SGBM16 | Sep 8 2015 3:00PM | Sep 10 2015 1:00PM | 49.907 | 47.575 |  | 28.462 | 2.332 | 19.113 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.2 | 18.0 | -100.0 | G35T2 | 1, 2 | 7, 11
V/28-1 | SGBM16 | Aug 19 2015 9:30AM | Aug 20 2015 1:50PM | 49.799 | 47.575 |  | 28.374 | 2.224 | 19.201 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.2 | 18.0 | -100.0 | G35T2 | 1, 2 | 7, 11
V/28-2 | SGBM16 | Aug 24 2015 5:30PM | Aug 25 2015 2:26PM | 49.798 | 47.575 |  | 28.288 | 2.223 | 19.287 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.3 | 15.0 | -100.0 | G35T2 | 1, 2 | 4, 11
V/32-1 | SGBM18 | Aug 15 2015 4:00PM | Aug 17 2015 3:10PM | 49.789 | 47.575 | 9, 12.4 | 28.061 | 2.214 | 19.514 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.4 | 17.0 | -100.0 | G35T2 | 1, 2 | 11, 6
V/32-2 | SGBM16 | Aug 17 2015 3:00PM | Aug 19 2015 3:00PM | 49.795 | 47.575 | 9, 19.2 | 27.927 | 2.220 | 19.648 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.5 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
W/23-1 | SGBM18 | Aug 12 2015 11:30AM | Aug 15 2015 3:34PM | 49.768 | 48.075 | 9, 17.7 | 29.914 | 1.693 | 18.161 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 11.6 | 13.0 | -100.0 | G35T2 | 1, 2 | 11, 2
W/23-2 | SGBM16 | Aug 22 2015 1:00PM | Aug 24 2015 4:30PM | 49.779 | 48.075 |  | 28.345 | 1.704 | 19.730 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.6 | 16.0 | -100.0 | G35T2 | 1, 2 | 11, 5
W/23-3 | SGBM16 | Sep 14 2015 11:28AM | Sep 14 2015 6:20PM | 49.713 | 48.075 | 8 | 28.398 | 1.638 | 19.677 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.5 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 11, 1
X/35-1 | SGBM19 | Aug 17 2015 8:05AM | Aug 17 2015 4:40PM | 49.602 | 48.075 | 8 | 27.015 | 1.527 | 21.060 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.4 | 15.0 | 11.9 | G35T2 | c480007170, c480007178 | 11, 4
X/35-2 | SGBM19 | Aug 18 2015 1:20PM | Aug 19 2015 1:20PM | 49.617 | 48.075 | 8, 21.4 | 26.967 | 1.542 | 21.108 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.4 | 15.0 | -100.0 | G35T2 | c480007289, c480007291 | 11, 4
X/35-3 | SGBM03 | Aug 12 2015 9:30AM | Aug 12 2015 5:05PM | 49.627 | 48.075 |  | 26.727 | 1.552 | 21.348 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.6 | 17.0 | -100.0 | G35T2 | 1, 2 | 10, 7
X/38-1 | SGBM03 | Aug 15 2015 8:05AM | Aug 15 2015 6:30PM | 49.604 | 48.075 | 8 | 22.679 | 1.529 | 25.396 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.2 | 20.0 | -100.0 | G35T2 | c480007117, c480007119, c480007124 | 6, 12, 2
X/38-2 | SGBM19 | Aug 13 2015 8:05AM | Aug 13 2015 7:40PM | 49.624 | 48.075 | 8 | 22.757 | 1.549 | 25.318 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.1 | 18.0 | -100.0 | G35T2 | c480006990, c480006987 | 11, 7
X/38-3 | SGBM19 | Aug 17 2015 3:10PM | Aug 18 2015 1:35PM | 49.617 | 48.075 | 8, 19 | 22.629 | 1.542 | 25.446 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.2 | 18.0 | 11.2 | G35T2 | c480007227, c480007229 | 12, 6
Y/29-1 | SGBM16 | Aug 4 2015 9:30AM | Aug 4 2015 9:35PM | 49.951 | 48.075 | 9, 16.3 | 27.305 | 1.876 | 20.770 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 16.5 | -13.2 | G35T2 | 1, 2, 3 | 4, 11, 1.5
Y/29-2 | SGBM20 | Aug 6 2015 7:40AM | Aug 6 2015 5:15PM | 49.904 | 48.075 |  | 26.274 | 1.829 | 21.801 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.9 | 18.0 | -100.0 | G35T2 | 1, 2 | 8, 10
Y/29-3 | SGBM16 | Aug 8 2015 8:30AM | Aug 8 2015 5:25PM | 49.893 | 48.075 | 9, 18.4 | 27.651 | 1.818 | 20.424 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.0 | 22.0 | -13.0 | G35T2 | 1, 2 | 11, 11
Y/37-1 | SGBM21 | Sep 23 2015 7:00PM | Sep 25 2015 8:10PM | 49.374 | 48.075 | 8, 17 | 21.930 | 1.299 | 26.145 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 20.0 | -100.0 | G45T2 | c1700012734, c1700012735 | 10, 10
Y/37-2 | SGBM19 | Aug 19 2015 2:40PM | Jul 21 2015 5:30PM | 49.564 | 48.075 | 6, 14 | 21.507 | 1.489 | 26.568 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 19.0 | -100.0 | G45T2 | c480007388, c520121107 | 8, 11
Y/37-3 | SGBM19 | Aug 22 2015 5:25PM | Aug 24 2015 5:10PM | 49.623 | 48.075 | 8, 15 | 21.813 | 1.548 | 26.262 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 18.0 | -100.0 | G45T2 | C480007524, c520121155 | 10, 8
Y/38-1 | SGBM19 | Aug 22 2015 8:20AM | Aug 24 2015 4:55PM | 49.705 | 48.075 | 8 | 22.058 | 1.630 | 26.017 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 18.0 | -16.6 | G45T2 | c520121153, c480007523, c480007524 | 6, 11, 1
Y/38-2 | SGBM03 | Aug 18 2015 5:25PM | Aug 20 2015 11:45AM | 49.598 | 48.075 | 8, 12 | 22.001 | 1.523 | 26.074 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 18.0 | -100.0 | G45T2 | c480007333, c480007334, c480007340 | 3, 11, 4
Y/38-3 | SGBM21 | Sep 19 2015 1:05PM | Sep 21 2015 2:25PM | 49.686 | 48.075 | 8 | 21.965 | 1.611 | 26.110 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 21.0 | -100.0 | G45T2 | c480008961, c480008963, c480008965 | 9, 11, 1
Z/22-1 | SGBM08 | Sep 11 2015 11:00AM | Sep 12 2015 4:16PM | 49.807 | 47.875 |  | 26.609 | 1.932 | 21.266 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.5 | 16.0 | -100.0 | G35T2 | 1, 2 | 9, 7
Z/22-2 | SGBM08 | Sep 14 2015 4:30PM | Sep 15 2015 5:32PM | 49.841 | 47.875 |  | 26.448 | 1.966 | 21.427 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.6 | 16.0 | -100.0 | G35T2 | 1, 2 | 11, 5
Z/23-1 | SGBM08 | Sep 10 2015 12:00PM | Sep 10 2015 9:50PM | 49.858 | 47.875 |  | 26.289 | 1.983 | 21.586 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.7 | 15.0 | -100.0 | G35T2 | 1, 2 | 4, 11
Z/23-2 | SGBM16 | Sep 14 2015 6:00PM | Sep 15 2015 6:46PM | 49.851 | 47.875 |  | 26.548 | 1.976 | 21.327 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.6 | 16.0 | -100.0 | G35T2 | 1, 2 | 6, 10
Z/24-1 | SGBM08 | Sep 9 2015 8:30AM | Sep 10 2015 7:30PM | 49.917 | 47.875 | 9 | 27.069 | 2.042 | 20.806 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 20.0 | -100.0 | G35T2 | 1, 2 | 9, 11
Z/24-2 | SGBM16 | Sep 12 2015 10:00AM | Sep 14 2015 4:45PM | 49.919 | 47.875 | 8 | 24.902 | 2.044 | 22.973 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 14.6 | 23.0 | -14.6 | G35T2 | 1, 2, 3 | 11, 2, 10
Z/25-1 | SGBM16 | Sep 11 2015 2:30PM | Sep 12 2015 4:54PM | 50.098 | 47.875 |  | 26.586 | 2.223 | 21.289 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.5 | 15.0 | -100.0 | G35T2 | 1, 2 | 4, 11
Z/25-2 | SGBM16 | Sep 11 2015 2:30PM | Sep 12 2015 4:10PM | 49.927 | 47.875 |  | 26.745 | 2.052 | 21.130 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.4 | 16.0 | -100.0 | G35T2 | 1, 2 | 6, 10
Z/33-1 | SGBM22 | Oct 23 2015 10:40AM | Oct 23 2015 3:17PM | 49.533 | 48.775 |  | 26.015 | 0.758 | 22.760 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.5 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 4
Y/22-1 | SGBM16 | Jul 9 2015 10:40AM | Jul 9 2015 3:05PM | 49.850 | 48.575 | 8 | 26.842 | 1.275 | 21.733 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.8 | 18.0 | -100.0 | G35T2 | c480005311, c480005312 | 10, 8
Y/22-2 | SGBM17 | Jul 11 2015 10:20AM | Aug 11 2015 10:19PM | 49.785 | 48.575 | 8 | 24.737 | 1.210 | 23.838 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 15.2 | 18.0 | -100.0 | G35T2 | 1, 2 | 10, 8
Y/22-3 | SGBM16 | Jul 19 2015 9:00AM | Jul 20 2015 6:20PM | 49.680 | 48.575 |  | 26.680 | 1.105 | 21.895 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.9 | 16.0 | -100.0 | G35T2 | 1, 2 | 11, 5
Y/24-1 | SGBM16 | Jul 10 2015 4:00PM | Jul 10 2015 9:30PM | 49.805 | 48.575 | 8 | 27.188 | 1.230 | 21.387 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.6 | 17.0 | 24.9 | G35T2 | c520120553, c520120552 | 8, 9
Y/24-2 | SGBM16 | Jul 15 2015 10:30AM | Jul 21 2015 4:30PM | 49.718 | 48.575 | 8 | 42.518 | 1.143 | 6.057 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 3.9 | 17.0 | 30.0 | G35T2 | C480005644, C480005648, C480005649 | 2, 11, 4
Y/24-3 | SGBM16 | Jul 23 2015 3:30PM | Jul 24 2015 1:20AM | 49.796 | 48.575 |  | 27.372 | 1.221 | 21.203 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.5 | 16.0 | -100.0 | G35T2 | 1, 2 | 11, 5
Y/26-1 | SGBM17 | Jul 10 2015 11:00AM | Jul 10 2015 8:49PM | 50.064 | 48.575 | 8 | 27.555 | 1.489 | 21.020 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.4 | 18.0 | 34.6 | G35T2 | c520120550, c520120551 | 9, 9
Y/26-2 | SGBM16 | Jul 13 2015 9:45AM | Jul 13 2015 7:00PM | 49.873 | 48.575 | 8 | 27.827 | 1.298 | 20.748 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 16.0 | -100.0 | G35T2 | C480005535, C480005539 | 6, 10
Y/26-3 | SGBM17 | Jul 24 2015 11:00AM | Jul 25 2015 2:50AM | 49.812 | 48.575 |  | 27.512 | 1.237 | 21.063 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.4 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
X/24-1 | SGBM18 | Jul 14 2015 11:15AM | Jul 14 2015 3:30PM | 49.756 | 48.575 | 8 | 29.008 | 1.181 | 19.567 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.4 | 16.0 | -100.0 | G35T2 | C480005581, C480005583 | 10, 6
X/24-2 | SGBM17 | Jul 15 2015 10:30AM | Jul 21 2015 6:30PM | 49.586 | 48.575 | 8 | 28.886 | 1.011 | 19.689 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.5 | 16.0 | -100.0 | G35T2 | C480005645, C480005644 | 11, 5
X/24-3 | SGBM17 | Jul 22 2015 8:30AM | Jul 23 2015 1:30AM | 49.779 | 48.575 |  | 27.200 | 1.204 | 21.375 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.6 | 17.0 | -100.0 | G35T2 | 1, 2 | 11, 6
W/44-1 | SGBM19 | Sep 12 2015 4:20PM | Sep 14 2015 7:00PM | 49.645 | 47.625 | 8, 17 | 20.299 | 2.020 | 27.326 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.4 | 26.0 | -100.0 | G35T2 | c520121605, c480008622, c480008632 | 9, 10, 7
W/44-2 | SGBM03 | Aug 25 2015 4:50PM | Sep 8 2015 3:40PM | 49.551 | 47.625 | 8, 16 | 20.728 | 1.926 | 26.897 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.1 | 20.0 | -100.0 | G35T2 | c480008233, c480008235 | 12, 8
W/44-3 | SGBM19 | Sep 9 2015 8:05AM | Sep 10 2015 2:15PM | 49.590 | 47.625 | 8, 29 | 20.453 | 1.965 | 27.172 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.3 | 27.0 | 56.2 | G35T2 | c480008348, c480008353, c480008359 | 11, 11, 5
X/45-1 | SGBM03 | Sep 25 2015 4:05PM | Sep 26 2015 5:30PM | 49.610 | 47.775 | 8, 25 | 21.495 | 1.835 | 26.280 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 23.0 | -100.0 | G45T2 | c520121904, c520121908 | 12, 11
W/40-1 | SGBM19 | Sep 8 2015 9:55AM | Sep 9 2015 11:00AM | 49.398 | 49.075 | 8 | 19.885 | 0.323 | 29.190 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.6 | 23.0 | 23.8 | G35T2 | c480008265, c480008266, c480008272 | 11, 11, 1
Z/40-1 | SGBM21 | Sep 28 2015 8:20PM | Sep 30 2015 12:47PM | 49.694 | 46.175 | 8, 14 | 17.008 | 1.069 | 29.167 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -18.6 | G45T2 | 1, 2 | 11, 11
Z/40-2 | SGBM08 | Oct 24 2015 8:00AM | Oct 24 2015 3:12PM | 49.669 | 46.175 |  | 17.164 | 3.494 | 29.011 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 7, 7, 4
Z/40-3 | SGBM08 | Oct 26 2015 8:00AM | Oct 26 2015 4:16PM | 49.587 | 46.175 |  | 17.172 | 3.412 | 29.003 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
Z/40-4 | SGBM21 | Oct 3 2015 8:00AM | Oct 5 2015 3:28PM | 49.654 | 46.175 |  | 16.969 | 3.479 | 29.206 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -18.6 | G45T2 | 1, 2, 3 | 9, 9, 4
Z/40-5 | SGBM21 | Oct 1 2015 2:40PM | Oct 2 2015 6:07PM | 49.597 | 46.175 | 8 | 17.152 | 0.972 | 29.023 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
Z/41-2 | SGBM19 | Nov 23 2015 12:05PM | Nov 23 2015 7:56PM | 49.573 | 47.725 | 9 | 19.702 | 1.848 | 28.023 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.8 | 28.0 | -17.8 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
Z/41-3 | SGBM21 | Oct 1 2015 7:05PM | Oct 2 2015 7:53PM | 49.671 | 47.725 | 8, 22 | 21.214 | 1.946 | 26.511 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.9 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 9, 5
Y/39a-1 | SGBM21 | Sep 17 2015 5:00PM | Sep 18 2015 4:00PM | 49.670 | 46.175 | 8, 24 | 18.368 | 3.495 | 27.807 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.7 | 22.0 | -100.0 | G45T2 | c480008823, c520121719, c520121721 | 9, 9, 4
Y/39a-2 | SGBM21 | Sep 22 2015 1:11PM | Sep 23 2015 1:30PM | 49.660 | 46.175 | 8 | 17.585 | 3.485 | 28.590 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.2 | 22.0 | -100.0 | G45T2 | c480009097, c480009098 | 11, 11
Y/39a-3 | SGBM21 | Sep 29 2015 3:15PM | Sep 30 2015 1:42PM | 49.627 | 46.175 | 8 | 17.795 | 3.452 | 28.380 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | -18.1 | G45T2 | 1, 2, 3, 4 | 4, 5, 10, 4
Y/39a-4 | SGBM21 | Oct 3 2015 2:00PM | Oct 5 2015 12:30PM | 49.650 | 46.175 |  | 18.136 | 3.475 | 28.039 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 22.0 | -17.8 | G45T2 | 1, 2 | 11, 11
Y/39a-5 | SGBM21 | Sep 28 2015 11:00AM | Sep 28 2015 6:40PM | 49.607 | 46.175 |  | 17.997 | 3.432 | 28.178 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 11, 7
Y/39a-6 | SGBM21 | Oct 1 2015 9:40AM | Oct 1 2015 6:55PM | 49.647 | 46.175 | 8 | 17.966 | 3.472 | 28.209 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 22.0 | -17.9 | G45T2 | 1, 2, 3 | 11, 9, 2
Y/39a-7 | SGBM21 | Sep 21 2015 5:25PM | Sep 22 2015 7:20PM | 49.553 | 46.175 | 8, 24 | 18.150 | 3.378 | 28.025 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 20.0 | -100.0 | G45T2 | c480009053, c480009060 | 11, 9
Y/39a-8 | SGBM03 | Sep 17 2015 2:45PM | Sep 18 2015 3:35PM | 49.516 | 46.175 | 8, 32 | 18.317 | 3.341 | 27.858 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.7 | 22.0 | -100.0 | G45T2 | c480008819, c520121716, c480008823 | 11, 9, 2
Y/40a-1 | SGBM08 | Sep 28 2015 2:30PM | Sep 29 2015 3:12PM | 49.611 | 46.175 |  | 17.777 | 3.436 | 28.398 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 8, 5
Y/40a-2 | SGBM03 | Oct 2 2015 11:40AM | Oct 3 2015 3:34PM | 49.605 | 46.175 | 8 | 17.325 | 3.430 | 28.850 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.4 | 25.0 | -100.0 | G45T2 | 1, 2, 4 | 9, 12, 4
Y/40a-3 | SGBM19 | Oct 13 2015 8:00AM | Oct 13 2015 8:44PM | 49.606 | 46.175 | 9, 13.7 | 17.937 | 3.431 | 28.238 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 21.0 | -18.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Y/40a-4 | SGBM03 | Oct 6 2015 8:00AM | Oct 6 2015 3:40PM | 49.583 | 46.175 |  | 17.676 | 3.408 | 28.499 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Y/40a-5 | SGBM19 | Oct 15 2015 1:15PM | Oct 15 2015 10:50PM | 49.540 | 46.175 | 9 | 18.152 | 3.365 | 28.023 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 21.0 | -17.8 | G45T2 | 1, 2, 3 | 7, 7, 7
Y/40a-6 | SGBM21 | Sep 30 2015 5:10PM | Oct 1 2015 11:05AM | 49.592 | 46.175 | 8, 32.5 | 17.658 | 3.417 | 28.517 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 26.0 | -18.1 | G45T2 | 1, 2, 3 | 11, 10, 5
Y/40a-7 | SGBM21 | Sep 23 2015 9:00AM | Sep 25 2015 6:45PM | 49.549 | 46.175 | 8 | 17.822 | 3.374 | 28.353 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 27.0 | 49.7 | G45T2 | c1700012730, c520121866, c170012731 | 9, 12, 6
Y/40a-8 | SGBM21 | Oct 2 2015 4:10PM | Oct 3 2015 5:10PM | 49.573 | 46.175 | 8 | 18.061 | 3.398 | 28.114 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 11, 2
X/41-1 | SGBM19 | Oct 18 2015 8:00AM | Oct 19 2015 5:26PM | 49.859 | 47.475 | 9, 19.8 | 19.769 | 1.784 | 27.706 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.6 | 21.0 | -17.6 | G45T2 | 1, 2, 3 | 7, 7, 7
X/41-2 | SGBM19 | Oct 12 2015 3:00PM | Oct 13 2015 12:31AM | 49.958 | 47.475 |  | 20.038 | 2.483 | 27.437 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.5 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 5
X/41-3 | SGBM21 | Oct 2 2015 10:30AM | Oct 3 2015 12:30PM | 49.552 | 47.475 | 8, 16 | 19.524 | 1.477 | 27.951 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 5, 12
W/42-1 | SGBM03 | Sep 29 2015 5:00PM | Sep 30 2015 5:12PM | 49.582 | 47.375 | 8 | 19.352 | 2.207 | 28.023 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.8 | 23.0 | -17.8 | G45T2 | 1, 2, 3 | 4, 7, 12
W/42-2 | SGBM21 | Sep 19 2015 9:00AM | Sep 21 2015 12:15PM | 49.464 | 47.375 | 8 | 19.503 | 2.089 | 27.872 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.7 | 22.0 | -100.0 | G45T2 | c480008951, c480008952 | 11, 11
W/42-3 | SGBM21 | Sep 25 2015 11:19AM | Sep 26 2015 6:20PM | 49.519 | 48.075 | 8, 28 | 19.483 | 1.444 | 28.592 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.2 | 19.0 | -100.0 | G45T2 | c520121907, c520121910 | 7, 12
W/43-1 | SGBM03 | Sep 29 2015 4:45PM | Sep 30 2015 8:11PM | 49.611 | 48.075 | 8, 28 | 19.439 | 1.536 | 28.636 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.2 | 22.0 | -18.2 | G45T2 | 1, 2 | 11, 11
W/43-2 | SGBM03 | Sep 19 2015 8:46AM | Sep 21 2015 1:30PM | 49.541 | 47.375 | 8 | 20.373 | 2.166 | 27.002 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.2 | 22.0 | -100.0 | G45T2 | c480008956, c480008957 | 11, 11
W/43-3 | SGBM03 | Sep 26 2015 4:30PM | Sep 28 2015 4:00PM | 49.551 | 47.375 |  | 20.516 | 2.176 | 26.859 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.1 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
H/29-1 | SGBM20 | Oct 26 2015 5:20PM | Oct 27 2015 4:32PM | 52.171 | 50.375 | 9 | 30.315 | 1.796 | 20.060 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.8 | 17.0 | 33.2 | G45T2 | 1, 2, 3 | 7, 7, 3
H/29-2 | SGBM20 | Oct 16 2015 2:40PM | Oct 17 2015 7:34PM | 52.139 | 50.375 | 9 | 30.379 | 1.764 | 19.996 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.7 | 18.0 | 41.5 | G45T2 | 1, 2, 3 | 7, 7, 4
H/29-3 | SGBM20 | Oct 23 2015 3:30PM | Oct 23 2015 8:54PM | 52.168 | 50.375 | 9 | 30.165 | -50.375 | 20.210 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.9 | 17.0 | -12.8 | G45T2 | 1, 2, 3 | 6, 6, 5
J/22-1 | SGBM20 | Oct 21 2015 9:30AM | Oct 21 2015 8:00PM | 52.441 | 50.575 | 9 | 26.968 | -50.575 | 23.607 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 15.0 | 18.0 | -15.0 | G45T2 | 1, 2, 3 | 6, 6, 6
J/22-2 | SGBM20 | Oct 15 2015 6:15PM | Oct 15 2015 11:44PM | 52.434 | 50.575 | 9 | 27.415 | 1.859 | 23.160 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 14.7 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
J/22-3 | SGBM20 | Oct 22 2015 5:15PM | Oct 23 2015 3:45PM | 52.393 | 50.575 | 9 | 27.303 | -50.575 | 23.272 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 14.8 | 21.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 3, 6, 6, 6
J/22-4 | SGBM20 | Oct 28 2015 8:00AM | Oct 29 2015 7:47PM | 52.406 | 50.575 | 9 | 27.365 | 1.831 | 23.210 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 14.8 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
J/22-5 | SGBM20 | Sep 10 2015 8:30AM | Sep 11 2015 11:50AM | 53.481 | 50.575 | 9 | 26.114 | 2.906 | 24.461 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 15.6 | 27.0 | -100.0 | G45T2 | c480008436, c170012571, c480008438 | 11, 10, 6
J/22-6 | SGBM20 | Oct 24 2015 5:13PM | Oct 27 2015 12:00PM | 52.361 | 50.575 | 9 | 27.172 | -50.575 | 23.403 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 14.9 | 20.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 2
J/22-7 | SGBM20 | Oct 13 2015 8:00AM | Oct 13 2015 4:55PM | 52.477 | 50.575 | 9 | -26.300 | 1.902 | 76.875 |  | 0.0 | 0.0 | 9T20 | T12-250 |  | 48.9 | 18.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 2, 2
J/22-8 | SGBM20 | Oct 10 2015 10:30AM | Oct 10 2015 2:13PM | 52.373 | 50.575 | 9 | 27.435 | 1.798 | 23.140 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 14.7 | 16.0 | 8.7 | G45T2 | 1, 2, 3 | 7, 7, 2
H/23-1 | SGBM15 | Sep 18 2015 11:30AM | Sep 19 2015 5:25PM | 52.944 | 50.375 | 9 | 28.500 | 3.169 | 21.875 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.9 | 18.0 | -100.0 | G45T2 | c480008894, c480008896 | 12, 6
H/23-2 | SGBM15 | Sep 12 2015 5:00PM | Sep 14 2015 5:45PM | 52.243 | 50.375 | 9 | 28.957 | 2.468 | 21.418 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 18.0 | -0.2 | G45T2 | c520121603, c170012592, c480008619 | 6, 8, 4
H/23-3 | SGBM15 | Sep 15 2015 1:40PM | Sep 17 2015 5:00PM | 52.233 | 50.375 | 9 | 29.726 | 1.858 | 20.649 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 16.0 | 2.9 | G45T2 | 1, 2 | 8, 8
L/28-1 | SGBM20 | Sep 11 2015 4:00PM | Sep 12 2015 1:35PM | 53.524 | 50.975 | 9 | 31.250 | 2.549 | 19.725 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.6 | 15.0 | -100.0 | G35T2 | c52012154, c520121551, c520121554 | 3, 11, 1
L/28-2 | SGBM15 | Sep 18 2015 8:00AM | Sep 18 2015 7:20PM | 53.548 | 50.975 | 9 | 31.816 | 2.573 | 19.159 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 12.2 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 5, 10, 2
L/29-1 | SGBM20 | Sep 14 2015 11:00AM | Sep 15 2015 11:55AM | 53.625 | 49.875 | 9 | 29.325 | 3.750 | 20.550 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.1 | 16.0 | 22.4 | G35T2 | c480008644, c480008645 | 11, 5
L/29-2 | SGBM20 | Oct 21 2015 12:30PM | Oct 22 2015 11:48AM | 52.722 | 49.875 | 9, 21 | 29.102 | 2.847 | 20.773 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 18.0 | -13.2 | G35T2 | 1, 2, 3 | 7, 6, 5
L/30-1 | SGBM20 | Oct 13 2015 11:30AM | Oct 15 2015 11:05AM | 53.370 | 49.875 | 9 | 29.124 | 3.495 | 20.751 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 17.0 | -13.2 | G35T2 | 1, 2, 3 | 6, 6, 5
L/30-2 | SGBM20 | Oct 6 2015 11:00AM | Oct 6 2015 7:59PM | 52.375 | 49.875 | 9 | 28.665 | 2.500 | 21.210 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 4
L/31-1 | SGBM20 | Oct 3 2015 9:00AM | Oct 3 2015 12:45PM | 52.215 | 49.875 | 9 | 29.192 | 2.340 | 20.683 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 15.0 | -100.0 | G35T2 | 1, 2 | 8, 7
L/31-2 | SGBM20 | Oct 8 2015 10:00AM | Oct 8 2015 2:40PM | 52.266 | 49.875 | 9 | 29.109 | 2.391 | 20.766 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 13.2 | 16.0 | -13.2 | G35T2 | 1, 2, 3 | 7, 7, 2
L/32-1 | SGBM20 | Oct 5 2015 8:00PM | Oct 6 2015 4:36PM | 52.210 | 49.825 | 9 | 29.085 | 2.385 | 20.740 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.2 | 16.0 | 2.8 | G45T2 | 1, 2, 3 | 7, 7, 2
L/32-2 | SGBM20 | Oct 1 2015 8:00PM | Oct 2 2015 7:21PM | 52.141 | 49.825 | 9 | 29.056 | 2.266 | 20.769 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.2 | 15.0 | -13.2 | G45T2 | 1, 2 | 10, 5
H/56-2 | SGBM18 | Sep 26 2015 3:10PM | Sep 28 2015 8:23PM | 51.936 | 46.875 | 6, 42.9 | 5.802 | 5.061 | 41.073 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 9, 2, 9
H/56-4 | SGBM18 | Oct 10 2015 7:00PM | Oct 12 2015 7:33PM | 51.815 | 46.875 |  | 5.798 | 4.940 | 41.077 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 35.0 | -100.0 | G45T2 | 1, 1, 3, 4 | 5, 10, 9, 11
H/56-6 | SGBM18 | Sep 28 2015 10:00AM | Sep 29 2015 4:43AM | 51.964 | 46.875 |  | 5.806 | 5.089 | 41.069 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 9, 9, 9
H/56-8 | SGBM17 | Oct 17 2015 5:20PM | Oct 19 2015 3:53PM | 51.782 | 46.875 | 8, 23, 31 | 5.799 | 4.907 | 41.076 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 31.0 | -26.1 | G45T2 | 1, 2, 3, 4, 5 | 7, 6, 7, 7, 4
H/56-10 | SGBM18 | Oct 16 2015 8:00AM | Oct 16 2015 5:50PM | 51.777 | 46.875 |  | 5.345 | 4.902 | 41.530 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.4 | 29.5 | -100.0 | G45T2 | 1, 2, 3 | 8, 11, 10.5
H/56-12 | SGBM17 | Sep 17 2015 5:00PM | Sep 21 2015 2:40PM | 51.930 | 46.875 | 6, 20, 47 | 3.853 | 5.055 | 43.022 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 27.4 | 51.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 9, 11, 11, 11
H/56-13 | SGBM17 | Oct 2 2015 5:00PM | Oct 3 2015 8:07PM | 51.846 | 46.875 | 6, 19.6 | 5.817 | 4.971 | 41.058 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 5, 10, 12, 3
H/56-14 | SGBM18 | Oct 17 2015 8:00AM | Oct 17 2015 1:04PM | 51.570 | 46.875 |  | 5.805 | 4.695 | 41.070 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
H/56-15 | SGBM17 | Sep 23 2015 8:00AM | Sep 23 2015 9:22PM | 52.000 | 46.875 |  | 5.778 | 5.125 | 41.097 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 51.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 11, 11, 11, 8
H/56-16 | SGBM18 | Oct 5 2015 1:00PM | Oct 6 2015 11:25AM | 51.900 | 46.875 | 9 | 5.825 | 5.025 | 41.050 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 30.0 | -26.1 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 2
H/56-17 | SGBM18 | Oct 9 2015 9:40AM | Oct 10 2015 10:33AM | 51.869 | 46.875 | 8 | 5.768 | 4.994 | 41.107 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.2 | 31.0 | -26.1 | G45T2 | 1, 2, 3, 4 | 9, 10, 10, 2
H/56-18 | SGBM17 | Sep 25 2015 6:45PM | Sep 30 2015 8:05PM | 51.922 | 46.875 | 6 | 5.789 | 5.047 | 41.086 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 4, 11, 11, 8
H/56-19 | SGBM18 | Oct 7 2015 9:50AM | Oct 8 2015 8:05PM | 51.854 | 46.875 | 9 | 5.826 | 4.979 | 41.049 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 31.0 | -26.1 | G45T2 | 1, 2, 3 | 11, 10, 10
Z/26-1 | SGBM19 | Sep 26 2015 5:00PM | Sep 28 2015 8:57PM | 50.737 | 48.075 |  | 26.312 | 2.662 | 21.763 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 13.8 | 20.0 | -100.0 | G45T2 | 1, 2 | 9, 11
Z/26-2 | SGBM19 | Sep 30 2015 11:30AM | Sep 30 2015 11:25PM | 49.990 | 48.075 |  | 26.106 | 1.915 | 21.969 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 14.0 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 11, 3
Z/26-3 | SGBM19 | Sep 22 2015 6:05PM | Sep 23 2015 3:40PM | 49.928 | 48.075 |  | 27.049 | 1.853 | 21.026 |  | 0.0 | 0.0 | 9T20 | T12-250 | 12 | 13.4 | 16.0 | -100.0 | G45T2 | 1, 2 | 11, 5
G/31-1 | SGBM20 | Oct 31 2015 2:15PM | Nov 1 2015 2:06PM | 52.129 | 48.175 | 9 | 32.206 | 3.972 | 15.969 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.2 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
Q/37-1 | SGBM16 | Sep 17 2015 3:30PM | Sep 18 2015 12:30PM | 52.681 | 50.175 | 8 | 30.435 | 2.506 | 19.740 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.6 | 18.0 | 43.3 | G45T2 | a1, a2, a3 | 10, 3, 5
Q/37-2 | SGBM16 | Sep 23 2015 4:30PM | Sep 25 2015 12:00PM | 52.588 | 50.175 | 8, 22 | 30.983 | 2.413 | 19.192 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 15.0 | -100.0 | G45T2 | a1, a2 | 11, 4
X/45-3 | SGBM21 | Sep 21 2015 10:00AM | Sep 22 2015 11:25AM | 49.686 | 47.775 | 8 | 21.536 | 1.911 | 26.239 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 18.0 | 7.8 | G45T2 | c480009011, c480009013 | 7, 11
X/45-2 | SGBM19 | Sep 18 2015 9:50AM | Sep 19 2015 2:35PM | 49.629 | 47.775 | 8 | 21.579 | 1.854 | 26.196 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 25.0 | -100.0 | G45T2 | c480008877, c480008879, c480008880 | 3, 11, 11
X3/Y4-1 | SGBM21 | Oct 27 2015 8:05AM | Oct 27 2015 3:00PM | 55.749 | 54.725 | 9 | 25.551 | 1.024 | 29.174 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 2
X3/Y5-1 | SGBM21 | Oct 22 2015 8:00AM | Oct 22 2015 3:20PM | 55.636 | 54.725 |  | 26.651 | 0.911 | 28.074 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.9 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
X4/Y6-1 | SGBM21 | Nov 2 2015 6:30PM | Nov 4 2015 12:35AM | 55.757 | 55.075 | 9 | 28.778 | -55.075 | 26.297 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.7 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
X5/Y3-1 | SGBM21 | Oct 27 2015 2:30PM | Oct 27 2015 9:00PM | 55.838 | 53.875 |  | 25.701 | 1.963 | 28.174 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
X5/Y3-2 | SGBM21 | Oct 24 2015 10:00AM | Oct 24 2015 5:13PM | 55.849 | 53.875 |  | 25.699 | 1.974 | 28.176 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 8
X5/Y3-3 | SGBM03 | Oct 30 2015 6:39PM | Oct 31 2015 8:10PM | 55.702 | 53.875 | 9 | 25.708 | 1.827 | 28.167 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
X5/Y3-4 | SGBM03 | Nov 3 2015 10:00AM | Nov 3 2015 9:56PM | 55.827 | 53.875 | 9 | 18.828 | -53.875 | 35.047 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 22.3 | 21.0 | -100.0 | G45T2 | 1, 2 | 12, 9
X5/Y3-5 | SGBM21 | Nov 7 2015 12:00PM | Nov 9 2015 11:50AM | 55.707 | 53.875 | 9 | 25.785 | 1.832 | 28.090 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 7
X5/Y3-6 | SGBM21 | Oct 28 2015 6:55PM | Oct 29 2015 2:47PM | 55.831 | 53.875 | 9 | 25.761 | 1.956 | 28.114 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 8
X6/Y5-1 | SGBM21 | Oct 19 2015 12:25PM | Oct 19 2015 9:17PM | 55.753 | 54.075 | 9 | 28.023 | -54.075 | 26.052 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.6 | 22.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 4, 4
X6/Y5-2 | SGBM21 | Oct 13 2015 10:30AM | Oct 13 2015 4:18PM | 55.813 | 54.075 |  | 27.877 | 1.738 | 26.198 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.7 | 21.0 | -16.7 | G45T2 | 1, 2, 3 | 7, 7, 7
X6/Y5-3 | SGBM21 | Oct 16 2015 1:00PM | Oct 16 2015 8:24PM | 55.750 | 54.075 |  | 27.877 | 1.675 | 26.198 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.7 | 23.0 | 38.0 | G45T2 | 1, 2, 3, 4 | 3, 6, 7, 7
X5a/Y4-1 | SGBM03 | Oct 30 2015 6:19PM | Oct 31 2015 2:58PM | 55.828 | 51.075 | 9 | 21.811 | 4.753 | 29.264 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.6 | 23.0 | -18.6 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 5
X5a/Y4-2 | SGBM21 | Oct 27 2015 7:30PM | Oct 28 2015 5:16PM | 55.776 | 51.075 | 9 | 21.928 | -51.075 | 29.147 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.5 | 23.0 | -18.5 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 5
X5a/Y4-3 | SGBM09 | Oct 8 2015 8:00AM | Oct 8 2015 4:15PM | 55.802 | 51.075 |  | 21.871 | 4.727 | 29.204 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.6 | 21.0 | -18.6 | G45T2 | 1, 2, 3 | 7, 7, 7
X5a/Y4-4 | SGBM21 | Oct 12 2015 9:30AM | Oct 12 2015 9:41PM | 55.827 | 51.075 |  | 21.908 | 4.752 | 29.167 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.6 | 26.0 | -18.6 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 5
X5a/Y4-5 | SGBM03 | Nov 4 2015 8:30AM | Nov 4 2015 7:20PM | 55.766 | 51.075 | 9 | 22.070 | 4.691 | 29.005 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 5
X5a/Y4-6 | SGBM21 | Oct 25 2015 9:00PM | Oct 26 2015 10:35AM | 56.607 | 51.075 |  | 21.261 | 5.532 | 29.814 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 19.0 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 8, 2
X5a/Y4-7 | SGBM21 | Oct 20 2015 8:30AM | Oct 20 2015 8:20PM | 55.843 | 51.075 | 9 | 21.903 | 4.768 | 29.172 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 5
X5a/Y4-8 | SGBM21 | Oct 23 2015 11:00AM | Oct 23 2015 5:01PM | 55.914 | 51.075 |  | 22.017 | 4.839 | 29.058 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 6, 6, 6, 3
X7/Y5-1 | SGBM21 | Oct 20 2015 8:13AM | Oct 21 2015 12:18AM | 55.805 | 54.075 | 9 | 27.933 | 1.730 | 26.142 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.6 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
X7/Y5-2 | SGBM21 | Oct 17 2015 8:30AM | Oct 17 2015 1:21PM | 55.780 | 54.075 |  | 28.064 | 1.705 | 26.011 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.5 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
X7/Y5-3 | SGBM21 | Oct 13 2015 2:45PM | Oct 13 2015 9:20PM | 55.828 | 54.075 |  | 27.871 | 1.753 | 26.204 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.7 | 26.0 | -16.7 | G45T2 | 1, 2, 3 | 11, 11, 4
X7/Y6-1 | SGBM21 | Oct 31 2015 3:30PM | Nov 2 2015 2:59PM | 55.715 | 53.875 | 9 | 28.769 | -53.875 | 25.106 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.0 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
X7/Y6-2 | SGBM03 | Nov 7 2015 6:15PM | Nov 11 2015 7:44PM | 55.683 | 53.875 | 9 | 28.924 | -53.875 | 24.951 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 15.9 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
X7/Y6-4 | SGBM03 | Nov 5 2015 2:00PM | Nov 6 2015 5:40PM | 55.704 | 53.875 | 9, 20 | 28.733 | -53.875 | 25.142 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.0 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 2
X7/Y6-5 | SGBM03 | Nov 13 2015 8:11AM | Nov 13 2015 8:00PM | 0.000 | 53.875 | 9 | -28.000 | -53.875 | 81.875 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 |  | 52.1 | 22.0 | -52.1 | G45T2 | pj1553, pj1556, pj1557, pj1560 | 7, 7, 6, 2
X8/Y7-1 | SGBM03 | Nov 4 2015 9:15AM | Nov 5 2015 1:58PM | 55.935 | 54.625 | 9 | 29.534 | -54.625 | 25.091 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 16.0 | 22.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 8, 5, 2
X9a/Y4-1 | SGBM02 | Nov 7 2015 11:00AM | Nov 7 2015 6:58PM | 55.513 | 53.875 | 9 | 24.600 | 1.638 | 29.275 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.6 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 3, 6, 7, 5
X9a/Y4-2 | SGBM21 | Nov 11 2015 9:47AM | Nov 12 2015 2:10PM | 55.723 | 53.875 | 9, 27.5 | 24.273 | -53.875 | 29.602 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.8 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 5
X9a/Y4a-1 | SGBM20 | Nov 18 2015 1:00PM | Nov 18 2015 8:27PM | 55.789 | 55.075 |  | 26.533 | 0.714 | 28.542 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 18.2 | 22.0 | -18.2 | G45T2 | 1, 2, 3 | 8, 7, 7
X9/Y5-1 | SGBM03 | Nov 4 2015 10:00AM | Nov 5 2015 12:00AM | 55.859 | 54.075 | 9 | 26.628 | 1.784 | 27.447 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.5 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
X9/Y5-2 | SGBM21 | Nov 11 2015 6:25PM | Nov 14 2015 4:51PM | 55.865 | 54.075 | 9, 16 | 26.852 | -54.075 | 27.223 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.3 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
X9/Y5-3 | SGBM03 | Nov 7 2015 2:00PM | Nov 9 2015 5:20PM | 55.835 | 54.075 | 9, 26.1 | 26.419 | 1.760 | 27.656 |  | 0.0 | 0.0 | 9T20 + 8T20 | T12-250 | 12 | 17.6 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
G/19-1 | SGBM05 | Nov 3 2015 11:00AM | Nov 3 2015 10:11PM | 53.643 | 52.175 | 9 | 28.411 | -52.175 | 23.764 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.1 | 18.0 | -15.1 | G45T2 | 1, 2, 3 | 6, 6, 6
G/20-1 | SGBM05 | Nov 5 2015 2:00PM | Nov 6 2015 5:35PM | 53.460 | 50.975 | 9, 20 | 27.390 | 2.485 | 23.585 |  | 0.0 | 0.0 | 12T20+9T20 | T12-250 | 12 | 15.0 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
G/20-2 | SGBM20 | Nov 9 2015 10:20AM | Nov 9 2015 6:00PM | 53.505 | 50.975 | 9 | 27.755 | -50.975 | 23.220 |  | 0.0 | 0.0 | 12T20+9T20 | T12-250 | 12 | 14.8 | 18.0 | -14.8 | G45T2 | 1, 2, 3 | 6, 6, 6
G/22-1 | SGBM20 | Oct 22 2015 4:40PM | Oct 23 2015 10:40AM | 52.273 | 49.575 | 9, 24 | 25.939 | -49.575 | 23.636 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.0 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
G/22-2 | SGBM20 | Oct 28 2015 6:10PM | Oct 29 2015 11:09PM | 52.313 | 49.575 | 9 | 26.260 | 2.738 | 23.315 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.8 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
G/23-1 | SGBM20 | Oct 20 2015 3:37PM | Oct 21 2015 5:04PM | 52.034 | 49.575 | 9, 23 | 28.317 | 2.459 | 21.258 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
G/23-2 | SGBM20 | Oct 24 2015 3:41PM | Oct 26 2015 5:38PM | 52.078 | 49.575 | 9, 20 | 28.529 | -49.575 | 21.046 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.4 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 8, 5
G/24-1 | SGBM20 | Oct 19 2015 8:40PM | Oct 21 2015 2:54PM | 52.185 | 49.575 | 9 | 28.114 | -49.575 | 21.461 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.7 | 17.0 | -13.7 | G45T2 | 1, 2, 3 | 7, 7, 3
G/24-2 | SGBM20 | Oct 17 2015 10:50AM | Oct 17 2015 2:40PM | 52.115 | 49.575 |  | 27.515 | 2.540 | 22.060 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 14.0 | 20.0 | 42.5 | G45T2 | 1, 2, 3 | 6, 7, 7
G/25-1 | SGBM20 | Oct 12 2015 9:00PM | Oct 13 2015 2:32PM | 52.027 | 49.575 | 9 | 28.182 | 2.452 | 21.393 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.6 | 18.0 | -13.6 | G45T2 | 1, 2, 3 | 7, 7, 4
G/25-2 | SGBM23 | Oct 7 2015 8:00AM | Oct 7 2015 1:19PM | 51.998 | 49.575 | 9 | 28.395 | 2.423 | 21.180 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.5 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
G/26-1 | SGBM20 | Oct 15 2015 12:00PM | Oct 15 2015 6:21PM | 52.147 | 49.575 |  | 28.424 | 2.572 | 21.151 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 7, 4
G/26-2 | SGBM20 | Oct 9 2015 7:00PM | Oct 9 2015 11:15PM | 52.041 | 49.575 | 9 | 28.261 | 2.466 | 21.314 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.6 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
G/27-1 | SGBM20 | Oct 16 2015 1:20PM | Oct 17 2015 12:35PM | 52.027 | 49.575 | 9 | 28.288 | 2.452 | 21.287 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
G/27-2 | SGBM20 | Oct 19 2015 3:50PM | Oct 19 2015 11:07PM | 52.238 | 49.575 | 9 | 28.289 | 2.663 | 21.286 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.5 | 21.0 | -13.5 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 3
G/28-1 | SGBM20 | Oct 20 2015 2:30PM | Oct 20 2015 10:35PM | 0.000 | 49.575 | 9 | -24.500 | -49.575 | 74.075 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 47.1 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 5, 6
G/28-2 | SGBM20 | Oct 16 2015 1:55PM | Oct 17 2015 8:43PM | 51.978 | 49.575 |  | 28.220 | 2.403 | 21.355 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.6 | 18.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 3, 7, 4, 4
G/29-1 | SGBM20 | Oct 22 2015 11:30AM | Oct 22 2015 5:32PM | 51.959 | 49.575 | 9 | 29.074 | 2.384 | 20.501 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.0 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
G/29-2 | SGBM20 | Oct 28 2015 10:31AM | Oct 28 2015 5:03PM | 52.151 | 49.575 | 9 | 29.278 | 2.576 | 20.297 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 12.9 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
G/30-1 | SGBM20 | Nov 5 2015 8:15AM | Nov 5 2015 6:25PM | 52.101 | 49.575 | 9 | 29.502 | 2.526 | 20.073 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 12.8 | 15.0 | -100.0 | G45T2 | 1, 2 | 4, 11
G/30-2 | SGBM20 | Nov 2 2015 11:00AM | Nov 2 2015 6:45PM | 52.162 | 49.575 | 9 | 29.163 | -49.575 | 20.412 |  | 0.0 | 0.0 | 9T20+8T20 | T12-225 | 12 | 13.0 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
G/34-1 | SGBM20 | Nov 3 2015 8:00AM | Nov 3 2015 3:04PM | 52.167 | 50.775 | 9 | 29.785 | -50.775 | 20.990 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 17.0 | -100.0 | G45T2 | 1, 2 | 8, 9
M/19-1 | SGBM05 | Nov 11 2015 9:40PM | Nov 12 2015 4:25PM | 55.443 | 50.975 |  | 30.821 | 4.468 | 20.154 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 16.0 | 24.8 | G45T2 | 1, 2, 3 | 6, 2, 8
M/19-2 | SGBM05 | Nov 2 2015 12:07PM | Nov 3 2015 12:24AM | 55.443 | 51.575 | 9 | 31.421 | -51.575 | 20.154 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 2
M/23-1 | SGBM20 | Oct 30 2015 8:55AM | Oct 30 2015 8:47PM | 53.560 | 52.775 | 9 | 32.736 | -52.775 | 20.039 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.7 | 18.0 | -12.8 | G45T2 | 1, 2, 3 | 6, 6, 6
M/26-1 | SGBM20 | Oct 29 2015 8:44PM | Oct 31 2015 10:49AM | 53.340 | 51.375 | 9 | 30.840 | 1.965 | 20.535 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
M/27-1 | SGBM05 | Nov 4 2015 12:12PM | Nov 5 2015 2:30PM | 53.204 | 51.375 | 9 | 31.155 | -51.025 | 20.220 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 16.0 | -12.9 | G45T2 | 1, 2 | 8, 8
M/28-1 | SGBM05 | Nov 4 2015 11:27AM | Nov 4 2015 7:45PM | 53.048 | 51.375 | 9 | 31.265 | -49.825 | 20.110 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 17.0 | -12.8 | G45T2 | 1, 2, 3 | 6, 6, 5
M/30-1 | SGBM20 | Nov 7 2015 1:40PM | Nov 7 2015 8:48PM | 52.016 | 51.075 | 9 | 32.985 | 0.941 | 18.090 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.5 | 16.0 | -11.5 | G45T2 | 1, 2, 3 | 7, 4, 5
L/20-1 | SGBM05 | Nov 3 2015 10:10AM | Nov 4 2015 12:14AM | 53.698 | 51.275 | 9 | 31.441 | -51.275 | 19.834 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.6 | 19.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 5, 2
L/20-2 | SGBM19 | Oct 26 2015 9:30AM | Oct 28 2015 8:25PM | 53.569 | 51.275 | 9 | 31.544 | 2.294 | 19.731 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.6 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 4
L/34-1 | SGBM21 | Oct 8 2015 7:30PM | Oct 8 2015 10:45PM | 52.032 | 51.075 | 9 | 29.707 | 0.957 | 21.368 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
K/19-1 | SGBM05 | Oct 29 2015 8:40AM | Oct 29 2015 9:16PM | 53.460 | 52.775 | 9 | 32.155 | -52.775 | 20.620 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 16.0 | -13.1 | G45T2 | 1, 2, 3 | 6, 6, 4
K/34-1 | SGBM20 | Oct 12 2015 2:00PM | Oct 13 2015 1:18AM | 52.082 | 51.375 | 9 | 30.097 | 0.707 | 21.278 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 16.0 | -13.5 | G45T2 | 1, 2, 3 | 7, 7, 2
J/20-1 | SGBM19 | Oct 23 2015 9:45AM | Oct 24 2015 1:59PM | 53.475 | 51.575 | 9, 23.2 | 28.473 | -51.575 | 23.102 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.7 | 19.0 | -14.7 | G45T2 | 1, 2, 3, 4 | 4, 6, 6, 3
J/20-2 | SGBM05 | Nov 3 2015 9:15AM | Nov 3 2015 5:35PM | 53.508 | 51.575 | 9 | 28.270 | -51.575 | 23.305 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.8 | 21.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 5, 2
J/33-1 | SGBM09 | Oct 10 2015 5:00PM | Oct 10 2015 9:59PM | 52.072 | 51.375 | 9 | 30.522 | 0.697 | 20.853 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.3 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
J/34-1 | SGBM20 | Oct 11 2015 8:03AM | Oct 12 2015 11:50AM | 52.082 | 51.375 | 9, 22.5 | 30.202 | 0.707 | 21.173 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
H/32-1 | SGBM20 | Oct 23 2015 6:10PM | Oct 24 2015 6:30PM | 52.069 | 50.175 | 9 | 29.655 | -50.175 | 20.520 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 5, 6
H/32-2 | SGBM20 | Oct 27 2015 3:55PM | Oct 28 2015 11:12AM | 52.069 | 50.175 | 9, 19 | 29.303 | 1.890 | 20.872 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.3 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
H/33-1 | SGBM20 | Oct 16 2015 8:00AM | Oct 16 2015 12:36PM | 52.192 | 51.375 |  | 30.524 | 0.817 | 20.851 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.3 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 4
H/34-1 | SGBM20 | Oct 23 2015 7:00PM | Oct 24 2015 8:00PM | 52.155 | 51.375 | 9 | 30.428 | -51.375 | 20.947 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.3 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
AB/28-1 | SGBM03 | Oct 23 2015 5:40PM | Oct 24 2015 1:23AM | 49.781 | 48.475 |  | 26.013 | 1.306 | 22.462 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.3 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 6, 6
AB/31a-1 | SGBM03 | Oct 27 2015 4:20PM | Oct 28 2015 1:57AM | 49.647 | 48.475 |  | 24.801 | 1.172 | 23.674 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.1 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 6, 6
AA/21-1 | SGBM20 | Oct 9 2015 9:20AM | Oct 9 2015 9:27PM | 49.832 | 48.775 |  | 26.338 | 1.057 | 22.437 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.3 | 18.0 | 26.1 | G35T2 | 1, 2 | 10, 8
AA/30-1 | SGBM19 | Oct 7 2015 8:30AM | Oct 7 2015 5:25PM | 50.107 | 48.725 |  | 26.414 | 1.382 | 22.311 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 4
AA/32-1 | SGBM22 | Oct 16 2015 6:20PM | Oct 16 2015 11:43PM | 49.736 | 47.875 |  | 25.210 | 1.861 | 22.665 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.4 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 4, 7, 7
AA/32-2 | SGBM03 | Oct 19 2015 12:30PM | Oct 19 2015 6:14PM | 49.728 | 47.875 |  | 25.172 | 1.853 | 22.703 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.4 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 7
Z/20-1 | SGBM08 | Oct 19 2015 10:00AM | Oct 19 2015 3:40PM | 49.912 | 48.475 |  | 26.220 | 1.437 | 22.255 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 4
Z/31-1 | SGBM22 | Oct 5 2015 8:30AM | Oct 6 2015 2:05PM | 50.051 | 47.425 |  | 26.254 | 2.626 | 21.171 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 3, 10, 4
Z/31-2 | SGBM19 | Oct 8 2015 10:00AM | Oct 8 2015 10:13PM | 50.010 | 47.425 |  | 26.223 | 2.585 | 21.202 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2 | 7, 11
Z/32-1 | SGBM19 | Oct 2 2015 8:30AM | Oct 3 2015 4:53PM | 49.939 | 47.575 |  | 25.316 | 2.364 | 22.259 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 19.0 | -100.0 | G45T2 | 1, 2 | 12, 7
Z/32-2 | SGBM19 | Sep 30 2015 8:30AM | Oct 1 2015 4:42PM | 49.939 | 47.575 |  | 25.207 | 2.364 | 22.368 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 18.0 | -100.0 | G45T2 | 1, 2 | 8, 10
Y/32-1 | SGBM19 | Sep 28 2015 5:30PM | Sep 29 2015 2:27PM | 49.816 | 48.075 |  | 27.061 | 1.741 | 21.014 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 2, 11, 3
Y/32-2 | SGBM19 | Sep 24 2015 4:00PM | Sep 25 2015 5:09PM | 49.768 | 48.075 |  | 26.905 | 1.693 | 21.170 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
Y/32-3 | SGBM22 | Sep 30 2015 3:00PM | Oct 1 2015 2:00PM | 49.793 | 48.075 |  | 26.859 | 1.718 | 21.216 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
Y/33-1 | SGBM22 | Oct 20 2015 1:10PM | Oct 21 2015 2:24AM | 49.736 | 48.775 |  | 27.373 | 0.961 | 21.402 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
X/33-1 | SGBM03 | Oct 20 2015 4:00PM | Oct 21 2015 12:41AM | 49.651 | 48.775 |  | 27.571 | 0.876 | 21.204 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
W/20-1 | SGBM03 | Oct 15 2015 9:50AM | Oct 15 2015 9:22PM | 49.738 | 48.475 |  | 26.738 | 1.263 | 21.737 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.8 | 20.0 | -100.0 | G45T2 | 1, 2 | 9, 11
W/33-1 | SGBM22 | Oct 21 2015 8:00AM | Oct 21 2015 3:10PM | 49.520 | 48.775 |  | 27.308 | 0.745 | 21.467 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
V/33-1 | SGBM22 | Oct 22 2015 10:30AM | Oct 22 2015 6:54PM | 49.325 | 48.775 |  | 27.015 | 0.550 | 21.760 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.8 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
U/20-1 | SGBM22 | Sep 16 2015 2:30PM | Sep 17 2015 7:03PM | 49.782 | 48.475 |  | 27.074 | 1.307 | 21.401 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 4
U/22-1 | SGBM18 | Sep 8 2015 10:00AM | Sep 8 2015 5:40PM | 49.772 | 49.075 |  | 28.740 | 0.697 | 20.335 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 10, 3
U/25-1 | SGBM22 | Oct 24 2015 8:00PM | Oct 26 2015 11:57AM | 49.937 | 47.575 |  | 29.345 | 2.362 | 18.230 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.6 | 15.0 | -100.0 | G45T2 | 1, 2 | 7, 8
U/25-2 | SGBM20 | Oct 27 2015 2:30PM | Oct 28 2015 12:22AM | 50.066 | 47.575 |  | 29.128 | 2.491 | 18.447 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 3
U/27-1 | SGBM22 | Oct 29 2015 3:20PM | Oct 30 2015 3:54AM | 52.045 | 51.375 |  | 32.655 | 0.670 | 18.720 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.9 | 20.0 | -11.9 | G45T2 | 1, 2, 3 | 7, 6, 7
U/33-1 | SGBM03 | Oct 29 2015 5:30PM | Oct 30 2015 1:02AM | 52.018 | 51.325 |  | 30.027 | 0.693 | 21.298 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 18.0 | -13.6 | G45T2 | 1, 2, 3 | 6, 6, 6
T/21-1 | SGBM22 | Oct 13 2015 8:10AM | Oct 13 2015 6:55PM | 49.827 | 49.075 |  | 27.831 | 0.752 | 21.244 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 22.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 4, 7, 4, 7
T/23-1 | SGBM22 | Oct 7 2015 12:00PM | Oct 8 2015 1:20AM | 49.795 | 49.075 |  | 28.918 | 0.720 | 20.157 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 18.0 | -100.0 | G45T2 | 1, 2 | 8, 10
T/24-1 | SGBM22 | Oct 8 2015 12:00PM | Oct 9 2015 12:00AM | 49.795 | 49.075 |  | 28.918 | 0.720 | 20.157 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 17.0 | -100.0 | G45T2 | 1, 2 | 5, 12
T/25-1 | SGBM22 | Oct 24 2015 10:10AM | Oct 24 2015 4:47PM | 50.060 | 48.775 |  | 30.366 | 1.285 | 18.409 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.7 | 15.0 | 28.1 | G45T2 | 1, 2, 3 | 6, 6, 3
T/26-1 | SGBM22 | Oct 30 2015 3:20PM | Oct 30 2015 7:50PM | 52.240 | 51.375 |  | 32.775 | 0.865 | 18.600 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.8 | 15.0 | 3.2 | G45T2 | 1, 2, 3 | 7, 6, 2
AE/31a-1 | SGBM22 | Nov 19 2015 2:10PM | Nov 19 2015 8:40PM | 49.380 | 48.475 |  | 23.808 | 0.905 | 24.667 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
AE/36-1 | SGBM22 | Nov 18 2015 11:50AM | Nov 19 2015 12:17AM | 49.614 | 48.775 | 9 | 24.053 | 0.839 | 24.722 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.7 | 19.0 | 20.8 | G45T2 | 1, 2, 3 | 6, 6, 7
Aca/35-1 | SGBM02 | Nov 9 2015 1:30PM | Nov 11 2015 12:40PM | 49.686 | 48.775 | 9 | 23.703 | 0.911 | 25.072 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.0 | 20.0 | -100.0 | G45T2 | PJ 1442, PJ 1444, PJ 1446, PJ 1452 | 6, 6, 6, 2
Aca/36a-1 | SGBM08 | Oct 17 2015 3:30PM | Oct 17 2015 10:07PM | 49.588 | 49.075 |  | 24.015 | 0.513 | 25.060 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.9 | 20.0 | -100.0 | G45T2 | 1, 2 | 9, 11
Aca/37-1 | SGBM08 | Oct 19 2015 3:25PM | Oct 20 2015 3:04AM | 49.590 | 49.075 |  | 23.074 | 0.515 | 26.001 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.5 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
Aca/38-1 | SGBM08 | Oct 17 2015 9:45AM | Oct 17 2015 5:43PM | 49.553 | 49.075 |  | 22.017 | 0.478 | 27.058 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 21.0 | 22.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Aca/39-1 | SGBM08 | Oct 19 2015 6:00PM | Oct 20 2015 4:22AM | 49.515 | 49.075 |  | 20.990 | 0.440 | 28.085 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Aca/40-1 | SGBM08 | Oct 22 2015 12:20PM | Oct 23 2015 3:08AM | 49.515 | 49.075 |  | 20.990 | 0.440 | 28.085 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 18.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 5, 1
Aca/41-1 | SGBM08 | Oct 20 2015 12:20PM | Oct 20 2015 1:08PM | 49.583 | 49.075 |  | 21.067 | 0.508 | 28.008 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 18.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 5, 1
Aca/42-1 | SGBM08 | Oct 30 2015 4:10PM | Nov 2 2015 7:00PM | 49.616 | 49.075 | 9, 21, 24 | 21.614 | 0.541 | 27.461 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.5 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Aca/43-1 | SGBM22 | Nov 4 2015 9:30AM | Nov 4 2015 4:30PM | 49.623 | 49.075 | 9 | 20.994 | 0.548 | 28.081 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 13 | 17.9 | 26.0 | -100.0 | G45T2 | 1a, 2a, 3a, 4a | 7, 7, 6, 6
Aca/44-1 | SGBM02 | Nov 3 2015 10:10AM | Nov 3 2015 11:12PM | 49.660 | 49.075 | 9 | 21.429 | 0.585 | 27.646 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.6 | 27.0 | 53.5 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
Aca/45-1 | SGBM02 | Nov 6 2015 8:40AM | Nov 6 2015 9:09PM | 49.443 | 49.075 |  | 20.044 | 0.368 | 29.031 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
AB/33-1 | SGBM02 | Nov 9 2015 7:33PM | Nov 11 2015 3:05PM | 49.613 | 48.775 | 9, 20 | 25.463 | 0.838 | 23.312 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.8 | 22.0 | -100.0 | G45T2 | PJ 1454, PJ 1455, PJ 1461 | 7, 8, 7
AB/46-1 | SGBM19 | Nov 6 2015 3:10PM | Nov 7 2015 2:45AM | 49.412 | 47.875 |  | 18.833 | 1.537 | 29.042 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 27.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 6
AB/46-2 | SGBM17 | Nov 11 2015 3:29PM | Nov 12 2015 11:55AM | 49.304 | 47.875 | 9 | 18.523 | 1.429 | 29.352 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 22.0 | -100.0 | G45T2 | C480011619, C480011620 | 11, 11
AA/41-1 | SGBM19 | Oct 13 2015 8:10AM | Oct 13 2015 3:28PM | 49.572 | 48.725 |  | 22.639 | 0.847 | 26.086 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 18.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 4
AA/42-1 | SGBM08 | Oct 12 2015 1:00PM | Oct 12 2015 9:35PM | 49.533 | 48.725 |  | 22.678 | 0.808 | 26.047 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 19.0 | -100.0 | G35T2 | 1, 2 | 7, 12
Z/45-1 | SGBM16 | Dec 22 2015 2:10PM | Dec 26 2015 2:45PM | 49.484 | 47.425 |  | 18.347 | 2.059 | 29.078 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G45T2 | PJ 3512, PJ 3515, PJ 3517 | 8, 8, 7
Z/45-2 | SGBM08 | Oct 22 2015 11:00AM | Oct 22 2015 7:28PM | 49.772 | 47.425 |  | 20.386 | 2.347 | 27.039 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 7, 5
Y/46-1 | SGBM22 | Dec 4 2015 5:30PM | Dec 5 2015 6:11PM | 49.676 | 48.775 |  | 22.148 | 0.901 | 26.627 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 25.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 4
X/46-1 | SGBM22 | Dec 29 2015 9:15AM | Dec 29 2015 11:55PM | 49.649 | 48.775 |  | 22.010 | 0.874 | 26.765 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.0 | 20.0 | -100.0 | G35T2 | PJ 3709, PJ 3711, PJ 3713 | 8, 6, 6
W/46-1 | SGBM19 | Jan 15 2016 9:34AM | Jan 15 2016 7:05PM | 49.911 | 47.425 |  | 21.333 | 2.486 | 26.092 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 21.0 | -100.0 | G45T2 | PJ 4443, PJ 4445, PJ 4446 | 7, 7, 7
W/46-2 | SGBM31 | Jan 11 2016 9:36AM | Jan 12 2016 4:30PM | 50.005 | 47.425 |  | 22.154 | 2.580 | 25.271 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.1 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
V/46-1 | SGBM20 | Jan 20 2016 8:32AM | Jan 20 2016 11:35PM | 50.285 | 47.775 |  | 21.263 | 2.510 | 26.512 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
V/46-2 | SGBM20 | Jan 21 2016 8:42AM | Jan 21 2016 6:00PM | 50.249 | 47.775 |  | 21.042 | 2.474 | 26.733 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.0 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
V/41-1 | SGBM19 | Oct 21 2015 2:20PM | Oct 21 2015 10:58PM | 49.466 | 47.275 |  | 18.689 | 2.191 | 28.586 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 4, 7, 7, 7
U/36-1 | SGBM20 | Jan 8 2016 8:00AM | Jan 8 2016 5:20PM | 52.242 | 51.375 |  | 27.812 | 0.867 | 23.563 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.0 | 18.0 | -15.0 | G45T2 | 1, 2 | 8, 10
T/27-1 | SGBM01 | Dec 31 2015 8:00AM | Dec 31 2015 7:23PM | 52.154 | 51.375 |  | -20.100 | 0.779 | 71.475 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 45.5 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T/28-1 | SGBM01 | Dec 31 2015 9:30AM | Dec 31 2015 5:43PM | 52.083 | 51.375 |  | 32.628 | 0.708 | 18.747 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.9 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
T/29-1 | SGBM01 | Dec 29 2015 8:00AM | Dec 29 2015 9:30PM | 52.035 | 51.375 |  | 31.790 | 0.660 | 19.585 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.5 | 16.0 | -12.5 | G45T2 | 1, 2 | 8, 8
T/30-1 | SGBM01 | Dec 29 2015 10:10AM | Dec 29 2015 7:00PM | 52.026 | 51.375 |  | 30.720 | 0.651 | 20.655 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 16.0 | -13.1 | G45T2 | 1, 2 | 8, 8
T/31-1 | SGBM20 | Dec 29 2015 5:45PM | Dec 31 2015 2:40PM | 52.078 | 51.375 |  | -22.000 | 0.703 | 73.375 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 46.7 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 9, 7
T/32-1 | SGBM20 | Dec 29 2015 5:00PM | Dec 31 2015 2:07PM | 52.174 | 51.375 |  | 31.062 | 0.799 | 20.313 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 17.0 | 31.5 | G45T2 | 1, 2 | 8, 9
T/33-1 | SGBM16 | Jan 5 2016 11:00AM | Jan 5 2016 6:37PM | 52.274 | 51.375 |  | -23.200 | 0.899 | 74.575 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 47.4 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
T/34-1 | SGBM20 | Jan 2 2016 8:00AM | Jan 2 2016 6:08PM | 52.420 | 51.375 |  | 29.977 | 1.045 | 21.398 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
T/35-1 | SGBM20 | Dec 31 2015 7:00PM | Jan 2 2016 7:11PM | 52.270 | 51.375 |  | -24.000 | 0.895 | 75.375 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 48.0 | 18.0 | -62.5 | G45T2 | 1, 2 | 10, 8
T/36-1 | SGBM20 | Jan 5 2016 1:45PM | Jan 6 2016 1:44PM | 52.382 | 51.375 |  | 29.095 | 1.007 | 22.280 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
S/27-1 | SGBM03 | Dec 17 2015 3:35PM | Dec 19 2015 11:22AM | 52.108 | 51.375 |  | 32.752 | 0.733 | 18.623 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.8 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
S/30-1 | SGBM03 | Dec 23 2015 3:00PM | Dec 26 2015 3:45PM | 51.997 | 51.375 |  | 32.180 | 0.622 | 19.195 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 16.0 | -100.0 | G45T2 | 1, 2 | 9, 7
S/32-1 | SGBM01 | Dec 16 2015 10:30AM | Dec 16 2015 10:46PM | 51.989 | 49.725 |  | 28.555 | 2.264 | 21.170 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
S/32-2 | SGBM01 | Dec 17 2015 1:00PM | Dec 18 2015 6:45PM | 52.119 | 49.725 |  | 28.520 | 2.394 | 21.205 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2 | 10, 7
S/34-1 | SGBM20 | Dec 17 2015 1:45PM | Dec 18 2015 3:02PM | 52.187 | 49.725 |  | -26.000 | 2.462 | 75.725 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 48.2 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
S/34-2 | SGBM01 | Dec 22 2015 11:25AM | Dec 23 2015 12:53AM | 52.202 | 49.725 |  | 29.624 | 2.477 | 20.101 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 20.0 | -100.0 | G45T2 | 1, 2 | 11, 9
S/35-1 | SGBM16 | Jan 2 2016 1:30PM | Jan 2 2016 9:35PM | 52.265 | 49.725 |  | 29.588 | 2.540 | 20.137 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 17.0 | -100.0 | G45T2 | 1, 2 | 8, 9
S/35-2 | SGBM20 | Jan 5 2016 1:00PM | Jan 5 2016 7:20PM | 52.320 | 49.725 |  | 29.246 | 2.595 | 20.479 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.0 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
S/38-1 | SGBM16 | Sep 29 2015 1:00PM | Sep 29 2015 11:57PM | 52.693 | 49.575 |  | 26.526 | 3.118 | 23.049 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.7 | 17.0 | -100.0 | G45T2 | 1, 2 | 11, 6
S/38-2 | SGBM08 | Oct 1 2015 10:00PM | Oct 2 2015 5:11PM | 52.635 | 49.575 |  | 26.575 | 3.060 | 23.000 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.6 | 18.0 | -100.0 | G45T2 | 1, 2 | 7, 11
R/27-1 | SGBM01 | Dec 15 2015 8:00AM | Dec 16 2015 7:55PM | 52.047 | 51.375 |  | 33.370 | 0.672 | 18.005 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.5 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
R/29-1 | SGBM01 | Dec 19 2015 5:00PM | Dec 20 2015 12:26AM | 51.836 | 51.375 |  | 32.126 | 0.461 | 19.249 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 17.0 | -100.0 | G45T2 | 1, 2 | 10, 7
R/30-1 | SGBM01 | Dec 19 2015 6:00PM | Dec 21 2015 6:59PM | 51.724 | 51.375 |  | 30.839 | 0.349 | 20.536 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 16.0 | -13.1 | G45T2 | 1, 2 | 8, 8
R/31-1 | SGBM20 | Jan 4 2016 8:00AM | Jan 4 2016 11:00AM | 51.994 | 51.375 |  | 29.875 | 0.619 | 21.500 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.7 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
R/32-1 | SGBM01 | Dec 22 2015 12:04PM | Dec 23 2015 7:39PM | 52.007 | 49.875 |  | 28.630 | 2.132 | 21.245 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
R/32-2 | SGBM20 | Dec 31 2015 2:20PM | Dec 31 2015 11:45PM | 52.127 | 49.875 |  | 28.670 | 2.252 | 21.205 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
R/35-1 | SGBM03 | Dec 28 2015 2:15PM | Dec 30 2015 12:05AM | 52.260 | 49.875 |  | 31.728 | 2.385 | 18.147 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.5 | 17.0 | -11.5 | G45T2 | 1, 2 | 8, 9
R/35-2 | SGBM16 | Jan 4 2016 11:00AM | Jan 4 2016 2:10PM | 52.338 | 49.875 |  | 31.714 | 2.463 | 18.161 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.6 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
R/36-1 | SGBM08 | Sep 29 2015 1:30PM | Sep 30 2015 1:51PM | 52.427 | 49.725 |  | 30.708 | 2.702 | 19.017 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.1 | 14.0 | -100.0 | G45T2 | 1, 2 | 11, 3
R/36-2 | SGBM20 | Jan 7 2016 9:00AM | Jan 7 2016 7:35PM | 52.470 | 49.725 |  | 30.200 | 2.745 | 19.525 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.4 | 16.0 | 28.8 | G45T2 | 1, 2 | 8, 8
R/37-1 | SGBM20 | Jan 15 2016 10:00AM | Jan 15 2016 8:05PM | 52.802 | 50.175 |  | 29.651 | 2.627 | 20.524 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 17.0 | -100.0 | G45T2 | 1, 2 | 9, 8
R/37-2 | SGBM20 | Jan 12 2016 10:30AM | Jan 12 2016 5:00PM | 52.700 | 50.175 |  | 30.086 | 2.525 | 20.089 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 17.0 | -100.0 | G45T2 | 1, 2 | 7, 10
R/37-3 | SGBM20 | Jan 13 2016 5:00PM | Jan 14 2016 12:35PM | 52.640 | 50.175 |  | 29.930 | 2.465 | 20.245 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 18.0 | 39.7 | G45T2 | 1, 2 | 10, 8
R/39-1 | SGBM08 | Sep 30 2015 11:00AM | Oct 1 2015 12:21AM | 52.650 | 51.375 |  | 28.298 | 1.275 | 23.077 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.7 | 18.0 | -14.7 | G45T2 | 1, 2 | 7, 11
Q/27-1 | SGBM01 | Dec 12 2015 6:20PM | Dec 14 2015 4:20PM | 52.106 | 51.375 |  | 32.294 | 0.731 | 19.081 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.1 | 15.0 | 23.6 | G45T2 | 1, 2 | 10, 5
Q/28-1 | SGBM01 | Dec 12 2015 4:30PM | Dec 13 2015 1:04AM | 52.067 | 51.375 |  | 32.273 | 0.692 | 19.102 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
Q/29-1 | SGBM01 | Dec 15 2015 8:00AM | Dec 15 2015 10:02PM | 52.000 | 51.375 |  | 35.206 | 0.625 | 16.169 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.3 | 18.0 | -100.0 | G45T2 | 1, 2 | 11, 7
Q/30-1 | SGBM01 | Dec 21 2015 3:00PM | Dec 21 2015 8:34PM | 51.696 | 51.375 |  | 30.994 | 0.321 | 20.381 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.0 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
Q/32-1 | SGBM20 | Dec 17 2015 1:00PM | Dec 17 2015 11:04PM | 52.102 | 51.075 |  | 30.954 | 1.027 | 20.121 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
Q/37-3 | SGBM16 | Sep 29 2015 8:00AM | Sep 29 2015 6:00PM | 52.725 | 50.175 |  | 30.968 | 2.550 | 19.207 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 16.0 | -12.2 | G45T2 | 1, 2 | 8, 8
P/26-1 | SGBM20 | Dec 24 2015 4:45PM | Dec 26 2015 11:45AM | 52.000 | 51.275 |  | 32.124 | 0.725 | 19.151 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
P/27-1 | SGBM01 | Dec 15 2015 8:00AM | Dec 16 2015 3:00PM | 51.818 | 51.375 |  | 32.224 | 0.443 | 19.151 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
P/28-1 | SGBM01 | Dec 12 2015 5:15PM | Dec 14 2015 7:30PM | 51.991 | 51.375 |  | 32.218 | 0.616 | 19.157 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 10, 5
P/29-1 | SGBM01 | Dec 15 2015 11:30AM | Dec 16 2015 1:30PM | 51.900 | 51.375 |  | 31.262 | -51.375 | 20.113 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
P/30-1 | SGBM01 | Dec 18 2015 11:00AM | Dec 19 2015 8:22PM | 51.909 | 51.375 |  | 31.270 | 0.534 | 20.105 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 16.0 | -100.0 | G45T2 | 1, 2 | 12, 4
P/31-1 | SGBM20 | Dec 24 2015 1:05PM | Dec 26 2015 1:41PM | 52.051 | 51.375 |  | 31.134 | 0.676 | 20.241 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 3
P/32-1 | SGBM01 | Dec 23 2015 9:30AM | Dec 23 2015 1:55PM | 52.055 | 49.875 |  | 30.702 | 2.180 | 19.173 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
P/32-2 | SGBM20 | Dec 26 2015 6:15PM | Dec 28 2015 2:31PM | 52.077 | 49.875 |  | 29.720 | 2.202 | 20.155 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
P/34-1 | SGBM16 | Jan 4 2016 3:10PM | Jan 4 2016 7:35PM | 51.928 | 50.075 |  | 33.314 | 1.853 | 16.761 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.7 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
P/34-2 | SGBM01 | Dec 31 2015 4:30PM | Jan 2 2016 3:55PM | 50.075 | 50.075 |  | 33.470 | 0.000 | 16.605 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.6 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
P/35-1 | SGBM01 | Dec 21 2015 7:25PM | Dec 22 2015 3:17PM | 51.826 | 49.875 |  | -19.000 | 1.951 | 68.875 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 43.8 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
P/35-2 | SGBM20 | Jan 5 2016 1:00PM | Jan 5 2016 4:25PM | 51.930 | 49.875 |  | 33.540 | 2.055 | 16.335 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.4 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
P/36-1 | SGBM16 | Sep 30 2015 7:10PM | Oct 1 2015 5:07PM | 51.974 | 49.725 |  | 32.653 | 2.249 | 17.072 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.9 | 16.0 | -100.0 | G45T2 | 1, 2 | 9, 7
P/36-2 | SGBM08 | Oct 2 2015 8:00PM | Oct 3 2015 3:51PM | 51.898 | 49.725 |  | 32.725 | 2.173 | 17.000 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.8 | 18.0 | -10.8 | G45T2 | 1, 2 | 12, 6
N/26-1 | SGBM21 | Nov 25 2015 1:30PM | Nov 26 2015 1:20AM | 53.317 | 51.375 | 9 | 31.714 | -51.375 | 19.661 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.5 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/29-1 | SGBM20 | Dec 24 2015 10:40AM | Dec 25 2015 2:38PM | 51.903 | 51.075 |  | 30.700 | 0.828 | 20.375 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.0 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 2
N/32-1 | SGBM01 | Dec 21 2015 6:00PM | Dec 21 2015 10:30PM | 51.876 | 49.875 |  | 32.749 | 2.001 | 17.126 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.9 | 17.0 | -100.0 | G45T2 | 1, 2 | 6, 11
N/32-2 | SGBM01 | Dec 17 2015 6:00PM | Dec 18 2015 1:15AM | 52.043 | 49.875 |  | 32.709 | 2.168 | 17.166 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.9 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/33-1 | SGBM20 | Dec 30 2015 10:00AM | Dec 30 2015 9:55PM | 52.040 | 50.175 |  | 32.202 | 1.865 | 17.973 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 10, 5
N/33-2 | SGBM20 | Dec 26 2015 5:40PM | Dec 28 2015 9:30PM | 51.998 | 50.175 |  | 32.856 | 1.823 | 17.319 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.0 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/34-1 | SGBM20 | Jan 4 2016 6:50PM | Jan 5 2016 11:05AM | 51.785 | 50.175 |  | 33.790 | 1.610 | 16.385 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/34-2 | SGBM16 | Jan 6 2016 1:00PM | Jan 6 2016 5:37PM | 51.930 | 50.175 |  | 33.513 | 1.755 | 16.662 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.6 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
N/35-1 | SGBM16 | Jan 4 2016 1:30PM | Jan 4 2016 4:20PM | 52.002 | 49.875 |  | 33.546 | 2.127 | 16.329 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.4 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/35-2 | SGBM16 | Jan 5 2016 5:30PM | Jan 6 2016 10:47AM | 51.730 | 49.875 |  | -19.100 | 1.855 | 68.975 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 43.9 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
N/36-1 | SGBM16 | Jan 8 2016 5:00PM | Jan 9 2016 1:20PM | 51.760 | 49.725 |  | 32.535 | 2.035 | 17.190 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 10.9 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/36-2 | SGBM20 | Jan 11 2016 2:30PM | Jan 12 2016 11:45AM | 52.006 | 49.725 |  | 32.434 | 2.281 | 17.291 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.0 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
N/38-1 | SGBM20 | Jan 12 2016 8:10AM | Jan 12 2016 9:25PM | 51.987 | 50.175 |  | 29.690 | 1.812 | 20.485 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.0 | 17.0 | -13.0 | G45T2 | 1, 2, 3 | 6, 6, 5
N/38-2 | SGBM20 | Jan 11 2016 9:00AM | Jan 11 2016 7:00PM | 51.930 | 50.175 |  | 29.922 | 1.755 | 20.253 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 17.0 | -100.0 | G45T2 | 1, 2 | 10, 7
N/39-1 | SGBM08 | Oct 3 2015 8:00PM | Oct 5 2015 12:12PM | 51.990 | 51.375 |  | 29.436 | 0.615 | 21.939 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.0 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 7, 1
N/40-1 | SGBM21 | Oct 8 2015 2:00PM | Oct 8 2015 7:10PM | 52.010 | 50.575 |  | 28.375 | 1.435 | 22.200 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.1 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 2, 7, 7
M/37-1 | SGBM15 | Dec 29 2015 9:50AM | Dec 29 2015 9:36PM | 51.821 | 51.375 |  | 32.144 | 0.446 | 19.231 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 15.0 | 22.6 | G45T2 | PJ 3694, PJ 3699 | 8, 7
M/40-1 | SGBM15 | Dec 30 2015 8:20AM | Dec 31 2015 3:05AM | 51.884 | 50.575 |  | 24.301 | 1.309 | 26.274 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 18.0 | -16.7 | G45T2 | PJ 3768, PJ 3770 | 10, 8
T/20-1 | SGBM22 | Oct 28 2015 3:20PM | Oct 28 2015 11:59PM | 49.812 | 47.275 |  | 26.017 | 2.537 | 21.258 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 3
T/20-2 | SGBM22 | Oct 26 2015 12:00PM | Oct 26 2015 9:28PM | 49.937 | 47.275 |  | 25.704 | 2.662 | 21.571 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
S/15-1 | SGBM03 | Dec 12 2015 1:00PM | Dec 13 2015 3:05AM | 56.000 | 53.275 |  | 31.090 | 2.725 | 22.185 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.1 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
S/15-2 | SGBM20 | Dec 5 2015 3:55PM | Dec 8 2015 1:35PM | 55.864 | 53.275 | 9 | 31.085 | 2.589 | 22.190 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.1 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
S/17-1 | SGBM21 | Nov 19 2015 8:00PM | Nov 20 2015 6:47PM | 55.861 | 53.875 | 9 | 33.018 | 1.986 | 20.857 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.3 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
S/17-2 | SGBM20 | Nov 28 2015 10:30AM | Nov 28 2015 7:45PM | 55.866 | 53.875 | 9 | 33.629 | 1.991 | 20.246 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 16.0 | -12.9 | G45T2 | 1, 2, 3 | 6, 5, 5
S/18-1 | SGBM21 | Nov 19 2015 8:25AM | Nov 20 2015 3:00PM | 55.915 | 53.875 | 9 | 33.217 | 2.040 | 20.658 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.1 | 16.0 | 2.9 | G45T2 | 1, 2 | 8, 8
S/18-2 | SGBM03 | Nov 26 2015 10:57AM | Nov 26 2015 8:44PM | 55.923 | 53.875 | 9 | 33.623 | 2.048 | 20.252 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 16.0 | -12.9 | G45T2 | 1, 2 | 8, 8
S/19-1 | SGBM21 | Nov 23 2015 5:25PM | Nov 24 2015 2:03PM | 55.696 | 53.875 | 9, 17.5 | 33.171 | 1.821 | 20.704 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.2 | 16.0 | -13.2 | G45T2 | 1, 2 | 8, 8
S/19-2 | SGBM20 | Nov 29 2015 1:00AM | Nov 30 2015 8:23PM | 55.967 | 53.875 | 9 | 33.763 | 2.092 | 20.112 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 16.0 | -12.8 | G45T2 | 1, 2 | 8, 8
S/21-1 | SGBM20 | Dec 22 2015 6:10PM | Dec 23 2015 10:46PM | 50.371 | 47.425 |  | 26.232 | 2.946 | 21.193 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
S/21-2 | SGBM21 | Dec 4 2015 10:00PM | Dec 5 2015 10:15AM | 49.994 | 47.425 |  | 26.417 | 2.569 | 21.008 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 2
S/22-1 | SGBM21 | Dec 2 2015 9:40AM | Dec 3 2015 2:38PM | 49.763 | 48.625 | 9 | 30.138 | 1.138 | 18.487 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.8 | 16.0 | -11.8 | G45T2 | 1, 2 | 8, 8
S/23-1 | SGBM21 | Dec 2 2015 8:00AM | Dec 3 2015 3:49PM | 49.794 | 48.625 | 9 | 28.294 | 1.169 | 20.331 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 16.0 | -12.9 | G45T2 | 1, 2 | 8, 8
S/25-1 | SGBM01 | Dec 30 2015 9:00AM | Dec 30 2015 9:25PM | 50.478 | 47.425 |  | 29.004 | 3.053 | 18.421 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.7 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
S/25-2 | SGBM16 | Dec 31 2015 9:50AM | Dec 31 2015 11:25PM | 50.691 | 47.425 |  | 29.139 | 3.266 | 18.286 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.6 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
R/17-1 | SGBM20 | Nov 18 2015 5:00PM | Nov 18 2015 9:18PM | 55.830 | 53.875 |  | 32.370 | 1.955 | 21.505 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.7 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
R/17-2 | SGBM21 | Nov 25 2015 6:05PM | Nov 26 2015 5:01PM | 55.897 | 53.875 |  | 32.156 | 2.022 | 21.719 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.8 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 6
R/18-1 | SGBM20 | Nov 23 2015 4:45PM | Nov 26 2015 2:26AM | 55.940 | 53.875 | 9 | 33.635 | -53.875 | 20.240 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 20.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 2
R/18-2 | SGBM20 | Nov 18 2015 5:55PM | Nov 19 2015 10:54AM | 55.903 | 53.875 | 9 | 33.909 | 2.028 | 19.966 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.7 | 18.0 | -12.7 | G45T2 | 1, 2, 3 | 6, 6, 6
R/20-1 | SGBM03 | Dec 17 2015 1:00PM | Dec 17 2015 8:02PM | 54.300 | 50.475 |  | 30.300 | 3.825 | 20.175 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
R/20-2 | SGBM20 | Dec 19 2015 10:25AM | Dec 19 2015 11:35PM | 54.437 | 50.475 |  | 30.231 | 3.962 | 20.244 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 20.0 | 55.3 | G45T2 | 1, 2 | 10, 10
R/20-3 | SGBM20 | Dec 18 2015 8:00AM | Dec 18 2015 11:37PM | 54.357 | 50.475 |  | 30.294 | 3.882 | 20.181 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
R/21-1 | SGBM03 | Dec 26 2015 5:44PM | Dec 28 2015 10:54AM | 50.528 | 47.875 |  | -24.600 | 2.653 | 72.475 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 46.1 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
R/21-2 | SGBM20 | Dec 23 2015 8:00AM | Dec 24 2015 12:44PM | 80.357 | 47.875 |  | 26.247 | 32.482 | 21.628 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.8 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 4
R/22-1 | SGBM21 | Nov 29 2015 10:00AM | Dec 1 2015 11:55AM | 50.335 | 47.875 | 9 | 26.723 | 2.460 | 21.152 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | 3.5 | G45T2 | 1, 2 | 11, 6
R/22-2 | SGBM21 | Dec 4 2015 10:40AM | Dec 5 2015 9:23PM | 50.241 | 47.875 | 9 | 26.662 | 2.366 | 21.213 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
R/25-1 | SGBM21 | Dec 4 2015 8:00AM | Dec 7 2015 6:16PM | 50.177 | 50.075 | 9 | 31.896 | 0.102 | 18.179 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.6 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
R/25-2 | SGBM01 | Dec 11 2015 7:00PM | Dec 12 2015 2:54PM | 50.304 | 50.075 |  | -19.200 | 0.229 | 69.275 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 44.1 | 15.0 | -44.1 | G45T2 | 2, 2 | 8, 7
Q/21-1 | SGBM21 | Nov 20 2015 7:15PM | Nov 21 2015 6:34PM | 53.921 | 52.675 | 9 | 31.354 | 1.246 | 21.321 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
Q/24-1 | SGBM05 | Nov 11 2015 2:57PM | Nov 12 2015 12:50PM | 53.445 | 52.775 | 9 | 33.498 | 0.670 | 19.277 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.3 | 12.0 | -100.0 | G45T2 | 1, 2 | 6, 6
P/17-1 | SGBM09 | Oct 6 2015 8:00AM | Oct 6 2015 7:32PM | 55.789 | 53.875 |  | 31.737 | 1.914 | 22.138 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.1 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
P/17-2 | SGBM03 | Nov 26 2015 11:30AM | Nov 27 2015 4:52PM | 55.832 | 53.875 | 9, 20 | 31.573 | 1.957 | 22.302 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 17.0 | 2.8 | G45T2 | 1, 2, 3 | 6, 6, 5
P/18-1 | SGBM03 | Dec 3 2015 12:30PM | Dec 4 2015 5:30PM | 55.745 | 53.875 | 9, 16 | 32.874 | 1.870 | 21.001 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 17.0 | -13.4 | G45T2 | 1, 2 | 9, 8
P/18-2 | SGBM20 | Dec 8 2015 10:30AM | Dec 9 2015 9:05PM | 55.684 | 53.875 | 9 | 32.527 | 1.809 | 21.348 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 18.0 | -100.0 | G45T2 | 1, 2 | 9, 9
P/19-1 | SGBM20 | Dec 10 2015 6:14PM | Dec 11 2015 6:00PM | 55.780 | 51.575 | 9 | 31.095 | 4.205 | 20.480 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.0 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
P/19-2 | SGBM20 | Nov 19 2015 2:30PM | Nov 19 2015 9:15PM | 55.822 | 51.575 | 9 | 31.549 | 4.247 | 20.026 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.7 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
P/21-1 | SGBM05 | Nov 15 2015 9:40AM | Nov 17 2015 12:10PM | 53.736 | 51.575 | 9 | 30.318 | 2.161 | 21.257 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
P/21-2 | SGBM05 | Nov 9 2015 1:00PM | Nov 11 2015 11:25AM | 53.720 | 51.575 | 9 | 30.159 | 2.145 | 21.416 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 17.0 | 24.8 | G45T2 | 1, 2, 3 | 6, 6, 5
P/24-1 | SGBM05 | Nov 15 2015 9:00AM | Nov 17 2015 2:47PM | 53.350 | 52.475 | 9 | 31.984 | 0.875 | 20.491 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.0 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 2
P/25-1 | SGBM05 | Nov 12 2015 5:45PM | Nov 13 2015 10:24PM | 53.357 | 51.275 | 9 | 32.041 | 2.082 | 19.234 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.2 | 15.0 | -100.0 | G45T2 | 1, 2 | 9, 6
N/15-1 | SGBM03 | Dec 5 2015 5:00PM | Dec 8 2015 12:05PM | 55.753 | 53.425 | 9 | 28.057 | 2.328 | 25.368 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.1 | 20.0 | -16.1 | G45T2 | 1, 2, 3 | 7, 7, 6
N/15-2 | SGBM03 | Dec 3 2015 11:30AM | Dec 4 2015 4:42PM | 55.710 | 53.425 | 9 | 27.835 | 2.285 | 25.590 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.3 | 20.0 | 3.7 | G45T2 | 1, 2 | 10, 10
N/17-1 | SGBM03 | Dec 11 2015 4:00PM | Dec 12 2015 3:58PM | 55.694 | 53.875 |  | 30.707 | 1.819 | 23.168 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.7 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
N/17-2 | SGBM20 | Dec 7 2015 4:50PM | Dec 9 2015 11:55AM | 55.646 | 53.875 | 9 | 30.487 | 1.771 | 23.388 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.9 | 19.0 | 4.1 | G45T2 | 1, 2, 3 | 7, 7, 5
N/18-1 | SGBM03 | Dec 14 2015 1:00PM | Dec 14 2015 9:04PM | 55.380 | 53.875 |  | 32.497 | 1.505 | 21.378 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
N/18-2 | SGBM20 | Dec 12 2015 1:05PM | Dec 12 2015 8:08PM | 55.358 | 53.875 |  | 32.318 | 1.483 | 21.557 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.7 | 16.0 | -100.0 | G45T2 | 1, 2 | 11, 5
N/19-1 | SGBM20 | Dec 8 2015 11:20AM | Dec 9 2015 3:19PM | 55.404 | 51.575 | 9 | 30.410 | 3.829 | 21.165 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
N/19-2 | SGBM03 | Dec 7 2015 8:00AM | Dec 7 2015 7:57PM | 55.105 | 51.575 | 9, 24 | 30.464 | 3.530 | 21.111 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 7, 6
N/20-1 | SGBM03 | Dec 15 2015 10:30AM | Dec 15 2015 7:41PM | 54.555 | 51.575 |  | 30.339 | 2.980 | 21.236 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
N/20-2 | SGBM20 | Dec 18 2015 1:00PM | Dec 18 2015 9:03PM | 54.167 | 51.575 |  | 30.420 | 2.592 | 21.155 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
N/24-1 | SGBM05 | Nov 12 2015 11:05AM | Nov 13 2015 11:08AM | 53.445 | 52.475 | 9 | 33.498 | 0.970 | 18.977 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.1 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
N/25-1 | SGBM05 | Nov 14 2015 9:00AM | Nov 16 2015 11:50AM | 53.323 | 52.475 | 9 | 32.162 | 0.848 | 20.313 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
M1/15-1 | SGBM17 | Jan 30 2016 10:00AM | Jan 30 2016 8:10PM | 55.735 | 54.625 |  | 29.460 | 1.110 | 25.165 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.0 | 18.0 | -16.0 | G45T2 | 5144, 5150 | 10, 8
M/15a-1 | SGBM20 | Dec 1 2015 8:00AM | Dec 2 2015 5:16PM | 55.669 | 54.625 | 9 | 27.995 | 1.044 | 26.630 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 20.0 | -16.9 | G45T2 | 1, 2, 3 | 7, 7, 6
M/16-1 | SGBM20 | Nov 27 2015 8:30AM | Nov 28 2015 3:35PM | 55.584 | 54.625 | 9 | 30.316 | 0.959 | 24.309 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.5 | 18.0 | -15.5 | G45T2 | 1, 2, 3 | 6, 6, 6
M/17-1 | SGBM20 | Nov 27 2015 10:30AM | Nov 27 2015 9:26PM | 55.557 | 54.625 | 9 | 31.086 | 0.932 | 23.539 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.0 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
M/18-1 | SGBM21 | Nov 27 2015 9:45AM | Nov 27 2015 11:05PM | 55.565 | 53.425 | 9 | 31.088 | -53.425 | 22.337 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.2 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
M/18-2 | SGBM03 | Dec 1 2015 5:00PM | Dec 2 2015 11:20AM | 55.478 | 53.425 | 9 | -25.000 | 2.053 | 78.425 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 49.9 | 18.0 | -49.9 | G45T2 | 1, 2, 3 | 6, 6, 6
Fa/35-1 | SGBM20 | Nov 14 2015 11:25AM | Nov 14 2015 4:17PM | 52.238 | 50.775 | 9 | 29.537 | -50.775 | 21.238 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
Ga/35-1 | SGBM20 | Nov 9 2015 8:05PM | Nov 11 2015 5:15PM | 52.235 | 51.375 | 9 | 31.800 | 0.860 | 19.575 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.5 | 15.0 | -100.0 | G45T2 | pj1463, pj1462 | 7, 8
J/35-1 | SGBM20 | Nov 4 2015 8:40AM | Nov 4 2015 6:15PM | 52.027 | 51.375 | 9 | 30.610 | 0.652 | 20.765 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.2 | 17.0 | -13.2 | G45T2 | 1, 2, 3 | 6, 6, 5
K/35-1 | SGBM20 | Nov 4 2015 9:40AM | Nov 5 2015 12:50AM | 52.036 | 51.375 | 9 | 30.399 | 0.661 | 20.976 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.3 | 17.0 | -13.3 | G45T2 | 1, 2, 3 | 7, 8, 2
L/35-1 | SGBM20 | Nov 3 2015 5:25PM | Nov 4 2015 10:20AM | 51.945 | 51.075 | 9 | 29.865 | 0.870 | 21.210 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 18.0 | -13.5 | G45T2 | 1, 2, 3 | 6, 6, 6
Ka/61-1 | SGBM17 | Oct 28 2015 5:20PM | Oct 29 2015 1:29PM | 52.030 | 49.775 |  | 12.550 | 2.255 | 37.225 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.7 | 29.0 | -100.0 | G45T2 | C480011008, C170013243, C170013244, C480011021 | 11, 8, 8, 2
Ka/62-1 | SGBM08 | Dec 19 2015 8:51AM | Dec 19 2015 10:44PM | 52.026 | 49.775 |  | 11.483 | 2.251 | 38.292 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.4 | 29.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 6, 12
K/61-1 | SGBM02 | Dec 5 2015 12:30PM | Dec 6 2015 12:58AM | 51.990 | 51.375 | 10 | 12.202 | 0.615 | 39.173 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.9 | 30.0 | -100.0 | G45T2 | PJ 2679, PJ 2681, PJ 2684, PJ 2688 | 10, 8, 9, 3
K/62-1 | SGBM02 | Dec 7 2015 1:50PM | Dec 8 2015 9:20PM | 52.031 | 51.375 | 9, 15, 30 | 12.258 | 0.656 | 39.117 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.9 | 28.0 | -100.0 | G45T2 | PJ 2780, PJ 2789, PJ 2790 | 8, 8, 12
K/63-1 | SGBM02 | Dec 11 2015 11:45AM | Dec 12 2015 12:15AM | 52.094 | 51.375 |  | 12.094 | 0.719 | 39.281 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.0 | 27.0 | 12.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 7
K/52-1 | SGBM23 | Oct 27 2015 8:10AM | Oct 27 2015 6:37PM | 52.162 | 51.275 |  | 16.434 | 0.887 | 34.841 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.2 | 29.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 11, 11
K/63a-1 | SGBM02 | Dec 11 2015 12:15PM | Dec 12 2015 6:45PM | 52.106 | 51.375 |  | 12.106 | 0.731 | 39.269 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.0 | 28.0 | 8.1 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
J/52-1 | SGBM01 | Oct 26 2015 9:00AM | Oct 26 2015 7:13PM | 52.089 | 51.375 |  | 15.723 | 0.714 | 35.652 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.7 | 28.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 6
J/61-1 | SGBM02 | Dec 5 2015 11:45AM | Dec 5 2015 10:59PM | 51.972 | 51.375 | 10 | 11.264 | 0.597 | 40.111 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.5 | 28.0 | -100.0 | G45T2 | PJ 2669, PJ 2673, PJ 2675 | 12, 9, 7
J/63-1 | SGBM02 | Dec 8 2015 8:22PM | Dec 9 2015 9:50PM | 51.979 | 51.275 | 9 | 10.829 | 0.704 | 40.446 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.7 | 38.0 | 47.7 | G45T2 | C480012952, C480012961, C480012964 | 10, 10, 10
H/52-1 | SGBM23 | Oct 25 2015 6:15PM | Oct 26 2015 3:35PM | 52.034 | 51.375 |  | 13.945 | 0.659 | 37.430 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.8 | 27.0 | 13.4 | G45T2 | 1, 2, 3 | 11, 11, 5
H/63-1 | SGBM15 | Nov 7 2015 10:28AM | Nov 7 2015 8:10PM | 51.600 | 51.375 | 9, 18, 32.3 | 9.412 | 0.225 | 41.963 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.7 | 33.0 | -26.7 | G45T2 | PJ 1384, PJ 1386, PJ 1387, PJ 1390, PJ 1394 | 7, 7, 7, 7, 5
H/63a-1 | SGBM17 | Nov 2 2015 11:55AM | Nov 3 2015 11:01AM | 52.032 | 50.725 | 9, 42 | -42.800 | 1.307 | 93.525 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 59.5 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
G/52-1 | SGBM23 | Oct 26 2015 10:40AM | Oct 26 2015 7:43PM | 51.964 | 51.375 |  | 12.841 | 0.589 | 38.534 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.5 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 11, 11
G/53-1 | SGBM18 | Oct 16 2015 8:30AM | Oct 16 2015 3:12PM | 51.900 | 51.375 |  | 12.086 | 0.525 | 39.289 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.0 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 4, 9, 11
G/63-1 | SGBM15 | Nov 5 2015 8:23PM | Nov 9 2015 8:01PM | 51.810 | 51.275 | 9, 15 | 9.964 | 0.535 | 41.311 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.3 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 3, 7, 7, 9, 5
F/52-1 | SGBM23 | Oct 27 2015 8:30PM | Oct 28 2015 12:25PM | 51.895 | 51.075 |  | 10.577 | 0.820 | 40.498 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.8 | 30.0 | 16.4 | G45T2 | 1, 2, 3 | 10, 10, 10
F/53-1 | SGBM18 | Oct 9 2015 7:30PM | Oct 10 2015 4:00PM | 51.882 | 51.375 |  | 11.310 | 0.507 | 40.065 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.5 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 10
F/54-1 | SGBM23 | Oct 22 2015 8:10AM | Oct 22 2015 5:07PM | 51.776 | 51.375 |  | 10.923 | 0.401 | 40.452 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.7 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 4, 11, 11, 2
F/62-1 | SGBM15 | Oct 30 2015 11:45AM | Oct 30 2015 8:35PM | 51.903 | 51.275 |  | 10.033 | 0.628 | 41.242 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.2 | 29.0 | 10.5 | G45T2 | 1, 2, 3 | 10, 10, 9
F/63-1 | SGBM23 | Oct 31 2015 8:00AM | Oct 31 2015 5:56PM | 51.910 | 51.275 |  | 10.863 | 0.635 | 40.412 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.7 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 2, 10, 10, 6
E/53-1 | SGBM18 | Oct 18 2015 7:45PM | Oct 19 2015 4:54PM | 51.732 | 51.375 |  | 10.275 | 0.357 | 41.100 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.2 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 4, 7, 4, 7, 6, 4
E/54-1 | SGBM15 | Oct 28 2015 9:40AM | Oct 28 2015 5:40PM | 51.830 | 51.375 |  | 10.182 | 0.455 | 41.193 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.2 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 3
E/61-1 | SGBM15 | Oct 22 2015 8:00AM | Oct 22 2015 2:42PM | 51.960 | 51.375 |  | 12.082 | 0.585 | 39.293 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.0 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 2, 10, 10, 6
E/62-1 | SGBM17 | Nov 3 2015 3:15PM | Nov 4 2015 5:25PM | 51.848 | 51.375 | 9, 19 | 12.304 | 0.473 | 39.071 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.9 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 3, 7
E/63a-1 | SGBM23 | Nov 7 2015 11:45AM | Nov 9 2015 10:17PM | 51.660 | 51.375 | 9, 15 | -39.200 | 0.285 | 90.575 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 57.6 | 28.0 | -57.6 | G45T2 | PJ 1396, PJ 1397, PJ 1399, PJ 1400 | 7, 7, 7, 7
D/53-1 | SGBM17 | Oct 20 2015 8:00PM | Oct 21 2015 2:11PM | 51.912 | 51.375 |  | 10.248 | 0.537 | 41.127 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.2 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 11, 10
D/54-1 | SGBM17 | Oct 30 2015 8:00AM | Oct 30 2015 9:55PM | 52.030 | 51.375 |  | 10.371 | 0.655 | 41.004 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 2, 11, 11, 11
D/55-1 | SGBM20 | Oct 31 2015 9:00AM | Nov 2 2015 10:20AM | 51.960 | 51.375 |  | 10.201 | 0.585 | 41.174 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.2 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 6, 7, 6
D/56-1 | SGBM17 | Oct 28 2015 3:00PM | Oct 29 2015 8:27PM | 51.910 | 51.375 |  | 11.205 | 0.535 | 40.170 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.6 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 11, 10
D/59-1 | SGBM23 | Oct 30 2015 8:10PM | Oct 31 2015 12:24PM | 51.800 | 51.375 |  | 12.947 | 0.425 | 38.428 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.4 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
D/60-1 | SGBM23 | Oct 30 2015 8:00AM | Oct 30 2015 3:35PM | 51.930 | 51.375 |  | 14.352 | 0.555 | 37.023 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.6 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 3
D/61-1 | SGBM20 | Oct 31 2015 3:25PM | Nov 2 2015 10:20AM | 51.950 | 51.375 |  | 15.334 | 0.575 | 36.041 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.9 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 7, 7, 8
D/62-1 | SGBM18 | Sep 11 2015 10:00AM | Sep 11 2015 6:30PM | 51.743 | 51.375 |  | 11.903 | 0.368 | 39.472 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.1 | 34.0 | 19.5 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 9, 4
D/63a-1 | SGBM02 | Nov 12 2015 10:45AM | Nov 12 2015 6:00PM | 0.000 | 51.375 | 15 | -30.300 | -51.375 | 81.675 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 52.0 | 21.0 | -52.0 | G45T2 | PJ 1503, PJ 1504, PJ 1505, PJ 1512 | 6, 6, 6, 3
C/53-1 | SGBM17 | Nov 2 2015 10:45AM | Nov 2 2015 5:20PM | 51.910 | 51.375 | 9 | 9.746 | 0.535 | 41.629 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.5 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 4, 2
C/55-1 | SGBM23 | Nov 3 2015 6:20PM | Nov 4 2015 8:45PM | 51.890 | 51.375 | 9, 15 | 11.220 | 0.515 | 40.155 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.5 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
C/56-1 | SGBM15 | Nov 5 2015 11:34AM | Nov 6 2015 3:00PM | 51.920 | 51.375 | 12, 20 | 11.291 | 0.545 | 40.084 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.5 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 8, 8, 4
C/57-1 | SGBM23 | Nov 6 2015 2:40PM | Nov 7 2015 3:55PM | 51.760 | 51.375 | 9, 26 | 12.060 | 0.385 | 39.315 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.0 | 32.0 | 7.0 | G45T2 | pj1366, pj1367, pj1368, pj1369, pj1370 | 6, 7, 7, 6, 6
C/58-1 | SGBM15 | Nov 4 2015 11:47AM | Nov 4 2015 10:30PM | 51.770 | 51.375 | 9 | 11.670 | 0.395 | 39.705 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.3 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 7, 9, 8, 8
C/59-1 | SGBM23 | Nov 3 2015 10:45AM | Nov 3 2015 10:29PM | 51.814 | 51.375 | 9, 34 | 13.507 | 0.439 | 37.868 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.1 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 10, 5
C/60-1 | SGBM18 | Nov 4 2015 7:15PM | Nov 5 2015 5:38PM | 51.920 | 51.375 | 9, 9 | 14.685 | 0.545 | 36.690 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.3 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 4
C/61-1 | SGBM18 | Nov 2 2015 1:40PM | Nov 3 2015 1:12PM | 51.880 | 51.375 |  | 16.443 | 0.505 | 34.932 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.2 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 6, 7, 4
C/62-1 | SGBM15 | Nov 3 2015 4:48PM | Nov 4 2015 4:27PM | 51.800 | 51.375 | 9, 23 | 17.322 | 0.425 | 34.053 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 21.7 | 27.0 | 5.3 | G45T2 | PJ 1190, PJ 1192, PJ 1193, PJ 1195 | 7, 7, 7, 6
B/56-1 | SGBM17 | Nov 7 2015 6:40PM | Nov 9 2015 9:21PM | 51.857 | 51.275 | 12 | 11.967 | 0.582 | 39.308 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.0 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 2, 7, 9, 7, 7, 3
B/61-1 | SGBM15 | Nov 6 2015 11:37AM | Nov 7 2015 11:20AM | 51.520 | 51.075 | 9 | 15.720 | 0.445 | 35.355 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.5 | 28.0 | 5.5 | G45T2 | pj1352, pj1353, pj1354, pj1357 | 7, 7, 7, 7
AA/56-1 | SGBM05 | Jan 4 2016 8:30AM | Jan 4 2016 8:30PM | 49.424 | 47.525 |  | 16.402 | 1.899 | 31.123 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.8 | 24.0 | -100.0 | G35T2 | PJ 3935, PJ 3937, PJ 3941 | 8, 8, 8
AA/61-1 | SGBM23 | Jan 27 2016 9:26AM | Jan 27 2016 9:00PM | 49.553 | 48.155 |  | 14.063 | 1.398 | 34.092 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 26.0 | -21.6 | G35T2 | 4988, 4980, 4984 | 8, 10, 8
L/53-1 | SGBM23 | Oct 23 2015 1:30PM | Oct 24 2015 8:15PM | 52.037 | 51.075 |  | 16.710 | 0.962 | 34.365 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 5
L/54-1 | SGBM23 | Oct 23 2015 2:30PM | Oct 23 2015 9:19PM | 52.058 | 51.075 |  | 16.342 | 0.983 | 34.733 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.1 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 11, 5
L/55-1 | SGBM23 | Oct 23 2015 11:20AM | Oct 23 2015 6:25PM | 52.075 | 51.075 |  | 17.025 | 1.000 | 34.050 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 2, 12, 9
L/56-1 | SGBM23 | Oct 22 2015 9:00PM | Oct 23 2015 11:12AM | 51.120 | 50.775 |  | 16.368 | 0.345 | 34.407 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 25.0 | -21.9 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
L/60-1 | SGBM15 | Oct 27 2015 11:20AM | Oct 27 2015 8:05PM | 52.060 | 51.075 |  | 14.576 | 0.985 | 36.499 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 5
M/42-1 | SGBM08 | Dec 21 2015 3:00PM | Dec 23 2015 6:12AM | 51.850 | 50.575 |  | 24.183 | 1.275 | 26.392 |  | 0.0 | 0.0 | 16T20+8T20 | T12-250 | 12 | 16.8 | 19.0 | 25.1 | G35T2 | 1, 2 | 11, 8
M/43-1 | SGBM08 | Dec 21 2015 4:10PM | Dec 23 2015 1:17AM | 51.897 | 50.575 |  | 23.398 | 1.322 | 27.177 |  | 0.0 | 0.0 | 16T20+8T20 | T12-250 | 12 | 17.3 | 20.0 | 15.7 | G35T2 | 1, 2 | 10, 10
M/44-1 | SGBM15 | Dec 30 2015 11:28AM | Dec 31 2015 1:30PM | 51.900 | 50.575 |  | 22.255 | 1.325 | 28.320 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 22.0 | -100.0 | G45T2 | PJ 3782, PJ 3783, PJ 3787 | 8, 7, 7
M/47-1 | SGBM08 | Dec 28 2015 1:30PM | Dec 29 2015 10:55PM | 51.680 | 50.575 |  | 18.885 | 1.105 | 31.690 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 23.0 | -20.2 | G45T2 | PJ 3702, PJ 3705, PJ 3708 | 8, 8, 7
K/36-1 | SGBM08 | Dec 15 2015 9:30PM | Dec 16 2015 9:00PM | 52.034 | 51.375 |  | 32.965 | 0.659 | 18.410 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 11.7 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
K/37-1 | SGBM08 | Dec 15 2015 8:44PM | Dec 17 2015 12:18AM | 51.954 | 51.375 |  | 31.076 | 0.579 | 20.299 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 14.0 | 1.1 | G45T2 | 1, 2 | 7, 7
K/39-1 | SGBM23 | Dec 11 2015 8:00PM | Dec 12 2015 7:44PM | 51.951 | 50.375 |  | 25.004 | 1.276 | 25.371 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.1 | 20.0 | -16.1 | G45T2 | 1, 2 | 9, 11
K/39-2 | SGBM08 | Dec 14 2015 4:15PM | Dec 15 2015 5:45PM | 51.912 | 50.375 |  | 26.269 | 1.537 | 24.106 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.3 | 19.0 | 23.9 | G45T2 | 1, 2, 3 | 7, 6, 6
K/39-3 | SGBM08 | Dec 16 2015 4:31PM | Dec 17 2015 2:15PM | 51.845 | 50.375 |  | 26.100 | 1.470 | 24.275 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.4 | 19.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 6, 6
K/41-1 | SGBM15 | Dec 10 2015 8:30PM | Dec 11 2015 6:35PM | 51.954 | 50.375 |  | 23.833 | 1.579 | 26.542 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 20.0 | 18.4 | G45T2 | PJ 2963, PJ 2966, 3 | 7, 7, 6
K/41-2 | SGBM08 | Dec 16 2015 5:36PM | Dec 17 2015 7:32PM | 51.850 | 50.375 |  | 23.846 | 1.475 | 26.529 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 20.0 | -100.0 | G45T2 | 1, 2 , 3 | 7, 7, 6
K/41-3 | SGBM15 | Dec 14 2015 3:40PM | Dec 15 2015 4:31PM | 51.824 | 50.375 |  | 23.926 | 1.449 | 26.449 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | 24.8 | G45T2 | 1, 2, 3 | 7, 7, 7
K/42-1 | SGBM23 | Dec 4 2015 8:30AM | Dec 4 2015 10:04PM | 51.860 | 50.375 | 9, 18, 27 | 23.054 | 1.485 | 27.321 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.4 | 20.0 | -100.0 | G45T2 | PJ 2605, PJ 2606, PJ 2610 | 7, 6, 7
K/42-2 | SGBM15 | Dec 8 2015 1:05PM | Dec 8 2015 8:36PM | 51.850 | 50.375 | 9, 17 | 23.223 | 1.475 | 27.152 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 22.0 | -100.0 | G45T2 | PJ 2778, PJ 2779, PJ 2781 | 7, 7, 8
K/42-3 | SGBM08 | Dec 9 2015 10:09AM | Dec 10 2015 1:54AM | 51.820 | 50.375 | 9 | 23.305 | 1.445 | 27.070 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 25.0 | 45.2 | G45T2 | PJ 2862, PJ 2863, PJ 2864, PJ 2868 | 4, 7, 5, 6
K/43-1 | SGBM15 | Dec 9 2015 10:49AM | Dec 10 2015 3:34PM | 51.820 | 50.375 | 11 | 22.130 | 1.445 | 28.245 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 21.0 | 16.9 | G45T2 | PJ 2890, PJ 2892, PJ 2895 | 7, 7, 7
K/43-2 | SGBM23 | Dec 4 2015 9:30AM | Dec 5 2015 1:07AM | 51.782 | 50.375 | 9 | 21.912 | 1.407 | 28.463 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 20.0 | -18.1 | G45T2 | PJ 2620, PJ 2622, PJ 2623 | 8, 6, 6
K/43-3 | SGBM15 | Dec 8 2015 1:30PM | Dec 9 2015 12:00AM | 51.900 | 50.375 | 9 | 22.050 | 1.525 | 28.325 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 23.0 | -100.0 | G45T2 | PJ 2791, PJ 2792, PJ 2793 | 7, 8, 8
K/44-1 | SGBM23 | Dec 19 2015 8:01PM | Dec 22 2015 1:58PM | 51.835 | 50.375 |  | 21.183 | 1.460 | 29.192 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 24.0 | 29.2 | G45T2 | 1, 2, 3 | 8, 9, 7
K/44-2 | SGBM15 | Dec 17 2015 1:43PM | Dec 17 2015 3:42AM | 51.955 | 50.375 |  | 21.099 | 1.580 | 29.276 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
K/44-3 | SGBM23 | Dec 23 2015 1:55PM | Dec 24 2015 1:14AM | 51.787 | 50.375 |  | 21.065 | 1.412 | 29.310 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 24.0 | -18.6 | G45T2 | C520124369, C520124370, C520124371 | 10, 10, 4
K/45-1 | SGBM15 | Dec 12 2015 12:00PM | Dec 12 2015 12:40AM | 51.750 | 50.375 |  | 20.028 | 1.375 | 30.347 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 24.0 | 24.3 | G45T2 | 1, 2, 3 | 8, 8, 8
K/45-2 | SGBM15 | Dec 7 2015 8:30AM | Dec 7 2015 11:42PM | 51.673 | 50.375 | 9 | 20.365 | 1.298 | 30.010 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.1 | 32.0 | 67.6 | G45T2 | C480012821, c480012823, C480012824 | 9, 4, 10
K/45-3 | SGBM15 | Dec 9 2015 9:55AM | Dec 10 2015 1:53PM | 51.647 | 50.375 | 9 | 20.225 | 1.272 | 30.150 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
K/46-1 | SGBM15 | Dec 11 2015 11:52AM | Dec 12 2015 10:30PM | 51.670 | 50.075 |  | 19.806 | 1.595 | 30.269 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
K/46-2 | SGBM15 | Dec 17 2015 1:23PM | Dec 18 2015 3:53PM | 51.560 | 50.075 |  | 18.836 | 1.485 | 31.239 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 25.0 | 15.7 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 2
K/46-3 | SGBM23 | Dec 22 2015 4:50PM | Dec 23 2015 3:25AM | 51.580 | 50.075 |  | 19.009 | -50.075 | 31.066 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.8 | 23.0 | 16.4 | G45T2 | 1, 2, 3 | 3, 10, 10
K/47-1 | SGBM23 | Dec 22 2015 4:45PM | Dec 23 2015 6:00AM | 51.570 | 50.375 |  | 18.746 | 1.195 | 31.629 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.1 | 23.0 | 4.4 | G45T2 | 1, 2, 3 | 10, 11, 2
K/47-2 | SGBM23 | Dec 30 2015 1:50PM | Dec 31 2015 12:00AM | 51.537 | 50.375 |  | 19.150 | 1.162 | 31.225 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 22.0 | -19.9 | G45T2 | PJ 3752, PJ 3754, PJ 3761 | 8, 7, 7
K/47-3 | SGBM15 | Dec 15 2015 10:15AM | Dec 16 2015 7:00PM | 51.471 | 50.375 |  | 18.988 | 1.096 | 31.387 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.0 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
K/50-1 | SGBM15 | Nov 14 2015 4:50PM | Nov 16 2015 4:55PM | 50.272 | 51.375 |  | 19.242 | -1.103 | 32.133 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.4 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
J/36-1 | SGBM08 | Dec 12 2015 12:31PM | Dec 14 2015 6:11PM | 52.016 | 51.375 |  | 31.800 | 0.641 | 19.575 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.5 | 15.0 | 20.4 | G45T2 | 1, 2 | 8, 7
J/37-1 | SGBM08 | Dec 12 2015 11:49AM | Dec 13 2015 5:12AM | 51.967 | 51.375 |  | 30.053 | 0.592 | 21.322 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
J/39-1 | SGBM15 | Dec 18 2015 10:08AM | Dec 18 2015 11:56PM | 51.772 | 50.675 |  | 24.514 | 1.097 | 26.161 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 19.0 | 14.1 | G45T2 | 1, 2, 3 | 7, 6, 6
J/39-2 | SGBM15 | Dec 28 2015 8:45AM | Dec 28 2015 8:53PM | 51.920 | 50.675 |  | 23.520 | 1.245 | 27.155 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 19.0 | 10.0 | G45T2 | PJ 3616, PJ 3619 | 10, 9
J/39-3 | SGBM15 | Dec 28 2015 9:00AM | Dec 28 2015 10:27PM | 51.964 | 50.675 |  | 24.401 | 1.289 | 26.274 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 19.0 | -100.0 | G45T2 | PJ 3624, PJ 3627 | 10, 9
J/39-4 | SGBM23 | Dec 30 2015 8:00AM | Dec 31 2015 4:22AM | 51.990 | 50.675 |  | 24.137 | 1.315 | 26.538 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 18.0 | -16.9 | G45T2 | PJ 3771, PJ 3772 | 8, 10
J/39-5 | SGBM23 | Jan 2 2016 5:00PM | Jan 4 2016 12:50PM | 51.979 | 50.675 |  | 23.427 | 1.304 | 27.248 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 23.0 | -17.3 | G45T2 | PJ 3898, PJ 3901, PJ 3909 | 10, 9, 4
J/39-6 | SGBM15 | Dec 22 2015 5:10PM | Dec 23 2015 9:29PM | 51.925 | 50.675 |  | 24.370 | 1.250 | 26.305 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 22.0 | -100.0 | G45T2 | C520124355, C520124356, C520124359 | 10, 2, 10
J/39-7 | SGBM15 | Dec 18 2015 10:56AM | Dec 19 2015 6:15PM | 51.900 | 50.675 |  | 24.651 | 1.225 | 26.024 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 23.0 | -100.0 | G45T2 | 1, 2 | 12, 11
J/39-8 | SGBM23 | Dec 30 2015 8:45AM | Dec 31 2015 2:20AM | 51.996 | 50.675 |  | 23.647 | 1.321 | 27.028 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 18.0 | -17.2 | G45T2 | Pending, PJ 3766 | 8, 10
J/40-1 | SGBM23 | Nov 28 2015 5:55PM | Nov 29 2015 3:06AM | 51.623 | 50.375 |  | 23.936 | 1.248 | 26.439 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
J/40-2 | SGBM23 | Dec 1 2015 11:50AM | Dec 1 2015 11:52PM | 51.750 | 50.375 | 9 | 23.371 | 1.375 | 27.004 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
J/40-3 | SGBM08 | Dec 2 2015 7:31PM | Dec 3 2015 10:55PM | 51.645 | 50.375 | 12 | 24.022 | 1.270 | 26.353 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
J/47-1 | SGBM08 | Dec 26 2015 4:40PM | Dec 28 2015 4:50PM | 51.590 | 50.375 |  | 17.732 | 1.215 | 32.643 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.8 | 24.0 | 15.6 | G45T2 | PJ3586, PJ 3590, PJ 3595, PJ 3605 | 8, 7, 7, 2
J/47-2 | SGBM15 | Dec 7 2015 10:20AM | Dec 8 2015 6:31PM | 51.670 | 50.375 | 10 | 18.202 | 1.295 | 32.173 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 24.0 | -100.0 | G45T2 | PJ 2770, PJ 2773, PJ 2775 | 8, 8, 8
J/47-3 | SGBM15 | Dec 4 2015 9:14PM | Dec 5 2015 8:58PM | 51.682 | 50.375 | 9 | 18.146 | 1.307 | 32.229 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 25.0 | -100.0 | G45T2 | C480012734, C480012737, C480012738 | 10, 10, 5
J/48-1 | SGBM15 | Dec 2 2015 4:09PM | Dec 4 2015 1:52AM | 51.519 | 50.675 | 9 | 18.443 | 0.844 | 32.232 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 7, 7
J/48-2 | SGBM15 | Nov 28 2015 10:16AM | Nov 29 2015 12:27AM | 51.520 | 50.675 | 9 | 18.120 | 0.845 | 32.555 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.7 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 8
J/48-3 | SGBM15 | Dec 9 2015 9:20AM | Dec 9 2015 10:36PM | 51.504 | 50.675 | 9, 22 | 18.224 | 0.829 | 32.451 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.6 | 27.0 | 30.8 | G45T2 | PJ 2843, PJ 2844, PJ 2845, PJ 2856 | 7, 9, 8, 3
J/48-4 | SGBM15 | Dec 7 2015 9:33AM | Dec 7 2015 10:44PM | 51.490 | 50.675 | 9 | 18.232 | 0.815 | 32.443 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.6 | 24.0 | 16.3 | G45T2 | C480002816, C480012817, C480012821 | 11, 11, 2
J/48-5 | SGBM15 | Nov 28 2015 9:45AM | Nov 29 2015 2:28AM | 51.491 | 50.675 | 9, 26 | 18.244 | -50.675 | 32.431 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.6 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 7, 8, 4
J/48-6 | SGBM15 | Dec 2 2015 4:53PM | Dec 4 2015 5:40PM | 51.416 | 50.675 | 9 | 18.229 | 0.741 | 32.446 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.6 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 9
J/48-7 | SGBM15 | Dec 11 2015 2:15PM | Dec 11 2015 11:20PM | 51.326 | 50.675 |  | 18.397 | 0.651 | 32.278 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 23.0 | 12.0 | G45T2 | 1, 2, 3 | 8, 8, 7
J/48-8 | SGBM15 | Dec 7 2015 9:15AM | Dec 8 2015 1:05AM | 51.340 | 50.675 | 10 | 18.197 | 0.665 | 32.478 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.7 | 30.0 | 45.2 | G45T2 | C480012825, C480012826, C480012827 | 10, 10, 4
J/50-1 | SGBM15 | Nov 20 2015 5:16PM | Nov 21 2015 2:14PM | 51.930 | 51.375 | 9, 19 | 18.169 | 0.555 | 33.206 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 24.0 | 2.9 | G45T2 | PJ 1914, PJ 1915, PJ 1916 | 8, 8, 8
J/51-1 | SGBM18 | Nov 13 2015 8:45AM | Nov 13 2015 4:58PM | 52.140 | 51.375 |  | 16.314 | 0.765 | 35.061 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.3 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 7, 6, 6, 4
H/36-1 | SGBM23 | Oct 17 2015 1:30PM | Oct 17 2015 6:48PM | 52.069 | 51.375 | 9 | 31.460 | 0.694 | 19.915 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.7 | 18.0 | -100.0 | G45T2 | 1, 2 | 11, 7
H/40-1 | SGBM23 | Nov 27 2015 5:45PM | Nov 30 2015 5:31PM | 51.778 | 50.375 | 9 | 23.112 | 1.403 | 27.263 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
H/40-2 | SGBM23 | Dec 2 2015 6:46PM | Dec 3 2015 11:41PM | 51.820 | 50.375 | 9, 27 | 23.083 | 1.425 | 27.292 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.4 | 21.0 | -100.0 | G45T2 | 1, 2 | 11, 10
H/40-3 | SGBM15 | Dec 18 2015 9:35AM | Dec 18 2015 9:38PM | 51.824 | 50.375 |  | 23.311 | 1.449 | 27.064 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 20.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 6
H/50-1 | SGBM15 | Nov 20 2015 4:50PM | Nov 21 2015 9:52PM | 51.949 | 51.375 | 9, 12 | 16.890 | 0.574 | 34.485 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 25.0 | 3.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
H/51-1 | SGBM15 | Nov 18 2015 6:50PM | Nov 19 2015 5:55PM | 52.053 | 51.375 | 9 | 14.935 | -51.375 | 36.440 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 9, 9
Ga/36-1 | SGBM15 | Dec 10 2015 1:50PM | Dec 11 2015 1:07AM | 52.062 | 51.075 |  | 30.339 | 0.987 | 20.736 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.2 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 2
Ga/37-1 | SGBM15 | Dec 10 2015 1:42PM | Dec 10 2015 10:44PM | 52.071 | 51.375 |  | 27.805 | 0.696 | 23.570 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.0 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 4, 9, 8
G/50-1 | SGBM15 | Nov 24 2015 10:47AM | Nov 25 2015 7:36PM | 51.847 | 51.375 | 9, 30, 37 | 13.891 | 0.472 | 37.484 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.8 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
G/51-1 | SGBM15 | Nov 18 2015 7:08PM | Nov 20 2015 7:54PM | 51.937 | 51.375 | 9 | 12.855 | 0.562 | 38.520 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.5 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
Fa/36-1 | SGBM08 | Dec 12 2015 3:00PM | Dec 14 2015 7:29PM | 51.990 | 51.375 |  | 29.928 | 0.615 | 21.447 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.6 | 16.0 | 17.3 | G45T2 | 1, 2 | 8, 8
F/38-1 | SGBM08 | Dec 15 2015 10:52AM | Dec 15 2015 11:19PM | 52.068 | 51.375 |  | 26.015 | 0.693 | 25.360 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.1 | 20.0 | 24.0 | G45T2 | 1, 2, 3 | 7, 7, 6
F/42-1 | SGBM23 | Dec 14 2015 5:16PM | Dec 15 2015 7:18PM | 51.936 | 51.375 |  | 20.847 | 0.561 | 30.528 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 22.0 | 13.3 | G45T2 | 1, 2, 3 | 7, 8, 7
F/43-1 | SGBM23 | Nov 23 2015 3:03PM | Nov 24 2015 11:23AM | 51.833 | 51.375 | 9 | 19.214 | 0.458 | 32.161 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 24.0 | -20.5 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
F/45-1 | SGBM23 | Nov 23 2015 4:38PM | Nov 24 2015 7:04PM | 51.962 | 51.375 | 9 | -37.300 | 0.587 | 88.675 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 56.4 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
F/46-1 | SGBM15 | Nov 21 2015 6:35PM | Nov 23 2015 7:40PM | 51.830 | 51.375 | 9 | 12.913 | 0.455 | 38.462 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.5 | 27.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 6
F/47-1 | SGBM15 | Nov 21 2015 7:02PM | Nov 24 2015 2:05PM | 51.840 | 51.075 | 9 | 12.989 | 0.765 | 38.086 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.2 | 28.0 | 15.5 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
F/50-1 | SGBM15 | Nov 24 2015 11:30AM | Nov 25 2015 12:00PM | 51.884 | 51.075 | 12 | 12.773 | 0.809 | 38.302 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.4 | 29.0 | -24.4 | G45T2 | 1, 2, 3, 4 | 7, 7, 8, 7
F/51-1 | SGBM15 | Nov 18 2015 7:30PM | Nov 20 2015 10:52PM | 51.769 | 51.075 | 9, 21, 32 | 10.788 | 0.694 | 40.287 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.6 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 5, 5, 7
E/48-1 | SGBM23 | Nov 15 2015 4:00PM | Nov 17 2015 2:40PM | 51.955 | 51.275 | 9 | 10.674 | -51.275 | 40.601 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.8 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 10, 10, 6
E/49-1 | SGBM23 | Nov 15 2015 2:00PM | Nov 17 2015 1:08PM | 51.950 | 51.275 | 9 | 11.300 | 0.675 | 39.975 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.4 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 3
E/47-1 | SGBM23 | Nov 18 2015 6:50PM | Nov 19 2015 4:11PM | 51.860 | 51.275 | 9, 30 | 11.694 | 0.585 | 39.581 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.2 | 29.0 | 3.8 | G45T2 | C480011907, C170013571, C170013573, C480011913 | 11, 8, 8, 2
E/50-1 | SGBM15 | Nov 11 2015 2:30PM | Nov 12 2015 10:50PM | 51.959 | 51.275 | 9 | 8.884 | 0.684 | 42.391 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 27.0 | 31.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 12, 12
Da/48-1 | SGBM23 | Nov 11 2015 4:53PM | Nov 12 2015 7:00PM | 51.988 | 50.775 | 15, 29 | 9.686 | 1.121 | 41.089 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.1 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 2, 11.5, 11.5, 4
D/50-1 | SGBM15 | Nov 11 2015 1:25PM | Nov 12 2015 5:00PM | 51.815 | 51.275 | 9 | 8.965 | 0.540 | 42.310 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.9 | 31.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 9
T1/50-1 | SGBM23 | Feb 27 2016 8:30AM | Feb 27 2016 5:45PM | 51.921 | 51.375 |  | 22.834 | 0.546 | 28.541 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.2 | 23.0 | -18.1 | G45T2 | 1, 2, 3 | 8, 8, 7
T1/51-1 | SGBM23 | Mar 2 2016 12:00PM | Mar 2 2016 10:40PM | 51.927 | 50.175 |  | 24.383 | 1.752 | 25.792 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.4 | 14.0 | -100.0 | G45T2 | 1, 2 | 7, 7
T1/52-1 | SGBM23 | Feb 22 2016 9:45AM | Feb 22 2016 11:45PM | 51.998 | 51.375 |  | 21.299 | 0.623 | 30.076 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.1 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 7
T1/55-1 | SGBM19 | Nov 5 2015 5:20PM | Nov 5 2015 10:42PM | 51.307 | 51.375 |  | 22.448 | -0.068 | 28.927 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.4 | 44.0 | -100.0 | G45T2 | Pending, 2, 3, 4 | 11, 11, 11, 11
T1/56-1 | SGBM15 | Feb 15 2016 1:50PM | Feb 15 2016 7:45PM | 51.816 | 51.375 |  | 22.336 | 0.441 | 29.039 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 7
T1/57-1 | SGBM01 | Jan 29 2016 5:30PM | Feb 2 2016 6:50PM | 51.892 | 51.375 |  | 23.877 | 0.517 | 27.498 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.5 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 6
T1/58-1 | SGBM23 | Feb 5 2016 4:25PM | Feb 10 2016 6:30PM | 51.977 | 51.375 |  | 23.304 | 0.602 | 28.071 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 8
T1/59-1 | SGBM23 | Feb 2 2016 3:55PM | Feb 3 2016 10:15PM | 52.030 | 50.375 |  | 23.510 | 1.655 | 26.865 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.1 | 21.0 | -100.0 | G45T2 | 2, 2, 3 | 7, 7, 7
T1/60-1 | SGBM23 | Feb 17 2016 11:13AM | Feb 18 2016 12:45AM | 51.999 | 49.775 |  | 23.371 | 2.224 | 26.404 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 22.0 | 31.0 | G45T2 | 1, 2, 3 | 8, 7, 7
T1/61-1 | SGBM15 | Feb 15 2016 11:25AM | Feb 16 2016 7:05PM | 52.023 | 49.775 |  | 23.410 | 2.248 | 26.365 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 23.0 | -16.8 | G45T2 | 1, 2, 3 | 8, 7, 8
T/49-1 | SGBM23 | Feb 25 2016 1:30PM | Feb 25 2016 11:10PM | 51.880 | 51.375 |  | 21.150 | 0.505 | 30.225 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 8
T/50-1 | SGBM15 | Feb 25 2016 3:25PM | Feb 26 2016 7:45PM | 51.993 | 51.375 |  | 20.415 | 0.618 | 30.960 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.7 | 24.0 | -19.7 | G45T2 | pj6063, pj6068, pj6073 | 8, 8, 8
T/52-1 | SGBM23 | Feb 27 2016 10:50AM | Feb 27 2016 8:00PM | 51.981 | 49.725 |  | 18.456 | 2.256 | 31.269 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 26.0 | -19.9 | G45T2 | 1, 2, 3 | 10, 8, 8
T/52-2 | SGBM15 | Feb 23 2016 10:50AM | Feb 23 2016 10:10PM | 51.947 | 49.725 |  | 18.322 | 2.222 | 31.403 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.0 | 26.0 | -20.0 | G45T2 | 1, 2, 3 | 10, 8, 8
T/53-1 | SGBM15 | Feb 23 2016 11:30AM | Feb 24 2016 6:00PM | 51.888 | 49.825 |  | 18.002 | 2.063 | 31.823 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 25.0 | 4.8 | G45T2 | PJ5951, PJ5952, PJ5954 | 9, 8, 8
T/53-2 | SGBM23 | Feb 20 2016 1:00PM | Feb 22 2016 7:20PM | 51.931 | 49.825 |  | 17.893 | 2.106 | 31.932 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.3 | 28.0 | -100.0 | G45T2 | PJ5859, PJ5860, PJ5862, pj 5868 | 8, 8, 10, 2
T/54-1 | SGBM23 | Feb 17 2016 5:15PM | Feb 18 2016 6:10PM | 52.057 | 49.825 |  | 19.350 | 2.232 | 30.475 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 8, 8, 2
T/54-2 | SGBM23 | Jan 27 2016 3:05PM | Jan 28 2016 6:30PM | 51.978 | 49.825 |  | 19.582 | 2.153 | 30.243 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 9
T/55-1 | SGBM01 | Jan 29 2016 5:30PM | Jan 31 2016 12:20AM | 51.991 | 50.175 |  | 17.947 | 1.816 | 32.228 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 2
T/55-2 | SGBM20 | Feb 13 2016 9:40AM | Feb 13 2016 5:30PM | 51.938 | 50.175 |  | 19.682 | 1.763 | 30.493 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 3
T/56-1 | SGBM23 | Feb 3 2016 5:25PM | Feb 4 2016 8:50PM | 51.915 | 50.175 |  | 19.879 | 1.740 | 30.296 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 27.0 | -19.3 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 3
T/56-2 | SGBM01 | Jan 27 2016 2:40PM | Jan 28 2016 8:25PM | 51.905 | 50.175 |  | 21.172 | 1.730 | 29.003 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
T/57-1 | SGBM15 | Feb 13 2016 2:35PM | Feb 15 2016 5:25PM | 51.995 | 50.175 |  | 20.182 | 1.820 | 29.993 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.1 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 7
T/57-2 | SGBM23 | Feb 10 2016 10:50AM | Feb 11 2016 6:25PM | 51.973 | 50.175 |  | 20.627 | 1.798 | 29.548 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.8 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
T/58-1 | SGBM23 | Feb 3 2016 5:00PM | Feb 4 2016 7:25PM | 52.092 | 51.375 |  | 22.682 | 0.717 | 28.693 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 26.0 | -18.3 | G45T2 | 1, 2, 3 | 8, 10, 8
S/49-1 | SGBM23 | Feb 15 2016 2:45PM | Feb 16 2016 5:10PM | 52.050 | 51.375 |  | 21.009 | 0.675 | 30.366 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 8
S/50-1 | SGBM23 | Feb 11 2016 4:45PM | Feb 12 2016 6:20PM | 51.841 | 51.075 |  | 19.181 | 0.766 | 31.894 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.3 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
S/51-1 | SGBM15 | Feb 20 2016 2:00PM | Feb 20 2016 10:35PM | 51.789 | 49.775 |  | 14.673 | 2.014 | 35.102 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.3 | 26.0 | -22.3 | G45T2 | 1, 2, 3 | 10, 8, 8
S/51-2 | SGBM23 | Feb 22 2016 10:15AM | Feb 23 2016 4:50PM | 51.827 | 49.775 |  | 16.651 | 2.052 | 33.124 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 27.0 | -100.0 | G45T2 | PJ5897, PJ5898, PJ5903 | 10, 9, 8
S/55-1 | SGBM23 | Feb 10 2016 11:15AM | Feb 11 2016 5:05PM | 51.949 | 50.375 |  | 18.867 | 1.574 | 31.508 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.0 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 4
S/55-2 | SGBM23 | Feb 2 2016 4:00PM | Feb 3 2016 5:10PM | 51.941 | 50.375 |  | 18.308 | 1.566 | 32.067 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.4 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
S/55-3 | SGBM05 | Jan 26 2016 9:45AM | Jan 26 2016 10:15PM | 51.987 | 50.375 |  | 18.660 | 1.612 | 31.715 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 9
S/60-1 | SGBM15 | Feb 17 2016 9:55AM | Feb 18 2016 10:00PM | 51.948 | 50.175 |  | 21.228 | 1.773 | 28.947 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.4 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 9
S/60-2 | SGBM15 | Feb 16 2016 12:25PM | Feb 16 2016 9:55PM | 51.895 | 50.175 |  | 21.844 | 1.720 | 28.331 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
S/61-1 | SGBM05 | Feb 5 2016 4:15PM | Feb 11 2016 12:35AM | 52.010 | 48.575 |  | 20.112 | 3.435 | 28.463 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | -18.1 | G45T2 | 1, 2, 3 | 8, 8, 7
S/61-2 | SGBM05 | Feb 3 2016 9:45AM | Feb 4 2016 12:35AM | 52.037 | 48.575 |  | 19.980 | 3.462 | 28.595 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.2 | 22.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 2, 7, 6
R/49-1 | SGBM23 | Feb 13 2016 3:30PM | Feb 15 2016 6:50PM | 51.905 | 51.375 |  | 20.155 | 0.530 | 31.220 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 8
R/50-1 | SGBM23 | Feb 11 2016 5:05PM | Feb 12 2016 8:20PM | 51.716 | 50.975 |  | 18.322 | 0.741 | 32.653 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.8 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 10, 8
R/51-1 | SGBM05 | Jan 13 2016 4:30PM | Jan 15 2016 1:15AM | 51.881 | 49.775 |  | 16.554 | 2.106 | 33.221 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 9
R/52-1 | SGBM23 | Jan 20 2016 11:30AM | Jan 21 2016 1:35AM | 51.884 | 49.775 |  | 15.630 | 2.109 | 34.145 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 32.0 | 10.3 | G45T2 | 1, 2, 3 | 11, 10, 11
R/52-2 | SGBM05 | Jan 13 2016 4:45PM | Jan 15 2016 11:35PM | 51.884 | 49.775 |  | 16.442 | 2.109 | 33.333 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
R/53-1 | SGBM23 | Jan 21 2016 12:35PM | Jan 22 2016 12:35AM | 51.802 | 50.175 |  | 15.807 | 1.627 | 34.368 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 8
R/53-2 | SGBM05 | Jan 13 2016 5:00PM | Jan 16 2016 9:00PM | 51.898 | 50.175 |  | 16.777 | 1.723 | 33.398 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 7
R/59-1 | SGBM01 | Feb 3 2016 4:10PM | Feb 4 2016 2:55PM | 52.058 | 51.375 |  | 21.652 | 0.683 | 29.723 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 25.0 | -18.9 | G45T2 | 1, 2, 3, 4 | 7, 7, 8, 3
R/60-1 | SGBM23 | Feb 20 2016 2:20PM | Feb 20 2016 9:00PM | 52.029 | 50.175 |  | 21.101 | 1.854 | 29.074 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
R/60-2 | SGBM15 | Feb 17 2016 10:30AM | Feb 18 2016 8:15PM | 52.033 | 50.175 |  | 19.910 | 1.858 | 30.265 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 8
R/61-1 | SGBM05 | Feb 2 2016 8:30AM | Feb 3 2016 3:40PM | 52.035 | 49.725 |  | 20.447 | 2.310 | 29.278 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 8
R/61-2 | SGBM01 | Feb 12 2016 8:30AM | Feb 13 2016 8:10PM | 52.024 | 49.725 |  | 19.121 | 2.299 | 30.604 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 8
Q/51-1 | SGBM01 | Jan 29 2016 9:05AM | Jan 30 2016 3:20PM | 51.843 | 50.175 |  | 14.529 | 1.668 | 35.646 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.7 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 9, 9
Q/51-2 | SGBM23 | Feb 4 2016 3:00PM | Feb 5 2016 5:35PM | 51.894 | 50.175 |  | 15.573 | 1.719 | 34.602 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.0 | 34.0 | 12.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 9, 7
Q/52-1 | SGBM23 | Jan 23 2016 11:10AM | Jan 23 2016 8:05PM | 51.859 | 50.175 |  | 14.886 | 1.684 | 35.289 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.5 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 8
Q/52-2 | SGBM23 | Jan 20 2016 11:05AM | Jan 21 2016 11:35PM | 51.790 | 50.175 |  | 15.873 | 1.615 | 34.302 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.8 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
Q/54-1 | SGBM23 | Jan 19 2016 11:35AM | Jan 20 2016 3:10PM | 51.914 | 51.375 |  | 16.520 | 0.539 | 34.855 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 9, 8, 2
Q/59-1 | SGBM05 | Feb 16 2016 12:10PM | Feb 16 2016 10:40PM | 52.134 | 51.375 |  | 20.788 | 0.759 | 30.587 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.5 | 27.0 | 38.7 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
Q/60-1 | SGBM23 | Feb 19 2016 11:30AM | Feb 19 2016 9:15PM | 52.229 | 50.175 |  | 19.196 | 2.054 | 30.979 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.7 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 9, 8
Q/60-2 | SGBM15 | Feb 17 2016 10:50AM | Feb 17 2016 8:30PM | 52.218 | 50.175 |  | 19.673 | 2.043 | 30.502 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 8, 8
Q/61-1 | SGBM05 | Feb 15 2016 1:15PM | Feb 15 2016 9:20PM | 52.100 | 49.725 |  | 19.166 | 2.375 | 30.559 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 24.0 | -19.4 | G45T2 | 1, 2, 3 | 8, 8, 8
Q/61-2 | SGBM05 | Feb 5 2016 4:00PM | Feb 11 2016 9:00PM | 52.026 | 49.725 |  | 18.887 | 2.301 | 30.838 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.6 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 8
P/49-1 | SGBM23 | Feb 11 2016 5:30PM | Feb 13 2016 4:10PM | 51.919 | 51.375 |  | 18.167 | 0.544 | 33.208 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
P/50-1 | SGBM23 | Jan 16 2016 5:30PM | Jan 18 2016 8:20PM | 51.911 | 51.175 |  | 17.322 | 0.736 | 33.853 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 9
P/51-1 | SGBM23 | Feb 13 2016 8:00AM | Feb 13 2016 7:15PM | 51.803 | 48.775 |  | 13.920 | 3.028 | 34.855 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
P/51-2 | SGBM23 | Feb 24 2016 2:00PM | Feb 25 2016 5:15PM | 51.942 | 48.775 |  | 14.037 | 3.167 | 34.738 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.1 | 27.0 | -22.1 | G45T2 | pj6004, pj6005, pj6007 | 10, 9, 8
P/51-3 | SGBM15 | Feb 27 2016 2:00PM | Feb 29 2016 6:30PM | 51.965 | 48.775 |  | 13.533 | 3.190 | 35.242 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.4 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 10, 2
P/51-4 | SGBM23 | Feb 24 2016 1:30PM | Feb 24 2016 10:00PM | 51.954 | 48.775 |  | 13.851 | 3.179 | 34.924 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.2 | 26.0 | 17.0 | G45T2 | 1, 2, 3 | 8, 8, 10
P/51-5 | SGBM01 | Feb 13 2016 8:30AM | Feb 15 2016 4:20PM | 51.842 | 48.775 |  | 43.585 | 3.067 | 5.190 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 3.3 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
P/52-1 | SGBM23 | Jan 16 2016 4:50PM | Jan 19 2016 3:20PM | 51.953 | 50.175 |  | 16.112 | 1.778 | 34.063 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 29.0 | -21.7 | G45T2 | 1, 2, 3, 4 | 8, 10, 8, 3
P/52-2 | SGBM23 | Jan 21 2016 11:30AM | Jan 22 2016 11:25PM | 51.988 | 50.175 |  | 15.192 | 1.813 | 34.983 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.3 | 27.0 | -100.0 | G45T2 | Pending, 2, 3, 4 | 7, 7, 7, 6
P/53-1 | SGBM23 | Jan 21 2016 11:40AM | Jan 23 2016 1:15PM | 51.968 | 50.175 |  | 13.995 | 1.793 | 36.180 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.0 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
P/53-2 | SGBM08 | Jan 16 2016 5:10PM | Jan 19 2016 1:25PM | 52.041 | 50.175 |  | 15.946 | 1.866 | 34.229 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.8 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 8
P/54-1 | SGBM23 | Jan 26 2016 9:00AM | Jan 26 2016 8:45PM | 51.933 | 50.175 |  | 18.488 | 1.758 | 31.687 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 10, 10
P/54-2 | SGBM01 | Jan 29 2016 8:20AM | Jan 29 2016 8:40PM | 51.982 | 50.175 |  | 15.778 | 1.807 | 34.397 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 9, 3
P/55-1 | SGBM23 | Jan 26 2016 3:40PM | Jan 28 2016 1:32AM | 51.890 | 50.175 |  | 15.418 | 1.715 | 34.757 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
P/55-2 | SGBM23 | Jan 21 2016 11:30AM | Jan 23 2016 1:10AM | 52.078 | 50.175 |  | 15.192 | 1.903 | 34.983 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.3 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
P/57-1 | SGBM08 | Jan 22 2016 4:50PM | Jan 26 2016 12:10PM | 52.063 | 50.175 |  | 16.273 | 1.888 | 33.902 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.6 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
P/57-2 | SGBM23 | Jan 20 2016 12:00PM | Jan 21 2016 10:00PM | 52.077 | 50.175 |  | 15.871 | 1.902 | 34.304 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.8 | 26.0 | 19.1 | G45T2 | 1, 2, 3 | 10, 8, 8
P/59-1 | SGBM15 | Feb 3 2016 4:00PM | Feb 4 2016 6:00PM | 52.093 | 50.375 |  | 17.692 | 1.718 | 32.683 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.8 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
P/59-2 | SGBM05 | Jan 30 2016 9:40AM | Jan 30 2016 10:00PM | 52.023 | 50.375 |  | 17.793 | 1.648 | 32.582 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.7 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 7, 10
P/59-3 | SGBM01 | Jan 26 2016 4:45PM | Jan 27 2016 8:15PM | 52.114 | 50.375 |  | 18.156 | 1.739 | 32.219 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 8
P/60-1 | SGBM23 | Feb 19 2016 11:00AM | Feb 20 2016 4:40PM | 52.169 | 50.175 |  | 18.454 | 1.994 | 31.721 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 10, 10, 2
P/60-2 | SGBM05 | Feb 15 2016 2:00PM | Feb 16 2016 8:50PM | 52.112 | 50.175 |  | 18.838 | 1.937 | 31.337 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 25.0 | -19.9 | G45T2 | 1, 2, 3 | 8, 8, 9
P/61-1 | SGBM05 | Feb 2 2016 9:15AM | Feb 2 2016 10:00PM | 52.044 | 49.725 |  | 18.762 | 2.319 | 30.963 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.7 | 24.0 | -19.7 | G45T2 | 1, 2, 3 | 8, 8, 8
P/61-2 | SGBM05 | Feb 10 2016 5:40PM | Feb 13 2016 6:45PM | 52.188 | 49.725 |  | 18.528 | 2.463 | 31.197 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.8 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 10, 8
N/50-1 | SGBM01 | Jan 6 2016 6:25PM | Jan 9 2016 5:15PM | 51.723 | 51.375 |  | 15.058 | 0.348 | 36.317 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.1 | 27.0 | 16.8 | G45T2 | 1, 2, 3 | 7, 7, 13
N/52-1 | SGBM05 | Jan 12 2016 12:45PM | Jan 15 2016 12:05AM | 52.041 | 49.575 |  | 15.553 | 2.466 | 34.022 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.6 | 26.0 | 20.1 | G45T2 | 1, 2, 3 | 8, 10, 8
N/52-2 | SGBM01 | Jan 6 2016 6:20PM | Jan 7 2016 11:25PM | 51.985 | 49.575 |  | 15.152 | 2.410 | 34.423 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 10
N/53-1 | SGBM08 | Jan 15 2016 2:30PM | Jan 16 2016 7:20PM | 52.048 | 50.175 |  | 15.985 | 1.873 | 34.190 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.8 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
N/53-2 | SGBM23 | Jan 11 2016 2:55PM | Jan 12 2016 4:35PM | 52.068 | 50.175 |  | 15.800 | 1.893 | 34.375 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
N/58-1 | SGBM05 | Jan 21 2016 3:45PM | Jan 23 2016 4:25PM | 52.153 | 50.175 |  | 15.937 | 1.978 | 34.238 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.8 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 8
N/58-2 | SGBM05 | Jan 12 2016 11:55AM | Jan 18 2016 9:35PM | 52.052 | 50.175 |  | 17.132 | 1.877 | 33.043 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 8, 10
M7/53-1 | SGBM01 | Jan 9 2016 11:10AM | Jan 9 2016 9:50PM | 52.030 | 50.925 |  | 16.670 | 1.105 | 34.255 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.8 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
M7/55-1 | SGBM15 | Jan 9 2016 11:35AM | Jan 11 2016 8:10PM | 52.031 | 50.925 |  | 15.628 | 1.106 | 35.297 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 10, 10
M7/60-1 | SGBM15 | Jan 27 2016 3:35PM | Jan 29 2016 12:35AM | 51.964 | 49.775 |  | 16.724 | 0.589 | 33.051 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 26.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 10, 8
M7/60a-1 | SGBM01 | Feb 2 2016 9:00AM | Feb 3 2016 10:30PM | 51.863 | 49.775 |  | 17.323 | 0.488 | 32.452 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.6 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 8, 7
M6/57-1 | SGBM15 | Jan 29 2016 5:35PM | Jan 30 2016 8:45PM | 52.020 | 50.075 |  | 16.583 | 1.945 | 33.492 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.3 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 8, 8
M6/57-2 | SGBM15 | Jan 27 2016 11:45AM | Jan 28 2016 3:00AM | 51.994 | 50.075 |  | 16.404 | 1.919 | 33.671 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.4 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 10
M6/58-1 | SGBM15 | Feb 2 2016 3:35PM | Feb 3 2016 8:15PM | 52.037 | 49.875 |  | 16.643 | 2.162 | 33.232 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
M6/58-2 | SGBM15 | Jan 28 2016 8:30AM | Jan 28 2016 10:10PM | 51.992 | 49.875 |  | 16.356 | 2.117 | 33.519 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.3 | 27.0 | -100.0 | G45T2 | 5041, 5042, 5048 | 10, 8, 9
M6/60-1 | SGBM08 | Jan 13 2016 4:50PM | Jan 14 2016 6:40PM | 51.864 | 51.375 |  | 18.122 | 0.489 | 33.253 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
M6/61-1 | SGBM08 | Jan 11 2016 8:25AM | Jan 12 2016 7:15PM | 51.854 | 51.375 |  | 21.164 | 0.479 | 30.211 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 22.0 | 14.5 | G35T2 | 1, 2, 3 | 8, 7, 7
M5/60-1 | SGBM08 | Jan 13 2016 4:13PM | Jan 15 2016 5:35PM | 51.802 | 51.375 |  | 18.248 | 0.427 | 33.127 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 24.0 | 13.9 | G45T2 | 1, 2, 3 | 8, 8, 8
M4/60a-1 | SGBM08 | Jan 11 2016 9:00AM | Jan 13 2016 9:05PM | 51.836 | 51.375 |  | 14.556 | 0.461 | 36.819 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.4 | 25.0 | 6.7 | G45T2 | 1, 2, 3 | 10, 7, 8
AB/52-1 | SGBM22 | Nov 12 2015 2:00PM | Nov 13 2015 4:24PM | 49.339 | 47.875 | 9, 24 | 18.098 | 1.464 | 29.777 |  | 3.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 25.0 | 32.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
AB/52-2 | SGBM22 | Nov 16 2015 6:00PM | Nov 17 2015 6:55PM | 49.250 | 47.875 | 9 | 17.015 | 1.375 | 30.860 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.6 | 24.0 | -100.0 | G45T2 | PJ 1707, PJ 1709, PJ 1711 | 8, 8, 8
AB/53-1 | SGBM22 | Nov 13 2015 3:03PM | Nov 14 2015 1:17PM | 49.284 | 49.075 | 9, 27 | 18.663 | 0.209 | 30.412 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 25.0 | 29.2 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
AB/54-1 | SGBM19 | Nov 14 2015 2:10PM | Nov 14 2015 6:40PM | 49.403 | 49.075 | 9 | 18.588 | 0.328 | 30.487 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 25.0 | 28.9 | G45T2 | 2, 2, 3, 4 | 7, 6, 6, 6
AB/55-1 | SGBM22 | Nov 15 2015 6:10PM | Nov 16 2015 11:25PM | 49.459 | 49.075 | 9, 18, 24 | 18.183 | 0.384 | 30.892 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.7 | 21.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 7, 2
AB/56-1 | SGBM31 | Feb 11 2016 4:40PM | Feb 12 2016 7:45PM | 49.407 | 49.075 |  | 16.171 | 0.332 | 32.904 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.9 | 24.0 | 14.6 | G35T2 | 1, 2, 3 | 8, 8, 8
AA/56-2 | SGBM17 | Dec 30 2015 1:20PM | Dec 31 2015 4:30PM | 49.445 | 47.525 |  | 16.675 | 1.920 | 30.850 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.6 | 26.0 | -100.0 | G35T2 | C480014316, C480014317, C480014321 | 11, 11, 4
Z/53-1 | SGBM17 | Dec 18 2015 9:30AM | Dec 18 2015 8:06PM | 49.478 | 47.425 |  | 17.227 | 2.053 | 30.198 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 23.0 | -100.0 | G45T2 | PJ 3377, PJ 3380, PJ 3385 | 8, 8, 7
Z/53-2 | SGBM16 | Dec 22 2015 1:20PM | Dec 23 2015 6:30AM | 49.448 | 47.425 |  | 18.331 | 2.023 | 29.094 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 26.0 | -100.0 | G45T2 | C480013883, C480013885, C520124340 | 6, 10, 10
Z/54-1 | SGBM19 | Dec 26 2015 8:00AM | Dec 26 2015 2:45PM | 49.484 | 47.425 |  | 18.347 | 2.059 | 29.078 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 7
Z/54-2 | SGBM05 | Dec 18 2015 1:40PM | Dec 22 2015 1:26AM | 49.510 | 47.425 |  | 18.367 | 2.085 | 29.058 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | 29.8 | G45T2 | C480013781, C480013783, C480013786 | 9, 10, 5
Z/55-1 | SGBM19 | Dec 23 2015 4:30PM | Dec 26 2015 7:51PM | 49.564 | 47.625 |  | 18.226 | 1.939 | 29.399 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 23.0 | -100.0 | G45T2 | PJ 3547, PJ 3549, PJ 3553 | 8, 8, 7
Z/55-2 | SGBM19 | Dec 16 2015 4:06PM | Dec 17 2015 5:44PM | 49.534 | 47.625 |  | 18.618 | 1.909 | 29.007 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G45T2 | PJ 3279, PJ 3285, PJ 3291 | 10, 6, 6
Z/55-3 | SGBM17 | Dec 21 2015 3:00PM | Dec 22 2015 3:04AM | 49.495 | 47.625 |  | 17.697 | 1.870 | 29.928 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.0 | 31.0 | -100.0 | G45T2 | C480013789, C520124305, C480013791 | 10, 10, 11
Z/56-1 | SGBM19 | Dec 10 2015 8:30AM | Dec 10 2015 9:50PM | 49.623 | 46.175 |  | 14.289 | 3.448 | 31.886 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.3 | 28.0 | 38.0 | G45T2 | PJ 2920, PJ 2922, PJ 2923, PJ 2928 | 8, 3, 9, 8
Z/56-2 | SGBM19 | Dec 15 2015 6:00PM | Dec 16 2015 7:12PM | 49.387 | 46.175 |  | 13.828 | 3.212 | 32.347 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.6 | 25.0 | 21.5 | G45T2 | PJ 3209, PJ 3210, PJ 3214 | 9, 8, 8
Z/56-3 | SGBM19 | Dec 11 2015 12:12PM | Dec 12 2015 6:11PM | 49.538 | 46.175 |  | 14.281 | 3.363 | 31.894 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.3 | 25.0 | 23.2 | G45T2 | PJ 3030, PJ 3033, PJ 3035 | 7, 11, 7
Z/56-4 | SGBM19 | Dec 9 2015 11:30AM | Dec 9 2015 11:00PM | 49.600 | 46.175 |  | 14.552 | 3.425 | 31.623 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.1 | 26.0 | -100.0 | G45T2 | PJ 2846, PJ 2847, PJ 2850 | 8, 9, 9
Z/56-5 | SGBM19 | Dec 10 2015 9:50AM | Dec 11 2015 4:37AM | 49.562 | 46.175 |  | 14.904 | 3.387 | 31.271 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 30.0 | 50.8 | G45T2 | PJ 2947, PJ 2948, PJ 2949 | 8, 7, 8
Z/58-1 | SGBM16 | Dec 14 2015 9:20AM | Dec 14 2015 9:45PM | 49.502 | 47.425 |  | 16.152 | 2.077 | 31.273 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.9 | 25.0 | -100.0 | G45T2 | PJ 3104, PJ 3106, PJ 3108, PJ 3109 | 8, 7, 8, 2
Z/58-2 | SGBM16 | Dec 12 2015 9:20AM | Dec 12 2015 8:44PM | 49.602 | 47.425 |  | 15.260 | 2.177 | 32.165 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.5 | 30.0 | -100.0 | G45T2 | C480013185, C480013186, C480013190 | 10, 10, 10
Z/59-1 | SGBM19 | Dec 14 2015 8:30AM | Dec 14 2015 11:30PM | 49.543 | 47.425 |  | 14.285 | 2.118 | 33.140 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 22.0 | -100.0 | G45T2 | C480013254, C480013260 | 11, 11
Z/59-2 | SGBM17 | Dec 10 2015 7:10PM | Dec 11 2015 6:25PM | 49.755 | 47.425 |  | 14.375 | 2.330 | 33.050 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 27.0 | -100.0 | G45T2 | PJ 2962, PJ 2964, PJ 2968, PJ 2975 | 8, 8, 9, 2
Z/60-1 | SGBM17 | Dec 19 2015 9:00AM | Dec 19 2015 9:54PM | 49.586 | 46.505 |  | 13.314 | 3.081 | 33.191 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 31.0 | -100.0 | G45T2 | C520124232, C520124234, C480013709 | 10, 10, 11
Z/60-2 | SGBM16 | Dec 21 2015 10:00AM | Dec 21 2015 10:17PM | 49.630 | 46.505 |  | 13.465 | 3.125 | 33.040 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 31.0 | -100.0 | G45T2 | PJ3471, PJ 3472, PJ 3474, PJ 3476, PJ 3477 | 7, 8, 6, 6, 4
Z/61-1 | SGBM19 | Dec 19 2015 8:33AM | Dec 19 2015 9:05PM | 49.684 | 46.505 |  | 13.540 | 3.179 | 32.965 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 22.0 | 4.9 | G45T2 | C520124229, C520124231 | 10, 12
Z/61-2 | SGBM17 | Dec 28 2015 6:30PM | Dec 29 2015 4:17PM | 49.533 | 46.505 |  | 13.865 | 3.028 | 32.640 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.8 | 25.0 | -100.0 | G45T2 | PJ 3661, PJ 3663, PJ3669 | 8, 10, 7
Z/62-1 | SGBM17 | Dec 28 2015 4:30PM | Dec 29 2015 10:00PM | 49.664 | 47.705 |  | 15.911 | 1.959 | 31.794 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 27.0 | -100.0 | G45T2 | PJ 3697, PJ 3698, PJ 3706 | 10, 9, 8
Z/63-1 | SGBM31 | Feb 15 2016 10:15AM | Feb 16 2016 4:45PM | 49.145 | 48.155 |  | 14.292 | 0.990 | 33.863 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.5 | 25.0 | -100.0 | G45T2 | PJ 5585, PJ 5588, PJ 5594 | 9, 8, 8
Y/51-1 | SGBM17 | Jan 5 2016 2:30PM | Jan 6 2016 1:15AM | 49.520 | 48.075 |  | 19.920 | 1.445 | 28.155 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 25.0 | -17.9 | G45T2 | PJ 4021, PJ 4022, PJ 4023 | 8, 10, 7
Y/51-2 | SGBM22 | Dec 31 2015 8:00AM | Jan 2 2016 2:30PM | 49.635 | 48.075 |  | 20.889 | 1.560 | 27.186 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 23.0 | -17.3 | G45T2 | PJ 3849, PJ 3852, PJ 3855 | 8, 8, 7
Y/51-3 | SGBM05 | Dec 26 2015 3:20PM | Dec 28 2015 4:16PM | 49.578 | 48.075 |  | 19.159 | 1.503 | 28.916 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.4 | 28.0 | 106.5 | G45T2 | PJ 3583, PJ 3585, PJ 3588, PJ 3593 | 8, 8, 7, 5
Y/54-1 | SGBM19 | Nov 27 2015 6:00PM | Nov 28 2015 5:07PM | 49.249 | 48.075 | 9, 15.8 | 19.356 | 1.174 | 28.719 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 23.0 | -18.3 | G45T2 | PJ 2298, PJ 2300, PJ 2304 | 8, 7, 8
Y/54-2 | SGBM17 | Nov 19 2015 10:26AM | Nov 19 2015 3:25PM | 49.227 | 48.075 | 9 | 19.952 | 1.152 | 28.123 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
Y/54-3 | SGBM19 | Dec 10 2015 6:00PM | Dec 11 2015 9:30PM | 49.477 | 48.075 |  | 20.023 | 1.402 | 28.052 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 22.0 | -100.0 | G45T2 | PJ 2977, PJ 2979, PJ 2985 | 8, 7, 7
Y/55-1 | SGBM17 | Dec 2 2015 4:00PM | Dec 3 2015 6:48PM | 49.162 | 48.075 | 9, 22.1 | 19.001 | 1.087 | 29.074 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | -18.5 | G45T2 | PJ 2549, PJ 2551, PJ 2552 | 6, 7, 11
Y/55-2 | SGBM19 | Dec 15 2015 9:10AM | Dec 15 2015 10:08PM | 49.324 | 48.075 |  | 19.027 | 1.249 | 29.048 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -18.5 | G45T2 | PJ 3167, PJ 3169, PJ 3170 | 8, 6, 8
Y/55-3 | SGBM17 | Dec 9 2015 11:35AM | Dec 9 2015 7:42PM | 49.447 | 48.075 |  | 18.786 | 1.372 | 29.289 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 26.0 | -100.0 | G45T2 | PJ 2830, PJ 2832, PJ 2837, PJ 2842 | 9, 7, 7, 3
Y/55a-1 | SGBM19 | Nov 24 2015 3:05PM | Nov 25 2015 10:05AM | 49.435 | 46.175 | 9, 32 | 18.175 | 3.260 | 28.000 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 25.0 | 40.3 | G45T2 | 2090, 2091, 2092, 2095 | 8, 7, 7, 3
Y/55a-2 | SGBM17 | Nov 26 2015 1:20PM | Nov 27 2015 5:16PM | 49.475 | 46.175 | 9 | 17.803 | 3.300 | 28.372 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | -18.1 | G45T2 | PJ 2239, PJ 2243, PJ 2248 | 8, 8, 7
Y/55a-3 | SGBM19 | Dec 5 2015 10:40AM | Dec 7 2015 5:30PM | 49.370 | 46.175 |  | 17.070 | 3.195 | 29.105 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G45T2 | PJ 2711, PJ 2713, PJ 2716 | 8, 8, 7
Y/55a-4 | SGBM19 | Dec 7 2015 8:30AM | Dec 8 2015 11:02PM | 49.393 | 46.175 |  | 17.793 | 3.218 | 28.382 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | -100.0 | G45T2 | C480012886, C480012890 | 11.5, 11.5
Y/55a-5 | SGBM19 | Dec 4 2015 8:30AM | Dec 5 2015 2:04AM | 49.592 | 46.175 |  | 18.012 | 3.417 | 28.163 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 7, 7
Y/55a-6 | SGBM19 | Nov 25 2015 8:17AM | Nov 25 2015 5:26PM | 49.620 | 46.175 | 9 | 18.080 | 3.445 | 28.095 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 21.0 | 3.1 | G45T2 | 2121, 2122, 2126 | 7, 7, 7
Y/55a-7 | SGBM19 | Nov 27 2015 2:02PM | Nov 27 2015 10:50PM | 49.516 | 46.175 | 9 | 17.849 | 3.341 | 28.326 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 23.0 | -100.0 | G45T2 | PJ 2267, PJ 2270, PJ 2274 | 8, 7, 8
Y/55a-8 | SGBM17 | Nov 28 2015 2:00PM | Dec 1 2015 4:43PM | 49.489 | 46.175 | 9, 24.8, 28.3 | 17.885 | 3.314 | 28.290 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 24.0 | -18.0 | G45T2 | PJ 2419, PJ 2421, PJ 2422 | 8, 8, 8
Y/56a-1 | SGBM19 | Dec 7 2015 8:30AM | Dec 8 2015 2:53AM | 49.449 | 46.175 |  | 21.174 | 3.274 | 25.001 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.9 | 23.0 | -15.9 | G45T2 | C480012831, C480012832 | 11.5, 11.5
Y/56a-2 | SGBM17 | Dec 2 2015 11:30AM | Dec 2 2015 10:16PM | 49.510 | 46.175 | 9 | 17.677 | 3.335 | 28.498 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | 26.8 | G45T2 | PJ 2484, PJ 2487, PJ 2490 | 9, 7, 7
Y/56a-3 | SGBM17 | Dec 9 2015 10:40AM | Dec 10 2015 2:39AM | 49.578 | 46.175 |  | 17.941 | 3.403 | 28.234 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 28.0 | 10.0 | G45T2 | PJ 2866, PJ 2869, PJ 2870, PJ 2871 | 8, 8, 7, 5
Y/56a-4 | SGBM19 | Dec 5 2015 9:00AM | Dec 6 2015 3:46AM | 49.501 | 46.175 |  | 17.938 | 3.326 | 28.237 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 23.0 | -100.0 | G45T2 | PJ 2689, PJ 2690, PJ 2691 | 8, 8, 7
Y/56a-5 | SGBM19 | Dec 7 2015 3:30PM | Dec 8 2015 9:30PM | 49.417 | 46.175 |  | 17.406 | 3.242 | 28.769 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 23.0 | -100.0 | G45T2 | C480012877, C480012880 | 11.5, 11.5
Y/56a-6 | SGBM17 | Dec 2 2015 1:20PM | Dec 3 2015 12:39AM | 49.570 | 46.175 | 9 | 17.466 | 3.395 | 28.709 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 23.0 | -100.0 | G45T2 | PJ 2496, PJ 2498, PJ 2500 | 8, 7, 8
Y/56a-7 | SGBM17 | Dec 4 2015 8:40AM | Dec 4 2015 11:20PM | 49.412 | 46.175 |  | 17.710 | 3.237 | 28.465 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 8, 7, 2
Y/56a-8 | SGBM17 | Dec 5 2015 8:30AM | Dec 5 2015 8:41PM | 49.549 | 46.175 |  | 17.628 | 3.374 | 28.547 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.2 | 23.0 | -18.2 | G45T2 | PJ 2659, PJ 2661, PJ 2664 | 4, 12, 7
Y/62-1 | SGBM19 | Dec 16 2015 8:00AM | Dec 16 2015 8:09PM | 49.837 | 49.075 |  | 19.013 | 0.762 | 30.062 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.1 | 22.0 | -100.0 | G45T2 | PJ 3213, PJ 3215, PJ 3217 | 7, 8, 7
X/51-1 | SGBM22 | Jan 2 2016 4:20PM | Jan 4 2016 4:55PM | 49.502 | 48.075 |  | 21.870 | 1.427 | 26.205 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 25.0 | -100.0 | G45T2 | C520124608, C480014442, C520124609 | 12, 11, 2
X/51-2 | SGBM05 | Dec 28 2015 1:30PM | Dec 29 2015 12:27AM | 49.478 | 48.075 |  | 21.271 | 1.403 | 26.804 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.1 | 22.0 | -100.0 | G45T2 | PJ 3631, PJ 3632, PJ 3633 | 8, 7, 7
X/51-3 | SGBM19 | Dec 22 2015 10:20AM | Dec 24 2015 12:53AM | 49.280 | 48.075 |  | 22.029 | 1.205 | 26.046 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 20.0 | -100.0 | G45T2 | C520124367, C520124372 | 8, 12
X/54-1 | SGBM19 | Nov 28 2015 8:30AM | Dec 1 2015 6:10PM | 49.317 | 48.075 | 9, 15.3 | 20.475 | 1.242 | 27.600 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.6 | 21.0 | -100.0 | G45T2 | 1, 2 | 11, 10
X/54-2 | SGBM19 | Nov 18 2015 8:05AM | Nov 19 2015 1:15AM | 49.404 | 48.075 | 9 | 22.000 | 1.329 | 26.075 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 27.0 | -16.6 | G45T2 | 2, 2, 3, 4 | 7, 8, 4, 8
X/54-3 | SGBM22 | Dec 10 2015 6:26PM | Dec 12 2015 3:00AM | 49.482 | 48.075 |  | 20.978 | 1.407 | 27.097 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 20.0 | -100.0 | G45T2 | PJ 3003, PJ 3005, PJ 3007 | 7, 7, 6
X/55-1 | SGBM22 | Dec 15 2015 8:00AM | Dec 15 2015 8:13PM | 49.491 | 48.075 |  | 20.854 | 1.416 | 27.221 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 23.0 | -17.3 | G45T2 | PJ 3155, PJ 3156, PJ 3161 | 8, 8, 7
X/55-2 | SGBM19 | Dec 11 2015 6:00PM | Dec 13 2015 5:25AM | 49.627 | 48.075 |  | 20.326 | 1.552 | 27.749 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.7 | 21.0 | -100.0 | G45T2 | PJ 3076, PJ 3079, PJ 3080 | 7, 7, 7
X/55-3 | SGBM22 | Dec 9 2015 10:40AM | Dec 10 2015 12:16AM | 49.520 | 48.075 |  | 19.674 | 1.445 | 28.401 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | -100.0 | G45T2 | PJ 2852, PJ 2855, PJ 2860 | 8, 8, 7
X/57-1 | SGBM17 | Dec 17 2015 9:00AM | Dec 18 2015 5:51PM | 49.500 | 48.075 |  | 19.378 | 1.425 | 28.697 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 28.0 | -100.0 | G45T2 | PJ 3365, PJ 3366, PJ 3368, PJ 3375 | 8, 7, 7, 6
X/57-2 | SGBM22 | Dec 11 2015 6:00PM | Dec 13 2015 12:00AM | 49.670 | 48.075 |  | 20.571 | 1.595 | 27.504 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.5 | 22.0 | 25.7 | G45T2 | PJ 3052, PJ 3054, PJ 3057 | 8, 6, 8
X/57-3 | SGBM22 | Dec 8 2015 2:30PM | Dec 9 2015 1:17AM | 49.628 | 48.075 |  | 20.525 | 1.553 | 27.550 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.5 | 19.0 | 1.5 | G45T2 | PJ 2794, PJ 2796, PJ 2797 | 7, 6, 6
X/62-1 | SGBM22 | Dec 16 2015 9:20AM | Dec 17 2015 12:50AM | 49.954 | 49.075 |  | 20.195 | 0.879 | 28.880 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.4 | 22.0 | -100.0 | G45T2 | PJ 3241, PJ 3243, PJ 3247 | 7, 8, 7
W/51-1 | SGBM17 | Dec 31 2015 8:20AM | Dec 31 2015 8:05PM | 49.376 | 47.625 |  | 21.514 | 1.751 | 26.111 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 26.0 | -100.0 | G45T2 | C480014337, C480014338, C480014340 | 5, 10, 11
W/51-2 | SGBM22 | Dec 28 2015 10:45AM | Dec 29 2015 1:36AM | 49.478 | 47.625 |  | 21.173 | 1.853 | 26.452 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 22.0 | -100.0 | G45T2 | PJ 3634, PJ 3635, PJ 3636 | 7, 8, 7
W/51-3 | SGBM22 | Dec 22 2015 10:00AM | Dec 23 2015 11:04PM | 49.182 | 47.625 |  | 21.521 | 1.557 | 26.104 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 25.0 | -100.0 | G45T2 | C480013953, C520124360, C520124367 | 11, 12, 2
W/53-1 | SGBM22 | Dec 10 2015 8:40AM | Dec 10 2015 6:30PM | 49.545 | 47.625 |  | 20.756 | 1.920 | 26.869 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.1 | 22.0 | -100.0 | G45T2 | PJ 2901, PJ 2903, PJ 2906 | 7, 8, 7
W/53-2 | SGBM19 | Dec 4 2015 1:30PM | Dec 4 2015 7:06PM | 49.450 | 47.625 |  | 21.321 | 1.825 | 26.304 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 23.0 | 37.4 | G45T2 | 1, 2, 3 | 9, 7, 7
W/53-3 | SGBM17 | Dec 7 2015 4:25PM | Dec 8 2015 12:11AM | 49.589 | 47.625 |  | 21.306 | 1.964 | 26.319 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 22.0 | -16.7 | G45T2 | C480012822, C480012823 | 11, 11
W/56-1 | SGBM22 | Dec 14 2015 3:00PM | Dec 15 2015 1:00AM | 49.603 | 49.075 |  | 22.467 | 0.528 | 26.608 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 22.0 | -100.0 | G45T2 | C480013262, C480013271 | 11, 11
W/62-1 | SGBM22 | Dec 17 2015 9:10AM | Dec 18 2015 2:30AM | 49.672 | 49.075 |  | 23.015 | 0.597 | 26.060 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 24.0 | -100.0 | G45T2 | PJ 3329, PJ 3331, PJ 3336 | 8, 8, 8
V/56-1 | SGBM17 | Dec 30 2015 8:40AM | Jan 30 2016 8:55PM | 49.412 | 48.775 |  | 22.740 | 0.637 | 26.035 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 22.0 | -100.0 | G45T2 | C480014278, C170014207, C170014210 | 11, 8, 3
V/61-1 | SGBM17 | Jan 9 2016 10:23AM | Jan 11 2016 12:25PM | 49.493 | 47.575 |  | 20.167 | 1.918 | 27.408 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.4 | 27.0 | -100.0 | G45T2 | 1, 2, 4, 4 | 8, 8, 8, 3
V/61-2 | SGBM17 | Jan 12 2016 4:36PM | Jan 13 2016 7:10PM | 49.517 | 47.575 |  | 19.915 | 1.942 | 27.660 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.6 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 7, 7
U/62-1 | SGBM20 | Feb 10 2016 10:45AM | Feb 10 2016 7:20PM | 51.141 | 51.375 |  | 21.891 | -0.234 | 29.484 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.8 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 7
J/44-1 | SGBM23 | Nov 12 2015 12:45PM | Nov 13 2015 8:52PM | 51.678 | 47.825 | 9 | 14.285 | 3.853 | 33.540 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.3 | 26.0 | -21.3 | G45T2 | C170013490, C170013491, C170013492 | 9, 10, 7
J/44-2 | SGBM18 | Nov 14 2015 8:40PM | Nov 16 2015 4:28PM | 51.791 | 47.825 |  | 14.441 | 3.966 | 33.384 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 7, 6
J/44-3 | SGBM15 | Nov 30 2015 1:30PM | Nov 30 2015 9:57PM | 51.638 | 47.825 | 9 | 14.435 | 3.813 | 33.390 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
J/44-5 | SGBM23 | Dec 4 2015 7:38PM | Dec 5 2015 5:41PM | 51.616 | 47.825 | 9 | 14.557 | 3.791 | 33.268 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 27.0 | -100.0 | G45T2 | C480012721, C480012723, C480012727 | 11, 11, 5
J/44-6 | SGBM18 | Nov 17 2015 8:30AM | Nov 17 2015 4:15PM | 51.776 | 47.825 |  | 14.667 | 3.951 | 33.158 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 4, 10, 10
J/44-7 | SGBM23 | Nov 12 2015 1:15PM | Nov 13 2015 5:55PM | 51.830 | 47.825 | 9 | 14.208 | 4.005 | 33.617 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.4 | 26.0 | -100.0 | G45T2 | C520123325, C520123326, C520123327 | 5, 11, 10
J/44-8 | SGBM15 | Dec 2 2015 3:30PM | Dec 3 2015 12:10PM | 51.593 | 47.825 | 9, 37 | 14.476 | 3.768 | 33.349 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 25.0 | -21.2 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
J/44-10 | SGBM23 | Nov 19 2015 6:10PM | Nov 21 2015 12:15PM | 51.730 | 47.825 | 9, 23, 25, 29 | 14.797 | 3.905 | 33.028 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 26.0 | -1.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 7, 6
J/44-11 | SGBM23 | Nov 12 2015 1:00PM | Nov 13 2015 9:25PM | 0.000 | 47.825 | 9 | -38.000 | -47.825 | 85.825 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 54.6 | 25.0 | -54.6 | G45T2 | C170013492, C480011692, C520123331 | 3, 11, 11
J/44-12 | SGBM15 | Nov 14 2015 6:00PM | Nov 16 2015 11:00PM | 51.884 | 47.825 | 9 | 14.752 | 4.059 | 33.073 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 4
J/44-13 | SGBM15 | Nov 18 2015 10:30AM | Nov 19 2015 11:35AM | 51.965 | 47.825 | 9 | 14.228 | -47.825 | 33.597 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.4 | 25.0 | -21.4 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
J/44-15 | SGBM15 | Nov 27 2015 5:05PM | Nov 28 2015 3:59PM | 51.613 | 47.825 | 9, 32 | 14.532 | 3.788 | 33.293 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.2 | 24.0 | 2.8 | G45T2 | c480012367, c480012368 | 12, 12
J/44-16 | SGBM15 | Nov 17 2015 6:44PM | Nov 18 2015 5:21PM | 51.950 | 47.825 | 9, 24 | 14.702 | 4.125 | 33.123 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 3
J/44-17 | SGBM23 | Nov 12 2015 1:48PM | Nov 13 2015 5:18PM | 51.775 | 47.825 | 9 | 14.632 | -47.825 | 33.193 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 31.0 | 9.9 | G45T2 | C520123323, C520123324, C520123325 | 11, 10, 10
J/44-18 | SGBM15 | Nov 14 2015 6:30PM | Nov 17 2015 12:42AM | 51.809 | 47.825 | 9 | 14.761 | 3.984 | 33.064 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 6, 6, 6, 3
M7/51-1 | SGBM01 | Jan 5 2016 5:45PM | Jan 6 2016 8:40PM | 51.846 | 50.775 |  | 16.915 | 1.071 | 33.860 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 9, 7
Ma/51-1 | SGBM01 | Jan 5 2016 6:00PM | Jan 6 2016 2:27PM | 51.890 | 50.775 |  | 16.392 | 1.115 | 34.383 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.9 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 8, 8
Ma/52-1 | SGBM23 | Dec 18 2015 10:38AM | Dec 19 2015 3:03PM | 51.977 | 51.375 |  | 17.276 | 0.602 | 34.099 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 11.5, 11.5, 4
M/52-1 | SGBM02 | Nov 30 2015 7:05PM | Dec 1 2015 5:50PM | 51.850 | 51.375 | 9, 24.5 | 16.744 | 0.505 | 34.631 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.0 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 3, 2
N/27-1 | SGBM01 | Dec 28 2015 4:15PM | Dec 29 2015 10:33AM | 51.984 | 51.075 |  | -22.000 | 0.909 | 73.075 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 46.5 | 17.0 | -100.0 | G45T2 | 1, 2 | 8, 9
N/28-1 | SGBM20 | Dec 24 2015 10:00AM | Dec 25 2015 1:27PM | 51.928 | 51.075 |  | 30.810 | 0.853 | 20.265 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 16.0 | -100.0 | G45T2 | 1, 2 | 8, 8
M5b/56-1 | SGBM23 | Jan 19 2016 11:05AM | Jan 19 2016 7:45PM | 51.905 | 51.375 |  | 17.706 | 0.530 | 33.669 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.4 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 3
M7a/61-1 | SGBM01 | Feb 5 2016 4:50PM | Feb 13 2016 1:10PM | 51.772 | 49.775 |  | 16.967 | 1.997 | 32.808 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.9 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 8
Ta/61a-1 | SGBM23 | Feb 18 2016 2:00PM | Feb 19 2016 7:00PM | 52.105 | 49.775 |  | 23.054 | 2.330 | 26.721 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.0 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 8
T1b/55-1 | SGBM23 | Feb 16 2016 11:20AM | Feb 16 2016 8:25PM | 51.931 | 51.075 |  | 21.935 | 0.856 | 29.140 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
T1b/58-1 | SGBM23 | Feb 17 2016 10:55AM | Feb 17 2016 5:55PM | 51.938 | 51.375 |  | 24.324 | 0.563 | 27.051 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 23.0 | 33.6 | G45T2 | 1, 2, 3 | 7, 8, 8
T1b/59-1 | SGBM23 | Feb 16 2016 11:00AM | Feb 17 2016 9:50PM | 51.918 | 51.375 |  | 24.837 | 0.543 | 26.538 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.9 | 21.0 | -100.0 | G45T2 | 1, 2 | 10.5, 10.5
T1b/60-1 | SGBM23 | Feb 18 2016 1:25PM | Feb 19 2016 12:10AM | 51.982 | 50.775 |  | 24.333 | 1.207 | 26.442 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
U/52-1 | SGBM17 | Jan 18 2016 8:23AM | Jan 18 2016 4:20PM | 52.599 | 50.175 |  | 22.930 | 2.424 | 27.245 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/52-2 | SGBM17 | Jan 21 2016 8:30AM | Jan 21 2016 5:35PM | 51.889 | 50.175 |  | 23.791 | 1.714 | 26.384 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 7
U/53-1 | SGBM17 | Jan 20 2016 9:12AM | Jan 20 2016 9:30PM | 51.842 | 50.175 |  | 23.851 | 1.667 | 26.324 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 4, 10, 7
U/53-2 | SGBM19 | Jan 16 2016 3:49PM | Jan 18 2016 2:35PM | 51.835 | 50.175 |  | 23.840 | 1.660 | 26.335 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/54-1 | SGBM19 | Jan 19 2016 8:40AM | Jan 19 2016 6:40PM | 51.925 | 50.175 |  | 23.954 | 1.750 | 26.221 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/54-2 | SGBM19 | Jan 15 2016 4:39PM | Jan 16 2016 4:40PM | 51.827 | 50.175 |  | 23.746 | 1.652 | 26.429 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | -100.0 | G45T2 | PJ 4492, PJ 4493, PJ 4494 | 7, 7, 7
U/56-1 | SGBM17 | Jan 22 2016 4:47PM | Jan 23 2016 2:45PM | 51.786 | 51.375 |  | 23.265 | 0.411 | 28.110 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 21.0 | 17.4 | G45T2 | 1, 2, 3 | 7, 7, 7
U/57-1 | SGBM17 | Jan 18 2016 8:32AM | Jan 18 2016 6:50PM | 51.859 | 50.175 |  | 23.811 | 1.684 | 26.364 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/57-2 | SGBM17 | Jan 21 2016 8:43AM | Jan 21 2016 9:30PM | 51.860 | 50.175 |  | 23.457 | 1.685 | 26.718 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.0 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/58-1 | SGBM17 | Jan 18 2016 8:23AM | Jan 18 2016 4:55PM | 51.986 | 50.175 |  | 23.218 | 1.811 | 26.957 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 21.0 | -100.0 | G45T2 | 4544, 4546, 4547 | 7, 7, 7
U/58-2 | SGBM17 | Jan 23 2016 1:47PM | Jan 26 2016 2:40PM | 51.919 | 50.175 |  | 23.806 | 1.744 | 26.369 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/59-1 | SGBM20 | Jan 22 2016 8:44AM | Jan 22 2016 6:40PM | 51.918 | 50.175 |  | 24.577 | 1.743 | 25.598 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.3 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
U/59-2 | SGBM17 | Jan 26 2016 10:50AM | Jan 26 2016 10:30PM | 51.976 | 50.175 |  | 24.367 | 1.801 | 25.808 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.4 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 8
U/60-1 | SGBM31 | Jan 30 2016 2:50PM | Feb 2 2016 7:05PM | 51.029 | 45.875 |  | 20.502 | 5.154 | 25.373 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.1 | 22.0 | -100.0 | G45T2 | C480016181, C480016182 | 11, 11
U/60-2 | SGBM17 | Jan 27 2016 9:34AM | Jan 27 2016 10:40PM | 51.982 | 45.875 |  | 20.559 | 6.107 | 25.316 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.1 | 19.0 | -100.0 | G45T2 | PJ 4990, PJ 4994 | 10, 9
T2a/52-1 | SGBM20 | Jan 28 2016 3:00PM | Jan 29 2016 9:10PM | 51.811 | 51.375 |  | 24.426 | 0.436 | 26.949 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.1 | 21.0 | -100.0 | G45T2 | PJ 5087, PJ 5088, PJ 5091 | 7, 7, 7
T2a/55-1 | SGBM20 | Jan 28 2016 8:35AM | Jan 28 2016 7:40PM | 51.827 | 51.375 |  | 23.288 | 0.452 | 28.087 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 23.0 | -100.0 | G45T2 | PJ 5028, PJ 5632, PJ 5036 | 8, 8, 7
T2a/56-1 | SGBM20 | Feb 3 2016 9:30AM | Feb 3 2016 11:25PM | 51.075 | 51.375 |  | 23.788 | -0.300 | 27.587 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.6 | 21.0 | -100.0 | G45T2 | PJ 5261, PJ 5262, PJ 5264 | 8, 6.5, 6.5
T2a/58-1 | SGBM17 | Jan 28 2016 8:15AM | Jan 28 2016 4:10PM | 51.909 | 51.375 |  | 24.569 | 0.534 | 26.806 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.1 | 21.0 | -100.0 | G45T2 | PJ 5014, PJ 5015, PJ 5017 | 7, 7, 7
T2a/59-1 | SGBM31 | Jan 30 2016 3:20PM | Feb 2 2016 3:45PM | 51.960 | 51.375 |  | 25.028 | 0.585 | 26.347 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | -100.0 | G45T2 | Pending, PJ 5180, PJ 5183 | 7, 7, 7
T2a/60-1 | SGBM17 | Jan 28 2016 3:30PM | Jan 30 2016 12:45AM | 52.012 | 51.375 |  | 25.634 | 0.637 | 25.741 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.4 | 22.0 | -100.0 | G45T2 | PJ 5102, PJ 5104, PJ 5106 | 8, 7, 7
Ua/35-1 | SGBM16 | Dec 28 2015 8:15AM | Dec 28 2015 4:25PM | 52.218 | 51.3725 |  | 29.325 | 0.846 | 22.047 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.0 | 18.0 | -100.0 | G45T2 | 1, 2 | 10, 8
Ua/38-1 | SGBM16 | Dec 30 2015 2:20PM | Dec 31 2015 2:30AM | 52.412 | 50.125 |  | 25.125 | 2.287 | 25.000 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.9 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Ua/38-2 | SGBM23 | Jan 7 2016 8:34AM | Jan 7 2016 5:10PM | 52.573 | 50.125 |  | 24.704 | 2.448 | 25.421 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.2 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Ua/42-1 | SGBM16 | Jan 4 2016 4:30PM | Jan 5 2016 7:20PM | 51.971 | 50.125 |  | 22.056 | 1.846 | 28.069 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 25.0 | 40.0 | G45T2 | 1, 2, 3 | 5, 10, 10
Ua/42-2 | SGBM19 | Jan 8 2016 8:20AM | Jan 8 2016 9:44PM | 52.008 | 50.125 |  | 22.078 | 1.883 | 28.047 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 24.0 | 34.5 | G45T2 | PJ 4174, PJ 4179, PJ 4183 | 8, 8, 8
Ua/43-1 | SGBM17 | Jan 6 2016 8:15AM | Jan 6 2016 11:00PM | 52.949 | 50.125 |  | 23.119 | 2.824 | 27.006 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 23.0 | -100.0 | G45T2 | PJ 4068, PJ 4070, PJ 4075 | 8, 8, 7
Ua/43-2 | SGBM19 | Jan 9 2016 8:07AM | Jan 9 2016 4:45PM | 51.893 | 50.125 |  | 23.073 | 1.768 | 27.052 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 8
Ua/44-1 | SGBM19 | Jan 6 2016 8:50AM | Jan 6 2016 7:28PM | 51.965 | 50.125 |  | 23.124 | 1.840 | 27.001 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 25.0 | -100.0 | G45T2 | C480014604, C520124663, C4800114612 | 7, 9, 9
Ua/44-2 | SGBM22 | Jan 8 2016 8:10AM | Jan 8 2016 7:19PM | 51.958 | 50.125 |  | 23.034 | 1.833 | 27.091 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 24.0 | 39.2 | G45T2 | PJ 4157, PJ 4161, PJ 4167 | 8, 8, 8
Ua/45-1 | SGBM31 | Jan 12 2016 10:19AM | Jan 12 2016 8:25PM | 51.829 | 50.125 |  | 24.089 | 1.704 | 26.036 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
Ua/45-2 | SGBM23 | Jan 15 2016 8:35AM | Jan 15 2016 6:15PM | 51.148 | 50.125 |  | 24.084 | 1.023 | 26.041 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.6 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
Ma/53-1 | SGBM23 | Dec 19 2015 9:50AM | Dec 19 2015 4:18PM | 51.860 | 51.375 |  | 16.865 | 0.485 | 34.510 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.0 | 26.0 | 18.4 | G45T2 | 1, 2, 3 | 6, 10, 10
Ma/54-1 | SGBM23 | Dec 19 2015 9:10AM | Dec 19 2015 10:26PM | 51.856 | 51.375 |  | 16.260 | 0.481 | 35.115 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.3 | 24.0 | 7.4 | G45T2 | 1, 2, 3 | 10, 10, 4
Ma/60-1 | SGBM23 | Dec 28 2015 1:50PM | Dec 29 2015 4:46PM | 51.818 | 49.875 |  | 14.815 | 1.943 | 35.060 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.3 | 25.0 | -22.3 | G45T2 | PJ 3665, PJ 3668, PJ 3671 | 7, 8, 10
Ma/60-2 | SGBM08 | Dec 31 2015 4:25PM | Jan 2 2016 11:30AM | 51.882 | 49.875 |  | 14.430 | 2.007 | 35.445 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.6 | 26.0 | -22.6 | G45T2 | PJ 3837, PJ 3838, PJ 3839 | 10, 8, 8
La/53-1 | SGBM02 | Nov 28 2015 7:06PM | Nov 30 2015 8:58PM | 51.777 | 51.375 | 9 | 15.646 | 0.402 | 35.729 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.7 | 25.0 | 2.3 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
La/54-1 | SGBM02 | Nov 26 2015 2:00PM | Nov 27 2015 11:38PM | 51.920 | 51.375 | 9 | 14.882 | -51.375 | 36.493 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.2 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 4, 8, 8, 8
La/55-1 | SGBM02 | Nov 27 2015 5:20PM | Nov 28 2015 10:36PM | 52.780 | 51.375 | 9 | 16.560 | 1.405 | 34.815 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
La/60-1 | SGBM02 | Nov 24 2015 6:23PM | Nov 26 2015 12:11AM | 53.027 | 51.375 | 9 | 16.100 | 1.652 | 35.275 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.4 | 27.0 | 20.3 | G35T2 | 1, 2, 3, 4 | 7, 7, 6, 7
La/61-1 | SGBM02 | Nov 24 2015 5:42PM | Nov 25 2015 7:00PM | 52.874 | 50.075 | 9 | 13.268 | 2.799 | 36.807 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 23.4 | 26.0 | -23.4 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 5
X7/Y6-3 | SGBM18 | Nov 18 2015 8:00PM | Nov 19 2015 12:50PM | 55.555 | 53.875 |  | 28.781 | 1.680 | 25.094 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.0 | 22.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 7
AA1/41a-1 | SGBM22 | Nov 20 2015 10:10AM | Nov 20 2015 10:02PM | 49.449 | 48.725 |  | 21.974 | 0.724 | 26.751 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 17.0 | 21.0 | -17.0 | G35T2 | 1, 2, 3, 4 | 7, 6, 7, 1
AA1/41b-1 | SGBM19 | Nov 21 2015 8:00AM | Nov 21 2015 6:03PM | 49.457 | 48.725 |  | 22.705 | 0.732 | 26.020 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 16.6 | 31.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 7, 7, 6, 8, 3
Z1/41a-1 | SGBM19 | Nov 23 2015 8:08AM | Nov 23 2015 2:50PM | 49.325 | 48.725 | 9 | 22.100 | 0.600 | 26.625 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12+6 | 16.9 | 20.0 | -16.9 | G35T2 | 1, 2, 3 | 7, 7, 6
Z1/41b-1 | SGBM19 | Nov 20 2015 6:00PM | Nov 21 2015 12:29AM | 49.366 | 48.725 |  | 21.886 | 0.641 | 26.839 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 17.1 | 22.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 6, 8, 7, 1
Ka/26a-1 | SGBM21 | Nov 21 2015 7:20PM | Nov 23 2015 5:35PM | 53.615 | 52.425 | 9, 18 | 32.115 | 1.190 | 20.310 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 12.9 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
Ka/26b-1 | SGBM21 | Nov 21 2015 6:30PM | Nov 23 2015 5:32PM | 53.498 | 52.425 | 9 | 31.949 | -52.425 | 20.476 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 13.0 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
Kb/26b-1 | SGBM21 | Nov 24 2015 1:00AM | Nov 23 2015 5:32PM | 53.498 | 52.425 | 9 | 31.949 | -52.425 | 20.476 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 13.0 | 15.0 | 15.1 | G35T2 | 1, 2 | 7, 8
Kb/26a-1 | SGBM21 | Nov 21 2015 8:00PM | Nov 23 2015 7:20PM | 53.615 | 52.425 | 9, 18 | 32.225 | 1.190 | 20.200 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 12.9 | 15.0 | -100.0 | G35T2 | 1, 2 | 7, 8
H/62-1a | SGBM02 | Nov 23 2015 10:03AM | Nov 24 2015 3:40PM | 52.856 | 50.175 | 9 | 9.345 | 2.681 | 40.830 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 26.0 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 8, 8, 7
H/62-1b | SGBM02 | Nov 23 2015 10:45AM | Nov 23 2015 9:51PM | 52.822 | 50.175 | 9, 42 | 9.808 | 2.647 | 40.367 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 25.7 | 33.0 | -25.7 | G35T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 6
Kb/32a-1 | SGBM21 | Nov 28 2015 10:40AM | Nov 29 2015 2:54PM | 52.110 | 52.425 | 9 | 35.261 | -0.315 | 17.164 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 10.9 | 17.0 | -10.9 | G35T2 | 1, 2, 3 | 6, 6, 5
Kb/33b-1 | SGBM21 | Nov 26 2015 11:45AM | Nov 27 2015 7:42PM | 52.063 | 52.425 | 9 | 35.088 | -0.362 | 17.337 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 11.0 | 13.0 | -100.0 | G35T2 | 1, 2 | 7, 6
Ka/33b-1 | SGBM21 | Nov 28 2015 10:00AM | Nov 29 2015 1:42PM | 52.130 | 52.425 | 9 | 35.153 | -0.362 | 17.272 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 11.0 | 17.0 | 6.0 | G35T2 | 1, 2, 3 | 6, 6, 5
Ka/32a-1 | SGBM21 | Nov 26 2015 11:00AM | Nov 27 2015 6:03PM | 52.038 | 52.425 | 9 | 35.206 | -0.387 | 17.219 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 11.0 | 13.0 | 2.0 | G35T2 | 1, 2 | 7, 6
X7/Y6-6 | SGBM18 | Dec 3 2015 8:00AM | Dec 3 2015 8:12PM | 55.515 | 53.875 |  | 28.835 | 1.640 | 25.040 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.9 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 5
X3/Y8-1 | SGBM18 | Dec 4 2015 5:30PM | Dec 5 2015 3:17PM | 55.698 | 54.775 | 9 | 30.709 | 0.923 | 24.066 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.3 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 6
X4/Y8-1 | SGBM18 | Dec 4 2015 6:10PM | Dec 5 2015 6:38PM | 55.717 | 55.075 | 9 | 32.339 | 0.642 | 22.736 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.5 | 19.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 6, 6
X5/Y8-1 | SGBM21 | Dec 7 2015 12:00PM | Dec 8 2015 12:50PM | 55.703 | 55.075 | 9 | 30.902 | 0.628 | 24.173 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.4 | 19.0 | 3.6 | G35T2 | 1, 2, 3 | 6, 6, 7
X9/Y8-1 | SGBM21 | Dec 8 2015 2:00PM | Dec 9 2015 8:23PM | 55.655 | 55.075 | 9, 21 | 29.966 | 0.580 | 25.109 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.0 | 20.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 7, 6
X11/Y8-1 | SGBM21 | Dec 11 2015 8:00PM | Dec 12 2015 7:38PM | 55.791 | 55.075 |  | 28.416 | 0.716 | 26.659 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.0 | 22.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 6, 2
X11/Y8-2 | SGBM21 | Dec 9 2015 11:30AM | Dec 9 2015 11:20PM | 55.694 | 55.075 | 9 | 29.094 | 0.619 | 25.981 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.5 | 22.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 7, 7
X3/Y1-1 | SGBM18 | Dec 9 2015 10:15AM | Dec 10 2015 4:35PM | 55.634 | 54.475 | 9, 26 | 21.446 | -54.475 | 33.029 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.0 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 7, 8, 7
X4/Y1-1 | SGBM18 | Dec 8 2015 3:05PM | Dec 9 2015 5:47PM | 55.559 | 54.775 | 9, 30 | 20.603 | 0.784 | 34.172 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 28.0 | -21.7 | G35T2 | 1, 2, 3, 4 | 7, 6, 7, 8
X5/Y1-1 | SGBM18 | Dec 10 2015 3:30PM | Dec 11 2015 4:23PM | 55.549 | 54.475 | 9, 19 | 20.443 | 1.074 | 34.032 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 29.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 10, 8
Ka/63-1 | SGBM02 | Dec 7 2015 1:10PM | Dec 8 2015 4:15PM | 52.133 | 49.775 | 9, 29 | 11.627 | 2.358 | 38.148 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 24.3 | 28.0 | 15.4 | G35T2 | PJ 2758, PJ 2760, PJ 2763, PJ 2765 | 7, 7, 7, 7
Pa/17-1 | SGBM03 | Dec 7 2015 8:00AM | Dec 8 2015 5:20PM | 55.864 | 55.075 | 9 | 33.832 | 0.789 | 21.243 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.5 | 17.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 6, 5
Qa/17-1 | SGBM03 | Dec 5 2015 3:20PM | Dec 5 2015 8:06PM | 55.778 | 55.075 |  | 34.022 | 0.703 | 21.053 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 17.0 | -100.0 | G35T2 | 1, 2 | 9, 8
Qa/21-1 | SGBM01 | Dec 29 2015 6:30PM | Dec 30 2015 6:30PM | 50.793 | 50.075 |  | 28.939 | 0.718 | 21.136 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 13.4 | 17.0 | -100.0 | G35T2 | 1, 2 | 10, 7
Qa/21-2 | SGBM16 | Dec 31 2015 10:35AM | Jan 1 2016 12:55AM | 50.525 | 50.075 |  | 26.496 | 0.450 | 23.579 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.0 | 16.0 | -100.0 | G35T2 | 1, 2 | 8, 8
Fa/37-1 | SGBM23 | Dec 12 2015 1:05PM | Dec 13 2015 3:12AM | 51.938 | 51.075 |  | 27.120 | -51.075 | 23.955 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 15.2 | 18.0 | 18.1 | G35T2 | 1, 2, 3 | 6, 6, 6
X10/Y2-1 | SGBM21 | Dec 18 2015 4:45PM | Dec 19 2015 1:55PM | 55.747 | 55.075 |  | 26.139 | 0.672 | 28.936 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.4 | 26.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 8, 8
X10/Y4-1 | SGBM20 | Dec 12 2015 12:45PM | Dec 12 2015 10:56PM | 55.102 | 54.975 |  | 25.555 | 0.127 | 29.420 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 27.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 8, 7, 5
X10/Y5-1 | SGBM18 | Nov 17 2015 2:00PM | Nov 18 2015 1:55AM | 55.365 | 55.075 |  | 26.947 | 0.290 | 28.128 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
R/5-1 | SGBM21 | Dec 28 2015 10:00AM | Dec 29 2015 6:03PM | 55.686 | 55.075 |  | 27.963 | 0.611 | 27.112 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.3 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 7
R/5-2 | SGBM21 | Dec 28 2015 10:45AM | Dec 28 2015 7:42PM | 55.750 | 55.075 |  | 28.019 | 0.675 | 27.056 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
G/30-1a | SGBM16 | Jan 7 2016 8:00AM | Jan 7 2016 6:30PM | 52.266 | 49.575 |  | 29.468 | 2.691 | 20.107 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.8 | 18.0 | -100.0 | G35T2 | 1, 2 | 8, 10
G/30-1b | SGBM16 | Jan 7 2016 8:45AM | Jan 7 2016 5:00PM | 52.266 | 49.575 |  | 29.363 | 2.691 | 20.212 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.9 | 17.0 | -100.0 | G35T2 | 1, 2 | 9, 8
X9a/Ya-1 | SGBM03 | Jan 22 2016 10:00AM | Jan 22 2016 4:40PM | 55.789 | 55.075 |  | 27.984 | 0.714 | 27.091 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.2 | 26.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 8, 8
X10/Ya-1 | SGBM03 | Jan 16 2016 8:30AM | Jan 18 2016 7:05PM | 55.963 | 55.075 |  | 27.770 | 0.888 | 27.305 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 27.0 | -100.0 | G35T2 | 1, 2, 3 | 9, 10, 8
X8/Ya-1 | SGBM03 | Jan 20 2016 10:00AM | Jan 20 2016 5:20PM | 55.640 | 55.075 |  | 27.845 | 0.565 | 27.230 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.3 | 27.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 11, 5
X8a/Ya-1 | SGBM03 | Jan 27 2016 9:00AM | Jan 27 2016 5:10PM | 55.840 | 55.075 |  | 27.518 | 0.765 | 27.557 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.5 | 25.0 | 42.6 | G35T2 | 1, 2, 3 | 8, 9, 8
X9/Ya-1 | SGBM03 | Jan 19 2016 11:00AM | Jan 19 2016 8:55PM | 55.872 | 55.075 |  | 27.932 | 0.797 | 27.143 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12+6 | 17.3 | 27.0 | -100.0 | G35T2 | 4620, 4622, 4626 | 10, 8, 9
X0/Y0-1 | SGBM03 | Feb 20 2016 8:00AM | Feb 20 2016 1:30PM | 55.923 | 54.975 |  | 47.941 | 0.948 | 7.034 |  | 0.0 | 0.0 | 14T25+7T25 | T12-175 | 12 | 4.5 | 31.5 | -100.0 | G35T2 | PJ 5778, PJ 5777, PJ 5780, PJ5786 | 8, 8, 10.5, 5
X3a/Ya-1 | SGBM17 | Feb 22 2016 5:35PM | Feb 22 2016 9:40PM | 55.687 | 55.075 |  | 27.602 | 0.612 | 27.473 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.5 | 28.0 | -17.5 | G35T2 | PJ 5871, PJ 5876, PJ 5881 | 10, 10, 8
X3a/Yb-1 | SGBM19 | Feb 26 2016 8:12AM | Feb 26 2016 5:25PM | 55.616 | 55.075 |  | 27.696 | 0.541 | 27.379 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 24.0 | -17.4 | G35T2 | PJ 6051, PJ 6054, PJ 6059 | 10, 6, 8
X4/Ya-1 | SGBM03 | Feb 16 2016 8:25AM | Feb 16 2016 6:05PM | 55.669 | 55.075 |  | 27.452 | 0.594 | 27.623 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.6 | 24.0 | -100.0 | G35T2 | PJ 5595, PJ 5599, PJ 5603 | 8, 8, 8
X4a/Ya-1 | SGBM03 | Feb 13 2016 8:14AM | Feb 13 2016 1:20PM | 55.780 | 55.075 |  | 27.770 | 0.705 | 27.305 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 28.0 | -100.0 | G35T2 | PJ 5464, PJ5466, PJ 5469, PJ 5482 | 8, 8, 8, 4
X5/Ya-1 | SGBM03 | Feb 10 2016 11:31AM | Feb 10 2016 10:10PM | 56.154 | 55.075 |  | 27.944 | 1.079 | 27.131 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.3 | 24.0 | -100.0 | G35T2 | PJ 5370, PJ 5373, PJ 5377 | 8, 8, 8
X5a/Ya-1 | SGBM03 | Feb 12 2016 1:35PM | Feb 12 2016 10:30AM | 55.685 | 55.075 |  | 27.752 | 0.610 | 27.323 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 26.0 | -100.0 | G35T2 | PJ 5424, PJ 5425, PJ 5426 | 8, 8, 10
X5a/Yb-1 | SGBM21 | Feb 17 2016 8:35AM | Feb 17 2016 5:25PM | 55.652 | 55.075 |  | 27.946 | 0.577 | 27.129 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.3 | 26.0 | -100.0 | G35T2 | PJ 5643, PJ 5645, PJ5650, PJ 5655 | 8, 7, 7, 4
X6/Ya-1 | SGBM03 | Feb 4 2016 8:13AM | Feb 4 2016 3:50PM | 55.685 | 55.075 |  | 27.740 | 0.610 | 27.335 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 24.0 | -100.0 | G35T2 | PJ 5279, PJ5280, PJ 5283 | 8, 8, 8
X6/Yb-1 | SGBM03 | Feb 15 2016 10:40AM | Feb 15 2016 9:00PM | 55.614 | 55.075 |  | 27.538 | 0.539 | 27.537 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.5 | 24.0 | -17.5 | G35T2 | PJ5550, PJ 5551, PJ 5557 | 8, 8, 8
X6a/Ya-1 | SGBM03 | Jan 28 2016 12:00PM | Jan 28 2016 11:10PM | 55.801 | 55.075 |  | 27.681 | 0.726 | 27.394 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 10, 7
X6a/Yb-1 | SGBM03 | Feb 2 2016 10:00AM | Feb 2 2016 7:50PM | 55.628 | 55.075 |  | 27.549 | 0.553 | 27.526 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.5 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 8, 8, 6
X7/Ya-1 | SGBM03 | Jan 23 2016 10:00AM | Jan 23 2016 4:20PM | 55.640 | 55.075 |  | 27.445 | 0.565 | 27.630 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.6 | 24.0 | 36.5 | G35T2 | 1, 2, 3 | 8, 8, 8
X7/Yb-1 | SGBM03 | Feb 11 2016 8:12AM | Feb 11 2016 3:30PM | 55.540 | 55.075 |  | 27.640 | 0.465 | 27.435 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.5 | 24.0 | -100.0 | G35T2 | PJ5390, PJ5391, PJ5393 | 8, 8, 8
X7a/Ya-1 | SGBM03 | Jan 27 2016 11:20AM | Jan 28 2016 1:35PM | 55.808 | 55.075 |  | 27.744 | 0.733 | 27.331 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12+6 | 17.4 | 25.0 | -100.0 | G35T2 | 5007, 5008, 5009 | 9, 8, 8
X7a/Yb-1 | SGBM03 | Jan 30 2016 8:00AM | Jan 30 2016 5:05PM | 55.665 | 55.075 |  | 27.963 | 0.590 | 27.112 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12+6 | 17.3 | 24.0 | -100.0 | G35T2 | 5128, 5130, 5140 | 8, 8, 8
X8a/Yb-1 | SGBM03 | Feb 4 2016 7:05PM | Feb 5 2016 11:50AM | 55.528 | 55.075 |  | 27.820 | 0.453 | 27.255 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.3 | 25.0 | -100.0 | G35T2 | PJ5321, PJ 5323, PJ 5326 | 9, 8, 8
X9/Yb-1 | SGBM03 | Feb 2 2016 9:00AM | Feb 2 2016 3:20PM | 55.645 | 55.075 |  | 27.737 | 0.570 | 27.338 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
X9a/Yb-1 | SGBM03 | Jan 29 2016 11:00AM | Jan 29 2016 5:55PM | 55.669 | 55.075 |  | 27.783 | 0.594 | 27.292 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.4 | 25.0 | 44.0 | G35T2 | 1, 2, 3, 4 | 4, 8, 8, 5
X10/Yb-1 | SGBM03 | Jan 26 2016 8:00AM | Jan 26 2016 4:40PM | 55.637 | 55.075 |  | 27.470 | 0.562 | 27.605 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12+6 | 17.6 | 24.0 | 36.6 | G35T2 | 4890, 4893, 4895 | 8, 8, 8
X10a/Ya-1 | SGBM20 | Mar 24 2016 10:30AM | Mar 24 2016 7:40PM | 55.481 | 55.075 |  | 27.540 | 0.406 | 27.535 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.5 | 24.0 | -100.0 | G35T2 | pj7157, pj7162, pj7164 | 8, 8, 8
X10a/Yb-1 | SGBM20 | Mar 30 2016 8:30AM | Mar 30 2016 7:20PM | 55.670 | 55.075 |  | 27.000 | 0.595 | 28.075 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.9 | 16.0 | -100.0 | G35T2 | pj7454, pj7455 | 8, 8
X11/Ya-1 | SGBM20 | Mar 24 2016 11:15AM | Mar 26 2016 7:00PM | 55.555 | 55.075 |  | 27.405 | 0.480 | 27.670 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.6 | 28.0 | -100.0 | G35T2 | pj7285, pj7289, pj7291 | 7, 10, 11
X11/Yb-1 | SGBM20 | Mar 28 2016 1:00PM | Mar 29 2016 5:15PM | 55.665 | 55.075 |  | 27.363 | 0.590 | 27.712 |  | 0.0 | 0.0 | 14T32+7T25 | T16-90+T12-250 | 12 | 17.6 | 26.0 | -100.0 | G35T2 | pj7384, pj7387, pj7390 | 10, 8, 8
N/3-1 | SGBM03 | Jan 29 2016 12:00PM | Jan 30 2016 12:05AM | 55.722 | 55.075 |  | 24.794 | 0.647 | 30.281 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 29.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 8, 8, 6
N/6-1 | SGBM19 | Feb 2 2016 9:00AM | Feb 2 2016 2:40PM | 55.800 | 55.075 |  | 25.857 | 0.725 | 29.218 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
N/10-1 | SGBM23 | Mar 14 2016 2:30PM | Mar 15 2016 3:35PM | 55.982 | 51.075 |  | 22.374 | 4.907 | 28.701 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 21.0 | -100.0 | G35T2 | pj6739, pj6742 | 11, 10
N/13-1 | SGBM23 | Mar 15 2016 5:00PM | Mar 16 2016 5:25PM | 55.898 | 55.075 |  | 23.261 | 0.823 | 31.814 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.2 | 32.0 | -20.2 | G35T2 | pj6784, pj6788, pj6791, pj6794 | 8, 8, 8, 8
N/13a-1 | SGBM23 | Mar 17 2016 11:30AM | Mar 17 2016 8:00PM | 55.770 | 55.075 |  | -31.000 | 0.695 | 86.075 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 54.8 | 22.0 | -100.0 | G35T2 | pj6877, pj6881 | 11, 11
M/10-1 | SGBM20 | Mar 2 2016 8:15AM | Mar 2 2016 2:05PM | 55.984 | 51.075 |  | 21.726 | 4.909 | 29.349 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 22.0 | -100.0 | G35T2 | PJ 6242, PJ 6243, PJ 6245 | 8, 7, 7
M/12-1 | SGBM20 | Mar 5 2016 12:17PM | Mar 5 2016 4:35PM | 55.770 | 55.075 |  | 25.903 | 0.695 | 29.172 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 21.0 | -100.0 | G35T2 | C480017882, C480017884, C480017886 | 3, 10, 8
M/13a-1 | SGBM21 | Nov 30 2015 8:00AM | Nov 30 2015 9:41PM | 55.432 | 55.075 |  | 26.042 | 0.357 | 29.033 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
L/3-1 | SGBM19 | Jan 29 2016 12:10PM | Jan 30 2016 2:30PM | 55.635 | 53.875 |  | 23.392 | 1.760 | 30.483 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 26.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 8, 7, 3
L/3-2 | SGBM19 | Feb 3 2016 8:00AM | Feb 3 2016 6:40PM | 55.687 | 53.875 |  | 23.627 | 1.812 | 30.248 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 24.0 | -19.2 | G35T2 | PJ 5236, PJ5238, PJ 5242 | 8, 8, 8
L/4-1 | SGBM19 | Feb 2 2016 9:30AM | Feb 3 2016 2:10PM | 55.720 | 53.875 |  | 23.500 | 1.845 | 30.375 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 23.0 | -19.3 | G35T2 | PJ 5216, PJ 5217, PJ 5221 | 8, 8, 7
L/4-2 | SGBM19 | Feb 10 2016 10:00AM | Feb 10 2016 4:10PM | 55.672 | 53.875 |  | 23.581 | 1.797 | 30.294 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.3 | 23.0 | -100.0 | G35T2 | PJ5343, PJ5349, PJ5344 | 7, 8, 8
L/5-1 | SGBM19 | Feb 4 2016 8:00AM | Feb 4 2016 5:30PM | 55.690 | 53.875 |  | 23.693 | 1.815 | 30.182 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 26.0 | -100.0 | G35T2 | PJ5288, PJ5289, PJ5293, PJ5298 | 7, 8, 7, 4
L/5-2 | SGBM17 | Feb 22 2016 12:15PM | Feb 22 2016 3:50PM | 55.650 | 53.875 |  | 23.726 | 1.775 | 30.149 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 26.0 | -100.0 | G35T2 | PJ 5840, PJ 5843, PJ 5843 | 10, 8, 8
L/6-1 | SGBM19 | Feb 4 2016 2:00PM | Feb 5 2016 3:30PM | 55.827 | 53.875 |  | 24.619 | 1.952 | 29.256 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | PJ5329, PJ5330, PJ5331 | 8, 7, 7
L/6-2 | SGBM17 | Feb 11 2016 6:00PM | Feb 12 2016 3:15PM | 55.639 | 53.875 |  | 24.293 | 1.764 | 29.582 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.8 | 23.0 | -100.0 | G35T2 | PJ5430, PJ5431, PJ5432 | 8, 8, 7
L/7-1 | SGBM17 | Feb 18 2016 8:00AM | Feb 18 2016 1:30PM | 55.980 | 53.875 |  | 24.320 | 2.105 | 29.555 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.8 | 23.0 | -100.0 | G35T2 | PJ5680, PJ5681, PJ5684 | 8, 8, 7
L/7-2 | SGBM17 | Feb 11 2016 10:00AM | Feb 11 2016 9:15PM | 55.994 | 53.875 |  | 24.577 | 2.119 | 29.298 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -18.6 | G35T2 | 5415, 5417, 5420 | 7, 8, 8
L/8-1 | SGBM17 | Feb 16 2016 9:15AM | Feb 16 2016 7:00PM | 55.996 | 53.875 |  | 24.728 | 2.121 | 29.147 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 25.0 | -100.0 | G35T2 | PJ5600, PJ5602, PJ5606 | 8, 9, 8
L/8-2 | SGBM17 | Feb 18 2016 9:00AM | Feb 18 2016 7:00PM | 55.900 | 53.875 |  | 24.695 | 2.025 | 29.180 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ5704, PJ5712, PJ5717 | 8, 8, 7
L/9-1 | SGBM17 | Feb 19 2016 8:12AM | Feb 19 2016 4:25PM | 55.965 | 53.875 |  | 24.689 | 2.090 | 29.186 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 27.0 | -100.0 | G35T2 | PJ 5738, PJ 5739, PJ 5473, PJ 5748 | 8, 8, 7, 4
L/9-2 | SGBM17 | Feb 15 2016 8:00AM | Feb 15 2016 2:00PM | 55.965 | 53.875 |  | 24.701 | 2.090 | 29.174 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ5519, PJ5520, PJ5521 | 8, 8, 7
L/10-1 | SGBM19 | Feb 20 2016 8:25AM | Feb 20 2016 7:30PM | 55.960 | 49.875 |  | 20.521 | 6.085 | 29.354 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 24.0 | -100.0 | G35T2 | PJ 5813, PJ 5817, PJ 5820 | 8, 8, 8
L/10-2 | SGBM19 | Feb 23 2016 8:14AM | Feb 23 2016 5:10PM | 55.950 | 49.875 |  | 20.710 | 6.075 | 29.165 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | PJ 5899, PJ 5902, PJ 5904 | 7, 8, 7
L/11-1 | SGBM19 | Mar 1 2016 8:12AM | Mar 1 2016 6:40PM | 55.500 | 49.875 |  | 20.515 | 5.625 | 29.360 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 23.0 | -100.0 | G35T2 | C480017652, C48001753, C520125653 | 10, 10, 3
L/11-2 | SGBM20 | Mar 4 2016 1:15PM | Mar 4 2016 9:20PM | 55.750 | 49.875 |  | 20.226 | 5.875 | 29.649 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 22.0 | -100.0 | G35T2 | PJ 6345, PJ 6346, PJ 6348 | 8, 7, 7
L/12-1 | SGBM20 | Feb 25 2016 8:30AM | Feb 25 2016 2:50PM | 55.718 | 53.875 |  | 24.620 | 1.843 | 29.255 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ5989, PJ5990, PJ5993 | 8, 8, 7
L/12-2 | SGBM20 | Feb 27 2016 8:30AM | Feb 27 2016 1:35PM | 55.700 | 53.875 |  | 24.701 | 1.825 | 29.174 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ 6103, 6106, PJ 6110 | 8, 8, 7
L/59-1 | SGBM15 | Oct 26 2015 8:50PM | Oct 27 2015 1:43PM | 52.180 | 51.075 |  | 15.677 | 1.105 | 35.398 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 22.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 10, 10
L/28-1a | SGBM05 | Nov 11 2015 10:00AM | Nov 11 2015 7:15PM | 53.343 | 50.975 |  | 31.350 | 2.368 | 19.625 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.5 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 4
L/28-1b | SGBM05 | Nov 7 2015 8:00AM | Nov 7 2015 2:25PM | 53.447 | 50.975 |  | 31.226 | 2.472 | 19.749 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 12.6 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 5, 5
Z1/56a-1 | SGBM23 | Jan 6 2016 10:20AM | Jan 7 2016 1:35PM | 49.502 | 48.475 |  | 17.376 | 1.027 | 31.099 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 19.8 | 24.0 | 4.2 | G35T2 | 1, 2, 3 | 8, 8, 8
Z1/56b-1 | SGBM23 | Dec 13 2015 3:13PM | Jan 14 2016 5:00PM | 49.454 | 48.475 |  | 17.190 | 0.979 | 31.285 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 19.9 | 27.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 8, 8, 3
AA/56a-1 | SGBM05 | Jan 11 2016 9:08AM | Jan 11 2016 8:00PM | 49.379 | 48.475 |  | 17.349 | 0.904 | 31.126 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 19.8 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 9, 11, 5
AA/56b-1 | SGBM05 | Jan 8 2016 3:37PM | Jan 9 2016 3:10PM | 49.474 | 48.475 |  | 17.398 | 0.999 | 31.077 |  | 0.0 | 0.0 | 24T20+12T20 | T12-250 | 12 | 19.8 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
V/62-1 | SGBM31 | Jan 18 2016 1:58PM | Jan 19 2016 9:30PM | 50.781 | 47.075 |  | 19.660 | 3.706 | 27.415 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.4 | 21.0 | -100.0 | G35T2 | 4623, 4625, 4627 | 7, 7, 7
T2a/51-1 | SGBM20 | Jan 22 2016 2:36PM | Jan 23 2016 11:15AM | 51.776 | 51.325 |  | 24.994 | 0.451 | 26.331 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.8 | 21.0 | -100.0 | G35T2 | 4807, 4808, 4809 | 7, 7, 7
Ua/39-1 | SGBM23 | Jan 9 2016 10:36AM | Jan 9 2016 11:05PM | 52.261 | 50.125 |  | 23.111 | 2.136 | 27.014 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
Ua/39-2 | SGBM23 | Jan 14 2016 3:25PM | Jan 15 2016 11:00AM | 52.595 | 50.125 |  | 23.109 | 2.470 | 27.016 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.2 | 22.0 | 28.0 | G35T2 | 1, 2, 3 | 8, 7, 7
R/51-1a | SGBM23 | Jan 26 2016 9:35AM | Jan 27 2016 2:05PM | 51.931 | 49.775 |  | 15.797 | 2.156 | 33.978 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.6 | 27.0 | -21.6 | G35T2 | 1, 2, 3 | 10, 8, 9
R/51-1b | SGBM23 | Feb 2 2016 8:45AM | Feb 2 2016 10:45PM | 51.786 | 49.775 |  | 15.984 | 2.011 | 33.791 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.5 | 25.0 | -21.5 | G35T2 | 1, 2, 3 | 8, 9, 8
Y/25-3b | SGBM22 | Oct 27 2015 10:00AM | Oct 27 2015 5:19PM | 49.813 | 47.475 |  | 24.206 | 2.338 | 23.269 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.8 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
Y/25-3a | SGBM03 | Oct 28 2015 7:50PM | Oct 29 2015 1:12PM | 49.818 | 47.475 |  | 24.070 | 2.343 | 23.405 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 14.9 | 18.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 6
AA/58-1 | SGBM16 | Dec 18 2015 4:30PM | Dec 19 2015 2:42AM | 49.642 | 48.475 |  | 15.361 | 1.167 | 33.114 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.1 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 10, 8, 8, 4
AA/59-1 | SGBM22 | Dec 19 2015 9:20AM | Dec 22 2015 1:05AM | 49.829 | 48.475 |  | 14.312 | 1.354 | 34.163 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 31.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 10, 11
AA/60-1 | SGBM23 | Jan 6 2016 11:00AM | Jan 7 2016 3:47PM | 49.679 | 47.075 |  | 12.923 | 2.604 | 34.152 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 21.7 | 26.0 | -100.0 | G35T2 | 4090, 4092, 4094 | 10, 8, 8
AA/62-1 | SGBM17 | Jan 29 2016 3:27PM | Jan 30 2016 3:10PM | 49.276 | 47.075 |  | 14.371 | 2.201 | 32.704 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.8 | 26.0 | -100.0 | G35T2 | 5114, 5117, 5120, 5222 | 8, 8, 8, 2
T/51-1 | SGBM15 | Feb 25 2016 3:50PM | Feb 27 2016 1:40AM | 51.901 | 50.175 |  | 19.249 | 1.726 | 30.926 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.7 | 41.0 | -23.8 | G35T2 | 1, 2, 3, 4, 5 | 10, 8, 8, 8, 7
T/51-2 | SGBM23 | Feb 27 2016 10:55AM | Feb 29 2016 10:30PM | 52.052 | 50.175 |  | 18.756 | 1.877 | 31.419 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 20.0 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 9, 8
P/5-1 | SGBM20 | Mar 16 2016 6:30PM | Mar 17 2016 9:10PM | 55.730 | 55.075 |  | 24.833 | 0.655 | 30.242 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 22.0 | -100.0 | G35T2 | pj6885, pj6887 | 11, 11
P/6-1 | SGBM20 | Mar 14 2016 6:00PM | Mar 15 2016 6:55PM | 55.986 | 55.075 |  | 26.604 | 0.911 | 28.471 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | -100.0 | G35T2 | pj6751, pj6752, pj6754 | 7, 8, 8
P/13-1 | SGBM23 | Mar 14 2016 8:00AM | Mar 14 2016 7:30PM | 55.852 | 55.075 |  | 25.922 | 0.777 | 29.153 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G35T2 | pj6705, pj6706, pj6709 | 8, 8, 7
P/13a-1 | SGBM20 | Mar 18 2016 3:55PM | Mar 19 2016 1:45PM | 55.900 | 53.875 |  | 23.777 | 2.025 | 30.098 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.1 | 22.0 | -100.0 | G35T2 | pj6932, pj6933, pj6935 | 8, 7, 7
P/13a-2 | SGBM20 | Mar 21 2016 10:00AM | Mar 21 2016 9:05PM | 56.091 | 53.875 |  | 25.409 | 2.216 | 28.466 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.1 | 23.0 | 27.0 | G35T2 | pj7023, pj7026, pj7030 | 8, 8, 7
R/14-1 | SGBM31 | Mar 26 2016 3:40PM | Mar 28 2016 6:50PM | 55.774 | 54.475 |  | 25.226 | 1.299 | 29.249 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 24.0 | -100.0 | G35T2 | pj7350, pj7351, pj7352 | 8, 8, 8
Pa/7-1 | SGBM23 | Mar 19 2016 9:10AM | Mar 19 2016 6:00PM | 55.286 | 55.075 |  | 26.019 | 0.211 | 29.056 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -18.5 | G35T2 | pj6948, pj6950, pj6952 | 8, 7, 7
Pa/8-1 | SGBM20 | Mar 15 2016 4:45PM | Mar 16 2016 10:35PM | 55.779 | 55.075 |  | 25.553 | 0.704 | 29.522 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.8 | 22.0 | -100.0 | G35T2 | pj6808, pj6810, pj6811 | 8, 7, 7
N/5-1 | SGBM20 | Mar 29 2016 11:20AM | Mar 29 2016 10:00PM | 55.755 | 55.075 |  | 24.571 | 0.680 | 30.504 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.4 | 23.0 | -100.0 | G35T2 | pj7416, pj7422, pj7423 | 8, 7, 8
N/7-1 | SGBM19 | Mar 17 2016 3:00PM | Mar 18 2016 6:25PM | 55.975 | 55.075 |  | 25.625 | 0.900 | 29.450 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 22.0 | -100.0 | G35T2 | pj6913, pj6915, pj6918 | 8, 8, 6
M/9-1 | SGBM23 | Mar 3 2016 8:12AM | Mar 3 2016 2:45PM | 55.720 | 55.075 |  | 25.796 | 0.645 | 29.279 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 24.0 | -18.6 | G35T2 | PJ 6289, PJ 6291, PJ 6293 | 8, 8, 8
Ka/16-1 | SGBM23 | Mar 31 2016 2:00PM | Apr 1 2016 7:05PM | 55.690 | 49.525 |  | 20.515 | 6.165 | 29.010 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 21.0 | -100.0 | G35T2 | pj7520, pj7521 | 11, 10
Ka/16-2 | SGBM20 | Apr 4 2016 8:30AM | Apr 4 2016 2:55PM | 55.737 | 49.525 |  | 20.074 | 6.212 | 29.451 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 22.0 | 28.1 | G35T2 | pj7567, pj7568, pj7569 | 8, 7, 7
K/7-1 | SGBM19 | Feb 27 2016 8:00AM | Feb 27 2016 2:30PM | 55.930 | 54.075 |  | 24.872 | 1.855 | 29.203 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ6109, PJ6113, PJ6118 | 8, 8, 7
K/7-2 | SGBM19 | Mar 1 2016 8:30AM | Mar 1 2016 11:30AM | 55.915 | 54.075 |  | 23.913 | 1.840 | 30.162 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 25.0 | 30.3 | G35T2 | PJ 6200, PJ 6203, PJ6204 | 9, 8, 8
K/7-3 | SGBM19 | Mar 4 2016 1:12PM | Mar 4 2016 7:20PM | 55.940 | 54.075 |  | 24.735 | 1.865 | 29.340 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 23.0 | -100.0 | G35T2 | PJ 6340, PJ 6341, PJ 6343 | 8, 8, 7
K/10-1 | SGBM20 | Mar 19 2016 1:15PM | Mar 31 2016 1:50PM | 55.900 | 50.075 |  | 20.963 | 5.825 | 29.112 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 26.0 | -100.0 | G35T2 | pj7471, pj7473, pj7475 | 10, 8, 8
K/10-2 | SGBM20 | Apr 1 2016 4:30PM | Apr 1 2016 8:45PM | 55.830 | 50.075 |  | 20.910 | 5.755 | 29.165 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 26.0 | -100.0 | G35T2 | pj7523, pj7524, pj7528 | 9, 8, 9
K/10-3 | SGBM20 | Apr 2 2016 9:00AM | Apr 2 2016 6:20PM | 55.892 | 50.075 |  | 47.730 | 5.817 | 2.345 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 1.5 | 23.0 | -100.0 | G35T2 | pj7555, pj7557, pj7558 | 7, 8, 8
K/11-1 | SGBM20 | Mar 2 2016 11:17AM | Mar 2 2016 9:30PM | 55.643 | 50.075 |  | 20.785 | 5.568 | 29.290 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -18.6 | G35T2 | PJ 6268, PJ 6269, PJ 6272 | 8, 7, 7
K/11-3 | SGBM23 | Mar 11 2016 10:00AM | Mar 12 2016 4:15PM | 55.880 | 50.075 |  | 21.800 | 5.805 | 28.275 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 22.0 | -100.0 | G35T2 | pj6643, pj6644, pj6649 | 8, 7, 7
K/12-1 | SGBM20 | Feb 29 2016 11:15AM | Feb 29 2016 5:30PM | 55.700 | 54.075 |  | 24.810 | 1.625 | 29.265 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ 6170, PJ 6172, PJ 6173 | 8, 8, 7
K/12-2 | SGBM23 | Mar 11 2016 5:00PM | Mar 12 2016 9:50PM | 55.605 | 54.075 |  | 25.967 | 1.530 | 28.108 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 23.0 | -100.0 | G35T2 | pj6680, pj6683, pj6685 | 8, 8, 7
J/7-1 | SGBM19 | Mar 5 2016 8:10AM | Mar 5 2016 2:30PM | 55.950 | 54.275 |  | 24.914 | 1.675 | 29.361 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 25.0 | -100.0 | G35T2 | C480017873, C480017874, C480017875 | 10, 10, 5
J/7-2 | SGBM19 | Mar 10 2016 1:00PM | Mar 10 2016 8:20PM | 55.922 | 54.275 |  | 24.999 | 1.647 | 29.276 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | PJ 8120, PJ 8122, PJ 8126 | 8, 7, 7
J/7-3 | SGBM17 | Mar 11 2016 1:00PM | Mar 12 2016 7:05PM | 55.895 | 54.275 |  | 26.005 | 1.620 | 28.270 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 22.0 | -100.0 | G35T2 | pj6661, pj6664, pj6667 | 8, 7, 7
J/7-4 | SGBM19 | Mar 14 2016 9:00AM | Mar 14 2016 5:30PM | 55.920 | 54.275 |  | 25.578 | 1.645 | 28.697 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 22.0 | 20.5 | G35T2 | pj6699, pj6700, pj6701 | 8, 7, 7
J/7-5 |  |  |  | 0.000 | 54.275 |  | 0.000 | 0.000 | 54.275 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 34.5 | 0.0 | 0.0 | G35T2
J/7-6 | SGBM17 | Mar 12 2016 9:30AM | Mar 12 2016 8:00PM | 55.931 | 54.275 |  | 26.201 | 1.656 | 28.074 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 24.0 | -100.0 | G35T2 | pj6668, pj6670, pj6676 | 8, 8, 8
J/7-7 | SGBM19 | Mar 10 2016 1:31PM | Mar 10 2016 6:40PM | 55.930 | 54.275 |  | 24.999 | 1.655 | 29.276 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ 7789, PJ 8900, PJ8990 | 8, 8, 7
J/7-8 | SGBM19 | Mar 8 2016 1:00PM | Mar 8 2016 6:18PM | 55.965 | 54.275 |  | 47.785 | 1.690 | 6.490 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 4.1 | 22.0 | -100.0 | G35T2 | pj 5579, pj 5603 | 11, 11
J/9-1 | SGBM23 | Mar 3 2016 2:00PM | Mar 3 2016 7:25PM | 55.951 | 51.025 |  | 21.794 | 4.926 | 29.231 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 26.0 | -100.0 | G35T2 | PJ6311, PJ 6313, PJ 6316, PJ 6318 | 8, 7, 7, 4
J/9-2 | SGBM19 | Feb 29 2016 11:10AM | Feb 29 2016 8:05PM | 55.950 | 51.025 |  | 21.750 | 4.925 | 29.275 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | PJ 6180, PJ 6185, PJ 6189 | 8, 7, 7
J/9-3 | SGBM17 | Feb 26 2016 4:00PM | Feb 27 2016 10:20AM | 55.940 | 51.025 |  | 21.664 | 4.915 | 29.361 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 22.0 | -100.0 | G35T2 | PJ6105, PJ6099, PJ6100 | 8, 7, 7
J/9-4 | SGBM19 | Mar 4 2016 3:15PM | Mar 4 2016 9:55PM | 55.900 | 51.025 |  | 21.629 | 4.875 | 29.396 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 23.0 | -100.0 | G35T2 | PJ 6347, PJ 6349, PJ 6350 | 8, 8, 7
J/9-5 | SGBM19 | Feb 29 2016 3:10PM | Feb 29 2016 11:20PM | 55.910 | 51.025 |  | 21.819 | 4.885 | 29.206 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | PJ 6196, PJ 6197, PJ 6198 | 8, 8, 7
J/9-6 | SGBM19 | Mar 15 2016 10:00AM | Mar 15 2016 11:10PM | 55.920 | 51.025 |  | 23.062 | 4.895 | 27.963 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.8 | 22.0 | -100.0 | G35T2 | pj6768, pj6769, pj6770 | 8, 7, 7
J/9-7 | SGBM19 | Mar 14 2016 8:30AM | Mar 14 2016 3:10PM | 55.805 | 51.025 |  | 22.783 | 4.780 | 28.242 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 22.0 | -100.0 | G35T2 | pj6692, pj6693, pj6695 | 8, 7, 7
J/9-8 | SGBM19 | Mar 2 2016 1:25PM | Mar 2 2016 6:15PM | 55.920 | 51.025 |  | 21.814 | 4.895 | 29.211 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | PJ6254, PJ 6255, PJ 6256 | 8, 7, 7
J/9-9 |  |  |  | 0.000 | 51.025 |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 32.5 | 0.0 | 0.0 | G35T2
J/9-10 | SGBM19 | Mar 1 2016 2:10PM | Mar 2 2016 10:50AM | 55.930 | 51.025 |  | 21.965 | 4.905 | 29.060 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G35T2 | PJ 6239, PJ 6240, PJ 6241 | 8, 8, 7
J/9-11 | SGBM19 | Feb 27 2016 10:00AM | Feb 27 2016 6:20PM | 55.940 | 51.025 |  | 21.740 | 4.915 | 29.285 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | PJ6131, PJ6133, PJ6136 | 8, 7, 7
J/9-12 |  |  |  | 0.000 | 51.025 |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 32.5 | 0.0 | 0.0 | G35T2
J/9-13 | SGBM19 | Mar 12 2016 9:30AM | Mar 12 2016 9:30PM | 55.888 | 51.025 |  | 22.665 | 4.863 | 28.360 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 22.0 | 21.9 | G35T2 | pj6678, pj6682, pj6686 | 8, 7, 7
J/9-14 | SGBM22 | Mar 15 2016 9:30AM | Mar 15 2016 9:30PM | 55.900 | 51.025 |  | 22.843 | 4.875 | 28.182 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 26.0 | 45.0 | G35T2 | pj6762, pj6763, pj6765, pj6767 | 8, 7, 7, 4
J/9-15 |  |  |  | 0.000 | 51.025 |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 32.5 | 0.0 | 0.0 | G35T2
J/9-16 |  |  |  | 0.000 | 51.025 |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 32.5 | 0.0 | 0.0 | G35T2
J/9-17 | SGBM19 | Mar 15 2016 9:30AM | Mar 16 2016 8:30PM | 55.920 | 51.025 |  | 21.785 | 4.895 | 29.240 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | pj6802, pj6806, pj6804 | 8, 7, 8
J/9-18 |  |  |  | 0.000 | 51.025 |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 32.5 | 0.0 | 0.0 | G35T2
J/9-19 | SGBM19 | Mar 14 2016 9:00AM | Mar 14 2016 10:00PM | 55.936 | 51.025 |  | 22.486 | 4.911 | 28.539 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.2 | 22.0 | -100.0 | G35T2 | pj6718, pj6719, pj6720 | 8, 7, 7
J/13-1 | SGBM20 | Mar 23 2016 11:45AM | Mar 23 2016 11:10PM | 55.720 | 54.675 |  | 25.451 | 1.045 | 29.224 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | 23.7 | G35T2 | pj7126, pj7128, pj7131 | 8, 8, 7
J/13-2 | SGBM23 | Mar 24 2016 5:25PM | Mar 25 2016 8:15PM | 55.660 | 54.675 |  | 24.951 | 0.985 | 29.724 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 23.0 | -18.9 | G35T2 | pj7211, pj7213, pj7217 | 8, 8, 7
J/13-3 | SGBM31 | Mar 26 2016 5:10PM | Mar 28 2016 8:00PM | 55780.000 | 54.675 |  | 25.570 | 55725.300 | 29.105 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G35T2 | pj7354, pj7355, pj7360 | 8, 7, 7
J/13-4 | SGBM19 | Mar 30 2016 10:40AM | Mar 31 2016 2:10PM | 55.730 | 54.675 |  | 25.130 | 1.055 | 29.545 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.8 | 23.0 | -100.0 | G35T2 | pj7472, pj7474, pj7476 | 8, 8, 7
J/13-5 | SGBM23 | Mar 24 2016 4:30PM | Mar 25 2016 10:20PM | 55.650 | 54.675 |  | -31.200 | 0.975 | 85.875 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 54.6 | 23.0 | -100.0 | G35T2 | pj7225, pj7227, pj7230 | 8, 8, 7
J/13-6 | SGBM20 | Mar 23 2016 10:50AM | Mar 24 2016 1:00AM | 55.746 | 54.675 |  | 25.375 | -54.675 | 29.300 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | pj7133, pj7134, pj7135 | 8, 8, 7
J/13-7 | SGBM19 | Mar 30 2016 11:20AM | Mar 30 2016 9:30PM | 55.620 | 54.675 |  | 25.630 | 0.945 | 29.045 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G35T2 | pj7465, pj7466, pj7467 | 8, 8, 7
J/13-8 | SGBM23 | Mar 26 2016 6:00PM | Mar 29 2016 4:50PM | 55.456 | 54.675 |  | 24.997 | 0.781 | 29.678 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 23.0 | -100.0 | G35T2 | pj7381, pj7382, pj7385 | 8, 8, 7
J/13-9 | SGBM31 | Apr 2 2016 10:00AM | Apr 2 2016 4:10PM | 55.630 | 54.675 |  | 25.474 | 0.955 | 29.201 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 22.0 | -100.0 | G35T2 | pj7545, pj7547, pj7550 | 8, 7, 7
J/13-10 | SGBM19 | Apr 1 2016 8:00AM | Apr 1 2016 4:00PM | 55.720 | 54.675 |  | 24.558 | 1.045 | 30.117 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 22.0 | -19.2 | G35T2 | pj7504, pj7505, pj7507 | 8, 7, 7
G/4-1 | SGBM17 | Mar 15 2016 8:00AM | Mar 15 2016 2:10PM | 55.356 | 53.275 |  | 47.120 | 2.081 | 6.155 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 3.9 | 24.0 | -100.0 | G35T2 | pj6729, pj6731, pj6735 | 8, 8, 8
G/5-1 | SGBM17 | Mar 14 2016 9:30AM | Mar 14 2016 11:00PM | 55.400 | 53.275 |  | 24.071 | 2.125 | 29.204 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | pj6721, pj6722, pj6723 | 8, 8, 7
G/5-2 | SGBM17 | Mar 11 2016 3:00PM | Mar 12 2016 2:00PM | 55.310 | 53.275 |  | 23.966 | 2.035 | 29.309 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 23.0 | 23.3 | G35T2 | pj6636, pj6637, pj6639 | 8, 8, 7
G/6-1 | SGBM17 | Mar 14 2016 11:00AM | Mar 14 2016 8:35PM | 55.450 | 53.275 |  | 24.539 | 2.175 | 28.736 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.3 | 23.0 | -100.0 | G35T2 | pj6712, pj6714, pj6715 | 8, 8, 7
G/6-2 | SGBM22 | Mar 15 2016 9:00AM | Mar 15 2016 7:15PM | 55.307 | 53.275 |  | 24.977 | 2.032 | 28.298 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 24.0 | -100.0 | G35T2 | pj6753, pj6755, pj6758 | 8, 7, 9
G/8-1 | SGBM19 | Mar 17 2016 11:20AM | Mar 17 2016 5:35PM | 55.810 | 53.275 |  | 24.210 | 2.535 | 29.065 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G35T2 | c480018582, c480018585, c480018588 | 3, 10, 10
G/8-2 | SGBM19 | Mar 16 2016 9:00AM | Mar 16 2016 10:30PM | 55.895 | 53.275 |  | 24.188 | 2.620 | 29.087 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G35T2 | pj6807, pj6800, pj6812 | 8, 7, 7
G/9-1 | SGBM31 | Mar 19 2016 2:15PM | Mar 22 2016 2:40AM | 55.900 | 53.275 |  | 24.192 | 2.625 | 29.083 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 22.0 | -100.0 | G35T2 | pj7049, pj7050, pj7051 | 8, 7, 7
G/9-2 | SGBM19 | Mar 22 2016 4:00PM | Mar 23 2016 4:30AM | 55.918 | 53.275 |  | 23.160 | 2.643 | 30.115 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.2 | 24.0 | -100.0 | G35T2 | pj7095, pj7096, pj7097 | 8, 8, 8
G/11-1 | SGBM20 | Mar 22 2016 4:40PM | Mar 23 2016 3:35AM | 55.830 | 49.875 |  | 20.761 | 5.955 | 29.114 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G35T2 | Pending, pj7093, pj7094 | 8, 8, 7
G/11-2 | SGBM23 | Mar 19 2016 1:00PM | Mar 21 2016 10:30PM | 55.845 | 49.875 |  | 20.536 | 5.970 | 29.339 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.7 | 21.0 | -100.0 | G35T2 | pj7032, pj7037 | 10, 11
G/12-1 | SGBM23 | Mar 22 2016 8:50AM | Mar 23 2016 2:30AM | 55.435 | 49.875 |  | 20.682 | 5.560 | 29.193 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 25.0 | -100.0 | G35T2 | pj7088, pj7089, pj7090 | 8, 8, 9
G/12-2 | SGBM20 | Mar 23 2016 5:00PM | Mar 24 2016 11:10PM | 55.481 | 49.875 |  | 20.734 | 5.606 | 29.141 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.5 | 23.0 | -100.0 | G35T2 | pj7175, pj7176, pj7177 | 8, 8, 7
G/16-1 | SGBM23 | Mar 23 2016 5:40PM | Mar 25 2016 1:00AM | 55.490 | 51.075 |  | 25.490 | 4.415 | 25.585 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.3 | 25.0 | -100.0 | G35T2 | pj7178, pj7179, pj7180, pj7181 | 8, 8, 7, 2
Tc/41-1 | SGBM15 | Mar 7 2016 10:30AM | Mar 7 2016 8:15PM | 52.089 | 50.575 |  | 22.333 | 1.514 | 28.242 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.0 | 24.0 | -100.0 | G35T2 | pj6405, pj6408, Pending | 8, 8, 8
Tc/42-1 | SGBM15 | Mar 8 2016 10:30AM | Mar 8 2016 10:46PM | 52.092 | 50.575 |  | 22.440 | 1.517 | 28.135 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 8
Tc/43-1 | SGBM15 | Mar 5 2016 9:50AM | Mar 5 2016 9:30PM | 52.020 | 50.575 |  | 22.758 | 1.445 | 27.817 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.7 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 8, 7
Tc/44-1 | SGBM31 | Mar 9 2016 9:30AM | Mar 10 2016 10:55PM | 51.966 | 50.575 |  | 23.058 | 1.391 | 27.517 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.5 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 8, 7
N/Ya-1 | SGBM20 | Mar 25 2016 11:00AM | Mar 26 2016 12:00AM | 55.555 | 55.075 |  | 28.860 | 0.480 | 26.215 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 16.7 | 25.0 | -100.0 | G35T2 | pj7236, pj7240, pj7245 | 10, 8, 7
L/17-2 | SGBM23 | Mar 29 2016 8:30AM | Mar 31 2016 8:00PM | 55.680 | 49.525 |  | 18.800 | 6.155 | 30.725 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 19.5 | 22.0 | -100.0 | G35T2 | pj7491, pj7492, pj7493 | 8, 7, 7
K/17-2 |  |  |  | 0.000 | 49.525 |  | 0.000 | 0.000 | 49.525 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 31.5 | 0.0 | 0.0 | G35T2
K/16-2 |  |  |  | 0.000 | 49.525 |  | 0.000 | 0.000 | 49.525 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 31.5 | 0.0 | 0.0 | G35T2
L/17-1 | SGBM23 | Apr 2 2016 8:00AM | Apr 2 2016 2:00PM | 55.630 | 49.525 |  | 19.804 | 6.105 | 29.721 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 22.0 | -100.0 | G35T2 | pj7534, pj7536, pj7538 | 8, 7, 7
K/17-1 | SGBM31 | Apr 1 2016 9:00AM | Apr 1 2016 9:25PM | 55.665 | 49.525 |  | 20.260 | 6.140 | 29.265 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.6 | 21.0 | -100.0 | G35T2 | pj7525, pj7527 | 10, 11
K/16-1 | SGBM19 | Mar 31 2016 1:00PM | Apr 1 2016 10:45PM | 55.773 | 49.525 |  | 19.866 | 6.248 | 29.659 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 18.9 | 26.0 | -100.0 | G35T2 | pj7529, pj7530, pj7532 | 10, 8, 8
Na/Yb-1 |  |  |  | 0.000 | 55.075 |  | 0.000 | 0.000 | 55.075 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 35.0 | 0.0 | 0.0 | G35T2
N/Yb-1 | SGBM20 | Mar 26 2016 9:00AM | Mar 28 2016 8:35PM | 55.545 | 55.075 |  | 26.970 | 0.470 | 28.105 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 | 12 | 17.9 | 26.0 | -100.0 | G35T2 | pj7357, pj7358, pj7361 | 10, 8, 8
L/16-1 |  |  |  | 0.000 | 50.725 |  | 0.000 | 0.000 | 50.725 |  | 0.0 | 0.0 | 9T20+8T20 | T12-250 |  | 32.3 | 0.0 | 0.0 | G35T2

## 1050
Summary List for 1891651800-Parcel F
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
E/56-1 | SGBM23 | Sep 28 2015 8:00PM | Sep 29 2015 11:53AM | 51.955 | 49.775 |  | 6.702 | 2.180 | 43.073 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 43.0 | 15.3 | G45T2 | 1, 2, 3, 4, 5 | 5, 9, 9, 9, 11
E/56-2 | SGBM23 | Sep 10 2015 1:20PM | Sep 14 2015 11:53AM | 52.010 | 49.775 | 9, 38 | 6.701 | 2.235 | 43.074 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 11, 9, 8, 11
E/56-3 | SGBM17 | Oct 23 2015 10:00AM | Oct 24 2015 5:28PM | 51.927 | 49.775 | 8, 26 | 7.615 | 2.152 | 42.160 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 46.0 | -36.5 | G45T2 | 1, 2, 3, 4, 5 | 2, 11, 11, 11, 11
E/57-1 | SGBM23 | Aug 14 2015 10:10AM | Aug 17 2015 11:06AM | 51.966 | 49.775 | 6, 43 | 6.761 | 2.191 | 43.014 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.3 | 46.0 | 8.7 | G35T2 | 1, 2, 3, 4, 5, 6 | 6.5, 6.5, 10, 10, 6.5, 6.5
E/57-2 | SGBM23 | Aug 24 2015 2:30PM | Aug 25 2015 10:23PM | 51.978 | 49.775 | 9, 23 | 6.773 | 2.203 | 43.002 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.2 | 50.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 8, 11, 11, 10, 10
E/57-3 | SGBM17 | Sep 10 2015 11:20AM | Sep 11 2015 6:40PM | 51.996 | 49.775 | 6, 34 | 6.677 | 2.221 | 43.098 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.3 | 44.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 11, 11, 11, 11
E/58-1 | SGBM23 | Aug 11 2015 8:15AM | Aug 11 2015 9:07PM | 51.941 | 49.775 | 8 | 6.754 | 2.166 | 43.021 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.3 | 46.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 12, 3, 11, 11, 9
E/58-2 | SGBM17 | Aug 20 2015 2:00PM | Aug 22 2015 11:30AM | 51.491 | 49.775 | 6, 15, 44 | 0.000 | 1.716 | 49.775 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 43.1 | 44.0 | 2.1 | G35T2 | 1116, 1117, 0039, 7426 | 11, 11, 10, 12
E/58-3 | SGBM17 | Aug 14 2015 8:00AM | Aug 15 2015 12:23PM | 51.900 | 49.775 | 7, 40 | 6.766 | 2.125 | 43.009 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.2 | 44.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 11, 11, 11, 11
E/59-1 | SGBM17 | Aug 12 2015 12:00PM | Aug 13 2015 8:45PM | 51.919 | 49.775 | 7, 35 | 6.625 | 2.144 | 43.150 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.4 | 51.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 9, 11, 11, 10, 10
E/59-2 | SGBM17 | Aug 22 2015 3:00PM | Aug 25 2015 10:45PM | 51.894 | 49.775 | 6, 18 | 6.724 | 2.119 | 43.051 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.3 | 44.0 | -100.0 | G35T2 | 7605, 7606, 7610, 7617 | 11, 11, 11, 11
E/59-3 | SGBM23 | Aug 17 2015 4:00PM | Aug 19 2015 11:30AM | 51.933 | 49.775 | 7, 44 | 6.654 | 2.158 | 43.121 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.3 | 47.0 | 9.7 | G35T2 | 1, 2, 3, 4, 5 | 11, 9, 7, 10, 10
F/60-1 | SGBM23 | Aug 8 2015 2:30PM | Aug 10 2015 3:18PM | 51.923 | 49.675 | 6, 27 | 5.604 | 2.248 | 44.071 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 2+12+12+12+12 | 38.2 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 12, 12, 12, 12
F/60-2 | SGBM17 | Sep 10 2015 10:50AM | Sep 14 2015 3:35PM | 51.985 | 49.675 | 6, 20, 42 | 5.625 | 2.310 | 44.050 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.1 | 51.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 12, 11, 9, 9
F/60-3 | SGBM17 | Aug 24 2015 4:10PM | Sep 9 2015 2:40PM | 51.973 | 49.675 | 5, 29 | 5.673 | 2.298 | 44.002 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.1 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 12, 12, 11, 8
G/59-1 | SGBM23 | Jul 31 2015 12:01PM | Aug 1 2015 3:59PM | 51.995 | 49.875 | 8 | 4.299 | 2.120 | 45.576 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.5 | 47.0 | -39.5 | G35T2 | c480006184, C480006186, C480006189, C480006194 | 12, 12, 11.5, 11.5
G/59-2 | SGBM23 | Aug 3 2015 10:20AM | Aug 3 2015 9:15PM | 52.015 | 49.875 | 8 | 4.807 | 2.140 | 45.068 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 47.0 | 20.4 | G35T2 | c480006345, c480006347, c480006353, c480006354, c480006355 | 11.5, 11.5, 11, 10, 3
G/59-3 | SGBM23 | Aug 6 2015 8:10PM | Aug 7 2015 11:35PM | 52.000 | 49.875 | 8 | 4.800 | 2.125 | 45.075 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 46.0 | 7.0 | G35T2 | C410000014, C410000015, C410000016, C410000017, C410000018 | 9, 10, 9, 9, 9
G/59-4 | SGBM23 | Aug 18 2015 8:10AM | Aug 21 2015 10:40AM | 51.976 | 49.875 | 6, 46 | 4.824 | 2.101 | 45.051 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 43.0 | -39.0 | G35T2 | 1, 2, 3, 4 | 10, 11, 11, 11
G/59-5 | SGBM23 | Aug 25 2015 8:50AM | Sep 8 2015 7:30PM | 52.009 | 49.875 | 6, 30 | 4.797 | 2.134 | 45.078 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 51.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 6, 12, 12, 12, 9
G/59-6 | SGBM18 | Sep 12 2015 8:50AM | Sep 15 2015 10:30AM | 51.967 | 49.875 | 6, 47.6 | 4.801 | 2.092 | 45.074 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 45.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 8, 11, 9, 11, 6
G/61-1 | SGBM15 | Aug 1 2015 2:00PM | Aug 3 2015 12:12PM | 51.930 | 49.675 | 8, 20.5 | 4.630 | 2.255 | 45.045 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 44.9 | 15.1 | G35T2 | c480006297, c480006298, c480006302, c480006306 | 11.5, 11.4, 11, 11
G/61-2 | SGBM23 | Aug 5 2015 8:00AM | Aug 6 2015 7:44PM | 51.896 | 49.675 | 8 | 4.637 | 2.221 | 45.038 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 46.0 | 17.9 | G35T2 | c480006527, c480006529, c480006532, c520120881 | 11, 11.5, 11.5, 12
G/61-3 | SGBM17 | Aug 10 2015 8:05AM | Aug 11 2015 12:40PM | 51.888 | 49.675 | 7, 36 | 4.648 | 2.213 | 45.027 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 50.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 12, 12, 11, 11, 4
H/60-1 | SGBM23 | Jul 29 2015 3:10PM | Jul 30 2015 10:20PM | 51.972 | 49.775 | 9 | 5.742 | 2.197 | 44.033 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.1 | 45.0 | 18.0 | G45T2 | c480006090, c480006092, c480006094, c480006096 | 11.5, 11.5, 11, 11
H/60-2 | SGBM23 | Aug 3 2015 5:40PM | Aug 4 2015 11:07PM | 52.028 | 49.775 | 8 | 5.573 | 2.253 | 44.202 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.3 | 56.0 | 46.3 | G45T2 | c480006418, c480006419, c480006420, c480006421, c480006422, c480006422 | 10, 10, 10, 8, 10, 8
H/60-3 | SGBM17 | Aug 6 2015 4:50PM | Aug 7 2015 7:25PM | 51.994 | 49.775 | 8, 33.5 | 5.723 | 2.219 | 44.052 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.1 | 47.0 | 23.2 | G45T2 | c480006607, c480006609, c480006615, c480006618, c480006624 | 11, 11, 11, 11, 3
H/61-1 | SGBM23 | Jul 31 2015 8:00AM | Jul 31 2015 7:52PM | 51.993 | 49.775 | 8 | 4.759 | 2.218 | 45.016 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 46.0 | 18.0 | G45T2 | c480006139, c480006140, c480006141, c480006144 | 11.5, 11.5, 11.5, 11.5
H/61-2 | SGBM23 | Aug 4 2015 11:10AM | Aug 5 2015 11:33AM | 52.010 | 49.775 | 8, 37.5 | 5.524 | 2.235 | 44.251 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 38.3 | 50.0 | 30.5 | G35T2 | c480006423, c480006424, c480006425, c480006426, c480006434 | 11.5, 11.5, 11, 11, 5
H/61-3 | SGBM17 | Aug 7 2015 10:00PM | Aug 8 2015 7:58PM | 51.904 | 49.775 | 6 | 4.197 | 2.129 | 45.578 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.5 | 51.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5, 6, 7 | 6.5, 6.5, 10, 8, 6.5, 6.5, 7
K/22-1 | SGBM20 | Aug 10 2015 6:40PM | Aug 11 2015 12:05PM | 53.445 | 51.075 | 9 | 28.745 | 2.370 | 22.330 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 22.0 | 13.8 | G35T2 | c480006857, c480006858 | 11, 11
K/22-2 | SGBM20 | Aug 16 2015 12:00PM | Aug 17 2015 12:37PM | 53.466 | 51.075 | 9 | 29.465 | 2.391 | 21.610 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.7 | 22.0 | 17.6 | G35T2 | pj25684704, pj25684706, pj25684705 | 5.5, 10, 6.5
K/23-1 | SGBM15 | Aug 13 2015 5:40PM | Aug 14 2015 9:35PM | 53.482 | 51.075 | 9 | 28.929 | 2.407 | 22.146 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 22.0 | 14.7 | G35T2 | c480007039, c480007307 | 11, 11
K/23-2 | SGBM20 | Aug 19 2015 4:30PM | Aug 20 2015 3:07PM | 53.481 | 51.075 | 9 | 28.801 | 2.406 | 22.274 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 22.0 | 14.0 | G35T2 | C480007348, C480007350 | 11, 11
K/24-1 | SGBM20 | Aug 22 2015 7:10PM | Aug 24 2015 2:42PM | 53.469 | 51.075 | 9 | 28.789 | 2.394 | 22.286 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 23.0 | -19.3 | G35T2 | 1, 2, 3 | 11, 10, 2
K/24-2 | SGBM20 | Aug 10 2015 6:00PM | Aug 11 2015 3:50PM | 53.418 | 51.075 |  | 28.798 | 2.343 | 22.277 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 22.0 | 14.0 | G35T2 | c480006843, c480006845 | 11, 11
K/25-1 | SGBM20 | Aug 17 2015 4:50PM | Aug 18 2015 5:58PM | 53.439 | 51.075 | 9 | 28.919 | 2.364 | 22.156 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 23.0 | 19.9 | G35T2 | 1, 2, 3 | 6, 10, 7
K/25-2 | SGBM20 | Aug 12 2015 1:35PM | Aug 13 2015 5:05PM | 53.463 | 51.075 | 9 | 28.858 | 2.388 | 22.217 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 22.0 | -100.0 | G35T2 | c480006978, c480006977, c480006987 | 10, 10, 2
K/56-1 | SGBM17 | Aug 15 2015 3:00PM | Aug 18 2015 11:05AM | 52.150 | 49.175 | 7, 38.1 | 11.945 | 2.975 | 37.230 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.2 | 41.5 | -100.0 | G45T2 | 1, 2, 3, 4 | 11.5, 7, 11.5, 11.5
K/56-2 | SGBM17 | Sep 9 2015 9:40AM | Sep 10 2015 5:40PM | 52.086 | 49.175 | 6, 28 | 12.171 | 2.911 | 37.004 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.0 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 4
K/56-3 | SGBM18 | Sep 14 2015 6:00PM | Sep 17 2015 11:14AM | 52.107 | 49.175 | 6, 36 | 12.133 | 2.932 | 37.042 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 39.0 | -32.1 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 6
K/57-1 | SGBM23 | Aug 21 2015 3:40PM | Aug 24 2015 7:07PM | 52.214 | 49.775 | 6, 28, 39.2 | 13.615 | 2.439 | 36.160 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12+12+12+7.4 | 31.3 | 41.0 | -100.0 | G45T2 | 1161, 1162, 1163, 1164 | 10, 11, 10, 10
K/57-2 | SGBM23 | Sep 11 2015 9:50AM | Sep 12 2015 4:05PM | 52.163 | 49.775 | 6, 34 | 13.753 | 2.388 | 36.022 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.2 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 9, 11, 2
K/57-3 | SGBM18 | Sep 21 2015 11:20AM | Sep 22 2015 12:51PM | 52.080 | 49.775 | 6, 33 | 13.753 | 2.305 | 36.022 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.2 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 5, 11, 10, 11
K/58-1 | SGBM23 | Aug 13 2015 11:20AM | Aug 14 2015 3:18PM | 52.215 | 49.775 | 8, 39.8 | 12.722 | 2.440 | 37.053 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 6, 11
K/58-2 | SGBM23 | Sep 9 2015 10:40AM | Sep 10 2015 11:45AM | 51.838 | 49.775 | 6, 35 | 12.758 | 2.063 | 37.017 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 3, 11, 11, 11, 7
K/58-3 | SGBM23 | Sep 14 2015 9:30AM | Sep 17 2015 6:17PM | 52.042 | 49.775 | 6, 30 | 12.697 | 2.267 | 37.078 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 8
K/59-1 | SGBM17 | Aug 18 2015 5:18PM | Aug 20 2015 4:00PM | 52.193 | 49.775 | 7 | 10.741 | 2.418 | 39.034 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.8 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
K/59-2 | SGBM18 | Sep 10 2015 2:10PM | Sep 12 2015 10:42AM | 51.713 | 49.775 | 6, 24, 40 | 10.722 | 1.938 | 39.053 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.8 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 11, 11
K/59-3 | SGBM23 | Sep 14 2015 8:40AM | Sep 15 2015 1:00PM | 51.820 | 49.775 | 6, 41.5 | 10.681 | 2.045 | 39.094 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.9 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 8, 10
L/26-1 | SGBM20 | Aug 12 2015 8:00AM | Aug 12 2015 5:44PM | 53.375 | 50.475 | 9 | 31.364 | 2.400 | 19.111 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 16.6 | 15.0 | -9.4 | G45T2 | 1, 2, 3 | 10, 2, 3
L/26-2 | SGBM15 | Aug 24 2015 8:00AM | Aug 24 2015 6:10PM | 53.450 | 50.475 | 9 | 31.180 | 2.475 | 19.295 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 16.7 | 17.0 | -100.0 | G45T2 | c520121157, c520121159 | 11, 6
L/27-1 | SGBM20 | Aug 16 2015 5:07PM | Aug 17 2015 5:05PM | 53.421 | 50.475 | 8, 17.9 | 31.388 | 2.446 | 19.087 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 16.5 | 18.0 | -100.0 | G45T2 | c520121054, c480007178 | 7, 11
L/27-2 | SGBM20 | Aug 19 2015 5:30PM | Aug 20 2015 4:51PM | 53.443 | 50.475 | 9 | 31.166 | 2.968 | 19.309 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 16.7 | 16.0 | -0.7 | G45T2 | C480007356, C480007357 | 10, 6
V/23-1 | SGBM16 | Aug 13 2015 6:00PM | Aug 15 2015 2:00PM | 49.725 | 47.375 | 9, 19.8 | 27.037 | 2.350 | 20.338 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 17.6 | 22.0 | -17.6 | G35T2 | 1, 2 | 11, 11
V/23-2 | SGBM18 | Aug 22 2015 5:30PM | Aug 24 2015 3:25PM | 49.745 | 47.375 |  | 26.156 | 2.370 | 21.219 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.4 | 21.0 | -100.0 | G35T2 | 1, 2 | 11, 10
V/24-1 | SGBM18 | Aug 13 2015 4:00PM | Aug 14 2015 6:30PM | 49.691 | 47.375 | 9, 12.4 | 27.869 | 2.316 | 19.506 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 16.9 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
V/24-2 | SGBM16 | Sep 16 2015 1:30PM | Sep 17 2015 3:37PM | 49.725 | 47.375 |  | 27.294 | 2.350 | 20.081 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 17.4 | 22.0 | -100.0 | G35T2 | 1, 2, 3 | 9, 11, 2
V/25-2 | SGBM16 | Sep 10 2015 4:00PM | Sep 11 2015 8:50PM | 49.909 | 47.075 | 9, 21 | 26.514 | 2.834 | 20.561 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 17.8 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 3, 11, 7
V/29-1 | SGBM20 | Aug 15 2015 10:30AM | Aug 17 2015 2:15PM | 49.775 | 47.075 |  | 24.950 | 2.700 | 22.125 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 22.0 | -19.2 | G35T2 | 1, 2 | 11, 11
V/29-2 | SGBM16 | Aug 19 2015 10:30AM | Aug 19 2015 5:25PM | 49.791 | 47.075 | 9 | 25.483 | 2.716 | 21.592 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.7 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 10, 7
V/30-1 | SGBM18 | Aug 17 2015 3:10PM | Aug 18 2015 4:30PM | 49.778 | 47.075 | 9, 17.9 | 25.634 | 2.703 | 21.441 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.6 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 7.5, 11.5, 4
V/30-2 | SGBM16 | Aug 20 2015 1:30PM | Sep 9 2015 1:16PM | 49.740 | 47.075 | 9, 16.8 | 25.708 | 2.665 | 21.367 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.5 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 12, 2
V/31-2 | SGBM16 | Aug 20 2015 3:00PM | Aug 21 2015 9:18PM | 49.751 | 47.075 |  | 24.713 | 2.676 | 22.362 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 9 | 19.4 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
W/24-1 | SGBM18 | Aug 12 2015 10:10AM | Aug 14 2015 6:30PM | 49.717 | 47.375 | 9, 20.1 | 26.893 | 2.342 | 20.482 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 17.7 | 22.0 | 24.0 | G35T2 | 1, 2 | 11, 11
W/24-2 | SGBM16 | Sep 5 2015 9:30AM | Sep 7 2015 4:40PM | 49.676 | 47.375 | 9 | 26.576 | 2.301 | 20.799 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.0 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 10, 5
W/25-1 | SGBM16 | Aug 12 2015 8:20AM | Aug 12 2015 3:45PM | 49.717 | 47.375 | 9, 20.3 | 26.779 | 2.342 | 20.596 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 17.8 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
W/25-2 | SGBM18 | Sep 9 2015 10:30AM | Sep 10 2015 3:40PM | 49.743 | 47.375 | 9, 16.4 | 26.847 | 2.368 | 20.528 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 17.8 | 22.0 | -100.0 | G35T2 | 1, 2, 3 | 6, 11, 5
W/26-1 | SGBM16 | Aug 11 2015 1:01PM | Aug 12 2015 2:10PM | 49.689 | 47.375 | 8 | 25.048 | 2.314 | 22.327 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 22.0 | -19.3 | G35T2 | 1, 2 | 11, 11
W/26-2 | SGBM16 | Aug 22 2015 8:00AM | Aug 22 2015 4:45PM | 49.643 | 47.375 |  | 25.125 | 2.268 | 22.250 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 22.0 | -100.0 | G35T2 | 1, 2, 3 | 4, 11, 7
W/28-1 | SGBM17 | Jul 30 2015 8:10AM | Jul 30 2015 11:15PM | 49.621 | 47.375 | 9 | 24.597 | 2.246 | 22.778 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.7 | 23.5 | -100.0 | G35T2 | 1, 2, 3, 4 | 6.5, 6.5, 7.5, 3
W/28-2 | SGBM20 | Aug 3 2015 1:44PM | Aug 3 2015 5:50PM | 49.715 | 47.375 | 9 | 25.771 | 2.340 | 21.604 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.7 | 23.0 | -18.7 | G35T2 | 1, 2 | 11.5, 11.5
W/29-1 | SGBM16 | Aug 1 2015 1:20PM | Aug 1 2015 7:20PM | 49.614 | 47.375 | 9 | 25.324 | 2.239 | 22.051 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.1 | 22.5 | -100.0 | G35T2 | 1, 2 | 11, 11.5
W/29-2 | SGBM20 | Aug 4 2015 8:30AM | Aug 4 2015 10:15PM | 49.622 | 47.375 | 9, 16.8 | 25.624 | 2.247 | 21.751 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.8 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 9.5, 11.5, 2
W/30-1 | SGBM17 | Jul 29 2015 5:00PM | Jul 30 2015 9:24PM | 49.621 | 47.375 | 8, 18.9 | 24.824 | 2.246 | 22.551 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.5 | 22.5 | 15.2 | G35T2 | pj25683684, pj25693686, pj25683687 | 6, 6.5, 10
W/30-2 | SGBM20 | Aug 3 2015 11:29AM | Aug 4 2015 12:28AM | 49.766 | 47.375 | 9 | 25.902 | 2.391 | 21.473 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.6 | 26.5 | -100.0 | G35T2 | 1, 2, 3 | 11.5, 11.5, 3.5
W/31-1 | SGBM17 | Jul 31 2015 8:30AM | Aug 1 2015 2:10PM | 49.482 | 47.375 | 9, 18.9 | 24.702 | -47.375 | 22.673 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.6 | 22.0 | -19.6 | G35T2 | 1, 2 | 11, 11
W/31-2 | SGBM16 | Aug 3 2015 8:00AM | Aug 3 2015 11:49PM | 49.742 | 47.375 | 9 | 26.210 | 2.367 | 21.165 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.3 | 26.5 | -18.3 | G35T2 | 1, 2, 3 | 10, 10, 6.5
W/32-1 | SGBM16 | Aug 10 2015 2:30PM | Aug 11 2015 3:35PM | 49.535 | 47.375 | 9, 12.5 | 24.859 | 2.160 | 22.516 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.5 | 22.0 | -19.5 | G35T2 | 1, 2 | 11, 11
W/32-2 | SGBM16 | Aug 12 2015 3:45PM | Aug 13 2015 3:30PM | 49.586 | 47.375 | 9, 14.9 | 25.534 | 2.211 | 21.841 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.9 | 24.0 | -18.9 | G35T2 | 1, 2, 3 | 11, 11, 2
W/35-1 | SGBM21 | Aug 3 2015 5:00PM | Aug 4 2015 1:15PM | 49.431 | 47.375 | 8 | 23.231 | 2.056 | 24.144 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.9 | 26.0 | -100.0 | G35T2 | c480006372, c480006373, c480006376 | 10, 10, 6
W/35-2 | SGBM03 | Aug 7 2015 1:00PM | Aug 7 2015 10:35PM | 49.446 | 47.375 |  | 23.160 | 2.071 | 24.215 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 21.0 | 27.0 | -100.0 | G35T2 | 1, 2, 3 | 8, 12, 7
W/36-1 | SGBM03 | Aug 5 2015 3:00PM | Aug 5 2015 8:16PM | 49.574 | 47.375 |  | 21.074 | 2.199 | 26.301 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 22.8 | 28.0 | 22.9 | G35T2 | 1, 2, 3 | 11, 11, 6
W/36-2 | SGBM03 | Aug 10 2015 1:50PM | Aug 10 2015 8:55PM | 49.577 | 47.375 |  | 21.077 | 2.202 | 26.298 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 22.8 | 30.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 11, 8
W/37-1 | SGBM03 | Aug 10 2015 8:50AM | Aug 10 2015 1:45PM | 43.458 | 47.375 |  | 19.958 | -3.917 | 27.417 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.7 | 31.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 10, 10
W/37-2 | SGBM03 | Aug 6 2015 12:00PM | Aug 6 2015 7:10PM | 49.550 | 47.375 |  | 19.950 | 2.175 | 27.425 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.8 | 28.0 | 17.9 | G35T2 | 1, 2, 3 | 11, 11, 6
W/38-1 | SGBM03 | Aug 4 2015 10:20AM | Aug 4 2015 8:45PM | 49.460 | 47.375 |  | 19.060 | 2.085 | 28.315 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.5 | 29.0 | -24.5 | G35T2 | 1, 2, 3 | 11, 11, 7
W/38-2 | SGBM03 | Aug 6 2015 6:30PM | Aug 7 2015 4:00PM | 49.508 | 47.375 |  | 19.014 | 2.133 | 28.361 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.6 | 32.0 | -24.6 | G35T2 | 1, 2, 3 | 11, 11, 10
X/28-1 | SGBM17 | Jul 30 2015 1:30PM | Jul 30 2015 6:40PM | 49.748 | 47.375 | 9 | 24.734 | 2.373 | 22.641 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.6 | 23.5 | -19.6 | G35T2 | 1, 2, 3, 4 | 2.5, 6.5, 6.5, 8
X/28-2 | SGBM17 | Aug 1 2015 1:00PM | Aug 1 2015 7:50PM | 49.791 | 47.375 | 9 | 25.083 | 2.416 | 22.292 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 23.5 | -100.0 | G35T2 | 1, 2 | 11.5, 12
X/29-1 | SGBM16 | Aug 6 2015 2:30PM | Aug 7 2015 2:20PM | 49.921 | 47.375 | 9, 15.8 | 24.779 | 2.546 | 22.596 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.6 | 25.0 | -19.6 | G35T2 | 1, 2, 3 | 9, 10, 6
X/29-2 | SGBM16 | Aug 5 2015 9:00AM | Aug 6 2015 12:24AM | 49.768 | 47.375 | 9 | 25.290 | 2.393 | 22.085 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.1 | 22.0 | -19.1 | G35T2 | 1, 2 | 11, 11
X/30-1 | SGBM17 | Jul 31 2015 2:00PM | Aug 1 2015 12:00AM | 49.746 | 47.375 | 9 | 25.020 | 2.371 | 22.355 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.4 | 25.0 | -100.0 | G35T2 | 1, 2, 3 | 9, 12, 4
X/30-2 | SGBM20 | Aug 4 2015 8:00AM | Aug 4 2015 5:20PM | 49.715 | 47.375 | 9 | 25.771 | 2.340 | 21.604 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.7 | 23.0 | -100.0 | G35T2 | 1, 2 | 11.5, 11.5
X/31-1 | SGBM16 | Aug 3 2015 10:10AM | Aug 3 2015 6:40PM | 49.876 | 47.475 | 9, 15.7 | 24.734 | 2.401 | 22.741 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.7 | 23.0 | -19.7 | G35T2 | 1, 2 | 11.5, 11.5
X/31-2 | SGBM20 | Aug 6 2015 3:30PM | Aug 7 2015 7:15PM | 49.814 | 47.475 | 9, 21.6 | 24.856 | 2.339 | 22.619 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.6 | 22.0 | -100.0 | G35T2 | 11, 2 | 11, 11
X/31-3 | SGBM16 | Aug 4 2015 4:20PM | Aug 5 2015 4:50PM | 49.761 | 47.475 | 9, 12.32 | 24.939 | 2.286 | 22.536 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.5 | 24.0 | -19.5 | G35T2 | 1, 2, 3 | 10, 10, 4
X/36-1 | SGBM21 | Aug 3 2015 8:15AM | Aug 3 2015 5:05PM | 49.552 | 47.475 | 8 | 21.152 | 2.077 | 26.323 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.8 | 28.0 | -100.0 | G45T2 | pj25683851, pj2568852, pj25683853, pj25683855 | 6.5, 6.5, 10, 5
X/36-2 | SGBM03 | Aug 10 2015 6:00PM | Aug 11 2015 2:00PM | 49.538 | 47.475 |  | 21.227 | 2.063 | 26.248 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.7 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 8
X/37-1 | SGBM19 | Aug 18 2015 5:15PM | Aug 20 2015 11:20AM | 49.535 | 47.475 | 8 | 20.327 | -47.475 | 27.148 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.5 | 30.0 | -100.0 | G35T2 | c480007331, c480007332, c480007333 | 11, 11, 8
X/37-2 | SGBM03 | Aug 11 2015 1:00PM | Aug 11 2015 9:00PM | 49.538 | 47.475 |  | 20.238 | 2.063 | 27.237 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.6 | 30.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 11, 8
X/37-3 | SGBM19 | Aug 14 2015 2:15PM | Aug 15 2015 11:25AM | 49.526 | 47.475 | 8, 26 | 20.326 | 2.051 | 27.149 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.5 | 29.0 | -100.0 | G35T2 | c480007080, c480007082, c480007085 | 11, 11, 7
X/39-1 | SGBM03 | Aug 17 2015 3:10PM | Aug 18 2015 1:40PM | 49.539 | 47.375 | 8, 17.5 | 17.982 | 2.164 | 29.393 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.5 | 33.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 6, 11.5, 11.5, 4
X/39-2 | SGBM03 | Aug 13 2015 9:15AM | Aug 13 2015 2:40PM | 49.542 | 47.375 |  | 18.042 | 2.167 | 29.333 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.4 | 33.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 11, 11
Y/28-1 | SGBM16 | Jul 29 2015 8:30AM | Jul 29 2015 8:30PM | 49.907 | 47.375 |  | 24.737 | 2.532 | 22.638 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.6 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 3, 10, 10
Y/28-2 | SGBM16 | Jul 31 2015 8:30AM | Jul 31 2015 10:10PM | 49.816 | 47.375 | 9, 12.3 | 25.184 | 2.441 | 22.191 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 25.0 | -19.2 | G35T2 | 1, 2, 3 | 11, 11, 3
Y/30-1 | SGBM20 | Aug 5 2015 7:30AM | Aug 5 2015 10:25PM | 49.821 | 47.375 | 9, 18.9 | 25.153 | 2.446 | 22.222 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 22.0 | -19.2 | G35T2 | 1, 2 | 11, 11
Y/30-2 | SGBM16 | Aug 6 2015 4:00PM | Aug 7 2015 3:00PM | 49.901 | 47.375 | 9, 25.525 | 24.951 | 2.526 | 22.424 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.4 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 4, 10, 10
Y/31-1 | SGBM20 | Aug 6 2015 6:00PM | Aug 7 2015 5:50PM | 49.844 | 47.475 | 9, 18.9 | 25.396 | 2.369 | 22.079 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.1 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
Y/31-2 | SGBM16 | Aug 8 2015 8:30AM | Aug 10 2015 1:00PM | 49.833 | 47.475 | 9, 14.5 | 25.037 | 2.358 | 22.438 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.4 | 22.0 | -19.4 | G35T2 | 1, 2 | 11, 11
Y/31-3 | SGBM20 | Aug 5 2015 9:30AM | Aug 5 2015 5:30PM | 49.801 | 47.475 | 9 | 25.217 | 2.326 | 22.258 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 24.0 | -19.3 | G35T2 | 1, 2, 3 | 6, 10, 8
Y/35-1 | SGBM03 | Aug 17 2015 8:00AM | Aug 17 2015 4:45PM | 0.000 | 47.275 | 8 | 0.000 | -47.275 | 47.275 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.9 | 24.0 | -100.0 | G45T2 | c480007171, c480007173, c520121054 | 11, 10, 3
Y/35-2 | SGBM03 | Aug 18 2015 3:05PM | Aug 19 2015 1:50PM | 49.711 | 47.275 | 8, 17.5 | 22.080 | 2.436 | 25.195 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 27.0 | -100.0 | G45T2 | c480007291, c480007293, c480007294, c520121074 | 7, 7, 5, 8
Y/36-1 | SGBM21 | Sep 9 2015 10:55AM | Sep 10 2015 7:50PM | 49.079 | 47.475 | 9, 25 | 21.160 | 1.604 | 26.315 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.8 | 32.0 | -100.0 | G45T2 | c520121497, c480008387, c520121500 | 10, 11, 11
Y/36-2 | SGBM03 | Aug 20 2015 10:40AM | Aug 21 2015 9:30AM | 49.602 | 47.475 |  | 21.208 | 2.127 | 26.267 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.7 | 27.0 | -100.0 | G45T2 | c170012413, c170012414, c170012415 | 10, 8, 9
Y/36-3 | SGBM03 | Aug 22 2015 9:42AM | Aug 24 2015 10:20AM | 49.670 | 47.475 | 8, 10.5, 29.1 | 21.374 | 2.195 | 26.101 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.6 | 29.0 | -100.0 | G45T2 | c520121135, c520121136, c170012423 | 11, 11, 7
Y/39-1 | SGBM03 | Aug 21 2015 8:05AM | Aug 22 2015 9:15AM | 49.696 | 47.375 | 8 | 17.330 | 2.321 | 30.045 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 33.0 | 26.8 | G45T2 | c480007417, c480007418, c480007420 | 11, 11, 11
Y/39-2 | SGBM03 | Aug 18 2015 10:30AM | Aug 19 2015 9:25AM | 49.655 | 47.375 | 8 | 18.085 | 2.280 | 29.290 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.4 | 33.0 | -100.0 | G45T2 | c480007275, c480007276, c480007278 | 11, 11, 11
Z/29-1 | SGBM16 | Aug 5 2015 7:00PM | Aug 6 2015 4:30PM | 49.817 | 47.375 | 9 | 24.321 | 2.442 | 23.054 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.0 | 24.0 | -20.0 | G35T2 | 1, 2, 3 | 11, 11, 2
Z/29-2 | SGBM16 | Aug 8 2015 7:40AM | Aug 10 2015 10:54PM | 50.068 | 47.375 | 9, 9 | 24.218 | -47.375 | 23.157 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.1 | 23.5 | -20.1 | G35T2 | 1, 2 | 11.5, 12
Z/35-1 | SGBM03 | Aug 21 2015 4:48PM | Aug 22 2015 2:55PM | 49.824 | 48.625 | 8, 15 | 22.845 | 1.199 | 25.780 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.3 | 27.0 | 4.7 | G45T2 | c480007435, c520121124, c520121123 | 12, 10, 5
Z/36-1 | SGBM03 | Sep 14 2015 4:15PM | Sep 15 2015 11:45AM | 49.782 | 46.925 | 8, 25 | 20.120 | 2.857 | 26.805 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.2 | 33.0 | 13.8 | G45T2 | c520121613, c520121614, c480008648, c480008653 | 4, 10, 11, 8
Z/36-2 | SGBM21 | Sep 11 2015 12:05PM | Sep 12 2015 2:20PM | 49.798 | 46.925 | 8, 25 | 20.520 | 2.873 | 26.405 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.9 | 29.0 | -100.0 | G45T2 | c520121549, c520121550, c480008512 | 9, 9, 11
Z/37-1 | SGBM03 | Sep 30 2015 10:35AM | Oct 1 2015 12:48PM | 49.746 | 46.925 | 8 | 18.400 | 2.821 | 28.525 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 32.0 | -24.7 | G45T2 | 1, 2, 3, 4 | 11, 8, 11, 2
Z/37-2 | SGBM21 | Sep 28 2015 1:00PM | Sep 29 2015 11:25AM | 49.700 | 46.925 |  | 18.448 | 2.775 | 28.477 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 11, 11, 3
Z/38-1 | SGBM19 | Aug 20 2015 3:45PM | Aug 21 2015 6:30PM | 49.724 | 46.925 | 8 | 18.534 | 2.799 | 28.391 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.6 | 33.0 | -100.0 | G45T2 | c480007392, c480007395, c480007398 | 11, 11, 11
Z/38-2 | SGBM21 | Sep 18 2015 11:44AM | Sep 19 2015 11:15AM | 49.762 | 46.925 | 8 | 18.502 | 2.837 | 28.423 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.6 | 28.0 | -100.0 | G45T2 | c480008862, c480008860, c480008868, c480008867 | 10, 6, 9, 3
Z/39-1 | SGBM03 | Sep 15 2015 11:30AM | Sep 17 2015 2:15PM | 49.716 | 47.025 | 8, 29 | 17.952 | 2.691 | 29.073 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 32.0 | -100.0 | G45T2 | c170012605, c480008762, c480008763, c480008767 | 10, 9, 11, 2
Z/39-3 | SGBM03 | Aug 24 2015 9:55AM | Aug 25 2015 9:15AM | 49.689 | 47.025 | 8 | 17.949 | 2.664 | 29.076 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 31.0 | 23.1 | G45T2 | c480007553, c480007554, c520121165 | 11, 11, 9
Y/23-1 | SGBM16 | Jul 13 2015 9:50AM | Jul 13 2015 8:33PM | 49.830 | 47.975 | 8 | 24.678 | 1.855 | 23.297 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.2 | 25.0 | -100.0 | G35T2 | c480005542, c480005541, c480007890 | 11, 11, 3
Y/23-2 | SGBM16 | Jul 23 2015 8:30AM | Jul 24 2015 12:20AM | 49.850 | 47.975 |  | 24.442 | 1.875 | 23.533 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
Z/39-2 | SGBM03 | Sep 19 2015 3:00PM | Sep 21 2015 5:00PM | 49.741 | 47.025 | 8, 28.6 | 17.875 | 2.716 | 29.150 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 33.0 | -100.0 | G45T2 | c480008970, c480008972, c480008975, c480008974 | 9, 11, 10, 3
Y/23-3 | SGBM16 | Jul 28 2015 11:00AM | Jul 28 2015 5:40PM | 49.819 | 47.975 |  | 24.191 | 1.844 | 23.784 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 23.5 | -100.0 | G35T2 | 1, 2, 3 | 7, 11.5, 5
Y/25-1 | SGBM16 | Jul 21 2015 8:45AM | Jul 22 2015 8:30PM | 49.877 | 47.975 | 8 | 23.900 | 1.902 | 24.075 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.8 | 25.0 | -100.0 | G35T2 | C480005694, C480005696, C480005699 | 10, 10, 5
Y/25-2 | SGBM17 | Jul 28 2015 9:20AM | Jul 28 2015 4:45PM | 49.858 | 47.975 |  | 24.121 | 1.883 | 23.854 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.7 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 9, 9, 5
Y/25-3 | SGBM16 | Jul 30 2015 8:30AM | Jul 30 2015 6:00PM | 49.846 | 47.975 | 9 | 25.022 | 1.871 | 22.953 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.9 | 25.0 | -19.9 | G35T2 | 1, 2, 3, 4 | 6.5, 6.5, 6.5, 5.5
X/22-1 | SGBM16 | Jul 10 2015 8:30AM | Jul 10 2015 3:29PM | 49.784 | 47.975 | 8 | 24.417 | 1.809 | 23.558 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 25.0 | 2.2 | G35T2 | c520120540, c480005344, c480005346 | 10, 10, 5
X/22-2 | SGBM16 | Jul 14 2015 11:15AM | Jul 14 2015 4:15PM | 49.738 | 47.975 | 8 | 25.180 | 1.763 | 22.795 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.7 | 22.0 | -100.0 | G35T2 | C480005583, C480005584, C480005586 | 4, 10, 8
X/22-3 | SGBM16 | Jul 27 2015 8:00AM | Jul 27 2015 6:58PM | 49.740 | 47.975 |  | 24.305 | 1.765 | 23.670 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
X/23-1 | SGBM16 | Jul 27 2015 1:30PM | Jul 27 2015 10:40PM | 49.790 | 47.975 |  | 24.345 | 1.815 | 23.630 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
X/23-2 | SGBM16 | Jul 29 2015 9:20AM | Jul 29 2015 9:30PM | 49.763 | 47.975 | 9 | 24.795 | 1.788 | 23.180 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.1 | 24.0 | -20.1 | G35T2 | 1, 2, 3 | 7, 10, 7
X/23-3 | SGBM16 | Jul 31 2015 8:30AM | Jul 31 2015 7:25PM | 49.812 | 47.975 | 9, 18.6 | 25.836 | 1.837 | 22.139 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.2 | 22.0 | -19.2 | G35T2 | 1, 2, 3 | 8, 7.5, 6.5
X/25-1 |  | Jul 11 2015 1:00PM | Jul 11 2015 8:50PM | 49.818 | 47.375 | 8, 25.1 | 25.371 | 2.443 | 22.004 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.1 | 22.0 | 15.4 | G35T2 | C480005418, C480005420 | 11, 11
X/25-2 | SGBM18 | Jul 27 2015 7:50AM | Jul 28 2015 1:36AM | 49.814 | 47.375 |  | 24.364 | 2.439 | 23.011 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.9 | 20.0 | -100.0 | G35T2 | 1, 2 | 10, 10
X/26-1 | SGBM17 | Jul 27 2015 11:15AM | Jul 28 2015 12:35AM | 49.870 | 47.375 |  | 24.805 | 2.495 | 22.570 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.5 | 22.0 | -100.0 | G35T2 | 1, 2 | 11, 11
X/26-2 | SGBM16 | Jul 15 2015 9:00AM | Jul 20 2015 6:00PM | 49.796 | 47.375 | 8, 17 | 23.796 | 2.421 | 23.579 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 25.0 | -100.0 | G35T2 | C480005621, C480005621, C480005622 | 11, 11, 3
F/55-1 | SGBM17 | Jul 16 2015 8:30AM | Jul 20 2015 6:58PM | 45.672 | 50.275 | 8 | 3.775 | -4.603 | 46.500 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 40.3 | 51.5 | -100.0 | G35T2 | c480005626, c480005627, c480005626, c480005629, c480005630 | 11, 11, 11.5, 11, 7
F/55-2 | SGBM23 | Jul 25 2015 8:03AM | Jul 28 2015 2:05PM | 51.974 | 50.275 | 8 | 6.499 | 1.699 | 43.776 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.9 | 52.5 | -100.0 | G35T2 | C480005925, c480005928, c480005930, c480005932, c480005936, c480005939 | 10, 10, 10, 10, 10.5, 2
F/55-3 | SGBM23 | Jul 23 2015 8:20AM | Jul 23 2015 9:01PM | 51.952 | 50.275 | 8 | 6.750 | 1.677 | 43.525 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 37.7 | 45.0 | -100.0 | G35T2 | c480005746, c480005747, c480005749, c480005753 | 12, 10, 12, 11
Y/41-2 | SGBM03 | Sep 13 2015 2:30PM | Sep 14 2015 10:40AM | 49.625 | 47.375 |  | 19.211 | 2.250 | 28.164 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 31.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 9, 11
W/41-1 | SGBM03 | Sep 10 2015 2:10PM | Sep 11 2015 12:30PM | 49.432 | 46.925 | 8, 27 | 15.798 | 2.507 | 31.127 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.0 | 30.0 | -100.0 | G35T2 | c170012572, c480008441, c480008442 | 8, 11, 11
Z/40a-1 | SGBM03 | Oct 3 2015 8:45PM | Oct 6 2015 6:20PM | 49.861 | 48.525 |  | 20.312 | 1.336 | 28.213 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 5, 7, 7, 7, 7, 3
L/57-1 | SGBM19 | Jul 11 2015 11:50AM | Jul 11 2015 9:17PM | 52.062 | 49.175 | 8 | 14.401 | 2.387 | 34.774 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.1 | 35.0 | 14.6 | G45T2 | c480005421, c480005423, c480005429, c480005443 | 11, 10, 10, 4
L/57-2 | SGBM23 | Jul 21 2015 8:40AM | Jul 21 2015 6:24PM | 55.121 | 49.175 | 8 | 14.428 | 5.446 | 34.747 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.1 | 39.0 | -100.0 | G45T2 | c480005646, c480005647, c480005648, c480005650 | 11, 11, 10, 7
L/57-3 | SGBM23 | Jul 25 2015 1:00PM | Jul 27 2015 4:06PM | 52.090 | 49.175 | 8, 15.1 | 14.170 | 2.415 | 35.005 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.3 | 36.0 | 17.1 | G45T2 | c480005859, c480005860, c480005865, c480005868 | 11, 11, 11, 3
L/58-1 | SGBM23 | Jul 13 2015 10:00AM | Jul 13 2015 4:20PM | 52.049 | 49.175 | 8 | 14.973 | 2.174 | 34.202 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.6 | 36.0 | 19.1 | G45T2 | c480005523, c480005524, c480005532, c480005535 | 11, 11, 10, 4
L/58-2 | SGBM23 | Jul 22 2015 8:30AM | Jul 22 2015 3:59PM | 52.127 | 49.175 | 8 | 14.476 | 2.252 | 34.699 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.0 | 35.0 | 14.2 | G45T2 | c480005679, c480005680, c480005683 | 11.5, 11.5, 12
L/58-3 | SGBM18 | Jul 28 2015 8:00AM | Jul 30 2015 12:35PM | 52.123 | 49.175 | 8 | 14.174 | 2.248 | 35.001 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.3 | 40.0 | 29.4 | G45T2 | c480006055, c480006056, c480006057, c480006059 | 10, 10, 10, 10
Z/43-1 | SGBM03 | Oct 3 2015 10:30AM | Oct 5 2015 11:11AM | 49.688 | 46.925 |  | 19.257 | 2.763 | 27.668 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.0 | 31.5 | -24.0 | G45T2 | 1, 2, 3, 4 | 11, 5.5, 11, 4
Z/43-2 | SGBM19 | Oct 29 2015 9:05AM | Oct 29 2015 4:55PM | 49.578 | 46.925 |  | 18.895 | 2.653 | 28.030 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 31.5 | -100.0 | G45T2 | 1, 2, 3, 4 | 9.5, 9, 8, 5
Z/44-1 | SGBM03 | Oct 1 2015 9:50AM | Oct 2 2015 3:45PM | 49.592 | 46.925 | 8 | 17.158 | 2.667 | 29.767 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.8 | 37.0 | -25.8 | G45T2 | 1, 2, 3, 4, 5, 6 | 9, 1, 8, 9, 9, 1
Z/44-2 | SGBM03 | Sep 28 2015 4:45PM | Sep 29 2015 7:45PM | 49.698 | 46.925 | 8, 28 | 17.698 | 2.773 | 29.227 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 34.0 | -25.3 | G45T2 | 1, 2, 3, 4 | 6, 9, 11, 8
Y/44-1 | SGBM03 | Sep 9 2015 11:50AM | Sep 10 2015 11:00AM | 49.720 | 47.475 | 8 | 19.408 | 2.245 | 28.067 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 30.0 | -100.0 | G45T2 | c480008331, c480008332, c480008335 | 11, 11, 8
Y/44-2 | SGBM03 | Sep 12 2015 6:00PM | Sep 14 2015 2:40PM | 49.654 | 47.475 |  | 19.219 | 2.179 | 28.256 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 10, 10, 6
Y/44-3 | SGBM03 | Sep 22 2015 8:25PM | Sep 25 2015 5:40PM | 49.624 | 47.475 | 8 | 19.181 | 2.149 | 28.294 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 32.0 | -100.0 | G45T2 | 520121862, c520121865, c520121864 | 12, 10, 10
Y/45-1 | SGBM19 | Sep 14 2015 5:05PM | Sep 15 2015 4:30PM | 49.674 | 47.075 | 8, 21 | 17.831 | 2.599 | 29.244 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 31.0 | -25.3 | G45T2 | c480008662, c480008665, c480008668 | 11, 11, 9
Y/45-2 | SGBM03 | Sep 18 2015 10:29AM | Sep 19 2015 3:25PM | 49.836 | 47.075 | 8, 22, 29 | 17.805 | 2.761 | 29.270 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 35.0 | -100.0 | G45T2 | c480008881, c480008887, c480008890, c480008893 | 11, 11.5, 11.5, 1
X/44-1 | SGBM03 | Sep 21 2015 10:45AM | Sep 22 2015 1:00PM | 49.626 | 47.475 | 8 | 18.226 | 2.151 | 29.249 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 33.0 | -100.0 | G45T2 | c480009020, c480009022, c480009024 | 11, 11, 11
X/44-2 | SGBM19 | Sep 11 2015 2:15PM | Sep 12 2015 11:50AM | 49.671 | 47.475 | 8, 27 | 18.372 | 2.196 | 29.103 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 33.0 | -100.0 | G45T2 | c480008497, c480008498, c480008499 | 11, 11, 11
X/44-3 | SGBM21 | Sep 15 2015 6:30PM | Sep 18 2015 9:25AM | 49.627 | 47.475 | 8, 16, 18 | 18.229 | 2.152 | 29.246 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 33.0 | -100.0 | G45T2 | c480008797, c480008798, c480008799 | 11, 11, 11
X/42-1 | SGBM03 | Aug 24 2015 5:15PM | Aug 25 2015 11:40AM | 49.689 | 47.375 |  | 18.049 | 2.314 | 29.326 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.4 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 9, 10, 5
Y/41-1 | SGBM03 | Sep 8 2015 4:10PM | Sep 9 2015 1:30PM | 49.620 | 47.375 | 8, 16 | 19.160 | 2.245 | 28.215 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 30.0 | 22.8 | G45T2 | c480008274, c480008275, c480008277 | 10, 12, 8
W/45-1 | SGBM21 | Sep 14 2015 6:30PM | Sep 17 2015 8:10PM | 49.726 | 47.625 | 8, 16, 24.2 | 19.570 | 2.101 | 28.055 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.3 | 42.0 | -24.3 | G35T2 | c170012622, c480008781, c480008783, c480008788 | 12, 12, 12, 6
W/45-2 | SGBM03 | Sep 22 2015 6:00PM | Sep 26 2015 2:45PM | 49.802 | 47.625 | 8, 28 | 19.457 | 2.177 | 28.168 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.4 | 33.0 | 35.3 | G35T2 | c520121896, c520121892, c520121897, c520121902 | 11, 10, 10, 2
X/42-2 | SGBM19 | Sep 10 2015 3:05PM | Sep 11 2015 3:50PM | 49.682 | 47.375 | 8, 20 | 18.154 | 2.307 | 29.221 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 34.0 | -100.0 | G45T2 | c170012573, c170012574, c480008455, c520121524 | 10, 3, 11, 10
W/41-2 | SGBM19 | Aug 24 2015 5:15PM | Aug 25 2015 6:55PM | 49.387 | 46.925 | 8, 12 | 15.606 | 2.462 | 31.319 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.1 | 36.0 | 32.7 | G35T2 | c480007587, c480007589, c480007594, c480007599 | 11, 11, 11, 3
Z/40a-2 | SGBM19 | Sep 17 2015 5:15PM | Sep 18 2015 7:45PM | 49.664 | 48.525 | 8, 24 | 19.505 | 1.039 | 29.020 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.1 | 31.0 | 22.9 | G45T2 | c520121729, c520121731, c480008843, c520121736 | 10, 10, 8, 3
Z/41-1 | SGBM17 | Nov 20 2015 3:00PM | Nov 22 2015 9:58AM | 49.492 | 48.525 |  | 18.198 | 0.967 | 30.327 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.3 | 32.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 2
Y/42-1 | SGBM03 | Sep 26 2015 12:00PM | Sep 28 2015 5:17PM | 49.679 | 47.375 |  | 18.797 | 2.304 | 28.578 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 32.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 10, 11
Y/42-2 | SGBM03 | Sep 22 2015 1:50PM | Sep 23 2015 2:05PM | 49.657 | 47.375 | 8 | 19.331 | 2.282 | 28.044 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 33.0 | -100.0 | G45T2 | c480009101, c520121838, c520121839 | 11, 10, 12
Y/43-1 | SGBM03 | Sep 30 2015 3:05PM | Oct 1 2015 3:45PM | 46.681 | 47.375 | 8 | 19.090 | -0.694 | 28.285 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 3
Y/43-2 | SGBM21 | Sep 21 2015 7:00PM | Sep 23 2015 5:35PM | 49.667 | 47.375 | 8, 16 | 19.167 | 2.292 | 28.208 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 28.0 | -100.0 | G45T2 | c480009116, c480009117, c480009121 | 11, 11, 6
X5/Y2-1 | SGBM03 | Nov 17 2015 2:00PM | Nov 17 2015 11:03PM | 55.714 | 53.175 |  | 16.775 | 2.539 | 36.400 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.5 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 8, 8, 7
X5/Y2-2 | SGBM09 | Oct 1 2015 6:00PM | Oct 2 2015 9:00PM | 55.690 | 53.175 | 9, 18 | 17.046 | 2.515 | 36.129 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.3 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 9, 11, 4, 6
X5/Y2-3 | SGBM18 | Nov 26 2015 11:40AM | Nov 27 2015 3:59PM | 55.480 | 53.175 | 9, 35 | 16.902 | -53.175 | 36.273 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.4 | 40.0 | -31.4 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 10
X5/Y2-4 | SGBM01 | Dec 2 2015 6:00PM | Dec 11 2015 7:05PM | 55.408 | 53.175 | 9, 15 | 17.446 | 2.233 | 35.729 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 30.9 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 8, 7, 7, 8
X6/Y2-1 | SGBM03 | Nov 15 2015 10:00AM | Nov 16 2015 6:16PM | 55.580 | 53.475 |  | 15.979 | 2.105 | 37.496 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 32.5 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 7, 4
X6/Y2-2 | SGBM18 | Nov 24 2015 2:00PM | Nov 25 2015 2:53PM | 55.617 | 53.475 | 9, 33.7, 39 | 16.391 | 2.142 | 37.084 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 32.1 | 38.0 | -32.1 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 7, 3
X6/Y2-3 | SGBM05 | Nov 29 2015 2:00PM | Nov 30 2015 10:32PM | 55.480 | 53.475 | 9 | 16.297 | 2.005 | 37.178 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 32.2 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 7, 8, 8, 7, 5
X7/Y2-1 | SGBM05 | Nov 21 2015 8:00PM | Nov 23 2015 9:27PM | 55.472 | 53.475 | 9, 21 | 16.411 | 1.997 | 37.064 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 32.1 | 39.0 | -32.1 | G45T2 | 1, 2, 3, 4, 5, 6 | 5, 7, 7, 7, 6, 7
X7/Y2-2 | SGBM05 | Nov 30 2015 8:00AM | Dec 1 2015 7:23PM | 55.314 | 53.475 | 9 | 16.417 | 1.839 | 37.058 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 32.1 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 6, 4
X7/Y2-3 | SGBM05 | Dec 4 2015 3:10PM | Dec 5 2015 12:40AM | 55.329 | 53.475 | 9 | 16.352 | 1.854 | 37.123 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 32.1 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 12, 8, 6, 6, 6
X8/Y2-1 | SGBM03 | Nov 18 2015 2:00PM | Nov 18 2015 10:12PM | 55.580 | 52.875 |  | 16.388 | 2.705 | 36.487 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.6 | 38.0 | -31.6 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 8, 8
X8/Y2-2 | SGBM01 | Dec 4 2015 2:30PM | Dec 7 2015 2:55PM | 55.442 | 52.875 | 9 | 16.395 | 2.567 | 36.480 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.6 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4, 4, 5 | 7, 7, 7, 6, 6, 6
X8/Y2-3 | SGBM05 | Dec 1 2015 6:00PM | Dec 2 2015 9:15PM | 55.586 | 52.875 | 9, 16 | 16.819 | 2.711 | 36.056 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.2 | 40.0 | -100.0 | G45T2 | 2, 2, 3, 4, 5 | 7, 7, 12, 7, 7
X8/Y2-4 | SGBM01 | Dec 9 2015 7:30PM | Dec 11 2015 1:54AM | 55.503 | 52.875 | 9, 20 | 16.694 | 2.628 | 36.181 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.3 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 8
X8/Y3-1 | SGBM09 | Oct 3 2015 1:00PM | Oct 5 2015 10:17PM | 55.640 | 53.175 | 9 | 16.850 | 2.465 | 36.325 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 31.5 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 9, 4
X8/Y3-2 | SGBM18 | Nov 20 2015 11:15AM | Nov 21 2015 8:35PM | 55.610 | 53.175 | 9 | 20.053 | 2.435 | 33.122 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.7 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 8, 8, 10
X8/Y3-3 | SGBM05 | Nov 24 2015 4:10PM | Nov 25 2015 11:30PM | 55.464 | 53.175 | 9, 16.3 | 20.105 | 2.289 | 33.070 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.6 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 7
X8/Y4-1 | SGBM05 | Dec 1 2015 6:40PM | Dec 3 2015 1:34PM | 55.574 | 52.875 | 9, 26 | -34.400 | 2.699 | 87.275 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 75.6 | 33.0 | -75.6 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 7, 6, 5
X8/Y4-2 | SGBM03 | Nov 12 2015 5:00PM | Nov 14 2015 3:10PM | 55.877 | 52.875 | 9 | 21.911 | 3.002 | 30.964 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.8 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
X8/Y4-3 | SGBM05 | Nov 25 2015 4:15PM | Nov 30 2015 3:33PM | 55.505 | 52.875 | 9 | 21.775 | 2.630 | 31.100 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.9 | 33.0 | -26.9 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 6
X8/Y4-4 | SGBM20 | Nov 23 2015 3:45PM | Nov 24 2015 7:40PM | 55.711 | 52.875 | 9 | 21.535 | 2.836 | 31.340 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.1 | 37.0 | 9.8 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 8, 7, 8
J/25-1 | SGBM20 | Oct 3 2015 12:00PM | Oct 3 2015 8:37PM | 52.597 | 47.325 | 9 | 23.607 | 5.272 | 23.718 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 25.0 | -20.5 | G45T2 | 1, 2, 3 | 7, 12, 6
J/25-2 | SGBM20 | Sep 30 2015 9:00PM | Oct 1 2015 8:15PM | 52.267 | 47.325 | 9 | 23.542 | 4.942 | 23.783 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 26.0 | -20.6 | G45T2 | 1, 2, 3 | 8, 10, 8
J/25-3 | SGBM20 | Oct 7 2015 9:30AM | Oct 7 2015 9:46PM | 52.460 | 47.325 | 9 | 23.300 | 5.135 | 24.025 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.8 | 25.0 | -20.8 | G45T2 | 1, 2, 3 | 9, 11, 5
J/25-4 | SGBM20 | Oct 3 2015 12:00PM | Oct 5 2015 5:38PM | 52.249 | 47.325 | 9 | 23.685 | 4.924 | 23.640 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 26.0 | -20.5 | G45T2 | 1, 2, 3 | 11, 11, 4
J/25-5 | SGBM20 | Sep 29 2015 1:00PM | Sep 29 2015 9:36PM | 52.262 | 47.325 |  | 23.554 | 4.937 | 23.771 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 25.0 | 21.4 | G45T2 | 1, 2, 3, 4 | 3, 9, 9, 4
J/25-6 | SGBM20 | Sep 23 2015 1:00PM | Sep 26 2015 7:25PM | 52.344 | 47.325 | 9 | 23.724 | 5.019 | 23.601 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 25.0 | -100.0 | G45T2 | c170012739, c520121916, c520121920 | 10, 10, 5
J/25-7 | SGBM20 | Oct 9 2015 11:00AM | Oct 9 2015 6:53PM | 52.495 | 47.325 | 9 | 23.711 | 5.170 | 23.614 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 28.0 | -20.4 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
J/25-8 | SGBM20 | Sep 22 2015 3:30PM | Sep 23 2015 1:20PM | 52.074 | 47.325 | 9, 20 | 23.602 | 4.749 | 23.723 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 25.0 | -100.0 | G45T2 | c480009095, c480009099, c480009100 | 5, 11, 9
J/25-9 | SGBM20 | Sep 15 2015 2:20PM | Sep 18 2015 12:20PM | 52.106 | 47.325 | 9 | 23.708 | 4.781 | 23.617 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 28.0 | -20.4 | G45T2 | 1, 2, 3 | 9, 10, 9
J/25-10 | SGBM20 | Sep 21 2015 12:00PM | Sep 22 2015 3:20PM | 52.105 | 47.325 | 9 | 23.616 | 4.780 | 23.709 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 27.0 | 4.8 | G45T2 | c480009035, c480009036, c480009038 | 4, 11.5, 11.5
J/25-11 | SGBM20 | Sep 30 2015 9:00PM | Oct 1 2015 6:13PM | 52.201 | 47.325 | 9 | 23.511 | 4.876 | 23.814 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 4
J/25-12 | SGBM20 | Sep 17 2015 8:00AM | Sep 17 2015 7:38PM | 52.030 | 47.325 | 9 | 24.268 | 4.705 | 23.057 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.0 | 27.0 | -20.0 | G45T2 | 1, 2, 3 | 12, 10, 5
J/25-13 | SGBM20 | Sep 22 2015 6:00PM | Sep 23 2015 5:55PM | 52.193 | 47.325 | 9 | 23.613 | 4.868 | 23.712 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 27.0 | 4.8 | G45T2 | c480009210, c480009121, c480009124 | 11, 5, 11
J/25-14 |  | Sep 25 2015 5:00PM | Sep 28 2015 1:50PM | 52.171 | 47.325 | 9, 29.5 | 23.451 | 4.846 | 23.874 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.7 | 27.0 | -100.0 | G45T2 | c480009189, c480009192, c480009195 | 11, 9, 7
J/25-15 | SGBM20 | Oct 5 2015 1:30PM | Oct 5 2015 9:54PM | 52.319 | 47.325 | 9 | 23.617 | 4.994 | 23.708 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 25.0 | -20.5 | G45T2 | 1, 2, 3 | 8, 9, 8
J/25-16 | SGBM20 | Sep 28 2015 5:30PM | Sep 29 2015 1:15AM | 52.120 | 47.325 | 9 | 23.724 | 4.795 | 23.601 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 24.0 | -100.0 | G45T2 | c480009264, c170012756, c480009272 | 8, 8, 8
J/27-1 | SGBM20 | Oct 9 2015 9:00AM | Oct 9 2015 3:00PM | 52.311 | 48.825 | 9 | 24.992 | 3.486 | 23.833 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 24.0 | -20.6 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
J/27-2 | SGBM20 | Sep 30 2015 1:00PM | Oct 1 2015 12:51AM | 52.166 | 48.825 | 9 | 25.316 | 3.341 | 23.509 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 12, 5
J/27-3 | SGBM20 | Oct 7 2015 9:00AM | Oct 7 2015 10:48PM | 52.242 | 48.825 | 9 | 24.918 | 3.417 | 23.907 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.7 | 26.0 | -20.7 | G45T2 | 1, 2, 3 | 4, 11, 11
J/27-4 | SGBM20 | Sep 25 2015 1:00PM | Sep 26 2015 4:40PM | 52.446 | 48.825 | 9 | 24.936 | 3.621 | 23.889 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.7 | 27.0 | -100.0 | G45T2 | c520121902, c520121995, c520121907 | 10, 12, 5
J/27-5 | SGBM15 | Sep 18 2015 3:00PM | Sep 19 2015 12:45PM | 52.052 | 48.825 | 9, 25.7 | 25.072 | 3.227 | 23.753 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 25.0 | -100.0 | G45T2 | c480008867, c480008871, c480008872 | 7, 10, 8
J/27-6 | SGBM20 | Sep 21 2015 7:30PM | Sep 23 2015 12:30AM | 52.074 | 48.825 | 9 | 25.002 | 3.249 | 23.823 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 26.5 | -100.0 | G45T2 | c480009072, c480009075, c480009082 | 10, 11.5, 5
J/27-7 | SGBM20 | Oct 1 2015 6:08PM | Oct 2 2015 4:21PM | 52.118 | 48.825 | 9 | 25.134 | 3.293 | 23.691 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 24.0 | -20.5 | G45T2 | 1, 2, 3 | 11, 8, 5
J/27-8 | SGBM20 | Sep 28 2015 8:00PM | Sep 30 2015 1:57AM | 51.375 | 48.825 | 9 | 27.008 | 2.550 | 21.817 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.9 | 28.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 9, 8
J/28-1 | SGBM20 | Oct 2 2015 6:40PM | Oct 3 2015 5:18PM | 52.199 | 51.375 | 9 | 27.495 | 0.824 | 23.880 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.7 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 4, 10, 10
J/28-2 | SGBM20 | Oct 6 2015 6:00PM | Oct 6 2015 11:05PM | 52.290 | 51.375 | 9 | 27.505 | 0.915 | 23.870 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.7 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 3
J/28-3 | SGBM20 | Sep 29 2015 7:00PM | Sep 30 2015 6:55PM | 52.222 | 51.375 | 9 | 27.635 | 0.847 | 23.740 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 11, 7
J/28-4 | SGBM20 | Sep 26 2015 6:50PM | Sep 28 2015 7:45PM | 52.204 | 51.375 | 9 | 27.684 | 0.829 | 23.691 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 27.0 | -100.0 | G45T2 | c520121949, c480009217, c480009220 | 11, 11, 5
J/28-5 | SGBM20 | Sep 15 2015 2:00PM | Sep 17 2015 12:48PM | 52.116 | 51.375 | 9 | 27.746 | 0.741 | 23.629 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 26.0 | -20.5 | G45T2 | 1, 2, 3 | 5, 11, 10
J/28-6 | SGBM20 | Sep 18 2015 4:29PM | Sep 21 2015 11:50AM | 52.142 | 51.375 | 9 | 27.615 | 0.767 | 23.760 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 23.0 | 2.4 | G45T2 | c480008953, c480008949, c520121791 | 8, 4, 11
J/28-7 | SGBM20 | Sep 23 2015 6:00PM | Sep 25 2015 5:30PM | 52.056 | 51.375 | 9 | 27.626 | 0.681 | 23.749 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.6 | 24.0 | -100.0 | G45T2 | c520121861, c520121860, c170012731 | 12, 10, 2
J/28-8 | SGBM20 | Oct 10 2015 1:30PM | Oct 10 2015 6:32PM | 52.145 | 51.375 | 9 | 27.737 | 0.770 | 23.638 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.5 | 28.0 | -20.5 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
J/29-1 | SGBM23 | Oct 19 2015 10:00AM | Oct 19 2015 7:00PM | 52.121 | 49.775 |  | 26.679 | 2.346 | 23.096 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.0 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 3, 3
J/29-2 | SGBM20 | Oct 23 2015 3:10PM | Oct 24 2015 1:08PM | 52.204 | 49.775 | 9, 21 | 26.350 | 2.429 | 23.425 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.3 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 6, 6, 6, 3
J/29-3 | SGBM20 | Oct 21 2015 11:30AM | Oct 22 2015 2:45PM | 52.169 | 49.775 | 9 | -26.500 | 2.394 | 76.275 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 66.1 | 26.0 | -40.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 5
J/30-1 | SGBM20 | Oct 13 2015 2:34PM | Oct 15 2015 3:40PM | 51.968 | 49.675 | 9 | 26.429 | -49.675 | 23.246 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 24.0 | -20.1 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
J/30-2 | SGBM20 | Oct 5 2015 10:30AM | Oct 5 2015 1:40PM | 52.103 | 49.675 | 9 | 26.557 | 2.428 | 23.118 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.0 | 25.0 | -20.0 | G45T2 | 1, 2, 3 | 10, 11, 4
H/30-1 | SGBM20 | Oct 28 2015 9:30AM | Oct 28 2015 9:34PM | 52.239 | 49.675 | 9 | 25.813 | 2.564 | 23.862 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.7 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 6, 6, 5, 1
H/30-2 | SGBM20 | Oct 20 2015 8:00AM | Oct 20 2015 2:23PM | 52.082 | 49.675 | 9 | 26.630 | 2.407 | 23.045 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.0 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 6, 6, 5, 1
J/31-1 | SGBM09 | Sep 26 2015 5:00PM | Sep 28 2015 9:35PM | 52.034 | 49.675 | 9 | 27.608 | 1.159 | 22.067 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 22.0 | -100.0 | G45T2 | c480009221, c480009222 | 11, 11
J/31-2 | SGBM20 | Sep 29 2015 7:00PM | Sep 30 2015 10:26PM | 52.113 | 49.675 | 9 | 27.523 | 1.238 | 22.152 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 4
J/31-3 | SGBM20 | Sep 18 2015 5:30PM | Sep 19 2015 4:20PM | 51.985 | 49.675 | 9, 23 | 27.537 | 1.110 | 22.138 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 22.0 | -100.0 | G45T2 | c480008893, c480008889 | 11.5, 10.5
J/31-4 | SGBM20 | Sep 21 2015 5:00PM | Sep 22 2015 11:30PM | 52.020 | 49.675 | 9 | 27.664 | 1.145 | 22.011 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 23.0 | -100.0 | G45T2 | c480009069, c480009071 | 11.5, 11.5
J/31-5 | SGBM20 | Oct 16 2015 4:15PM | Oct 16 2015 9:27PM | 52.039 | 49.675 | 9 | 27.350 | 2.364 | 22.325 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
J/31-6 | SGBM20 | Oct 12 2015 8:00AM | Oct 12 2015 3:42PM | 52.014 | 50.875 | 9 | 27.875 | 1.139 | 23.000 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.9 | 25.0 | -19.9 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
L/21-1 | SGBM20 | Aug 24 2015 3:00PM | Aug 25 2015 10:09AM | 53.511 | 50.775 | 9 | 29.895 | 2.736 | 20.880 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.1 | 23.0 | -100.0 | G35T2 | 1, 2, 3 | 10, 9, 4
L/21-2 | SGBM20 | Sep 9 2015 8:00AM | Sep 10 2015 1:40PM | 53.482 | 50.775 | 9 | 29.003 | 2.707 | 21.772 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.9 | 22.0 | -18.9 | G35T2 | 1, 2 | 11, 11
K/21-1 | SGBM20 | Sep 9 2015 8:00AM | Sep 9 2015 5:40PM | 53.430 | 51.075 | 9 | 30.322 | 2.355 | 20.753 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.0 | 24.0 | -100.0 | G35T2 | 1, 2, 3 | 11, 11, 2
K/21-2 | SGBM20 | Sep 10 2015 6:00PM | Sep 11 2015 8:00PM | 53.512 | 51.075 | 9 | 29.109 | 2.437 | 21.966 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.0 | 23.0 | -100.0 | G35T2 | c170012577, c480008473, c480008475 | 8, 11, 4
J/21-1 | SGBM20 | Sep 9 2015 1:00PM | Sep 10 2015 6:50PM | 53.505 | 51.075 | 9 | 25.358 | 2.430 | 25.717 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.3 | 29.0 | -100.0 | G45T2 | c480008377, c520121495, c480008380, c480008382 | 7, 9, 9, 4
J/21-2 | SGBM20 | Aug 24 2015 8:00PM | Aug 25 2015 1:43PM | 53.489 | 51.075 | 9, 12.5 | 25.056 | 2.414 | 26.019 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.5 | 25.0 | -22.5 | G45T2 | 1, 2, 3 | 10, 8, 7
H/21-1 | SGBM20 | Sep 10 2015 3:35PM | Sep 11 2015 3:25PM | 53.730 | 49.775 | 9 | 23.968 | 3.955 | 25.807 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.3 | 28.0 | -100.0 | G45T2 | c480008448, hx043, c170012574 | 11, 11, 6
H/21-2 | SGBM20 | Aug 25 2015 5:00PM | Sep 8 2015 4:20PM | 53.607 | 49.775 | 9 | 24.427 | 3.832 | 25.348 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.0 | 30.0 | -21.9 | G45T2 | 1, 2, 3, 4 | 4, 11, 10, 5
H/21-3 | SGBM20 | Sep 12 2015 4:30PM | Sep 14 2015 12:50PM | 53.582 | 49.775 | 9, 22 | 24.177 | 3.807 | 25.598 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.2 | 26.0 | -100.0 | G45T2 | c480008594, c520121591, c480008602 | 11, 12, 3
J/23-1 | SGBM20 | Sep 10 2015 8:30AM | Sep 11 2015 11:50AM | 53.481 | 49.775 | 9 | 26.214 | 3.706 | 23.561 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.4 | 27.0 | -20.4 | G45T2 | 1, 2, 3 | 11, 10, 6
J/23-3 | SGBM20 | Sep 21 2015 1:00PM | Sep 21 2015 6:11PM | 52.426 | 49.775 | 9 | 26.786 | 2.651 | 22.989 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.9 | 25.0 | -19.9 | G45T2 | 1, 2, 3 | 10, 11, 4
J/23-2 | SGBM15 | Sep 12 2015 3:35PM | Sep 14 2015 3:25PM | 52.193 | 49.775 | 9 | 25.911 | 2.718 | 23.864 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.7 | 27.0 | 32.3 | G45T2 | c480008603, c5290121597, c480008611, c520121603 | 3, 10, 11, 3
J/24-1 | SGBM15 | Sep 14 2015 3:00PM | Sep 15 2015 1:45PM | 52.304 | 49.775 | 9 | 26.085 | 2.529 | 23.690 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.5 | 25.0 | -100.0 | G45T2 | c480008651, c480008653, c480008654 | 11, 3, 11
J/24-2 | SGBM15 | Sep 11 2015 10:30AM | Sep 12 2015 1:25PM | 52.115 | 49.775 | 9 | 26.215 | 2.424 | 23.560 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.4 | 24.0 | 17.6 | G45T2 | c520121544, c5201211546, c520121545 | 9, 10, 5
J/24-3 | SGBM15 | Sep 9 2015 9:00AM | Sep 9 2015 6:30PM | 51.093 | 49.775 | 9 | 26.252 | 1.318 | 23.523 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.4 | 29.0 | -100.0 | G45T2 | c480008302, c480008306, c480008309 | 9, 10, 10
H/24-1 | SGBM20 | Sep 29 2015 6:00PM | Sep 30 2015 1:57PM | 52.139 | 49.775 | 9 | 26.219 | 2.364 | 23.556 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.4 | 24.0 | -20.4 | G45T2 | 1, 2, 3 | 2, 11, 11
H/24-2 | SGBM15 | Sep 10 2015 8:00AM | Sep 10 2015 4:30PM | 52.174 | 49.775 | 9 | 25.934 | 2.399 | 23.841 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.6 | 25.0 | -100.0 | G45T2 | c480008363, c480008363, c480008369 | 6, 11, 8
H/24-3 | SGBM15 | Aug 24 2015 3:00PM | Aug 25 2015 9:13PM | 52.165 | 49.775 | 9 | 25.935 | 2.990 | 23.840 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.6 | 26.0 | -20.6 | G45T2 | 1, 2, 3 | 11, 8, 7
K/28-1 | SGBM20 | Sep 11 2015 3:00PM | Sep 12 2015 6:00PM | 53.492 | 50.775 | 9 | 28.504 | 2.717 | 22.271 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.3 | 24.0 | -100.0 | G35T2 | c520121566, c520121567, c520121568 | 7, 11, 6
K/28-2 | SGBM20 | Sep 17 2015 5:57PM | Sep 18 2015 10:10PM | 53.528 | 50.775 | 9 | 28.335 | 2.753 | 22.440 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.4 | 28.0 | -19.4 | G35T2 | 1, 2, 3 | 9, 10, 9
K/29-1 | SGBM20 | Sep 15 2015 11:00AM | Sep 15 2015 8:00PM | 53.501 | 49.375 | 9 | 26.967 | 4.126 | 22.408 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 19.4 | 25.5 | -19.4 | G35T2 | 1, 2, 3 | 10, 12, 3.5
K/29-2 | SGBM20 | Oct 16 2015 10:30AM | Oct 16 2015 4:27PM | 52.121 | 49.375 | 9 | 26.199 | 2.746 | 23.176 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.1 | 25.0 | -20.1 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 4
K/30-1 | SGBM20 | Oct 19 2015 4:29PM | Oct 20 2015 7:55PM | 52.043 | 49.375 | 9 | 26.262 | 2.668 | 23.113 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.0 | 25.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 6, 6, 6, 7
K/30-2 | SGBM09 | Sep 29 2015 10:00AM | Sep 29 2015 6:50PM | 52.020 | 49.375 |  | 26.330 | 2.645 | 23.045 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.0 | 24.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 2, 10, 10, 2
K/31-1 | SGBM09 | Sep 22 2015 6:00PM | Sep 23 2015 7:10PM | 52.020 | 49.675 | 9 | 26.230 | 2.345 | 23.445 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.3 | 26.0 | -100.0 | G35T2 | c480009129, c480009130, c480009136 | 9, 11, 6
K/31-2 | SGBM09 | Sep 26 2015 8:00AM | Sep 26 2015 9:30PM | 52.051 | 49.675 | 9 | 26.239 | 2.376 | 23.436 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.3 | 26.0 | -100.0 | G35T2 | c52012198, c520121919, c520121920 | 12, 12, 2
K/32-1 | SGBM09 | Sep 19 2015 6:20PM | Sep 21 2015 9:45PM | 52.005 | 49.325 | 9 | 29.944 | 1.830 | 19.381 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 16.8 | 15.0 | -100.0 | G45T2 | c520121802, c520121801 | 6, 9
K/32-2 | SGBM09 | Sep 23 2015 1:00PM | Sep 25 2015 9:00PM | 52.309 | 49.325 | 9 | 29.604 | 2.134 | 19.721 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.1 | 16.0 | 1.7 | G45T2 | c520121871, c520121872 | 10, 6
H/56-1 | SGBM18 | Sep 15 2015 11:20AM | Sep 18 2015 10:31AM | 52.007 | 46.875 | 6, 47 | 3.847 | 5.132 | 43.028 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 44.0 | -37.3 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
H/56-3 | SGBM15 | Sep 21 2015 5:10PM | Sep 23 2015 11:12AM | 52.020 | 46.875 | 6, 19.1 | 3.865 | 5.145 | 43.010 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.2 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 5, 11, 11, 11, 6
H/56-5 | SGBM17 | Oct 21 2015 9:00AM | Oct 22 2015 1:53PM | 51.810 | 46.875 | 8 | 3.607 | 4.935 | 43.268 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.5 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 10, 11, 7
H/56-7 | SGBM23 | Oct 5 2015 11:00AM | Oct 6 2015 10:40PM | 51.949 | 46.875 | 6, 25.1 | 3.875 | 5.074 | 43.000 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.2 | 51.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 5, 9, 10, 11, 11, 5
H/56-9 | SGBM17 | Sep 28 2015 3:00PM | Sep 30 2015 11:30AM | 51.982 | 46.875 | 6 | 3.852 | 5.107 | 43.023 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 3
H/56-11 | SGBM23 | Sep 14 2015 11:20AM | Sep 15 2015 9:50PM | 51.894 | 46.875 | 6 | 3.874 | 5.019 | 43.001 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.2 | 47.5 | 27.6 | G45T2 | 1, 2, 3, 4, 5 | 8.5, 12, 9, 10, 8
H/57-1 | SGBM17 | Sep 14 2015 10:30AM | Sep 15 2015 2:54PM | 51.978 | 46.375 | 6, 40 | 0.363 | 5.603 | 46.012 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.8 | 55.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 11
H/57-2 | SGBM17 | Sep 26 2015 8:00AM | Sep 26 2015 4:14PM | 51.960 | 46.375 |  | 0.298 | 5.585 | 46.077 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 53.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 11, 9, 10, 8, 7
H/57-3 | SGBM17 | Sep 19 2015 5:00PM | Sep 22 2015 9:35AM | 51.972 | 46.375 | 6, 18, 51.5 | 0.300 | 5.597 | 46.075 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 4
H/57-4 | SGBM15 | Oct 5 2015 8:00AM | Oct 6 2015 8:57PM | 51.938 | 46.375 | 6, 27.1 | 0.332 | 5.563 | 46.043 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 11, 11
H/57-5 | SGBM15 | Sep 26 2015 6:00PM | Sep 30 2015 3:12PM | 52.026 | 46.375 | 6, 24.4 | 0.349 | 5.651 | 46.026 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 10, 10, 7
H/57-6 | SGBM17 | Oct 13 2015 2:00PM | Oct 15 2015 10:50AM | 51.860 | 46.375 |  | -0.100 | 5.485 | 46.475 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.2 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 6, 4, 9, 9, 8, 7, 6
H/57-7 | SGBM23 | Oct 2 2015 3:10PM | Oct 3 2015 4:00PM | 51.880 | 46.375 | 6, 23 | 0.365 | 5.505 | 46.010 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.8 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 12, 12, 11, 12
H/57-8 | SGBM23 | Oct 7 2015 1:10PM | Oct 8 2015 9:00PM | 51.843 | 46.375 | 9 | -0.115 | 5.468 | 46.490 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.3 | 51.0 | -40.3 | G45T2 | 1, 2, 3, 4, 5, 6, 7, 8 | 7, 2, 7, 7, 7, 7, 7, 7
H/57-9 | SGBM15 | Sep 21 2015 5:50PM | Sep 25 2015 3:20PM | 51.975 | 46.375 | 6, 23.2, 49 | 0.286 | 5.600 | 46.089 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 12, 10, 10, 6
H/57-10 | SGBM23 | Sep 15 2015 4:10PM | Sep 19 2015 10:07AM | 52.036 | 46.375 | 6, 24 | 0.296 | 5.661 | 46.079 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 49.0 | -39.9 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 5
H/58-1 | SGBM23 | Oct 8 2015 3:45PM | Oct 9 2015 6:51PM | 51.960 | 46.375 | 8, 34 | -0.030 | 5.585 | 46.405 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.2 | 60.0 | 49.3 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 9, 10, 10, 10, 8, 8, 5
H/58-2 | SGBM15 | Sep 22 2015 1:50PM | Sep 28 2015 9:53PM | 52.000 | 46.375 | 6, 32 | 0.337 | 5.625 | 46.038 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 11, 6, 12, 11
H/58-3 | SGBM17 | Sep 15 2015 5:15PM | Sep 18 2015 5:12PM | 52.033 | 46.375 | 6, 30 | 0.309 | 5.658 | 46.066 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 56.0 | -39.9 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 11, 9, 12, 11, 6
H/58-4 | SGBM17 | Oct 15 2015 6:00PM | Oct 16 2015 11:00AM | 51.956 | 46.375 |  | 0.073 | 5.581 | 46.302 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.1 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6, 7, 8 | 7, 7, 7, 7, 7, 7, 4, 3
H/58-5 | SGBM17 | Oct 10 2015 5:00PM | Oct 12 2015 2:58PM | 51.909 | 46.375 |  | 0.231 | 5.534 | 46.144 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.0 | 53.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 9
H/58-6 | SGBM15 | Sep 30 2015 4:00PM | Oct 1 2015 12:58PM | 51.898 | 46.375 | 6 | 0.370 | 5.523 | 46.005 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.8 | 57.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 11, 11, 11, 8, 8
H/58-8 | SGBM17 | Oct 14 2015 7:20PM | Oct 15 2015 2:27PM | 51.910 | 46.375 |  | 0.073 | 5.535 | 46.302 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.1 | 46.0 | 14.7 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 10, 9, 9, 9, 2
H/58-9 | SGBM23 | Oct 9 2015 3:45PM | Oct 12 2015 10:40AM | 51.900 | 46.375 | 9 | -0.239 | 5.525 | 46.614 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 40.4 | 53.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 9
H/58-10 | SGBM17 | Oct 5 2015 11:40AM | Oct 6 2015 3:22PM | 51.938 | 46.375 | 9 | 0.373 | 5.563 | 46.002 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.8 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 11, 11, 11, 7
H/58-11 | SGBM15 | Sep 26 2015 12:40PM | Sep 29 2015 10:31PM | 51.987 | 46.375 | 6 | 0.334 | 5.612 | 46.041 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 4, 3, 11, 11, 9, 11
H/58-12 | SGBM15 | Sep 30 2015 9:00AM | Oct 1 2015 5:38AM | 52.000 | 46.375 | 6 | 0.372 | 5.625 | 46.003 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.8 | 53.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 10, 10
H/58-13 | SGBM17 | Oct 2 2015 4:00PM | Oct 3 2015 6:10PM | 51.949 | 46.375 | 6, 22.8 | 0.311 | 5.574 | 46.064 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 10, 12, 12, 5
H/58-14 | SGBM17 | Sep 22 2015 8:00AM | Sep 22 2015 7:25PM | 52.000 | 46.375 |  | 0.305 | 5.625 | 46.070 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.9 | 50.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 11, 11, 10, 10
Z/27-1 | SGBM19 | Oct 3 2015 5:00PM | Oct 6 2015 12:22PM | 50.043 | 47.425 |  | 22.952 | 2.618 | 24.473 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 21.2 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 11, 7
Z/27-2 | SGBM20 | Oct 7 2015 2:10PM | Oct 9 2015 4:22PM | 49.953 | 47.425 |  | 23.261 | 2.528 | 24.164 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.9 | 28.0 | -100.0 | G45T2 | PJ192, PJ193, PJ195, PJ196 | 7, 7, 7, 7
Z/27-3 | SGBM19 | Oct 7 2015 5:00PM | Oct 8 2015 7:12PM | 50.000 | 47.425 |  | 23.192 | 2.575 | 24.233 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 21.0 | 28.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 7, 11
Z/27-4 | SGBM19 | Oct 5 2015 8:00AM | Oct 5 2015 5:58PM | 50.012 | 47.425 |  | 23.143 | 2.587 | 24.282 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 21.0 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 10, 8
Z/27a-1 | SGBM22 | Sep 18 2015 7:00PM | Sep 21 2015 11:43AM | 50.079 | 49.075 | 8 | 27.434 | 1.004 | 21.641 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.7 | 18.0 | -100.0 | G45T2 | 1, 2 | 11, 7
Z/27a-2 | SGBM19 | Oct 7 2015 10:00AM | Oct 7 2015 11:40PM | 49.819 | 49.075 |  | 27.627 | 0.744 | 21.448 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.6 | 16.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 2
Z/27a-3 | SGBM19 | Sep 21 2015 1:00PM | Sep 21 2015 10:35PM | 50.091 | 49.075 |  | 27.319 | 1.016 | 21.756 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 18.8 | 19.0 | -100.0 | G45T2 | 1, 2 | 9, 10
Z/28-1 | SGBM19 | Sep 22 2015 10:30AM | Sep 22 2015 6:36PM | 50.066 | 48.575 |  | 24.296 | 1.491 | 24.279 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 21.0 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 3
Z/28-2 | SGBM19 | Sep 25 2015 1:00PM | Sep 26 2015 2:27PM | 49.996 | 48.575 |  | 24.541 | 1.421 | 24.034 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.8 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
Z/28-3 | SGBM19 | Sep 19 2015 8:00AM | Sep 19 2015 7:50PM | 44.956 | 48.575 |  | 24.252 | -3.619 | 24.323 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 21.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 5, 11, 11
Qa/35-1 | SGBM16 | Sep 18 2015 5:00PM | Sep 19 2015 2:00PM | 52.324 | 51.375 | 8 | 31.352 | 0.949 | 20.023 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.3 | 22.0 | 26.9 | G45T2 | a1, a2, a3 | 11, 3, 8
Qa/36-1 | SGBM16 | Sep 18 2015 4:00PM | Sep 21 2015 2:00PM | 52.525 | 50.925 | 8, 23 | 29.746 | 1.600 | 21.179 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 22.8 | -100.0 | G45T2 | a1, a2, a3 | 11.8, 10, 1
Q/38-1 | SGBM16 | Sep 22 2015 6:00PM | Sep 23 2015 2:30PM | 52.573 | 49.575 | 8 | 25.668 | 2.998 | 23.907 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.7 | 24.0 | -100.0 | G45T2 | a1, a2, a3 | 2, 11, 11
Q/38-2 | SGBM16 | Sep 28 2015 9:00AM | Sep 28 2015 3:32PM | 52.573 | 49.575 |  | 25.668 | 2.998 | 23.907 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.7 | 24.0 | -20.7 | G45T2 | 1, 2, 3 | 4, 11, 9
Pb/35-1 | SGBM16 | Sep 21 2015 3:00PM | Sep 22 2015 3:00PM | 52.262 | 51.375 | 8, 19 | 33.313 | 0.887 | 18.062 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 15.6 | 18.0 | 15.1 | G45T2 | a1, a2 | 11, 7
Pb/36-1 | SGBM16 | Sep 19 2015 5:30PM | Sep 22 2015 11:50AM | 52.450 | 50.925 | 8, 21 | 31.786 | 1.525 | 19.139 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 16.6 | 20.0 | 20.7 | G45T2 | a1, a2 | 11, 9
R/38-1 | SGBM16 | Sep 22 2015 5:30PM | Sep 23 2015 11:00AM | 52.790 | 49.575 | 8, 28.5 | 24.561 | 3.215 | 25.014 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.7 | 26.0 | -100.0 | G45T2 | a1, a2, a3 | 11, 11, 4
R/38-2 | SGBM16 | Sep 25 2015 5:35PM | Sep 26 2015 3:30PM | 52.822 | 49.575 | 8, 29 | 24.443 | 3.247 | 25.132 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 25.0 | -100.0 | G45T2 | a1, a2, a3 | 11, 11, 3
X/36-3 | SGBM03 | Aug 14 2015 9:30AM | Aug 14 2015 5:15PM | 49.557 | 47.475 |  | 21.209 | 2.082 | 26.266 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.7 | 28.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 6
G/59-7 | SGBM18 | Sep 23 2015 4:00PM | Sep 25 2015 7:30PM | 52.010 | 49.875 | 6, 22, 42.8 | 4.826 | 2.135 | 45.049 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 39.0 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 12, 8, 8, 7
G/59-8 | SGBM18 | Sep 19 2015 3:00PM | Sep 21 2015 10:39AM | 51.976 | 49.875 | 6, 20, 47.5 | 4.780 | 2.101 | 45.095 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.1 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 11, 8, 10, 4
J/32-1 | SGBM20 | Oct 8 2015 1:30PM | Oct 8 2015 5:45PM | 52.145 | 49.675 | 9 | 26.500 | 2.470 | 23.175 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 23.0 | 2.9 | G45T2 | 1, 2, 3, 4 | 7, 5, 7, 4
J/32-2 | SGBM20 | Oct 13 2015 9:00AM | Oct 13 2015 10:59PM | 52.126 | 49.675 |  | 26.544 | 2.451 | 23.131 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.0 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
X4/Y4-1 | SGBM21 | Oct 26 2015 8:40AM | Oct 28 2015 12:29PM | 55.805 | 54.725 | 9 | 23.565 | -54.725 | 31.160 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.0 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
X4/Y5-1 | SGBM21 | Oct 29 2015 8:00AM | Oct 30 2015 6:26PM | 55.814 | 54.725 | 9, 26 | 25.477 | 1.089 | 29.248 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.3 | 31.0 | -25.3 | G45T2 | 1, 2, 3, 4 | 10, 9, 9, 3
X5/Y4-1 | SGBM21 | Oct 15 2015 9:00AM | Oct 15 2015 9:28PM | 55.820 | 53.375 |  | 22.249 | 2.445 | 31.126 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.0 | 31.0 | 15.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
X5/Y4-2 | SGBM21 | Oct 19 2015 2:04PM | Oct 21 2015 1:30PM | 55.821 | 53.375 | 9, 28.7 | 22.262 | 2.446 | 31.113 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.9 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
X5/Y5-1 | SGBM21 | Oct 23 2015 9:15PM | Oct 24 2015 12:55PM | 55.688 | 53.175 |  | 24.017 | 2.513 | 29.158 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.3 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 8
X5/Y5-2 | SGBM21 | Oct 15 2015 9:00AM | Oct 15 2015 4:18PM | 55.695 | 53.175 |  | 24.125 | 2.520 | 29.050 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.2 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 7, 7, 3, 7
X5/Y5-3 | SGBM21 | Oct 21 2015 5:00PM | Oct 22 2015 12:09PM | 56.551 | 53.175 | 9 | 23.359 | 3.376 | 29.816 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.8 | 30.0 | -25.8 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
X5/Y5-4 | SGBM21 | Oct 17 2015 2:30PM | Oct 17 2015 8:01PM | 55.700 | 53.175 |  | 24.118 | 2.525 | 29.057 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.2 | 32.0 | 27.2 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 4, 7
X4a/Y4-1 | SGBM21 | Oct 22 2015 6:00PM | Oct 23 2015 12:04PM | 55.815 | 47.375 | 9, 25.6 | 23.874 | 8.440 | 23.501 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.4 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
X4a/Y4a-1 | SGBM21 | Oct 26 2015 11:30AM | Oct 26 2015 7:57PM | 55.722 | 47.975 |  | 24.906 | 7.747 | 23.069 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 20.0 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
X4b/Y5-1 | SGBM21 | Oct 30 2015 5:46PM | Oct 31 2015 5:14PM | 55.666 | 47.975 | 9 | 35.796 | 7.691 | 12.179 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 10.5 | 11.0 | -100.0 | G45T2 | 1, 2 | 5.5, 5.5
X6/Y3-1 | SGBM03 | Nov 19 2015 10:00AM | Nov 19 2015 8:00PM | 55.683 | 52.475 | 9 | 19.466 | 3.208 | 33.009 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.6 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
X6/Y3-2 | SGBM03 | Nov 14 2015 11:41AM | Nov 17 2015 11:29AM | 55.695 | 52.475 | 9, 26.3 | 19.116 | 3.220 | 33.359 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.9 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
X6/Y3-3 | SGBM05 | Nov 20 2015 7:15PM | Nov 22 2015 11:05AM | 55.660 | 52.475 | 9, 17.8, 33.7 | 19.308 | 3.185 | 33.167 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.7 | 38.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5, 6 | 8, 7, 7, 7, 7, 2
X6/Y3-4 | SGBM20 | Nov 24 2015 12:14PM | Nov 26 2015 5:05PM | 55.530 | 52.475 | 9, 16.3 | 19.583 | 3.055 | 32.892 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.5 | 37.0 | -28.5 | G35T2 | 1, 2, 3, 4 | 11, 10, 10, 6
X6/Y3-5 | SGBM03 | Nov 14 2015 10:00AM | Nov 14 2015 11:10PM | 55.664 | 52.475 | 9, 26 | 19.515 | -52.475 | 32.960 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.5 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 8, 8, 5
X6/Y3-6 | SGBM18 | Nov 23 2015 6:25PM | Nov 24 2015 10:14PM | 55.541 | 52.475 | 9 | 18.500 | 3.066 | 33.975 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 29.4 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
X6/Y3-7 | SGBM18 | Nov 22 2015 9:00AM | Nov 23 2015 6:34PM | 55.504 | 52.475 | 9 | 19.206 | 3.029 | 33.269 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.8 | 36.0 | -28.8 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 6, 2
X6/Y3-8 | SGBM18 | Nov 26 2015 1:20PM | Dec 2 2015 6:53PM | 55.545 | 52.475 | 9, 34 | 19.262 | 3.070 | 33.213 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.8 | 36.0 | 25.2 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 8
X6/Y3-9 | SGBM03 | Nov 11 2015 6:58PM | Nov 12 2015 9:10PM | 55.535 | 52.475 | 9 | 19.543 | 3.060 | 32.932 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.5 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
X6/Y3-10 | SGBM20 | Nov 20 2015 2:30PM | Nov 21 2015 10:17AM | 55.584 | 52.475 | 9 | 19.411 | 3.109 | 33.064 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.6 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
X6/Y6-1 | SGBM03 | Oct 31 2015 3:59PM | Nov 3 2015 7:47PM | 55.702 | 53.475 | 9, 23.4 | 25.724 | 2.227 | 27.751 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.0 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 10, 11
X6/Y6-2 | SGBM03 | Nov 5 2015 1:00PM | Nov 6 2015 11:17AM | 55.706 | 53.475 | 9, 13 | 26.006 | -53.475 | 27.469 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.8 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 8
X6/Y6-3 | SGBM03 | Nov 7 2015 8:40PM | Nov 11 2015 11:43AM | 55.618 | 53.475 | 9 | 25.830 | -53.475 | 27.645 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 23.9 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 4, 7
X7/Y4-1 | SGBM18 | Nov 23 2015 5:15PM | Nov 24 2015 4:27PM | 55.697 | 53.475 | 9, 20.2 | 22.345 | 2.222 | 31.130 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.0 | 37.0 | -26.9 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 8, 7
X7/Y4-2 | SGBM05 | Dec 3 2015 3:29PM | Dec 4 2015 3:09PM | 55.466 | 53.475 | 9, 28 | 22.468 | 1.991 | 31.007 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.9 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 6, 6, 5
X7/Y4-3 | SGBM20 | Nov 20 2015 8:00AM | Nov 20 2015 6:24PM | 55.740 | 53.475 | 9 | 22.400 | 2.265 | 31.075 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.9 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 6, 6, 7, 2
X8/Y5-1 | SGBM21 | Oct 23 2015 7:00PM | Oct 24 2015 10:14AM | 55.841 | 53.175 |  | 23.043 | 2.666 | 30.132 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.1 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
X8/Y5-2 | SGBM21 | Oct 21 2015 9:35AM | Oct 21 2015 6:59PM | 55.844 | 53.175 |  | 22.819 | 2.669 | 30.356 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.3 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
X8/Y5-3 | SGBM21 | Oct 19 2015 8:00AM | Oct 19 2015 3:13PM | 55.841 | 53.175 | 9 | 23.152 | 2.666 | 30.023 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.0 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 4
X8/Y6-1 | SGBM21 | Oct 31 2015 4:38PM | Nov 3 2015 8:52PM | 55.780 | 52.925 | 9 | 24.808 | -52.925 | 28.117 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.3 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 4, 1
X8/Y6-2 | SGBM03 | Nov 6 2015 6:00PM | Nov 7 2015 11:56AM | 55.766 | 52.925 | 9, 23 | 24.928 | 2.841 | 27.997 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 24.2 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 2
X9/Y3-1 | SGBM05 | Nov 18 2015 9:00AM | Nov 20 2015 9:14PM | 55.497 | 50.075 | 9, 27, 35 | 16.996 | 5.422 | 33.079 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.6 | 34.0 | -28.6 | G45T2 | 1, 2, 3 | 11, 11, 12
X9/Y3-2 | SGBM05 | Nov 27 2015 2:45PM | Nov 29 2015 12:04PM | 55.300 | 50.075 | 9 | 16.762 | 5.225 | 33.313 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.8 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 5
X9/Y3-3 | SGBM05 | Nov 23 2015 4:20PM | Nov 19 2015 5:27PM | 55.412 | 50.075 | 9 | 16.605 | 5.438 | 33.470 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 29.0 | 34.0 | -29.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
X9/Y3-4 | SGBM03 | Dec 1 2015 7:45PM | Dec 3 2015 1:59AM | 55.262 | 50.075 | 9, 21 | 17.005 | 5.187 | 33.070 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.6 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
X9/Y3-5 | SGBM05 | Nov 23 2015 4:20PM | Nov 24 2015 11:50AM | 55.412 | 50.075 | 9 | 24.605 | 5.337 | 25.470 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 22.1 | 35.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
X9/Y3-6 | SGBM05 | Nov 24 2015 6:15PM | Nov 26 2015 12:45PM | 55.365 | 50.075 | 9 | 17.009 | 5.290 | 33.066 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 28.6 | 35.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 10, 10, 10, 5
X9/Y4-1 | SGBM21 | Nov 13 2015 7:00PM | Nov 16 2015 9:59PM | 55.725 | 53.375 | 9, 17 | 22.294 | 2.350 | 31.081 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 26.9 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
X9/Y4-2 | SGBM05 | Nov 25 2015 4:55PM | Nov 28 2015 1:46PM | 55.529 | 53.375 | 9, 27 | 22.069 | 2.154 | 31.306 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 27.1 | 34.0 | -27.1 | G45T2 | 1, 2, 3 | 11.5, 11.5, 11
X9/Y6-1 | SGBM03 | Nov 5 2015 3:30PM | Nov 5 2015 8:57PM | 55.796 | 53.375 | 9 | 24.186 | 2.421 | 29.189 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.3 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 6, 6, 7, 6
X9/Y6-2 | SGBM03 | Nov 6 2015 4:46PM | Nov 7 2015 9:30PM | 55.722 | 53.375 | 9 | 24.170 | 2.347 | 29.205 |  | 0.0 | 0.0 | 12T20 + 9T20 | T12-225 | 12 | 25.3 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 5, 2
G/21-1 | SGBM20 | Nov 13 2015 3:15PM | Nov 14 2015 12:37PM | 52.540 | 50.475 | 9 | 23.863 | -50.475 | 26.612 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.0 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 5
G/21-2 | SGBM05 | Nov 6 2015 5:45PM | Nov 12 2015 9:30PM | 52.391 | 50.475 | 9 | 24.758 | 1.916 | 25.717 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.3 | 26.0 | -22.3 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 5
M/20-1 | SGBM05 | Nov 4 2015 9:15AM | Nov 5 2015 10:56AM | 54.747 | 52.775 | 9, 23.9 | 29.567 | 1.972 | 23.208 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 24.0 | -20.1 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
M/21-1 | SGBM19 | Oct 24 2015 10:30AM | Oct 24 2015 7:24PM | 54.191 | 52.775 | 9, 16 | 28.374 | 1.416 | 24.401 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.1 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
M/22-1 | SGBM05 | Oct 27 2015 4:20PM | Oct 28 2015 3:01PM | 53.786 | 52.775 | 9 | 27.429 | 1.011 | 25.346 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.9 | 26.0 | -21.9 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
M/24-1 | SGBM19 | Oct 24 2015 11:18AM | Oct 26 2015 10:24AM | 53.411 | 52.475 | 9 | 29.874 | -52.775 | 22.601 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.6 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 3
M/25-1 | SGBM20 | Oct 28 2015 5:05PM | Oct 29 2015 9:58AM | 53.384 | 52.475 | 9, 20 | 29.786 | 0.909 | 22.689 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.6 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
M/29-1 | SGBM20 | Oct 30 2015 9:58AM | Oct 30 2015 5:16PM | 52.658 | 51.075 | 9 | 26.251 | 1.583 | 24.824 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.5 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
M/31-1 | SGBM20 | Oct 31 2015 9:30AM | Oct 31 2015 4:03PM | 52.024 | 51.075 | 9 | 29.753 | -51.075 | 21.322 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.5 | 17.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 6, 5
M/32-1 | SGBM19 | Oct 24 2015 6:20PM | Oct 27 2015 10:39PM | 52.021 | 51.075 | 9 | 27.000 | -51.075 | 24.075 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
M/33-1 | SGBM20 | Oct 26 2015 9:30PM | Oct 27 2015 7:09PM | 51.965 | 51.075 |  | 26.464 | 0.890 | 24.611 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.3 | 26.0 | -21.3 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
M/34-1 | SGBM21 | Oct 29 2015 9:00AM | Oct 29 2015 4:55PM | 51.954 | 51.075 | 9 | 26.685 | -51.375 | 24.390 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.1 | 25.0 | -21.1 | G45T2 | 1, 2, 3, 4 | 6, 7, 6, 6
L/19-1 | SGBM05 | Oct 31 2015 10:20AM | Oct 31 2015 10:30PM | 53.709 | 52.775 | 9 | 30.403 | -52.775 | 22.372 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.4 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 2
K/20-1 | SGBM05 | Oct 31 2015 8:30AM | Nov 2 2015 2:20PM | 53.463 | 51.075 | 9 | 29.620 | -51.075 | 21.455 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.6 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
K/20-2 | SGBM19 | Oct 23 2015 8:30AM | Oct 23 2015 5:50PM | 53.484 | 51.075 | 9 | 29.325 | 2.409 | 21.750 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.8 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 5, 6
J/19-1 | SGBM05 | Oct 28 2015 9:00PM | Oct 30 2015 11:06PM | 53.477 | 52.775 | 9, 13, 22 | 26.322 | 0.702 | 26.453 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.9 | 23.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 7, 4, 6
H/19-1 | SGBM19 | Oct 23 2015 9:05AM | Oct 23 2015 10:37PM | 53.490 | 52.675 | 9 | 26.240 | -52.675 | 26.435 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.9 | 31.0 | -22.9 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 4, 6
H/20-1 | SGBM20 | Oct 28 2015 6:13PM | Oct 29 2015 3:14PM | 53.085 | 50.975 | 9 | 24.875 | -50.975 | 26.100 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.6 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 7
H/20-2 | SGBM19 | Oct 26 2015 8:45AM | Oct 26 2015 4:25PM | 53.505 | 50.975 | 9, 12 | 25.163 | -50.975 | 25.812 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.4 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
AB/26-1 | SGBM03 | Oct 20 2015 1:20PM | Oct 21 2015 9:08PM | 49.581 | 48.475 |  | 23.430 | 1.106 | 25.045 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.7 | 25.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 4
AB/27-1 | SGBM03 | Oct 21 2015 3:30PM | Oct 23 2015 12:17AM | 49.792 | 48.475 |  | 22.684 | 1.317 | 25.791 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.3 | 26.3 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 5.3
AB/29-1 | SGBM03 | Oct 23 2015 8:30AM | Oct 23 2015 6:53PM | 50.189 | 48.475 |  | 22.878 | 1.714 | 25.597 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.2 | 33.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5, 6 | 3, 5, 6, 6, 6, 7
AA/25-1 | SGBM19 | Oct 9 2015 6:00PM | Oct 10 2015 4:39PM | 49.913 | 49.075 |  | 23.638 | 0.838 | 25.437 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.0 | 25.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 4
AA/33-1 | SGBM03 | Oct 24 2015 10:00AM | Oct 24 2015 6:16PM | 48.751 | 48.775 |  | 23.422 | -0.024 | 25.353 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.0 | 26.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 6, 6, 6, 6, 2
Z/21-1 | SGBM20 | Oct 10 2015 8:50AM | Oct 10 2015 11:55PM | 49.792 | 48.775 |  | 24.532 | 1.017 | 24.243 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.0 | 27.0 | -21.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
Z/30-1 | SGBM19 | Oct 5 2015 8:30AM | Oct 6 2015 5:03PM | 49.988 | 47.025 |  | 22.849 | 2.963 | 24.176 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.9 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 4, 11
Z/30-2 | SGBM19 | Oct 7 2015 9:00PM | Oct 8 2015 3:59PM | 49.887 | 47.025 |  | 22.918 | 2.862 | 24.107 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.9 | 27.0 | 29.3 | G45T2 | 1, 2, 3, 4 | 3, 11, 10, 3
Y/20-1 | SGBM19 | Oct 16 2015 9:20AM | Oct 16 2015 5:10PM | 49.756 | 48.475 |  | 23.932 | 1.281 | 24.543 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
Y/21-1 | SGBM19 | Oct 12 2015 8:00AM | Oct 12 2015 5:50PM | 49.809 | 48.775 |  | 24.257 | 1.034 | 24.518 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.2 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 5, 7, 7
X/20-1 | SGBM19 | Oct 16 2015 10:00AM | Oct 17 2015 6:19PM | 49.812 | 48.475 |  | 24.210 | 1.337 | 24.265 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.0 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
X/21-1 | SGBM19 | Oct 12 2015 8:10AM | Oct 12 2015 11:00PM | 49.742 | 48.775 |  | 25.512 | 0.967 | 23.263 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
X/32-1 | SGBM19 | Sep 26 2015 4:00PM | Sep 28 2015 4:48PM | 49.659 | 47.475 |  | 24.312 | 2.184 | 23.163 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 2, 9, 11
X/32-3 | SGBM22 | Sep 29 2015 3:00PM | Sep 30 2015 1:00PM | 49.709 | 47.475 |  | 23.847 | 2.234 | 23.628 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.5 | 21.0 | -100.0 | G45T2 | 1, 2 | 11, 10
W/21-1 | SGBM03 | Oct 6 2015 3:00PM | Oct 7 2015 2:37AM | 49.742 | 48.725 |  | 25.419 | 1.017 | 23.306 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.2 | 29.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 10, 10
W/22-1 | SGBM03 | Oct 6 2015 3:00PM | Oct 7 2015 1:07AM | 49.967 | 47.025 |  | 25.063 | 2.942 | 21.962 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.0 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 6, 10, 11
W/22-2 | SGBM03 | Oct 7 2015 3:00PM | Oct 8 2015 11:30PM | 49.872 | 47.025 |  | 24.863 | 2.847 | 22.162 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 10, 6
V/21-1 | SGBM22 | Oct 7 2015 3:00PM | Oct 8 2015 12:50AM | 49.773 | 48.725 |  | 24.392 | 1.048 | 24.333 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.1 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 9, 6
V/22-1 | SGBM03 | Oct 8 2015 11:00AM | Oct 9 2015 7:22PM | 49.703 | 47.025 |  | 24.900 | 2.678 | 22.125 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
V/22-2 | SGBM19 | Oct 12 2015 11:00AM | Oct 13 2015 1:40AM | 49.716 | 47.025 |  | 24.696 | 2.691 | 22.329 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
U/21-1 | SGBM19 | Oct 12 2015 12:00PM | Oct 13 2015 3:51AM | 49.786 | 49.075 |  | 25.764 | 0.711 | 23.311 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
U/23-1 | SGBM18 | Aug 24 2015 2:00PM | Aug 25 2015 11:00PM | 49.821 | 49.075 |  | 27.643 | 0.746 | 21.432 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.6 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
U/24-1 | SGBM16 | Sep 10 2015 3:30PM | Sep 11 2015 10:40AM | 49.615 | 49.075 |  | 27.212 | 0.540 | 21.863 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.9 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
U/26-1 | SGBM18 | Aug 21 2015 6:00PM | Aug 22 2015 11:00AM | 52.197 | 51.375 |  | 30.687 | 0.822 | 20.688 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.9 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
U/28-1 | SGBM16 | Aug 19 2015 4:00PM | Aug 20 2015 2:20PM | 51.942 | 51.375 |  | 29.794 | 0.567 | 21.581 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.7 | 22.0 | -100.0 | G45T2 | 1, 2 | 11, 11
U/29-1 | SGBM18 | Aug 20 2015 2:30PM | Aug 21 2015 9:00PM | 51.851 | 51.375 |  | 30.159 | 0.476 | 21.216 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.4 | 21.0 | -100.0 | G45T2 | 1, 2 | 11, 10
U/30-1 | SGBM18 | Aug 20 2015 8:00AM | Aug 20 2015 12:10PM | 51.892 | 51.375 |  | 29.358 | 0.517 | 22.017 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 21.0 | -100.0 | G45T2 | 1, 2 | 11, 10
U/31-1 | SGBM03 | Oct 30 2015 4:20PM | Oct 30 2015 9:47PM | 51.975 | 51.375 |  | 29.363 | 0.600 | 22.012 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 25.0 | -19.1 | G45T2 | 1, 2, 3, 4 | 5, 6, 7, 7
U/32-1 | SGBM03 | Oct 29 2015 5:30PM | Oct 30 2015 1:57AM | 52.091 | 51.375 |  | 29.187 | 0.716 | 22.188 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 25.0 | -19.2 | G45T2 | 1, 2, 3, 4 | 6, 7, 6, 6
AB/37-1 | SGBM02 | Oct 31 2015 8:11AM | Oct 31 2015 8:05PM | 49.586 | 49.075 | 9 | 22.571 | 0.511 | 26.504 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.0 | 30.0 | -22.9 | G35T2 | PJ 1032, PJ 1034, PJ 1036, PJ 1038, PJ 1039 | 7, 7, 6, 5, 5
Z/42-1 | SGBM19 | Oct 16 2015 3:00PM | Oct 16 2015 11:47PM | 49.969 | 47.025 |  | 19.994 | 2.944 | 27.031 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 10, 11
Z/42-2 | SGBM19 | Oct 20 2015 3:00PM | Oct 21 2015 1:09AM | 49.700 | 47.025 |  | 20.010 | 2.675 | 27.015 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 32.0 | 36.8 | G45T2 | 1, 2, 3, 4, 5 | 7, 6, 7, 6, 6
Z/46-1 | SGBM17 | Dec 4 2015 7:00PM | Dec 7 2015 1:20PM | 49.455 | 48.625 |  | 18.590 | 0.830 | 30.035 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 30.0 | -100.0 | G45T2 | PJ 2694, PJ 2695, PJ 2696, PJ 2697 | 8, 7, 8, 7
V/35-1 | SGBM03 | Oct 28 2015 10:20AM | Oct 28 2015 6:40PM | 49.620 | 47.075 |  | 23.013 | 2.545 | 24.062 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 6, 6, 6, 2
V/35-2 | SGBM19 | Nov 2 2015 9:20AM | Nov 2 2015 11:32PM | 49.601 | 47.075 | 9 | 22.749 | 2.526 | 24.326 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
V/36-2 | SGBM02 | Oct 27 2015 7:00PM | Oct 28 2015 1:14PM | 49.648 | 47.075 |  | 21.060 | 2.573 | 26.015 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.5 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 6, 6, 6, 5
V/37-1 | SGBM19 | Oct 31 2015 8:30AM | Oct 31 2015 8:40PM | 49.615 | 47.075 | 9 | 20.072 | 2.540 | 27.003 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 39.0 | -23.4 | G45T2 | C480011141, C48001142, C480011144, C480011147 | 11, 11, 11, 6
V/37-2 | SGBM02 | Oct 29 2015 10:20AM | Oct 29 2015 6:15PM | 49.619 | 47.075 |  | 20.072 | 2.544 | 27.003 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 4
V/38-2 | SGBM02 | Oct 30 2015 3:50PM | Oct 31 2015 12:17AM | 49.372 | 47.075 |  | 18.060 | 2.297 | 29.015 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.1 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 7, 3
V/39-2 | SGBM02 | Oct 28 2015 10:50AM | Oct 29 2015 2:00AM | 49.497 | 47.075 |  | 17.074 | 2.422 | 30.001 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 5, 5, 3
V/40-1 | SGBM19 | Oct 29 2015 2:20PM | Oct 30 2015 12:40AM | 49.438 | 49.075 |  | 17.789 | 0.363 | 31.286 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.1 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
V/41-2 | SGBM08 | Oct 31 2015 8:16AM | Oct 31 2015 6:39PM | 49.522 | 47.275 | 9 | 17.668 | 2.247 | 29.607 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.6 | 30.0 | -100.0 | G45T2 | PJ 1025, PJ 1027, PJ 1030, PJ 1031 | 7, 9, 7, 7
V/42-1 | SGBM02 | Nov 2 2015 2:00PM | Nov 3 2015 7:26PM | 49.433 | 47.275 | 9, 31 | 19.269 | 2.158 | 28.006 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 40.0 | -100.0 | G45T2 | 2, 2, 3, 4, 5, 5 | 7, 7, 7, 7, 4, 8
V/42-2 | SGBM02 | Nov 5 2015 3:35PM | Nov 6 2015 3:20AM | 49.467 | 47.275 |  | 15.457 | 2.192 | 31.818 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 46.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 7, 6, 7, 7, 7, 6, 6
V/43-1 | SGBM19 | Oct 27 2015 8:00AM | Oct 27 2015 2:14PM | 49.459 | 47.275 |  | 17.217 | 2.184 | 30.058 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 4, 2
V/43-2 | SGBM02 | Oct 30 2015 9:10AM | Oct 30 2015 7:18PM | 49.401 | 47.275 |  | 17.245 | 2.126 | 30.030 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 4, 7, 7, 7, 7, 4
V/44-1 | SGBM02 | Nov 2 2015 8:00AM | Nov 3 2015 1:40AM | 49.447 | 47.275 |  | 18.208 | 2.172 | 29.067 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 6, 6, 6, 7, 2, 2
V/44-2 | SGBM02 | Nov 4 2015 9:00AM | Nov 5 2015 2:53AM | 49.309 | 47.275 | 9 | 17.679 | 2.034 | 29.596 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.6 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 8, 6
V/45-1 | SGBM31 | Jan 13 2016 4:40PM | Jan 14 2016 4:45PM | 50.573 | 47.275 |  | 19.195 | 3.298 | 28.080 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
V/45-2 | SGBM31 | Jan 16 2016 8:37AM | Jan 16 2016 7:00PM | 50.550 | 47.275 |  | 19.110 | 3.275 | 28.165 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 31.0 | -100.0 | G45T2 | PJ 4501, PJ 4508, PJ 4511, PJ 4514 | 10, 7, 7, 7
V/36-1 | SGBM02 | Oct 19 2015 7:00PM | Oct 20 2015 11:11AM | 49.635 | 47.075 |  | 21.019 | 2.560 | 26.056 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.6 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 4
V/38-1 | SGBM19 | Oct 21 2015 11:00AM | Oct 21 2015 8:48PM | 49.552 | 47.075 |  | 17.979 | 2.477 | 29.096 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 7, 2, 3
V/39-1 | SGBM19 | Oct 19 2015 9:10AM | Oct 20 2015 12:18AM | 49.478 | 47.075 |  | 16.992 | 2.403 | 30.083 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 34.0 | 30.5 | G45T2 | 1, 2, 3 | 11, 11, 12
U/38-1 | SGBM03 | Jan 13 2016 5:35PM | Jan 14 2016 11:05PM | 52.366 | 51.325 |  | 22.910 | 1.041 | 28.415 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.6 | 32.0 | 30.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 5
T/38-1 | SGBM03 | Jan 12 2016 4:00PM | Jan 14 2016 3:00PM | 52.289 | 51.325 |  | 24.047 | 0.964 | 27.278 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.6 | 30.0 | 6.4 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 3
Ta/39-1 | SGBM03 | Jan 11 2016 5:00PM | Jan 12 2016 2:10PM | 52.241 | 51.325 |  | 23.038 | 0.916 | 28.287 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
X/43-1 | SGBM21 | Oct 5 2015 6:15PM | Oct 6 2015 1:47PM | 49.597 | 47.375 |  | 17.974 | 2.222 | 29.401 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.5 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
X/43-2 | SGBM03 | Oct 2 2015 6:15PM | Oct 3 2015 11:57AM | 49.611 | 47.375 |  | 18.305 | 2.236 | 29.070 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 29.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 10, 11
T/37-1 | SGBM20 | Jan 9 2016 10:00AM | Jan 9 2016 4:05PM | 52.518 | 51.375 |  | 24.945 | 1.143 | 26.430 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.9 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 9, 8
S/26-1 | SGBM03 | Dec 26 2015 4:25PM | Dec 28 2015 8:00PM | 52.065 | 51.275 |  | 31.090 | 0.790 | 20.185 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.5 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
S/28-1 | SGBM20 | Dec 15 2015 7:00PM | Dec 16 2015 4:45PM | 52.084 | 51.375 |  | 30.115 | 0.709 | 21.260 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.4 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 7
S/29-1 | SGBM01 | Dec 17 2015 8:00AM | Dec 17 2015 8:53PM | 52.022 | 51.375 |  | 30.227 | 0.647 | 21.148 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 7
S/33-1 | SGBM01 | Dec 17 2015 2:30PM | Dec 18 2015 12:13PM | 52.166 | 49.225 |  | 26.055 | 2.941 | 23.170 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 7, 6, 6
S/33-2 | SGBM20 | Dec 22 2015 5:10PM | Dec 24 2015 12:16PM | 52.250 | 49.225 |  | 27.026 | 3.025 | 22.199 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 10, 6
S/36-1 | SGBM16 | Sep 28 2015 7:30PM | Sep 29 2015 10:40AM | 52.390 | 49.225 |  | 25.210 | 3.165 | 24.015 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 24.0 | -20.8 | G45T2 | 1, 2, 3 | 11, 11, 2
S/36-2 | SGBM16 | Sep 30 2015 10:00AM | Oct 1 2015 12:10PM | 51.540 | 49.225 |  | 25.190 | 2.315 | 24.035 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 3
S/37-1 | SGBM20 | Jan 6 2016 4:00PM | Jan 7 2016 10:55AM | 52.720 | 49.575 |  | 24.440 | 3.145 | 25.135 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 7, 7, 6
S/37-2 | SGBM20 | Jan 9 2016 1:00PM | Jan 9 2016 8:40PM | 52.612 | 49.575 |  | 24.395 | 3.037 | 25.180 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 11.5, 11.5, 4
S/39-1 | SGBM16 | Sep 29 2015 1:00PM | Sep 30 2015 6:27PM | 52.638 | 51.375 |  | 24.311 | 1.263 | 27.064 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 27.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 5
R/26-1 | SGBM01 | Dec 11 2015 2:30PM | Dec 12 2015 1:34AM | 55.097 | 51.275 |  | 30.184 | 3.822 | 21.091 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 7
R/28-1 | SGBM01 | Dec 14 2015 3:15PM | Dec 15 2015 2:52PM | 52.097 | 51.375 |  | 30.151 | 0.722 | 21.224 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.4 | 21.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 7, 7
R/33-1 | SGBM20 | Dec 17 2015 6:00PM | Dec 18 2015 8:19PM | 52.131 | 49.775 |  | 24.175 | 2.356 | 25.600 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.2 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 2
R/33-2 | SGBM20 | Dec 21 2015 4:25PM | Dec 22 2015 9:52PM | 51.920 | 49.775 |  | 26.275 | 2.145 | 23.500 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.4 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 3
R/33-3 | SGBM03 | Dec 28 2015 3:47PM | Dec 29 2015 1:22PM | 52.215 | 49.775 |  | 27.708 | 2.440 | 22.067 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 24.0 | 4.9 | G45T2 | 1, 2, 3 | 8, 8, 8
R/34-1 | SGBM20 | Dec 26 2015 1:00PM | Dec 26 2015 5:54PM | 52.123 | 48.825 |  | 26.323 | 3.298 | 22.502 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.5 | 24.0 | -19.5 | G45T2 | 1, 2, 3 | 8, 8, 8
R/34-2 | SGBM20 | Dec 21 2015 3:30PM | Dec 21 2015 9:33PM | 51.968 | 48.825 |  | 26.724 | 3.143 | 22.101 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 25.0 | -19.1 | G45T2 | 1, 2, 3 | 12, 10, 3
R/34-3 | SGBM01 | Jan 2 2016 11:45AM | Jan 2 2016 10:10PM | 52.203 | 48.825 |  | 26.534 | 3.378 | 22.291 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 8
R/34-4 | SGBM03 | Dec 28 2015 3:00PM | Dec 29 2015 4:22PM | 52.145 | 48.825 |  | 26.638 | 3.320 | 22.187 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 25.0 | -19.2 | G45T2 | 1, 2, 3 | 10, 8, 7
R/34-5 | SGBM01 | Dec 18 2015 7:15PM | Dec 19 2015 4:48PM | 52.211 | 48.825 |  | 26.502 | 3.386 | 22.323 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 26.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 4
R/34-6 | SGBM20 | Dec 21 2015 3:40PM | Dec 22 2015 4:47PM | 51.953 | 48.825 |  | 26.526 | 3.128 | 22.299 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 9, 7
R/34-7 | SGBM01 | Jan 2 2016 11:00AM | Jan 2 2016 7:15PM | 52.223 | 48.825 |  | 26.324 | 3.398 | 22.501 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 8, 8
R/34-8 | SGBM20 | Dec 30 2015 8:00PM | Dec 31 2015 12:54AM | 52.180 | 48.825 |  | 26.430 | 3.355 | 22.395 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.4 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 2
R/34-9 | SGBM20 | Dec 29 2015 8:00AM | Dec 29 2015 10:35PM | 52.098 | 48.825 |  | 26.355 | 3.273 | 22.470 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 9
R/34-10 | SGBM01 | Dec 18 2015 6:30PM | Dec 19 2015 2:21PM | 52.076 | 48.825 |  | 26.244 | 3.251 | 22.581 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.6 | 25.0 | -100.0 | G45T2 | Pending, 2, 3, 4 | 8, 5, 5, 7
Q/26-1 | SGBM03 | Dec 26 2015 8:00AM | Dec 26 2015 7:26PM | 52.076 | 51.275 |  | 30.159 | 0.801 | 21.116 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 9, 7, 6
Qb/32-1 | SGBM20 | Dec 14 2015 3:13PM | Dec 15 2015 6:13PM | 52.149 | 51.075 |  | 29.020 | 1.074 | 22.055 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 22.5 | -100.0 | G45T2 | 1, 2 | 11.5, 11
Q/33a-1 | SGBM20 | Dec 16 2015 11:25AM | Dec 17 2015 3:06PM | 52.165 | 49.675 |  | 28.574 | 2.490 | 21.101 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 8
Q/33a-2 | SGBM01 | Dec 26 2015 4:00PM | Dec 26 2015 9:15PM | 52.223 | 49.675 |  | 27.400 | 2.548 | 22.275 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 25.0 | -19.3 | G45T2 | 1, 2, 3 | 10, 8, 7
Q/39-1 | SGBM16 | Oct 2 2015 9:00AM | Oct 2 2015 9:48PM | 52.780 | 51.375 |  | 26.375 | 1.405 | 25.000 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.7 | 25.0 | -21.6 | G45T2 | 1, 2, 3 | 11, 11, 3
Pa/32-1 | SGBM20 | Dec 16 2015 1:30PM | Dec 17 2015 1:25PM | 52.077 | 51.075 |  | 28.651 | 1.002 | 22.424 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.4 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
P/33-1 | SGBM20 | Dec 29 2015 7:00PM | Dec 30 2015 6:07PM | 52.135 | 49.725 |  | 29.176 | 2.410 | 20.549 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.8 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
P/33-2 | SGBM01 | Dec 31 2015 3:45PM | Jan 1 2016 1:20AM | 52.080 | 49.725 |  | 29.600 | 2.355 | 20.125 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.4 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
P/33-3 | SGBM20 | Dec 21 2015 5:25PM | Dec 22 2015 6:37PM | 51.868 | 49.725 |  | 29.323 | 2.143 | 20.402 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.7 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 8
P/33-4 | SGBM01 | Dec 26 2015 6:30PM | Dec 28 2015 6:48PM | 51.951 | 49.725 |  | 29.638 | 2.226 | 20.087 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.4 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
P/37-1 | SGBM16 | Jan 8 2016 8:00AM | Jan 8 2016 10:34PM | 52.012 | 49.475 |  | 27.889 | 2.537 | 21.586 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.7 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 7
P/37-2 | SGBM16 | Jan 8 2016 8:30AM | Jan 8 2016 10:34PM | 52.012 | 49.475 |  | 27.889 | 2.537 | 21.586 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.7 | 23.0 | 23.0 | G45T2 | 1, 2, 3 | 8, 8, 7
P/38-1 | SGBM16 | Oct 1 2015 8:00AM | Oct 1 2015 10:39PM | 52.013 | 49.475 |  | 26.319 | 2.538 | 23.156 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 9, 5
P/38-2 | SGBM16 | Jan 7 2016 5:05PM | Jan 8 2016 6:39PM | 51.913 | 49.475 |  | 26.299 | 2.438 | 23.176 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 28.0 | 39.5 | G45T2 | 1, 2, 3, 4 | 8, 9, 8, 3
P/39-1 | SGBM16 | Oct 2 2015 9:00PM | Oct 3 2015 11:01AM | 51.905 | 51.375 |  | 27.375 | 0.530 | 24.000 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 24.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 9, 4
N/37-1 | SGBM08 | Oct 6 2015 12:00PM | Oct 6 2015 6:35PM | 51.911 | 49.575 |  | 28.575 | 2.336 | 21.000 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.2 | 21.0 | -100.0 | G45T2 | 1, 2 | 11, 10
N/37-2 | SGBM20 | Jan 11 2016 8:00AM | Jan 11 2016 2:55PM | 51.894 | 49.575 |  | 28.440 | 2.319 | 21.135 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 15.0 | -100.0 | G45T2 | 1, 2 | 8, 7
M/35-1 | SGBM20 | Nov 7 2015 9:45AM | Nov 7 2015 4:56PM | 51.982 | 51.075 | 9 | 26.440 | 0.907 | 24.635 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.3 | 27.0 | -21.3 | G45T2 | 1, 2, 3, 4, 5 | 6, 6, 6, 6, 3
M/36-1 | SGBM15 | Dec 29 2015 10:51AM | Dec 30 2015 6:40PM | 51.890 | 51.075 |  | 30.844 | 0.815 | 20.231 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.5 | 22.0 | -17.5 | G45T2 | PJ 3725, 3729, PJ 3732 | 8, 7, 7
M/38-1 | SGBM15 | Dec 29 2015 10:20AM | Dec 30 2015 9:45PM | 51.824 | 51.375 |  | 28.292 | 0.449 | 23.083 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.0 | 24.0 | -100.0 | G45T2 | PJ 3740, PJ 3744, PJ 3746 | 9, 7, 8
M/39-1 | SGBM15 | Dec 30 2015 8:00AM | Dec 30 2015 11:25PM | 51.930 | 51.375 |  | 27.168 | 0.555 | 24.207 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.0 | 26.0 | -21.0 | G45T2 | PJ 3748, PJ 3751, PJ 3753 | 8, 10, 8
S/16-1 | SGBM20 | Nov 30 2015 2:15PM | Dec 1 2015 12:43PM | 55.883 | 53.275 | 9, 25.3 | 28.923 | 2.608 | 24.352 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.1 | 27.0 | -21.1 | G45T2 | 1, 2, 3 | 5, 11, 11
S/16-2 | SGBM20 | Nov 26 2015 9:30AM | Nov 26 2015 10:43PM | 55.880 | 53.275 | 9 | 29.256 | 2.605 | 24.019 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
S/20-1 | SGBM20 | Dec 11 2015 4:30PM | Dec 11 2015 11:02PM | 5.452 | 47.375 |  | 5.452 | -41.923 | 41.923 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.3 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 4
S/20-2 | SGBM20 | Dec 12 2015 1:45PM | Dec 12 2015 9:11PM | 54.452 | 47.375 |  | 23.712 | 7.071 | 23.663 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.5 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
S/24-1 | SGBM21 | Dec 1 2015 7:30PM | Dec 2 2015 8:25PM | 49.900 | 48.625 | 9 | 27.264 | 1.275 | 21.361 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.5 | 24.0 | -18.5 | G45T2 | 1, 2, 3 | 7, 7, 10
R/16-1 | SGBM20 | Nov 19 2015 6:20PM | Nov 21 2015 10:37PM | 55.797 | 53.375 | 9 | 26.848 | 2.422 | 26.527 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.0 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
R/16-2 | SGBM03 | Nov 27 2015 4:40PM | Nov 28 2015 5:19PM | 55.768 | 53.375 | 9 | 29.169 | 2.393 | 24.206 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.0 | 25.0 | -21.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
R/19-1 | SGBM03 | Nov 27 2015 5:55PM | Nov 28 2015 1:33PM | 56.010 | 48.925 | 9 | 26.648 | 7.085 | 22.277 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 23.0 | 3.7 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 5
R/19-2 | SGBM20 | Dec 3 2015 3:15PM | Dec 4 2015 11:16AM | 56.013 | 48.925 | 9 | 26.369 | 7.088 | 22.556 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.5 | 23.0 | -19.5 | G45T2 | 1, 2, 3 | 7, 8, 8
R/19-3 | SGBM03 | Dec 16 2015 8:00AM | Dec 16 2015 9:10PM | 55.878 | 48.925 |  | 26.514 | 6.953 | 22.411 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.4 | 26.0 | -19.4 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 2
R/19-4 | SGBM20 | Dec 1 2015 8:00AM | Dec 3 2015 10:56AM | 55.950 | 48.925 | 9 | -30.000 | 7.025 | 78.925 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 68.4 | 24.0 | -68.3 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
R/19-5 | SGBM03 | Dec 14 2015 8:00AM | Dec 14 2015 7:08PM | 55.870 | 48.925 |  | 26.639 | 6.945 | 22.286 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 5
R/19-6 | SGBM03 | Dec 4 2015 4:45PM | Dec 5 2015 2:07PM | 55.821 | 48.925 | 9 | 26.138 | 6.896 | 22.787 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.7 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
R/19-7 | SGBM05 | Nov 13 2015 7:16PM | Nov 14 2015 6:58PM | 55.802 | 48.925 | 9 | 26.202 | -48.925 | 22.723 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.7 | 28.0 | 8.3 | G45T2 | 1, 2, 3, 4 | 7, 8, 8, 5
R/19-8 | SGBM20 | Dec 8 2015 12:00PM | Dec 8 2015 7:20PM | 55.728 | 48.925 | 9 | 26.904 | 6.803 | 22.021 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 24.0 | 4.9 | G45T2 | 1, 2, 3 | 7, 9, 8
R/19-9 | SGBM03 | Dec 3 2015 8:00AM | Dec 4 2015 2:55PM | 55.737 | 48.925 | 9 | 26.827 | 6.812 | 22.098 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 24.0 | -19.1 | G45T2 | 1, 2, 3 | 8, 8, 8
R/19-10 | SGBM20 | Nov 29 2015 11:28AM | Nov 30 2015 5:20PM | 55.777 | 48.925 | 9, 19 | 26.691 | 6.852 | 22.234 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
R/24-1 | SGBM21 | Nov 29 2015 11:00AM | Dec 1 2015 2:10PM | 50.387 | 49.075 | 9 | 26.868 | 1.312 | 22.207 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 22.0 | -19.2 | G45T2 | 1, 2 | 11, 11
Q/15-1 | SGBM20 | Nov 20 2015 6:29PM | Nov 23 2015 1:35PM | 55.000 | 52.925 | 9, 18 | 24.668 | -52.925 | 28.257 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 26.0 | -24.5 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
Q/15-2 | SGBM21 | Dec 2 2015 6:10PM | Dec 3 2015 5:55PM | 55.762 | 52.925 | 9, 13 | 25.852 | 2.837 | 27.073 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 30.0 | -23.4 | G45T2 | 1, 2, 3, 4 | 7, 8, 8, 7
Q/16-1 | SGBM20 | Nov 19 2015 6:20PM | Nov 24 2015 4:42PM | 55.797 | 52.925 | 9, 25 | 27.404 | 2.872 | 25.521 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.1 | 25.0 | -22.1 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 4
Q/16-2 | SGBM03 | Nov 27 2015 5:20PM | Nov 28 2015 9:06PM | 55.709 | 52.925 | 9 | 27.731 | 2.784 | 25.194 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 26.0 | -21.8 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
Q/19a-1 | SGBM20 | Dec 10 2015 3:20PM | Dec 11 2015 4:04PM | 55.908 | 49.775 | 9, 24 | 27.621 | 6.133 | 22.154 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.2 | 29.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 9, 12
Q/19a-2 | SGBM20 | Dec 12 2015 7:05PM | Dec 14 2015 4:40PM | 54.404 | 49.775 |  | 27.708 | 4.629 | 22.067 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.1 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 5
Q/23-1 | SGBM05 | Nov 17 2015 8:30PM | Nov 18 2015 3:07PM | 53.454 | 52.775 | 9 | 29.802 | 0.679 | 22.973 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.9 | 23.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 7
Q/25-1 | SGBM21 | Nov 16 2015 8:00AM | Nov 16 2015 2:09PM | 52.468 | 51.275 |  | 30.029 | 1.193 | 21.246 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.4 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 7, 8, 7
P/15-1 | SGBM20 | Dec 9 2015 4:50PM | Dec 10 2015 11:03AM | 55.653 | 52.925 | 9, 25 | 24.798 | 2.728 | 28.127 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 29.0 | 19.1 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 8
P/15-2 | SGBM20 | Dec 5 2015 5:45PM | Dec 7 2015 2:22PM | 55.610 | 52.925 | 9 | 24.594 | 2.685 | 28.331 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 7, 5
P/16-1 | SGBM20 | Nov 24 2015 10:48AM | Nov 24 2015 8:49PM | 55.696 | 52.925 | 9 | 26.477 | 2.771 | 26.448 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.9 | 26.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 7, 6, 6
P/16-2 | SGBM03 | Dec 2 2015 7:05PM | Dec 3 2015 9:54PM | 55.652 | 52.925 | 9 | -29.600 | 2.727 | 82.525 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 71.5 | 28.0 | -71.5 | G45T2 | 1, 2, 3 | 7, 12, 9
P/20-1 | SGBM20 | Dec 17 2015 8:00AM | Dec 17 2015 8:38PM | 55.716 | 51.125 |  | 27.846 | 4.591 | 23.279 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.2 | 22.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 7, 7
P/20-2 | SGBM03 | Dec 19 2015 8:00AM | Dec 19 2015 7:35PM | 54.034 | 51.125 |  | 27.641 | 2.909 | 23.484 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.3 | 20.0 | -100.0 | G45T2 | 1, 2 | 10, 10
P/20-3 | SGBM03 | Dec 14 2015 6:05PM | Dec 15 2015 2:13PM | 55.730 | 51.125 |  | 27.631 | 4.605 | 23.494 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.3 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 6, 6
P/20-4 | SGBM20 | Dec 21 2015 8:00AM | Dec 21 2015 3:01PM | 53.869 | 51.125 |  | 27.828 | 2.744 | 23.297 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.2 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
Pa/21-1 | SGBM05 | Nov 12 2015 3:30PM | Nov 13 2015 5:45PM | 53.800 | 52.375 | 9 | 28.105 | 1.425 | 24.270 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.0 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
P/23-1 | SGBM05 | Nov 9 2015 2:00PM | Nov 11 2015 4:56PM | 53.428 | 52.475 | 9 | 27.428 | 0.953 | 25.047 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.7 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
N/16-1 | SGBM20 | Nov 24 2015 6:00PM | Nov 25 2015 8:30PM | 55.841 | 52.925 | 9 | 25.461 | 2.916 | 27.464 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.8 | 25.0 | -23.8 | G45T2 | 1, 2, 3, 4 | 6, 8, 6, 5
N/16-2 | SGBM20 | Nov 30 2015 6:03PM | Dec 1 2015 7:10PM | 55.811 | 52.925 | 9, 20 | 25.720 | 2.886 | 27.205 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.6 | 30.0 | -23.6 | G45T2 | 1, 2, 3 | 10, 10, 10
N/21-1 | SGBM21 | Nov 18 2015 6:50PM | Nov 19 2015 7:03PM | 53.412 | 52.775 | 9 | 27.645 | 0.637 | 25.130 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 24.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 6, 6, 6
N/22-1 | SGBM05 | Nov 15 2015 10:30AM | Nov 16 2015 7:22PM | 53.367 | 52.775 | 9 | 27.289 | 0.592 | 25.486 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.1 | 25.0 | -22.1 | G45T2 | 1, 2, 3, 4 | 7, 6, 6, 6
K/53-1 | SGBM18 | Sep 22 2015 5:00PM | Sep 23 2015 4:30PM | 52.148 | 51.025 |  | 13.973 | 1.123 | 37.052 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 3, 11, 11, 11
K/54-1 | SGBM17 | Sep 26 2015 8:00AM | Sep 26 2015 7:00PM | 52.116 | 51.025 |  | 13.926 | 1.091 | 37.099 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 12, 12, 10, 7
K/55-1 | SGBM15 | Oct 12 2015 9:00PM | Oct 13 2015 1:27PM | 52.198 | 49.775 |  | 12.720 | 2.423 | 37.055 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 9, 9, 10
K/55-2 | SGBM23 | Oct 1 2015 8:30AM | Oct 2 2015 12:42AM | 51.973 | 49.775 |  | 12.743 | 2.198 | 37.032 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 8, 8, 8, 5
K/55-3 | SGBM15 | Oct 2 2015 7:40PM | Oct 3 2015 9:09PM | 51.954 | 49.775 |  | 12.734 | 2.179 | 37.041 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 10, 10, 12, 7
K/60-1 | SGBM15 | Sep 15 2015 8:00AM | Sep 15 2015 8:22PM | 52.028 | 49.475 |  | 9.389 | 2.553 | 40.086 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 4, 11, 5
K/60-2 | SGBM15 | Oct 8 2015 9:00AM | Oct 9 2015 4:39PM | 52.049 | 49.475 |  | 9.376 | 2.574 | 40.099 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 12, 10, 10
K/60-3 | SGBM15 | Oct 6 2015 1:00PM | Oct 7 2015 11:25AM | 51.837 | 49.475 |  | 9.401 | 2.362 | 40.074 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 9, 11, 10
K/60-4 | SGBM17 | Oct 4 2015 9:00PM | Oct 5 2015 2:07PM | 51.837 | 49.475 |  | 9.401 | 2.362 | 40.074 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 43.0 | 23.9 | G45T2 | 1, 2, 3, 4, 5 | 8, 11, 6, 10, 8
J/53-1 | SGBM18 | Sep 26 2015 8:00AM | Sep 26 2015 6:46PM | 52.080 | 51.025 |  | 12.996 | 1.055 | 38.029 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.9 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 10, 8
J/54-1 | SGBM18 | Sep 21 2015 8:30AM | Sep 21 2015 7:20PM | 51.820 | 51.025 |  | 10.681 | 0.795 | 40.344 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.9 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 11, 9, 8, 4
J/55-1 | SGBM17 | Oct 2 2015 8:10AM | Oct 3 2015 12:02AM | 52.056 | 49.375 |  | 10.300 | 2.681 | 39.075 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.8 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 11, 11, 11, 7
J/55-2 | SGBM15 | Oct 7 2015 8:10AM | Oct 7 2015 9:00PM | 51.957 | 49.375 |  | 10.365 | 2.582 | 39.010 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.8 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 11, 9, 10, 2
J/55-3 | SGBM23 | Oct 5 2015 12:30PM | Oct 6 2015 12:17AM | 51.948 | 49.375 |  | 10.368 | 2.573 | 39.007 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.8 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 10, 10, 11
J/55-4 | SGBM15 | Oct 9 2015 8:00AM | Oct 9 2015 9:45PM | 51.900 | 49.375 |  | 10.087 | 2.525 | 39.288 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.0 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 10, 11, 12, 5
J/56-1 | SGBM15 | Oct 16 2015 8:10AM | Oct 16 2015 4:50PM | 51.980 | 49.075 |  | 8.872 | 2.905 | 40.203 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.8 | 40.5 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 8, 11.5, 11, 1
J/56-2 | SGBM17 | Oct 11 2015 6:30PM | Oct 13 2015 11:09AM | 51.892 | 49.075 |  | 9.012 | 2.817 | 40.063 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 9
J/56-3 | SGBM23 | Oct 19 2015 8:30AM | Oct 19 2015 9:41PM | 51.976 | 49.075 |  | 8.211 | 2.901 | 40.864 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.4 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 10, 11
J/57-1 | SGBM17 | Oct 16 2015 9:00PM | Oct 17 2015 3:24PM | 52.017 | 48.775 |  | 8.404 | 3.242 | 40.371 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.0 | 44.0 | 25.9 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
J/57-2 | SGBM17 | Oct 23 2015 8:00AM | Oct 23 2015 4:36PM | 52.101 | 48.775 |  | 8.601 | 3.326 | 40.174 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.8 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 9, 10, 12
J/57-3 | SGBM23 | Oct 21 2015 8:40AM | Oct 21 2015 8:18PM | 52.030 | 48.775 |  | 8.427 | 3.255 | 40.348 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.9 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 9
J/57-4 | SGBM17 | Oct 24 2015 11:00AM | Oct 24 2015 8:34PM | 51.966 | 48.775 |  | 8.174 | 3.191 | 40.601 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.2 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 5, 10, 11, 11, 8
J/58-1 | SGBM17 | Oct 15 2015 8:20PM | Oct 16 2015 8:35PM | 52.000 | 49.475 |  | 8.264 | 2.525 | 41.211 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.7 | 50.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 10, 10, 10
J/58-2 | SGBM23 | Oct 17 2015 6:20PM | Oct 18 2015 12:35PM | 51.986 | 49.475 |  | 8.287 | 2.511 | 41.188 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.7 | 42.0 | 17.7 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 3, 7, 7, 4, 7, 7, 7
J/58-3 | SGBM17 | Oct 13 2015 8:00AM | Oct 13 2015 2:59PM | 51.942 | 49.475 |  | 8.395 | 2.467 | 41.080 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.6 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 9, 9, 9, 9, 6, 6
J/58-4 | SGBM23 | Oct 20 2015 6:30PM | Oct 21 2015 4:18PM | 51.970 | 49.475 |  | 8.050 | 2.495 | 41.425 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.9 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
J/59-1 | SGBM17 | Oct 19 2015 9:00PM | Oct 20 2015 1:30PM | 51.909 | 49.775 |  | 7.468 | 2.134 | 42.307 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.6 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
J/59-2 | SGBM15 | Oct 14 2015 6:00PM | Oct 15 2015 12:33PM | 51.890 | 49.775 |  | 7.590 | 2.115 | 42.185 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 42.0 | -36.5 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 4, 9, 8, 4, 6, 9, 2
J/59-3 | SGBM23 | Oct 21 2015 6:50PM | Oct 22 2015 11:31AM | 51.906 | 49.775 |  | 7.601 | 2.131 | 42.174 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 12, 11
J/60-1 | SGBM15 | Oct 16 2015 8:00AM | Oct 16 2015 6:45PM | 51.904 | 49.775 |  | 6.632 | 2.129 | 43.143 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.4 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
J/60-2 | SGBM15 | Oct 11 2015 7:00PM | Oct 12 2015 12:11PM | 51.930 | 49.775 |  | 6.687 | 2.155 | 43.088 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 2, 11, 11, 11.5, 11.5
J/60-3 | SGBM17 | Oct 17 2015 7:50PM | Oct 19 2015 10:40AM | 51.928 | 49.775 |  | 6.157 | 2.153 | 43.618 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.8 | 46.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 7, 7, 7, 7, 7, 7, 4
J/62-1 | SGBM15 | Oct 29 2015 10:20AM | Oct 29 2015 5:19PM | 51.990 | 51.375 |  | 8.250 | 0.615 | 43.125 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 41.5 | -100.0 | G45T2 | 1, 2, 3, 4 | 11.5, 10, 10, 10
J/63a-1 | SGBM23 | Dec 14 2015 4:03PM | Dec 15 2015 4:09PM | 52.026 | 51.275 |  | 9.115 | 0.751 | 42.160 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 44.0 | 20.5 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 8, 8, 7
H/54-1 | SGBM17 | Oct 22 2015 8:30AM | Oct 22 2015 7:17PM | 51.910 | 49.775 |  | 8.978 | 2.135 | 40.797 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.3 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 11, 11, 10
H/54-2 | SGBM23 | Oct 20 2015 8:20AM | Oct 20 2015 7:55PM | 51.910 | 49.775 |  | 9.754 | 2.135 | 40.021 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 12
H/54-3 | SGBM17 | Oct 25 2015 6:50PM | Oct 26 2015 4:44PM | 51.850 | 49.775 |  | 9.282 | 2.075 | 40.493 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.1 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 10, 10, 10, 7
H/55-1 | SGBM23 | Oct 20 2015 11:25AM | Oct 20 2015 10:00PM | 51.765 | 49.675 |  | 8.215 | 2.090 | 41.460 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.9 | 43.0 | 19.8 | G45T2 | 1, 2, 3, 4, 5 | 9, 8, 9, 9, 8
H/55-2 | SGBM17 | Oct 23 2015 10:00AM | Oct 23 2015 7:45PM | 51.850 | 49.675 |  | 8.417 | 2.175 | 41.258 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.7 | 46.0 | 28.7 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 10, 12, 2
H/55-3 | SGBM15 | Oct 15 2015 8:00AM | Oct 15 2015 6:34PM | 51.815 | 49.675 |  | 8.638 | 2.140 | 41.037 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.5 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 10, 10, 10, 4
H/62-1 | SGBM15 | Oct 26 2015 6:20PM | Oct 27 2015 11:50AM | 51.890 | 51.375 |  | 7.212 | 0.515 | 44.163 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.2 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 10, 10, 5
G/54-1 | SGBM23 | Oct 12 2015 6:00PM | Oct 13 2015 7:12PM | 51.883 | 49.775 |  | 8.738 | 2.108 | 41.037 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.5 | 48.0 | 35.1 | G45T2 | 1, 2, 3, 4, 5, 6 | 9, 9, 9, 9, 8, 4
G/54-2 | SGBM15 | Oct 9 2015 7:20PM | Oct 10 2015 4:47PM | 51.820 | 49.775 |  | 8.327 | 2.045 | 41.448 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.9 | 52.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 10, 11, 11, 11
G/54-3 | SGBM23 | Oct 17 2015 8:35AM | Oct 17 2015 2:06PM | 51.683 | 49.775 |  | 8.595 | 1.908 | 41.180 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.7 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 10, 1
G/55-1 | SGBM17 | Oct 23 2015 6:45PM | Oct 24 2015 1:10PM | 51.782 | 49.675 |  | 7.605 | 2.107 | 42.070 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.4 | 44.0 | 20.8 | G45T2 | 1, 2, 3, 4, 5, 6 | 3, 9, 9, 9, 10, 4
G/55-2 | SGBM15 | Oct 19 2015 7:00PM | Oct 20 2015 12:23PM | 51.765 | 49.675 |  | 7.552 | 2.090 | 42.123 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
G/60-1 | SGBM23 | Oct 2 2015 11:00AM | Oct 2 2015 11:00PM | 51.895 | 49.675 |  | 4.630 | 2.220 | 45.045 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 45.0 | -39.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 9, 11, 11, 3
G/60-2 | SGBM23 | Oct 7 2015 8:00AM | Oct 7 2015 8:02PM | 51.891 | 49.675 |  | 4.672 | 2.216 | 45.003 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 11, 8, 9, 11
G/60-3 | SGBM23 | Sep 30 2015 6:00PM | Oct 1 2015 11:35AM | 51.862 | 49.675 |  | 4.629 | 2.187 | 45.046 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 11, 6, 11, 10
G/62-1 | SGBM15 | Oct 29 2015 2:00PM | Oct 29 2015 11:09PM | 51.733 | 51.275 |  | 6.259 | 0.458 | 45.016 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 10, 11.5, 11.5
G/63a-1 | SGBM17 | Nov 2 2015 12:50PM | Nov 3 2015 5:47PM | 51.960 | 51.275 | 9 | 8.787 | 0.685 | 42.488 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.8 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 9, 7, 7, 7, 7, 7
F/56-1 | SGBM15 | Sep 28 2015 8:00AM | Sep 29 2015 1:24PM | 52.941 | 49.775 |  | 5.739 | 3.166 | 44.036 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.1 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
F/56-2 | SGBM23 | Sep 30 2015 8:10AM | Oct 1 2015 3:01AM | 51.868 | 49.775 |  | 5.702 | 2.093 | 44.073 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.2 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 12, 11, 11, 11
F/56-3 | SGBM19 | Oct 8 2015 9:00PM | Oct 9 2015 5:48PM | 51.911 | 49.775 |  | 5.729 | 2.136 | 44.046 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.1 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 12, 11, 10, 12, 2
F/57-1 | SGBM22 | Oct 11 2015 7:00PM | Oct 12 2015 5:01PM | 51.879 | 49.775 |  | 4.200 | 2.104 | 45.575 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.5 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 2, 9, 9, 10, 10, 5
F/57-2 | SGBM18 | Oct 1 2015 1:20PM | Oct 1 2015 10:49PM | 52.010 | 49.775 |  | 4.751 | 2.235 | 45.024 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 5, 11, 10, 10, 11
F/57-3 | SGBM23 | Oct 9 2015 4:50PM | Oct 10 2015 2:00PM | 51.910 | 49.775 |  | 4.462 | 2.135 | 45.313 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.2 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 9, 9, 11, 9, 9
F/58-1 | SGBM15 | Sep 25 2015 11:00AM | Sep 25 2015 9:22PM | 51.947 | 49.775 |  | 4.677 | 2.172 | 45.098 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.1 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 9, 11, 7, 11
F/58-2 | SGBM17 | Oct 7 2015 8:00AM | Oct 7 2015 11:49PM | 51.930 | 49.775 |  | 4.721 | 2.155 | 45.054 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 9, 10, 6
F/58-3 | SGBM18 | Sep 30 2015 8:00AM | Sep 30 2015 7:25PM | 51.906 | 49.775 |  | 4.692 | 2.131 | 45.083 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 39.0 | 40.0 | -39.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 10
F/61-1 | SGBM15 | Oct 16 2015 7:00PM | Oct 17 2015 7:03PM | 51.895 | 50.775 |  | 6.603 | 1.120 | 44.172 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.3 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 5 | 4, 11, 11, 10, 10, 3
F/63a-1 | SGBM17 | Nov 5 2015 7:35PM | Nov 6 2015 7:43PM | 51.858 | 51.275 | 9, 16, 19 | 9.098 | 0.583 | 42.177 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 50.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 7, 7, 7, 9, 6, 7, 7
E/52-1 | SGBM23 | Oct 28 2015 9:10AM | Oct 28 2015 7:40PM | 51.950 | 51.275 |  | 6.922 | 0.675 | 44.353 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.4 | 48.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 7, 10, 10, 11
E/55-1 | SGBM17 | Oct 1 2015 9:00AM | Oct 2 2015 2:45PM | 51.888 | 49.475 |  | 6.448 | 2.413 | 43.027 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 42.0 | 4.7 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 9
E/55-2 | SGBM17 | Oct 7 2015 8:10AM | Oct 8 2015 11:43AM | 51.873 | 49.475 |  | 6.371 | 2.398 | 43.104 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 50.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 10, 10, 10
E/55-3 | SGBM17 | Oct 9 2015 7:00PM | Oct 10 2015 11:10AM | 51.897 | 49.475 |  | 6.398 | 2.422 | 43.077 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 37.3 | 49.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 10, 10, 9, 9, 3
E/55-4 | SGBM23 | Oct 4 2015 9:00PM | Oct 5 2015 11:16PM | 51.937 | 49.475 |  | 9.414 | 2.462 | 40.061 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.7 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 11, 11, 8, 5
E/60-1 | SGBM18 | Oct 1 2015 10:10AM | Oct 2 2015 5:33PM | 51.918 | 49.475 |  | 7.409 | 2.443 | 42.066 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.4 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 11, 9, 11, 9
E/60-2 | SGBM18 | Oct 8 2015 4:45PM | Oct 9 2015 11:39AM | 51.939 | 49.475 |  | 7.277 | 2.464 | 42.198 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 44.0 | 20.4 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 3, 10, 9
E/60-3 | SGBM18 | Oct 6 2015 10:10AM | Oct 7 2015 4:21PM | 51.919 | 49.475 |  | 7.473 | 2.444 | 42.002 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.4 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11, 11, 11, 11, 3
E/60-4 | SGBM18 | Oct 4 2015 9:00PM | Oct 5 2015 6:15PM | 51.929 | 49.475 |  | 7.463 | 2.454 | 42.012 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.4 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 6, 10, 10
D/52-1 | SGBM23 | Sep 26 2015 9:00PM | Sep 27 2015 4:33PM | 51.800 | 51.275 |  | 6.737 | 0.525 | 44.538 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.6 | 44.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 11
D/57-1 | SGBM15 | Oct 20 2015 6:00PM | Oct 21 2015 11:30AM | 51.857 | 49.775 |  | 7.670 | 2.082 | 42.105 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 7, 7, 7, 7, 7, 7, 5
D/57-2 | SGBM15 | Oct 23 2015 9:12AM | Oct 23 2015 5:13PM | 51.880 | 49.775 |  | 7.695 | 2.105 | 42.080 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.4 | 47.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 9, 9, 9
D/57-3 | SGBM15 | Oct 25 2015 5:10PM | Oct 26 2015 12:24PM | 51.875 | 49.775 |  | 7.508 | 2.100 | 42.267 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.6 | 45.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 11.5, 11, 11.5, 6, 5
D/58-1 | SGBM15 | Oct 17 2015 7:00PM | Oct 19 2015 6:15PM | 51.790 | 49.775 |  | 7.672 | 2.015 | 42.103 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.5 | 43.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 11, 11, 11
D/58-2 | SGBM15 | Oct 22 2015 8:00PM | Oct 23 2015 11:05AM | 51.920 | 49.775 |  | 7.700 | 2.145 | 42.075 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.4 | 45.0 | -36.4 | G45T2 | 1, 2, 3, 4, 5, 6, 7 | 7, 7, 7, 6, 6, 5, 7
D/58-3 | SGBM15 | Oct 21 2015 8:00AM | Oct 21 2015 6:30PM | 51.770 | 49.775 |  | 7.300 | 1.995 | 42.475 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 36.8 | 46.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 12, 11.5, 11.5
AA/57-1 | SGBM05 | Jan 4 2016 2:30PM | Jan 5 2016 3:55PM | 49.567 | 48.725 |  | 14.159 | 0.842 | 34.566 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 9 | 29.9 | 33.0 | -29.9 | G45T2 | C4800145526, C480014527, C480014532 | 11, 11, 11
L/52-1 | SGBM23 | Oct 24 2015 8:00AM | Oct 24 2015 3:36PM | 52.010 | 51.075 |  | 14.089 | 0.935 | 36.986 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.0 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 11, 11, 9
L/36-1 | SGBM15 | Jan 2 2016 4:50PM | Jan 4 2016 4:05PM | 51.964 | 51.075 |  | 30.869 | 0.889 | 20.206 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 17.5 | 22.0 | -17.5 | G45T2 | PJ 3912, PJ 3915, PJ 3917 | 8, 7, 7
L/37-1 | SGBM15 | Dec 31 2015 10:45AM | Jan 2 2016 2:25PM | 51.909 | 51.075 |  | 28.790 | 0.834 | 22.285 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.3 | 25.0 | -19.3 | G45T2 | PJ 3848, PJ 3850, PJ 3854 | 8, 9, 8
L/38-1 | SGBM15 | Jan 4 2016 2:00PM | Jan 5 2016 2:20PM | 51.953 | 49.375 |  | 25.927 | 2.578 | 23.448 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.3 | 36.0 | -20.3 | G45T2 | PJ 3968, PJ 3969, PJ 3970 | 18, 8, 10
L/38-2 | SGBM15 | Dec 31 2015 10:00AM | Jan 2 2016 8:50PM | 52.042 | 49.375 |  | 26.103 | 2.667 | 23.272 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.2 | 25.0 | -100.0 | G45T2 | 1, 2, 3 | 8, 8, 9
L/39-1 | SGBM23 | Jan 4 2016 8:53AM | Jan 4 2016 5:00PM | 52.035 | 49.075 |  | 21.049 | 2.960 | 28.026 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 30.0 | -24.3 | G45T2 | PJ 3918, PJ 3920, PJ 3921, PJ 3923 | 8, 8, 7, 7
L/39-2 | SGBM15 | Dec 31 2015 9:25AM | Jan 2 2016 6:35PM | 51.947 | 49.075 |  | 23.899 | 2.872 | 25.176 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 27.0 | -21.8 | G45T2 | PJ 3868, PJ 3869, PJ 3873 | 8, 10, 9
L/40-1 | SGBM15 | Jan 5 2016 9:40AM | Jan 5 2016 6:00PM | 51.990 | 49.075 |  | 22.753 | 2.915 | 26.322 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.8 | 28.0 | -100.0 | G45T2 | 1, 2, 3 | 10, 10, 8
L/40-2 | SGBM15 | Jan 2 2016 4:00PM | Jan 4 2016 7:00PM | 51.890 | 49.075 |  | 22.880 | 2.815 | 26.195 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.7 | 29.0 | -22.7 | G45T2 | PJ 3925, PJ 3927, PJ 3928, PJ 3931 | 8, 7, 7, 7
L/41-1 | SGBM15 | Jan 5 2016 10:10AM | Jan 5 2016 8:55PM | 51.880 | 49.075 |  | 20.501 | 2.805 | 28.574 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
L/41-2 | SGBM15 | Jan 2 2016 3:15PM | Jan 4 2016 9:00PM | 51.915 | 49.075 |  | 20.385 | 2.840 | 28.690 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.8 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 7, 8, 8
L/42-1 | SGBM15 | Jan 5 2016 10:40AM | Jan 6 2016 3:17PM | 51.860 | 49.075 |  | 19.676 | 2.785 | 29.399 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.5 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
L/42-2 | SGBM15 | Jan 9 2016 9:10AM | Jan 10 2016 12:25AM | 51.810 | 49.075 |  | 19.710 | 2.735 | 29.365 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.4 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
L/43-1 | SGBM15 | Jan 5 2016 11:05AM | Jan 6 2016 9:10PM | 51.870 | 49.075 |  | 18.689 | 2.795 | 30.386 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.3 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
L/43-2 | SGBM15 | Jan 9 2016 10:55AM | Jan 9 2016 7:45PM | 51.857 | 49.075 |  | 18.853 | 2.782 | 30.222 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.2 | 33.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 11
L/44-1 | SGBM15 | Jan 7 2016 8:20AM | Jan 7 2016 9:25PM | 51.850 | 49.075 |  | 18.546 | 2.775 | 30.529 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.4 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
L/44-2 | SGBM23 | Jan 4 2016 3:00PM | Jan 5 2016 10:55AM | 51.787 | 49.075 |  | 18.674 | 2.712 | 30.401 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.3 | 32.0 | -26.3 | G45T2 | PJ 3956, PJ 3957, PJ 3960, PJ 3963 | 9, 8, 8, 7
L/45-1 | SGBM15 | Jan 7 2016 9:00AM | Jan 8 2016 9:33PM | 51.652 | 49.075 |  | 16.034 | 2.577 | 33.041 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.6 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
L/45-2 | SGBM23 | Jan 4 2016 3:50PM | Jan 5 2016 5:25PM | 51.760 | 49.075 |  | 16.271 | 2.685 | 32.804 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.4 | 34.0 | -28.4 | G45T2 | PJ 3980, PJ 3981, PJ 3982, PJ 3986 | 7, 10, 10, 7
L/46-1 | SGBM23 | Jan 9 2016 9:55AM | Jan 11 2016 4:40PM | 51.731 | 49.075 |  | 15.159 | 2.656 | 33.916 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.4 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 10, 8
L/46-2 | SGBM23 | Jan 5 2016 5:50PM | Jan 6 2016 10:50PM | 51.750 | 49.075 |  | 15.054 | 2.675 | 34.021 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.5 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 8, 10, 8
L/47-1 | SGBM23 | Jan 5 2016 2:35PM | Jan 6 2016 5:19PM | 51.650 | 49.075 |  | 15.889 | -49.075 | 33.186 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.7 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 10, 9, 8
L/47-2 | SGBM23 | Jan 5 2016 1:50PM | Jan 6 2016 5:19PM | 51.650 | 49.075 |  | 15.889 | 2.575 | 33.186 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.7 | 35.0 | 21.8 | G45T2 | 1, 2, 3, 4 | 8, 10, 9, 8
L/48-1 | SGBM15 | Dec 15 2015 10:48AM | Dec 15 2015 8:48PM | 51.590 | 49.075 |  | 14.974 | 2.515 | 34.101 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.5 | 37.0 | 25.3 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 7, 8, 7
L/48-2 | SGBM15 | Dec 16 2015 10:25AM | Dec 17 2015 5:15PM | 51.652 | 49.075 |  | 14.661 | 2.577 | 34.414 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.8 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 7
L/49-1 | SGBM23 | Dec 31 2015 8:52AM | Jan 2 2016 4:53PM | 51.845 | 49.075 |  | 14.530 | 2.770 | 34.545 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.9 | 37.0 | -29.9 | G45T2 | PJ 3860, PJ 3862, PJ 3863, PJ 3865 | 10, 9, 8, 10
L/49-2 | SGBM15 | Dec 16 2015 9:57AM | Dec 17 2015 8:27PM | 51.900 | 49.075 |  | 14.742 | 2.825 | 34.333 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.7 | 37.0 | 24.4 | G45T2 | 1, 2, 3, 4 | 10, 7, 10, 10
L/50-1 | SGBM15 | Dec 12 2015 5:00PM | Dec 14 2015 10:10PM | 51.980 | 51.075 |  | 15.508 | 0.905 | 35.567 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.8 | 37.0 | 6.2 | G45T2 | 1, 2, 3, 4 | 10, 9, 11, 7
L/51-1 | SGBM02 | Dec 2 2015 3:46PM | Dec 4 2015 3:39AM | 51.945 | 51.075 | 9 | 14.921 | 0.870 | 36.154 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.3 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 7
K/38-1 | SGBM23 | Nov 25 2015 8:05PM | Nov 26 2015 11:25PM | 51.911 | 49.675 | 9 | 25.621 | 2.236 | 24.054 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.8 | 27.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 6
K/38-2 | SGBM23 | Nov 30 2015 1:35PM | Nov 30 2015 1:48AM | 51.950 | 49.675 | 9 | 20.904 | 2.275 | 28.771 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.9 | 30.0 | 5.1 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
K/40-1 | SGBM15 | Dec 18 2015 9:15AM | Dec 18 2015 6:30PM | 51.862 | 49.675 |  | 22.639 | 2.187 | 27.036 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 30.0 | 28.1 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
K/40-2 | SGBM15 | Dec 22 2015 5:35PM | Dec 23 2015 2:22AM | 51.890 | 49.675 |  | 22.528 | 2.215 | 27.147 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.5 | 27.0 | 27.6 | G45T2 | 1, 2, 3 | 10, 10, 7
K/48-1 | SGBM15 | Dec 16 2015 10:49AM | Dec 16 2015 10:05PM | 51.340 | 49.675 |  | 16.655 | 1.665 | 33.020 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.6 | 35.0 | 22.4 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
K/48-2 | SGBM15 | Dec 12 2015 6:05PM | Dec 15 2015 4:40AM | 51.426 | 49.675 |  | 16.417 | 1.751 | 33.258 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.8 | 35.5 | 6.7 | G45T2 | 1, 2, 3, 4 | 11.5, 9, 11.5, 3.5
K/49-1 | SGBM15 | Dec 12 2015 5:20PM | Dec 15 2015 12:40AM | 51.620 | 49.675 |  | 15.393 | 1.945 | 34.282 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.7 | 37.5 | 26.3 | G45T2 | 1, 2, 3, 4 | 4, 11.5, 11, 11
K/49-2 | SGBM23 | Dec 8 2015 8:10PM | Dec 10 2015 6:05PM | 51.860 | 49.675 | 9 | 15.670 | 2.185 | 34.005 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.4 | 37.0 | -100.0 | G45T2 | PJ 2899, PJ 2900, PJ 2902, PJ 2904, PJ 2907 | 7, 8, 7, 8, 7
K/51-1 | SGBM15 | Nov 12 2015 11:20AM | Nov 13 2015 3:03PM | 52.041 | 51.275 | 9 | 15.143 | 0.766 | 36.132 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.3 | 42.0 | -31.3 | G45T2 | pj1532, pj1533, pj1534, pj1535, pj1536, pj1542 | 8, 8, 8, 7, 7, 4
J/38-1 | SGBM23 | Nov 25 2015 8:25PM | Nov 26 2015 9:06PM | 51.970 | 49.675 | 9 | 24.620 | 2.295 | 25.055 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.7 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
J/38-2 | SGBM23 | Nov 30 2015 2:45PM | Dec 1 2015 10:41PM | 52.015 | 49.675 | 9 | 24.300 | 2.340 | 25.375 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.0 | 28.0 | 27.4 | G45T2 | 1, 2, 3 | 8, 10, 10
J/41-1 | SGBM23 | Nov 24 2015 5:58PM | Nov 25 2015 1:50PM | 51.808 | 49.775 | 9, 20 | 16.491 | 2.033 | 33.284 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.8 | 32.0 | -28.8 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 6.5, 5.5, 6
J/41-2 | SGBM23 | Nov 19 2015 11:00AM | Nov 19 2015 7:27PM | 51.875 | 49.775 | 9 | 19.840 | -49.775 | 29.935 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.9 | 32.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 10, 11
J/41-3 | SGBM23 | Nov 15 2015 2:00PM | Nov 16 2015 12:35PM | 51.885 | 49.775 | 8 | 20.109 | 2.110 | 29.666 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.7 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 6, 7, 7, 6
J/46-1 | SGBM23 | Dec 19 2015 7:05PM | Dec 22 2015 2:09AM | 51.595 | 49.375 |  | 13.523 | 2.220 | 35.852 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.0 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 11, 10, 10
J/46-2 | SGBM23 | Dec 23 2015 1:30PM | Dec 24 2015 3:12AM | 51.583 | 49.375 |  | 14.031 | 2.208 | 35.344 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 35.0 | -30.6 | G45T2 | C520124376, C52014377, C520124380, C520124381, C520124382 | 7, 6, 10, 3, 9
J/46-3 | SGBM23 | Dec 10 2015 4:17PM | Dec 11 2015 4:30PM | 51.570 | 49.375 |  | 14.003 | 2.195 | 35.372 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 37.0 | 20.8 | G45T2 | PJ 2953, PJ 2956, PJ 2957, PJ 2958, PJ 2961 | 7, 8, 7, 7, 8
J/46-4 | SGBM23 | Dec 29 2015 2:35PM | Dec 30 2015 7:42PM | 51.580 | 49.375 |  | 14.206 | 2.205 | 35.169 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.5 | 38.0 | -8.1 | G45T2 | PJ 3731, PJ 3734, PJ 3739, PJ 3742 | 10, 10, 8, 10
J/49-1 | SGBM15 | Nov 25 2015 3:27PM | Nov 26 2015 7:12PM | 51.808 | 49.675 | 9 | 15.170 | 2.133 | 34.505 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.9 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 8, 7, 7
J/49-2 | SGBM15 | Nov 30 2015 12:40PM | Dec 1 2015 8:53PM | 51.780 | 49.675 | 9 | 15.433 | 2.105 | 34.242 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.7 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 4
H/38-1 | SGBM23 | Nov 30 2015 1:47PM | Dec 1 2015 12:22AM | 52.020 | 49.675 | 9 | 21.015 | 2.345 | 28.660 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.8 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 6, 6, 6
H/38-2 | SGBM23 | Dec 2 2015 8:16PM | Dec 3 2015 9:28PM | 52.014 | 49.675 | 10 | 22.605 | 2.339 | 27.070 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 31.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 10, 10
H/41-1 | SGBM23 | Nov 4 2015 4:50PM | Nov 5 2015 11:17AM | 51.980 | 49.775 | 9 | 19.012 | 2.205 | 30.763 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.6 | 33.5 | -100.0 | G45T2 | C480011354, C480011355, C480011359 | 11, 11, 11.5
H/41-2 | SGBM23 | Nov 19 2015 11:30AM | Nov 20 2015 4:03PM | 51.821 | 49.775 | 9 | 19.085 | 2.046 | 30.690 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.6 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 7, 6, 6
H/41-3 | SGBM23 | Nov 22 2015 1:30PM | Nov 23 2015 5:14PM | 51.900 | 49.775 | 9 | 19.550 | 2.125 | 30.225 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.2 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 6, 6, 6
H/46-1 | SGBM23 | Dec 19 2015 7:30PM | Dec 22 2015 12:06AM | 51.430 | 49.475 |  | 12.234 | 1.955 | 37.241 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.3 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 11, 10, 10
H/46-2 | SGBM23 | Dec 31 2015 8:15AM | Jan 2 2016 12:40PM | 51.424 | 49.475 |  | 11.782 | 1.949 | 37.693 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.6 | 40.0 | 7.3 | G45T2 | PJ 3841, PJ 3842, PJ3843, PJ 3845, PJ 3847 | 8, 10, 8, 7, 7
H/46-3 | SGBM23 | Dec 17 2015 11:16AM | Dec 18 2015 2:24AM | 51.464 | 49.475 |  | 11.901 | 1.989 | 37.574 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.5 | 38.0 | 19.9 | G45T2 | 1, 2, 3, 4, 5 | 8, 9, 7, 8, 6
H/46-4 | SGBM15 | Dec 28 2015 5:30PM | Dec 29 2015 2:48PM | 51.379 | 49.475 |  | 12.013 | 1.904 | 37.462 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.4 | 40.0 | 23.3 | G45T2 | PJ 3653, PJ 3655, PJ 3656, PJ 3658, PJ 3660 | 7, 7, 10, 8, 8
H/47-1 | SGBM23 | Dec 12 2015 6:29PM | Dec 15 2015 6:15AM | 51.331 | 49.675 |  | 14.342 | 1.656 | 35.333 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 38.0 | 24.2 | G45T2 | 1, 2, 3, 4 | 8, 11, 9, 10
H/47-2 | SGBM15 | Dec 4 2015 8:08PM | Dec 5 2015 6:48PM | 51.321 | 49.675 | 9 | 14.478 | 1.646 | 35.197 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.5 | 36.0 | -100.0 | G45T2 | C480012727, C480012728, C480012730, C480012732 | 6, 10, 10, 10
H/49-1 | SGBM15 | Nov 26 2015 10:00AM | Nov 27 2015 8:10PM | 51.747 | 49.675 | 9 | 14.492 | -49.675 | 35.183 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.5 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 7, 8
H/49-2 | SGBM15 | Nov 30 2015 11:05AM | Dec 2 2015 7:46PM | 51.788 | 49.675 | 9 | 14.697 | 2.113 | 34.978 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.3 | 39.0 | 28.8 | G45T2 | 1, 2, 3, 4, 5 | 7, 11, 7, 7, 7
G/38-1 | SGBM23 | Nov 24 2015 6:24PM | Nov 25 2015 9:25PM | 52.082 | 49.675 | 9 | 21.945 | 2.407 | 27.730 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.0 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 8, 8, 7
G/38-2 | SGBM23 | Nov 27 2015 5:05PM | Nov 28 2015 8:11PM | 52.010 | 49.675 | 9 | -31.000 | 2.335 | 80.675 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 69.9 | 32.0 | -69.9 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 6, 6, 6
G/39-1 | SGBM23 | Nov 24 2015 6:48PM | Nov 25 2015 4:58PM | 51.983 | 49.675 | 9 | 19.602 | 2.308 | 30.073 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 33.0 | 7.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 6
G/39-2 | SGBM23 | Nov 27 2015 12:00PM | Nov 28 2015 12:57AM | 52.040 | 49.675 |  | 20.501 | 2.365 | 29.174 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 34.0 | 34.6 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
G/40-1 | SGBM15 | Dec 19 2015 2:36PM | Dec 21 2015 7:35PM | 52.000 | 49.675 |  | 19.561 | 2.325 | 30.114 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 34.0 | 30.4 | G45T2 | 1, 2, 3 | 12, 10, 12
G/40-2 | SGBM15 | Dec 23 2015 2:00PM | Dec 26 2015 6:50PM | 52.000 | 49.675 |  | 19.575 | 2.325 | 30.100 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 32.0 | -100.0 | G45T2 | PJ3541, PJ3545, PJ 3546, PJ 3550 | 8, 8, 8, 8
G/41-1 | SGBM15 | Dec 19 2015 1:53PM | Dec 21 2015 9:09PM | 51.850 | 49.675 |  | 18.424 | 2.175 | 31.251 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.1 | 31.0 | 14.5 | G45T2 | 1, 2, 3 | 10, 11, 10
G/41-2 | SGBM15 | Dec 23 2015 2:00PM | Dec 26 2015 9:03PM | 51.908 | 49.675 |  | 18.452 | 2.233 | 31.223 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.0 | 34.0 | 25.7 | G45T2 | PJ 3555, PJ 3557, PJ 3560, PJ 3563 | 8, 8, 8, 10
G/42-1 | SGBM15 | Dec 23 2015 1:35PM | Dec 28 2015 11:08AM | 51.935 | 49.775 |  | 18.475 | 2.160 | 31.300 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.1 | 33.0 | 21.7 | G45T2 | PJ3568, PJ 3571, PJ 3572, PJ3575 | 8, 9, 8, 8
G/42-2 | SGBM15 | Dec 19 2015 1:19PM | Dec 22 2015 10:00PM | 51.873 | 49.775 |  | 17.331 | -49.775 | 32.444 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 37.0 | 31.7 | G45T2 | 1, 2, 3, 4 | 3, 12, 11, 11
G/43-1 | SGBM23 | Dec 15 2015 4:40PM | Dec 17 2015 1:27AM | 51.811 | 49.675 |  | 16.624 | 2.136 | 33.051 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.6 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 8, 7
G/44-1 | SGBM23 | Dec 15 2015 5:30PM | Dec 16 2015 4:35PM | 51.500 | 49.675 |  | 13.542 | 1.825 | 36.133 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.3 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 7
G/42-3 | SGBM23 | Dec 30 2015 9:50AM | Dec 31 2015 11:10AM | 51.925 | 49.775 |  | 18.385 | 2.150 | 31.390 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.2 | 35.0 | -100.0 | G45T2 | PJ 3777, PJ 3778, PJ 3779, PJ 3780, PJ 3781 | 8, 7, 7, 7, 6
G/43-2 | SGBM15 | Dec 19 2015 12:55PM | Dec 22 2015 10:00PM | 51.660 | 49.675 |  | 16.505 | 1.985 | 33.170 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.7 | 37.0 | -28.7 | G45T2 | C480013853, C520124330, C480013866, C480013867 | 3, 12, 11, 11
G/44-2 | SGBM23 | Dec 17 2015 1:20PM | Dec 18 2015 10:15PM | 51.540 | 49.675 |  | 14.043 | 1.865 | 35.632 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.9 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 10
G/45-1 | SGBM23 | Dec 17 2015 12:59PM | Dec 18 2015 7:40PM | 51.492 | 49.675 |  | 11.119 | 1.817 | 38.556 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.4 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 11, 11, 11
G/45-2 | SGBM23 | Dec 23 2015 8:40AM | Dec 23 2015 11:35PM | 51.560 | 49.675 |  | 11.558 | 1.885 | 38.117 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.0 | 42.0 | -33.0 | G45T2 | C521024361, C520124362, C520124366, C520124368 | 10, 10, 10, 12
G/46-1 | SGBM23 | Dec 17 2015 12:38PM | Dec 18 2015 6:43PM | 51.590 | 49.675 |  | 9.250 | 1.915 | 40.425 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.0 | 43.0 | 22.8 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 10
G/46-2 | SGBM23 | Dec 14 2015 5:56PM | Dec 15 2015 1:47PM | 51.540 | 49.675 |  | 9.131 | 1.865 | 40.544 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 35.1 | 43.0 | 22.5 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 8, 7, 7, 7, 7
G/47-1 | SGBM23 | Dec 8 2015 8:40PM | Dec 10 2015 12:27AM | 51.493 | 49.675 | 9, 24 | 10.250 | 1.818 | 39.425 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.1 | 45.0 | 31.8 | G45T2 | PJ2853, PJ 2854, PJ 2856, PJ 2859, PJ 2858, PJ 2861, PJ 2862 | 7, 9, 3, 9, 7, 7, 3
G/47-2 | SGBM15 | Dec 3 2015 5:56PM | Dec 4 2015 7:48PM | 51.500 | 49.675 | 9, 31 | 10.210 | 1.825 | 39.465 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.2 | 40.0 | 5.8 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 10
G/48-1 | SGBM23 | Dec 8 2015 8:55PM | Dec 9 2015 8:14PM | 51.216 | 49.675 |  | 10.303 | 1.541 | 39.372 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 34.1 | 40.0 | 17.3 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 10
G/48-2 | SGBM15 | Dec 3 2015 5:35PM | Dec 4 2015 10:35PM | 51.303 | 49.675 | 9 | 11.308 | 1.628 | 38.367 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.2 | 42.0 | -100.0 | G45T2 | PJ 2607, PJ 2611, PJ 2612, PJ 2615, PJ 2617, PJ 2619 | 7, 7, 7, 7, 7, 7
G/49-1 | SGBM15 | Nov 26 2015 9:20AM | Nov 27 2015 3:07PM | 51.632 | 49.675 | 9 | 11.572 | 1.957 | 38.103 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 33.0 | 40.0 | 21.2 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 6, 6, 7, 7
G/49-2 | SGBM15 | Nov 30 2015 10:35AM | Dec 2 2015 9:08PM | 51.680 | 49.675 | 9, 30 | 12.295 | 2.005 | 37.380 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.4 | 42.0 | 9.6 | G45T2 | 1, 2, 3, 4, 5 | 9, 7, 9, 8, 9
F/39-1 | SGBM23 | Dec 15 2015 12:43PM | Dec 17 2015 9:54PM | 51.919 | 51.375 |  | 22.188 | 0.544 | 29.187 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 28.0 | 10.8 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
E/51-1 | SGBM23 | Nov 13 2015 8:00PM | Nov 14 2015 8:05PM | 52.050 | 51.275 | 9 | 6.960 | -51.275 | 44.315 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.4 | 45.5 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 4, 11, 11.5, 10, 9
D/49-1 | SGBM23 | Nov 4 2015 3:20PM | Nov 5 2015 4:54PM | 51.720 | 51.275 | 9 | 6.803 | 0.445 | 44.472 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.5 | 52.0 | -38.5 | G45T2 | C480011375, C170013361, C480011377, C480011378, C170013362 | 11, 9, 11, 11, 10
D/51-1 | SGBM23 | Nov 4 2015 4:00PM | Nov 6 2015 3:55PM | 51.874 | 51.275 | 9 | 6.920 | 0.599 | 44.355 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 38.4 | 48.0 | -38.4 | G45T2 | C480011430, C480011431, C170013372, C480011434, C520123166 | 10, 10, 8, 10, 10
T1/49-1 | SGBM23 | Mar 1 2016 11:40AM | Mar 1 2016 10:30PM | 51.838 | 51.375 |  | 20.750 | 0.463 | 30.625 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.5 | 30.0 | -100.0 | G45T2 | pj6229, pj6230, m67s6tri, 4 | 8, 8, 7, 7
T1/53-1 | SGBM15 | Feb 19 2016 8:30AM | Feb 19 2016 9:00PM | 51.944 | 51.025 |  | 18.948 | 0.919 | 32.077 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 33.0 | -100.0 | G45T2 | 2, 2, 3, 4 | 8, 8, 8, 9
T1/54-1 | SGBM01 | Feb 3 2016 5:50PM | Feb 4 2016 10:15PM | 51.801 | 51.025 |  | 19.273 | 0.776 | 31.752 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.5 | 36.0 | -27.5 | G45T2 | 1, 2, 3, 4, 5 | 8, 10, 8, 7, 3
T/61-1 | SGBM05 | Jan 29 2016 9:40AM | Jan 30 2016 4:20PM | 52.045 | 49.775 |  | 20.549 | 2.270 | 29.226 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 34.0 | -100.0 | G45T2 | 2, 2, 3, 4, 5 | 8, 8, 8, 7, 3
S/52-1 | SGBM23 | Feb 27 2016 11:25AM | Feb 29 2016 4:30PM | 51.809 | 49.225 |  | -39.200 | 2.584 | 88.425 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 76.6 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 8, 10
S/52-2 | SGBM15 | Feb 24 2016 1:40PM | Feb 25 2016 8:00PM | 51.902 | 49.225 |  | 13.840 | 2.677 | 35.385 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 41.0 | -30.6 | G45T2 | pj6014, pj6015, pj6019, pj6021, pj6026 | 10, 10, 8, 9, 4
S/53-1 | SGBM15 | Feb 22 2016 10:59AM | Feb 22 2016 9:05PM | 51.821 | 49.675 |  | 12.773 | 2.146 | 36.902 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.0 | 36.0 | -100.0 | G45T2 | pj5867, pj5869, pj5872, pj5878 | 8, 8, 10, 10
S/53-2 | SGBM15 | Feb 19 2016 4:50PM | Feb 20 2016 5:25PM | 51.869 | 49.675 |  | 13.773 | 2.194 | 35.902 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.1 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 8, 7
S/54-1 | SGBM15 | Jan 20 2016 9:40AM | Jan 20 2016 10:55PM | 51.972 | 49.675 |  | 13.314 | 2.297 | 36.361 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.5 | 50.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 10, 10, 9, 11
S/54-2 | SGBM15 | Jan 26 2016 10:35AM | Jan 27 2016 12:15AM | 51.978 | 49.675 |  | 13.845 | 2.303 | 35.830 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.0 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 7
S/56-1 | SGBM15 | Jan 20 2016 9:00AM | Jan 21 2016 8:00PM | 51.894 | 49.675 |  | 15.945 | 2.219 | 33.730 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.2 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 8, 8
S/56-2 | SGBM23 | Jan 13 2016 5:20PM | Jan 14 2016 9:40PM | 51.961 | 49.675 |  | 16.118 | 2.286 | 33.557 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.1 | 37.0 | -29.1 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 6
S/57-1 | SGBM01 | Jan 28 2016 10:45AM | Jan 28 2016 10:35PM | 52.064 | 49.675 |  | 15.304 | 2.389 | 34.371 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.8 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 8, 8
S/57-2 | SGBM01 | Jan 23 2016 3:00PM | Jan 26 2016 7:25PM | 51.973 | 49.675 |  | 17.361 | 2.298 | 32.314 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 10, 8, 8, 4
S/58-1 | SGBM15 | Jan 16 2016 2:45PM | Jan 18 2016 11:05PM | 52.029 | 49.675 |  | 17.899 | 2.354 | 31.776 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.5 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
S/58-2 | SGBM01 | Jan 20 2016 3:35PM | Jan 21 2016 5:45PM | 52.069 | 49.675 |  | 18.228 | 2.394 | 31.447 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.2 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 10, 8
S/59-1 | SGBM15 | Jan 30 2016 2:00PM | Feb 2 2016 8:05PM | 52.013 | 49.675 |  | 18.658 | 2.338 | 31.017 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.9 | 33.0 | -26.9 | G45T2 | 1, 2, 3 | 11, 11, 11
S/59-2 | SGBM23 | Feb 4 2016 1:50PM | Feb 10 2016 10:05PM | 51.949 | 49.675 |  | 18.759 | 2.274 | 30.916 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.8 | 32.0 | -26.8 | G45T2 | 1, 2, 3, 4 | 8, 8, 8, 8
R/54-1 | SGBM15 | Jan 16 2016 9:30AM | Jan 16 2016 10:30PM | 51.932 | 51.375 |  | 15.091 | 0.557 | 36.284 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.4 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 6
R/55-1 | SGBM15 | Jan 21 2016 12:30PM | Jan 22 2016 5:00PM | 51.922 | 51.375 |  | 14.578 | 0.547 | 36.797 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.9 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 8, 8
R/56-1 | SGBM15 | Jan 16 2016 11:05AM | Jan 18 2016 7:20PM | 51.985 | 51.375 |  | 15.203 | 0.610 | 36.172 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.3 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 10, 8, 9
R/57-1 | SGBM15 | Jan 16 2016 11:40AM | Jan 19 2016 5:45PM | 51.878 | 51.375 |  | 17.258 | 0.503 | 34.117 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.5 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 9, 8
Q/50-1 | SGBM05 | Feb 4 2016 2:05PM | Feb 5 2016 4:40PM | 51.816 | 51.375 |  | 14.574 | 0.441 | 36.801 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.9 | 36.0 | -31.9 | G45T2 | 1, 2, 3, 4 | 9, 9, 8, 10
Q/53-1 | SGBM15 | Jan 13 2016 5:40PM | Jan 15 2016 8:40PM | 51.970 | 51.375 |  | 13.652 | 0.595 | 37.723 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.7 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 7
Q/55-1 | SGBM23 | Jan 12 2016 12:45PM | Jan 15 2016 10:15PM | 51.928 | 51.375 |  | 14.039 | 0.553 | 37.336 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.3 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 7, 7
Q/56-1 | SGBM15 | Jan 12 2016 12:00PM | Jan 14 2016 6:45PM | 51.895 | 51.375 |  | 14.139 | 0.520 | 37.236 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.2 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 10, 7, 8, 7, 6
Q/57-1 | SGBM15 | Jan 12 2016 12:00PM | Jan 15 2016 7:40PM | 51.893 | 51.375 |  | 15.668 | 0.518 | 35.707 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.9 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 7
P/56-1 | SGBM15 | Jan 22 2016 5:45PM | Jan 23 2016 5:55PM | 52.050 | 49.675 |  | 12.131 | 2.375 | 37.544 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.5 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 7
P/56-2 | SGBM15 | Jan 26 2016 3:00PM | Jan 27 2016 10:25PM | 52.094 | 49.675 |  | 11.814 | 2.419 | 37.861 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.8 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 8, 8, 8, 8, 2
P/58-1 | SGBM23 | Jan 16 2016 12:47PM | Jan 16 2016 11:35PM | 52.010 | 51.375 |  | 14.465 | 0.635 | 36.910 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.0 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 7, 6
N/51-1 | SGBM05 | Jan 12 2016 1:41PM | Jan 12 2016 10:23PM | 51.968 | 50.775 |  | 13.059 | 1.193 | 37.716 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.7 | 39.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 8
N/54-1 | SGBM23 | Jan 6 2016 5:00PM | Jan 8 2016 11:30AM | 51.765 | 49.675 |  | 12.486 | 2.090 | 37.189 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.2 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 7
N/54-2 | SGBM15 | Jan 11 2016 2:35PM | Jan 12 2016 7:35PM | 52.019 | 49.675 |  | 12.573 | 2.344 | 37.102 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 10
N/55-1 | SGBM23 | Jan 6 2016 5:10PM | Jan 8 2016 7:50PM | 51.890 | 49.675 |  | 12.330 | 2.215 | 37.345 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.3 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 8, 7, 7
N/55-2 | SGBM23 | Jan 11 2016 2:10PM | Jan 13 2016 9:30PM | 52.036 | 49.675 |  | 12.654 | 2.361 | 37.021 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 40.0 | 24.8 | G45T2 | 1, 2, 3, 4, 5 | 10, 8, 8, 7, 7
N/56-1 | SGBM23 | Jan 15 2016 10:40AM | Jan 16 2016 5:20PM | 52.153 | 49.675 |  | 12.485 | 2.478 | 37.190 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.2 | 41.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 8, 8, 7, 7, 4
N/56-2 | SGBM15 | Jan 19 2016 10:30AM | Jan 19 2016 11:05PM | 52.106 | 49.675 |  | 11.911 | 2.431 | 37.764 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.7 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 8, 8, 10
N/57-1 | SGBM23 | Jan 12 2016 10:45AM | Jan 14 2016 8:35PM | 52.109 | 49.675 |  | 12.608 | 2.434 | 37.067 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.1 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 10, 7
N/57-2 | SGBM05 | Jan 19 2016 9:30AM | Jan 20 2016 7:40PM | 52.140 | 49.675 |  | 13.434 | 2.465 | 36.241 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.4 | 41.0 | 65.7 | G45T2 | 1, 2, 3, 4, 5 | 3, 10, 11, 11, 6
N/61-1 | SGBM23 | Feb 26 2016 8:30AM | Feb 26 2016 10:30PM | 51.717 | 50.925 |  | 15.342 | 0.792 | 35.583 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.8 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 10, 10, 7
M7/56-1 | SGBM05 | Jan 16 2016 8:45AM | Jan 17 2016 1:05AM | 52.133 | 50.925 |  | 13.717 | 1.208 | 37.208 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.2 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 8, 7, 7
M7/57-1 | SGBM01 | Feb 5 2016 3:15PM | Feb 10 2016 11:15PM | 52.102 | 50.925 |  | 13.263 | 1.177 | 37.662 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.6 | 43.0 | 4.4 | G45T2 | 1, 2, 3, 4, 5, 6 | 10, 10, 6, 7, 6, 4
M7/58-1 | SGBM05 | Feb 13 2016 12:55PM | Feb 13 2016 9:40PM | 52.049 | 50.925 |  | 14.485 | 1.124 | 36.440 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.6 | 37.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 8, 7, 6
M7/59-1 | SGBM01 | Jan 21 2016 4:35PM | Jan 23 2016 2:10PM | 51.999 | 51.275 |  | 15.009 | 0.724 | 36.266 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.4 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 8, 8, 7
M6/56-1 | SGBM15 | Jan 29 2016 8:30AM | Jan 29 2016 11:00PM | 52.040 | 51.375 |  | 14.522 | 0.665 | 36.853 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.9 | 42.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 7, 8, 7, 7, 5
M6/59-1 | SGBM01 | Jan 18 2016 4:55PM | Jan 19 2016 10:05PM | 51.935 | 51.075 |  | 15.473 | 0.860 | 35.602 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.8 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 10, 10, 8
M5/58-1 | SGBM01 | Jan 21 2016 1:40PM | Jan 22 2016 10:35PM | 51.911 | 51.275 |  | 14.390 | 0.636 | 36.885 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.9 | 42.0 | 15.8 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 8, 7, 7, 7, 5
M5/59-1 | SGBM01 | Jan 18 2016 5:30PM | Jan 20 2016 2:25PM | 51.851 | 51.075 |  | 13.861 | 0.776 | 37.214 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 32.2 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 8, 7
AA/53-1 | SGBM19 | Nov 16 2015 5:20PM | Nov 18 2015 7:13PM | 49.242 | 49.075 | 9, 12 | 16.799 | 0.167 | 32.276 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 33.0 | 5.0 | G35T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 5
AA/54-1 | SGBM17 | Nov 17 2015 4:30PM | Nov 18 2015 9:43PM | 49.308 | 49.075 | 9, 21 | 15.776 | 0.233 | 33.299 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.8 | 33.0 | -28.8 | G45T2 | PJ 1778, PJ 1781, PJ 1784, PJ 1787, PJ 1790 | 7, 7, 7, 6, 6
AA/55-1 | SGBM17 | Nov 24 2015 5:22PM | Nov 25 2015 1:35PM | 49.509 | 49.075 | 9, 19.7 | 16.932 | 0.434 | 32.143 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 36.0 | 7.4 | G35T2 | 2098, 2099, 2100, 2103, 2106, 2114 | 7, 7, 6, 7, 6, 3
Z/51-1 | SGBM19 | Dec 28 2015 5:45PM | Dec 29 2015 6:15PM | 49.501 | 46.925 |  | 16.399 | 2.576 | 30.526 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.4 | 30.0 | -100.0 | G45T2 | PJ 3675, PJ 3677, PJ 3682, PJ 3685 | 8, 8, 7, 7
Z/51-2 | SGBM17 | Dec 23 2015 9:20AM | Dec 24 2015 3:44AM | 49.460 | 46.925 |  | 16.574 | 2.535 | 30.351 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.3 | 40.0 | -100.0 | G45T2 | C520124379, C520124381, C520124384, C520124385, C520124389 | 9, 9, 7, 10, 5
Z/52-1 | SGBM19 | Dec 22 2015 9:10AM | Dec 23 2015 2:07AM | 49.571 | 46.925 |  | 15.886 | 2.646 | 31.039 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.9 | 36.0 | -100.0 | G45T2 | C480013870, C480013875, C480013879, C480013883 | 11, 10, 10, 5
Z/52-2 | SGBM05 | Dec 29 2015 9:20AM | Jan 30 2016 10:10PM | 49.525 | 46.925 |  | 12.418 | 2.600 | 34.507 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.9 | 34.0 | -100.0 | G45T2 | C170014211, C170014213, C170014214, C170014216 | 10, 8, 8, 8
Z/56a-1 | SGBM19 | Dec 14 2015 10:40AM | Dec 15 2015 4:35AM | 49.473 | 48.425 |  | 16.323 | 1.048 | 32.102 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 33.0 | 18.7 | G45T2 | C480013278, C480013283, C480013287, C480013289 | 9, 11.5, 11, 1.5
Z/56a-2 | SGBM16 | Dec 17 2015 11:26AM | Dec 18 2015 2:40AM | 49.328 | 48.425 |  | 16.400 | 0.903 | 32.025 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 34.0 | -100.0 | G45T2 | C480013565, C480013566, C520124196, C520124198 | 10, 10, 10, 4
Y/52-1 | SGBM05 | Dec 12 2015 5:30PM | Dec 16 2015 11:11PM | 49.666 | 47.475 |  | 17.035 | 2.191 | 30.440 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.4 | 32.0 | -100.0 | G45T2 | PJ 3231, PJ 3234, PJ 3238, PJ 3240 | 8, 8, 8, 8
Y/52-2 | SGBM17 | Nov 28 2015 8:12AM | Dec 1 2015 12:42AM | 49.321 | 47.475 | 9 | 17.337 | 1.846 | 30.138 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 32.0 | 22.6 | G45T2 | PJ 2402, PJ 2405, PJ 2407, PJ 2411, PJ 2413 | 7, 7, 6, 6, 6
Y/52-3 | SGBM17 | Nov 23 2015 9:30AM | Nov 24 2015 3:22PM | 49.401 | 47.475 |  | 17.389 | 1.926 | 30.086 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 7, 8, 7
Y/53-1 | SGBM17 | Nov 16 2015 8:10AM | Nov 17 2015 1:39AM | 49.412 | 47.475 |  | 17.412 | 1.937 | 30.063 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 8, 8, 8
Y/53-2 | SGBM17 | Nov 27 2015 2:30PM | Nov 28 2015 9:32PM | 49.292 | 47.475 | 9, 16.6, 21.6 | 17.262 | 1.817 | 30.213 |  | 3.7 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.2 | 32.0 | -100.0 | G45T2 | PJ 2319, PJ 2322, PJ 2326, PJ 2329, PJ 2332 | 7, 7, 6, 6, 6
Y/53-3 | SGBM17 | Dec 7 2015 5:30PM | Dec 9 2015 1:30PM | 49.543 | 47.475 |  | 17.139 | 2.068 | 30.336 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.3 | 33.0 | -100.0 | G45T2 | PJ 2801, PJ 2802, PJ 2804, PJ 2805, PJ 2807 | 7, 7, 7, 6, 6
Y/57-1 | SGBM17 | Dec 11 2015 9:10AM | Dec 11 2015 11:00PM | 49.450 | 47.375 |  | 17.206 | 2.075 | 30.169 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 34.0 | -100.0 | G45T2 | C480013105, C480013107, C480013113 | 11.5, 11.5, 11
Y/57-2 | SGBM05 | Dec 16 2015 1:30PM | Dec 17 2015 4:45AM | 49.364 | 47.375 |  | 16.808 | 1.989 | 30.567 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.5 | 35.0 | -100.0 | G45T2 | PJ 3255, PJ 3256, Pending, PJ 3258, PJ 3259 | 7, 7, 7, 7, 7
Y/58-1 | SGBM17 | Dec 15 2015 4:30PM | Dec 16 2015 2:11AM | 49.315 | 47.375 |  | 23.549 | 1.940 | 23.826 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.6 | 39.0 | -100.0 | G45T2 | PJ 3177, PJ 3179, PJ 3180, PJ 3182, PJ 3184, PJ 3185 | 7, 7, 7, 6, 7, 5
Y/58-2 | SGBM17 | Dec 10 2015 8:10AM | Dec 11 2015 1:29AM | 49.673 | 47.375 |  | 15.527 | 2.298 | 31.848 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 33.0 | 8.8 | G45T2 | PJ 2935, PJ 2937, PJ 2942, PJ 2944, PJ 2946 | 7, 7, 6, 6, 7
Y/59-2 | SGBM16 | Dec 16 2015 4:15PM | Dec 17 2015 6:57PM | 49.569 | 47.275 |  | 14.900 | 2.294 | 32.375 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 34.0 | -100.0 | G45T2 | PJ 3287, PJ 3294, PJ 3297, PJ 3303 | 10, 10, 7, 7
Y/60-1 | SGBM16 | Dec 19 2015 10:30AM | Dec 20 2015 12:36AM | 49.487 | 47.375 |  | 13.460 | 2.112 | 33.915 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.4 | 33.0 | -100.0 | G45T2 | C520124244, C480013695, C520124247 | 12, 11, 10
Y/59-1 | SGBM17 | Dec 12 2015 8:30AM | Dec 13 2015 2:23AM | 49.611 | 47.275 |  | 14.784 | 2.336 | 32.491 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 35.0 | -100.0 | G45T2 | PJ 3062, PJ 3065, PJ 3068, PJ 3071, PJ 3074 | 7, 7, 7, 7, 7
Y/60-2 | SGBM05 | Dec 22 2015 5:40PM | Dec 23 2015 7:20PM | 49.316 | 47.375 |  | 14.134 | 1.941 | 33.241 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.8 | 37.0 | -100.0 | G45T2 | C480013928, C480013930, C520124351, C520124356 | 11, 9, 12, 5
Y/60-3 | SGBM19 | Dec 21 2015 10:00AM | Dec 21 2015 7:13PM | 49.408 | 47.375 |  | 14.865 | 2.033 | 32.510 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.2 | 36.0 | -100.0 | G45T2 | PJ3457, PJ 3460, PJ 3462, PJ 3465 | 10, 10, 8, 8
Y/61-1 | SGBM17 | Dec 21 2015 9:30AM | Dec 21 2015 5:20PM | 49.673 | 47.475 |  | 15.046 | 2.198 | 32.429 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 31.0 | 2.9 | G45T2 | PJ 3448, PJ 3451, PJ 3454, PJ 3459 | 8, 7, 8, 8
Y/61-2 | SGBM17 | Dec 14 2015 3:40PM | Dec 15 2015 5:58PM | 49.766 | 47.475 |  | 14.513 | 2.291 | 32.962 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.5 | 33.5 | -100.0 | G45T2 | C480013318, C480013321, C480013326 | 11.5, 11, 11
Y/61-3 | SGBM05 | Dec 17 2015 8:40AM | Dec 18 2015 11:18PM | 49.749 | 47.475 |  | 14.788 | 2.274 | 32.687 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.3 | 37.0 | -100.0 | G45T2 | PJ 3394, PJ 3397, PJ 3400, PJ 3401, PJ 3406, PJ 3407 | 7, 7, 7, 7, 6, 3
X/52-1 | SGBM19 | Dec 1 2015 11:30AM | Dec 2 2015 4:22PM | 49.132 | 47.175 | 9, 29.8 | 17.658 | 1.417 | 29.517 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.6 | 34.0 | -26.0 | G45T2 | PJ 2456, PJ 2459, PJ 2461, PJ 2463, PJ 2469 | 8, 8, 7, 7, 4
X/52-2 | SGBM19 | Dec 7 2015 11:00AM | Dec 9 2015 5:14PM | 49.475 | 47.715 |  | 18.084 | 1.760 | 29.631 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.7 | 32.0 | -100.0 | G45T2 | PJ 2816, PJ 2817, PJ 2818, PJ 2822, PJ 2827 | 7, 7, 6, 6, 6
X/52-3 | SGBM17 | Nov 25 2015 2:15PM | Nov 26 2015 11:55AM | 49.304 | 47.715 | 9, 14.3, 19.2 | 18.051 | 1.589 | 29.664 |  | 17.9 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.7 | 30.0 | 4.3 | G45T2 | PJ 2175, PJ 2176, PJ 2177, PJ 2178 | 8, 7, 8, 7
X/52-4 | SGBM17 | Nov 18 2015 9:40AM | Nov 19 2015 6:06AM | 49.279 | 47.715 | 9 | 18.397 | 1.564 | 29.318 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.4 | 38.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 7, 8, 7, 8, 4, 4
X/53-1 | SGBM19 | Dec 2 2015 1:20PM | Dec 6 2015 12:02AM | 49.180 | 47.475 |  | 17.000 | 1.705 | 30.475 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.4 | 35.0 | -26.4 | G45T2 | PJ 2674, PJ 2676, PJ 2678, PJ 2682 | 7, 8, 7, 13
X/53-2 | SGBM17 | Nov 12 2015 9:36AM | Nov 12 2015 6:46PM | 31.435 | 47.475 | 9 | 18.762 | -16.040 | 28.713 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.9 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
X/53-3 | SGBM17 | Nov 17 2015 8:30AM | Nov 17 2015 7:35PM | 49.461 | 47.475 | 9 | 17.980 | 1.986 | 29.495 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.5 | 36.0 | -100.0 | G45T2 | PJ 1712, PJ 1714, PJ 1715, PJ 1716, PJ 1722 | 8, 8, 8, 8, 4
X/58-1 | SGBM19 | Sep 23 2015 10:20AM | Sep 23 2015 9:47PM | 49.664 | 47.375 |  | 19.356 | 2.289 | 28.019 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 11, 11, 8
X/58-2 | SGBM17 | Dec 8 2015 4:00PM | Dec 10 2015 11:41PM | 49.580 | 47.375 |  | 18.679 | 2.205 | 28.696 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.9 | 32.0 | -100.0 | G45T2 | PJ 2925, PJ 2929, PJ 2930, PJ 2933 | 7, 8, 9, 8
X/59-1 | SGBM16 | Dec 11 2015 5:20PM | Dec 12 2015 3:55AM | 49.651 | 47.275 |  | 17.933 | 2.376 | 29.342 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.4 | 37.0 | -100.0 | G45T2 | C480013138, C480013139, C480013144, C480013152 | 10, 10, 10, 7
X/59-2 | SGBM17 | Dec 9 2015 6:00PM | Dec 10 2015 7:41PM | 49.754 | 47.275 |  | 17.589 | 2.479 | 29.686 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.7 | 32.0 | -100.0 | G45T2 | PJ 2908, PJ 2912, PJ 2914, PJ 2918 | 7, 7, 8, 10
X/60-1 | SGBM17 | Dec 28 2015 8:35AM | Dec 28 2015 8:28PM | 49.589 | 47.375 |  | 16.568 | 2.214 | 30.807 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.7 | 33.0 | -100.0 | G45T2 | PJ 3612, PJ 3615, PJ 3617, PJ 3621 | 9, 8, 8, 8
W/61-2 | SGBM17 | Jan 7 2016 10:37AM | Jan 8 2016 3:45PM | 49.560 | 47.375 |  | 18.808 | 2.185 | 28.567 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 8, 3
V/51-1 | SGBM20 | Jan 30 2016 5:03PM | Feb 2 2016 5:30PM | 49.802 | 47.375 |  | 24.130 | 2.427 | 23.245 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.1 | 30.0 | -100.0 | G45T2 | PJ 5187, PJ 5190, PJ 5194, PJ 5202 | 10, 10, 8, 2
X/60-2 | SGBM17 | Dec 19 2015 10:30AM | Dec 20 2015 3:29AM | 49.666 | 47.375 |  | 14.796 | 2.291 | 32.579 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.2 | 37.5 | -28.2 | G45T2 | C480013702, C480013703, C480013706, C480013709 | 10, 11, 11.5, 5
X/60-3 | SGBM17 | Dec 22 2015 3:55PM | Dec 26 2015 4:55PM | 49.754 | 47.375 |  | 16.500 | 2.379 | 30.875 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.7 | 40.0 | -100.0 | G45T2 | PJ3528, PJ 3530, PJ 3534, PJ 3537, PJ 3542 | 10, 8, 8, 9, 5
X/61-1 | SGBM19 | Dec 19 2015 2:14PM | Dec 20 2015 3:48AM | 49.756 | 47.475 |  | 16.557 | 2.281 | 30.918 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.8 | 31.5 | -100.0 | G45T2 | 1, 2, 3 | 9, 11.5, 11
X/61-2 | SGBM17 | Dec 14 2015 6:30PM | Dec 15 2015 8:22PM | 49.775 | 47.475 |  | 17.106 | 2.300 | 30.369 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.3 | 33.0 | -100.0 | G45T2 | C480013332, C480013334, C480013335 | 11, 11, 11
X/61-3 | SGBM05 | Dec 17 2015 8:45AM | Dec 18 2015 3:08AM | 49.725 | 47.475 |  | 17.394 | 2.250 | 30.081 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 32.0 | -100.0 | G45T2 | C520124198, C520124200, C480013751 | 10, 12, 10
W/52-1 | SGBM19 | Dec 21 2015 2:20PM | Dec 21 2015 9:36PM | 49.232 | 47.025 |  | 18.447 | 2.207 | 28.578 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 34.0 | -100.0 | G45T2 | PJ 3469, PJ 3470, PJ 3473, PJ 3475, PJ 3477 | 8, 8, 7, 7, 4
W/52-2 | SGBM17 | Dec 5 2015 6:00PM | Dec 7 2015 10:21PM | 49.339 | 47.025 |  | 18.493 | 2.314 | 28.532 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 33.0 | -100.0 | G45T2 | C480012814, C480012815, C480012820 | 11, 11, 11
W/52-3 | SGBM19 | Dec 18 2015 8:35AM | Dec 18 2015 11:02PM | 49.230 | 47.025 |  | 18.507 | 2.205 | 28.518 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 33.0 | -100.0 | G45T2 | PJ 3392, PJ 3393, PJ 3395, PJ3404 | 7, 8, 8, 10
W/54-1 | SGBM17 | Dec 22 2015 8:40AM | Dec 22 2015 7:15PM | 49.469 | 47.375 |  | 18.363 | 2.094 | 29.012 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.1 | 30.0 | -100.0 | G45T2 | C4800137835, C480013837, C480013843 | 10, 9, 11
W/54-2 | SGBM19 | Dec 11 2015 5:15PM | Dec 12 2015 5:15AM | 49.616 | 47.375 |  | 18.355 | 2.241 | 29.020 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.1 | 34.0 | -100.0 | G45T2 | PJ 3008, PJ 3009, PJ 3010, PJ 3011, PJ 3012 | 8, 9, 8, 7, 2
W/55-1 | SGBM17 | Dec 3 2015 2:10PM | Dec 4 2015 2:17AM | 49.634 | 47.375 | 9 | 17.961 | 2.259 | 29.414 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.5 | 32.0 | -25.5 | G45T2 | PJ 2567, PJ 2568, PJ 2570, PJ 2571 | 8, 8, 8, 8
W/55-2 | SGBM17 | Dec 16 2015 4:45PM | Dec 17 2015 9:40PM | 49.646 | 47.375 |  | 18.372 | 2.271 | 29.003 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.1 | 32.0 | -100.0 | G45T2 | PJ 3307, PJ 3313, PJ 3314, PJ 3318 | 10, 9, 8, 5
W/57-1 | SGBM16 | Dec 21 2015 4:00PM | Dec 22 2015 9:50PM | 49.441 | 47.375 |  | 19.332 | 2.066 | 28.043 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 33.0 | -100.0 | G45T2 | C480013851, C480013861, C480013863 | 11, 11, 11
W/57-2 | SGBM17 | Dec 14 2015 8:45AM | Dec 15 2015 7:15AM | 49.531 | 47.375 |  | 19.262 | 2.156 | 28.113 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 33.5 | -100.0 | G45T2 | C48001389, C480013291, C480013294, C480013295 | 7.5, 10, 8, 8
W/58-1 | SGBM16 | Dec 16 2015 9:00AM | Dec 17 2015 3:00AM | 49.280 | 47.375 |  | 18.986 | 1.905 | 28.389 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.6 | 30.0 | -100.0 | G45T2 | PJ 3251, PJ 3252, PJ 3253, PJ 3254 | 8, 8, 8, 6
W/58-2 | SGBM05 | Dec 22 2015 8:20AM | Dec 23 2015 1:56AM | 49.223 | 47.375 |  | 19.263 | 1.848 | 28.112 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 32.0 | -100.0 | G45T2 | C520124333, C520124336, C480013876 | 12, 10, 10
W/59-1 | SGBM17 | Dec 15 2015 8:40AM | Dec 13 2015 6:28AM | 49.641 | 47.375 |  | 18.619 | 2.348 | 28.756 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.9 | 31.0 | 24.5 | G45T2 | PJ 3081, PJ 3082, PJ 3083, PJ 3084 | 8, 8, 8, 7
W/59-2 | SGBM17 | Dec 12 2015 6:30PM | Dec 13 2015 6:28AM | 49.723 | 47.375 |  | 18.680 | 2.348 | 28.695 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.9 | 31.0 | 24.7 | G45T2 | PJ 3081, PJ 3082, PJ 3083, PJ 3084 | 8, 8, 8, 7
W/60-2 | SGBM17 | Jan 8 2016 11:00AM | Jan 8 2016 7:23PM | 49.437 | 47.375 |  | 19.306 | 2.062 | 28.069 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 7, 7, 7
W/61-1 | SGBM19 | Jan 5 2016 3:30PM | Jan 5 2016 10:30PM | 49.693 | 47.375 |  | 18.900 | 2.318 | 28.475 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 33.0 | -24.7 | G45T2 | PJ 4008, PJ 4010, PJ 4012, PJ 4018 | 7, 8, 10, 8
W/60-1 | SGBM17 | Jan 5 2016 8:30AM | Jan 5 2016 5:05PM | 49.455 | 47.375 |  | 19.108 | 2.080 | 28.267 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.5 | 36.0 | -24.5 | G45T2 | C480014533, C480014535, C480014540, C480014543 | 11, 10, 10, 5
V/51-2 | SGBM31 | Jan 29 2016 8:52AM | Jan 29 2016 6:40PM | 49.456 | 47.375 |  | 20.115 | 2.081 | 27.260 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.6 | 34.0 | -100.0 | G45T2 | PJ 5073, PJN5074, PJ 5077, PJ 5079, PJ 5083 | 8, 8, 8, 7, 3
V/52-1 | SGBM20 | Jan 23 2016 1:57PM | Jan 26 2016 7:00PM | 49.407 | 47.375 |  | 19.633 | 2.032 | 27.742 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.0 | 37.0 | 54.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 7, 8, 6
V/52-2 | SGBM31 | Jan 19 2016 10:40AM | Jan 19 2016 5:03PM | 49.520 | 47.375 |  | 20.290 | 2.145 | 27.085 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.5 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 9, 10, 10, 5
V/53-1 | SGBM17 | Jan 15 2016 3:49PM | Jan 16 2016 2:25PM | 49.460 | 47.275 |  | 19.267 | 2.185 | 28.008 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 33.0 | -100.0 | G45T2 | PJ 4479, PJ 4482, PJ 4483, PJ 4485, PJ 4490 | 8, 8, 7, 7, 3
V/53-2 | SGBM17 | Jan 11 2016 3:46PM | Jan 12 2016 2:25PM | 49.560 | 47.275 |  | 19.267 | 2.285 | 28.008 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 30.0 | 23.7 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
V/54-1 | SGBM19 | Dec 31 2015 8:05AM | Dec 31 2015 6:10PM | 49.406 | 47.375 |  | 19.346 | 2.031 | 28.029 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.3 | 33.5 | -100.0 | G45T2 | C480014327, C480014330, C480014332, C480014337 | 6, 11, 11.5, 5
V/54-2 | SGBM05 | Jan 5 2016 1:30PM | Jan 5 2016 9:25PM | 49.159 | 47.375 |  | 18.684 | 1.784 | 28.691 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.8 | 30.0 | -24.8 | G45T2 | PJ 4001, PJ 4003, PJ 4005, PJ4007 | 8, 8, 7, 7
V/55-1 | SGBM19 | Dec 29 2015 1:20PM | Dec 30 2015 1:25AM | 49.497 | 47.375 |  | 17.918 | 2.122 | 29.457 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.5 | 30.0 | -100.0 | G45T2 | PJ 3714, PJ 3715, PJ 3716, PJ 3717 | 8, 8, 7, 7
V/55-2 | SGBM17 | Jan 2 2016 2:40PM | Jan 2 2016 10:10PM | 49.419 | 47.375 |  | 18.317 | 2.044 | 29.058 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.2 | 35.0 | -25.2 | G45T2 | C480014413, C480014414, C480014417 | 12, 12, 11
V/57-1 | SGBM17 | Dec 29 2015 5:30PM | Jan 31 2016 5:35AM | 49.486 | 47.075 |  | 17.351 | 2.411 | 29.724 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.7 | 32.0 | -100.0 | G45T2 | PJ 3773, PJ 3774, PJ 3775, PJ 3776 | 8, 10, 7, 7
V/57-2 | SGBM17 | Jan 4 2016 11:30AM | Jan 4 2016 7:30PM | 49.524 | 47.075 |  | 16.535 | 2.449 | 30.540 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.4 | 33.0 | -26.4 | G45T2 | C480014454, C480014455, C480014458 | 10, 11.5, 11.5
V/58-1 | SGBM17 | Dec 31 2015 2:20PM | Jan 4 2016 5:10PM | 49.375 | 47.075 |  | 17.071 | 2.300 | 30.004 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 35.0 | -26.0 | G45T2 | C520124609, C480014443, C520124612, C521024613 | 7, 11, 9, 8
V/58-2 | SGBM05 | Jan 6 2016 1:35PM | Jan 7 2016 1:12AM | 49.309 | 47.075 |  | 17.227 | 2.234 | 29.848 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.8 | 33.0 | -100.0 | G45T2 | PJ 4075, PJ 4077, PJ 4078, PJ 4079 | 8, 8, 7, 10
V/59-1 | SGBM05 | Dec 31 2015 5:00PM | Jan 2 2016 4:50PM | 49.305 | 47.075 |  | 17.337 | 2.230 | 29.738 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.8 | 33.0 | -100.0 | G45T2 | C480014395, C480014397, C48014399 | 11, 11, 11
V/59-2 | SGBM17 | Jan 7 2016 4:40PM | Jan 7 2016 8:20PM | 49.392 | 47.075 |  | 17.303 | 2.317 | 29.772 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.8 | 34.0 | -100.0 | G45T2 | PJ 4110, PJ 4113, PJN4118, PJ 4124 | 8, 10, 8, 8
V/60-1 | SGBM17 | Dec 31 2015 2:00PM | Jan 2 2016 5:55PM | 49.354 | 47.075 |  | 17.302 | 2.279 | 29.773 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.8 | 32.0 | -25.8 | G45T2 | C480014401, C480014403, C520124586 | 11, 11, 10
M5b/57-1 | SGBM08 | Jan 20 2016 11:24AM | Jan 21 2016 11:20PM | 51.932 | 51.275 |  | 14.670 | 0.657 | 36.605 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.7 | 38.0 | -100.0 | G45T2 | Pending, 2, 3, 4, 5 | 8, 8, 8, 7, 7
U/50-1 | SGBM20 | Feb 3 2016 10:30AM | Feb 3 2016 6:55PM | 51.328 | 51.375 |  | 22.905 | -0.047 | 28.470 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 28.0 | -100.0 | G45T2 | PJ 5237, PJ 5241, PJ 5243 | 10, 10, 8
U/51-1 | SGBM17 | Jan 18 2016 1:15PM | Jan 19 2016 3:30PM | 51.817 | 51.375 |  | 23.248 | 0.442 | 28.127 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.4 | 29.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 7, 7, 7
U/55-1 | SGBM17 | Jan 19 2016 4:24PM | Jan 20 2016 3:25PM | 51.827 | 51.375 |  | 21.940 | 0.452 | 29.435 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.5 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
V/60-2 | SGBM05 | Jan 6 2016 8:30AM | Jan 6 2016 5:20PM | 49.285 | 47.075 |  | 17.338 | 2.210 | 29.737 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.8 | 41.0 | -100.0 | G45T2 | C480014589, C480014T91, C480014593, C480014604 | 18, 10, 10, 3
J/43-1 | SGBM23 | Nov 20 2015 4:22PM | Nov 23 2015 12:15PM | 51.694 | 48.425 | 8 | 16.261 | 3.269 | 32.164 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 |  | 27.9 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
J/43-2 | SGBM23 | Dec 7 2015 9:13AM | Dec 7 2015 5:50PM | 51.817 | 48.425 | 9 | 16.100 | 3.392 | 32.325 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 33.0 | 5.0 | G45T2 | PJ 2712, PJ 2714, PJ 2717, PJ 2720, PJ 2723 | 7, 7, 7, 6, 6
J/43-3 | SGBM23 | Dec 1 2015 2:14PM | Dec 3 2015 2:05PM | 51.790 | 48.425 | 9 | 14.946 | 3.365 | 33.479 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.0 | 33.0 | 4.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 6, 6, 6, 6, 4, 5
J/43-4 | SGBM23 | Nov 20 2015 4:50PM | Nov 27 2015 5:36PM | 51.845 | 48.425 | 9, 15.6, 29.6 | 15.593 | 3.420 | 32.832 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.4 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
J/43-5 | SGBM23 | Nov 20 2015 5:45PM | Nov 23 2015 2:08PM | 51.312 | 48.425 | 9 | 16.191 | 2.887 | 32.234 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 34.0 | 21.8 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 6
J/43-6 | SGBM23 | Dec 7 2015 9:41AM | Dec 8 2015 1:55AM | 51.860 | 48.425 | 9, 20 | 15.522 | 3.435 | 32.903 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.5 | 36.0 | 7.5 | G45T2 | 1, 2, 3, 4 | 6, 10, 10, 10
J/43-7 | SGBM23 | Dec 1 2015 1:40PM | Dec 3 2015 3:36PM | 51.861 | 48.425 | 9 | 16.130 | 3.436 | 32.295 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 3, 7, 8, 6
J/43-8 | SGBM15 | Nov 20 2015 7:18PM | Nov 21 2015 3:53PM | 51.685 | 48.425 | 9, 15 | 15.817 | 3.260 | 32.608 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.2 | 36.0 | 7.8 | G45T2 | PJ 1923, PJ 1924, PJ 1925, PJ 1926, PJ 1927 | 7, 7, 7, 7, 8
J/44-4 | SGBM23 | Dec 7 2015 10:26AM | Dec 8 2015 10:00PM | 51.596 | 47.825 | 10, 20 | 12.045 | 3.771 | 35.780 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.0 | 38.0 | 22.6 | G45T2 | PJ 2783, PJ 2786, PJ 2786, PJ 2787 | 12, 7, 8, 10
J/44-9 | SGBM23 | Dec 10 2015 5:30PM | Dec 11 2015 8:10PM | 51.630 | 47.825 |  | 12.504 | 3.805 | 35.321 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 39.0 | 27.5 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 7, 9
J/44-14 | SGBM15 | Dec 4 2015 9:22PM | Dec 5 2015 10:27PM | 51.666 | 47.825 | 9 | 12.537 | 3.841 | 35.288 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 39.0 | -30.6 | G45T2 | PJ 2667, PJ 2668, PJ 2760, PJ 2671, PJ 2672 | 7, 9, 8, 8, 7
J/44-19 | SGBM23 | Dec 7 2015 10:01AM | Dec 8 2015 4:00PM | 51.436 | 47.825 | 9 | 12.236 | 3.611 | 35.589 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.8 | 36.0 | 16.8 | G45T2 | PJ 2756, PJ 2757, PJ 2759, PJ 2761, PJ 2762 | 8, 7, 7, 7, 7
F/44-1 | SGBM23 | Nov 23 2015 4:00PM | Nov 24 2015 5:05PM | 51.872 | 51.375 | 9 | 15.070 | 0.497 | 36.305 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.4 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 7, 7
M/49-1 | SGBM01 | Jan 4 2016 7:15PM | Jan 5 2016 10:35PM | 51.678 | 51.375 |  | 15.901 | 0.303 | 35.474 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.7 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 8, 6, 6, 6
M7/50-1 | SGBM01 | Jan 4 2016 7:35PM | Jan 5 2016 8:15PM | 51.783 | 51.175 |  | 15.479 | 0.608 | 35.696 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.9 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 10, 8, 9, 8
M/50-1 | SGBM02 | Dec 3 2015 7:49PM | Dec 4 2015 6:41PM | 51.900 | 51.175 | 9, 20, 30 | 14.585 | 0.725 | 36.590 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.7 | 38.0 | -100.0 | G45T2 | PJ 2593, PJ 2594, PJ 2598, PJ 2599, PJ 2601 | 9, 7, 7, 8, 7
M/51-1 | SGBM02 | Dec 2 2015 3:10PM | Dec 3 2015 3:08PM | 51.810 | 51.375 | 9, 32, 34 | 15.116 | 0.435 | 36.259 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.4 | 40.0 | 8.6 | G45T2 | 1, 2, 3, 4, 5 | 8, 9, 8, 8, 7
R/15-1 | SGBM20 | Dec 4 2015 4:05PM | Dec 5 2015 4:41PM | 55.790 | 52.775 | 9 | 26.542 | 3.015 | 26.233 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.7 | 26.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 6, 7, 7, 6
R/15-2 | SGBM20 | Dec 9 2015 3:00PM | Dec 10 2015 2:57PM | 55.805 | 52.775 | 9 | 26.323 | 3.030 | 26.452 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.9 | 31.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 3
M6/55-1 | SGBM01 | Jan 23 2016 9:20AM | Jan 23 2016 7:15PM | 51.902 | 51.275 |  | 14.721 | 0.627 | 36.554 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.7 | 36.0 | 13.7 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 8, 7, 7
U/61-1 | SGBM31 | Feb 4 2016 8:45AM | Feb 5 2016 11:30AM | 51.380 | 47.075 |  | 19.580 | 4.305 | 27.495 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.8 | 29.0 | -100.0 | G45T2 | PJ 5319, PJ 5322, PJ 5324, PJ 5325 | 10, 8, 6, 5
Ua/36-1 | SGBM16 | Dec 29 2015 1:00PM | Dec 29 2015 8:24PM | 52.278 | 51.325 |  | 25.325 | 0.953 | 26.000 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 22.5 | 28.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 7
Ua/37-1 | SGBM16 | Dec 28 2015 7:00PM | Dec 29 2015 3:35PM | 52.234 | 51.325 |  | 24.325 | 0.909 | 27.000 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 23.4 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 8, 8, 7, 7
AB/30-1 | SGBM22 | Oct 23 2015 3:30PM | Oct 23 2015 11:19PM | 50.150 | 48.475 |  | 23.305 | 1.675 | 25.170 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 21.8 | 30.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5 | 5, 7, 7, 6, 5
Ma/55-1 | SGBM23 | Dec 26 2015 9:48AM | Dec 26 2015 9:45PM | 51.790 | 50.075 |  | 13.683 | 1.715 | 36.392 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.5 | 38.0 | -100.0 | G45T2 | PJ 3558, PJ 3561, PJ3564, PJ 3565, PJ3566 | 10, 7, 7, 7, 7
Ma/56-1 | SGBM23 | Dec 28 2015 10:00AM | Dec 28 2015 12:00PM | 51.894 | 50.075 |  | 14.018 | 1.819 | 36.057 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.2 | 37.0 | 18.5 | G45T2 | PJ3573, PJ 3574, PJ 3576, PJ 3577, PJ 3578 | 10, 8, 7, 6, 6
Ma/57-1 | SGBM23 | Dec 26 2015 10:00AM | Dec 28 2015 6:07PM | 51.760 | 50.075 |  | 13.753 | 1.685 | 36.322 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.5 | 37.0 | 17.6 | G45T2 | PJ3596, PJ 3598, PJ 3601, PJ 3603, PJ 3607 | 8, 7, 8, 7, 7
Ma/58-1 | SGBM15 | Dec 30 2015 3:33PM | Dec 31 2015 8:45PM | 51.850 | 51.375 |  | 15.324 | 0.475 | 36.051 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.2 | 34.0 | -31.2 | G45T2 | PJ 3815, PJ 3817, PJ3821, Pending | 8, 10, 8, 8
Ma/58a-1 | SGBM23 | Dec 28 2015 1:00PM | Dec 29 2015 11:56AM | 51.807 | 51.075 |  | 14.977 | 0.732 | 36.098 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.3 | 36.0 | 15.2 | G45T2 | PJ 3642, PJ 3643, PJ 3644, PJ 3645, PJ 3648 | 8, 7, 7, 7, 7
La/56-1 | SGBM02 | Nov 27 2015 7:30PM | Nov 28 2015 6:34PM | 52.780 | 51.375 | 9, 16, 26 | 16.080 | -51.375 | 35.295 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.6 | 37.0 | 6.4 | G45T2 | 1, 2, 3, 4, 5 | 7, 8, 7, 8, 7
La/57-1 | SGBM02 | Nov 26 2015 1:00PM | Nov 27 2015 8:40PM | 51.800 | 51.375 | 9, 33 | 14.859 | -51.375 | 36.516 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 31.6 | 40.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 8, 7, 8, 7, 7, 3
La/58-1 | SGBM02 | Nov 24 2015 8:00PM | Nov 26 2015 8:39PM | 53.066 | 51.375 | 9 | 15.959 | 1.691 | 35.416 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.7 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 2, 7, 7, 7, 7, 6
La/59-1 | SGBM02 | Nov 24 2015 8:40PM | Nov 26 2015 6:58PM | 53.104 | 51.375 | 9 | 15.777 | 1.729 | 35.598 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 30.8 | 35.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 8, 6
J/42-1 | SGBM15 | Nov 13 2015 8:50PM | Nov 14 2015 4:43PM | 51.940 | 50.375 |  | 19.832 | 1.565 | 30.543 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.5 | 29.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 9, 9
J/42-2 | SGBM23 | Nov 17 2015 12:00PM | Nov 18 2015 2:21PM | 52.050 | 50.375 | 9 | 20.425 | -50.375 | 29.950 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.9 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 8, 7, 8, 7, 3
J/42-3 | SGBM23 | Nov 17 2015 10:26AM | Nov 18 2015 8:52PM | 51.865 | 50.375 | 9 | 19.136 | 1.490 | 31.239 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.1 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 6
J/42-4 | SGBM15 | Nov 14 2015 12:10PM | Nov 14 2015 11:55PM | 51.906 | 50.375 |  | 20.200 | 1.531 | 30.175 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.1 | 34.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5, 6 | 2, 7, 7, 7, 6, 5
J/42-5 | SGBM15 | Nov 13 2015 9:20AM | Nov 14 2015 6:12PM | 51.920 | 50.375 |  | 20.098 | 1.545 | 30.277 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.2 | 30.0 | -100.0 | G45T2 | 1, 2, 3 | 11, 11, 8
J/42-6 | SGBM23 | Nov 17 2015 11:18AM | Nov 17 2015 6:20PM | 51.980 | 50.375 | 9 | 20.325 | 1.605 | 30.050 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 32.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 6, 7, 7, 6, 6
J/42-7 | SGBM23 | Nov 17 2015 11:00AM | Nov 18 2015 10:56PM | 51.891 | 50.375 | 9 | 20.349 | 1.516 | 30.026 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 6, 6
J/42-8 | SGBM15 | Nov 14 2015 11:00AM | Nov 14 2015 6:50PM | 51.811 | 50.375 |  | 19.932 | 1.436 | 30.443 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.4 | 30.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 3, 11, 9, 7
X9/Y6a-1 | SGBM20 | Nov 22 2015 5:15PM | Nov 23 2015 3:52PM | 55.075 | 55.075 | 9 | 26.595 | 0.000 | 28.480 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 29.0 | 4.3 | G35T2 | 1, 2, 3, 4 | 7, 7, 7, 8
Pa/18-1 | SGBM20 | Dec 5 2015 8:00AM | Dec 7 2015 11:10PM | 55.813 | 55.075 | 9 | 33.997 | 0.738 | 21.078 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 18.3 | 21.0 | -100.0 | G35T2 | 1, 2, 3 | 5, 7, 9
Qa/18-1 | SGBM20 | Nov 18 2015 1:00PM | Nov 18 2015 6:07PM | 55.805 | 55.075 |  | 32.447 | 0.730 | 22.628 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 19.6 | 22.0 | -100.0 | G35T2 | 1, 2, 3 | 7, 8, 7
X10/Y3-1 | SGBM18 | Dec 12 2015 12:00PM | Dec 14 2015 1:39PM | 55.376 | 55.075 |  | 22.873 | 0.301 | 32.202 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 37.0 | 29.1 | G35T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 7, 8, 7, 1
J/27-2a | SGBM20 | Nov 5 2015 9:55AM | Nov 5 2015 4:56PM | 52.310 | 48.825 |  | 17.163 | 3.485 | 31.662 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 33.0 | -100.0 | G45T2 | 1, 2, 3, 4, 5 | 7, 7, 7, 7, 5
J/16-1 | SGBM20 | Dec 4 2015 4:30PM | Dec 4 2015 9:15PM | 55.640 | 51.375 |  | 19.738 | 4.265 | 31.637 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 41.0 | -100.0 | G35T2 | 1, 2, 3, 4, 5, 6 | 7, 7, 9, 7, 7, 4
Z/57-1 | SGBM19 | Jan 4 2016 8:30AM | Jan 4 2016 11:10PM | 49.524 | 48.625 |  | 15.853 | 0.899 | 32.772 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.4 | 35.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 10, 8, 8, 9
Z/57-2 | SGBM05 | Dec 30 2015 6:50PM | Dec 31 2015 5:10PM | 49.519 | 48.625 |  | 14.906 | 0.894 | 33.719 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 29.2 | 34.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 7, 11, 11, 5
T2a/50a-1 | SGBM20 | Jan 26 2016 1:57PM | Jan 27 2016 3:20PM | 51.735 | 51.325 |  | 22.631 | 0.410 | 28.694 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.8 | 31.0 | 24.8 | G35T2 | PJ 4949, PJ 4953, PJ 4957, PJ 4964 | 10, 10, 8, 3
W/39-1 | SGBM03 | Aug 8 2015 9:45AM | Aug 8 2015 4:05PM | 49.518 | 47.375 |  | 16.018 | 2.143 | 31.357 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.2 | 36.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 11, 11, 11, 3
W/39-2 | SGBM03 | Aug 5 2015 9:00AM | Aug 5 2015 3:10PM | 49.415 | 47.375 |  | 15.915 | 2.040 | 31.460 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.2 | 32.5 | 19.3 | G45T2 | 1, 2, 3, 4 | 10, 10, 11, 1.5
V/39-1a | SGBM19 | Dec 30 2015 8:00AM | Dec 30 2015 7:15PM | 49.940 | 47.075 |  | 17.017 | 2.865 | 30.058 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 34.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 11, 10, 8, 5
V/39-1b | SGBM17 | Dec 28 2015 8:40AM | Dec 28 2015 11:10PM | 49.652 | 47.075 |  | 15.827 | 2.577 | 31.248 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.1 | 33.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 8, 8, 9
U/39-1 | SGBM20 | Jan 16 2016 8:36AM | Jan 16 2016 11:05PM | 52.340 | 51.325 |  | 22.159 | 1.015 | 29.166 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 29.0 | -100.0 | G35T2 | 1, 2, 3, 4 | 8, 7, 7, 7
Tb/40-1 | SGBM20 | Jan 21 2016 9:03AM | Jan 21 2016 3:10PM | 52.200 | 51.325 |  | 22.059 | 0.875 | 29.266 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 25.3 | 31.0 | 22.3 | G35T2 | 1, 2, 3, 4 | 8, 8, 8, 7
W/30-1b | SGBM03 | Oct 23 2015 8:10AM | Oct 23 2015 7:05PM | 48.519 | 47.375 |  | 23.882 | 1.144 | 23.493 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.3 | 22.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 5, 6, 7, 4
W/30-1a | SGBM03 | Oct 26 2015 10:00AM | Oct 26 2015 10:49PM | 48.426 | 47.375 |  | 23.865 | 1.051 | 23.510 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.4 | 25.0 | 8.1 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
X/28-1b | SGBM03 | Oct 25 2015 7:20PM | Oct 26 2015 12:45PM | 48.612 | 47.375 |  | 23.907 | 1.237 | 23.468 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.3 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
X/28-1a | SGBM03 | Oct 27 2015 8:00AM | Oct 27 2015 6:23PM | 48.730 | 47.375 |  | 23.650 | 1.355 | 23.725 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 20.5 | 25.0 | -100.0 | G45T2 | 1, 2, 3, 4 | 7, 7, 7, 4
P/1-1 | SGBM19 | Mar 19 2016 3:00PM | Mar 21 2016 7:00PM | 55.765 | 55.075 |  | 23.050 | 0.690 | 32.025 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 38.0 | -100.0 | G35T2 | pj7009, pj7012, pj7016, pj7018, pj7025 | 8, 10, 8, 8, 4
K/3-2 | SGBM19 | Feb 17 2016 8:00AM | Feb 17 2016 3:45PM | 55.631 | 53.375 |  | 20.745 | 2.256 | 32.630 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.3 | 32.0 | -100.0 | G35T2 | PJ5631, PJ5633, PJ5637, PJ5641 | 8, 8, 8, 8
K/5-2 | SGBM19 | Feb 15 2016 8:00AM | Feb 15 2016 4:40PM | 55.670 | 53.375 |  | 21.220 | 2.295 | 32.155 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 37.0 | -100.0 | G35T2 | PJ5526, PJ5527, PJ5530, PJ5533, PJ5536 | 8, 8, 7, 7, 7
K/6-2 | SGBM19 | Feb 18 2016 8:00AM | Feb 18 2016 1:40PM | 55.593 | 53.375 |  | 21.239 | 2.218 | 32.136 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 36.0 | -100.0 | G35T2 | PJ5686, PJ5688, PJ5689, PJ5691 | 10, 10, 8, 8
K/4-1 | SGBM19 | Feb 12 2016 11:00AM | Feb 12 2016 6:30PM | 55.740 | 53.375 |  | 20.929 | 2.365 | 32.446 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 43.0 | -100.0 | G35T2 | PJ 5437, PJ5438, PJ5441, PJ5445, PJ 5448, PJ5455 | 7, 8, 8, 8, 8, 4
K/4-2 | SGBM19 | Feb 15 2016 6:11PM | Feb 16 2016 2:40PM | 55.640 | 53.375 |  | 20.871 | 2.265 | 32.504 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 40.0 | -100.0 | G35T2 | PJ 5576, PJ 5577, PJ 5578, 5580, 5584, PJ 5591 | 8, 8, 8, 6, 6, 4
K/6-1 | SGBM17 | Feb 20 2016 8:14AM | Feb 20 2016 2:45PM | 55.573 | 53.375 |  | 21.423 | 2.198 | 31.952 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 41.0 | -100.0 | G35T2 | PJ 5782, PJ 5784, PJ 5787, PJ 5792, PJ 5795 | 8, 7, 8, 8, 10
K/8-1 | SGBM17 | Feb 15 2016 11:00AM | Feb 15 2016 9:30PM | 55.943 | 53.375 |  | 21.710 | 2.568 | 31.665 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 37.0 | -100.0 | G35T2 | PJ5554, PJ5558, PJ5560, PJ5563, PJ5566 | 8, 7, 8, 7, 7
K/8-2 | SGBM19 | Feb 17 2016 12:00PM | Feb 18 2016 1:05AM | 55.960 | 53.375 |  | 21.489 | 2.585 | 31.886 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 41.0 | -100.0 | G35T2 | PJ5668, PJ5669, PJ5672, PJ5673, PJ5675 | 9, 9, 10, 9, 4
K/9-1 | SGBM17 | Feb 22 2016 8:30AM | Feb 22 2016 1:45PM | 55.908 | 53.375 |  | 21.283 | 2.533 | 32.092 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 35.0 | -100.0 | G35T2 | PJ 5835, PJ 5836, PJ 5837, PJ 5838 | 10, 9, 9, 7
K/9-2 | SGBM19 | Feb 24 2016 5:10PM | Feb 25 2016 10:30AM | 55.926 | 53.375 |  | 21.341 | 2.551 | 32.034 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 37.0 | -100.0 | G35T2 | PJ 5977, PJ 5978, PJ 5979, PJ 5982, PJ 5984 | 9, 8, 8, 8, 4
K/13-1 | SGBM20 | Feb 23 2016 9:10AM | Feb 23 2016 7:55PM | 55.691 | 53.375 |  | 21.530 | 2.316 | 31.845 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 33.0 | -100.0 | G35T2 | PJ 5912, PJ 5914, PJ 5920, PJ 5922 | 9, 8, 8, 8
K/13-2 | SGBM20 | Feb 25 2016 1:00PM | Feb 25 2016 7:30PM | 55.710 | 53.375 |  | 21.516 | 2.335 | 31.859 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 32.0 | -100.0 | G35T2 | PJ6012, PJ6013, PJ6020, PJ6023 | 8, 8, 8, 8
K/14-1 | SGBM20 | Mar 5 2016 11:19AM | Mar 5 2016 7:25PM | 55.576 | 53.375 |  | 21.348 | 2.201 | 32.027 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 34.0 | -100.0 | G35T2 | C480017896, C480017897, C480017899 | 11.5, 11.5, 11
K/15-1 | SGBM20 | Feb 29 2016 8:00AM | Feb 29 2016 1:30PM | 55.676 | 49.375 |  | 17.171 | 6.301 | 32.204 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 30.0 | -100.0 | G35T2 | PJ 6151, PJ 6154, PJ 6156, PJ 6159 | 8, 8, 7, 7
K/15-2 | SGBM31 | Mar 29 2016 10:35AM | Mar 30 2016 5:30PM | 55.751 | 49.375 |  | 17.493 | 6.376 | 31.882 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 30.0 | -100.0 | G35T2 | pj7446, pj7447, pj7448, pj7450 | 9, 7, 7, 7
J/3-1 | SGBM19 | Feb 19 2016 8:16AM | Feb 19 2016 7:16PM | 55.576 | 53.375 |  | 21.147 | 2.201 | 32.228 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 38.0 | -100.0 | G35T2 | PJ 5753, PJ 5755, PJ 5757, PJ 5959 | 10, 10, 10, 8
J/3-2 | SGBM17 | Feb 23 2016 8:17AM | Feb 23 2016 3:30PM | 55.576 | 53.375 |  | 21.082 | 2.201 | 32.293 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 30.0 | -100.0 | G35T2 | PJ 5891, PJ 5892, PJ 5893, PJ 5896 | 8, 8, 7, 7
J/5-1 | SGBM17 | Feb 22 2016 8:45AM | Feb 22 2016 8:00PM | 55.587 | 53.375 |  | 21.194 | 2.212 | 32.181 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 43.0 | -100.0 | G35T2 | PJ 5862, PJ 5864, PJ 5865, PJ 5870, PJ 5875 | 10, 9, 10, 8, 6
J/6-1 | SGBM17 | Feb 23 2016 9:05AM | Feb 23 2016 6:50PM | 55.625 | 53.475 |  | 21.490 | 2.150 | 31.985 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 30.0 | -100.0 | G35T2 | PJ 5907, PJ 5908, PJ 5915 | 10, 10, 10
J/6-2 | SGBM19 | Mar 1 2016 1:35PM | Mar 1 2016 7:50PM | 55.610 | 53.475 |  | 21.859 | 2.135 | 31.616 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 33.0 | -100.0 | G35T2 | C480017659, C480017661, C480017662, C480017668 | 9, 11, 10, 3
J/6-3 | SGBM17 | Feb 27 2016 8:00AM | Feb 27 2016 3:30PM | 55.590 | 53.475 |  | 21.933 | 2.115 | 31.542 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.3 | 29.0 | -100.0 | G35T2 | PJ6116, PJ6120, PJ6123, PJ6127 | 10, 8, 8, 3
J/11-2 | SGBM20 | Mar 8 2016 1:15PM | Mar 8 2016 11:11PM | 55.860 | 49.475 |  | 17.488 | 6.385 | 31.987 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 29.0 | -27.7 | G35T2 | PJ 6480, PJ6483, PJ 6486, PJ6489, PJ6426 | 1, 10, 8, 8, 2
J/11-3 | SGBM20 | Mar 4 2016 8:09AM | Mar 4 2016 3:22PM | 55.320 | 49.475 |  | 17.388 | 5.845 | 32.087 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 32.0 | -100.0 | G35T2 | PJ6332, PJ 6331, PJ 6337, PJ 6339 | 8, 8, 8, 8
J/12-1 | SGBM20 | Feb 24 2016 10:15AM | Feb 24 2016 7:45PM | 55.630 | 53.375 |  | 21.439 | 2.255 | 31.936 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 32.0 | -100.0 | G35T2 | PJ 5959, PJ 5960, PJ 5965, PJ 5970 | 8, 8, 8, 8
J/12-2 | SGBM20 | Feb 25 2016 12:50PM | Feb 26 2016 2:50PM | 55.687 | 53.375 |  | 21.285 | 2.312 | 32.090 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 32.0 | -100.0 | G35T2 | PJ6037, PJ6038, PJ6040, PJ6044 | 8, 8, 8, 8
J/14-1 | SGBM20 | Mar 1 2016 8:00AM | Mar 1 2016 4:05PM | 55.722 | 53.375 |  | 21.355 | 2.347 | 32.020 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 33.0 | -100.0 | G35T2 | C480017636, C480017640, C480017645, C480017647 | 10, 10, 10, 3
J/14-2 | SGBM20 | Mar 22 2016 9:00AM | Mar 22 2016 11:00PM | 55.777 | 53.375 |  | 21.791 | 2.402 | 31.584 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 32.0 | -100.0 | G35T2 | pj7073, pj7074, pj7076, pj7079 | 8, 8, 8, 8
J/15-1 | SGBM19 | Mar 24 2016 6:30PM | Mar 26 2016 3:00AM | 55.792 | 49.375 |  | 17.422 | 6.417 | 31.953 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 42.0 | 14.3 | G35T2 | pj7258, pj7259, pj7260, pj7261, pj7262, pj7263, pj7264 | 8, 7, 8, 7, 6, 4, 2
J/15-2 | SGBM23 | Mar 29 2016 10:00AM | Mar 29 2016 8:20PM | 55.743 | 49.375 |  | 17.686 | 6.368 | 31.689 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 34.0 | -100.0 | G35T2 | pj7401, pj74102, pj7408, Pending | 8, 10, 8, 8
X11/Y2a-1 | SGBM19 | Mar 21 2016 3:30PM | Mar 22 2016 5:50PM | 55.690 | 55.075 |  | 21.974 | 0.615 | 33.101 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.7 | 33.0 | -100.0 | G35T2 | pj7059, pj7061, pj7062, pj7064 | 8, 9, 8, 8
X11/Y3a-1 | SGBM31 | Mar 21 2016 4:10PM | Mar 22 2016 3:30AM | 55.605 | 55.075 |  | 25.009 | 0.530 | 30.066 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.0 | 23.0 | -11.7 | G35T2 | pj7052, pj7053, pj7054 | 8, 8, 7
X11/Y4a-1 | SGBM19 | Mar 18 2016 4:00PM | Mar 19 2016 5:00PM | 55.680 | 55.075 |  | 22.892 | 0.605 | 32.183 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 34.0 | -27.9 | G35T2 | pj6943, pj6945, pj6946, pj6947 | 8, 10, 8, 8
Pa/5-1 | SGBM22 | Mar 18 2016 5:00PM | Mar 19 2016 7:00PM | 55.730 | 55.075 |  | 22.915 | 0.655 | 32.160 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 35.0 | -100.0 | G35T2 | pj6953, pj6954, pj6955, pj6957 | 10, 8, 9, 8
Pa/6-1 | SGBM19 | Mar 21 2016 11:00AM | Mar 22 2016 1:25AM | 55.802 | 55.075 |  | 23.103 | 0.727 | 31.972 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 32.0 | 4.3 | G35T2 | pj7044, pj7045, pj7048 | 11, 11, 10
Pa/9-1 | SGBM20 | Mar 15 2016 5:30PM | Mar 16 2016 3:20PM | 55.773 | 55.075 |  | 23.567 | 0.698 | 31.508 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.3 | 31.0 | -100.0 | G35T2 | pj6773, pj6775, pj6776, pj6780 | 10, 7, 7, 7
Pa/11-1 |  |  |  | 0.000 | 51.075 |  | 0.000 | 0.000 | 51.075 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 |  | 44.2 | 0.0 | 0.0 | G35T2
Pa/12-1 | SGBM23 | Mar 15 2016 5:35PM | Mar 17 2016 1:50PM | 55.778 | 55.075 |  | 22.860 | 0.703 | 32.215 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 33.0 | -100.0 | G35T2 | pj6854, pj6855, pj6858, pj6860 | 8, 8, 9, 8
L/13-1 | SGBM20 | Mar 1 2016 3:00PM | Mar 1 2016 9:20PM | 55.702 | 53.375 |  | 21.552 | 2.327 | 31.823 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 37.0 | -100.0 | G35T2 | C480017668, C520125659, C520125658, C480017670 | 7, 10, 10, 10
L/14-1 | SGBM20 | Mar 3 2016 2:00PM | Mar 3 2016 9:30PM | 55.672 | 53.375 |  | 21.520 | 2.297 | 31.855 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 35.0 | -100.0 | G35T2 | PJ 6320, PJ 6322, PJ 6326, PJ 6329 | 9, 8, 10, 8
L/14-2 | SGBM20 | Feb 29 2016 12:10PM | Feb 29 2016 9:00PM | 55.694 | 53.375 |  | 21.491 | 2.319 | 31.884 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 33.0 | -100.0 | G35T2 | PJ 6187, PJ 6188, PJ 6191, PJ 6192 | 8, 8, 8, 9
L/15-1 | SGBM20 | Feb 26 2016 1:00PM | Feb 26 2016 7:30PM | 55.710 | 49.375 |  | 17.004 | 6.335 | 32.371 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 30.0 | -100.0 | G35T2 | PJ6062, PJ6065, PJ6071 | 10, 10, 10
J/8-1 | SGBM17 | Feb 29 2016 10:10AM | Feb 29 2016 7:17PM | 55.926 | 54.675 |  | 22.581 | 1.251 | 32.094 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 32.0 | -100.0 | G35T2 | PJ 6178, PJ 6179, PJ 6183, PJ 6186 | 8, 8, 8, 8
J/8-4 | SGBM17 | Mar 2 2016 8:00AM | Mar 2 2016 2:40PM | 55.940 | 54.675 |  | 22.815 | 1.265 | 31.860 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 31.0 | -100.0 | G35T2 | PJ 6244, PJ 6246, PJ 6249, PJ 6251 | 8, 8, 8, 7
J/8-6 | SGBM19 | Mar 8 2016 12:17PM | Mar 8 2016 10:05PM | 55.945 | 54.675 |  | 22.993 | 1.270 | 31.682 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 30.0 | -27.4 | G35T2 | PJ 6475, PJ 6477, PJ 6480 | 11, 10, 9
J/8-5 | SGBM23 | Mar 5 2016 8:15AM | Mar 5 2016 3:30PM | 55.975 | 54.675 |  | 22.962 | 1.300 | 31.713 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.5 | 35.0 | -100.0 | G35T2 | C480017876, C480017875, C480017879, C480017882 | 11.5, 6.5, 10, 7
J/17-1 | SGBM31 | Mar 30 2016 10:00AM | Mar 31 2016 5:00PM | 55.641 | 51.075 |  | 19.056 | 4.566 | 32.019 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 31.0 | -100.0 | G35T2 | 7480, pj7478, pj7481, pj7487 | 7, 8, 8, 8
H/3-1 | SGBM19 | Mar 5 2016 1:20PM | Mar 5 2016 8:25PM | 55.470 | 53.375 |  | 20.942 | 2.095 | 32.433 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 33.0 | -28.1 | G35T2 | PJ 6369, PJ 6370, PJ 6372, PJ 6374 | 8, 9, 8, 8
H/3-2 | SGBM17 | Mar 3 2016 1:23PM | Mar 3 2016 9:35PM | 55.546 | 53.375 |  | 21.289 | 2.171 | 32.086 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 33.0 | -100.0 | G35T2 | PJ 6321, PJ 6323, PJ 6325, PJ 6328 | 8, 8, 9, 8
H/5-1 | SGBM17 | Feb 24 2016 8:00AM | Feb 24 2016 1:45PM | 55.498 | 53.375 |  | 21.077 | 2.123 | 32.298 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 34.0 | -100.0 | G35T2 | PJ 5937, PJ 5938, PJ 5940, PJ 5941 | 8, 8, 10, 8
H/5-2 | SGBM17 | Feb 29 2016 8:12AM | Feb 29 2016 2:15PM | 55.425 | 53.375 |  | 21.012 | 2.050 | 32.363 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 35.0 | -100.0 | G35T2 | PJ 6155, PJ 6157, PJ 6161, PJ 6162 | 10, 10, 8, 7
H/6-1 | SGBM17 | Feb 26 2016 8:00AM | Feb 26 2016 3:45PM | 55.470 | 53.475 |  | 21.258 | 1.995 | 32.217 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.9 | 36.0 | -100.0 | G35T2 | PJ6041, PJ6043, PJ6046, PJ6049 | 8, 10, 10, 8
H/6-2 | SGBM19 | Mar 3 2016 12:20PM | Mar 3 2016 5:30PM | 55.490 | 53.475 |  | 21.493 | 2.015 | 31.982 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 32.0 | 15.5 | G35T2 | PJ 6303, PJ 6304, PJ 6306, PJ 6309 | 8, 8, 8, 8
H/6-3 | SGBM23 | Mar 5 2016 6:00PM | Mar 5 2016 10:05AM | 55.440 | 53.475 |  | 21.058 | 1.965 | 32.417 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 34.0 | -100.0 | G35T2 | C480017859, C480017860, C480017863 | 11.5, 11.5, 11
H/11-1 | SGBM20 | Mar 30 2016 8:40AM | Mar 31 2016 5:30PM | 55.740 | 49.475 |  | 17.332 | 6.265 | 32.143 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 32.0 | -100.0 | G35T2 | pj7482, pj7483, pj7485, pj7489 | 8, 8, 8, 8
H/11-2 | SGBM19 | Mar 24 2016 3:35PM | Mar 25 2016 3:20PM | 55.625 | 49.475 |  | 17.837 | 6.150 | 31.638 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 30.0 | 2.6 | G35T2 | pj7187, pj7191, pj7195 | 10, 10, 10
H/11-3 | SGBM20 | Apr 1 2016 1:00PM | Apr 2 2016 2:10PM | 55.830 | 49.475 |  | 17.646 | 6.355 | 31.829 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 37.0 | 8.8 | G35T2 | pj7535, pj7537, pj7540, pj7542 | 10, 10, 10, 7
H/12-1 | SGBM23 | Mar 26 2016 8:30AM | Mar 28 2016 10:45PM | 55.523 | 53.375 |  | 21.385 | 2.148 | 31.990 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 33.0 | -100.0 | G35T2 | pj7366, pj7367, pj7369, pj7370 | 11, 7, 8, 7
H/12-2 | SGBM20 | Apr 1 2016 8:10AM | Apr 1 2016 5:09PM | 55.780 | 53.375 |  | 20.382 | 2.405 | 32.993 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.6 | 32.0 | -28.6 | G35T2 | pj7508, pj7500, pj7512, pj7515 | 8, 8, 8, 8
H/14-1 | SGBM23 | Mar 25 2016 3:30PM | Mar 26 2016 1:20AM | 55.532 | 53.375 |  | 21.283 | 2.157 | 32.092 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 33.0 | -27.8 | G35T2 | pj7248, pj7251, pj7256 | 11, 11, 11
H/14-2 | SGBM19 | Mar 23 2016 11:50AM | Mar 23 2016 11:25PM | 55.670 | 53.375 |  | 21.413 | 2.295 | 31.962 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.7 | 32.0 | -100.0 | G35T2 | pj7127, pj7129, pj7130, pj7132 | 7, 8, 8, 9
H/15-1 | SGBM19 | Mar 23 2016 1:00PM | Mar 24 2016 4:30PM | 55.640 | 49.375 |  | 17.801 | 6.265 | 31.574 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.3 | 33.0 | -100.0 | G35T2 | pj7146, pj7147, pj7148, pj7151 | 9, 8, 8, 8
H/15-2 | SGBM31 | Mar 30 2016 9:20AM | Mar 31 2016 9:00PM | 55.640 | 49.375 |  | 17.497 | 6.265 | 31.878 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 31.0 | -100.0 | G35T2 | pj7497, Pending, pj7499, pj7500 | 8, 8, 7, 8
H/16-1 | SGBM23 | Mar 23 2016 1:45PM | Mar 24 2016 2:30PM | 55.600 | 51.075 |  | -37.300 | 4.525 | 88.375 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 76.5 | 33.0 | -100.0 | G35T2 | pj7141, pj7142, pj7143, pj7144 | 9, 8, 8, 8
H/17-1 | SGBM23 | Mar 23 2016 2:15PM | Mar 24 2016 2:40AM | 55.570 | 51.075 |  | 19.296 | 4.495 | 31.779 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.5 | 30.0 | -100.0 | G35T2 | pj7136, pj7137, pj7138, pj7139 | 8, 8, 7, 7
G/3-1 | SGBM31 | Mar 16 2016 10:45AM | Mar 16 2016 6:25PM | 55.357 | 55.075 |  | -33.000 | 0.282 | 88.075 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 76.3 | 23.0 | -76.3 | G35T2 | pj6793, pj6798, pj6796 | 8, 7, 8
G/7-1 | SGBM23 | Mar 14 2016 1:00PM | Mar 15 2016 8:30PM | 55.868 | 52.775 |  | 21.660 | 3.093 | 31.115 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 26.9 | 32.0 | -100.0 | G35T2 | pj6760, pj6761, pj6764, pj6766 | 8, 8, 8, 8
G/7-2 | SGBM20 | Mar 14 2016 10:00AM | Mar 14 2016 7:10PM | 55.840 | 52.775 |  | 21.541 | 3.065 | 31.234 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.0 | 34.0 | -100.0 | G35T2 | pj6702, pj6703, pj6704, pj6707 | 8, 8, 8, 10
G/10-1 | SGBM23 | Mar 22 2016 5:20PM | Mar 23 2016 7:20PM | 55.847 | 49.375 |  | 16.915 | 6.472 | 32.460 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.1 | 33.0 | -100.0 | G35T2 | pj7118, pj7119, pj7120, pj7121 | 10, 8, 7, 8
G/10-2 | SGBM23 | Mar 19 2016 1:35PM | Mar 22 2016 12:00AM | 55.860 | 49.375 |  | 17.076 | 6.485 | 32.299 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 28.0 | 36.0 | -100.0 | G35T2 | pj7039, pj7040, pj7042, pj7043 | 10, 10, 8, 8
G/13-1 | SGBM23 | Mar 22 2016 9:30AM | Mar 23 2016 1:00AM | 55.490 | 49.375 |  | -38.800 | 6.115 | 88.175 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 76.4 | 37.0 | -100.0 | G35T2 | pj7082, pj7083, pj7084, pj7086 | 10, 10, 8, 9
G/13-2 | SGBM19 | Mar 23 2016 6:25PM | Mar 24 2016 9:30PM | 55.475 | 49.375 |  | 17.530 | 6.100 | 31.845 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 33.0 | -100.0 | G35T2 | pj7168, pj7169, pj7171, pj7172 | 8, 8, 9, 8
G/14-1 | SGBM23 | Mar 25 2016 2:30PM | Mar 28 2016 3:00PM | 55.442 | 49.375 |  | 17.500 | 6.067 | 31.875 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 31.0 | 12.3 | G35T2 | pj7338, pj7339, pj7340, pj7341 | 8, 8, 8, 7
G/14-2 | SGBM31 | Mar 30 2016 8:00AM | Mar 30 2016 8:05PM | 55.588 | 49.375 |  | 17.692 | 6.213 | 31.683 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.4 | 36.0 | -100.0 | G35T2 | pj7358, pj7459, pj7460, pj7461 | 10, 8, 10, 8
G/15-1 | SGBM23 | Mar 23 2016 7:00PM | Mar 24 2016 7:00PM | 55.502 | 49.375 |  | 17.307 | 6.127 | 32.068 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.8 | 34.0 | -100.0 | G35T2 | pj7154, pj7155, pj7158, Pending | 10, 8, 8, 8
G/15-2 | SGBM19 | Mar 25 2016 11:20AM | Mar 26 2016 10:05AM | 55.460 | 49.375 |  | 17.511 | 6.085 | 31.864 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.6 | 39.0 | 41.3 | G35T2 | pj7265, pj7266, pj7267 | 18, 11, 10
G/17-1 | SGBM19 | Mar 25 2016 5:00PM | Mar 26 2016 4:20PM | 55.523 | 51.075 |  | 19.284 | 4.448 | 31.791 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 27.5 | 33.0 | -100.0 | G35T2 | pj7274, pj7275, pj7279, pj7280, pj7282 | 8, 7, 8, 8, 2
Tc/45-1 | SGBM31 | Mar 11 2016 2:30PM | Mar 11 2016 11:20PM | 51.673 | 50.575 |  | 22.082 | 1.098 | 28.493 |  | 0.0 | 0.0 | 12T20+9T20 | T12-225 | 12 | 24.7 | 35.0 | 10.3 | G35T2 | 1, 2, 3, 4 | 10, 9, 8, 8