## 800
Summary List for 18916523-MRT-v201
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
test | SGBM09 | Sep 4 2016 7:09PM |  | 0.000 | 27 | 2 | -1.000 | -27.000 | 28.000 |  | 0.0 | 0.0 | 22test22 | T123 |  | 14.1 | 0.0 | -14.6 | G123

## 1200
Summary List for 18916523-MRT-v201
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DD18-1 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD18-2 | SGBM12 | Aug 22 2016 1:30PM |  | 38.962 | 32.575 | 4.8, 6.5, 6.9, 7.2, 8.7, 10.5 | 30.580 | 6.387 | 1.995 |  | 5.8 | 5.8 | 18T20 | T12-200 | 4 | 2.3 | 0.0 | -100.0 | G40T2
DD18-3 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD18-4 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD17-1 | SGBM12 | Sep 4 2016 10:30AM |  | 38.825 | 32.575 | 8, 8.6, 10.4 | 29.085 | 6.250 | 3.490 |  | 3.1 | 3.1 | 18T20 | T12-200 | 4.5 | 3.9 | 0.0 | -100.0 | G40T2
DD17-2 | SGBM12 | Aug 27 2016 6:45PM |  | 39.005 | 32.575 | 7.3, 8, 9.6 | 29.650 | 6.430 | 2.925 |  | 3.1 | 3.1 | 18T20 | T12-200 | 4.8 | 3.3 | 0.0 | -100.0 | G40T2
DD17-3 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD17-4 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD16-1 |  |  |  | 0.000 | 32.575 |  | 0.000 | -32.575 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 | 2+2+2+2+2 | 36.8 | 0.0 | 0.0 | G40T2
DD16-2 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD16-3 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2
DD16-4 |  |  |  | 0.000 | 32.575 |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 18T20 | T12-200 |  | 36.8 | 0.0 | 0.0 | G40T2

## 1350
Summary List for 18916523-MRT-v201
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DD20-1 | SGBM31 | Aug 29 2016 6:20PM |  | 39.172 | 32.275 | 17.3, 17.9 | 22.041 | 6.897 | 10.234 |  | 2.7 | 2.7 | 22T20 | T12-200 | 11.3 | 14.7 | 0.0 | -100.0 | G40T2
DD20-2 | SGBM31 | Sep 4 2016 9:45AM |  | 39.240 | 32.275 | 16, 16.5, 18.1 | 21.765 | 6.965 | 10.510 |  | 2.7 | 2.7 | 22T20 | T12-200 | 11.5 | 15.0 | 0.0 | -100.0 | G40T2
DD20-3 | SGBM31 | Aug 24 2016 4:00PM |  | 39.168 | 32.275 | 16.5, 17.9, 18.3 | 22.165 | 6.893 | 10.110 |  | 2.7 | 2.7 | 22T20 | T12-200 | 11.6 | 14.5 | 0.0 | -100.0 | G40T2
DD20-4 | SGBM31 | Aug 19 2016 3:20PM | Aug 22 2016 10:50PM | 39.003 | 32.275 | 16.2, 18, 18.5 | 21.839 | 6.728 | 10.436 |  | 2.9 | 2.7 | 22T20 | T12-200 | 12 | 14.9 | 19.0 | -100.0 | G40T2 | c570008122, c570008123, c570008124 | 8, 8, 3
DD19-1 | SGBM31 | Sep 1 2016 5:30PM |  | 39.152 | 32.275 | 14.3, 16.2 | 22.973 | 6.877 | 9.302 |  | 3.8 | 3.8 | 22T20 | T12-200 | 10.3 | 13.3 | 0.0 | -100.0 | G40T2
DD19-2 | SGBM32 | Aug 22 2016 4:30AM | Aug 24 2016 8:10PM | 39.214 | 32.275 | 13.65, 14.6, 16.8 | 22.773 | 6.939 | 9.502 |  | 3.8 | 3.8 | 22T20 | T12-200 | 12 | 13.6 | 17.0 | 25.0 | G40T2 | c570008148, c570008149 | 10, 7
DD19-3 | SGBM31 | Aug 27 2016 11:50AM |  | 39.146 | 32.275 | 14, 15 | 24.092 | 6.871 | 8.183 |  | 2.6 | 2.6 | 22T20 | T12-200 | 9.3 | 11.7 | 0.0 | -100.0 | G40T2
DD19-4 | SGBM31 | Sep 6 2016 12:12PM |  | 39.050 | 32.275 | 10.7, 12.6, 14.2 | 27.070 | 6.775 | 5.205 |  | 3.8 | 3.8 | 22T20 | T12-200 | 7.3 | 7.5 | 0.0 | -100.0 | G40T2
CBP1 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP2 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP3 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP4 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP5 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP6 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP7 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP8 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP9 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP10 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP11 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP12 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP13 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP14 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP15 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP16 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP17 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP18 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP19 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP20 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP21 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP22 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP23 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP24 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP25 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP26 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP27 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP28 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP29 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP30 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP31 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP32 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP33 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP34 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP35 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP36 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP37 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP38 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP39 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP40 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP41 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP42 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP43 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP44 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP45 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP46 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP47 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP48 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP49 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP50 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP51 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP52 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP53 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP54 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP55 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP56 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP57 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP58 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP59 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP60 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP61 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP62 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP63 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP64 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP65 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP66 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP67 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP68 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP69 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP70 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP71 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP72 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP73 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP74 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP75 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP76 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP77 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP78 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP79 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP80 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP81 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP82 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP83 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP84 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP85 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP86 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP87 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP88 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP89 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP90 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP91 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP92 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP93 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP94 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP95 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP96 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP97 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP98 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP99 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP100 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP101 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP102 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP103 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP104 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP105 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP106 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP107 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP108 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP109 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP110 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP111 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP112 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP113 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP114 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP115 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP116 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP117 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP118 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP119 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP120 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP121 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP122 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP123 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP124 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP125 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP126 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP127 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP128 |  |  |  | 0.000 | 42.075 |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 25T25 | T10-125 |  | 60.2 | 0.0 | 0.0 | G40T2