## 750
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
14 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
15 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
16 |  |  |  | 55555.000 | 9.875 |  | 55555.000 | 0.000 | -55545.100 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | -24542.3 | 0.0 | -100.0 | 40 TREMIE 2
19 |  | Aug 22 2016 6:33PM | Aug 23 2016 10:20PM | 11.230 | 6.275 | 14.6, 15.8 | -4.926 | 1.655 | 11.201 |  | 4.1 | 3.7 | 12T16 | R8-175 | 16.8 | 4.9 | 8.0 | -6.4 | 40 TREMIE 2 | 2412829, 2412832 | 8, 4
20 |  | Sep 6 2016 7:00AM | Sep 8 2016 3:18PM | 11.158 | 9.575 | 15.7, 18 | -6.008 | 1.583 | 15.583 |  | 7.3 | 2.9 | 12T16 | R8-175 | 12 | 6.9 | 8.0 | 1.1 | 40 TREMIE 2 | 2418596 | 8
21 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
22 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
23 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
24 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
25 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
26 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
27 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
28 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
29 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
30 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
31 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
32 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
62 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
63 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
64 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
66 | SGBM01 | Aug 24 2016 7:00PM | Sep 1 2016 11:05AM | 11.278 | 9.875 | 23.8, 24.7 | -12.462 | 1.403 | 22.337 |  | 1.8 | 1.6 | 12T16 | R8-175 | 12 | 9.9 | 21.0 | -8.8 | 40 TREMIE 2 | 2418002, 2418003, 2418021 | 9, 7, 5
67 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
68 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
69 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
70 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
72 |  | Aug 1 2016 4:25PM | Aug 4 2016 7:30PM | 11.123 | 10.075 | 25, 27.2, 28.9 | -17.000 | 1.048 | 27.075 |  | 8.1 | 8.1 | 12T16 | R8-175 | 12 | 12.0 | 9.0 | -24.8 | 40 TREMIE 2 | 2408956, 2408957 | 9, 7
76 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
77 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
78 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
79 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
138 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
139 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
140 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
141 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
156 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.5 | 0.0 | 0.0 | 40 TREMIE 2
157 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
158 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
159 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
160 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
161 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
162 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
163 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
164 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
171 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
172 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
173 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
174 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | -100.0 | 40 TREMIE 2
175 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
176 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
184 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
185 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
186 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
187 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
188 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
189 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
190 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
191 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 12T16 | R8-175 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
PTP 1 | SGBM01 | Jul 13 2016 9:00AM | Jun 11 2016 6:38PM | 10.729 | 11.507 | 27.5, 28 | -18.793 | -0.778 | 30.300 |  | 3.0 | 3.0 | 12T16 | R8-175 | 30 | 13.4 | 17.0 | 6.6 | G50T3 | 17082328, 17082335 | 10, 7
PTP 1a | SGBM01 | Jul 13 2016 9:00AM | Jul 14 2016 5:40PM | 10.900 | 11.736 | 16.5, 17.4 | -4.764 | -0.836 | 16.500 |  | 3.0 | 3.0 | 12T16 | R8-175 | 18.3 | 7.3 | 12.0 | 3.9 | G50T3 | 17083026, 17083033 | 10, 2
KS8 | SGBM05 | Jul 16 2016 9:20AM | Jul 18 2016 11:05AM | 10.867 | 10.867 | 22.7 | -10.949 | -0.869 | 21.816 |  | 0.5 | 0.5 | na | na |  | 9.6 | 14.0 | -100.0 | G20P | 2393251, 2393254 | 9, 5
KS12 | SGBM01 | Jul 16 2016 9:00AM | Jul 18 2016 11:20AM | 10.943 | 10.943 | 19.6 | -7.531 | -0.793 | 18.474 |  | 0.6 | 0.5 | na | na |  | 8.2 | 13.0 | -100.0 | G20P | 32393254, 2393257 | 4, 9
KS15 | SGBM01 | Jul 18 2016 10:05AM | Jul 19 2016 12:30PM | 11.021 | 11.736 | 12.7 | -0.827 | -0.715 | 12.563 |  | 0.5 | 0.5 | na | na |  | 5.6 | 9.0 | -100.0 | G20P | 2393364 | 9
KS2 | SGBM05 | Jul 18 2016 9:35AM | Jul 19 2016 11:55AM | 10.872 | 11.736 | 12.7 | -0.849 | -0.864 | 12.585 |  | 0.5 | 0.5 | na | na |  | 5.6 | 9.0 | -100.0 | G20P | 2393362 | 9
KS4 | SGBM05 | Jul 18 2016 9:05AM | Jul 19 2016 10:14AM | 10.912 | 11.736 | 13.5 | -1.747 | -0.824 | 13.483 |  | 0.5 | 0.5 | na | na |  | 6.0 | 9.0 | -100.0 | G20P | 2393354 | 9
KS1 | SGBM01 | Jul 15 2016 10:00AM | Jul 16 2016 4:10PM | 10.894 | 11.736 | 27.8 | -16.009 | -0.842 | 27.745 |  | 0.5 | 0.5 | na | na |  | 12.3 | 21.0 | 8.7 | G20P | 2393159, 2393164, 2393170 | 7, 9, 5
KS3 | SGBM05 | Jul 19 2016 3:50PM | Jul 20 2016 10:54PM | 10.852 | 10.852 | 15.1 | -3.355 | -0.884 | 14.207 |  | 0.5 | 0.5 | na | na |  | 6.3 | 10.0 | -100.0 | G20P | 2403019 | 10
KS5 | SGBM05 | Jul 21 2016 8:25AM | Jul 21 2016 4:15PM | 10.881 | 10.881 | 16.9, 17.1 | -5.286 | -0.419 | 16.167 |  | 0.5 | 0.5 | na | na |  | 7.1 | 11.0 | 50.1 | G20P | 2403089, 2403101 | 8, 3
KS6 | SGBM05 | Jul 19 2016 3:15PM | Jul 20 2016 8:45PM | 10.901 | 11.736 | 17.3 | -5.544 | -0.835 | 17.280 |  | 0.5 | 0.5 | na | na |  | 7.6 | 10.0 | -100.0 | G20P | 2402993 | 10
KS7 | SGBM05 | Jul 15 2016 9:04AM | Jul 15 2016 6:20PM | 10.901 | 11.736 | 24.1 | -12.390 | -0.835 | 24.126 |  | 0.5 | 0.5 | na | na |  | 10.7 | 12.0 | -100.0 | G20P | 2393059, 2393062 | 8, 4
KS9 | SGBM01 | Jul 19 2016 2:05PM | Jul 20 2016 3:45PM | 10.887 | 11.3 | 23.2 | -11.465 | -0.413 | 22.765 |  | 0.5 | 0.5 | na | na |  | 10.1 | 15.0 | -100.0 | G20P | 2402971, 2402986 | 10, 5
KS10 | SGBM05 | Jul 15 2016 1:21PM | Jul 15 2016 6:55PM | 10.945 | 11.736 | 13.5 | -1.773 | -0.791 | 13.509 |  | 0.5 | 0.5 | na | na |  | 6.0 | 10.0 | -100.0 | G20P | 2393062, 2393072 | 4, 6
KS11 | SGBM01 | Jul 21 2016 8:35AM | Jul 21 2016 5:10PM | 11.000 | 11.3 | 17.8 | -6.071 | -0.300 | 17.371 |  | 0.5 | 0.5 | na | na |  | 7.7 | 11.0 | -100.0 | G20P | 2403096, 2403101 | 5, 6
KS13 | SGBM01 | Jul 20 2016 11:00AM | Jul 20 2016 6:55PM | 11.039 | 11.736 | 19.8 | -7.746 | -0.697 | 19.482 |  | 0.5 | 0.5 | na | na |  | 8.6 | 12.0 | -100.0 | G20P | 2402986, 2402993 | 4, 8
KS14 | SGBM01 | Jul 18 2016 5:00PM | Jul 19 2016 2:10PM | 10.926 | 11.524 | 21.8 | -10.046 | -0.598 | 21.570 |  | 0.5 | 0.5 | na | na |  | 9.5 | 14.0 | -100.0 | G20P | 2393371, 2393377 | 7, 7
KS16 | SGBM01 | Jul 15 2016 3:40PM | Jul 16 2016 5:45PM | 11.039 | 11.736 | 12.9 | -0.933 | -0.697 | 12.669 |  | 0.5 | 0.5 | na | na |  | 5.6 | 6.0 | -100.0 | G20P | 2393170, 2393172 | 3, 3
217 |  | Jul 30 2016 9:00AM | Aug 5 2016 6:40PM | 11.386 | 10.075 | 18, 18.4 | -6.345 | 1.311 | 16.420 |  | 1.8 | 1.7 | 12T16 | R8-175 | 12 | 7.3 | 12.0 | 65.4 | 40 TREMIE 2 | 2409038 | 12
KS17 |  | Sep 8 2016 9:52AM | Sep 8 2016 8:25PM | 11.255 | 0 | 27.2 | -15.278 | 11.255 | 15.278 |  | 0.8 | 0.8 | na | na |  | 6.8 | 18.0 | -6.8 | G20P | 2418620, 2418622 | 10, 8
KS18 |  | Sep 3 2016 5:09PM | Sep 5 2016 11:50PM | 11.122 | 11.213 | 21.6, 21.6 | -9.422 | 11.122 | 20.635 |  | 2.7 | 0.5 | na | na | 0.0 | 9.1 | 9.0 | -1.3 | G20P | 2418339, 2418346 | 9, 5
KS19 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS20 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS21 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS22 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS23 |  | Sep 8 2016 10:40AM | Sep 9 2016 9:25PM | 11.057 | 0 | 20.2 | -8.356 | 11.057 | 8.356 |  | 0.8 | 0.8 | na | na |  | 3.7 | 9.0 | -3.7 | G20P | 2418696, 2418698 | 9, 3
KS24 |  | Sep 3 2016 4:00PM | Sep 5 2016 11:55PM | 11.122 | 10.978 | 20.8 | -9.577 | 0.144 | 20.555 |  | 1.6 | 0.5 | na | na |  | 9.1 | 14.0 | 54.2 | G20P | 2418346, 2418352 | 4.5, 9.5
KS25 | SGBM01 | Sep 1 2016 2:40PM | Sep 2 2016 7:50PM | 11.453 | 11.453 | 14.1, 14.1 | -1.844 | 11.453 | 13.297 |  | 2.1 | 0.0 | na | na |  | 5.9 | 9.0 | -100.0 | G20P | Pending | 9
KS26 |  | Sep 6 2016 10:48AM | Sep 7 2016 2:55PM | 11.708 | 11.708 | 13.9, 13.9 | -1.379 | 11.708 | 13.087 |  | 2.2 | 0.8 | na | na |  | 5.8 | 9.0 | -0.6 | G20P | 2418526 | 9
KS27 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS28 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS29 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS30 |  |  |  | 0.000 | 0 |  | 0.000 | 0.000 | 0.000 |  | 0.0 | 0.0 | na | na |  | 0.0 | 0.0 | 0.0 | G20P
KS31 |  | Sep 6 2016 10:13AM | Sep 6 2016 7:50PM | 11.322 | 11.322 | 17.1 | -4.963 | 11.322 | 16.285 |  | 1.0 | 0.8 | na | na |  | 7.2 | 10.0 | -2.2 | G20P | 2418419 | 10
KS32 |  | Sep 1 2016 10:30AM | Sep 2 2016 6:15PM | 11.531 | 11.531 | 16.1, 15.2 | -3.922 | 11.531 | 15.453 |  | 3.0 | 0.0 | na | na |  | 6.8 | 9.0 | -100.0 | G20P | 2418065 | 9

## 900
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
18 |  | Aug 11 2016 9:15AM | Aug 13 2016 8:50PM | 11.169 | 9.075 | 27.2, 28, 30 | -18.997 | 2.094 | 28.072 |  | 4.3 | 4.2 | 14T16 | R8-175 | 12 | 17.9 | 23.0 | 28.8 | 40 TREMIE 2 | 2410533, 2410534, 2410536 | 9, 8, 6
33 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
34 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
35 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
36 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
37 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
40 |  |  |  | 0.000 | 6.475 |  | 0.000 | 0.000 | 6.475 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 4.1 | 0.0 | 0.0 | 40 TREMIE 2
43 |  | Aug 15 2016 1:00PM | Aug 17 2016 3:20PM | 7.626 | 6.475 | 15.6, 18 | -9.497 | -2.449 | 15.972 |  | 3.5 | 3.5 | 14T16 | R8-175 | 12 | 10.2 | 14.0 | -12.4 | 40 TREMIE 2 | 2410810, 2410811 | 7, 7
44 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
45 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
51 |  | Aug 24 2016 1:00PM | Aug 25 2016 4:20PM | 7.786 | 10.075 | 8.8, 10.7, 11.3 | -2.857 | -2.289 | 12.932 |  | 4.7 | 3.5 | 14T16 | R8-175 | 10.3 | 8.2 | 15.0 | -8.2 | 40 TREMIE 2 | 2412945, 2412953 | 8.5, 6.5
52 |  | Aug 26 2016 4:13PM | Aug 27 2016 5:24PM | 7.746 | 5.975 | 11, 11.6 | -3.234 | -2.329 | 9.209 |  | 1.3 | 1.3 | 14T16 | R8-175 | 12 | 5.9 | 14.0 | -100.0 | 40 TREMIE 2 | 2413158, 2413161 | 7.5, 6.5
53 |  | Aug 18 2016 5:00PM | Aug 22 2016 7:30PM | 7.573 | 5.975 | 13.1 | -5.230 | -2.502 | 11.205 |  | 1.8 | 1.8 | 14T16 | R8-175 | 12 | 7.1 | 14.0 | 43.8 | 40 TREMIE 2 | 2412760, 2412762 | 7, 7
60 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
61 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
81 |  | Jul 30 2016 3:20PM | Aug 8 2016 8:05PM | 10.999 | 10.075 | 25.9, 27.5, 27.6 | -15.649 | 0.924 | 25.724 |  | 2.9 | 2.9 | 14T16 | R8-175 | 12 | 16.4 | 26.0 | 58.9 | 40 TREMIE 2 | 2409212, 2409210, 2409213 | 8, 10, 8
82 |  | Jul 21 2016 5:50PM | Jul 26 2016 1:15PM | 11.021 | 10.075 | 24.3, 25.8, 26.9, 29.7 | -18.996 | 0.946 | 29.071 |  | 7.2 | 7.2 | 14T16 | R8-175 | 12 | 18.5 | 28.0 | 51.4 | 40 TREMIE 2 | 2403380, 2403383, 2403388, 2403390 | 8, 8, 8, 4
85 |  | Aug 19 2016 8:25AM | Aug 19 2016 8:10PM | 10.737 | 10.075 | 15 | -3.732 | 0.662 | 13.807 |  | 3.2 | 3.1 | 14T16 | R8-175 | 12 | 8.8 | 8.0 | -100.0 | 40 TREMIE 2 | 2412501, 2412504 | 8, 7
86 |  | Aug 9 2016 7:00AM | Aug 10 2016 2:30PM | 10.643 | 10.075 | 12.5, 14.8 | -3.196 | 0.568 | 13.271 |  | 2.6 | 3.0 | 14T16 | R8-175 | 12 | 8.4 | 11.0 | 30.3 | 40 TREMIE 2 | 2409315, 2409318 | 8, 3
90 |  | Sep 2 2016 7:00AM | Sep 3 2016 5:35PM | 11.031 | 10.075 | 14, 13.5, 14.6, 15.7 | -3.954 | 0.956 | 14.029 |  | 8.0 | 2.7 | 14T16 | R8-175 | 12 | 8.9 | 12.0 | -8.9 | 40 TREMIE 2 | 2418190, 2418191 | 7, 5
91 |  | Sep 5 2016 7:12PM | Sep 7 2016 8:10PM | 11.013 | 10.075 | 17.5, 21.3, 21.7, 28.7 | -19.394 | 0.938 | 29.469 | 5.5,3.1,1.3 | 9.5 | 3.5 | 14T16 | R8-175 | 12 | 18.7 | 25.0 | -100.0 | 40 TREMIE 2 | 2418545, 2418549, 2418558 | 10, 9, 6
94 |  | Jul 26 2016 7:10PM | Aug 4 2016 2:35PM | 11.123 | 10.075 | 13, 15.5 | -5.100 | 1.048 | 15.175 |  | 5.0 | 5.0 | 14T16 | R8-175 | 12 | 9.7 | 14.0 | 45.0 | 40 TREMIE 2 | 2403930, 2403933 | 7, 7
95 |  | Aug 12 2016 11:20AM | Aug 15 2016 9:10PM | 10.798 | 10.075 | 15.8, 16, 19.4, 20 | -8.295 | 0.723 | 18.370 |  | 4.6 | 4.6 | 14T16 | R8-175 | 12 | 11.7 | 16.0 | 36.9 | 40 TREMIE 2 | 2410656, 2410657 | 10, 6
96 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
101 |  | Aug 16 2016 3:15PM | Aug 17 2016 7:45PM | 10.451 | 10.075 | 13.6, 14.6 | -5.433 | 0.376 | 15.508 |  | 3.4 | 3.8 | 14T16 | R8-175 | 12 | 9.9 | 16.0 | -9.9 | 40 TREMIE 2 | 2410835, 2410836 | 8, 8
114 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
119 |  | Aug 1 2016 4:40PM | Aug 4 2016 4:23PM | 10.523 | 10.075 | 20.7, 22.3, 23.3 | -11.885 | 0.448 | 21.960 |  | 3.4 | 3.4 | 14T16 | R8-175 | 12 | 14.0 | 18.0 | 28.8 | 40 TREMIE 2 | 2403940, 2403941 | 9, 9
127 |  | Aug 15 2016 2:25PM | Aug 18 2016 7:20PM | 10.496 | 10.075 | 15.4, 17.7 | -6.730 | 0.421 | 16.805 |  | 4.1 | 3.5 | 14T16 | R8-175 | 12 | 10.7 | 14.0 | 30.9 | 40 TREMIE 2 | 2410906, 2410907 | 8, 6
143 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
148 |  | Aug 17 2016 8:00PM | Aug 20 2016 3:40PM | 10.461 | 10.075 | 24.6, 25.3 | -14.290 | 0.386 | 24.365 |  | 2.7 | 2.7 | 14T16 | R8-175 | 12 | 15.5 | 20.0 | 4.5 | 40 TREMIE 2 | 2412572, 2412576 | 12, 8
149 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | -100.0 | 40 TREMIE 2
150 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
151 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
152 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
153 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
154 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
155 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
165 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
166 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
167 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
168 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.3 | 0.0 | 0.0 | 40 TREMIE 2
169 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
170 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
177 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
178 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
192 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
193 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
194 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
200 |  |  |  | 0.000 | 6.575 |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
201 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
202 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
203 |  |  |  | 0.000 | 6.575 |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
204 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
205 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
208 |  |  |  | 0.000 | 6.375 |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 4.1 | 0.0 | 0.0 | 40 TREMIE 2
209 |  |  |  | 0.000 | 6.575 |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
210 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
211 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
212 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
213 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
214 |  | Aug 17 2016 9:40AM | Aug 19 2016 4:55PM | 13.129 | 10.075 | 43.3, 44.9 | -31.070 | 3.054 | 41.145 |  | 3.7 | 3.7 | 14T16 | R8-175 | 12 | 26.2 | 34.0 | 29.9 | 40 TREMIE 2 | 2412479, 2412480, 2412481, 2412482 | 8.5, 8.5, 8, 9
216 | SGBM23 | Aug 6 2016 9:45AM |  | 0.000 | 10.075 | 19.4 | -13.000 | 0.000 | 23.075 |  | 8.4 | 0.0 | 14T16 | R8-175 |  | 14.7 | 0.0 | -100.0 | 40 TREMIE 2
PTP-2 | SGBM17 | Aug 20 2016 11:34AM | Aug 22 2016 9:20PM | 11.389 | 11 | 18, 20.2 | -8.906 | 0.389 | 19.906 |  | 3.6 | 3.5 | 14T16 | R8-175 | 21 | 12.7 | 20.0 | 7.3 | G50 | 0171788, 0171789 | 10, 10
7. |  | Aug 25 2016 7:00AM | Aug 26 2016 4:55PM | 11.432 | 9.075 | 20.7, 22.3, 24.8 | -12.614 | 2.357 | 21.689 |  | 6.9 | 4.5 | 14T16 | R8-175 | 12 | 13.8 | 26.0 | 88.4 | 40 TREMIE 2 | 2413046, 2413047, 2413048, 2413060 | 7, 8, 6, 5
7a |  | Aug 29 2016 2:25PM | Sep 2 2016 8:48PM | 11.417 | 9.075 | 19.3, 22.7 | -10.532 | 2.342 | 19.607 |  | 4.6 | 4.6 | 14T16 | R8-175 | 12 | 12.5 | 7.5 | 68.3 | 40 TREMIE 2 | 2418087, 2418091, 2418093 | 7.5, 7.5, 6

## 1000
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
1 |  | Aug 17 2016 7:00AM | Aug 18 2016 1:35PM | 12.418 | 12.475 | 24.3 | -12.312 | 2.343 | 24.787 |  | 2.3 | 2.3 | 14T16 | R8-175 | 12 | 19.5 | 34.0 | 0.4 | 40 TREMIE 2 | 2410876, 2410882, 2410881, 2410889 | 11, 9, 7, 7
2 |  | Aug 23 2016 7:00AM | Aug 24 2016 8:40PM | 12.077 | 10.075 | 23.7, 23.5, 25.7 | -13.753 | 2.002 | 23.828 | 4.5 | 6.5 | 3.9 | 14T16 | R8-175 | 12 | 18.7 | 7.0 | -62.6 | 40 TREMIE 2 | 2412883, 2412885, 2412886, 2412887 | 7, 7, 8, 8
8 |  | Sep 7 2016 7:45AM |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.5 | 0.0 | -100.0 | 40 TREMIE 2
9 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.5 | 0.0 | 0.0 | 40 TREMIE 2
10 |  |  |  | 0.000 | 9.575 |  | 0.000 | -9.575 | 9.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.5 | 0.0 | -100.0 | 40 TREMIE 2 | Pending | 20
11 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.5 | 0.0 | 0.0 | 40 TREMIE 2
12 |  |  |  | 0.000 | 9.575 |  | 0.000 | 0.000 | 9.575 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.5 | 0.0 | 0.0 | 40 TREMIE 2
13 |  | Sep 2 2016 5:50PM | Sep 5 2016 9:25PM | 11.262 | 6.275 | 19.3, 21 | -10.725 | 1.687 | 17.000 |  | 4.7 | 4.7 | 14T16 | R8-175 | 12 | 13.4 | 14.0 | 6.0 | 40 TREMIE 2 | 2418328, 2418329, 2418337 | 7, 7, 9
41 |  |  |  | 0.000 | 6.475 |  | 0.000 | 0.000 | 6.475 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 5.1 | 0.0 | 0.0 | 40 TREMIE 2
54 |  | Aug 17 2016 1:05PM | Aug 19 2016 10:50AM | 10.075 | 10.075 | 16.6, 20.8, 24.3 | -13.142 | 0.000 | 23.217 | 1.5 | 5.2 | 4.4 | 14T16 | R8-175 | 12 | 18.2 | 28.0 | 53.5 | 40 TREMIE 2 | 2412466, 2412467, 2412469, 2412470 | 7, 9, 6, 6
75 |  | Aug 15 2016 11:40AM | Aug 16 2016 7:42PM | 10.825 | 10.075 | 14.8, 16.1, 18 | -7.075 | 0.750 | 17.150 |  | 5.4 | 5.0 | 14T16 | R8-175 | 12 | 13.5 | 19.0 | -13.5 | 40 TREMIE 2 | 2410733, 2410734 | 9.5, 9.5
80 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
83 |  | Aug 26 2016 3:33PM | Sep 1 2016 1:00PM | 10.938 | 10.075 | 31.5, 31.7, 33.5, 34 | -22.629 | 0.863 | 32.704 |  | 6.6 | 3.9 | 14T16 | R8-175 | 12 | 25.7 | 42.0 | -25.7 | 40 TREMIE 2 | 2418006, 2418007, 2418008, 2418010, 2418018 | 8, 7, 9, 9, 9
84 |  | Aug 20 2016 5:14PM | Aug 23 2016 8:10PM | 10.770 | 10.075 | 20.2, 22.2 | -12.569 | 0.695 | 22.644 |  | 5.6 | 3.9 | 14T16 | R8-175 | 12 | 17.8 | 31.0 | -100.0 | 40 TREMIE 2 | 2412822, 2412821, 2412825, 2412829 | 8, 9, 9, 5
89 |  | Aug 3 2016 5:15PM | Aug 8 2016 4:15PM | 11.113 | 10.075 | 20.8, 22.6, 23.8, 26 | -14.521 | 1.038 | 24.596 |  | 3.8 | 5.9 | 14T16 | R8-175 | 12 | 19.3 | 31.0 | 60.5 | 40 TREMIE 2 | 2409192, 2409194, 2409195, 2409203 | 8, 9, 8, 6
92 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
93 |  | Sep 1 2016 8:40AM | Sep 1 2016 9:20PM | 10.798 | 10.075 | 18.9 | -7.289 | 0.723 | 17.364 |  | 3.9 | 2.9 | 14T16 | R8-175 | 12 | 13.6 | 8.5 | -37.7 | 40 TREMIE 2 | 2418030, 2418029 | 8.5, 7.5
105 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
110 |  | Aug 10 2016 11:20AM | Aug 13 2016 1:15PM | 10.502 | 10.075 | 25.9, 27.5, 30.5, 31.5 | -20.056 | 0.427 | 30.131 |  | 6.5 | 6.4 | 14T16 | R8-175 | 12 | 23.7 | 36.0 | 52.1 | 40 TREMIE 2 | 2410506, 2410507, 2410508, 2398373, 2410517 | 8, 8, 9, 8, 3
113 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
120 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
131 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
136 |  | Aug 9 2016 7:00AM | Aug 12 2016 8:40PM | 10.391 | 10.075 | 16.7, 23.5, 27.2, 29.2 | -18.106 | 0.316 | 28.181 | 5.8 | 8.5 | 5.8 | 14T16 | R8-175 | 12 | 22.1 | 32.0 | 44.6 | 40 TREMIE 2 | 2410462, 2410464, 2410467, 2410470 | 8, 8, 9, 7
144 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
147 |  | Aug 22 2016 2:00PM | Aug 23 2016 6:10PM | 10.421 | 10.075 | 20.8 | -12.662 | 0.346 | 22.737 |  | 4.3 | 3.9 | 14T16 | R8-175 | 12 | 17.9 | 26.0 | -17.9 | 40 TREMIE 2 | 2412810, 2412811, 2412812 | 8.5, 9, 8.5
179 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
195 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
199 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
207 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2

## 1200
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
3 |  | Aug 19 2016 6:10PM | Aug 20 2016 7:28PM | 11.930 | 12.275 | 16.3, 18.4 | -5.659 | 2.055 | 17.934 |  | 2.8 | 2.3 | 16T16 | R8-175 | 12 | 20.3 | 25.0 | 42.3 | 40 TREMIE 2 | 2412601, 2412602, 2412603 | 9, 8.5, 7.5
4 |  | Aug 3 2016 11:20AM | Aug 10 2016 5:00PM | 11.509 | 9.875 | 24.4, 29, 29.3 | -17.396 | 1.634 | 27.271 |  | 6.3 | 6.0 | 16T16 | R8-175 | 12 | 30.8 | 49.0 | 18.1 | 40 TREMIE 2 | 2409328, 2409329, 2409332, 2409334, 2409339, 2409347 | 7, 8, 9, 8, 10, 7
6 |  | Jul 26 2016 5:10PM | Aug 13 2016 10:50AM | 11.312 | 9.875 | 24.6, 25.9, 27 | -14.959 | 1.437 | 24.834 |  | 5.0 | 5.2 | 16T16 | R8-175 | 12 | 28.1 | 45.0 | 16.9 | 40 TREMIE 2 | 2410497, 2410498, 2410499, 2410501, 2410505, 2410504, 2398372 | 6, 7, 8, 6, 4, 8, 6
7 |  | Jul 19 2016 5:05PM |  | 11.567 | 9.875 | 24.3, 25.3, 29.3, 31.5, 32.5 | -20.102 | 0.000 | 29.977 |  | 3.9 | 6.0 | 16T16 | R8-175 |  | 33.9 | 0.0 | -33.9 | 40 TREMIE 2
17 |  | Aug 15 2016 8:30AM | Aug 17 2016 1:30PM | 11.250 | 9.875 | 14, 15 | -3.264 | 1.375 | 13.139 |  | 3.4 | 3.0 | 16T16 | R8-175 | 12 | 14.9 | 22.0 | 7.1 | 40 TREMIE 2 | 2410801, 2410803, 2410804 | 8, 8, 6
38 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
39 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
46 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
47 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
48 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
49 |  | Sep 5 2016 8:18AM | Sep 8 2016 4:35PM | 7.894 | 9.875 | 11.3, 9, 13.1, 14.2, 15.6 | -6.849 | -1.981 | 16.724 |  | 13.4 | 4.7 | 16T16 | R8-175 | 12 | 18.9 | 8.0 | -18.9 | 40 TREMIE 2 | 2418601, 2418602, 2418604 | 8, 9, 7
50 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
55 |  | Aug 27 2016 4:20PM | Sep 3 2016 8:10PM | 8.269 | 6.275 | 18.3, 21.5, 20.5, 20.5, 20.6, 20.7 | -14.118 | 1.994 | 20.393 |  | 9.7 | 3.3 | 16T16 | R8-175 | 12 | 23.1 | 30.0 | 6.9 | 40 TREMIE 2 | 2418192, 2418193, 2418194, 2418197, 2418204 | 6, 9, 8, 7, 5
59 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
65 |  | Aug 8 2016 11:00AM | Aug 10 2016 9:50PM | 11.376 | 9.875 | 18.4, 20.2, 22.6 | -10.591 | 1.501 | 20.466 |  | 3.9 | 5.2 | 16T16 | R8-175 | 12 | 23.1 | 31.0 | 33.9 | 40 TREMIE 2 | 2409355, 2409356, 2409357, 2409358 | 8, 9, 8, 6
71 |  | Aug 27 2016 7:00AM | Aug 27 2016 7:03PM | 11.180 | 9.875 | 21.3 | -9.856 | 1.305 | 19.731 |  | 3.2 | 1.8 | 16T16 | R8-175 | 12 | 22.3 | 30.0 | -22.3 | 40 TREMIE 2 | 2413176, 2413178, 2413181, 2413148 | 9, 7, 6, 8
73 | SGBM23 | Jul 26 2016 6:25PM | Jul 30 2016 1:34PM | 11.018 | 10.075 | 13.9, 14, 15, 17 | -5.859 | 0.943 | 15.934 |  | 4.0 | 4.9 | 14T16 | R8-175 | 12 | 18.0 | 25.0 | 38.7 | 40 TREMIE 2 | 2403653, 2403652, 2403654 | 8.5, 9.5, 7
74 |  | Aug 1 2016 3:00PM | Aug 6 2016 5:00PM | 10.841 | 10.075 | 15.5, 16, 16.5, 18, 19 | -7.388 | 0.766 | 17.463 |  | 1.7 | 4.2 | 14T16 | R8-175 | 12 | 19.8 | 28.0 | 41.8 | 40 TREMIE 2 | 2409119, 2409123, 2409124 | 10, 9, 9
87 |  | Aug 11 2016 9:35AM | Aug 15 2016 2:57PM | 11.266 | 9.875 | 18, 18.4, 20, 21.3, 24.5 | -12.775 | 1.391 | 22.650 |  | 7.0 | 7.2 | 16T16 | R8-175 | 12 | 25.6 | 34.0 | 8.4 | 40 TREMIE 2 | 2410639, 2410640, 2410641, 2410642 | 9, 9, 8.5, 7.5
97 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
98 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.4 | 0.0 | 0.0 | 40 TREMIE 2
99 |  | Aug 24 2016 2:00PM | Aug 26 2016 8:54PM | 10.771 | 9.875 | 14, 13, 14.1, 19, 18.3, 21.7 | -11.118 | 0.696 | 20.993 | 3.1 | 10.5 | 3.3 | 16T16 | R8-175 | 12 | 23.7 | 34.0 | -100.0 | 40 TREMIE 2 | 2413067, 2413068, 2413069, 2413070 | 8, 9, 9, 8
100 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 14T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
102 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
104 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
106 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
109 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
115 |  | Sep 1 2016 6:30PM | Sep 5 2016 1:30PM | 10.839 | 9.875 | 15, 17.5, 18.5 | -7.096 | 0.964 | 16.971 |  | 3.4 | 4.7 | 16T16 | R8-175 | 12 | 19.2 | 28.0 | -19.2 | 40 TREMIE 2 | 2418285, 2418286, 2418291, 2418299 | 8, 9, 8, 3
111 |  | Jul 26 2016 10:00AM | Aug 3 2016 9:00PM | 11.274 | 9.875 | 23.5, 23.6, 24.1, 25, 26.6, 26.8, 28.6, 29 | -18.614 | 1.399 | 28.489 |  | 6.0 | 8.1 | 16T16 | R8-175 | 12 | 32.2 | 42.0 | 30.3 | 40 TREMIE 2 | 2403891, 2403892, 2403894, 2403895, 2403896 | 9, 9, 9, 11, 4
116 |  | Aug 27 2016 10:00AM | Aug 30 2016 2:05PM | 10.840 | 9.875 | 28.1, 28.1, 30.6, 30.6 | -19.040 | 0.965 | 28.915 |  | 0.0 | 4.7 | 18T16 | R8-175 | 12 | 32.7 | 45.0 | -24.7 | 40 TREMIE 2 | 2413378, 2413382, 2413384, 2413385, 2413397, 2413399 | 8, 6, 9, 8, 8, 6
117 |  | Aug 23 2016 3:20PM | Aug 25 2016 1:20PM | 10.638 | 9.975 | 27.6, 29.5, 32 | -20.529 | 0.763 | 30.504 |  | 0.0 | 4.7 | 18T16 | R8-175 | 12 | 34.5 | 9.0 | 1.6 | 40 TREMIE 2 | 2412928, 2412929, 2412930, 2412933, 2412934 | 9, 9, 9, 9, 9
118 |  | Aug 18 2016 1:00PM | Aug 20 2016 5:50PM | 10.640 | 9.875 | 15.7, 19.8 | -8.410 | 0.765 | 18.285 |  | 4.7 | 4.7 | 16T16 | R8-175 | 12 | 20.7 | 27.0 | -20.7 | 40 TREMIE 2 | 2412588, 2412591, 2412594 | 9, 9, 9
121 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
122 |  |  |  | 0.000 | 8.875 |  | 0.000 | 0.000 | 8.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 10.0 | 0.0 | 0.0 | 40 TREMIE 2
123 |  |  |  | 0.000 | 8.875 |  | 0.000 | 0.000 | 8.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 10.0 | 0.0 | 0.0 | 40 TREMIE 2
124 |  | Sep 1 2016 7:50AM | Sep 3 2016 2:00PM | 10.549 | 8.975 | 25.9, 28.1, 31, 32 | -20.641 | 1.674 | 29.616 |  | 5.4 | 3.3 | 16T16 | R8-175 | 12 | 33.5 | 40.0 | -33.5 | 40 TREMIE 2 | 2418163, 2418164, 2418169, 2418174, 2418177 | 10, 9, 9, 7, 5
125 |  | Aug 25 2016 8:36AM | Aug 27 2016 11:25AM | 10.632 | 8.975 | 29, 32.6, 32.1 | -20.883 | 1.757 | 29.858 |  | 6.8 | 3.8 | 16T16 | R8-175 | 12 | 33.8 | 45.0 | -33.7 | 40 TREMIE 2 | 2413108, 2413112, 2413114, 2413115, 2413127 | 8, 9, 10, 9, 9
126 |  | Sep 5 2016 8:50AM | Sep 6 2016 8:30PM | 10.729 | 9.875 | 29.9, 29.9, 32 | -21.283 | 0.854 | 31.158 | 17.0 | 6.1 | 3.3 | 16T16 | R8-175 | 12 | 35.2 | 42.0 | -35.2 | 40 TREMIE 2 | c660002413, c660002414, c660002415, c660002416 | 11, 11, 10, 10
128 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
130 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
132 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
135 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
137 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
142 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
145 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.4 | 0.0 | 0.0 | 40 TREMIE 2
146 |  |  |  | 0.000 | 10.075 |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.4 | 0.0 | 0.0 | 40 TREMIE 2
183 |  |  |  | 0.000 | 6.575 |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.4 | 0.0 | 0.0 | 40 TREMIE 2
196 |  |  |  | 0.000 | 6.375 |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
197 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
198 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
206 |  |  |  | 0.000 | 6.375 |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 16T16 | R8-175 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
215 |  | Aug 20 2016 2:00PM | Aug 22 2016 5:40PM | 12.726 | 10.075 | 21, 22, 22.5 | -8.911 | 2.651 | 18.986 |  | 2.2 | 1.9 | 16T16 | R8-175 | 12 | 21.5 | 16.0 | -21.5 | 40 TREMIE 2 | 2412741, 2412742, 2412746, 2412745 | 8.5, 7.5, 9, 9
107a |  | Sep 8 2016 8:37AM | Sep 9 2016 4:13PM | 10.739 | 8.875 | 22, 25 | -14.899 | 1.864 | 23.774 |  | 8.2 | 4.7 | 16T16 | R8-175 | 12 | 26.9 | 36.0 | -100.0 | 40 TREMIE 2 | 2418673, 2418674, 2418675, 2418679 | 9, 9, 9, 9
108a |  | Sep 6 2016 6:04PM | Sep 7 2016 8:50PM | 10.608 | 8.875 | 18.4 | -10.767 | 1.733 | 19.642 |  | 7.7 | 4.7 | 16T16 | R8-175 | 12 | 22.2 | 30.0 | -22.2 | 40 TREMIE 2 | 2418546, 2418551, 2418556, 2418552 | 8, 9, 7, 6

## 1350
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
5 |  | Jul 20 2016 11:50AM | Jul 26 2016 8:35PM | 11.420 | 9.875 | 29.1, 31.4, 31.8, 32.7, 34.5, 35.5 | -25.884 | 1.545 | 35.759 |  | 6.8 | 10.5 | 18T16 | R8-175 | 12 | 51.2 | 65.5 | -54.1 | 40 TREMIE 2 | 2403404, 2403405, 2403408, 2403407, 2403406, 2403409, 2403410, 2403419 | 8.5, 7.5, 7.5, 8.5, 7.5, 7.5, 8.5, 10
42 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 22T16 | R8-175 |  | 9.0 | 0.0 | 0.0 | 40 TREMIE 2
56 |  |  |  | 0.000 | 6.275 |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 9.0 | 0.0 | 0.0 | 40 TREMIE 2
57 |  | Aug 23 2016 6:00PM | Aug 26 2016 9:26PM | 8.039 | 6.275 | 18.3, 19.6, 22.2 | -13.358 | -1.836 | 19.633 |  | 7.9 | 5.7 | 18T16 | R8-175 | 12 | 28.1 | 35.5 | -33.3 | 40 TREMIE 2 | 2413071, 2413072, 2413073, 2413076 | 8, 9, 9.5, 9
58 |  | Aug 18 2016 1:00PM | Aug 22 2016 1:00PM | 7.855 | 6.275 | 18.7, 22.7, 23.3, 24.3 | -15.837 | -2.020 | 22.112 |  | 6.3 | 6.3 | 18T16 | R8-175 | 12 | 31.7 | 38.0 | 1.2 | 40 TREMIE 2 | 2412721, 2412722, 2412728, 2412729, 2412731 | 9, 8, 8, 7, 6
88 | SGBM05 | Jul 28 2016 8:20AM | Aug 1 2016 11:20AM | 11.133 | 9.875 | 21.5, 22.6, 26, 27.8 | -15.932 | 1.258 | 25.807 |  | 4.3 | 7.9 | 18T16 | R8-175 | 12 | 36.9 | 45.0 | 21.8 | 40 TREMIE 2 | 2403714, 2403715, 2403716, 2403718, 2403719 | 10, 10, 9, 8, 8
103 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 14.1 | 0.0 | 0.0 | 40 TREMIE 2
112 |  | Aug 13 2016 8:00PM | Aug 17 2016 4:40PM | 11.094 | 9.875 | 23.5, 24.5, 27.6 | -15.845 | 1.219 | 25.720 |  | 3.1 | 6.8 | 18T16 | R8-175 | 12 | 36.8 | 36.0 | 7.2 | 40 TREMIE 2 | 2410815, 2410816, 2410819, 2410822, 2410821 | 9, 9, 9, 9, 8
129 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 14.1 | 0.0 | 0.0 | 40 TREMIE 2
133 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 14.1 | 0.0 | 0.0 | 40 TREMIE 2
134 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 14.1 | 0.0 | 0.0 | 40 TREMIE 2
180 |  |  |  | 0.000 | 6.375 |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 9.1 | 0.0 | 0.0 | 40 TREMIE 2
181 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 14.1 | 0.0 | 0.0 | 40 TREMIE 2
182 |  |  |  | 0.000 | 9.875 |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 18T16 | R8-175 |  | 14.1 | 0.0 | 0.0 | 40 TREMIE 2

## 1500
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
107 |  |  |  | 0.000 | 9.725 |  | 0.000 | 0.000 | 9.725 |  | 0.0 | 0.0 | 22T16 | R8-175 |  | 17.2 | 0.0 | 0.0 | 40 TREMIE 2
108 |  |  |  | 0.000 | 9.725 |  | 0.000 | 0.000 | 9.725 |  | 0.0 | 0.0 | 22T16 | R8-175 |  | 17.2 | 0.0 | 0.0 | 40 TREMIE 2