## 1500
Summary List for J2380-KLCC P2
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DP 9 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 22T32 | T10-150 |  | 34.6 | 0.0 | 0.0 | G50T3
DP 10 | SGBM26 | Sep 1 2016 11:05AM | Sep 1 2016 7:00PM | 0.000 | 19.575 |  | -25.000 | -19.575 | 44.575 |  | 0.0 | 0.0 | 22T32 | T10-150 | 8.5+12+12+12 | 78.8 | 10.0 | -87.3 | G50T3 | qqq122 | 10
DP 11 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 22T32 | T10-150 |  | 34.6 | 0.0 | 0.0 | G50T3
DP 12 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 22T32 | T10-150 |  | 34.6 | 0.0 | 0.0 | G50T3
DP 13 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 22T32 | T10-150 |  | 34.6 | 0.0 | 0.0 | G50T3

## 2000
Summary List for J2380-KLCC P2
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DQ 18 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 19 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 20 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 21 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 22 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 23 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 24 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 25 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 27 |  |  |  | 0.000 | 16.575 |  | 0.000 | 0.000 | 16.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 52.1 | 0.0 | 0.0 | G50T3
DQ 28 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 29 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 30 | SGBM16 | Aug 10 2016 1:00AM |  | 0.000 | 18.575 | 9 | -9.000 | 0.000 | 27.575 |  | 9.0 | 0.0 | 40T32 | T10-150 | 0 | 86.6 | 0.0 | -100.0 | G50T3
DQ 31 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 32 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 33 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 34 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 35 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 36 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 37 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 38 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 39 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 40 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 41 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 42 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 43 |  |  |  | 0.000 | 19.575 |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 61.5 | 0.0 | 0.0 | G50T3
DQ 44 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 45 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3
DQ 46 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 40T32 | T10-150 |  | 58.4 | 0.0 | 0.0 | G50T3

## 2200
Summary List for J2380-KLCC P2
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DQ 26-R |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 11 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 12 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 13 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 14 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 15 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 16 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 17 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 18 |  | Sep 1 2016 8:00AM |  | 35.918 | 18.575 |  | 35.918 | 17.343 | -17.343 |  | 0.0 | 9.0 | 48T32 | T10-150 | 5.6+12+12+12 | -65.9 | 0.0 | -100.0 | G50T3
DR 19 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 20 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 21 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 22 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3
DR 23 |  |  |  | 0.000 | 18.575 |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 48T32 | T10-150 |  | 70.6 | 0.0 | 0.0 | G50T3