## 880
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
CB393 | SGBM12 | Jan 19 2016 6:30PM | Jan 21 2016 11:16AM | 39.36 | 37.775 | 6, 8, 14 | 26.521 | 39.36 | 11.254 |  | 0 | 9.485 | 10T25 | T10-150 | 12.254 | 6.8457 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100055426 | 8.5
CB394 | SGBM12 | Jan 15 2016 5:00PM | Jan 18 2016 11:26AM | 39.69 | 37.775 | 0.25, 7, 11, 13.8 | 26.625 | 39.69 | 11.15 |  | 0 | 9 | 10T25 | T10-150 | 12.15 | 6.7824 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201045276 | 8.5
CB395 | SGBM12 | Jan 23 2016 9:00AM | Jan 26 2016 4:05PM | 39.675 | 37.775 | 5, 6, 9, 11, 13 | 26.598 | 39.675 | 11.177 |  | 0 | 9.917 | 10T25 | T10-150 | 12.177 | 6.7989 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201045489 | 8.5
CB396 | SGBM12 | Jan 29 2016 8:15AM | Jan 30 2016 5:05PM | 39.85 | 37.775 | 0.25, 5, 7, 11, 13 | 26.645 | 39.85 | 11.13 |  | 0 | 9.89 | 10T25 | T10-150 | 12.13 | 6.7703 | 9 | -100 | 30 TREMIE 2 (JKR) | P201045745 | 9
CB397 | SGBM12 | Jan 12 2016 4:10PM | Jan 14 2016 2:40PM | 39.84 | 37.775 | 6, 8, 12, 14.15 | 26.655 | 39.84 | 11.12 |  | 0 | 9.938 | 10T25 | T10-150 | 12.12 | 6.7642 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100055243 | 8.5
CB398 | SGBM12 | Jan 21 2016 2:12PM | Jan 22 2016 7:35PM | 39.65 | 37.775 | 0.25, 6, 9, 11 | 26.585 | 39.65 | 11.19 |  | 0 | 9.9 | 10T25 | T10-150 | 12.19 | 6.8068 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201045417 | 8.5
CB399 | SGBM12 | Jan 27 2016 8:15AM | Jan 28 2016 8:30PM | 39.8 | 37.775 | 5, 6, 10 | 26.456 | 39.8 | 11.319 |  | 0 | 10.15 | 10T25 | T10-150 | 12.319 | 6.8853 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201045602 | 8.5
CB400 | SGBM12 | Feb 12 2016 8:00AM | Feb 15 2016 10:00AM | 39.92 | 37.775 | 6, 7, 10, 12, 14.598 | 26.602 | 39.92 | 11.173 |  | 0 | 9.935 | 10T25 | T10-150 | 12.137 | 6.7964 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201046268 | 8.5
CB401 | SGBM12 | Feb 2 2016 8:30AM | Feb 3 2016 8:55PM | 39.88 | 37.775 | 6, 7, 11, 13 | 26.507 | 39.88 | 11.268 |  | 0 | 10.005 | 10T25 | T10-150 | 12.268 | 6.8542 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201046009 | 8.5
CB402 | SGBM12 | Feb 25 2016 2:30PM | Feb 27 2016 2:30PM | 39.66 | 37.775 | 6, 8, 10, 13 | 26.99 | 39.66 | 10.785 |  | 0 | 9.785 | 10T25 | T10-150 | 12.218 | 6.5604 | 10 | -100 | 30 TREMIE 2 (JKR) | P201047067 | 10
CB403 | SGBM12 | Mar 2 2016 2:00PM | Mar 4 2016 4:56PM | 39.6 | 37.775 | 6, 8, 10, 12.5 | 26.655 | 39.6 | 11.12 |  | 0 | 9.885 | 10T25 | T10-150 | 12.12 | 6.7642 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201047403 | 8.5
CB404 | SGBM12 | Mar 9 2016 8:00AM | Mar 11 2016 12:19PM | 39.57 | 37.775 | 6, 8, 10.5, 12, 14 | 26.626 | 39.57 | 11.149 |  | 0 | 9.307 | 10T25 | T10-150 | 12.149 | 6.7818 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201047763 | 8.5
CB405 | SGBM12 | Mar 15 2016 8:00AM | Mar 16 2016 11:30AM | 39.64 | 37.775 | 7, 9, 14 | 26.698 | 39.64 | 11.077 |  | 0 | 9.762 | 10T25 | T10-150 | 12.077 | 6.738 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P101055644 | 8.5
CB406 | SGBM12 | Mar 12 2016 8:00AM | Mar 14 2016 1:55PM | 39.55 | 37.775 | 6, 8, 12, 14.45 | 26.56 | 39.55 | 11.215 |  | 0 | 10.362 | 10T25 | T10-150 | 12.215 | 6.822 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P101055611 | 8.5
CB407 | SGBM12 | Mar 5 2016 8:30AM | Mar 8 2016 5:10PM | 39.6 | 37.775 | 6, 8, 10, 12, 14 | 26.532 | 39.6 | 11.243 |  | 0 | 10.39 | 10T25 | T10-150 | 12.24 | 6.839 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201047606 | 8.5
CB408 | SGBM12 | Feb 29 2016 8:00AM | Mar 2 2016 12:45PM | 39.5 | 37.775 | 6, 7, 10, 12, 14.5 | 26.575 | 39.5 | 11.2 |  | 0 | 10.125 | 10T25 | T10-150 | 12.2 | 6.8129 | 10 | -100 | 30 TREMIE 2 (JKR) | P201047244 | 10
CB409 | SGBM12 | Jan 18 2016 4:10PM | Jan 19 2016 6:01PM | 39.836 | 38.425 | 6, 8, 12 | 26.554 | 39.836 | 11.871 |  | 0 | 10.12 | 10T25 | T10-150 | 12.221 | 7.221 | 8.5 | -100 | 30 TREMIE 2 (JKR) | Pending | 8.5
CB410 | SGBM12 | Dec 18 2015 3:30PM | Dec 21 2015 11:35AM | 39.77 | 37.775 | 6, 8, 12, 14.025 | 26.672 | 39.77 | 11.103 |  | 8.025 | 9.825 | 10T25 | T10-150 | 12.103 | 6.7539 | 8.5 | 25.9 | 30 TREMIE 2 (JKR) | P100054073 | 8.5
CB412 | SGBM12 | Dec 28 2015 8:00AM | Dec 29 2015 6:55PM | 39.77 | 37.775 | 6, 8, 12, 14.23 | 26.652 | 39.77 | 11.123 |  | 8.23 | 10.028 | 10T25 | T10-150 | 12.123 | 6.766 | 8 | -100 | 30 TREMIE 2 (JKR) | P100054453 | 8
CB413 | SGBM12 | Dec 31 2015 10:35AM | Jan 2 2016 6:26PM | 39.715 | 37.775 | 5, 6.5, 11, 13 | 26.663 | 39.715 | 11.112 |  | 0 | 9.83 | 10T25 | T10-150 | 12.112 | 6.7593 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100054671 | 8.5
CB414 | SGBM12 | Jan 6 2016 9:00AM | Jan 7 2016 2:40PM | 39.734 | 37.775 | 6, 8, 12 | 26.603 | 39.734 | 11.172 |  | 0 | 9.57 | 10T25 | T10-150 | 12.172 | 6.7958 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100054918 | 8.5
CB411 | SGBM10 | Dec 10 2015 5:10PM | Dec 15 2015 4:08PM | 39.715 | 37.775 | 5, 7.5, 8.5, 10, 12, 13.595 | 26.625 | 39.715 | 11.15 |  | 8.595 | 10.145 | 10T25 | T10-150 | 12.15 | 6.7824 | 8 | -100 | 30 TREMIE 2 (JKR) | P100053838 | 8
CB415 | SGBM12 | Jan 14 2016 3:30PM | Jan 15 2016 3:44PM | 39.674 | 37.775 | 6, 10 | 26.577 | 39.674 | 11.198 |  | 0 | 8.55 | 10T25 | T10-150 | 12.189 | 6.8117 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P201045210 | 8.5
CB416 | SGBM12 | Dec 23 2015 9:30AM | Dec 26 2015 10:45PM | 39.974 | 37.775 | 5, 6, 10.9, 12.3 | 26.63 | 39.974 | 11.145 |  | 8.47 | 9.17 | 10T25 | T10-150 | 12.145 | 6.7794 | 8 | -100 | 30 TREMIE 2 (JKR) | P100054337 | 8
CB417 | SGBM10 | Dec 15 2015 8:00AM | Dec 17 2015 3:35PM | 39.745 | 37.775 | 6, 7, 11, 14.5 | 26.556 | 39.745 | 11.219 |  | 8.6 | 10.5 | 10T25 | T10-150 | 12.219 | 6.8244 | 8 | -100 | 30 TREMIE 2 (JKR) | P100053930 | 8
CB418 | SGBM10 | Dec 9 2015 10:30AM | Dec 10 2015 7:30PM | 39.768 | 37.775 | 6, 10.5, 13 | 26.58 | 39.768 | 11.195 |  | 8.4 | 10.203 | 10T25 | T10-150 | 12.195 | 6.8098 | 8 | -100 | 30 TREMIE 2 (JKR) | P100053624 | 8
CB419 | SGBM12 | Jan 9 2016 6:10PM | Jan 12 2016 4:58PM | 39.83 | 37.775 | 6, 9, 13 | 26.656 | 39.83 | 11.119 |  | 0 | 9.78 | 10T25 | T10-150 | 12.119 | 6.7636 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100055150 | 8.5
CB420 | SGBM12 | Jan 4 2016 10:00AM | Jan 5 2016 2:56PM | 39.885 | 37.775 | 4.5, 6, 12, 14.5 | 26.565 | 39.885 | 11.21 |  | 0 | 10.442 | 10T25 | T10-150 | 12.21 | 6.819 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100054786 | 8.5
CB421 | SGBM12 | Dec 29 2015 11:00AM | Dec 31 2015 4:16PM | 40.006 | 37.775 | 6, 7.5, 10, 14.4 | 26.601 | 40.006 | 11.174 |  | 8.542 | 9.848 | 10T25 | T10-150 | 12.175 | 6.797 | 8 | -100 | 30 TREMIE 2 (JKR) | P100054604 | 8
CB422 | SGBM12 | Dec 21 2015 11:50AM | Dec 23 2015 9:50AM | 40.651 | 37.775 | 6, 9.2, 11, 14.4 | 26.603 | 40.651 | 11.172 |  | 8.4 | 10.15 | 10T25 | T10-150 | 12.172 | 6.7958 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100054204 | 8.5
CB423 | SGBM10 | Dec 9 2015 6:00PM | Dec 12 2015 6:00PM | 40.666 | 37.775 | 5, 6.5, 8, 13.5, 14.8 | 26.546 | 40.666 | 11.229 |  | 9.92 | 10.26 | 10T25 | T10-150 | 12.229 | 6.8305 | 8 | -100 | 30 TREMIE 2 (JKR) | P100053771 | 8
CB424 | SGBM32 | Oct 23 2015 10:55AM | Oct 26 2015 2:55PM | 40.67 | 37.775 | 7, 9, 12, 14.6 | 26.519 | 2.895 | 11.256 |  | 7.705 | 10.6 | 10T25 | T10-150 | 12.6 | 6.8469 | 9 | -100 | 30 TREMIE 2 (JKR) | P100051088 | 9
CB425 | SGBM32 | Oct 6 2015 1:10PM | Dec 7 2015 9:20PM | 40.675 | 37.775 | 5.7, 7.5, 12 | 26.488 | 2.9 | 11.287 |  | 9.89 | 9.79 | 10T25 | T10-150 | 12.287 | 6.8658 | 9 | 31.1 | 30 TREMIE 2 (JKR) | 1 | 9
CB426 | SGBM32 | Oct 15 2015 8:00AM | Oct 16 2015 6:00PM | 40.68 | 37.775 | 4.255, 6, 11, 13 | 26.62 | 2.905 | 11.155 |  | 10.6 | 10.545 | 10T25 | T10-150 | 12.155 | 6.7855 | 9 | 32.6 | 30 TREMIE 2 (JKR) | P100050567 | 9
CB427 | SGBM32 | Oct 19 2015 9:15AM | Oct 21 2015 8:20PM | 40.69 | 37.775 | 4.194, 4.2, 5, 10 | 26.6 | 40.69 | 11.175 |  | 10.407 | 10.41 | 10T25 | T10-150 | 12.6 | 6.7977 | 9 | 32.4 | 30 TREMIE 2 (JKR) | P100050814 | 9
CB428 | SGBM32 | Oct 28 2015 11:15AM | Oct 29 2015 6:55PM | 40.62 | 37.775 | 7, 9, 13 | 26.552 | 40.62 | 11.223 |  | 9.33 | 9.885 | 10T25 | T10-150 | 12.5 | 6.8269 | 8 | -100 | 30 TREMIE 2 (JKR) | P100051339 | 8
CB429 | SGBM32 | Oct 10 2015 2:30PM | Oct 12 2015 9:42PM | 40.694 | 37.775 | 7.11, 9, 13.6 | 26.454 | 2.919 | 11.321 |  | 8.39 | 8.6 | 10T25 | T10-150 | 12.325 | 6.8865 | 9 | -100 | 30 TREMIE 2 (JKR) | P100050336 | 9
CB430 | SGBM32 | Oct 3 2015 8:45AM | Oct 5 2015 2:30PM | 40.68 | 37.775 | 8.2, 15.4 | 26.27 | 40.68 | 11.505 |  | 7.3 | 7.423 | 18T32 | T12-200 | 12.65 | 6.9984 | 10 | 42.9 | 30 TREMIE 2 (JKR) | 1 | 10
CB431 |  | Oct 22 2015 8:00AM | Oct 23 2015 5:45PM | 40.64 | 37.775 | 9.145, 10.5, 15.4 | 26.123 | 40.64 | 11.652 |  | 6.63 | 7.202 | 18T32 | T12-200 | 13.2 | 7.0878 | 9 | -100 | 30 TREMIE 2 (JKR) | P100050909 | 9
CB432 | SGBM32 | Oct 26 2015 8:50AM | Oct 27 2015 5:05PM | 40.57 | 37.775 | 7.843, 13 | 26.163 | 40.57 | 11.612 |  | 6.857 | 6.857 | 18T32 | T12-200 | 13.2 | 7.0635 | 9 | -100 | 30 TREMIE 2 (JKR) | P100051162 | 9
CB433 | SGBM32 | Oct 8 2015 9:00AM | Oct 10 2015 5:05PM | 40.651 | 37.775 | 10.585, 12.6, 14, 15.8 | 26.046 | 2.876 | 11.729 |  | 5.395 | 5.395 | 18T32 | T12-200 | 13.029 | 7.1346 | 10 | -100 | 30 TREMIE 2 (JKR) | P100050234 | 10
CB434 | SGBM32 | Oct 13 2015 8:00AM | Oct 13 2015 9:00PM | 40.65 | 37.775 | 11.33 | 25.98 | 40.65 | 11.795 |  | 4.47 | 4.47 | 18T32 | T12-200 | 13.745 | 7.1748 | 10 | -100 | 30 TREMIE 2 (JKR) | P100050379 | 10
CB435 | SGBM32 | Oct 1 2015 5:00PM | Oct 2 2015 9:50PM | 40.66 | 37.775 | 12.64 | 26.105 | 40.66 | 11.67 |  | 2.81 | 2.81 | 18T32 | T12-200 | 12.97 | 7.0988 | 10 | -100 | 30 TREMIE 2 (JKR) | P100049787 | 10
CB436 | SGBM32 | Oct 5 2015 11:10AM | Oct 6 2015 7:15PM | 40.635 | 37.775 | 18.21 | 21.555 | 40.635 | 16.22 |  | 2.04 | 16.22 | 18T32 | T12-200 | 17.7 | 9.8665 | 14 | -100 | 30 TREMIE 2 (JKR) | P100049983, P100049987 | 7, 7
CB437 | SGBM32 | Oct 27 2015 11:30AM | Oct 28 2015 8:35PM | 40.62 | 37.775 | 18 | 22.582 | 2.845 | 15.193 |  | 0.803 | 3.438 | 18T32 | T12-200 | 18.7 | 9.2418 | 13 | -9.24 | 30 TREMIE 2 (JKR) | P100051265, P100051266 | 7, 6
CB438 | SGBM32 | Nov 2 2015 5:50PM | Nov 3 2015 8:26PM | 40.64 | 37.775 | 4.88, 7.6, 9, 19.2 | 16.504 | 40.64 | 21.271 |  | 5.3 | 19.62 | 18T32 | T12-200 | 22.571 | 12.939 | 19 | -280.9 | 30 TREMIE 2 (JKR) | P100051579, P100051580 | 10, 9
CB439 | SGBM32 | Oct 16 2015 5:15PM | Oct 19 2015 7:05PM | 40.66 | 37.775 | 5.5, 6.5, 21.768, 23.5 | 17.652 | 40.66 | 20.123 |  | 2.068 | 18.77 | 18T32 | T12-200 | 20.8 | 12.2406 | 15 | 22.5 | 30 TREMIE 2 (JKR) | P100050685, P100050686 | 9, 6
CB440 | SGBM32 | Sep 29 2015 9:00AM | Oct 2 2015 4:20PM | 40.66 | 37.775 | 5.32, 6, 8.6, 9.5, 11, 19.8, 25 | 16.54 | 40.66 | 21.235 |  | 19.78 | 2.075 | 18T32 | T12-200 | 22.532 | 12.9171 | 18 | -100 | 30 TREMIE 2 (JKR) | P100049752, P100049753 | 9, 9
CB441 | SGBM32 | Oct 29 2015 6:20PM | Oct 31 2015 6:20PM | 40.64 | 37.775 | 6.155, 7.5 | 16.477 | 40.64 | 21.298 |  | 7.345 | 18.388 | 18T32 | T12-200 | 22.7 | 12.9554 | 18 | 10.48 | 30 TREMIE 2 (JKR) | P100051469, P100051473 | 9, 9
CB442 | SGBM32 | Nov 4 2015 8:30AM | Nov 5 2015 5:50PM | 40.64 | 37.775 | 6.317, 8, 15, 16.6 | 22.846 | 40.64 | 14.929 |  | 3.32 | 10.983 | 18T32 | T12-200 | 16.229 | 9.0812 | 12 | -100 | 30 TREMIE 2 (JKR) | P100051665 | 12
CB443 | SGBM32 | Nov 12 2015 8:00AM | Nov 20 2015 5:42PM | 40.61 | 37.775 | 6.215, 9, 13 | 26.492 | 40.61 | 11.283 |  | 8.205 | 8.205 | 10T25 | T10-150 | 12.3 | 6.8633 | 9 | -100 | 30 TREMIE 2 (JKR) | P100052485 | 9
CB444 | SGBM10 | Nov 26 2015 8:30AM | Nov 28 2015 3:13PM | 40.59 | 37.775 | 6.112, 8, 12 | 26.463 | 40.59 | 11.312 |  | 8.838 | 8.838 | 10T25 | T10-150 | 12.312 | 6.881 | 9 | 30.8 | 30 TREMIE 2 (JKR) | P100052883 | 9
CB445 | SGBM10 | Nov 21 2015 4:45PM | Nov 24 2015 3:40PM | 40.62 | 37.775 | 6.24, 8, 10, 12.8, 14.6 | 26.269 | 40.62 | 11.506 |  | 8.465 | 8.461 | 10T25 | T10-150 | 12.506 | 6.999 | 8 | -100 | 30 TREMIE 2 (JKR) | P100052702 | 8
CB446 | SGBM10 | Nov 11 2015 5:30PM | Nov 17 2015 6:22PM | 40.67 | 37.775 | 4.24, 6, 10 | 26.35 | 40.67 | 11.425 |  | 10.35 | 10.35 | 10T25 | T10-150 | 13.4 | 6.9497 | 9 | -100 | 30 TREMIE 2 (JKR) | P100052291 | 9
CB447 | SGBM12 | Oct 1 2015 8:00AM | Oct 2 2015 7:40PM | 40.66 | 37.775 | 5.188, 10.5, 11.2, 13.6, 14.4 | 26.41 | 40.66 | 11.365 |  | 9.912 | 10.19 | 18T32 | T12-200 | 13.02 | 6.9132 | 10 | -6.91 | 30 TREMIE 2 (JKR) | P100049774 | 10
CB448 | SGBM32 | Nov 4 2015 7:40PM | Nov 6 2015 8:35PM | 40.64 | 38.425 | 4.265, 7, 10, 12 | 26.638 | 40.64 | 11.787 |  | 9.977 | 9.977 | 10T25 | T10-150 | 12.787 | 7.1699 | 9 | -100 | 30 TREMIE 2 (JKR) | 1 | 9
CB449 | SGBM12 | Oct 12 2015 4:30PM | Oct 15 2015 4:45PM | 40.67 | 38.425 | 5.55, 7, 9.5, 12.8, 14.5 | 26.37 | 40.67 | 12.055 |  | 9.43 | 9.43 | 10T25 | T10-150 | 13.055 | 7.333 | 9 | -100 | 30 TREMIE 2 (JKR) | P100050514 | 9
CB450 | SGBM12 | Oct 19 2015 8:55AM | Oct 22 2015 3:30PM | 40.66 | 38.425 | 4.5, 5.5, 8, 12.5, 14.7 | 26.35 | 40.66 | 12.075 |  | 10.563 | 0 | 10T25 | T10-150 | 13.1 | 7.3451 | 9 | -100 | 30 TREMIE 2 (JKR) | P100050844 | 9
CB451 | SGBM32 | Oct 31 2015 2:00PM | Nov 2 2015 7:00PM | 40.665 | 38.425 | 4.5, 8, 12 | 26.606 | 40.665 | 11.819 |  | 9.763 | 9.763 | 10T25 | T10-150 | 13.1 | 7.1894 | 9 | -7.18 | 30 TREMIE 2 (JKR) | P100051553 | 9
CB452 | SGBM12 | Oct 5 2015 12:10PM | Oct 6 2015 9:10PM | 40.66 | 38.425 | 4.875, 7.3, 9, 10.5 | 26.675 | 2.235 | 11.75 |  | 9.68 | 9.68 | 10T25 | T10-150 | 12.75 | 7.1474 | 10 | -7.14 | 30 TREMIE 2 (JKR) | P100049989 | 10
CB454 |  | Oct 7 2015 8:45AM | Oct 9 2015 3:20PM | 40.67 | 38.425 | 5.02, 7.7, 10, 12.8, 15 | 26.585 | 40.67 | 11.84 |  | 10.13 | 10.125 | 10T25 | T10-150 | 12.835 | 7.2022 | 10 | -7.2 | 30 TREMIE 2 (JKR) | P100050170 | 10
CB455 | SGBM12 | Sep 23 2015 10:00AM | Sep 26 2015 9:06PM | 40.68 | 38.425 | 4.297, 5, 8, 9.2, 11.2, 13 | 26.7 | 40.68 | 11.725 |  | 10.303 | 9.548 | 10T25 | T10-150 | 12.725 | 7.1322 | 10 | 16.98 | 30 TREMIE 2 (JKR) | P100049420 | 10
CB453 | SGBM12 | Sep 28 2015 9:35AM | Sep 30 2015 8:50PM | 40.68 | 38.425 | 4.97, 6, 11.8, 13.5, 14.5, 15 | 26.6 | 40.68 | 11.825 |  | 10.03 | 10.271 | 10T25 | T10-150 | 13.05 | 7.193 | 12 | -7.19 | 30 TREMIE 2 (JKR) | P100049657 | 12
CB456 | SGBM12 | Oct 22 2015 2:00PM | Oct 28 2015 4:15PM | 40.62 | 38.425 | 4.28, 7.3, 9.4, 11, 11.8, 13.8, 14.5 | 26.586 | 40.62 | 11.839 |  | 10.334 | 0 | 10T25 | T10-150 | 13.1 | 7.2016 | 9 | -7.2 | 30 TREMIE 2 (JKR) | P100051246 | 9
CB457 | SGBM12 | Oct 15 2015 3:50PM | Oct 17 2015 7:25PM | 40.63 | 38.425 | 5.2, 6.5, 11, 13.1 | 26.613 | 40.63 | 11.812 |  | 10.347 | 0 | 10T25 | T10-150 | 12.812 | 7.1851 | 9 | -7.18 | 30 TREMIE 2 (JKR) | P100050618 | 9
CB458 | SGBM12 | Sep 28 2015 8:00AM | Sep 29 2015 6:58PM | 40.69 | 38.425 | 6, 9, 14.2 | 26.599 | 2.265 | 11.826 |  | 9.969 | 9.97 | 10T25 | T10-150 | 12.826 | 7.1936 | 10 | -100 | 30 TREMIE 2 (JKR) | P100049541 | 10
CB459 | SGBM12 | Oct 3 2015 9:15AM | Oct 5 2015 2:00PM | 40.69 | 38.425 | 5.02, 6.5, 13.5 | 26.52 | 40.69 | 11.905 |  | 10.08 | 10.09 | 10T25 | T10-150 | 12.947 | 7.2417 | 10 | -7.24 | 30 TREMIE 2 (JKR) | 1 | 10
CB460 | SGBM12 | Sep 22 2015 3:30PM | Sep 25 2015 8:57PM | 40.685 | 38.425 | 5.5, 7.5, 9, 10.2 | 26.713 | 40.685 | 11.712 |  | 9.375 | 9.375 | 10T25 | T10-150 | 12.712 | 7.1243 | 13 | 16.99 | 30 TREMIE 2 (JKR) | P100049356, P100049358 | 6.5, 6.5
CB461 | SGBM12 | Oct 7 2015 6:00PM | Oct 12 2015 9:00PM | 40.67 | 38.425 | 4.755, 7, 8.5, 10, 13 | 26.58 | 40.67 | 11.845 |  | 9.715 | 9.722 | 10T25 | T10-150 | 12.852 | 7.2052 | 10 | -100 | 30 TREMIE 2 (JKR) | P100050331 | 10
CB462 | SGBM12 | Oct 16 2015 5:30PM | Oct 20 2015 5:40PM | 40.68 | 38.425 | 6.5, 10.3, 14.5 | 26.56 | 40.68 | 11.865 |  | 9.16 | 0 | 10T25 | T10-150 | 13 | 7.2174 | 9 | -100 | 30 TREMIE 2 (JKR) | P100050734 | 9
CB463 | SGBM12 | Oct 28 2015 10:35AM | Oct 29 2015 8:00PM | 40.73 | 38.425 | 6.5, 10.5, 12.5 | 26.485 | 40.73 | 11.94 |  | 9.532 | 0 | 10T25 | T10-150 | 13.1 | 7.263 | 9 | -100 | 30 TREMIE 2 (JKR) | P100051345 | 9
CB464 |  | Nov 2 2015 4:15PM | Nov 4 2015 2:23PM | 40.68 | 38.425 | 6.258, 8.2, 10.9, 14 | 26.841 | 40.68 | 11.584 |  | 8.61 | 0 | 10T25 | T10-150 | 12.887 | 7.0465 | 9 | -100 | 30 TREMIE 2 (JKR) | P100051596 | 9
CB465 | SGBM32 | Nov 12 2015 9:35AM | Nov 19 2015 6:45PM | 40.501 | 38.425 | 5.45, 7, 8.6, 11, 12 | 26.68 | 40.501 | 11.745 |  | 8.76 | 8.76 | 10T25 | T10-150 | 12.8 | 7.1444 | 9 | -100 | 30 TREMIE 2 (JKR) | P100052433 | 9
CB466 | SGBM10 | Nov 24 2015 8:30AM | Nov 25 2015 2:52PM | 40.5 | 38.425 | 6.49, 9, 13, 15.145 | 26.577 | 40.5 | 11.848 |  | 8.655 | 8.65 | 10T25 | T10-150 | 12.845 | 7.207 | 10 | -7.2 | 30 TREMIE 2 (JKR) | P100052762 | 10
CB467 | SGBM10 | Nov 28 2015 3:45PM | Nov 30 2015 11:49PM | 40.45 | 38.425 | 9.2, 12 | 26.695 | 40.45 | 11.73 |  | 5.432 | 7.432 | 10T25 | T10-150 | 12.73 | 7.1353 | 10 | -7.13 | 30 TREMIE 2 (JKR) | P100053019 | 10
CB468 | SGBM10 | Dec 4 2015 5:30PM | Dec 5 2015 12:15AM | 40.44 | 38.425 | 7.675, 9, 12 | 26.484 | 40.44 | 11.941 |  | 6.775 | 6.775 | 10T25 | T10-150 | 12.941 | 7.2636 | 9 | -100 | 30 TREMIE 2 (JKR) | P100053412 | 9
CB469 | SGBM10 | Nov 25 2015 8:30AM | Nov 27 2015 2:09PM | 40.447 | 38.425 | 9.023, 14.6 | 26.64 | 40.447 | 11.785 |  | 5.772 | 5.772 | 10T25 | T10-150 | 12.785 | 7.1687 | 10 | -100 | 30 TREMIE 2 (JKR) | P100052833 | 10
CB471 | SGBM12 | Oct 31 2015 2:50PM | Nov 2 2015 5:05PM | 40.43 | 38.425 | 7.13, 10.5, 13 | 26.645 | 40.43 | 11.78 |  | 7.085 | 7.085 | 10T25 | T10-150 | 13.1 | 7.1657 | 9 | -100 | 30 TREMIE 2 (JKR) | P100051545 | 9
CB472 | SGBM10 | Nov 19 2015 6:30PM | Nov 21 2015 11:20PM | 40.51 | 38.425 | 6, 11.7, 13.3 | 26.672 | 40.51 | 11.753 |  | 8.228 | 8.228 | 10T25 | T10-150 | 12.753 | 7.1493 | 9 | -100 | 30 TREMIE 2 (JKR) | 1 | 9
CB474 | SGBM32 | Nov 7 2015 10:15AM | Nov 9 2015 6:00PM | 40.53 | 38.425 | 6.335, 10, 13 | 26.655 | 40.53 | 11.77 |  | 8.11 | 7.775 | 10T25 | T10-150 | 12.77 | 7.1596 | 9 | 25.7 | 30 TREMIE 2 (JKR) | P100051902 | 9
CB475 | SGBM12 | Oct 30 2015 8:00AM | Oct 31 2015 4:30PM | 40.47 | 38.425 | 8, 9, 11.8, 14.7 | 26.42 | 2.045 | 12.005 |  | 7.3 | 7.63 | 10T25 | T10-150 | 13.2 | 7.3025 | 9 | -100 | 30 TREMIE 2 (JKR) | P100051456 | 9
CB476 |  | Nov 3 2015 7:00PM | Nov 5 2015 5:50PM | 40.54 | 38.425 | 7.62, 8, 11.9, 14.7 | 26.468 | 40.54 | 11.957 |  | 7.585 | 0 | 10T25 | T10-150 | 22.957 | 7.2733 | 10 | -100 | 30 TREMIE 2 (JKR) | P100051673 | 10
CB477 | SGBM10 | Nov 25 2015 8:00AM | Nov 28 2015 4:09PM | 40.527 | 38.425 | 7.207, 8.3, 12, 13.6 | 26.483 | 40.527 | 11.942 |  | 7.413 | 7.406 | 10T25 | T10-150 | 12.935 | 7.2642 | 9 | -100 | 30 TREMIE 2 (JKR) | P100052885 | 9
CB478 | SGBM10 | Dec 1 2015 8:00AM | Dec 4 2015 7:30PM | 40.469 | 38.425 | 7.128, 8, 11, 13.5, 14.6 | 26.643 | 40.469 | 11.782 |  | 7.599 | 7.6 | 10T25 | T10-150 | 12.783 | 7.1669 | 9 | 25.6 | 30 TREMIE 2 (JKR) | P100053290 | 9
CB479 | SGBM10 | Dec 22 2015 8:00AM | Dec 23 2015 5:53PM | 40.58 | 38.425 | 9, 12, 14.8 | 26.63 | 40.58 | 11.795 |  | 5.94 | 7.748 | 10T25 | T10-150 | 12.795 | 7.1748 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054220 | 9
CB480 | SGBM10 | Dec 26 2015 6:10PM | Dec 29 2015 8:12PM | 40.597 | 38.425 | 9, 10.5, 14, 15.238 | 26.672 | 40.597 | 11.753 |  | 6.238 | 7.688 | 10T25 | T10-150 | 12.753 | 7.1493 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054464 | 9
CB481 | SGBM10 | Jan 6 2016 10:45AM | Jan 7 2016 6:34PM | 40.6 | 38.425 | 9, 12 | 26.679 | 40.6 | 11.746 |  | 0 | 7.056 | 10T25 | T10-150 | 12.75 | 7.145 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054952 | 9
CB482 | SGBM10 | Jan 13 2016 8:15AM | Jan 15 2016 10:10AM | 40.452 | 38.425 | 8, 9, 11.2, 12.5, 14.65 | 26.6 | 40.452 | 11.825 |  | 0 | 6.805 | 10T25 | T10-150 | 12.825 | 7.193 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100055295 | 8.5
CB483 | SGBM10 | Dec 7 2015 8:00AM | Dec 8 2015 1:27PM | 40.69 | 38.425 | 9.273, 13 | 26.613 | 40.69 | 11.812 |  | 5.272 | 5.272 | 10T25 | T10-150 | 12.812 | 7.1851 | 9 | 25.3 | 30 TREMIE 2 (JKR) | P100053487 | 9
CB484 | SGBM12 | Dec 11 2015 11:15AM | Dec 15 2015 1:40PM | 40.69 | 38.425 | 11.5 | 27.312 | 40.69 | 11.113 |  | 2.4 | 4.197 | 12T25 | T12-150 | 12.113 | 6.7599 | 9 | -100 | 30 TREMIE 2 (JKR) | 28066400 | 9
CB485 | SGBM10 | Dec 23 2015 4:15PM | Dec 26 2015 2:40PM | 40.61 | 38.425 | 11 | 27.41 | 40.61 | 11.015 |  | 2.85 | 3.548 | 12T25 | T10-150 | 12 | 6.7003 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054286 | 9
CB486 | SGBM10 | Dec 30 2015 10:00AM | Dec 30 2015 5:55PM | 40.73 | 38.425 | 13 | 27.453 | 40.73 | 10.972 |  | 1.045 | 2.745 | 12T25 | T10-150 | 12 | 6.6742 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054547 | 9
CB487 | SGBM10 | Nov 28 2015 8:30AM | Dec 2 2015 9:52PM | 40.7 | 38.425 | 12.16, 16, 19.5, 21 | 20.23 | 40.7 | 18.195 |  | 8.99 | 9.932 | 12T25 | T10-150 | 20.423 | 11.0679 | 15 | -27.7 | 30 TREMIE 2 (JKR) | P100053146, P100053148 | 8, 7
CB488 | SGBM12 | Dec 9 2015 10:00AM | Dec 10 2015 7:56PM | 40.74 | 38.425 | 0.25, 15.278 | 24.77 | 40.74 | 13.655 |  | 1.092 | 1.092 | 12T25 | T10-150 | 14.655 | 8.3062 | 10 | -100 | 30 TREMIE 2 (JKR) | P100053626 | 10
CB489 | SGBM12 | Dec 15 2015 3:40PM | Dec 18 2015 6:25PM | 40.597 | 38.425 | 11, 12 | 27.423 | 40.597 | 11.002 |  | 2.45 | 3.765 | 12T25 | T12-150 | 9 | 6.6924 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054018 | 9
CB491 | SGBM10 | Jan 9 2016 5:00PM | Jan 11 2016 7:52PM | 40.635 | 38.425 | 10.5, 13.5 | 27.451 | 40.635 | 10.974 |  | 0 | 4.337 | 12T25 | T10-150 | 12 | 6.6754 | 9 | -100 | 30 TREMIE 2 (JKR) | P100055107 | 9
CB492 | SGBM10 | Jan 4 2016 4:00PM | Jan 5 2016 4:13PM | 40.692 | 38.425 | 11.5, 13.8 | 27.464 | 40.692 | 10.961 |  | 0 | 3.898 | 12T25 | T10-150 | 12 | 6.6675 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100054791 | 8.5
CB493 | SGBM10 | Dec 31 2015 4:40PM | Jan 2 2016 5:00PM | 40.627 | 38.425 | 12, 14 | 27.407 | 40.627 | 11.018 |  | 2.11 | 3.105 | 12T25 | T10-150 | 12 | 6.7021 | 8.5 | -100 | 30 TREMIE 2 (JKR) | P100054665 | 8.5
CB494 | SGBM10 | Jan 8 2016 8:00AM | Jan 8 2016 5:06PM | 40.6 | 38.425 | 12, 12.6 | 27.487 | 40.6 | 10.938 |  | 0 | 2.295 | 12T25 | T10-150 | 12 | 6.6535 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054969 | 9
CB495 | SGBM10 | Jan 12 2016 4:34PM | Jan 13 2016 7:45PM | 40.685 | 38 | 10.5, 12 | 27.37 | 40.685 | 10.63 |  | 0 | 4.362 | 12T25 | T10-150 | 12 | 6.4661 | 9 | -100 | 30 TREMIE 2 (JKR) | P100055196 | 9
CB496 | SGBM10 | Dec 19 2015 8:00AM | Dec 21 2015 5:50PM | 40.625 | 38.425 | 13, 14.2 | 27.339 | 40.625 | 11.086 |  | 1.305 | 2.115 | 12T25 | T10-150 | 12.086 | 6.7435 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054097 | 9
CB497 | SGBM10 | Dec 8 2015 9:50AM | Dec 8 2015 6:39PM | 40.66 | 38.425 | 13 | 27.122 | 2.235 | 11.303 |  | 2.19 | 2.19 | 12T25 | T10-150 | 12.303 | 6.8755 | 9 | -100 | 30 TREMIE 2 (JKR) | P100053503 | 9
CB498 | SGBM10 | Jan 12 2016 8:00AM | Jan 12 2016 5:39PM | 40.77 | 38.425 | 4, 13 | 27.26 | 40.77 | 11.165 |  | 0 | 2.635 | 12T25 | T10-150 | 12.162 | 6.7916 | 9 | -100 | 30 TREMIE 2 (JKR) | P100055151 | 9
CB499 | SGBM10 | Jan 2 2016 5:30PM | Jan 4 2016 4:42PM | 40.831 | 38.425 | 11, 12.5 | 27.42 | 40.831 | 11.005 |  | 0 | 5.096 | 12T25 | T10-150 | 12 | 6.6942 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054747 | 9
CB500 | SGBM10 | Dec 29 2015 3:00PM | Dec 30 2015 3:02PM | 40.76 | 38.425 | 11.6, 13 | 27.44 | 40.76 | 10.985 |  | 2.668 | 3.34 | 12T25 | T10-150 | 12 | 6.6821 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054533 | 9
CB501 | SGBM10 | Jan 8 2016 6:00PM | Jan 9 2016 6:11PM | 40.58 | 38.425 | 12, 13 | 27.186 | 40.58 | 11.239 |  | 0 | 2.535 | 12T25 | T10-150 | 12.239 | 6.8366 | 9 | -100 | 30 TREMIE 2 (JKR) | P100055035 | 9
CB502 | SGBM10 | Jan 19 2016 4:45PM | Jan 20 2016 6:45PM | 40.738 | 38.425 | 11, 14.4 | 27.324 | 40.738 | 11.101 |  | 0 | 4.973 | 12T25 | T10-150 | 12.102 | 6.7526 | 9 | -100 | 30 TREMIE 2 (JKR) | P201045375 | 9
CB503 | SGBM10 | Dec 21 2015 8:00AM | Dec 21 2015 7:08PM | 40.674 | 38.425 | 11, 13 | 27.2 | 40.674 | 11.225 |  | 3.308 | 4.438 | 12T25 | T10-150 | 12.225 | 6.8281 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054103 | 9
CB504 | SGBM12 | Dec 14 2015 6:20PM | Dec 15 2015 3:55PM | 40.68 | 38.425 | 13, 14.4 | 27.292 | 40.68 | 11.133 |  | 1.5 | 2.2 | 12T25 | T12-150 | 12 | 6.7721 | 9 | -100 | 30 TREMIE 2 (JKR) | P100053837 | 9
CB505 | SGBM10 | Jan 5 2016 3:30PM | Jan 6 2016 3:14PM | 40.76 | 38.425 | 10.5, 11.5 | 27.405 | 40.76 | 11.02 |  | 0 | 4.902 | 12T25 | T10-150 | 12 | 6.7034 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054837 | 9
CB506 | SGBM10 | Dec 30 2015 5:30PM | Dec 31 2015 7:48PM | 40.7 | 38.425 | 11, 14 | 27.383 | 40.7 | 11.042 |  | 3.34 | 5.01 | 12T25 | T10-150 | 12.042 | 6.7168 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054622 | 9
CB507 | SGBM10 | Dec 26 2015 1:00PM | Dec 26 2015 10:00PM | 40.77 | 38 | 12 | 27.436 | 40.77 | 10.564 |  | 2.132 | 4.197 | 12T25 | T10-150 | 12 | 6.426 | 8 | -100 | 30 TREMIE 2 (JKR) | P100054333 | 8
CB508 | SGBM10 | Dec 17 2015 3:25PM | Dec 18 2015 11:50AM | 40.705 | 38.425 | 10, 12 | 27.355 | 40.705 | 11.07 |  | 4.25 | 4.755 | 12T25 | T12-150 | 12.07 | 6.7338 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054065 | 9
CB509 | SGBM12 | Dec 9 2015 2:15PM | Dec 11 2015 6:40PM | 40.92 | 38.425 | 18 | 27.528 | 40.92 | 10.897 |  | 1.215 | 1.215 | 12T25 | T10-150 | 15.462 | 6.6285 | 12 | 27.6 | 30 TREMIE 2 (JKR) | P100053692 | 12
CB510 | SGBM12 | Dec 3 2015 8:00AM | Dec 3 2015 7:10PM | 40.925 | 38.425 | 16.815 | 23.66 | 40.925 | 14.765 |  | 1.185 | 1.185 | 12T25 | T10-150 | 15.765 | 8.9814 | 12 | -100 | 30 TREMIE 2 (JKR) | P100053224, P100053224 | 6, 6
CB511 | SGBM12 | Nov 6 2015 8:00AM | Nov 7 2015 5:10PM | 40.915 | 38.425 | 17.65, 20.5, 24 | 16.515 | 40.915 | 21.91 |  | 8.15 | 8.15 | 10T25 | T10-150 | 22.51 | 13.3277 | 22 | -147.6 | 30 TREMIE 2 (JKR) | P100051815, P100051820 | 5, 17
CB512 | SGBM12 | Nov 21 2015 8:00AM | Nov 21 2015 11:25PM | 40 | 38.425 | 17.053 | 23.451 | 40 | 14.974 |  | 1.097 | 1.097 | 12T25 | T10-150 | 15.974 | 9.1085 | 12 | -100 | 30 TREMIE 2 (JKR) | P100052591 | 12
CB513 | SGBM12 | Nov 30 2015 8:00AM | Nov 30 2015 8:25PM | 41.005 | 38.425 | 16.392 | 24.385 | 41.005 | 14.04 |  | 1.058 | 1.058 | 12T25 | T10-150 | 15.04 | 8.5404 | 12 | -100 | 30 TREMIE 2 (JKR) | P100052991 | 12
CB514 | SGBM12 | Dec 4 2015 9:34AM | Dec 4 2015 9:06PM | 41.005 | 38.425 | 17 | 24.177 | 41.005 | 14.248 |  | 0.628 | 1.17 | 12T25 | T10-150 | 15.248 | 8.6669 | 13 | -100 | 30 TREMIE 2 (JKR) | P100053307, P100053308 | 7, 6
CB515 | SGBM12 | Dec 8 2015 8:00AM | Dec 8 2015 8:30PM | 41.188 | 38.425 | 16.7 | 24.021 | 41.188 | 14.404 |  | 1.15 | 1.15 | 12T25 | T10-150 | 15.404 | 8.7618 | 11 | -100 | 30 TREMIE 2 (JKR) | P100053512 | 11
CB516 | SGBM10 | Nov 14 2015 8:00AM | Nov 16 2015 4:40PM | 40.95 | 38.425 | 16.6 | 25.208 | 40.95 | 13.217 |  | 0.262 | 1.087 | 12T25 | T10-150 | 12 | 8.0398 | 10 | -100 | 30 TREMIE 2 (JKR) | P100052243 | 10
CB517 | SGBM12 | Nov 25 2015 8:30AM | Nov 27 2015 10:00PM | 40.965 | 38.425 | 17.5 | 24.305 | 40.965 | 14.12 |  | 0.56 | 1.302 | 12T25 | T10-150 | 15.113 | 8.5891 | 12 | -100 | 30 TREMIE 2 (JKR) | P100052866 | 12
CB518 | SGBM12 | Dec 1 2015 4:30PM | Dec 2 2015 7:20PM | 41.101 | 38.425 | 14.61 | 26.104 | 41.101 | 12.321 |  | 1.147 | 1.147 | 12T25 | T10-150 | 13.322 | 7.4948 | 10 | -100 | 30 TREMIE 2 (JKR) | P100053127 | 10
CB519 | SGBM12 | Dec 5 2015 2:59PM | Dec 7 2015 5:00PM | 41.25 | 38.425 | 14.145 | 26.499 | 41.25 | 11.926 |  | 1.123 | 1.123 | 12T25 | T10-150 | 12.926 | 7.2545 | 10 | -100 | 30 TREMIE 2 (JKR) | P100053412 | 10
CB520 | SGBM12 | Nov 23 2015 8:00AM | Nov 23 2015 9:53PM | 41.06 | 38.425 | 14.4, 15 | 26.338 | 41.06 | 12.087 |  | 1.18 | 1.18 | 12T25 | T10-150 | 13.087 | 7.3524 | 10 | -100 | 30 TREMIE 2 (JKR) | P100052668 | 10
CB521 | SGBM10 | Nov 12 2015 4:00PM | Nov 16 2015 6:05PM | 40.97 | 38.425 | 14.005 | 26.374 | 40.97 | 12.051 |  | 1.1 | 1.1 | 12T25 | T10-150 | 13.051 | 7.3305 | 12 | -100 | 30 TREMIE 2 (JKR) | P100052252, P100052259 | 9, 3
CB522 | SGBM12 | Dec 5 2015 8:00AM | Dec 5 2015 10:45PM | 41.22 | 38.425 | 14.41, 15 | 26.422 | 41.22 | 12.003 |  | 1.148 | 1.148 | 12T25 | T10-150 | 13.003 | 7.3013 | 9 | -100 | 30 TREMIE 2 (JKR) | P100053435 | 9
CB523 | SGBM12 | Nov 30 2015 5:00PM | Dec 1 2015 8:28PM | 41.143 | 38.425 | 15.78 | 24.87 | 41.143 | 13.555 |  | 1.003 | 1.003 | 12T25 | T10-150 | 14.565 | 8.2454 | 12 | -100 | 30 TREMIE 2 (JKR) | P100053073 | 12
CB524 |  | Nov 23 2015 10:00AM | Nov 23 2015 11:45PM | 41.142 | 38.425 | 14.215 | 26.375 | 41.142 | 12.05 |  | 1.132 | 1.13 | 12T25 | T10-150 | 13.05 | 7.3299 | 10 | -100 | 30 TREMIE 2 (JKR) | P100052675 | 10
CB525 | SGBM12 | Nov 19 2015 2:00PM | Nov 20 2015 10:03PM | 41.14 | 38.425 | 13.707 | 26.942 | 41.14 | 11.483 |  | 1.108 | 1.108 | 12T25 | T10-150 | 12.5 | 6.985 | 10 | -100 | 30 TREMIE 2 (JKR) | P100052507 | 10
CB526 | SGBM12 | Dec 7 2015 8:00AM | Dec 7 2015 6:50PM | 41.31 | 38.425 | 14.163 | 27.095 | 41.31 | 11.33 |  | 1.142 | 1.142 | 12T25 | T12-150 | 12.33 | 6.8919 | 9 | -100 | 30 TREMIE 2 (JKR) | P100053445 | 9
CB527 | SGBM12 | Dec 3 2015 8:00AM | Dec 4 2015 6:25PM | 41.14 | 38.425 | 14 | 27.211 | 41.14 | 11.214 |  | 0.69 | 1.17 | 12T25 | T10-150 | 12.214 | 6.8214 | 9 | -100 | 30 TREMIE 2 (JKR) | P100053286 | 9
CB528 | SGBM12 | Nov 28 2015 8:00AM | Nov 30 2015 12:59PM | 41.022 | 38.425 | 14.357 | 27.002 | 41.022 | 11.423 |  | 1.088 | 1.088 | 12T25 | T10-150 | 12.423 | 6.9485 | 9 | -100 | 30 TREMIE 2 (JKR) | P100052961 | 9
CB529 | SGBM12 | Nov 24 2015 8:00AM | Nov 24 2015 7:35PM | 41.28 | 38.425 | 16.063 | 25.66 | 41.28 | 12.765 |  | 1.057 | 1.057 | 12T25 | T10-150 | 13.765 | 7.7648 | 10 | -100 | 30 TREMIE 2 (JKR) | P100052716 | 10
CB392 | SGBM12 | Jan 7 2016 1:15PM | Jan 9 2016 3:12PM | 39.753 | 37.775 | 6, 9, 11.3, 14.3 | 26.68 | 1.978 | 11.095 |  | 10.342 | 10.342 | 10T25 | T10-150 | 12.095 | 6.749 | 8.5 | -6.74 | 30 TREMIE 2 (JKR) | P100055012 | 8.5

## 900
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
CB470 | SGBM32 | Nov 7 2015 8:15AM | Nov 11 2015 6:20PM | 40.44 | 38.425 | 8, 10, 12.5 | 26.591 | 40.44 | 11.834 |  | 6.597 | 0 | 10T25 | T10-150 | 12.834 | 7.5294 | 9 | 19.5 | 30 TREMIE 2 (JKR) | P100051965 | 9
CB473 | SGBM32 | Nov 12 2015 11:15AM | Nov 13 2015 6:45PM | 40.535 | 38.425 | 6.7, 10, 12.5 | 26.625 | 40.535 | 11.8 |  | 7.633 | 7.633 | 10T25 | T10-150 | 12.8 | 7.5078 | 9 | 19.9 | 30 TREMIE 2 (JKR) | P100052109 | 9
CB490 | SGBM10 | Dec 22 2015 9:30AM | Dec 22 2015 6:30PM | 40.705 | 38.425 | 11 | 27.337 | 2.28 | 11.088 |  | 3.113 | 4.361 | 12T25 | T10-150 | 12.088 | 7.0548 | 9 | -100 | 30 TREMIE 2 (JKR) | P100054176 | 9
CB530 | SGBM12 | Nov 19 2015 5:30PM | Nov 20 2015 8:15PM | 41.19 | 0 | 15.737 | 24.608 | 41.19 | -24.608 |  | 0 | 1.048 |  |  | 14.8 | -15.657 | 12 | -176.6 | 30 TREMIE 2 (JKR) | P100052498 | 12

## 1050
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
17.1/K2 | SGBM10 | Jan 15 2016 2:00PM | Jan 19 2016 4:45PM | 40.464 | 28.575 | 8, 9, 11, 12.1, 15, 15.8 | 25.291 | 11.889 | 3.284 |  | 8.175 | 8.176 | 9T25 | T10-150 | 4.285 | 2.844 | 4 | -100 | 30 TREMIE 2 (JKR) | P201045344 | 4
18.1/K2 | SGBM12 | Feb 15 2016 9:30AM | Feb 16 2016 5:50PM | 40.54 | 28.575 | 9, 14 | 25.265 | 11.965 | 3.31 |  | 8.38 | 8.38 | 9T25 | T10-150 | 4.31 | 2.8665 | 4.5 | -100 | 30 TREMIE 2 (JKR) | P201046405 | 4.5
18.1a/K2 | SGBM10 | Jan 21 2016 8:00AM | Jan 22 2016 8:08PM | 40.61 | 35.525 | 17, 18.5, 20 | 19.993 | 5.085 | 15.532 |  | 6.905 | 6.905 | 9T25 | T10-150 | 12 | 13.4509 | 16 | -100 | 30 TREMIE 2 (JKR) | P201045417, P201045419 | 8, 8
19.1/K2 | SGBM10 | Jan 23 2016 8:30AM | Jan 27 2016 11:24PM | 40.59 | 35.525 | 13, 14, 15, 16, 18.5, 20, 21.3 | 19.951 | 5.065 | 15.574 |  | 10.117 | 10.118 | 9T25 | T10-150 | 12 | 13.4873 | 16 | -100 | 30 TREMIE 2 (JKR) | P201045597, P201045602 | 8, 8
20.1/K2 | SGBM10 | Jan 30 2016 8:30AM | Feb 12 2016 9:55AM | 40.78 | 35.525 | 12, 14.5, 16, 18.5, 20, 21.5, 22.2 | 19.57 | 5.255 | 15.955 |  | 12.105 | 12.105 | 9T25 | T10-150 | 12 | 13.8173 | 18 | -100 | 30 TREMIE 2 (JKR) | P201046236, P201046237 | 9, 9
21.1/K2 | SGBM10 | Jan 28 2016 8:30AM | Jan 29 2016 6:55PM | 40.85 | 35.525 | 11, 16, 18 | 19.847 | 5.325 | 15.678 |  | 13.323 | 13.323 | 9T25 | T10-150 | 12 | 13.5774 | 18 | -100 | 30 TREMIE 2 (JKR) | P201045744, P201045745 | 9, 9

## 1500
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
10.1/H2/1 | SGBM28 | Feb 2 2016 3:30PM | Feb 5 2016 4:05PM | 39.1 | 28.275 | 5.5, 7, 10, 12, 16, 16.25 | 23.7 | 10.825 | 4.575 |  | 11.3 | 11.3 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.575 | 8.0857 | 10 | 1.91 | 30 TREMIE 2 (JKR) | P201046174 | 10
10.1/H2/2 | SGBM28 | Feb 23 2016 1:00PM | Feb 29 2016 3:45PM | 39.405 | 28.275 | 5, 6, 8, 9, 11, 11.5, 13, 13.6, 15, 15.5, 16.4 | 23.69 | 11.13 | 4.585 |  | 13.608 | 13.608 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.585 | 8.1034 | 10 | 1.89 | 30 TREMIE 2 (JKR) | P101055556 | 10
10.1/H2/3 | SGBM30 | Mar 5 2016 8:30AM | Mar 7 2016 8:05PM | 39.53 | 28.275 | 6, 9, 12 | 23.72 | 11.255 | 4.555 |  | 12.26 | 12.26 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.6 | 8.0504 | 10 | 24.2 | 30 TREMIE 2 (JKR) | P201047538 | 10
10.1/H2/4 | SGBM28 | Mar 1 2016 8:00AM | Mar 3 2016 8:45PM | 39.55 | 28.275 | 7.5, 9, 13, 14.5, 16.8 | 23.73 | 11.275 | 4.545 |  | 11.9 | 11.9 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.545 | 8.0327 | 10 | 24.5 | 30 TREMIE 2 (JKR) | P201047380 | 10
10.1/K2/1 | SGBM28 | Feb 15 2016 10:00AM | Feb 20 2016 4:35PM | 39.39 | 28.075 | 5.3, 6, 7, 8, 9, 10, 10.5, 12, 13, 15, 16.5, 16.78 | 23.31 | 11.315 | 4.765 |  | 11.768 | 11.768 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.765 | 8.4215 | 10 | 18.7 | 30 TREMIE 2 (JKR) | P201046663 | 10
10.1/K2/2 | SGBM28 | Jan 28 2016 8:00AM | Feb 2 2016 2:30PM | 39.52 | 28.075 | 3, 4, 6.5, 9.3, 11, 13.5, 15, 17.65 | 23.427 | 11.445 | 4.648 |  | 15.65 | 15.65 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 8.648 | 8.2148 | 10.5 | 27.8 | 30 TREMIE 2 (JKR) | P201046013 | 10.5
11.1/H2/1 | SGBM28 | Feb 20 2016 4:30PM | Feb 23 2016 2:13PM | 39.65 | 28.275 | 7, 9, 12, 16.5 | 23.622 | 11.375 | 4.653 |  | 11.143 | 11.143 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.653 | 8.2236 | 12 | 45.9 | 30 TREMIE 2 (JKR) | P201046815 | 12
11.1/H2/2 | SGBM25 | Jan 14 2016 8:15AM | Jan 16 2016 12:20PM | 40.68 | 28.275 | 6, 8, 12.5, 14.5, 17.6 | 23.74 | 12.405 | 4.535 |  | 11.913 | 4.535 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.535 | 8.015 | 10 | 24.8 | 30 TREMIE 2 (JKR) | P201045237 | 10
11.1/H2/3 | SGBM32 | Jan 6 2016 10:30AM | Jan 8 2016 4:46PM | 40.66 | 28.275 | 7, 10.5, 12.6, 17.6 | 23.565 | 12.385 | 4.71 |  | 12.238 | 4.71 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.71 | 8.3243 | 10 | 20.1 | 30 TREMIE 2 (JKR) | P100054968 | 10
11.1/H2/4 | SGBM30 | Dec 5 2015 5:30PM | Dec 8 2015 1:40PM | 40.58 | 28.275 | 6, 9.5, 12, 17.1 | 23.653 | 12.305 | 4.622 |  | 11.715 | 4.622 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.622 | 8.1688 | 10 | 22.4 | 30 TREMIE 2 (JKR) | P100053486 | 10
11.1/K2/1 | SGBM28 | Dec 17 2015 11:00AM | Dec 21 2015 4:55PM | 40.58 | 28.075 | 7, 8.5, 10, 13, 14.5, 17.6 | 23.504 | 12.505 | 4.571 |  | 11.905 | 4.571 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.571 | 8.0787 | 12 | 48.5 | 30 TREMIE 2 (JKR) | P100054092 | 12
11.1/K2/2 | SGBM30 | Dec 10 2015 4:20PM | Dec 12 2015 10:40AM | 40.614 | 28.075 | 6, 8, 13, 17.7 | 23.514 | 12.539 | 4.561 |  | 13.118 | 4.561 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.561 | 8.061 | 10 | 24.1 | 30 TREMIE 2 (JKR) | P100053732 | 10
16.1/H2/1 | SGBM30 | Nov 25 2015 11:30AM | Nov 27 2015 7:40PM | 40.547 | 28.075 | 6, 8, 13.5, 18.2 | 23.52 | 12.472 | 4.555 |  | 13.14 | 4.555 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.555 | 8.0504 | 11 | -100 | 30 TREMIE 2 (JKR) | P100052858 | 11
16.1/H2/2 | SGBM30 | Nov 30 2015 6:30PM | Dec 2 2015 8:25PM | 40.571 | 28.075 | 6.5, 8.5, 12.5, 15 | 23.442 | 12.496 | 4.633 |  | 12.97 | 4.633 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.633 | 8.1883 | 10 | -100 | 30 TREMIE 2 (JKR) | P100053136 | 10
16.1/H2/3 | SGBM25 | Jan 23 2016 11:00AM | Jan 27 2016 4:05PM | 40.46 | 28.075 | 8, 9, 12, 13, 15, 18 | 23.535 | 12.385 | 4.54 |  | 12.905 | 12.905 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.54 | 8.0239 | 10 | -100 | 30 TREMIE 2 (JKR) | P201045545 | 10
16.1/H2/4 | SGBM32 | Dec 21 2015 6:30PM | Dec 28 2015 1:56PM | 40.599 | 28.075 | 6, 7, 9, 10.3, 11, 12.5, 14, 16, 17.7 | 23.49 | 12.524 | 4.585 |  | 12.772 | 4.585 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.585 | 8.1034 | 10 | -100 | 30 TREMIE 2 (JKR) | P100054353 | 10
16.1/H2/5 | SGBM25 | Jan 9 2016 1:30PM | Jan 13 2016 10:15PM | 40.514 | 28.075 | 5, 7, 9.6, 11, 14, 16, 18.6 | 22.46 | 12.439 | 5.615 |  | 14.275 | 5.499 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 6.615 | 9.9238 | 12 | -100 | 30 TREMIE 2 (JKR) | P100055213 | 12
17.1/H2/3 | SGBM12 | Feb 19 2016 3:40PM | Feb 24 2016 11:13AM | 40.45 | 25.775 | 9, 10, 12, 13, 15, 16, 18.5, 19.8 | 21.174 | 14.675 | 4.601 |  | 11.5 | 11.5 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.601 | 8.1317 | 10 | -100 | 30 TREMIE 2 (JKR) | P201046876 | 10
17.1/H2/4 | SGBM25 | Feb 24 2016 8:15AM | Mar 1 2016 6:30PM | 40.413 | 25.775 | 8.5, 10, 12, 13, 15, 15.6, 17, 17.6, 19, 19.8, 20 | 20.982 | 14.638 | 4.793 |  | 12.61 | 12.61 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.793 | 8.471 | 10 | -100 | 30 TREMIE 2 (JKR) | P201047200 | 10
17.1/H2/5 | SGBM25 | Mar 11 2016 1:00PM | Mar 15 2016 12:35PM | 40.34 | 25.775 | 9, 10, 11.5, 14.5, 16.5, 19.7 | 21.05 | 14.565 | 4.725 |  | 11.05 | 4.725 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.725 | 8.3508 | 10 | -100 | 30 TREMIE 2 (JKR) | P101055620 | 10
17.1/H2/6 | SGBM25 | Mar 2 2016 8:00AM | Mar 7 2016 11:30AM | 40.47 | 25.775 | 10.5, 12, 14, 15, 16, 17, 19.7, 19.81 | 21.163 | 14.695 | 4.612 |  | 11.428 | 11.428 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.606 | 8.1511 | 12 | -100 | 30 TREMIE 2 (JKR) | P101055589 | 12
17.1/J2/1 | SGBM25 | Feb 2 2016 2:30PM | Feb 5 2016 7:33PM | 40.42 | 25.875 | 7, 8.3, 10, 13, 16.5, 19.6 | 21.22 | 14.545 | 4.655 |  | 14.55 | 14.55 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.555 | 8.2271 | 10 | -8.22 | 30 TREMIE 2 (JKR) | P201046181 | 10
17.1/J2/2 | SGBM25 | Feb 11 2016 11:30AM | Feb 15 2016 8:05PM | 40.5 | 25.875 | 8, 9.2, 10.5, 13.5, 14.5, 17.5, 18.5 | 21.205 | 14.625 | 4.67 |  | 13.025 | 13.025 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.57 | 8.2536 | 10 | -100 | 30 TREMIE 2 (JKR) | P201046332 | 10
17.1/J2/3 | SGBM25 | Jan 28 2016 8:00AM | Feb 2 2016 4:25PM | 40.49 | 25.875 | 6, 7, 9, 10.5, 12.5, 13.2, 15, 17, 18.5 | 21.192 | 14.615 | 4.683 |  | 14.38 | 14.38 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.583 | 8.2766 | 10 | -100 | 30 TREMIE 2 (JKR) | P201045924 | 10
17.1/J2/4 | SGBM32 | Dec 31 2015 5:00PM | Jan 6 2016 4:45PM | 40.535 | 25.875 | 8, 9.5, 12.5, 14, 17, 19.8, 19.95 | 21.094 | 14.66 | 4.781 |  | 13.475 | 4.781 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.781 | 8.4498 | 11 | -100 | 30 TREMIE 2 (JKR) | P100047290 | 11
17.1/J2/5 | SGBM25 | Jan 16 2016 10:30AM | Jan 19 2016 5:55PM | 40.464 | 25.875 | 7.5, 12, 14.2, 18, 19.8 | 21.291 | 14.589 | 4.584 |  | 14.615 | 14.615 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.514 | 8.1016 | 10 | -100 | 30 TREMIE 2 (JKR) | P201045348 | 10
17.1/J2/6 | SGBM32 | Dec 28 2015 1:00PM | Dec 31 2015 7:25PM | 40.522 | 25.875 | 6.427, 10.052, 8.752, 6.452, 13.452, 13.952, 18.952 | 21.826 | 14.647 | 4.049 |  | 33.89 | 4.597 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.597 | 7.1561 | 11 | 53.7 | 30 TREMIE 2 (JKR) | P100054619 | 11
17.1/J2/7 | SGBM25 | Jan 20 2016 10:00AM | Jan 23 2016 1:56PM | 40.44 | 25.875 | 9, 11, 14, 15, 17, 19.7 | 21.12 | 14.565 | 4.755 |  | 13.353 | 13.353 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.655 | 8.4039 | 10 | -100 | 30 TREMIE 2 (JKR) | P100055515 | 10
17.1/J2/8 | SGBM32 | Jan 8 2016 1:30PM | Jan 12 2016 4:20PM | 40.485 | 25.875 | 7.5, 9, 11, 14, 16.5, 21, 21.278 | 19.78 | 14.61 | 6.095 |  | 14.366 | 4.497 | 19T25 (1-12m), 19T20 (12-15m) | T10-150 | 5.497 | 10.7722 | 10 | -100 | 30 TREMIE 2 (JKR) | P100055141 | 10

## 1650
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
11.1/F2 | SGBM32 | Dec 18 2015 2:30PM | Dec 21 2015 2:29PM | 30.74 | 28.575 | 5.5, 7, 9, 12.1 | 19.601 | 2.165 | 8.974 |  | 7.23 | 7.23 | 24T25 | T10-150 | 9.974 | 19.1911 | 24 | 25.1 | 30 TREMIE 2 (JKR) | P100054079, P100054080, P100054083 | 8, 8, 8
12.1/K2/1 | SGBM28 | Nov 30 2015 10:00AM | Dec 2 2015 5:16PM | 40.582 | 27.775 | 8, 9, 11, 13, 17, 19.5 | 21.533 | 12.807 | 6.242 |  | 13.31 | 6.242 | 24T25 | T10-150 | 7.242 | 13.3487 | 16 | 19.9 | 30 TREMIE 2 (JKR) | P100053117, P100053118 | 8, 8
12.1/K2/2 | SGBM28 | Nov 21 2015 6:30PM | Nov 25 2015 5:22PM | 40.55 | 27.775 | 9.5, 12, 15, 19.8 | 21.4 | 12.775 | 6.375 |  | 11.18 | 6.375 | 24T25 | T10-150 | 7.375 | 13.6331 | 16 | 17.4 | 30 TREMIE 2 (JKR) | P100052773, P100052775 | 8, 8
13.1/K2/1 | SGBM28 | Dec 4 2015 1:00PM | Dec 8 2015 3:45PM | 40.6 | 27.775 | 6.5, 9, 12.5, 18, 21, 26.4 | 14.833 | 12.825 | 12.942 |  | 21.375 | 12.942 | 24T25 | T10-150 | 13.942 | 27.6768 | 36 | 30.1 | 30 TREMIE 2 (JKR) | P100053493, P100053494, P100053495, P100053497 | 9, 9, 9, 9
13.1/K2/2 | SGBM28 | Dec 11 2015 3:30PM | Dec 15 2015 2:20PM | 40.612 | 27.775 | 7, 9, 12, 18, 23 | 14.843 | 12.837 | 12.932 |  | 21.677 | 12.932 | 24T25 | T10-150 | 13.932 | 27.6554 | 34 | 22.9 | 30 TREMIE 2 (JKR) | 28066409, 28066410, 28066415, 28066427 | 8, 6, 10, 10
14.1/K2/1 | SGBM28 | Dec 2 2015 3:30PM | Dec 4 2015 3:15PM | 40.6 | 27.775 | 5.265, 7, 10, 13, 18.7 | 22.72 | 12.825 | 5.055 |  | 18.827 | 5.05 | 24T25 | T10-150 | 6.05 | 10.8102 | 13 | 20.3 | 30 TREMIE 2 (JKR) | P100053267, P100053272 | 7, 6
14.1/K2/2 | SGBM28 | Dec 21 2015 1:00PM | Dec 23 2015 11:10PM | 40.599 | 27.775 | 5.25, 6, 9, 13.4, 15 | 22.65 | 12.824 | 5.125 |  | 8.95 | 5.125 | 24T25 | T10-150 | 6.125 | 10.9599 | 14 | 27.7 | 30 TREMIE 2 (JKR) | Pending, Pending | 7, 7
15.1/K2/1 | SGBM28 | Dec 29 2015 2:30PM | Jan 4 2016 11:20PM | 40.574 | 27.775 | 5.5, 6.5, 8.6, 9.5, 11.5, 12.4, 15, 16.5, 19 | 20.977 | 12.799 | 6.798 |  | 15.495 | 6.798 | 24T25 | T10-150 | 7.798 | 14.5377 | 18 | -100 | 30 TREMIE 2 (JKR) | P100054770, P100054773 | 9, 9
15.1/K2/2 | SGBM28 | Nov 25 2015 1:00PM | Nov 30 2015 12:32PM | 40.62 | 27.775 | 8, 9.5, 11.5, 13, 15, 16.5, 18.5, 19.4 | 22.773 | 12.845 | 5.002 |  | 14.41 | 14.41 | 24T25 | T10-150 | 6 | 10.6969 | 14 | -100 | 30 TREMIE 2 (JKR) | P100052959, P100052960 | 7, 7
16.1/K2/1 | SGBM28 | Dec 8 2015 8:15AM | Dec 11 2015 4:45PM | 40.6 | 27.775 | 5.5, 8, 11.5, 12.5, 14.3, 15, 17.5, 18.6 | 22.713 | 12.825 | 5.062 |  | 13.907 | 5.063 | 24T25 | T10-150 | 6.063 | 10.8252 | 12 | -100 | 30 TREMIE 2 (JKR) | P100053679 | 12
16.1/K2/2 | SGBM28 | Jan 5 2016 8:15AM | Jan 8 2016 6:40PM | 40.51 | 27.775 | 7, 9, 12, 13.5, 15.5, 17, 18.4 | 22.71 | 12.735 | 5.065 |  | 13.518 | 5.065 | 24T25 | T10-150 | 6.065 | 10.8316 | 14 | -100 | 30 TREMIE 2 (JKR) | P100054981, P100054980 | 7, 7
17.1/H2/1 | SGBM30 | Mar 3 2016 3:00PM | Mar 4 2016 7:55PM | 40.45 | 25.775 | 11, 14, 16 | 20.645 | 14.675 | 5.13 |  | 12.258 | 12.258 | 24T25 | T10-150 | 6.2 | 10.9706 | 15 | -100 | 30 TREMIE 2 (JKR) | P201047414, P201047417 | 8, 7
17.1/H2/2 | SGBM25 | Mar 8 2016 8:30AM | Mar 10 2016 8:15PM | 40.444 | 25.775 | 10.5, 14, 16.2, 18, 20.3 | 20.725 | 14.669 | 5.05 |  | 11.65 | 5.05 | 24T25 | T10-150 | 6.05 | 10.7995 | 14 | -100 | 30 TREMIE 2 (JKR) | P201047754, P201047757 | 7, 7

## 1800
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
12.1/H2/1 | SGBM28 | Dec 14 2015 7:15PM | Dec 17 2015 11:17AM | 40.625 | 27.775 | 5, 7.5, 13, 15, 18.6 | 22.363 | 12.85 | 5.412 |  | 15.122 | 5.412 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.412 | 13.7736 | 17 | 23.4 | 30 TREMIE 2 (JKR) | P100053921, P100053923 | 9, 8
12.1/H2/2 | SGBM28 | Dec 26 2015 8:30AM | Dec 29 2015 5:05PM | 40.66 | 27.775 | 6.5, 8.5, 12.5, 14.5, 19, 19.125 | 22.152 | 12.885 | 5.623 |  | 13.76 | 5.623 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.623 | 14.3106 | 18 | 25.8 | 30 TREMIE 2 (JKR) | P100054440, P100054441 | 9, 9
12.1/J2/1 | SGBM28 | Nov 13 2015 1:00PM | Nov 18 2015 5:48PM | 40.595 | 27.775 | 9, 11, 12.5, 16, 17.5, 21, 22.5, 25.4, 25.5 | 16.412 | 12.82 | 11.363 |  | 18.345 | 11.363 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 12.365 | 28.9191 | 34 | 17.6 | 30 TREMIE 2 (JKR) | P100052371, P100052372, P100052373 | 12, 10, 12
12.1/J2/2 | SGBM28 | Oct 31 2015 1:30PM | Nov 5 2015 9:20PM | 40.66 | 27.775 | 8, 10, 12, 12.5, 17, 18, 23, 25 | 16.43 | 12.885 | 11.345 |  | 17.283 | 11.345 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 12.345 | 28.8732 | 32 | 10.8 | 30 TREMIE 2 (JKR) | P100051678, P100051679, P100051680, P100051681 | 8, 8, 8, 8
13.1/G2/1 | SGBM25 | Mar 15 2016 4:50PM | Mar 18 2016 3:49PM | 32.01 | 27.775 | 2, 3.5, 4.3, 6.5, 8.5, 9.9 | -10.05 | 4.235 | 37.825 |  | 10.05 | 5.815 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.815 | 96.2654 | 18 | -81.3 | 30 TREMIE 2 (JKR) | P201048048, P201048049 | 9, 9
13.1/G2/2 | SGBM30 | Dec 2 2015 7:00PM | Dec 5 2015 8:30PM | 40.585 | 27.775 | 5, 9, 17, 19.1 | 22.295 | 12.81 | 5.48 |  | 15.345 | 5.48 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.48 | 13.9467 | 17 | 21.9 | 30 TREMIE 2 (JKR) | P100053393, P100053397 | 9, 8
13.1/H2/1 | SGBM25 | Feb 20 2016 11:00AM | Feb 27 2016 12:10PM | 40.61 | 27.775 | 7, 10.5, 12.5, 15.6, 17.8, 21, 22.3, 26, 27.5, 30, 31.3 | 12.013 | 12.835 | 15.762 |  | 26.4 | 26.4 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.212 | 40.1146 | 49 | 11.9 | 30 TREMIE 2 (JKR) | P201047058, P201047059, P201047060, P201047061, P201047062 | 10, 10, 10, 10, 9
13.1/H2/2 | SGBM30 | Jan 16 2016 10:30AM | Jan 20 2016 3:30PM | 40.6 | 27.775 | 7, 10, 14, 21, 24, 30.4 | 10.665 | 12.825 | 17.11 |  | 26.018 | 26.018 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 19.07 | 43.5453 | 51 | 17.1 | 30 TREMIE 2 (JKR) | P201045364, P201045365, P100055415, P100055417, P201045368 | 9, 12, 12, 9, 9
13.1/J2/1 | SGBM28 | Nov 18 2015 3:00PM | Nov 21 2015 11:20PM | 40.64 | 27.775 | 7, 10, 12.5, 18, 20.5, 26, 29 | 10.794 | 12.865 | 16.981 |  | 26.155 | 26.155 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 17.981 | 43.217 | 50 | 15.7 | 30 TREMIE 2 (JKR) | P100052590, P100052594, P100052598, P100052604, P100052605 | 10, 10, 10, 10, 10
13.1/J2/2 | SGBM28 | Nov 6 2015 9:00AM | Nov 13 2015 5:05PM | 40.666 | 27.775 | 6, 8, 11.5, 13, 16.5, 18, 20, 22, 24, 25, 27, 28.5, 31 | 11 | 12.891 | 16.775 |  | 26.19 | 16.775 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 17.775 | 42.6927 | 46 | 7.7 | 30 TREMIE 2 (JKR) | P100052102, P100052103, P100052104, P100052105, P100052107 | 9, 10, 9, 9, 9
14.1/G2/1 | SGBM30 | Dec 8 2015 11:30AM | Dec 10 2015 5:59PM | 40.55 | 27.775 | 7, 10, 13, 17, 18.8 | 22.251 | 12.775 | 5.524 |  | 13.07 | 5.524 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.524 | 14.0587 | 18 | 28 | 30 TREMIE 2 (JKR) | P100053614, P100053615 | 9, 9
14.1/G2/2 | SGBM30 | Nov 27 2015 9:30AM | Nov 30 2015 10:30PM | 40.53 | 27.775 | 6, 10, 12, 16, 17.5 | 22.285 | 12.755 | 5.49 |  | 14.915 | 5.49 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.49 | 13.9722 | 18 | 28.8 | 30 TREMIE 2 (JKR) | P100053009, P100053013 | 9, 9
14.1/H2/1 | SGBM30 | Nov 9 2015 2:00PM | Nov 14 2015 1:30PM | 40.675 | 27.775 | 5.107, 7, 8, 9, 11, 13, 14, 16, 17, 19, 19.9 | 22.3 | 12.9 | 5.475 |  | 20.04 | 5.475 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.475 | 13.934 | 18 | 29.2 | 30 TREMIE 2 (JKR) | P100052120, P100052121 | 9, 9
14.1/H2/2 | SGBM30 | Nov 18 2015 9:30AM | Nov 20 2015 10:25PM | 40.63 | 27.775 | 6, 8, 10, 14, 16 | 22.22 | 12.855 | 5.555 |  | 15.118 | 5.555 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.555 | 14.1376 | 16 | 13.2 | 30 TREMIE 2 (JKR) | P100052509, P100052510 | 8, 8
14.1/J2/1 | SGBM30 | Oct 23 2015 3:00PM | Oct 28 2015 6:55PM | 40.64 | 27.775 | 6, 8.5, 9.3, 12.5, 14, 16, 18, 19.4 | 22.288 | 12.865 | 5.487 |  | 14.6 | 5.487 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.5 | 13.9645 | 18 | 28.9 | 30 TREMIE 2 (JKR) | P100051256, P100051258 | 9, 9
14.1/J2/2 | SGBM30 | Oct 12 2015 3:00PM | Oct 19 2015 4:05PM | 40.7 | 27.775 | 7, 7.6, 9, 9.5, 11, 11.7, 13, 13.5, 15, 15.5, 17.2, 20 | 20.51 | 12.925 | 7.265 |  | 15.175 | 15.175 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 8.3 | 18.4896 | 24 | 29.8 | 30 TREMIE 2 (JKR) | P100050669, P100050674, P100050675 | 8, 8, 8
15.1/G2/1 | SGBM30 | Nov 21 2015 1:00PM | Nov 25 2015 4:15PM | 40.54 | 27.775 | 5.5, 7.5, 9, 13, 15, 18.4, 18.59 | 22.33 | 12.765 | 5.445 |  | 13.735 | 5.445 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.445 | 13.8576 | 18 | 29.9 | 30 TREMIE 2 (JKR) | P100052767, P100052770 | 9, 9
15.1/G2/2 | SGBM28 | Oct 27 2015 9:30AM | Oct 31 2015 3:40PM | 40.55 | 27.775 | 6, 7, 9.5, 10.7, 12, 15, 17, 19.9 | 22.238 | 12.775 | 5.537 |  | 15.02 | 5.542 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.0918 | 18 | 27.7 | 30 TREMIE 2 (JKR) | P100051447, P100051449 | 9, 9
15.1/H2/1 | SGBM30 | Oct 6 2015 4:30PM | Oct 12 2015 2:55PM | 40.5 | 27.775 | 6.2, 9, 10, 12, 13, 15, 16.2, 18.6, 19.8 | 22.26 | 12.725 | 5.515 |  | 14.895 | 14.895 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 7 | 14.0358 | 18 | 28.2 | 30 TREMIE 2 (JKR) | P100050278, P100050281 | 9, 9
15.1/H2/2 | SGBM30 | Oct 19 2015 2:20PM | Oct 23 2015 6:00PM | 40.5 | 27.775 | 5.5, 7, 9.3, 10.5, 13, 14.5, 19 | 22.21 | 12.725 | 5.565 |  | 15.075 | 5.565 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.163 | 20 | 41.2 | 30 TREMIE 2 (JKR) | P100050910, P100050912 | 10, 10
15.1/J2/1 | SGBM30 | Nov 5 2015 1:30PM | Nov 9 2015 4:00PM | 40.675 | 27.775 | 6, 8, 10, 14, 15.5, 19.8, 20.047 | 20.493 | 12.9 | 7.282 |  | 16.495 | 7.282 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 8.252 | 18.5328 | 21 | 13.3 | 30 TREMIE 2 (JKR) | P100051892, P100051893 | 10, 11
15.1/J2/2 | SGBM30 | Oct 28 2015 4:00PM | Nov 2 2015 2:30PM | 40.68 | 27.775 | 4, 5.5, 7, 9.5, 11.2, 14, 16, 18.4 | 22.239 | 12.905 | 5.536 |  | 14.905 | 5.536 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.0892 | 19 | -100 | 30 TREMIE 2 (JKR) | P100051530, P100051531 | 9.5, 9.5
16.1/G2/1 | SGBM30 | Nov 14 2015 2:30PM | Nov 18 2015 12:30PM | 40.54 | 27.775 | 7, 9, 11, 15, 17, 19.8 | 22.263 | 12.765 | 5.512 |  | 14.649 | 5.512 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.512 | 14.0281 | 19 | -100 | 30 TREMIE 2 (JKR) | P100052353, P100052354 | 9, 10
16.1/G2/2 | SGBM30 | Nov 2 2015 11:30AM | Nov 5 2015 4:03PM | 40.55 | 27.775 | 7, 9, 10.5, 14, 16.5, 19, 19.6 | 22.243 | 12.775 | 5.532 |  | 14.732 | 5.532 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.6 | 14.079 | 19 | -100 | 30 TREMIE 2 (JKR) | P100051656, P100051658 | 10, 9
17.1/G2/1 | SGBM30 | Dec 29 2015 11:30AM | Jan 2 2016 3:00PM | 40.488 | 27.775 | 8, 10, 12, 15.5, 19 | 22.249 | 12.713 | 5.526 |  | 12.9 | 5.526 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.526 | 14.0638 | 18 | -100 | 30 TREMIE 2 (JKR) | P100054653, P100054657 | 9, 9
17.1/G2/2 | SGBM30 | Jan 6 2016 8:30AM | Jan 13 2016 4:35PM | 40.666 | 27.775 | 9.5, 10.5, 11.5, 12.2, 13.4, 14.3, 15.3, 16, 17.2, 18.8 | 22.276 | 12.891 | 5.499 |  | 11.065 | 5.499 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.499 | 13.9951 | 18 | -100 | 30 TREMIE 2 (JKR) | P100055180, P100055183 | 9, 9
18.1/G2/1 | SGBM30 | Dec 12 2015 9:30AM | Dec 15 2015 11:25AM | 40.725 | 27.775 | 7, 14, 16.5, 18 | 22.223 | 12.95 | 5.552 |  | 15.14 | 5.552 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.552 | 14.13 | 18 | -100 | 30 TREMIE 2 (JKR) | 28066396, 28066397 | 9, 9
18.1/G2/2 | SGBM28 | Jan 18 2016 9:30AM | Jan 20 2016 5:35PM | 40.73 | 27.775 | 10.687, 13, 14.5, 18.5, 19.1 | 22.128 | 12.955 | 5.647 |  | 8.349 | 8.575 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.647 | 14.3717 | 19 | 32.2 | 30 TREMIE 2 (JKR) | P201045370, P100055418 | 9, 10
18.1/H2/1 | SGBM30 | Feb 3 2016 9:30AM | Feb 5 2016 2:59PM | 40.64 | 27.775 | 11, 13.5, 15, 18.8 | 22.22 | 12.865 | 5.555 |  | 8.932 | 8.932 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.555 | 14.1376 | 18 | -100 | 30 TREMIE 2 (JKR) | P201046171, P201046172 | 10, 8
18.1/H2/2 | SGBM30 | Jan 22 2016 3:00PM | Jan 27 2016 5:35PM | 40.64 | 27.775 | 10, 11.5, 13, 16, 18, 19, 19.28 | 22.12 | 12.865 | 5.655 |  | 11.163 | 11.163 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 6.655 | 14.3921 | 18 | -100 | 30 TREMIE 2 (JKR) | P201045557, P201045558 | 9, 9
18.1a/G2/1 | SGBM30 | Dec 22 2015 9:00AM | Dec 23 2015 8:25PM | 40.855 | 34.025 | 14, 17, 18 | 22.016 | 6.83 | 12.009 |  | 8.592 | 8.592 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.009 | 30.5632 | 38 | -100 | 30 TREMIE 2 (JKR) | P100054237, P100054238, P100054239, P100054241 | 9, 10, 9, 10
18.1a/G2/2 | SGBM30 | Jan 5 2016 9:30AM | Jan 7 2016 4:47PM | 40.75 | 34.025 | 15, 16, 18, 19.2, 19.377 | 21.973 | 6.725 | 12.052 |  | 6.325 | 6.325 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.052 | 30.6726 | 37 | -100 | 30 TREMIE 2 (JKR) | P100054929, P100054933, P100054938, P100054939 | 9, 9, 9, 10
18.1a/H2/1 | SGBM30 | Feb 5 2016 1:00PM | Feb 16 2016 2:50PM | 40.64 | 34.025 | 12, 13, 14, 15, 15.5, 16.5, 17.5, 18, 19, 19.41 | 21.969 | 6.615 | 12.056 |  | 8.578 | 8.578 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.056 | 30.6828 | 18 | -100 | 30 TREMIE 2 (JKR) | P201046385, P201046386, P201046389, P201046393 | 9, 9, 9, 9
18.1a/H2/2 | SGBM30 | Jan 27 2016 2:30PM | Jan 29 2016 4:55PM | 40.69 | 34.025 | 13, 14.5, 16, 19, 19.33 | 21.963 | 6.665 | 12.062 |  | 6.778 | 6.778 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 13.062 | 30.698 | 36 | -100 | 30 TREMIE 2 (JKR) | P201045733, P201045735, P201045736, P201045737 | 9, 9, 9, 9
19.1/G2/1 | SGBM30 | Dec 14 2015 6:45PM | Dec 18 2015 3:30PM | 40.974 | 34.025 | 14, 16, 17.5, 21, 22.5, 24.6 | 16.898 | 6.949 | 17.127 |  | 13.36 | 13.36 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.127 | 43.5886 | 50 | -100 | 30 TREMIE 2 (JKR) | P100053997, P100053998, P100054005, P100054011, P100054012 | 10, 10, 10, 10, 10
19.1/G2/2 | SGBM28 | Jan 13 2016 9:00AM | Jan 18 2016 1:20PM | 40.75 | 34.025 | 11, 13.5, 15.5, 16.6, 18, 19, 24, 24.7 | 16.905 | 6.725 | 17.12 |  | 13.355 | 14.855 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.12 | 43.5707 | 49 | -100 | 30 TREMIE 2 (JKR) | P201045279, P201045280, P201045283, P201045285, P100055339 | 10, 10, 9, 10, 10
19.1/H2/1 | SGBM25 | Feb 17 2016 9:00AM | Feb 20 2016 12:59PM | 40.74 | 34.025 | 16, 16.6, 17.5, 19, 21, 24.6 | 16.915 | 6.715 | 17.11 |  | 7.562 | 9.562 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 17.11 | 43.5453 | 53 | -100 | 30 TREMIE 2 (JKR) | P201046647, P201046648, P201046649, P201046650, P201046652, P201046653, P201046657 | 8, 8, 9, 9, 8, 8, 3
19.1/H2/2 | SGBM30 | Jan 29 2016 11:00AM | Feb 3 2016 6:23PM | 40.7 | 34.025 | 12, 13.2, 14, 16.5, 18, 20, 21, 24.6, 24.7 | 16.78 | 6.675 | 17.245 |  | 14.045 | 14.045 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 18.245 | 43.8889 | 50 | -100 | 30 TREMIE 2 (JKR) | P201045993, P201045995, P201045996, P201046005, P201046006, P201046013 | 9, 9, 9, 8, 8, 7
21.1/J2/1 | SGBM10 | Feb 3 2016 8:40AM | Feb 16 2016 6:05PM | 40.82 | 34.025 | 10, 11.3, 13.2, 14.2, 17, 18, 20, 21, 22 | 19.515 | 6.795 | 14.51 |  | 13.485 | 13.485 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 16.51 | 36.9282 | 44.5 | -100 | 30 TREMIE 2 (JKR) | P201045211, P201045845, P201045501, P201045503, P201045504 | 4.5, 9, 9, 12, 10
21.1/J2/2 | SGBM28 | Jan 22 2016 8:30AM | Jan 27 2016 9:06PM | 40.875 | 34.025 | 11, 12, 15, 16, 18, 18.5, 20.5, 21.8, 22.04 | 19.448 | 6.85 | 14.577 |  | 11.68 | 11.68 | 26T25 (1-12m), 26T20 (12-18m) | T10-150 | 15.577 | 37.0988 | 44 | -100 | 30 TREMIE 2 (JKR) | P201045580, P201045583, P201045587, P201045590 | 12, 10, 10, 12

## 2000
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
18.1a/J2/1 | SGBM30 | Feb 16 2016 1:00PM | Feb 18 2016 5:35PM | 40.644 | 33.725 | 12, 14, 17, 23, 26 | 14.779 | 6.919 | 18.946 |  | 17.198 | 17.198 | 34T25 | T10-150 | 12 | 59.5283 | 66 | -100 | 30 TREMIE 2 (JKR) | P201046532, P201046534, P201046536, P201046538, P201046544, P201046545, P201046548 | 8, 9, 9, 12, 12, 8, 8
18.1a/J2/2 | SGBM30 | Feb 20 2016 5:30PM | Feb 23 2016 5:00PM | 40.49 | 33.725 | 13, 16, 24 | 14.616 | 6.765 | 19.109 |  | 14.732 | 14.732 | 34T25 | T10-150 | 12 | 60.0405 | 69 | -100 | 30 TREMIE 2 (JKR) | P201046828, P201046829, P201046831, P201046834, P201046839, P201046841 | 12, 9, 12, 12, 12, 12
19.1/J2/1 | SGBM30 | Feb 25 2016 2:30PM | Feb 29 2016 11:05AM | 40.57 | 33.725 | 11, 13, 16, 20.6 | 20.375 | 6.845 | 13.35 |  | 11.635 | 11.635 | 34T25 | T10-150 | 12 | 41.9457 | 50 | -100 | 30 TREMIE 2 (JKR) | P201047100, P201047101, P201047102, P201047104, P201047103 | 12, 8, 10, 9, 11
19.1/J2/2 | SGBM30 | Mar 1 2016 8:00AM | Mar 3 2016 4:35PM | 40.77 | 33.725 | 11, 15.5, 18.5, 20.4, 20.697 | 20.603 | 7.045 | 13.122 |  | 12.017 | 12.017 | 34T25 | T10-150 | 14.2 | 41.2293 | 48 | -100 | 30 TREMIE 2 (JKR) | P201047350, P201047352, P201047354, P201047356 | 12, 12, 12, 12
20.1/J2/1 | SGBM30 | Feb 23 2016 2:00PM | Feb 26 2016 10:40AM | 40.825 | 33.725 | 13, 15, 17.5, 18.2 | 23.258 | 7.1 | 10.467 |  | 7.277 | 7.277 | 34T25 | T10-150 | 11.467 | 32.8873 | 38 | -100 | 30 TREMIE 2 (JKR) | P201046988, P201046989, P201046990, P201046992 | 12, 9, 9, 8
20.1/J2/2 | SGBM30 | Feb 18 2016 3:00PM | Feb 22 2016 2:15PM | 40.825 | 33.725 | 11, 12, 14, 17, 18.2 | 23.237 | 7.1 | 10.488 |  | 8.24 | 8.24 | 34T25 | T10-150 | 11.5 | 32.9533 | 40.5 | -100 | 30 TREMIE 2 (JKR) | P201046723, Pending, P201046727, P201046732 | 9, 10, 12, 9.5

## 2200
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
20.1/G2/1 | SGBM30 | Jan 7 2016 2:00PM | Jan 11 2016 2:20PM | 40.945 | 33.325 | 11.21, 13, 15, 16.5, 19, 21, 22 | 18.37 | 7.62 | 14.955 |  | 17.25 | 12.04 | 40T25 | T10-150 | 12 | 56.8562 | 68 | -100 | 30 TREMIE 2 (JKR) | P100055085, P100055088, P100055092, P100055093, P100055094, P100055099, P100055102 | 12, 10, 9, 10, 10, 10, 7
20.1/G2/2 | SGBM30 | Dec 26 2015 8:15AM | Dec 29 2015 3:00PM | 41.08 | 33.325 | 12, 16, 18, 23.1 | 18.364 | 7.755 | 14.961 |  | 12.5 | 12.5 | 40T25 | T10-150 | 12 | 56.879 | 70 | -100 | 30 TREMIE 2 (JKR) | P100054427, P100054428, P100054429, P100054431, P100054433, P100054435, P100054436 | 10, 10, 10, 9, 10, 10, 11
20.1/G2/3 | SGBM30 | Dec 18 2015 9:00AM | Dec 22 2015 11:10AM | 40.995 | 33.325 | 13, 14, 18, 20 | 18.368 | 7.67 | 14.957 |  | 10.735 | 10.735 | 40T25 | T10-150 | 12 | 56.8638 | 68 | -100 | 30 TREMIE 2 (JKR) | P100054143, P100054144, P100054146, P100054148, P100054149, P100054150, P100054151 | 10, 9, 12, 10, 9, 9, 9
20.1/H2/1 | SGBM30 | Jan 20 2016 11:00AM | Jan 26 2016 1:30PM | 40.92 | 33.325 | 11, 13.5, 17, 19, 23.4 | 18.171 | 7.595 | 15.154 |  | 14.13 | 14.13 | 40T25 | T10-150 | 12 | 57.6128 | 65 | -100 | 30 TREMIE 2 (JKR) | P201045489, P201045490, P201045491, P201045492, P201045496, P201045499, P201045500 | 9, 9, 9, 9, 12, 9, 8
20.1/H2/2 | SGBM30 | Jan 13 2016 2:30PM | Jan 16 2016 3:17PM | 40.945 | 33.325 | 11.108, 14, 16, 19.5, 22.5, 23.4 | 18.349 | 7.62 | 14.976 |  | 17.55 | 12.443 | 40T25 | T10-150 | 12 | 56.9361 | 65 | -100 | 30 TREMIE 2 (JKR) | P201045243, P201045244, P201045246, P201045247, P201045250, P201045253 | 12, 12, 10, 12, 10, 9
20.1/H2/3 | SGBM30 | Dec 31 2015 1:00PM | Jan 6 2016 9:40PM | 41 | 33.325 | 14, 15.5, 17.5, 18.8, 21, 22.5, 23.2 | 18.442 | 7.675 | 14.883 |  | 10.505 | 10.505 | 40T25 | T10-150 | 12 | 56.5825 | 68 | -100 | 30 TREMIE 2 (JKR) | P100054871, P100054873, P100054875, P100054881, P100054884, P100054890, P100054892 | 9, 12, 10, 9, 10, 9, 9