## 750
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
BP P9 |  |  |  | 0 | 68.35 |  | 0 | 0 | 68.35 |  | 0 | 0 | 12T16 | T10 - 150 |  | 30.2 | 0 | 0 | G35T2
BP P12 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P16 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P18 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P21 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P22 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P24 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P27 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P28 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P29 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P30 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2
BP P32 |  |  |  | 0 | 63.625 |  | 0 | 0 | 63.625 |  | 0 | 0 | 12T16 | T10 - 150 |  | 28.1123 | 0 | 0 | G35T2

## 1200
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  | Pile Details |  |  |  |  | Steel Cage |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Helical/Spiral | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
C1 |  | Jul 30 2016 11:00AM | Aug 8 2016 6:50PM | 71.78 | 70.793 | 12.1, 12.6, 13.3, 13.6, 14.9, 15, 15.5, 15.6 | 55.461 | 0.987 | 15.332 |  | 3.8 | 3.8 | 24T32 | 2T16 - 100 , T12 -175 | 12+5.5 | 17.3423 | 20 | 2.65 | G35T2 | c15002317, c150023179 | 10, 10
C2 | SGBM05 | Aug 11 2016 2:10PM | Aug 17 2016 5:05PM | 71.641 | 71.15 | 15, 15.6, 16.1 | 56.87 | 0.491 | 14.28 |  | 2.2 | 2.2 | 24T32 | 2T16 - 100 , T12 -175 | 12+6.4 | 16.1524 | 21 | 3.83 | G35T2 | C150023655, C150023663 | 12, 9
C3 |  | Aug 24 2016 7:45AM | Aug 27 2016 11:35AM | 71.78 | 71.507 | 14.7, 15.3, 17.1, 18.6, 18.8 | 53.95 | 0.273 | 17.557 |  | 3.9 | 2.1 | 24T32 | 2T16 - 100 , T12 -175 | 19 | 19.8591 | 26 | 30.9 | G35T2 | C150024163, C150024164, C150024165 | 9, 9, 8
C4 |  | Sep 1 2016 11:30AM | Sep 7 2016 1:20PM | 71.93 | 71.863 | 14.2, 15, 16.1 | 56.67 | -71.863 | 15.193 |  | 2.2 | 2.2 | 24T32 | 2T16 - 100 , T12 -175 | 12+5.6 | 17.1851 | 22 | 4.81 | G35T2 | C150024629, C150024634 | 12, 10
C5 |  | Aug 18 2016 10:53AM | Aug 23 2016 5:05PM | 71.584 | 72.22 | 15.8, 17.8, 18.2, 18.5, 19.2, 19.6, 19.8 | 52.952 | -0.636 | 19.268 |  | 3.6 | 2 | 24T32 | 2T16 - 100 , T12 -175 | 12+9.3 | 21.7944 | 24 | 10.1 | G35T2 | C150023956, C150023962 , C150023965 | 8, 8, 8
C6 |  | Jul 26 2016 7:30AM | Aug 11 2016 11:20AM | 71.83 | 72.577 | 12.7, 13, 13.9, 16.8, 18 | 54.27 | -0.747 | 18.307 |  | 3.9 | 2 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 | 8+12 | 20.7074 | 24 | 3.29 | G35T2 | 1, 2, 3 | 9, 8, 7
C7 |  | Aug 27 2016 4:45PM | Sep 3 2016 12:30PM | 71.62 | 72.934 | 15.7, 16.2, 16.7, 17, 17.5, 17.8 | 55.134 | -72.934 | 17.8 |  | 2.2 | 2 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 | 12+7.9 | 20.1339 | 17 | -15.6 | G35T2 | C150024476, C150024477, C150024480 | 9, 8, 9
C8 |  | Sep 5 2016 4:30PM |  | 71.58 | 73.29 | 13.6, 14.1, 14.7, 15.35 | 57.346 | -1.71 | 15.944 |  | 2.4 | 2.4 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 18.0346 | 0 | -100 | G35T2
C9 |  |  |  | 0 | 73.647 |  | 0 | 0 | 73.647 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.3036 | 0 | 0 | G35T2
C10 |  |  |  | 0 | 74.004 |  | 0 | 0 | 74.004 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.7074 | 0 | 0 | G35T2
C11 | SGBM05 | Aug 9 2016 7:30AM | Sep 5 2016 1:35PM | 71.86 | 74.175 | 16.601, 16.9, 17, 17.3, 17.4, 17.6, 18, 18.3 | 53.86 | -2.315 | 20.315 |  | 1.401 | 2 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 | 3.6+12+4.6 | 22.9787 | 18 | -21.7 | G35T2 | C150024519, C150024521, C150024522 | 9, 9, 8
C12 | SGBM05 | Sep 8 2016 9:00AM |  | 0 | 74.175 |  | 0 | 0 | 74.175 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.9008 | 0 | -83.9 | G35T2
C13 |  |  |  | 0 | 74.175 |  | 0 | 0 | 74.175 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.9008 | 0 | 0 | G35T2
C14 |  |  |  | 0 | 74.175 |  | 0 | 0 | 74.175 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.9008 | 0 | 0 | G35T2
C15 |  |  |  | 0 | 74.175 |  | 0 | 0 | 74.175 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.9008 | 0 | 0 | G35T2
C16 |  |  |  | 0 | 74.175 |  | 0 | 0 | 74.175 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.9008 | 0 | 0 | G35T2
C17 |  |  |  | 0 | 73.675 |  | 0 | 0 | 73.675 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.3353 | 0 | -83.33 | G35T2
C18 |  |  |  | 0 | 73.675 |  | 0 | 0 | 73.675 |  | 0 | 0 | 15X2T32 , 15T20 | 2T16 - 100 , T12 -175 |  | 83.3353 | 0 | 0 | G35T2
C19 |  |  |  | 0 | 73.675 |  | 0 | 0 | 73.675 |  | 0 | 0 | 24T32 | 2T16 - 100 , T12 -175 |  | 83.3353 | 0 | 0 | G35T2
C20 |  |  |  | 0 | 73.675 |  | 0 | 0 | 73.675 |  | 0 | 0 | 24T32 | 2T16 - 100 , T12 -175 |  | 83.3353 | 0 | 0 | G35T2
C21 |  |  |  | 0 | 73.175 |  | 0 | 0 | 73.175 |  | 0 | 0 | 24T32 | 2T16 - 100 , T12 -175 |  | 82.7697 | 0 | 0 | G35T2
C22 |  |  |  | 0 | 73.175 |  | 0 | 0 | 73.175 |  | 0 | 0 | 24T32 | 2T16 - 100 , T12 -175 |  | 82.7697 | 0 | 0 | G35T2
C23 |  |  |  | 0 | 73.175 |  | 0 | 0 | 73.175 |  | 0 | 0 | 24T32 | 2T16 - 100 , T12 -175 |  | 82.7697 | 0 | 0 | G35T2
C24 |  |  |  | 0 | 73.175 |  | 0 | 0 | 73.175 |  | 0 | 0 | 24T32 | 2T16 - 100 , T12 -175 |  | 82.7697 | 0 | 0 | G35T2