## 880
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
CB393 | SGBM12 | Jan 19 2016 6:30PM | Jan 21 2016 11:16AM | 39.360 | 37.775 | 4.72 | 9.48 | 26.521 | 39.360 | 11.254 |  | 0.0 | 0.0 | 9.5 | 10T25 | 1281.609 | T10-150 | 524.5474 | 12.254 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055426 | 8.5
CB394 | SGBM12 | Jan 15 2016 5:00PM | Jan 18 2016 11:26AM | 39.690 | 37.775 | 4.80 | 9.00 | 26.625 | 39.690 | 11.150 |  | 0.0 | 0.0 | 9.0 | 10T25 | 1277.601 | T10-150 | 523.5472 | 12.15 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045276 | 8.5
CB395 | SGBM12 | Jan 23 2016 9:00AM | Jan 26 2016 4:05PM | 39.675 | 37.775 | 4.64 | 9.92 | 26.598 | 39.675 | 11.177 |  | 0.0 | 0.0 | 9.9 | 10T25 | 1278.642 | T10-150 | 523.8068 | 12.177 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045489 | 8.5
CB396 | SGBM12 | Jan 29 2016 8:15AM | Jan 30 2016 5:05PM | 39.850 | 37.775 | 4.64 | 9.89 | 26.645 | 39.850 | 11.130 |  | 0.0 | 0.0 | 9.9 | 10T25 | 1276.830 | T10-150 | 523.3549 | 12.13 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045745 | 9
CB397 | SGBM12 | Jan 12 2016 4:10PM | Jan 14 2016 2:40PM | 39.840 | 37.775 | 4.21 | 9.94 | 26.655 | 39.840 | 11.120 |  | 0.0 | 0.0 | 9.9 | 10T25 | 1276.445 | T10-150 | 523.2588 | 12.12 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055243 | 8.5
CB398 | SGBM12 | Jan 21 2016 2:12PM | Jan 22 2016 7:35PM | 39.650 | 37.775 | 4.65 | 9.90 | 26.585 | 39.650 | 11.190 |  | 0.0 | 0.0 | 9.9 | 10T25 | 1279.143 | T10-150 | 523.9319 | 12.19 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045417 | 8.5
CB399 | SGBM12 | Jan 27 2016 8:15AM | Jan 28 2016 8:30PM | 39.800 | 37.775 | 4.60 | 10.15 | 26.456 | 39.800 | 11.319 |  | 0.0 | 0.0 | 10.2 | 10T25 | 1284.114 | T10-150 | 525.1730 | 12.319 | 6.9 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045602 | 8.5
CB400 | SGBM12 | Feb 12 2016 8:00AM | Feb 15 2016 10:00AM | 39.920 | 37.775 | 4.66 | 9.93 | 26.602 | 39.920 | 11.173 |  | 0.0 | 0.0 | 9.9 | 10T25 | 1278.487 | T10-150 | 523.7683 | 12.137 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046268 | 8.5
CB401 | SGBM12 | Feb 2 2016 8:30AM | Feb 3 2016 8:55PM | 39.880 | 37.775 | 4.61 | 10.00 | 26.507 | 39.880 | 11.268 |  | 0.0 | 0.0 | 10.0 | 10T25 | 1282.149 | T10-150 | 524.6819 | 12.268 | 6.9 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046009 | 8.5
CB402 | SGBM12 | Feb 25 2016 2:30PM | Feb 27 2016 2:30PM | 39.660 | 37.775 | 4.68 | 9.32 | 26.990 | 39.660 | 10.785 |  | 0.0 | 0.0 | 9.8 | 10T25 | 1263.534 | T10-150 | 520.0447 | 12.218 | 6.6 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047067 | 10
CB403 | SGBM12 | Mar 2 2016 2:00PM | Mar 4 2016 4:56PM | 39.600 | 37.775 | 4.61 | 9.86 | 26.655 | 39.600 | 11.120 |  | 0.0 | 0.0 | 9.9 | 10T25 | 1276.445 | T10-150 | 523.2588 | 12.12 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201047403 | 8.5
CB404 | SGBM12 | Mar 9 2016 8:00AM | Mar 11 2016 12:19PM | 39.570 | 37.775 | 4.74 | 9.31 | 26.626 | 39.570 | 11.149 |  | 0.0 | 0.0 | 9.3 | 10T25 | 1277.562 | T10-150 | 523.5375 | 12.149 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201047763 | 8.5
CB405 | SGBM12 | Mar 15 2016 8:00AM | Mar 16 2016 11:30AM | 39.640 | 37.775 | 4.54 | 9.76 | 26.698 | 39.640 | 11.077 |  | 0.0 | 0.0 | 9.8 | 10T25 | 1274.788 | T10-150 | 522.8458 | 12.077 | 6.7 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P101055644 | 8.5
CB406 | SGBM12 | Mar 12 2016 8:00AM | Mar 14 2016 1:55PM | 39.550 | 37.775 | 4.09 | 10.36 | 26.560 | 39.550 | 11.215 |  | 0.0 | 0.0 | 10.4 | 10T25 | 1280.106 | T10-150 | 524.1722 | 12.215 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P101055611 | 8.5
CB407 | SGBM12 | Mar 5 2016 8:30AM | Mar 8 2016 5:10PM | 39.600 | 37.775 | 4.30 | 10.39 | 26.532 | 39.600 | 11.243 |  | 0.0 | 0.0 | 10.4 | 10T25 | 1281.185 | T10-150 | 524.4414 | 12.240 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201047606 | 8.5
CB408 | SGBM12 | Feb 29 2016 8:00AM | Mar 2 2016 12:45PM | 39.500 | 37.775 | 4.47 | 10.13 | 26.575 | 39.500 | 11.200 |  | 0.0 | 0.0 | 10.1 | 10T25 | 1279.528 | T10-150 | 524.0280 | 12.2 | 6.8 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047244 | 10
CB409 | SGBM12 | Jan 18 2016 4:10PM | Jan 19 2016 6:01PM | 39.836 | 38.425 | 4.20 | 10.12 | 26.554 | 39.836 | 11.871 |  | 0.0 | 0.0 | 10.1 | 10T25 | 1305.388 | T10-150 | 530.4989 | 12.221 | 7.2 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | Pending | 8.5
CB410 | SGBM12 | Dec 18 2015 3:30PM | Dec 21 2015 11:35AM | 39.770 | 37.775 | 4.20 | 9.82 | 26.672 | 39.770 | 11.103 |  | 8.0 | 0.0 | 9.8 | 10T25 | 1275.790 | T10-150 | 523.0956 | 12.103 | 6.8 | 8.5 | 25.9 | 30 TREMIE 2 (JKR) | P100054073 | 8.5
CB411 | SGBM10 | Dec 10 2015 5:10PM | Dec 15 2015 4:08PM | 39.715 | 37.775 | 3.45 | 10.15 | 26.625 | 39.715 | 11.150 |  | 8.6 | 0.0 | 10.1 | 10T25 | 1277.601 | T10-150 | 523.5472 | 12.15 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053838 | 8
CB412 | SGBM12 | Dec 28 2015 8:00AM | Dec 29 2015 6:55PM | 39.770 | 37.775 | 4.20 | 10.03 | 26.652 | 39.770 | 11.123 |  | 8.2 | 0.0 | 10.0 | 10T25 | 1276.560 | T10-150 | 523.2876 | 12.123 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054453 | 8
CB413 | SGBM12 | Dec 31 2015 10:35AM | Jan 2 2016 6:26PM | 39.715 | 37.775 | 4.17 | 9.83 | 26.663 | 39.715 | 11.112 |  | 0.0 | 0.0 | 9.8 | 10T25 | 1276.136 | T10-150 | 523.1820 | 12.112 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054671 | 8.5
CB414 | SGBM12 | Jan 6 2016 9:00AM | Jan 7 2016 2:40PM | 39.734 | 37.775 | 4.20 | 9.57 | 26.603 | 39.734 | 11.172 |  | 0.0 | 0.0 | 9.6 | 10T25 | 1278.449 | T10-150 | 523.7586 | 12.172 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054918 | 8.5
CB415 | SGBM12 | Jan 14 2016 3:30PM | Jan 15 2016 3:44PM | 39.674 | 37.775 | 4.80 | 8.55 | 26.577 | 39.674 | 11.198 |  | 0.0 | 0.0 | 8.6 | 10T25 | 1279.451 | T10-150 | 524.0086 | 12.189 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045210 | 8.5
CB416 | SGBM12 | Dec 23 2015 9:30AM | Dec 26 2015 10:45PM | 39.974 | 37.775 | 4.30 | 9.17 | 26.630 | 39.974 | 11.145 |  | 8.5 | 0.0 | 9.2 | 10T25 | 1277.408 | T10-150 | 523.4992 | 12.145 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054337 | 8
CB417 | SGBM10 | Dec 15 2015 8:00AM | Dec 17 2015 3:35PM | 39.745 | 37.775 | 4.10 | 10.50 | 26.556 | 39.745 | 11.219 |  | 8.6 | 0.0 | 10.5 | 10T25 | 1280.260 | T10-150 | 524.2107 | 12.219 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053930 | 8
CB418 | SGBM10 | Dec 9 2015 10:30AM | Dec 10 2015 7:30PM | 39.768 | 37.775 | 4.00 | 10.40 | 26.580 | 39.768 | 11.195 |  | 8.4 | 0.0 | 10.2 | 10T25 | 1279.335 | T10-150 | 523.9798 | 12.195 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053624 | 8
CB419 | SGBM12 | Jan 9 2016 6:10PM | Jan 12 2016 4:58PM | 39.830 | 37.775 | 4.57 | 9.78 | 26.656 | 39.830 | 11.119 |  | 0.0 | 0.0 | 9.8 | 10T25 | 1276.406 | T10-150 | 523.2493 | 12.119 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055150 | 8.5
CB420 | SGBM12 | Jan 4 2016 10:00AM | Jan 5 2016 2:56PM | 39.885 | 37.775 | 4.19 | 10.44 | 26.565 | 39.885 | 11.210 |  | 0.0 | 0.0 | 10.4 | 10T25 | 1279.913 | T10-150 | 524.1240 | 12.21 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054786 | 8.5
CB421 | SGBM12 | Dec 29 2015 11:00AM | Dec 31 2015 4:16PM | 40.006 | 37.775 | 4.70 | 9.85 | 26.601 | 40.006 | 11.174 |  | 8.5 | 0.0 | 9.8 | 10T25 | 1278.526 | T10-150 | 523.7780 | 12.175 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054604 | 8
CB422 | SGBM12 | Dec 21 2015 11:50AM | Dec 23 2015 9:50AM | 40.651 | 37.775 | 4.25 | 10.15 | 26.603 | 40.651 | 11.172 |  | 8.4 | 0.0 | 10.2 | 10T25 | 1278.449 | T10-150 | 523.7586 | 12.172 | 6.8 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054204 | 8.5
CB423 | SGBM10 | Dec 9 2015 6:00PM | Dec 12 2015 6:00PM | 40.666 | 37.775 | 3.86 | 11.06 | 26.546 | 40.666 | 11.229 |  | 9.9 | 0.0 | 10.3 | 10T25 | 1280.646 | T10-150 | 524.3070 | 12.229 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053771 | 8
CB424 | SGBM32 | Oct 23 2015 10:55AM | Oct 26 2015 2:55PM | 40.670 | 37.775 | 4.11 | 10.60 | 26.519 | 2.895 | 11.256 |  | 7.7 | 0.0 | 10.6 | 10T25 | 1281.686 | T10-150 | 524.5665 | 12.6 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051088 | 9
CB425 | SGBM32 | Oct 6 2015 1:10PM | Dec 7 2015 9:20PM | 40.675 | 37.775 | 5.60 | 9.89 | 26.488 | 2.900 | 11.287 |  | 9.9 | 0.0 | 9.8 | 10T25 | 1282.881 | T10-150 | 524.8650 | 12.287 | 6.9 | 9.0 | 31.1 | 30 TREMIE 2 (JKR) | 1 | 9
CB426 | SGBM32 | Oct 15 2015 8:00AM | Oct 16 2015 6:00PM | 40.680 | 37.775 | 4.20 | 10.60 | 26.620 | 2.905 | 11.155 |  | 10.6 | 0.0 | 10.5 | 10T25 | 1277.794 | T10-150 | 523.5954 | 12.155 | 6.8 | 9.0 | 32.6 | 30 TREMIE 2 (JKR) | P100050567 | 9
CB427 | SGBM32 | Oct 19 2015 9:15AM | Oct 21 2015 8:20PM | 40.690 | 37.775 | 4.19 | 10.41 | 26.600 | 40.690 | 11.175 |  | 10.4 | 0.0 | 10.4 | 10T25 | 1278.564 | T10-150 | 523.7874 | 12.6 | 6.8 | 9.0 | 32.4 | 30 TREMIE 2 (JKR) | P100050814 | 9
CB428 | SGBM32 | Oct 28 2015 11:15AM | Oct 29 2015 6:55PM | 40.620 | 37.775 | 5.81 | 9.33 | 26.552 | 40.620 | 11.223 |  | 9.3 | 0.0 | 9.9 | 10T25 | 1280.414 | T10-150 | 524.2490 | 12.5 | 6.8 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051339 | 8
CB429 | SGBM32 | Oct 10 2015 2:30PM | Oct 12 2015 9:42PM | 40.694 | 37.775 | 7.10 | 8.40 | 26.454 | 2.919 | 11.321 |  | 8.4 | 0.0 | 8.6 | 10T25 | 1284.191 | T10-150 | 525.1921 | 12.325 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050336 | 9
CB430 | SGBM32 | Oct 3 2015 8:45AM | Oct 5 2015 2:30PM | 40.680 | 37.775 | 8.10 | 7.40 | 26.270 | 40.680 | 11.505 |  | 7.3 | 0.0 | 7.4 | 18T32 | 4507.293 | T12-200 | 572.0832 | 12.65 | 7.0 | 10.0 | 42.9 | 30 TREMIE 2 (JKR) | 1 | 10
CB431 |  | Oct 22 2015 8:00AM | Oct 23 2015 5:45PM | 40.640 | 37.775 | 9.00 | 6.63 | 26.123 | 40.640 | 11.652 |  | 6.6 | 0.0 | 7.2 | 18T32 | 4523.997 | T12-200 | 573.5923 | 13.2 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050909 | 9
CB432 | SGBM32 | Oct 26 2015 8:50AM | Oct 27 2015 5:05PM | 40.570 | 37.775 | 7.70 | 7.00 | 26.163 | 40.570 | 11.612 |  | 6.9 | 0.0 | 6.9 | 18T32 | 4519.451 | T12-200 | 573.1817 | 13.2 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051162 | 9
CB433 | SGBM32 | Oct 8 2015 9:00AM | Oct 10 2015 5:05PM | 40.651 | 37.775 | 10.50 | 5.48 | 26.046 | 2.876 | 11.729 |  | 5.4 | 0.0 | 5.4 | 18T32 | 4532.747 | T12-200 | 574.3838 | 13.029 | 7.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050234 | 10
CB434 | SGBM32 | Oct 13 2015 8:00AM | Oct 13 2015 9:00PM | 40.650 | 37.775 | 11.30 | 4.50 | 25.980 | 40.650 | 11.795 |  | 4.5 | 0.0 | 4.5 | 18T32 | 4540.246 | T12-200 | 575.0629 | 13.745 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050379 | 10
CB435 | SGBM32 | Oct 1 2015 5:00PM | Oct 2 2015 9:50PM | 40.660 | 37.775 | 12.60 | 2.85 | 26.105 | 40.660 | 11.670 |  | 2.8 | 0.0 | 2.8 | 18T32 | 4526.042 | T12-200 | 573.7772 | 12.97 | 7.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049787 | 10
CB436 | SGBM32 | Oct 5 2015 11:10AM | Oct 6 2015 7:15PM | 40.635 | 37.775 | 18.20 | 2.05 | 21.555 | 40.635 | 16.220 |  | 2.0 | 0.0 | 16.2 | 18T32 | 5043.077 | T12-200 | 621.3528 | 17.7 | 9.9 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049983 P100049987 | 7 7
CB437 | SGBM32 | Oct 27 2015 11:30AM | Oct 28 2015 8:35PM | 40.620 | 37.775 | 17.24 | 1.57 | 22.582 | 2.845 | 15.193 |  | 0.8 | 0.0 | 3.4 | 18T32 | 4926.375 | T12-200 | 610.5045 | 18.7 | 9.2 | 13.0 | -9.2 | 30 TREMIE 2 (JKR) | P100051265 P100051266 | 7 6
CB438 | SGBM32 | Nov 2 2015 5:50PM | Nov 3 2015 8:26PM | 40.640 | 37.775 | 4.80 | 17.70 | 16.504 | 40.640 | 21.271 |  | 5.3 | 0.0 | 19.6 | 18T32 | 5617.042 | T12-200 | 675.2187 | 22.571 | 12.9 | 19.0 | -280.9 | 30 TREMIE 2 (JKR) | P100051579 P100051580 | 10 9
CB439 | SGBM32 | Oct 16 2015 5:15PM | Oct 19 2015 7:05PM | 40.660 | 37.775 | 4.73 | 5.34 | 17.652 | 40.660 | 20.123 |  | 2.1 | 0.0 | 18.8 | 18T32 | 5486.590 | T12-200 | 662.9197 | 20.8 | 12.2 | 15.0 | 22.5 | 30 TREMIE 2 (JKR) | P100050685 P100050686 | 9 6
CB440 | SGBM32 | Sep 29 2015 9:00AM | Oct 2 2015 4:20PM | 40.660 | 37.775 | 5.30 | 19.80 | 16.540 | 40.660 | 21.235 |  | 19.8 | 0.0 | 2.1 | 18T32 | 5612.951 | T12-200 | 674.8327 | 22.532 | 12.9 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049752 P100049753 | 9 9
CB441 | SGBM32 | Oct 29 2015 6:20PM | Oct 31 2015 6:20PM | 40.640 | 37.775 | 6.00 | 7.50 | 16.477 | 40.640 | 21.298 |  | 7.3 | 0.0 | 18.4 | 18T32 | 5620.110 | T12-200 | 675.5081 | 22.7 | 13.0 | 18.0 | 10.5 | 30 TREMIE 2 (JKR) | P100051469 P100051473 | 9 9
CB442 | SGBM32 | Nov 4 2015 8:30AM | Nov 5 2015 5:50PM | 40.640 | 37.775 | 5.90 | 11.54 | 22.846 | 40.640 | 14.929 |  | 3.3 | 0.0 | 11.0 | 18T32 | 4896.375 | T12-200 | 607.7238 | 16.229 | 9.1 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051665 | 12
CB443 | SGBM32 | Nov 12 2015 8:00AM | Nov 20 2015 5:42PM | 40.610 | 37.775 | 6.20 | 8.22 | 26.492 | 40.610 | 11.283 |  | 8.2 | 0.0 | 8.2 | 10T25 | 1282.727 | T10-150 | 524.8264 | 12.3 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052485 | 9
CB444 | SGBM10 | Nov 26 2015 8:30AM | Nov 28 2015 3:13PM | 40.590 | 37.775 | 6.10 | 8.85 | 26.463 | 40.590 | 11.312 |  | 8.8 | 0.0 | 8.8 | 10T25 | 1283.844 | T10-150 | 525.1056 | 12.312 | 6.9 | 9.0 | 30.8 | 30 TREMIE 2 (JKR) | P100052883 | 9
CB445 | SGBM10 | Nov 21 2015 4:45PM | Nov 24 2015 3:40PM | 40.620 | 37.775 | 6.20 | 8.51 | 26.269 | 40.620 | 11.506 |  | 8.5 | 0.0 | 8.5 | 10T25 | 1291.321 | T10-150 | 526.9746 | 12.506 | 7.0 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052702 | 8
CB446 | SGBM10 | Nov 11 2015 5:30PM | Nov 17 2015 6:22PM | 40.670 | 37.775 | 4.20 | 10.39 | 26.350 | 40.670 | 11.425 |  | 10.3 | 0.0 | 10.3 | 10T25 | 1288.199 | T10-150 | 526.1939 | 13.4 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052291 | 9
CB447 | SGBM12 | Oct 1 2015 8:00AM | Oct 2 2015 7:40PM | 40.660 | 37.775 | 5.10 | 10.00 | 26.410 | 40.660 | 11.365 |  | 9.9 | 0.0 | 10.2 | 18T32 | 4491.384 | T12-200 | 570.6484 | 13.02 | 6.9 | 10.0 | -6.9 | 30 TREMIE 2 (JKR) | P100049774 | 10
CB448 | SGBM32 | Nov 4 2015 7:40PM | Nov 6 2015 8:35PM | 40.640 | 38.425 | 4.00 | 10.24 | 26.638 | 40.640 | 11.787 |  | 10.0 | 0.0 | 10.0 | 10T25 | 1302.151 | T10-150 | 529.6869 | 12.787 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | 1 | 9
CB449 | SGBM12 | Oct 12 2015 4:30PM | Oct 15 2015 4:45PM | 40.670 | 38.425 | 5.50 | 9.48 | 26.370 | 40.670 | 12.055 |  | 9.4 | 0.0 | 9.4 | 10T25 | 1312.480 | T10-150 | 532.2793 | 13.055 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050514 | 9
CB450 | SGBM12 | Oct 19 2015 8:55AM | Oct 22 2015 3:30PM | 40.660 | 38.425 | 4.24 | 10.56 | 26.350 | 40.660 | 12.075 |  | 10.6 | 0.0 | 0.0 | 10T25 | 1313.251 | T10-150 | 532.4730 | 13.1 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050844 | 9
CB451 | SGBM32 | Oct 31 2015 2:00PM | Nov 2 2015 7:00PM | 40.665 | 38.425 | 4.40 | 9.86 | 26.606 | 40.665 | 11.819 |  | 9.8 | 0.0 | 9.8 | 10T25 | 1303.384 | T10-150 | 529.9964 | 13.1 | 7.2 | 9.0 | -7.2 | 30 TREMIE 2 (JKR) | P100051553 | 9
CB452 | SGBM12 | Oct 5 2015 12:10PM | Oct 6 2015 9:10PM | 40.660 | 38.425 | 4.80 | 9.76 | 26.675 | 2.235 | 11.750 |  | 9.7 | 0.0 | 9.7 | 10T25 | 1300.725 | T10-150 | 529.3295 | 12.75 | 7.1 | 10.0 | -7.1 | 30 TREMIE 2 (JKR) | P100049989 | 10
CB453 | SGBM12 | Sep 28 2015 9:35AM | Sep 30 2015 8:50PM | 40.680 | 38.425 | 4.90 | 10.10 | 26.600 | 40.680 | 11.825 |  | 10.0 | 0.0 | 10.3 | 10T25 | 1303.616 | T10-150 | 530.0543 | 13.05 | 7.2 | 12.0 | -7.2 | 30 TREMIE 2 (JKR) | P100049657 | 12
CB454 |  | Oct 7 2015 8:45AM | Oct 9 2015 3:20PM | 40.670 | 38.425 | 5.00 | 10.15 | 26.585 | 40.670 | 11.840 |  | 10.1 | 0.0 | 10.1 | 10T25 | 1304.194 | T10-150 | 530.1992 | 12.835 | 7.2 | 10.0 | -7.2 | 30 TREMIE 2 (JKR) | P100050170 | 10
CB455 | SGBM12 | Sep 23 2015 10:00AM | Sep 26 2015 9:06PM | 40.680 | 38.425 | 4.20 | 10.40 | 26.700 | 40.680 | 11.725 |  | 10.3 | 0.0 | 9.5 | 10T25 | 1299.762 | T10-150 | 529.0881 | 12.725 | 7.1 | 10.0 | 17.0 | 30 TREMIE 2 (JKR) | P100049420 | 10
CB456 | SGBM12 | Oct 22 2015 2:00PM | Oct 28 2015 4:15PM | 40.620 | 38.425 | 4.20 | 10.33 | 26.586 | 40.620 | 11.839 |  | 10.3 | 0.0 | 0.0 | 10T25 | 1304.155 | T10-150 | 530.1895 | 13.1 | 7.2 | 9.0 | -7.2 | 30 TREMIE 2 (JKR) | P100051246 | 9
CB457 | SGBM12 | Oct 15 2015 3:50PM | Oct 17 2015 7:25PM | 40.630 | 38.425 | 4.28 | 10.35 | 26.613 | 40.630 | 11.812 |  | 10.3 | 0.0 | 0.0 | 10T25 | 1303.114 | T10-150 | 529.9287 | 12.812 | 7.2 | 9.0 | -7.2 | 30 TREMIE 2 (JKR) | P100050618 | 9
CB458 | SGBM12 | Sep 28 2015 8:00AM | Sep 29 2015 6:58PM | 40.690 | 38.425 | 4.41 | 9.97 | 26.599 | 2.265 | 11.826 |  | 10.0 | 0.0 | 10.0 | 10T25 | 1303.654 | T10-150 | 530.0638 | 12.826 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100049541 | 10
CB459 | SGBM12 | Oct 3 2015 9:15AM | Oct 5 2015 2:00PM | 40.690 | 38.425 | 5.00 | 10.10 | 26.520 | 40.690 | 11.905 |  | 10.1 | 0.0 | 10.1 | 10T25 | 1306.699 | T10-150 | 530.8278 | 12.947 | 7.2 | 10.0 | -7.2 | 30 TREMIE 2 (JKR) | 1 | 10
CB460 | SGBM12 | Sep 22 2015 3:30PM | Sep 25 2015 8:57PM | 40.685 | 38.425 | 5.40 | 9.47 | 26.713 | 40.685 | 11.712 |  | 9.4 | 0.0 | 9.4 | 10T25 | 1299.260 | T10-150 | 528.9625 | 12.712 | 7.1 | 13.0 | 17.0 | 30 TREMIE 2 (JKR) | P100049356 P100049358 | 6.5 6.5
CB461 | SGBM12 | Oct 7 2015 6:00PM | Oct 12 2015 9:00PM | 40.670 | 38.425 | 4.70 | 9.77 | 26.580 | 40.670 | 11.845 |  | 9.7 | 0.0 | 9.7 | 10T25 | 1304.386 | T10-150 | 530.2475 | 12.852 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050331 | 10
CB462 | SGBM12 | Oct 16 2015 5:30PM | Oct 20 2015 5:40PM | 40.680 | 38.425 | 5.70 | 9.16 | 26.560 | 40.680 | 11.865 |  | 9.2 | 0.0 | 0.0 | 10T25 | 1305.157 | T10-150 | 530.4409 | 13 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100050734 | 9
CB463 | SGBM12 | Oct 28 2015 10:35AM | Oct 29 2015 8:00PM | 40.730 | 38.425 | 5.64 | 9.53 | 26.485 | 40.730 | 11.940 |  | 9.5 | 0.0 | 0.0 | 10T25 | 1308.048 | T10-150 | 531.1663 | 13.1 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051345 | 9
CB464 |  | Nov 2 2015 4:15PM | Nov 4 2015 2:23PM | 40.680 | 38.425 | 6.20 | 8.61 | 26.841 | 40.680 | 11.584 |  | 8.6 | 0.0 | 0.0 | 10T25 | 1294.327 | T10-150 | 527.7267 | 12.887 | 7.0 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051596 | 9
CB465 | SGBM32 | Nov 12 2015 9:35AM | Nov 19 2015 6:45PM | 40.501 | 38.425 | 5.40 | 8.81 | 26.680 | 40.501 | 11.745 |  | 8.8 | 0.0 | 8.8 | 10T25 | 1300.532 | T10-150 | 529.2810 | 12.8 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052433 | 9
CB466 | SGBM10 | Nov 24 2015 8:30AM | Nov 25 2015 2:52PM | 40.500 | 38.425 | 6.40 | 8.75 | 26.577 | 40.500 | 11.848 |  | 8.7 | 0.0 | 8.7 | 10T25 | 1304.502 | T10-150 | 530.2767 | 12.845 | 7.2 | 10.0 | -7.2 | 30 TREMIE 2 (JKR) | P100052762 | 10
CB467 | SGBM10 | Nov 28 2015 3:45PM | Nov 30 2015 11:49PM | 40.450 | 38.425 | 7.20 | 7.43 | 26.695 | 40.450 | 11.730 |  | 5.4 | 0.0 | 7.4 | 10T25 | 1299.954 | T10-150 | 529.1362 | 12.73 | 7.1 | 10.0 | -7.1 | 30 TREMIE 2 (JKR) | P100053019 | 10
CB468 | SGBM10 | Dec 4 2015 5:30PM | Dec 5 2015 12:15AM | 40.440 | 38.425 | 7.50 | 6.95 | 26.484 | 40.440 | 11.941 |  | 6.8 | 0.0 | 6.8 | 10T25 | 1308.086 | T10-150 | 531.1761 | 12.941 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053412 | 9
CB469 | SGBM10 | Nov 25 2015 8:30AM | Nov 27 2015 2:09PM | 40.447 | 38.425 | 9.00 | 5.80 | 26.640 | 40.447 | 11.785 |  | 5.8 | 0.0 | 5.8 | 10T25 | 1302.074 | T10-150 | 529.6676 | 12.785 | 7.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052833 | 10
CB471 | SGBM12 | Oct 31 2015 2:50PM | Nov 2 2015 5:05PM | 40.430 | 38.425 | 7.00 | 7.22 | 26.645 | 40.430 | 11.780 |  | 7.1 | 0.0 | 7.1 | 10T25 | 1301.881 | T10-150 | 529.6194 | 13.1 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051545 | 9
CB472 | SGBM10 | Nov 19 2015 6:30PM | Nov 21 2015 11:20PM | 40.510 | 38.425 | 5.90 | 8.33 | 26.672 | 40.510 | 11.753 |  | 8.2 | 0.0 | 8.2 | 10T25 | 1300.841 | T10-150 | 529.3585 | 12.753 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | 1 | 9
CB474 | SGBM32 | Nov 7 2015 10:15AM | Nov 9 2015 6:00PM | 40.530 | 38.425 | 6.00 | 8.11 | 26.655 | 40.530 | 11.770 |  | 8.1 | 0.0 | 7.8 | 10T25 | 1301.496 | T10-150 | 529.5228 | 12.77 | 7.2 | 9.0 | 25.7 | 30 TREMIE 2 (JKR) | P100051902 | 9
CB475 | SGBM12 | Oct 30 2015 8:00AM | Oct 31 2015 4:30PM | 40.470 | 38.425 | 7.50 | 7.30 | 26.420 | 2.045 | 12.005 |  | 7.3 | 0.0 | 7.6 | 10T25 | 1310.553 | T10-150 | 531.7954 | 13.2 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051456 | 9
CB476 |  | Nov 3 2015 7:00PM | Nov 5 2015 5:50PM | 40.540 | 38.425 | 7.60 | 7.59 | 26.468 | 40.540 | 11.957 |  | 7.6 | 0.0 | 0.0 | 10T25 | 1308.703 | T10-150 | 531.3309 | 22.957 | 7.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051673 | 10
CB477 | SGBM10 | Nov 25 2015 8:00AM | Nov 28 2015 4:09PM | 40.527 | 38.425 | 7.00 | 7.62 | 26.483 | 40.527 | 11.942 |  | 7.4 | 0.0 | 7.4 | 10T25 | 1308.125 | T10-150 | 531.1856 | 12.935 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052885 | 9
CB478 | SGBM10 | Dec 1 2015 8:00AM | Dec 4 2015 7:30PM | 40.469 | 38.425 | 7.10 | 7.63 | 26.643 | 40.469 | 11.782 |  | 7.6 | 0.0 | 7.6 | 10T25 | 1301.958 | T10-150 | 529.6387 | 12.783 | 7.2 | 9.0 | 25.6 | 30 TREMIE 2 (JKR) | P100053290 | 9
CB479 | SGBM10 | Dec 22 2015 8:00AM | Dec 23 2015 5:53PM | 40.580 | 38.425 | 7.19 | 7.75 | 26.630 | 40.580 | 11.795 |  | 5.9 | 0.0 | 7.7 | 10T25 | 1302.459 | T10-150 | 529.7643 | 12.795 | 7.2 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054220 | 9
CB480 | SGBM10 | Dec 26 2015 6:10PM | Dec 29 2015 8:12PM | 40.597 | 38.425 | 7.55 | 7.69 | 26.672 | 40.597 | 11.753 |  | 6.2 | 0.0 | 7.7 | 10T25 | 1300.841 | T10-150 | 529.3585 | 12.753 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054464 | 9
CB481 | SGBM10 | Jan 6 2016 10:45AM | Jan 7 2016 6:34PM | 40.600 | 38.425 | 7.47 | 7.06 | 26.679 | 40.600 | 11.746 |  | 0.0 | 0.0 | 7.1 | 10T25 | 1300.571 | T10-150 | 529.2908 | 12.75 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054952 | 9
CB482 | SGBM10 | Jan 13 2016 8:15AM | Jan 15 2016 10:10AM | 40.452 | 38.425 | 7.84 | 6.80 | 26.600 | 40.452 | 11.825 |  | 0.0 | 0.0 | 6.8 | 10T25 | 1303.616 | T10-150 | 530.0543 | 12.825 | 7.2 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100055295 | 8.5
CB483 | SGBM10 | Dec 7 2015 8:00AM | Dec 8 2015 1:27PM | 40.690 | 38.425 | 9.10 | 5.44 | 26.613 | 40.690 | 11.812 |  | 5.3 | 0.0 | 5.3 | 10T25 | 1303.114 | T10-150 | 529.9287 | 12.812 | 7.2 | 9.0 | 25.3 | 30 TREMIE 2 (JKR) | P100053487 | 9
CB484 | SGBM12 | Dec 11 2015 11:15AM | Dec 15 2015 1:40PM | 40.690 | 38.425 | 9.70 | 4.20 | 27.312 | 40.690 | 11.113 |  | 2.4 | 0.0 | 4.2 | 12T25 | 1531.410 | T12-150 | 752.9891 | 12.113 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | 28066400 | 9
CB485 | SGBM10 | Dec 23 2015 4:15PM | Dec 26 2015 2:40PM | 40.610 | 38.425 | 10.30 | 3.55 | 27.410 | 40.610 | 11.015 |  | 2.9 | 0.0 | 3.5 | 12T25 | 1526.878 | T10-150 | 522.2504 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054286 | 9
CB486 | SGBM10 | Dec 30 2015 10:00AM | Dec 30 2015 5:55PM | 40.730 | 38.425 | 11.30 | 2.74 | 27.453 | 40.730 | 10.972 |  | 1.0 | 0.0 | 2.7 | 12T25 | 1524.889 | T10-150 | 521.8375 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054547 | 9
CB487 | SGBM10 | Nov 28 2015 8:30AM | Dec 2 2015 9:52PM | 40.700 | 38.425 | 12.00 | 9.15 | 20.230 | 40.700 | 18.195 |  | 9.0 | 0.0 | 9.9 | 12T25 | 1858.938 | T10-150 | 592.5949 | 20.423 | 11.1 | 15.0 | -27.7 | 30 TREMIE 2 (JKR) | P100053146 P100053148 | 8 7
CB488 | SGBM12 | Dec 9 2015 10:00AM | Dec 10 2015 7:56PM | 40.740 | 38.425 | 0.00 | 1.52 | 24.770 | 40.740 | 13.655 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1648.972 | T10-150 | 547.8499 | 14.655 | 8.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053626 | 10
CB489 | SGBM12 | Dec 15 2015 3:40PM | Dec 18 2015 6:25PM | 40.597 | 38.425 | 9.69 | 3.76 | 27.423 | 40.597 | 11.002 |  | 2.5 | 0.0 | 3.8 | 12T25 | 1526.276 | T12-150 | 751.4546 | 9 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054018 | 9
CB491 | SGBM10 | Jan 9 2016 5:00PM | Jan 11 2016 7:52PM | 40.635 | 38.425 | 9.78 | 4.34 | 27.451 | 40.635 | 10.974 |  | 0.0 | 0.0 | 4.3 | 12T25 | 1524.982 | T10-150 | 521.8569 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055107 | 9
CB492 | SGBM10 | Jan 4 2016 4:00PM | Jan 5 2016 4:13PM | 40.692 | 38.425 | 10.03 | 3.90 | 27.464 | 40.692 | 10.961 |  | 0.0 | 0.0 | 3.9 | 12T25 | 1524.380 | T10-150 | 521.7322 | 12 | 6.7 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054791 | 8.5
CB493 | SGBM10 | Dec 31 2015 4:40PM | Jan 2 2016 5:00PM | 40.627 | 38.425 | 11.01 | 3.10 | 27.407 | 40.627 | 11.018 |  | 2.1 | 0.0 | 3.1 | 12T25 | 1527.016 | T10-150 | 522.2791 | 12 | 6.7 | 8.5 | -100.0 | 30 TREMIE 2 (JKR) | P100054665 | 8.5
CB494 | SGBM10 | Jan 8 2016 8:00AM | Jan 8 2016 5:06PM | 40.600 | 38.425 | 11.44 | 2.30 | 27.487 | 40.600 | 10.938 |  | 0.0 | 0.0 | 2.3 | 12T25 | 1523.317 | T10-150 | 521.5115 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054969 | 9
CB495 | SGBM10 | Jan 12 2016 4:34PM | Jan 13 2016 7:45PM | 40.685 | 38 | 9.94 | 4.36 | 27.370 | 40.685 | 10.630 |  | 0.0 | 0.0 | 4.4 | 12T25 | 1509.072 | T10-150 | 518.5611 | 12 | 6.5 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055196 | 9
CB496 | SGBM10 | Dec 19 2015 8:00AM | Dec 21 2015 5:50PM | 40.625 | 38.425 | 12.19 | 2.12 | 27.339 | 40.625 | 11.086 |  | 1.3 | 0.0 | 2.1 | 12T25 | 1530.161 | T10-150 | 522.9322 | 12.086 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054097 | 9
CB497 | SGBM10 | Dec 8 2015 9:50AM | Dec 8 2015 6:39PM | 40.660 | 38.425 | 12.06 | 2.19 | 27.122 | 2.235 | 11.303 |  | 2.2 | 0.0 | 2.2 | 12T25 | 1540.197 | T10-150 | 525.0190 | 12.303 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053503 | 9
CB498 | SGBM10 | Jan 12 2016 8:00AM | Jan 12 2016 5:39PM | 40.770 | 38.425 | 11.65 | 2.64 | 27.260 | 40.770 | 11.165 |  | 0.0 | 0.0 | 2.6 | 12T25 | 1533.815 | T10-150 | 523.6913 | 12.162 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055151 | 9
CB499 | SGBM10 | Jan 2 2016 5:30PM | Jan 4 2016 4:42PM | 40.831 | 38.425 | 9.42 | 5.10 | 27.420 | 40.831 | 11.005 |  | 0.0 | 0.0 | 5.1 | 12T25 | 1526.415 | T10-150 | 522.1543 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054747 | 9
CB500 | SGBM10 | Dec 29 2015 3:00PM | Dec 30 2015 3:02PM | 40.760 | 38.425 | 10.93 | 3.34 | 27.440 | 40.760 | 10.985 |  | 2.7 | 0.0 | 3.3 | 12T25 | 1525.490 | T10-150 | 521.9623 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054533 | 9
CB501 | SGBM10 | Jan 8 2016 6:00PM | Jan 9 2016 6:11PM | 40.580 | 38.425 | 11.82 | 2.53 | 27.186 | 40.580 | 11.239 |  | 0.0 | 0.0 | 2.5 | 12T25 | 1537.237 | T10-150 | 524.4029 | 12.239 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055035 | 9
CB502 | SGBM10 | Jan 19 2016 4:45PM | Jan 20 2016 6:45PM | 40.738 | 38.425 | 9.48 | 4.97 | 27.324 | 40.738 | 11.101 |  | 0.0 | 0.0 | 5.0 | 12T25 | 1530.855 | T10-150 | 523.0762 | 12.102 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045375 | 9
CB503 | SGBM10 | Dec 21 2015 8:00AM | Dec 21 2015 7:08PM | 40.674 | 38.425 | 9.87 | 4.44 | 27.200 | 40.674 | 11.225 |  | 3.3 | 0.0 | 4.4 | 12T25 | 1536.590 | T10-150 | 524.2684 | 12.225 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054103 | 9
CB504 | SGBM12 | Dec 14 2015 6:20PM | Dec 15 2015 3:55PM | 40.680 | 38.425 | 12.30 | 2.20 | 27.292 | 40.680 | 11.133 |  | 1.5 | 0.0 | 2.2 | 12T25 | 1532.335 | T12-150 | 753.2654 | 12 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053837 | 9
CB505 | SGBM10 | Jan 5 2016 3:30PM | Jan 6 2016 3:14PM | 40.760 | 38.425 | 9.36 | 4.90 | 27.405 | 40.760 | 11.020 |  | 0.0 | 0.0 | 4.9 | 12T25 | 1527.109 | T10-150 | 522.2982 | 12 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054837 | 9
CB506 | SGBM10 | Dec 30 2015 5:30PM | Dec 31 2015 7:48PM | 40.700 | 38.425 | 9.33 | 5.01 | 27.383 | 40.700 | 11.042 |  | 3.3 | 0.0 | 5.0 | 12T25 | 1528.126 | T10-150 | 522.5097 | 12.042 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054622 | 9
CB507 | SGBM10 | Dec 26 2015 1:00PM | Dec 26 2015 10:00PM | 40.770 | 38 | 9.94 | 4.20 | 27.436 | 40.770 | 10.564 |  | 2.1 | 0.0 | 4.2 | 12T25 | 1506.020 | T10-150 | 517.9303 | 12 | 6.4 | 8.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054333 | 8
CB508 | SGBM10 | Dec 17 2015 3:25PM | Dec 18 2015 11:50AM | 40.705 | 38.425 | 9.49 | 4.76 | 27.355 | 40.705 | 11.070 |  | 4.3 | 0.0 | 4.8 | 12T25 | 1529.421 | T12-150 | 752.3944 | 12.07 | 6.7 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054065 | 9
CB509 | SGBM12 | Dec 9 2015 2:15PM | Dec 11 2015 6:40PM | 40.920 | 38.425 | 17.35 | 1.22 | 27.528 | 40.920 | 10.897 |  | 1.2 | 0.0 | 1.2 | 12T25 | 1521.420 | T10-150 | 521.1183 | 15.462 | 6.6 | 12.0 | 27.6 | 30 TREMIE 2 (JKR) | P100053692 | 12
CB510 | SGBM12 | Dec 3 2015 8:00AM | Dec 3 2015 7:10PM | 40.925 | 38.425 | 16.70 | 1.30 | 23.660 | 40.925 | 14.765 |  | 1.2 | 0.0 | 1.2 | 12T25 | 1700.308 | T10-150 | 558.7267 | 15.765 | 9.0 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053224 P100053224 | 6 6
CB511 | SGBM12 | Nov 6 2015 8:00AM | Nov 7 2015 5:10PM | 40.915 | 38.425 | 17.60 | 8.20 | 16.515 | 40.915 | 21.910 |  | 8.2 | 0.0 | 8.2 | 10T25 | 1692.291 | T10-150 | 629.5505 | 22.51 | 13.3 | 22.0 | -147.6 | 30 TREMIE 2 (JKR) | P100051815 P100051820 | 5 17
CB512 | SGBM12 | Nov 21 2015 8:00AM | Nov 21 2015 11:25PM | 40.000 | 38.425 | 17.00 | 1.15 | 23.451 | 40.000 | 14.974 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1709.974 | T10-150 | 560.7805 | 15.974 | 9.1 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052591 | 12
CB513 | SGBM12 | Nov 30 2015 8:00AM | Nov 30 2015 8:25PM | 41.005 | 38.425 | 16.30 | 1.15 | 24.385 | 41.005 | 14.040 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1666.778 | T10-150 | 551.6164 | 15.04 | 8.5 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052991 | 12
CB514 | SGBM12 | Dec 4 2015 9:34AM | Dec 4 2015 9:06PM | 41.005 | 38.425 | 16.46 | 1.17 | 24.177 | 41.005 | 14.248 |  | 0.6 | 0.0 | 1.2 | 12T25 | 1676.398 | T10-150 | 553.6543 | 15.248 | 8.7 | 13.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053307 P100053308 | 7 6
CB515 | SGBM12 | Dec 8 2015 8:00AM | Dec 8 2015 8:30PM | 41.188 | 38.425 | 16.60 | 1.25 | 24.021 | 41.188 | 14.404 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1683.612 | T10-150 | 555.1836 | 15.404 | 8.8 | 11.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053512 | 11
CB516 | SGBM10 | Nov 14 2015 8:00AM | Nov 16 2015 4:40PM | 40.950 | 38.425 | 15.00 | 1.86 | 25.208 | 40.950 | 13.217 |  | 0.3 | 0.0 | 1.1 | 12T25 | 1628.716 | T10-150 | 543.5733 | 12 | 8.0 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052243 | 10
CB517 | SGBM12 | Nov 25 2015 8:30AM | Nov 27 2015 10:00PM | 40.965 | 38.425 | 16.75 | 1.31 | 24.305 | 40.965 | 14.120 |  | 0.6 | 0.0 | 1.3 | 12T25 | 1670.478 | T10-150 | 552.4001 | 15.113 | 8.6 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052866 | 12
CB518 | SGBM12 | Dec 1 2015 4:30PM | Dec 2 2015 7:20PM | 41.101 | 38.425 | 14.60 | 1.16 | 26.104 | 41.101 | 12.321 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1587.278 | T10-150 | 534.8574 | 13.322 | 7.5 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053127 | 10
CB519 | SGBM12 | Dec 5 2015 2:59PM | Dec 7 2015 5:00PM | 41.250 | 38.425 | 14.00 | 1.27 | 26.499 | 41.250 | 11.926 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1569.010 | T10-150 | 531.0308 | 12.926 | 7.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053412 | 10
CB520 | SGBM12 | Nov 23 2015 8:00AM | Nov 23 2015 9:53PM | 41.060 | 38.425 | 14.30 | 1.28 | 26.338 | 41.060 | 12.087 |  | 1.2 | 0.0 | 1.2 | 12T25 | 1576.456 | T10-150 | 532.5892 | 13.087 | 7.4 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052668 | 10
CB521 | SGBM10 | Nov 12 2015 4:00PM | Nov 16 2015 6:05PM | 40.970 | 38.425 | 14.00 | 1.10 | 26.374 | 40.970 | 12.051 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1574.791 | T10-150 | 532.2408 | 13.051 | 7.3 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052252 P100052259 | 9 3
CB522 | SGBM12 | Dec 5 2015 8:00AM | Dec 5 2015 10:45PM | 41.220 | 38.425 | 14.30 | 1.26 | 26.422 | 41.220 | 12.003 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1572.571 | T10-150 | 531.7759 | 13.003 | 7.3 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053435 | 9
CB523 | SGBM12 | Nov 30 2015 5:00PM | Dec 1 2015 8:28PM | 41.143 | 38.425 | 15.70 | 1.08 | 24.870 | 41.143 | 13.555 |  | 1.0 | 0.0 | 1.0 | 12T25 | 1644.348 | T10-150 | 546.8726 | 14.565 | 8.2 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053073 | 12
CB524 |  | Nov 23 2015 10:00AM | Nov 23 2015 11:45PM | 41.142 | 38.425 | 14.10 | 1.25 | 26.375 | 41.142 | 12.050 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1574.744 | T10-150 | 532.2310 | 13.05 | 7.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052675 | 10
CB525 | SGBM12 | Nov 19 2015 2:00PM | Nov 20 2015 10:03PM | 41.140 | 38.425 | 13.70 | 1.11 | 26.942 | 41.140 | 11.483 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1548.522 | T10-150 | 526.7528 | 12.5 | 7.0 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052507 | 10
CB526 | SGBM12 | Dec 7 2015 8:00AM | Dec 7 2015 6:50PM | 41.310 | 38.425 | 14.00 | 1.31 | 27.095 | 41.310 | 11.330 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1541.446 | T12-150 | 755.9927 | 12.33 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053445 | 9
CB527 | SGBM12 | Dec 3 2015 8:00AM | Dec 4 2015 6:25PM | 41.140 | 38.425 | 13.52 | 1.17 | 27.211 | 41.140 | 11.214 |  | 0.7 | 0.0 | 1.2 | 12T25 | 1536.081 | T10-150 | 524.1625 | 12.214 | 6.8 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053286 | 9
CB528 | SGBM12 | Nov 28 2015 8:00AM | Nov 30 2015 12:59PM | 41.022 | 38.425 | 14.20 | 1.24 | 27.002 | 41.022 | 11.423 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1545.747 | T10-150 | 526.1744 | 12.423 | 6.9 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052961 | 9
CB529 | SGBM12 | Nov 24 2015 8:00AM | Nov 24 2015 7:35PM | 41.280 | 38.425 | 16.00 | 1.12 | 25.660 | 41.280 | 12.765 |  | 1.1 | 0.0 | 1.1 | 12T25 | 1607.812 | T10-150 | 539.1705 | 13.765 | 7.8 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052716 | 10
CB392 | SGBM12 | Jan 7 2016 1:15PM | Jan 9 2016 3:12PM | 39.753 | 37.775 | 4.11 | 10.34 | 26.680 | 1.978 | 11.095 |  | 10.3 | 0.0 | 10.3 | 10T25 | 1275.481 | T10-150 | 523.0186 | 12.095 | 6.7 | 8.5 | -6.7 | 30 TREMIE 2 (JKR) | P100055012 | 8.5

## 900
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
CB470 | SGBM32 | Nov 7 2015 8:15AM | Nov 11 2015 6:20PM | 40.440 | 38.425 | 7.67 | 6.60 | 26.591 | 40.440 | 11.834 |  | 6.6 | 0.0 | 0.0 | 10T25 | 1323.232 | T10-150 | 543.6844 | 12.834 | 7.5 | 9.0 | 19.5 | 30 TREMIE 2 (JKR) | P100051965 | 9
CB473 | SGBM32 | Nov 12 2015 11:15AM | Nov 13 2015 6:45PM | 40.535 | 38.425 | 6.40 | 7.63 | 26.625 | 40.535 | 11.800 |  | 7.6 | 0.0 | 7.6 | 10T25 | 1321.922 | T10-150 | 543.3475 | 12.8 | 7.5 | 9.0 | 19.9 | 30 TREMIE 2 (JKR) | P100052109 | 9
CB490 | SGBM10 | Dec 22 2015 9:30AM | Dec 22 2015 6:30PM | 40.705 | 38.425 | 9.75 | 4.36 | 27.337 | 2.280 | 11.088 |  | 3.1 | 0.0 | 4.4 | 12T25 | 1553.378 | T10-150 | 536.3109 | 12.088 | 7.1 | 9.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054176 | 9
CB530 | SGBM12 | Nov 19 2015 5:30PM | Nov 20 2015 8:15PM | 41.190 | 0 | 15.70 | 1.09 | 24.608 | 41.190 | -24.608 |  | 0.0 | 0.0 | 1.0 |  | 0 |  | 0 | 14.8 | -15.7 | 12.0 | -176.6 | 30 TREMIE 2 (JKR) | P100052498 | 12

## 1050
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
17.1/K2 | SGBM10 | Jan 15 2016 2:00PM | Jan 19 2016 4:45PM | 40.464 | 28.575 | 7.65 | 8.17 | 25.291 | 11.889 | 3.284 |  | 8.2 | 0.0 | 8.2 | 9T25 | 1024.416 | T10-150 | 556.4109 | 4.285 | 2.8 | 4.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045344 | 4
18.1/K2 | SGBM12 | Feb 15 2016 9:30AM | Feb 16 2016 5:50PM | 40.540 | 28.575 | 7.32 | 8.38 | 25.265 | 11.965 | 3.310 |  | 8.4 | 0.0 | 8.4 | 9T25 | 1025.318 | T10-150 | 556.5546 | 4.31 | 2.9 | 4.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046405 | 4.5
18.1a/K2 | SGBM10 | Jan 21 2016 8:00AM | Jan 22 2016 8:08PM | 40.610 | 35.525 | 14.44 | 6.90 | 19.993 | 5.085 | 15.532 |  | 6.9 | 0.0 | 6.9 | 9T25 | 1449.250 | T10-150 | 689.2689 | 12 | 13.5 | 16.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045417 P201045419 | 8 8
19.1/K2 | SGBM10 | Jan 23 2016 8:30AM | Jan 27 2016 11:24PM | 40.590 | 35.525 | 11.32 | 10.12 | 19.951 | 5.065 | 15.574 |  | 10.1 | 0.0 | 10.1 | 9T25 | 1450.707 | T10-150 | 689.7726 | 12 | 13.5 | 16.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045597 P201045602 | 8 8
20.1/K2 | SGBM10 | Jan 30 2016 8:30AM | Feb 12 2016 9:55AM | 40.780 | 35.525 | 10.24 | 12.11 | 19.570 | 5.255 | 15.955 |  | 12.1 | 0.0 | 12.1 | 9T25 | 1463.923 | T10-150 | 694.3433 | 12 | 13.8 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046236 P201046237 | 9 9
21.1/K2 | SGBM10 | Jan 28 2016 8:30AM | Jan 29 2016 6:55PM | 40.850 | 35.525 | 8.41 | 13.32 | 19.847 | 5.325 | 15.678 |  | 13.3 | 0.0 | 13.3 | 9T25 | 1454.315 | T10-150 | 691.0196 | 12 | 13.6 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045744 P201045745 | 9 9

## 1500
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
10.1/H2/1 | SGBM28 | Feb 2 2016 3:30PM | Feb 5 2016 4:05PM | 39.100 | 28.275 | 4.95 | 11.30 | 23.700 | 10.825 | 4.575 |  | 11.3 | 0.0 | 11.3 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.4555 | 5.575 | 8.1 | 10.0 | 1.9 | 30 TREMIE 2 (JKR) | P201046174 | 10
10.1/H2/2 | SGBM28 | Feb 23 2016 1:00PM | Feb 29 2016 3:45PM | 39.405 | 28.275 | 2.94 | 13.61 | 23.690 | 11.130 | 4.585 |  | 13.6 | 0.0 | 13.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.5852 | 5.585 | 8.1 | 10.0 | 1.9 | 30 TREMIE 2 (JKR) | P101055556 | 10
10.1/H2/3 | SGBM30 | Mar 5 2016 8:30AM | Mar 7 2016 8:05PM | 39.530 | 28.275 | 4.65 | 12.26 | 23.720 | 11.255 | 4.555 |  | 12.3 | 0.0 | 12.3 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.1980 | 5.6 | 8.1 | 10.0 | 24.2 | 30 TREMIE 2 (JKR) | P201047538 | 10
10.1/H2/4 | SGBM28 | Mar 1 2016 8:00AM | Mar 3 2016 8:45PM | 39.550 | 28.275 | 5.03 | 11.90 | 23.730 | 11.275 | 4.545 |  | 11.9 | 0.0 | 11.9 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.0695 | 5.545 | 8.0 | 10.0 | 24.5 | 30 TREMIE 2 (JKR) | P201047380 | 10
10.1/K2/1 | SGBM28 | Feb 15 2016 10:00AM | Feb 20 2016 4:35PM | 39.390 | 28.075 | 5.01 | 11.77 | 23.310 | 11.315 | 4.765 |  | 11.8 | 0.0 | 11.8 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 835.9489 | 5.765 | 8.4 | 10.0 | 18.7 | 30 TREMIE 2 (JKR) | P201046663 | 10
10.1/K2/2 | SGBM28 | Jan 28 2016 8:00AM | Feb 2 2016 2:30PM | 39.520 | 28.075 | 2.00 | 15.65 | 23.427 | 11.445 | 4.648 |  | 15.7 | 0.0 | 15.7 | 19T25 (1-12m), 19T20 (12-15m) | 585.8080 | T10-150 | 834.4043 | 8.648 | 8.2 | 10.5 | 27.8 | 30 TREMIE 2 (JKR) | P201046013 | 10.5
11.1/H2/1 | SGBM28 | Feb 20 2016 4:30PM | Feb 23 2016 2:13PM | 39.650 | 28.275 | 5.54 | 11.14 | 23.622 | 11.375 | 4.653 |  | 11.1 | 0.0 | 11.1 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 834.4696 | 5.653 | 8.2 | 12.0 | 45.9 | 30 TREMIE 2 (JKR) | P201046815 | 12
11.1/H2/2 | SGBM25 | Jan 14 2016 8:15AM | Jan 16 2016 12:20PM | 40.680 | 28.275 | 5.84 | 11.91 | 23.740 | 12.405 | 4.535 |  | 11.9 | 0.0 | 4.5 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 832.9407 | 5.535 | 8.0 | 10.0 | 24.8 | 30 TREMIE 2 (JKR) | P201045237 | 10
11.1/H2/3 | SGBM32 | Jan 6 2016 10:30AM | Jan 8 2016 4:46PM | 40.660 | 28.275 | 5.46 | 12.24 | 23.565 | 12.385 | 4.710 |  | 12.2 | 0.0 | 4.7 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 835.2195 | 5.71 | 8.3 | 10.0 | 20.1 | 30 TREMIE 2 (JKR) | P100054968 | 10
11.1/H2/4 | SGBM30 | Dec 5 2015 5:30PM | Dec 8 2015 1:40PM | 40.580 | 28.275 | 5.49 | 11.72 | 23.653 | 12.305 | 4.622 |  | 11.7 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 834.0650 | 5.622 | 8.2 | 10.0 | 22.4 | 30 TREMIE 2 (JKR) | P100053486 | 10
11.1/K2/1 | SGBM28 | Dec 17 2015 11:00AM | Dec 21 2015 4:55PM | 40.580 | 28.075 | 5.74 | 11.91 | 23.504 | 12.505 | 4.571 |  | 11.9 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.4043 | 5.571 | 8.1 | 12.0 | 48.5 | 30 TREMIE 2 (JKR) | P100054092 | 12
11.1/K2/2 | SGBM30 | Dec 10 2015 4:20PM | Dec 12 2015 10:40AM | 40.614 | 28.075 | 4.68 | 13.12 | 23.514 | 12.539 | 4.561 |  | 13.1 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.2749 | 5.561 | 8.1 | 10.0 | 24.1 | 30 TREMIE 2 (JKR) | P100053732 | 10
16.1/H2/1 | SGBM30 | Nov 25 2015 11:30AM | Nov 27 2015 7:40PM | 40.547 | 28.075 | 5.09 | 13.14 | 23.520 | 12.472 | 4.555 |  | 13.1 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.1980 | 5.555 | 8.1 | 11.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052858 | 11
16.1/H2/2 | SGBM30 | Nov 30 2015 6:30PM | Dec 2 2015 8:25PM | 40.571 | 28.075 | 5.12 | 12.97 | 23.442 | 12.496 | 4.633 |  | 13.0 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 834.2086 | 5.633 | 8.2 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053136 | 10
16.1/H2/3 | SGBM25 | Jan 23 2016 11:00AM | Jan 27 2016 4:05PM | 40.460 | 28.075 | 5.12 | 12.90 | 23.535 | 12.385 | 4.540 |  | 12.9 | 0.0 | 12.9 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.0054 | 5.54 | 8.0 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045545 | 10
16.1/H2/4 | SGBM32 | Dec 21 2015 6:30PM | Dec 28 2015 1:56PM | 40.599 | 28.075 | 5.03 | 12.77 | 23.490 | 12.524 | 4.585 |  | 12.8 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.5852 | 5.585 | 8.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054353 | 10
16.1/H2/5 | SGBM25 | Jan 9 2016 1:30PM | Jan 13 2016 10:15PM | 40.514 | 28.075 | 4.43 | 14.28 | 22.460 | 12.439 | 5.615 |  | 14.3 | 0.0 | 5.5 | 19T25 (1-12m), 19T20 (12-15m) | 439.3560 | T10-150 | 847.8864 | 6.615 | 9.9 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055213 | 12
17.1/H2/3 | SGBM12 | Feb 19 2016 3:40PM | Feb 24 2016 11:13AM | 40.450 | 25.775 | 8.35 | 11.50 | 21.174 | 14.675 | 4.601 |  | 11.5 | 0.0 | 11.5 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.7920 | 5.601 | 8.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046876 | 10
17.1/H2/4 | SGBM25 | Feb 24 2016 8:15AM | Mar 1 2016 6:30PM | 40.413 | 25.775 | 7.39 | 12.61 | 20.982 | 14.638 | 4.793 |  | 12.6 | 0.0 | 12.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 836.3227 | 5.793 | 8.5 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047200 | 10
17.1/H2/5 | SGBM25 | Mar 11 2016 1:00PM | Mar 15 2016 12:35PM | 40.340 | 25.775 | 8.75 | 11.05 | 21.050 | 14.565 | 4.725 |  | 11.1 | 0.0 | 4.7 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 835.4177 | 5.725 | 8.4 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P101055620 | 10
17.1/H2/6 | SGBM25 | Mar 2 2016 8:00AM | Mar 7 2016 11:30AM | 40.470 | 25.775 | 8.38 | 11.43 | 21.163 | 14.695 | 4.612 |  | 11.4 | 0.0 | 11.4 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.9351 | 5.606 | 8.2 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P101055589 | 12
17.1/J2/1 | SGBM25 | Feb 2 2016 2:30PM | Feb 5 2016 7:33PM | 40.420 | 25.875 | 5.30 | 14.55 | 21.220 | 14.545 | 4.655 |  | 14.6 | 0.0 | 14.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 834.4959 | 5.555 | 8.2 | 10.0 | -8.2 | 30 TREMIE 2 (JKR) | P201046181 | 10
17.1/J2/2 | SGBM25 | Feb 11 2016 11:30AM | Feb 15 2016 8:05PM | 40.500 | 25.875 | 6.88 | 13.02 | 21.205 | 14.625 | 4.670 |  | 13.0 | 0.0 | 13.0 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 834.6929 | 5.57 | 8.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046332 | 10
17.1/J2/3 | SGBM25 | Jan 28 2016 8:00AM | Feb 2 2016 4:25PM | 40.490 | 25.875 | 5.49 | 14.38 | 21.192 | 14.615 | 4.683 |  | 14.4 | 0.0 | 14.4 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 834.8633 | 5.583 | 8.3 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045924 | 10
17.1/J2/4 | SGBM32 | Dec 31 2015 5:00PM | Jan 6 2016 4:45PM | 40.535 | 25.875 | 6.47 | 13.48 | 21.094 | 14.660 | 4.781 |  | 13.5 | 0.0 | 4.8 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 836.1624 | 5.781 | 8.4 | 11.0 | -100.0 | 30 TREMIE 2 (JKR) | P100047290 | 11
17.1/J2/5 | SGBM25 | Jan 16 2016 10:30AM | Jan 19 2016 5:55PM | 40.464 | 25.875 | 5.21 | 14.61 | 21.291 | 14.589 | 4.584 |  | 14.6 | 0.0 | 14.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 833.5719 | 5.514 | 8.1 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045348 | 10
17.1/J2/6 | SGBM32 | Dec 28 2015 1:00PM | Dec 31 2015 7:25PM | 40.522 | 25.875 | 4.93 | 32.89 | 21.826 | 14.647 | 4.049 |  | 33.9 | 0.0 | 4.6 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 827.0171 | 5.597 | 7.2 | 11.0 | 53.7 | 30 TREMIE 2 (JKR) | P100054619 | 11
17.1/J2/7 | SGBM25 | Jan 20 2016 10:00AM | Jan 23 2016 1:56PM | 40.440 | 25.875 | 6.54 | 13.35 | 21.120 | 14.565 | 4.755 |  | 13.4 | 0.0 | 13.4 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 835.8159 | 5.655 | 8.4 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055515 | 10
17.1/J2/8 | SGBM32 | Jan 8 2016 1:30PM | Jan 12 2016 4:20PM | 40.485 | 25.875 | 6.91 | 14.37 | 19.780 | 14.610 | 6.095 |  | 14.4 | 0.0 | 4.5 | 19T25 (1-12m), 19T20 (12-15m) | 366.1300 | T10-150 | 855.0532 | 5.497 | 10.8 | 10.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055141 | 10

## 1650
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
11.1/F2 | SGBM32 | Dec 18 2015 2:30PM | Dec 21 2015 2:29PM | 30.740 | 28.575 | 4.91 | 7.23 | 19.601 | 2.165 | 8.974 |  | 7.2 | 0.0 | 7.2 | 24T25 | 4645.519 | T10-150 | 997.9354 | 9.974 | 19.2 | 24.0 | 25.1 | 30 TREMIE 2 (JKR) | P100054079 P100054080 P100054083 | 8 8 8
12.1/K2/1 | SGBM28 | Nov 30 2015 10:00AM | Dec 2 2015 5:16PM | 40.582 | 27.775 | 6.23 | 13.31 | 21.533 | 12.807 | 6.242 |  | 13.3 | 0.0 | 6.2 | 24T25 | 4392.820 | T10-150 | 949.0460 | 7.242 | 13.3 | 16.0 | 19.9 | 30 TREMIE 2 (JKR) | P100053117 P100053118 | 8 8
12.1/K2/2 | SGBM28 | Nov 21 2015 6:30PM | Nov 25 2015 5:22PM | 40.550 | 27.775 | 8.66 | 11.18 | 21.400 | 12.775 | 6.375 |  | 11.2 | 0.0 | 6.4 | 24T25 | 4405.122 | T10-150 | 951.3097 | 7.375 | 13.6 | 16.0 | 17.4 | 30 TREMIE 2 (JKR) | P100052773 P100052775 | 8 8
13.1/K2/1 | SGBM28 | Dec 4 2015 1:00PM | Dec 8 2015 3:45PM | 40.600 | 27.775 | 5.20 | 21.38 | 14.833 | 12.825 | 12.942 |  | 21.4 | 0.0 | 12.9 | 24T25 | 5012.543 | T10-150 | 1073.3531 | 13.942 | 27.7 | 36.0 | 30.1 | 30 TREMIE 2 (JKR) | P100053493 P100053494 P100053495 P100053497 | 9 9 9 9
13.1/K2/2 | SGBM28 | Dec 11 2015 3:30PM | Dec 15 2015 2:20PM | 40.612 | 27.775 | 5.03 | 21.68 | 14.843 | 12.837 | 12.932 |  | 21.7 | 0.0 | 12.9 | 24T25 | 5011.618 | T10-150 | 1073.1600 | 13.932 | 27.7 | 34.0 | 22.9 | 30 TREMIE 2 (JKR) | 28066409 28066410 28066415 28066427 | 8 6 10 10
14.1/K2/1 | SGBM28 | Dec 2 2015 3:30PM | Dec 4 2015 3:15PM | 40.600 | 27.775 | 0.00 | 18.83 | 22.720 | 12.825 | 5.055 |  | 18.8 | 0.0 | 5.0 | 24T25 | 4283.027 | T10-150 | 929.7801 | 6.05 | 10.8 | 13.0 | 20.3 | 30 TREMIE 2 (JKR) | P100053267 P100053272 | 7 6
14.1/K2/2 | SGBM28 | Dec 21 2015 1:00PM | Dec 23 2015 11:10PM | 40.599 | 27.775 | 3.00 | 15.55 | 22.650 | 12.824 | 5.125 |  | 8.9 | 0.0 | 5.1 | 24T25 | 4289.502 | T10-150 | 930.8581 | 6.125 | 11.0 | 14.0 | 27.7 | 30 TREMIE 2 (JKR) | Pending Pending | 7 7
15.1/K2/1 | SGBM28 | Dec 29 2015 2:30PM | Jan 4 2016 11:20PM | 40.574 | 27.775 | 5.00 | 15.50 | 20.977 | 12.799 | 6.798 |  | 15.5 | 0.0 | 6.8 | 24T25 | 4444.248 | T10-150 | 958.6137 | 7.798 | 14.5 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054770 P100054773 | 9 9
15.1/K2/2 | SGBM28 | Nov 25 2015 1:00PM | Nov 30 2015 12:32PM | 40.620 | 27.775 | 5.09 | 14.41 | 22.773 | 12.845 | 5.002 |  | 14.4 | 0.0 | 14.4 | 24T25 | 4278.125 | T10-150 | 928.9698 | 6 | 10.7 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052959 P100052960 | 7 7
16.1/K2/1 | SGBM28 | Dec 8 2015 8:15AM | Dec 11 2015 4:45PM | 40.600 | 27.775 | 4.89 | 13.91 | 22.713 | 12.825 | 5.062 |  | 13.9 | 0.0 | 5.1 | 24T25 | 4283.675 | T10-150 | 929.8876 | 6.063 | 10.8 | 12.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053679 | 12
16.1/K2/2 | SGBM28 | Jan 5 2016 8:15AM | Jan 8 2016 6:40PM | 40.510 | 27.775 | 5.03 | 13.52 | 22.710 | 12.735 | 5.065 |  | 13.5 | 0.0 | 5.1 | 24T25 | 4283.952 | T10-150 | 929.9334 | 6.065 | 10.8 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054981 P100054980 | 7 7
17.1/H2/1 | SGBM30 | Mar 3 2016 3:00PM | Mar 4 2016 7:55PM | 40.450 | 25.775 | 8.14 | 12.26 | 20.645 | 14.675 | 5.130 |  | 12.3 | 0.0 | 12.3 | 24T25 | 4289.964 | T10-150 | 930.9354 | 6.2 | 11.0 | 15.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047414 P201047417 | 8 7
17.1/H2/2 | SGBM25 | Mar 8 2016 8:30AM | Mar 10 2016 8:15PM | 40.444 | 25.775 | 8.80 | 11.65 | 20.725 | 14.669 | 5.050 |  | 11.7 | 0.0 | 5.0 | 24T25 | 0.000 | T10-150 | 929.7035 | 6.05 | 10.8 | 14.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047754 P201047757 | 7 7

## 1800
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
12.1/H2/1 | SGBM28 | Dec 14 2015 7:15PM | Dec 17 2015 11:17AM | 40.625 | 27.775 | 3.65 | 15.12 | 22.363 | 12.850 | 5.412 |  | 15.1 | 0.0 | 5.4 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1025.8031 | 6.412 | 13.8 | 17.0 | 23.4 | 30 TREMIE 2 (JKR) | P100053921 P100053923 | 9 8
12.1/H2/2 | SGBM28 | Dec 26 2015 8:30AM | Dec 29 2015 5:05PM | 40.660 | 27.775 | 5.36 | 13.76 | 22.152 | 12.885 | 5.623 |  | 13.8 | 0.0 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1029.5263 | 6.623 | 14.3 | 18.0 | 25.8 | 30 TREMIE 2 (JKR) | P100054440 P100054441 | 9 9
12.1/J2/1 | SGBM28 | Nov 13 2015 1:00PM | Nov 18 2015 5:48PM | 40.595 | 27.775 | 7.16 | 18.34 | 16.412 | 12.820 | 11.363 |  | 18.3 | 0.0 | 11.4 | 26T25 (1-12m), 26T20 (12-18m) | 1202.4480 | T10-150 | 1143.8421 | 12.365 | 28.9 | 34.0 | 17.6 | 30 TREMIE 2 (JKR) | P100052371 P100052372 P100052373 | 12 10 12
12.1/J2/2 | SGBM28 | Oct 31 2015 1:30PM | Nov 5 2015 9:20PM | 40.660 | 27.775 | 7.77 | 17.28 | 16.430 | 12.885 | 11.345 |  | 17.3 | 0.0 | 11.3 | 26T25 (1-12m), 26T20 (12-18m) | 1202.4480 | T10-150 | 1143.4650 | 12.345 | 28.9 | 32.0 | 10.8 | 30 TREMIE 2 (JKR) | P100051678 P100051679 P100051680 P100051681 | 8 8 8 8
13.1/G2/1 | SGBM25 | Mar 15 2016 4:50PM | Mar 18 2016 3:49PM | 32.010 | 27.775 | 0.00 | 10.05 | -10.050 | 4.235 | 37.825 |  | 10.1 | 0.0 | 5.8 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1717.3474 | 6.815 | 96.3 | 18.0 | -81.3 | 30 TREMIE 2 (JKR) | P201048048 P201048049 | 9 9
13.1/G2/2 | SGBM30 | Dec 2 2015 7:00PM | Dec 5 2015 8:30PM | 40.585 | 27.775 | 3.86 | 15.35 | 22.295 | 12.810 | 5.480 |  | 15.3 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1026.9954 | 6.48 | 13.9 | 17.0 | 21.9 | 30 TREMIE 2 (JKR) | P100053393 P100053397 | 9 8
13.1/H2/1 | SGBM25 | Feb 20 2016 11:00AM | Feb 27 2016 12:10PM | 40.610 | 27.775 | 5.05 | 26.40 | 12.013 | 12.835 | 15.762 |  | 26.4 | 0.0 | 26.4 | 26T25 (1-12m), 26T20 (12-18m) | 1803.6720 | T10-150 | 1237.2914 | 18.212 | 40.1 | 49.0 | 11.9 | 30 TREMIE 2 (JKR) | P201047058 P201047059 P201047060 P201047061 P201047062 | 10 10 10 10 9
13.1/H2/2 | SGBM30 | Jan 16 2016 10:30AM | Jan 20 2016 3:30PM | 40.600 | 27.775 | 4.54 | 26.02 | 10.665 | 12.825 | 17.110 |  | 26.0 | 0.0 | 26.0 | 26T25 (1-12m), 26T20 (12-18m) | 1903.8760 | T10-150 | 1266.2607 | 19.07 | 43.5 | 51.0 | 17.1 | 30 TREMIE 2 (JKR) | P201045364 P201045365 P100055415 P100055417 P201045368 | 9 12 12 9 9
13.1/J2/1 | SGBM28 | Nov 18 2015 3:00PM | Nov 21 2015 11:20PM | 40.640 | 27.775 | 5.00 | 26.16 | 10.794 | 12.865 | 16.981 |  | 26.2 | 0.0 | 26.2 | 26T25 (1-12m), 26T20 (12-18m) | 1703.4680 | T10-150 | 1263.4839 | 17.981 | 43.2 | 50.0 | 15.7 | 30 TREMIE 2 (JKR) | P100052590 P100052594 P100052598 P100052604 P100052605 | 10 10 10 10 10
13.1/J2/2 | SGBM28 | Nov 6 2015 9:00AM | Nov 13 2015 5:05PM | 40.666 | 27.775 | 5.10 | 26.19 | 11.000 | 12.891 | 16.775 |  | 26.2 | 0.0 | 16.8 | 26T25 (1-12m), 26T20 (12-18m) | 1703.4680 | T10-150 | 1259.0515 | 17.775 | 42.7 | 46.0 | 7.7 | 30 TREMIE 2 (JKR) | P100052102 P100052103 P100052104 P100052105 P100052107 | 9 10 9 9 9
14.1/G2/1 | SGBM30 | Dec 8 2015 11:30AM | Dec 10 2015 5:59PM | 40.550 | 27.775 | 5.80 | 13.07 | 22.251 | 12.775 | 5.524 |  | 13.1 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.7707 | 6.524 | 14.1 | 18.0 | 28.0 | 30 TREMIE 2 (JKR) | P100053614 P100053615 | 9 9
14.1/G2/2 | SGBM30 | Nov 27 2015 9:30AM | Nov 30 2015 10:30PM | 40.530 | 27.775 | 4.11 | 14.91 | 22.285 | 12.755 | 5.490 |  | 14.9 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.1712 | 6.490 | 14.0 | 18.0 | 28.8 | 30 TREMIE 2 (JKR) | P100053009 P100053013 | 9 9
14.1/H2/1 | SGBM30 | Nov 9 2015 2:00PM | Nov 14 2015 1:30PM | 40.675 | 27.775 | 0.00 | 20.04 | 22.300 | 12.900 | 5.475 |  | 20.0 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1026.9076 | 6.475 | 13.9 | 18.0 | 29.2 | 30 TREMIE 2 (JKR) | P100052120 P100052121 | 9 9
14.1/H2/2 | SGBM30 | Nov 18 2015 9:30AM | Nov 20 2015 10:25PM | 40.630 | 27.775 | 3.57 | 15.12 | 22.220 | 12.855 | 5.555 |  | 15.1 | 0.0 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1028.3187 | 6.555 | 14.1 | 16.0 | 13.2 | 30 TREMIE 2 (JKR) | P100052509 P100052510 | 8 8
14.1/J2/1 | SGBM30 | Oct 23 2015 3:00PM | Oct 28 2015 6:55PM | 40.640 | 27.775 | 4.91 | 14.60 | 22.288 | 12.865 | 5.487 |  | 14.6 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.1183 | 6.5 | 14.0 | 18.0 | 28.9 | 30 TREMIE 2 (JKR) | P100051256 P100051258 | 9 9
14.1/J2/2 | SGBM30 | Oct 12 2015 3:00PM | Oct 19 2015 4:05PM | 40.700 | 27.775 | 5.38 | 15.17 | 20.510 | 12.925 | 7.265 |  | 15.2 | 0.0 | 15.2 | 26T25 (1-12m), 26T20 (12-18m) | 801.6320 | T10-150 | 1060.3162 | 8.3 | 18.5 | 24.0 | 29.8 | 30 TREMIE 2 (JKR) | P100050669 P100050674 P100050675 | 8 8 8
15.1/G2/1 | SGBM30 | Nov 21 2015 1:00PM | Nov 25 2015 4:15PM | 40.540 | 27.775 | 4.86 | 13.74 | 22.330 | 12.765 | 5.445 |  | 13.7 | 0.0 | 5.4 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1026.3809 | 6.445 | 13.9 | 18.0 | 29.9 | 30 TREMIE 2 (JKR) | P100052767 P100052770 | 9 9
15.1/G2/2 | SGBM28 | Oct 27 2015 9:30AM | Oct 31 2015 3:40PM | 40.550 | 27.775 | 4.99 | 15.02 | 22.238 | 12.775 | 5.537 |  | 15.0 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1028.0004 | 6.6 | 14.1 | 18.0 | 27.7 | 30 TREMIE 2 (JKR) | P100051447 P100051449 | 9 9
15.1/H2/1 | SGBM30 | Oct 6 2015 4:30PM | Oct 12 2015 2:55PM | 40.500 | 27.775 | 5.01 | 14.89 | 22.260 | 12.725 | 5.515 |  | 14.9 | 0.0 | 14.9 | 26T25 (1-12m), 26T20 (12-18m) | 701.4280 | T10-150 | 1027.6119 | 7 | 14.0 | 18.0 | 28.2 | 30 TREMIE 2 (JKR) | P100050278 P100050281 | 9 9
15.1/H2/2 | SGBM30 | Oct 19 2015 2:20PM | Oct 23 2015 6:00PM | 40.500 | 27.775 | 4.93 | 15.08 | 22.210 | 12.725 | 5.565 |  | 15.1 | 0.0 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1028.4962 | 6.6 | 14.2 | 20.0 | 41.2 | 30 TREMIE 2 (JKR) | P100050910 P100050912 | 10 10
15.1/J2/1 | SGBM30 | Nov 5 2015 1:30PM | Nov 9 2015 4:00PM | 40.675 | 27.775 | 3.55 | 16.50 | 20.493 | 12.900 | 7.282 |  | 16.5 | 0.0 | 7.3 | 26T25 (1-12m), 26T20 (12-18m) | 801.6320 | T10-150 | 1060.6475 | 8.252 | 18.5 | 21.0 | 13.3 | 30 TREMIE 2 (JKR) | P100051892 P100051893 | 10 11
15.1/J2/2 | SGBM30 | Oct 28 2015 4:00PM | Nov 2 2015 2:30PM | 40.680 | 27.775 | 3.61 | 14.90 | 22.239 | 12.905 | 5.536 |  | 14.9 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.9828 | 6.6 | 14.1 | 19.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051530 P100051531 | 9.5 9.5
16.1/G2/1 | SGBM30 | Nov 14 2015 2:30PM | Nov 18 2015 12:30PM | 40.540 | 27.775 | 5.18 | 14.65 | 22.263 | 12.765 | 5.512 |  | 14.6 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.5588 | 6.512 | 14.0 | 19.0 | -100.0 | 30 TREMIE 2 (JKR) | P100052353 P100052354 | 9 10
16.1/G2/2 | SGBM30 | Nov 2 2015 11:30AM | Nov 5 2015 4:03PM | 40.550 | 27.775 | 5.05 | 14.73 | 22.243 | 12.775 | 5.532 |  | 14.7 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.9121 | 6.6 | 14.1 | 19.0 | -100.0 | 30 TREMIE 2 (JKR) | P100051656 P100051658 | 10 9
17.1/G2/1 | SGBM30 | Dec 29 2015 11:30AM | Jan 2 2016 3:00PM | 40.488 | 27.775 | 6.29 | 12.90 | 22.249 | 12.713 | 5.526 |  | 12.9 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.8063 | 6.526 | 14.1 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054653 P100054657 | 9 9
17.1/G2/2 | SGBM30 | Jan 6 2016 8:30AM | Jan 13 2016 4:35PM | 40.666 | 27.775 | 7.91 | 11.07 | 22.276 | 12.891 | 5.499 |  | 11.1 | 0.0 | 5.5 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1027.3297 | 6.499 | 14.0 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055180 P100055183 | 9 9
18.1/G2/1 | SGBM30 | Dec 12 2015 9:30AM | Dec 15 2015 11:25AM | 40.725 | 27.775 | 11.02 | 8.14 | 22.223 | 12.950 | 5.552 |  | 15.1 | 0.0 | 5.6 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1028.2660 | 6.552 | 14.1 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | 28066396 28066397 | 9 9
18.1/G2/2 | SGBM28 | Jan 18 2016 9:30AM | Jan 20 2016 5:35PM | 40.730 | 27.775 | 10.60 | 8.66 | 22.128 | 12.955 | 5.647 |  | 8.3 | 0.0 | 8.6 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1029.9543 | 6.647 | 14.4 | 19.0 | 32.2 | 30 TREMIE 2 (JKR) | P201045370 P100055418 | 9 10
18.1/H2/1 | SGBM30 | Feb 3 2016 9:30AM | Feb 5 2016 2:59PM | 40.640 | 27.775 | 9.99 | 8.93 | 22.220 | 12.865 | 5.555 |  | 8.9 | 0.0 | 8.9 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1028.3187 | 6.555 | 14.1 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046171 P201046172 | 10 8
18.1/H2/2 | SGBM30 | Jan 22 2016 3:00PM | Jan 27 2016 5:35PM | 40.640 | 27.775 | 8.12 | 11.16 | 22.120 | 12.865 | 5.655 |  | 11.2 | 0.0 | 11.2 | 26T25 (1-12m), 26T20 (12-18m) | 601.2240 | T10-150 | 1030.0972 | 6.655 | 14.4 | 18.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045557 P201045558 | 9 9
18.1a/G2/1 | SGBM30 | Dec 22 2015 9:00AM | Dec 23 2015 8:25PM | 40.855 | 34.025 | 10.73 | 8.59 | 22.016 | 6.830 | 12.009 |  | 8.6 | 0.0 | 8.6 | 26T25 (1-12m), 26T20 (12-18m) | 1302.6520 | T10-150 | 1157.4167 | 13.009 | 30.6 | 38.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054237 P100054238 P100054239 P100054241 | 9 10 9 10
18.1a/G2/2 | SGBM30 | Jan 5 2016 9:30AM | Jan 7 2016 4:47PM | 40.750 | 34.025 | 13.05 | 6.33 | 21.973 | 6.725 | 12.052 |  | 6.3 | 0.0 | 6.3 | 26T25 (1-12m), 26T20 (12-18m) | 1302.6520 | T10-150 | 1158.3226 | 13.052 | 30.7 | 37.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054929 P100054933 P100054938 P100054939 | 9 9 9 10
18.1a/H2/1 | SGBM30 | Feb 5 2016 1:00PM | Feb 16 2016 2:50PM | 40.640 | 34.025 | 10.83 | 8.58 | 21.969 | 6.615 | 12.056 |  | 8.6 | 0.0 | 8.6 | 26T25 (1-12m), 26T20 (12-18m) | 1302.6520 | T10-150 | 1158.4069 | 13.056 | 30.7 | 36.0 | -41.3 | 30 TREMIE 2 (JKR) | P201046385 P201046386 P201046389 P201046393 | 9 9 9 9
18.1a/H2/2 | SGBM30 | Jan 27 2016 2:30PM | Jan 29 2016 4:55PM | 40.690 | 34.025 | 12.55 | 6.78 | 21.963 | 6.665 | 12.062 |  | 6.8 | 0.0 | 6.8 | 26T25 (1-12m), 26T20 (12-18m) | 1302.6520 | T10-150 | 1158.5332 | 13.062 | 30.7 | 36.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045733 P201045735 P201045736 P201045737 | 9 9 9 9
19.1/G2/1 | SGBM30 | Dec 14 2015 6:45PM | Dec 18 2015 3:30PM | 40.974 | 34.025 | 11.27 | 13.36 | 16.898 | 6.949 | 17.127 |  | 13.4 | 0.0 | 13.4 | 26T25 (1-12m), 26T20 (12-18m) | 1803.6720 | T10-150 | 1266.6267 | 18.127 | 43.6 | 50.0 | -100.0 | 30 TREMIE 2 (JKR) | P100053997 P100053998 P100054005 P100054011 P100054012 | 10 10 10 10 10
19.1/G2/2 | SGBM28 | Jan 13 2016 9:00AM | Jan 18 2016 1:20PM | 40.750 | 34.025 | 9.88,12.50 | 1.12,12.24 | 16.905 | 6.725 | 17.120 |  | 13.4 | 0.0 | 14.9 | 26T25 (1-12m), 26T20 (12-18m) | 1803.6720 | T10-150 | 1266.4759 | 18.12 | 43.6 | 49.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045279 P201045280 P201045283 P201045285 P100055339 | 10 10 9 10 10
19.1/H2/1 | SGBM25 | Feb 17 2016 9:00AM | Feb 20 2016 12:59PM | 40.740 | 34.025 | 15.20 | 7.56 | 16.915 | 6.715 | 17.110 |  | 7.6 | 0.0 | 9.6 | 26T25 (1-12m), 26T20 (12-18m) | 1703.4680 | T10-150 | 1266.2607 | 17.11 | 43.5 | 53.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046647 P201046648 P201046649 P201046650 P201046652 P201046653 P201046657 | 8 8 9 9 8 8 3
19.1/H2/2 | SGBM30 | Jan 29 2016 11:00AM | Feb 3 2016 6:23PM | 40.700 | 34.025 | 10.65 | 14.05 | 16.780 | 6.675 | 17.245 |  | 14.0 | 0.0 | 14.0 | 26T25 (1-12m), 26T20 (12-18m) | 1803.6720 | T10-150 | 1269.1677 | 18.245 | 43.9 | 50.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045993 P201045995 P201045996 P201046005 P201046006 P201046013 | 9 9 9 8 8 7
21.1/J2/1 | SGBM10 | Feb 3 2016 8:40AM | Feb 16 2016 6:05PM | 40.820 | 34.025 | 8.57 | 13.48 | 19.515 | 6.795 | 14.510 |  | 13.5 | 0.0 | 13.5 | 26T25 (1-12m), 26T20 (12-18m) | 1603.2640 | T10-150 | 1210.4947 | 16.51 | 36.9 | 44.5 | -100.0 | 30 TREMIE 2 (JKR) | P201045211 P201045845 P201045501 P201045503 P201045504 | 4.5 9 9 12 10
21.1/J2/2 | SGBM28 | Jan 22 2016 8:30AM | Jan 27 2016 9:06PM | 40.875 | 34.025 | 10.36 | 11.68 | 19.448 | 6.850 | 14.577 |  | 11.7 | 0.0 | 11.7 | 26T25 (1-12m), 26T20 (12-18m) | 1503.0600 | T10-150 | 1211.9257 | 15.577 | 37.1 | 44.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045580 P201045583 P201045587 P201045590 | 12 10 10 12

## 2000
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
18.1a/J2/1 | SGBM30 | Feb 16 2016 1:00PM | Feb 18 2016 5:35PM | 40.644 | 33.725 | 9.13 | 17.20 | 14.779 | 6.919 | 18.946 |  | 17.2 | 0.0 | 17.2 | 34T25 | 9034.408 | T10-150 | 1459.3852 | 12 | 59.5 | 66.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046532 P201046534 P201046536 P201046538 P201046544 P201046545 P201046548 | 8 9 9 12 12 8 8
18.1a/J2/2 | SGBM30 | Feb 20 2016 5:30PM | Feb 23 2016 5:00PM | 40.490 | 33.725 | 11.82 | 14.73 | 14.616 | 6.765 | 19.109 |  | 14.7 | 0.0 | 14.7 | 34T25 | 9055.767 | T10-150 | 1463.3227 | 12 | 60.0 | 69.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046828 P201046829 P201046831 P201046834 P201046839 P201046841 | 12 9 12 12 12 12
19.1/J2/1 | SGBM30 | Feb 25 2016 2:30PM | Feb 29 2016 11:05AM | 40.570 | 33.725 | 9.11 | 11.64 | 20.375 | 6.845 | 13.350 |  | 11.6 | 0.0 | 11.6 | 34T25 | 8301.131 | T10-150 | 1325.1886 | 12 | 41.9 | 50.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047100 P201047101 P201047102 P201047104 P201047103 | 12 8 10 9 11
19.1/J2/2 | SGBM30 | Mar 1 2016 8:00AM | Mar 3 2016 4:35PM | 40.770 | 33.725 | 8.68 | 12.02 | 20.603 | 7.045 | 13.122 |  | 12.0 | 0.0 | 12.0 | 34T25 | 8271.254 | T10-150 | 1319.7798 | 14.2 | 41.2 | 48.0 | -100.0 | 30 TREMIE 2 (JKR) | P201047350 P201047352 P201047354 P201047356 | 12 12 12 12
20.1/J2/1 | SGBM30 | Feb 23 2016 2:00PM | Feb 26 2016 10:40AM | 40.825 | 33.725 | 11.02 | 7.28 | 23.258 | 7.100 | 10.467 |  | 7.3 | 0.0 | 7.3 | 34T25 | 7923.354 | T10-150 | 1257.4126 | 11.467 | 32.9 | 38.0 | -100.0 | 30 TREMIE 2 (JKR) | P201046988 P201046989 P201046990 P201046992 | 12 9 9 8
20.1/J2/2 | SGBM30 | Feb 18 2016 3:00PM | Feb 22 2016 2:15PM | 40.825 | 33.725 | 10.08 | 8.24 | 23.237 | 7.100 | 10.488 |  | 8.2 | 0.0 | 8.2 | 34T25 | 7926.106 | T10-150 | 1257.9001 | 11.5 | 33.0 | 40.5 | -100.0 | 30 TREMIE 2 (JKR) | P201046723 Pending P201046727 P201046732 | 9 10 12 9.5

## 2200
Summary List for 1891642800-SVMC
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
20.1/G2/1 | SGBM30 | Jan 7 2016 2:00PM | Jan 11 2016 2:20PM | 40.945 | 33.325 | 6.00 | 17.25 | 18.370 | 7.620 | 14.955 |  | 17.3 | 0.0 | 12.0 | 40T25 | 10784.263 | T10-150 | 1506.8606 | 12 | 56.9 | 68.0 | -100.0 | 30 TREMIE 2 (JKR) | P100055085 P100055088 P100055092 P100055093 P100055094 P100055099 P100055102 | 12 10 9 10 10 10 7
20.1/G2/2 | SGBM30 | Dec 26 2015 8:15AM | Dec 29 2015 3:00PM | 41.080 | 33.325 | 10.81 | 12.50 | 18.364 | 7.755 | 14.961 |  | 12.5 | 0.0 | 12.5 | 40T25 | 10785.188 | T10-150 | 1507.0192 | 12 | 56.9 | 70.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054427 P100054428 P100054429 P100054431 P100054433 P100054435 P100054436 | 10 10 10 9 10 10 11
20.1/G2/3 | SGBM30 | Dec 18 2015 9:00AM | Dec 22 2015 11:10AM | 40.995 | 33.325 | 12.72 | 10.74 | 18.368 | 7.670 | 14.957 |  | 10.7 | 0.0 | 10.7 | 40T25 | 10784.571 | T10-150 | 1506.9135 | 12 | 56.9 | 68.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054143 P100054144 P100054146 P100054148 P100054149 P100054150 P100054151 | 10 9 12 10 9 9 9
20.1/H2/1 | SGBM30 | Jan 20 2016 11:00AM | Jan 26 2016 1:30PM | 40.920 | 33.325 | 9.46 | 14.13 | 18.171 | 7.595 | 15.154 |  | 14.1 | 0.0 | 14.1 | 40T25 | 10814.941 | T10-150 | 1512.1201 | 12 | 57.6 | 65.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045489 P201045490 P201045491 P201045492 P201045496 P201045499 P201045500 | 9 9 9 9 12 9 8
20.1/H2/2 | SGBM30 | Jan 13 2016 2:30PM | Jan 16 2016 3:17PM | 40.945 | 33.325 | 6.00 | 17.55 | 18.349 | 7.620 | 14.976 |  | 17.6 | 0.0 | 12.4 | 40T25 | 10787.500 | T10-150 | 1507.4155 | 12 | 56.9 | 65.0 | -100.0 | 30 TREMIE 2 (JKR) | P201045243 P201045244 P201045246 P201045247 P201045250 P201045253 | 12 12 10 12 10 9
20.1/H2/3 | SGBM30 | Dec 31 2015 1:00PM | Jan 6 2016 9:40PM | 41.000 | 33.325 | 12.80 | 10.51 | 18.442 | 7.675 | 14.883 |  | 10.5 | 0.0 | 10.5 | 40T25 | 10773.163 | T10-150 | 1504.9588 | 12 | 56.6 | 68.0 | -100.0 | 30 TREMIE 2 (JKR) | P100054871 P100054873 P100054875 P100054881 P100054884 P100054890 P100054892 | 9 12 10 9 10 9 9