## 1200
Summary List for 18916521-MRT-V1 Spur Line
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
ABUT FDD-1 |  | Feb 23 2016 9:30AM | Feb 25 2016 2:30PM | 40.714 | 40.547 | 0.00 | 0.00 | 0.543 | 0.167 | 40.004 |  | 0.0 | 0.0 | 0.0 | 23T40 | 19977.788 | T16-150 | 2924.3911 | 12+12+12+12 | 45.2 | 60.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 | 9 9 9 9 9 9 6
ABUT FDD-2 |  | Feb 27 2016 8:30AM | Feb 29 2016 6:00PM | 40.733 | 40.547 | 0.00 | 0.00 | 1.226 | 0.186 | 39.321 |  | 0.0 | 0.0 | 0.0 | 23T40 | 19822.740 | T16-150 | 2899.6136 | 12+12+12+12 | 44.5 | 60.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 | 9 9 9 9 9 9 6
ABUT FDA-1 | SGBM32 | Feb 25 2016 7:50PM | Mar 1 2016 8:10PM | 40.408 | 41.304 | 41.10 | 3.60 | -3.200 | -0.896 | 44.504 |  | 3.6 | 0.0 | 3.6 | 23T40 | 20999.333 | T16-150 | 3087.7131 | 12+12+12+12+6 | 50.3 | 63.0 | -16.6 | G40T2 | 1 2 3 4 5 6 7 | 9 9 9 9 9 9 9
ABUT FDA-2 | SGBM32 | Mar 3 2016 9:20AM | Mar 5 2016 6:50PM | 40.343 | 41.304 | 47.70 | 1.70 | -8.087 | -0.961 | 49.391 |  | 1.7 | 1.7 | 1.7 | 23T40 | 22108.731 | T16-150 | 3265.1948 | 12+12+12+12+8 | 55.9 | 72.0 | -67.8 | G40T2 | 1 2 3 4 5 6 7 8 | 9 9 9 9 9 9 9 9

## 1500
Summary List for 18916521-MRT-V1 Spur Line
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
FDD 17-1 | SGBM32 | Jan 25 2016 10:30AM | Jan 26 2016 5:30PM | 39.370 | 35.856 | 0.00 | 0.00 | -3.973 | 3.514 | 39.829 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4821.553 | T12-150 | 2087.8605 | 12+12+12+8 | 70.4 | 78.0 | -70.4 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 17-2 | SGBM32 | Jan 28 2016 9:30AM | Jan 30 2016 12:00AM | 39.650 | 35.856 | 0.00 | 0.00 | -3.252 | 3.794 | 39.108 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4771.769 | T12-150 | 2069.1466 | 12+12+12+8 | 69.1 | 82.0 | 24.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 6 4
FDD 17-3 | SGBM32 | Jan 21 2016 8:30AM | Jan 23 2016 5:59PM | 39.869 | 35.856 | 0.00 | 0.00 | -3.722 | 4.013 | 39.578 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4804.222 | T12-150 | 2081.3454 | 12+12+12+8 | 69.9 | 78.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 17-4 | SGBM32 | Jan 19 2016 1:30PM | Jan 22 2016 3:45PM | 39.484 | 35.856 | 0.00 | 0.00 | -3.385 | 3.628 | 39.241 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4780.953 | T12-150 | 2072.5984 | 12+12+12+11 | 69.4 | 85.0 | 22.6 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 4
FDD 17-5 | SGBM32 | Jan 31 2016 8:30AM | Feb 1 2016 5:40PM | 39.598 | 35.856 | 0.00 | 0.00 | -3.735 | 3.742 | 39.591 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4805.119 | T12-150 | 2081.6829 | 12+12+12+8 | 70.0 | 78.0 | -35.7 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 17-6 | SGBM32 | Jan 26 2016 10:00AM | Jan 27 2016 7:10PM | 39.720 | 35.856 | 0.00 | 0.00 | -3.487 | 3.864 | 39.343 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4787.995 | T12-150 | 2075.2459 | 12+12+12+8 | 69.5 | 78.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 17-7 | SGBM32 | Jan 27 2016 10:00AM | Jan 28 2016 4:37PM | 39.725 | 35.856 | 0.00 | 0.00 | -3.448 | 3.869 | 39.304 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4785.303 | T12-150 | 2074.2336 | 12+12+12+8 | 69.5 | 82.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 6 4
FDD 17-8 | SGBM32 | Jan 23 2016 8:40AM | Jan 25 2016 5:20PM | 39.816 | 35.856 | 0.00 | 0.00 | -3.786 | 3.960 | 39.642 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4808.641 | T12-150 | 2083.0066 | 12+12+12+8 | 70.1 | 75.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 3
FDD 17-9 | SGBM32 | Jan 19 2016 3:30PM | Jan 21 2016 4:45AM | 39.878 | 35.856 | 0.00 | 0.00 | -3.635 | 4.022 | 39.491 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4798.215 | T12-150 | 2079.0872 | 12+12+12+8 | 69.8 | 78.0 | 11.8 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 16-1 | SGBM32 | Feb 6 2016 8:30AM | Feb 11 2016 3:44PM | 42.139 | 35.976 | 0.00 | 0.00 | -5.630 | 6.163 | 41.606 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4944.251 | T12-150 | 2133.9946 | 12+12+12+10 | 73.5 | 81.0 | 10.2 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 16-2 | SGBM32 | Feb 17 2016 8:45AM | Feb 17 2016 8:45PM | 41.462 | 35.976 | 0.00 | 0.00 | -5.735 | 5.486 | 41.711 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4951.501 | T12-150 | 2136.7209 | 12+12+12+11 | 73.7 | 81.0 | 9.9 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 16-3 | SGBM32 | Feb 3 2016 4:10PM | Feb 5 2016 3:20PM | 42.123 | 35.976 | 0.00 | 0.00 | -5.101 | 6.147 | 41.077 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4907.725 | T12-150 | 2120.2592 | 12+12+12+10 | 72.6 | 81.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 16-4 | SGBM32 | Feb 2 2016 8:00AM | Feb 3 2016 12:30AM | 41.912 | 35.976 | 0.00 | 0.00 | -5.506 | 5.936 | 41.482 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4935.689 | T12-150 | 2130.7748 | 12+12+12+10 | 73.3 | 81.0 | -14.1 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 16-5 | SGBM32 | Feb 19 2016 8:30AM | Feb 19 2016 9:10PM | 42.230 | 35.976 | 0.00 | 0.00 | -5.197 | 6.254 | 41.173 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4914.353 | T12-150 | 2122.7517 | 12+12+12+10 | 72.8 | 81.0 | 11.3 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 16-6 | SGBM32 | Feb 13 2016 10:30AM | Feb 15 2016 6:10PM | 41.940 | 35.976 | 0.00 | 0.00 | -5.434 | 5.964 | 41.410 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4930.718 | T12-150 | 2128.9052 | 12+12+12+10 | 73.2 | 84.0 | 2.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 3 9 9 9 9 9 9 9 9 9
FDD 16-7 | SGBM32 | Feb 13 2016 2:30PM | Feb 16 2016 7:40PM | 41.869 | 35.976 | 0.00 | 0.00 | -5.651 | 5.893 | 41.627 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4945.701 | T12-150 | 2134.5397 | 12+12+12+10 | 73.6 | 86.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 5 9 9
FDD 16-8 | SGBM32 | Feb 5 2016 9:00AM | Feb 12 2016 6:18PM | 42.004 | 35.976 | 0.00 | 0.00 | -5.560 | 6.028 | 41.536 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4939.418 | T12-150 | 2132.1769 | 12+12+12+10 | 73.4 | 90.0 | 22.6 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 16-9 | SGBM32 | Feb 2 2016 10:00AM | Feb 3 2016 10:50PM | 41.899 | 35.976 | 0.00 | 0.00 | -5.393 | 5.923 | 41.369 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4927.887 | T12-150 | 2127.8407 | 12+12+12+10 | 73.1 | 81.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 15-1 | SGBM26 | Feb 2 2016 11:00AM | Feb 3 2016 2:10AM | 39.476 | 37.075 | 0.00 | 0.00 | -8.757 | 2.401 | 45.832 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5236.048 | T12-150 | 2243.7607 | 12+12+12+12+3 | 81.0 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 15-2 | SGBM26 | Feb 6 2016 3:00PM | Feb 10 2016 8:10PM | 39.481 | 37.075 | 0.00 | 0.00 | -8.812 | 2.406 | 45.887 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5239.846 | T12-150 | 2245.1899 | 12+12+12+12+4 | 81.1 | 95.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 9 5
FDD 15-3 | SGBM26 | Jan 28 2016 8:15AM | Jan 30 2016 9:45PM | 39.590 | 37.075 | 0.00 | 0.00 | -8.282 | 2.515 | 45.357 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5203.250 | T12-150 | 2231.4199 | 12+12+12+12+4 | 80.2 | 95.0 | 18.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 9 5
FDD 15-4 | SGBM26 | Jan 25 2016 10:10AM | Jan 27 2016 1:40AM | 39.454 | 37.075 | 0.00 | 0.00 | -8.363 | 2.379 | 45.438 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5208.843 | T12-150 | 2233.5244 | 12+12+12+12+4 | 80.3 | 85.0 | 5.8 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 4
FDD 15-5 | SGBM13 | Feb 14 2016 8:30AM | Feb 15 2016 4:00PM | 39.402 | 37.075 | 0.00 | 0.00 | -7.781 | 2.327 | 44.856 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5168.657 | T12-150 | 2218.4044 | 12+12+12+12+3 | 79.3 | 88.0 | -32.6 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 7 9 9 9
FDD 15-6 | SGBM26 | Feb 3 2016 9:40AM | Feb 4 2016 3:40AM | 39.355 | 37.075 | 0.00 | 0.00 | -8.463 | 2.280 | 45.538 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5215.748 | T12-150 | 2236.1224 | 12+12+12+12+3 | 80.5 | 93.0 | 23.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 7 5
FDD 15-7 | SGBM26 | Feb 4 2016 10:40AM | Feb 5 2016 8:10PM | 39.105 | 37.075 | 0.00 | 0.00 | -8.216 | 2.030 | 45.291 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5198.693 | T12-150 | 2229.7052 | 12+12+12+12+3 | 80.0 | 90.0 | -55.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 15-8 | SGBM26 | Jan 31 2016 2:10PM | Feb 2 2016 1:38AM | 39.146 | 37.075 | 0.00 | 0.00 | -8.520 | 2.071 | 45.595 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5219.684 | T12-150 | 2237.6033 | 12+12+12+12+4 | 80.6 | 83.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 7 4
FDD 15-9 | SGBM26 | Feb 11 2016 2:55PM | Feb 12 2016 7:00PM | 39.113 | 37.075 | 0.00 | 0.00 | -8.331 | 2.038 | 45.406 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5206.633 | T12-150 | 2232.6930 | 12+12+12+12+3 | 80.2 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 12-1 | SGBM26 | Feb 22 2016 8:30AM | Feb 23 2016 1:45AM | 40.357 | 34.503 | 0.00 | 0.00 | -19.075 | 5.854 | 53.578 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5770.894 | T12-150 | 2445.0977 | 12+12+12+12+11 | 94.7 | 104.0 | 9.3 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 5
FDD 12-2 | SGBM13 | Feb 13 2016 3:40PM | Feb 15 2016 8:24PM | 40.389 | 34.503 | 0.00 | 0.00 | -18.737 | 5.886 | 53.240 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5747.556 | T12-150 | 2436.3093 | 12+12+12+12+11 | 94.1 | 117.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 11 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 12-3 |  | Feb 24 2016 12:30PM | Feb 26 2016 9:10PM | 40.339 | 34.503 | 0.00 | 0.00 | -19.582 | 5.836 | 54.085 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5805.901 | T12-150 | 2458.2808 | 12+12+12+12+12 | 95.6 | 117.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 12-4 | SGBM26 | Feb 17 2016 8:30AM | Feb 18 2016 8:00PM | 40.356 | 34.503 | 0.00 | 0.00 | -13.715 | 5.853 | 48.218 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5400.796 | T12-150 | 2305.7618 | 12+12+12+12+11 | 85.2 | 108.0 | 14.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDD 12-5 | SGBM26 | Feb 20 2016 12:00PM | Feb 21 2016 12:30AM | 40.360 | 34.503 | 0.00 | 0.00 | -18.800 | 5.857 | 53.303 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5751.906 | T12-150 | 2437.9474 | 12+12+12+12+12+6 | 94.2 | 122.0 | 27.8 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDD 11-1 |  | Feb 26 2016 9:00AM | Feb 27 2016 8:10PM | 40.102 | 35.092 | 0.00 | 0.00 | -21.225 | 5.010 | 56.317 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5960.016 | T12-150 | 2516.3233 | 12+12+12+12+12+4 | 99.5 | 122.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 7 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDD 11-2 |  | Feb 16 2016 5:00PM | Feb 19 2016 7:00PM | 40.040 | 35.092 | 0.00 | 0.00 | -21.833 | 4.948 | 56.925 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6001.997 | T12-150 | 2532.1357 | 12+12+12+12+12 | 100.6 | 130.0 | 29.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 4
FDD 11-3 | SGBM26 | Feb 29 2016 1:00PM | Mar 1 2016 8:30PM | 40.097 | 35.092 | 0.00 | 0.00 | -22.309 | 5.005 | 57.401 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6034.864 | T12-150 | 2544.5155 | 12+12+12+12+12+4 | 101.4 | 115.0 | 13.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 7
FDD 11-4 | SGBM13 | Mar 17 2016 10:00AM | Mar 18 2016 6:45PM | 39.617 | 35.092 | 44.50 | 2.00 | 30.467 | 4.525 | 4.625 |  | 2.0 | 2.0 | 2.0 | 28T20 | 2390.787 | T12-150 | 1200.4616 | 12+12+129 | 8.2 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 11-5 | SGBM26 | Feb 22 2016 4:30PM | Feb 24 2016 7:00PM | 39.912 | 35.092 | 0.00 | 0.00 | -22.984 | 4.820 | 58.076 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6081.472 | T12-150 | 2562.0717 | 12+12+12+12+12+4 | 102.6 | 117.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-1 | SGBM26 | Mar 1 2016 11:00AM | Mar 2 2016 8:00PM | 40.570 | 36.102 | 0.00 | 0.00 | -22.278 | 4.468 | 58.380 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6102.462 | T12-150 | 2569.9787 | 12+12+12+12+12+5 | 103.2 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-2 | SGBM26 | Feb 22 2016 10:45AM | Feb 25 2016 7:10PM | 40.487 | 36.102 | 0.00 | 0.00 | -22.606 | 4.385 | 58.708 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6125.110 | T12-150 | 2578.5101 | 12+12+12+12+12+5 | 103.8 | 108.0 | 4.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-3 | SGBM26 | Mar 4 2016 8:30AM | Mar 5 2016 3:20PM | 40.535 | 36.102 | 0.00 | 0.00 | -22.152 | 4.433 | 58.254 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6093.762 | T12-150 | 2566.7015 | 12+12+12+12+12+5.8 | 103.0 | 135.0 | 31.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 12 14 15 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-4 | SGBM32 | Feb 22 2016 2:00PM | Feb 23 2016 10:55PM | 40.388 | 36.102 | 0.00 | 0.00 | -28.098 | 4.286 | 64.200 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6504.322 | T12-150 | 2721.3822 | 12+12+12+12+12 | 113.5 | 135.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-5 |  | Feb 27 2016 11:00AM | Feb 29 2016 8:50PM | 40.508 | 36.102 | 0.00 | 0.00 | -22.511 | 4.406 | 58.613 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6118.550 | T12-150 | 2576.0392 | 12+12+12+12+12+7 | 103.6 | 129.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | 3 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-1 | SGBM26 | Mar 24 2016 1:00PM | Apr 1 2016 8:50PM | 38.247 | 35.049 | 59.10 | 1.80 | -21.619 | 3.198 | 56.668 |  | 1.8 | 0.0 | 1.8 | 28T20 | 5984.252 | T12-150 | 2525.4518 | 12+12+12+12+12+5 | 100.2 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-2 | SGBM13 | Apr 6 2016 5:20PM | Apr 8 2016 8:40PM | 38.203 | 35.049 | 57.80 | 1.70 | -20.084 | 3.154 | 55.133 |  | 1.7 | 1.7 | 1.7 | 28T20 | 5878.263 | T12-150 | 2485.5325 | 12+12+12+12+12+2 | 97.4 | 114.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 13-3 | SGBM26 | Mar 17 2016 8:00PM | Mar 22 2016 6:39PM | 38.574 | 35.049 | 58.00 | 1.80 | -20.102 | 3.525 | 55.151 |  | 1.8 | 1.8 | 1.8 | 28T20 | 5879.506 | T12-150 | 2486.0007 | 12+12+12+12+2 | 97.5 | 105.0 | 7.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 6
FDA 13-4 | SGBM13 | Apr 10 2016 11:00AM | Apr 18 2016 8:00PM | 38.772 | 35.049 | 56.20 | 2.20 | -16.747 | 3.723 | 51.796 |  | 2.2 | 2.2 | 2.2 | 28T20 | 5647.850 | T12-150 | 2398.7662 | 12+12+12+12+12 | 91.5 | 114.0 | 19.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 13-5 | SGBM13 | Feb 20 2016 10:00AM | Feb 24 2016 9:50PM | 38.604 | 35.049 | 52.60 | 2.00 | -14.987 | 3.555 | 50.036 |  | 2.0 | 2.0 | 0.0 | 28T20 | 5526.326 | T12-150 | 2353.0138 | 12+12+12+12+8 | 88.4 | 117.0 | 32.3 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-6 |  | Feb 26 2016 3:50PM | Mar 1 2016 1:10PM | 38.591 | 35.049 | 55.10 | 1.90 | -17.482 | 3.542 | 52.531 |  | 1.9 | 1.6 | 1.9 | 28T20 | 5698.600 | T12-150 | 2417.8751 | 12+12+12+12+10 | 92.8 | 99.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 9 9
FDA 13-7 | SGBM26 | Apr 3 2016 11:40AM | Apr 4 2016 11:20PM | 38.733 | 35.049 | 56.50 | 2.00 | -18.801 | 3.684 | 53.850 |  | 2.0 | 2.0 | 2.0 | 28T20 | 5789.675 | T12-150 | 2452.1701 | 12+12+12+12+12 | 95.2 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-8 | SGBM26 | Mar 21 2016 2:20PM | Apr 1 2016 7:40PM | 38.545 | 35.049 | 52.20 | 1.90 | -14.809 | 3.496 | 49.858 |  | 1.9 | 1.9 | 1.9 | 28T20 | 5514.035 | T12-150 | 2348.3870 | 12+12+12+12+11 | 88.1 | 112.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 4
FDA 13-9 | SGBM32 | Mar 12 2016 8:30AM | Mar 16 2016 4:16PM | 38.441 | 35.049 | 49.75 | 1.95 | -12.289 | 3.392 | 47.338 |  | 1.9 | 1.9 | 1.9 | 28T20 | 5340.034 | T12-150 | 2282.8927 | 12+12+12+12+4.8 | 83.7 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 12-1 | SGBM26 | Mar 11 2016 5:00PM | Mar 14 2016 6:50PM | 38.580 | 35.025 | 48.26 | 1.74 | -10.182 | 3.555 | 45.207 |  | 1.7 | 1.6 | 1.7 | 28T20 | 5192.893 | T12-150 | 2227.5230 | 12+12+12+12+3.5 | 79.9 | 84.0 | 5.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 3
FDA 12-2 | SGBM13 | Feb 5 2016 11:00AM | Feb 19 2016 11:35PM | 38.984 | 35.025 | 49.65 | 2.65 | -12.610 | 3.959 | 47.635 |  | 2.1 | 2.0 | 2.6 | 28T20 | 5360.541 | T12-150 | 2290.6108 | 12+12+12+12+5 | 84.2 | 104.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 5 9 9 9 9 9 9 9 9 9 9 9
FDA 12-3 | SGBM13 | Feb 28 2016 1:00PM | Mar 3 2016 1:45PM | 38.745 | 35.025 | 47.80 | 2.20 | -10.239 | 3.720 | 45.264 |  | 2.2 | 0.0 | 2.2 | 28T20 | 5196.829 | T12-150 | 2229.0038 | 12+12+12+12+3 | 80.0 | 108.0 | 35.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 12-4 | SGBM26 | Mar 7 2016 8:30AM | Mar 9 2016 1:31AM | 39.025 | 35.025 | 53.70 | 1.70 | -15.401 | 4.000 | 50.426 |  | 1.7 | 1.7 | 1.7 | 28T20 | 5553.254 | T12-150 | 2363.1514 | 12+12+12+12+9 | 89.1 | 108.0 | 21.2 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 12-5 | SGBM26 | Mar 16 2016 1:30PM | Mar 17 2016 4:30PM | 38.977 | 35.025 | 49.90 | 1.90 | -11.939 | 3.952 | 46.964 |  | 1.9 | 1.9 | 0.0 | 28T20 | 5314.210 | T12-150 | 2273.1740 | 12+12+12+12+4.5 | 83.0 | 90.0 | 8.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 12-6 | SGBM26 | Mar 8 2016 6:40PM | Mar 12 2016 5:17PM | 38.720 | 35.025 | 48.80 | 1.70 | -10.866 | 3.695 | 45.891 |  | 1.7 | 1.7 | 1.7 | 28T20 | 5240.122 | T12-150 | 2245.2937 | 12+12+12+12+6 | 81.1 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 12-7 | SGBM13 | Feb 23 2016 4:15PM | Feb 27 2016 1:00AM | 39.043 | 35.025 | 0.00 | 0.00 | -25.039 | 4.018 | 60.064 |  | 0.0 | 0.0 | 0.0 | 28T20 | 6218.739 | T12-150 | 2613.7821 | 12+12+12+12+12+9 | 106.2 | 149.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 12-8 | SGBM13 | Feb 6 2016 11:00AM | Feb 16 2016 1:50PM | 39.193 | 35.025 | 50.85 | 2.25 | -13.204 | 4.168 | 48.229 |  | 2.3 | 2.3 | 2.3 | 28T20 | 5401.556 | T12-150 | 2306.0476 | 12+12+12+12+6.5 | 85.2 | 117.0 | -85.2 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 12-9 | SGBM13 | Jan 31 2016 2:20PM | Feb 4 2016 10:10PM | 39.082 | 35.025 | 49.50,53.60 | 2.00,1.60 | -15.252 | 4.057 | 50.277 |  | 3.6 | 3.6 | 3.5 | 28T20 | 5542.966 | T12-150 | 2359.2783 | 12+12+12+12+12 | 88.9 | 126.0 | 41.8 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 11-1 | SGBM32 | Mar 11 2016 8:30AM | Mar 12 2016 5:30PM | 39.688 | 34.635 | 0.00 | 0.00 | -6.547 | 5.053 | 41.182 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4914.975 | T12-150 | 2122.9855 | 12+12+12+12 | 72.8 | 81.0 | 8.2 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDA 11-2 | SGBM32 | Mar 4 2016 8:30PM | Mar 5 2016 10:45PM | 39.813 | 34.635 | 0.00 | 0.00 | -6.437 | 5.178 | 41.072 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4907.379 | T12-150 | 2120.1294 | 12+12+12+12 | 72.6 | 90.0 | 24.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 11-1 | SGBM32 | Mar 11 2016 8:30AM | Mar 12 2016 5:30PM | 39.688 | 34.635 | 0.00 | 0.00 | -6.547 | 5.053 | 41.182 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4914.975 | T12-150 | 2122.9855 | 12+12+12+12+12 | 72.8 | 81.0 | 11.3 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDA 11-4 | SGBM13 | Mar 17 2016 10:00AM | Mar 18 2016 6:30PM | 39.617 | 34.635 | 44.50 | 2.00 | -6.033 | 4.982 | 40.668 |  | 2.0 | 2.0 | 2.0 | 28T20 | 4879.484 | T12-150 | 2109.6406 | 12+12+12+9 | 71.9 | 81.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 10 | 9 9 9 9 9 9 9 9 9
FDA 11-5 | SGBM32 | Mar 7 2016 4:45PM | Mar 8 2016 6:10PM | 39.555 | 34.635 | 0.00 | 0.00 | -7.094 | 4.920 | 41.729 |  | 0.0 | 0.0 | 0.0 | 28T20 | 4952.744 | T12-150 | 2137.1884 | 12+12+12+12+3.1 | 73.8 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 10-1 | SGBM32 | Feb 23 2016 1:45PM | Feb 26 2016 4:30PM | 40.184 | 35.351 | 38.50 | 2.75 | -0.169 | 4.833 | 35.520 |  | 2.8 | 2.5 | 2.8 | 28T20 | 4524.025 | T12-150 | 1976.0612 | 12+12+12+5 | 62.8 | 78.0 | -62.8 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 6 9 9
FDA 10-2 | SGBM26 | Mar 5 2016 8:30AM | Mar 7 2016 9:30PM | 39.981 | 35.351 | 0.00 | 0.00 | -20.669 | 4.630 | 56.020 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5939.509 | T12-150 | 2508.5993 | 12+12+12+12+12+4 | 99.0 | 123.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 10-3 | SGBM32 | Mar 12 2016 1:00PM | Mar 14 2016 9:54PM | 40.014 | 35.351 | 0.00 | 0.00 | -21.171 | 4.663 | 56.522 |  | 0.0 | 0.0 | 0.0 | 28T20 | 5974.171 | T12-150 | 2521.6547 | 12+12+12+12+12+4 | 99.9 | 104.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 5
FDA 10-4 | SGBM32 | Mar 8 2016 3:15PM | Mar 10 2016 9:00PM | 40.043 | 35.351 | 54.80 | 2.70 | -9.143 | 4.692 | 44.494 |  | 2.7 | 2.5 | 2.7 | 28T20 | 5143.662 | T12-150 | 2209.0004 | 12+12+12+12+10 | 78.6 | 122.0 | 37.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 10-5 | SGBM32 | Mar 1 2016 4:00PM | Mar 3 2016 6:50PM | 39.818 | 35.351 | 55.00 | 2.30 | -16.826 | 4.467 | 52.177 |  | 2.3 | 0.0 | 2.3 | 28T20 | 5674.157 | T12-150 | 2408.6715 | 12+12+12+12+12+3 | 92.2 | 126.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9

## 2200
Summary List for 18916521-MRT-V1 Spur Line
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
FDA 15-1 | SGBM26 | Apr 5 2016 12:00PM | Apr 7 2016 4:20AM | 42.067 | 36.975 | 0.00 | 0.00 | -14.252 | 5.092 | 51.227 |  | 0.0 | 0.0 | 0.0 | 44T40 | 60463.502 | T16-150 | 6356.5542 | 12+12+12+12+12+4 | 194.8 | 194.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 15-2 | SGBM26 | Mar 29 2016 4:30PM | Apr 3 2016 6:00PM | 41.892 | 36.975 | 0.00 | 0.00 | 28.782 | 4.917 | 8.193 |  | 0.0 | 0.0 | 0.0 | 44T40 | 41774.696 | T16-150 | 3409.5086 | 12+12+12+12+8 | 31.1 | 198.0 | -3.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 15-3 | SGBM26 | Apr 11 2016 11:00AM | Apr 12 2016 11:42PM | 41.898 | 36.975 | 0.00 | 0.00 | 2.746 | 4.923 | 34.229 |  | 0.0 | 0.0 | 0.0 | 44T40 | 53081.610 | T16-150 | 5179.6592 | 12+12+12+12+12+4 | 130.1 | 207.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 15-4 | SGBM26 | Apr 8 2016 11:00AM | Apr 9 2016 8:35PM | 41.894 | 36.975 | 0.00 | 0.00 | 38.060 | 4.919 | -1.085 |  | 0.0 | 0.0 | 0.0 | 44T40 | 37745.446 | T16-150 | 2329.8469 | 12+12+12+12+12+4 | -4.1 | 189.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-1 | SGBM13 | Mar 13 2016 10:00AM | Mar 20 2016 5:10AM | 38.731 | 35.475 | 52.60 | 6.50 | -19.489 | 3.256 | 54.964 |  | 6.5 | 6.5 | 6.5 | 44T40 + 44T40 | 0.000 | T16-150 | 6615.6289 | 12+12+12+12+12+7.3 | 209.0 | 225.0 | 3.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-2 | SGBM13 | Feb 29 2016 2:00PM | Mar 11 2016 5:30PM | 38.616 | 35.475 | 50.90 | 6.60 | -17.864 | 3.141 | 53.339 |  | 6.4 | 6.4 | 6.6 | 44T40 + 44T40 | 0.000 | T16-150 | 6502.9630 | 12+12+12+12+12+6 | 202.8 | 216.0 | 6.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-3 |  | Mar 21 2016 3:15PM | Mar 3 2016 11:00AM | 38.672 | 35.475 | 52.00 | 6.50 | -18.635 | 3.197 | 54.110 |  | 6.5 | 6.5 | 6.5 | 44T40 + 44T40 | 0.000 | T16-150 | 6556.4172 | 12+12+12+12+12+8.8 | 205.7 | 234.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 6 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-4 | SGBM13 | Mar 29 2016 9:00AM | May 2 2016 10:10AM | 38.638 | 35.475 | 52.30 | 7.35 | -19.765 | 3.163 | 55.240 |  | 7.3 | 7.3 | 7.4 | 44T40 + 44T40 | 0.000 | T16-150 | 6634.7661 | 12+12+12+12+12+10 | 210.0 | 249.0 | 17.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 8 19 20 21 22 23 24 25 26 27 28 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 6