## 1200
Summary List for 18916523-MRT-v201
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DD18-1 | SGBM13 | Aug 29 2016 6:30PM | Sep 22 2016 7:35PM | 38.855 | 32.575 | 3.90,7.50 | 3.60,3.00 | 29.751 | 6.280 | 2.824 |  | 6.6 | 0.0 | 3.1 | 18T20 | 1190.664 | T12-200 | 704.8754 | 4.5 | 3.2 | 6.0 | -100.0 | G40T2 | C570008586 | 6
DD18-2 | SGBM12 | Aug 22 2016 1:30PM | Aug 27 2016 6:40PM | 38.962 | 32.575 | 4.70 | 5.82 | 30.580 | 6.387 | 1.995 |  | 5.8 | 0.0 | 5.8 | 18T20 | 1153.866 | T12-200 | 710.2276 | 4 | 2.3 | 6.0 | -100.0 | G40T2 | C570008217 | 6
DD18-3 | SGBM12 | Sep 6 2016 1:30PM | Sep 15 2016 6:20PM | 38.881 | 32.575 | 4.60 | 5.90 | 29.505 | 6.306 | 3.070 |  | 5.9 | 0.0 | 3.0 | 18T20 | 1201.583 | T12-200 | 705.1670 | 5 | 3.5 | 7.0 | 100.9 | G40T2 | C570008460 | 7
DD18-4 | SGBM13 | Sep 24 2016 9:30AM | Oct 2 2016 12:45AM | 38.875 | 32.575 | 4.10 | 6.20 | 30.735 | 6.300 | 1.840 |  | 6.2 | 0.0 | 3.0 | 18T20 | 1146.986 | T12-200 | 713.0362 | 4.5 | 2.1 | 6.0 | -100.0 | G40T2 | C570008706 | 6
DD17-1 | SGBM12 | Sep 4 2016 10:30AM | Sep 7 2016 11:30AM | 38.825 | 32.575 | 7.70 | 3.11 | 30.085 | 6.250 | 2.490 |  | 3.1 | 0.0 | 3.1 | 18T20 | 1175.838 | T12-200 | 705.5826 | 4.5 | 2.8 | 6.0 | 52.0 | G40T2 | c570008371 | 6
DD17-2 | SGBM12 | Aug 27 2016 6:45PM | Aug 29 2016 10:55PM | 39.005 | 32.575 | 7.10 | 3.12 | 29.650 | 6.430 | 2.925 |  | 3.1 | 0.0 | 3.1 | 18T20 | 1195.147 | T12-200 | 704.9243 | 4.8 | 3.3 | 5.0 | 51.1 | G40T2 | C500065060 | 5
DD17-3 | SGBM12 | Sep 9 2016 11:40AM | Sep 17 2016 10:50PM | 38.760 | 32.575 | 7.00 | 3.60 | 29.401 | 6.185 | 3.174 |  | 3.6 | 0.0 | 3.6 | 18T20 | 1206.200 | T12-200 | 705.4528 | 4.5 | 3.6 | 5.0 | 39.3 | G40T2 | C570008490 | 5
DD17-4 | SGBM12 | Sep 19 2016 10:30AM | Sep 21 2016 10:20PM | 38.648 | 32.575 | 8.80 | 3.20 | 28.015 | 6.073 | 4.560 |  | 3.2 | 0.0 | 3.2 | 18T20 | 1267.721 | T12-200 | 714.9822 | 6 | 5.2 | 8.0 | 48.9 | G40T2 | c570008577 | 8
DD16-1 | SGBM31 | Sep 15 2016 4:20PM | Sep 17 2016 9:50PM | 38.550 | 32.575 | 10.10 | 3.00 | 26.540 | 5.975 | 6.035 |  | 3.0 | 0.0 | 3.0 | 18T20 | 1333.194 | T12-200 | 731.0636 | 6.045+1 | 6.8 | 9.0 | -100.0 | G40T2 | C570008485 | 9
DD16-2 | SGBM12 | Sep 9 2016 2:45PM | Sep 13 2016 8:30PM | 38.520 | 32.575 | 9.40 | 3.00 | 28.046 | 5.945 | 4.529 |  | 3.0 | 0.0 | 3.0 | 18T20 | 1266.345 | T12-200 | 714.6903 | 5.5+1 | 5.1 | 8.0 | 1.9 | G40T2 | C570008437 | 8
DD16-3 | SGBM31 | Sep 19 2016 1:00PM | Sep 22 2016 9:00PM | 38.426 | 32.575 | 11.20 | 3.00 | 25.203 | 5.851 | 7.372 |  | 3.0 | 0.0 | 3.0 | 18T20 | 1392.540 | T12-200 | 747.9191 | 8 | 8.3 | 10.0 | 19.8 | G40T2 | C570008588 | 10
DD16-4 | SGBM31 | Sep 24 2016 1:45PM |  | 38.491 | 32.575 | 11.90 | 3.10 | 25.726 | 5.916 | 6.849 |  | 3.1 | 0.0 | 3.1 | 18T20 | 1369.325 | T12-200 | 741.1542 | 9 | 7.7 | 0.0 | -100.0 | G40T2
DD11-1 |  |  |  | 0.000 | 31.875 |  |  | 0.000 | 0.000 | 31.875 |  | 0.0 | 0.0 | 0.0 | 20T20 | 2755.755 | T12-200 | 1111.7370 |  | 36.1 | 0.0 | 0.0 | G40T2(ice)
DD11-2 |  |  |  | 0.000 | 31.875 |  |  | 0.000 | 0.000 | 31.875 |  | 0.0 | 0.0 | 0.0 | 20T20 | 2755.755 | T12-200 | 1111.7370 |  | 36.1 | 0.0 | 0.0 | G40T2(ice)
DD11-3 |  |  |  | 0.000 | 31.875 |  |  | 0.000 | 0.000 | 31.875 |  | 0.0 | 0.0 | 0.0 | 20T20 | 2755.755 | T12-200 | 1111.7370 |  | 36.1 | 0.0 | 0.0 | G40T2(ice)
DD11-4 |  |  |  | 0.000 | 31.875 |  |  | 0.000 | 0.000 | 31.875 |  | 0.0 | 0.0 | 0.0 | 20T20 | 2755.755 | T12-200 | 1111.7370 |  | 36.1 | 0.0 | 0.0 | G40T2(ice)
DD12-1 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD12-2 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD12-3 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD12-4 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD13-1 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD13-2 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD13-3 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD13-4 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD14-1 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD14-2 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD14-3 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD14-4 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD15-1 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD15-2 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD15-3 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
DD15-4 |  |  |  | 0.000 | 32.575 |  |  | 0.000 | 0.000 | 32.575 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2511.251 | T12-200 | 1122.4141 |  | 36.8 | 0.0 | 0.0 | G40T2(ice)
SBN14-1 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN14-2 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN14-3 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN14-4 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS14-1 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS14-2 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS14-3 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS14-4 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN15-1 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN15-2 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN15-3 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN15-4 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS15-1 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS15-2 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS15-3 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS15-4 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBN16-1 |  |  |  | 0.000 | 34.275 |  |  | 0.000 | 0.000 | 34.275 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2586.711 | T12-200 | 1148.3578 |  | 38.8 | 0.0 | 0.0 | G40T2(ice)
SBN16-2 |  |  |  | 0.000 | 34.275 |  |  | 0.000 | 0.000 | 34.275 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2586.711 | T12-200 | 1148.3578 |  | 38.8 | 0.0 | 0.0 | G40T2(ice)
SBN16-3 |  |  |  | 0.000 | 34.275 |  |  | 0.000 | 0.000 | 34.275 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2586.711 | T12-200 | 1148.3578 |  | 38.8 | 0.0 | 0.0 | G40T2(ice)
SBN16-4 |  |  |  | 0.000 | 34.275 |  |  | 0.000 | 0.000 | 34.275 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2586.711 | T12-200 | 1148.3578 |  | 38.8 | 0.0 | 0.0 | G40T2(ice)
SBS16-1 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS16-2 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS16-3 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)
SBS16-4 |  |  |  | 0.000 | 34.475 |  |  | 0.000 | 0.000 | 34.475 |  | 0.0 | 0.0 | 0.0 | 18T20 | 2595.588 | T12-200 | 1151.4112 |  | 39.0 | 0.0 | 0.0 | G40T2(ice)

## 1350
Summary List for 18916523-MRT-v201
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
DD20-1 | SGBM31 | Aug 29 2016 6:20PM | Sep 1 2016 8:40PM | 39.172 | 32.275 | 15.80 | 2.72 | 23.261 | 6.897 | 9.014 |  | 2.7 | 0.0 | 2.7 | 22T20 | 1953.832 | T12-200 | 874.8073 | 11.3 | 12.9 | 21.0 | -18.1 | G40T2 | C570008310 C570008310 | 12 9
DD20-2 | SGBM31 | Sep 4 2016 9:45AM | Sep 6 2016 3:50PM | 39.240 | 32.275 | 15.80 | 2.71 | 21.765 | 6.965 | 10.510 |  | 2.7 | 0.0 | 2.7 | 22T20 | 2034.993 | T12-200 | 898.7224 | 11.5 | 15.0 | 19.0 | -100.0 | G40T2 | C570008362 C570008364 | 12 7
DD20-3 | SGBM31 | Aug 24 2016 4:00PM | Aug 27 2016 11:10PM | 39.168 | 32.275 | 15.90 | 2.72 | 22.165 | 6.893 | 10.110 |  | 2.7 | 0.0 | 2.7 | 22T20 | 2013.292 | T12-200 | 892.2643 | 11.6 | 14.5 | 20.0 | -100.0 | G40T2 | C570008229 C570008230 | 12 8
DD20-4 | SGBM31 | Aug 19 2016 3:20PM | Aug 22 2016 10:50PM | 39.003 | 32.275 | 15.70 | 2.90 | 21.839 | 6.728 | 10.436 |  | 2.9 | 0.0 | 2.7 | 22T20 | 2030.978 | T12-200 | 897.5248 | 12 | 14.9 | 19.0 | -100.0 | G40T2 | c570008122 c570008123 c570008124 | 8 8 3
DD19-1 | SGBM31 | Sep 1 2016 5:30PM | Sep 3 2016 8:30PM | 39.152 | 32.275 | 13.30 | 3.82 | 22.973 | 6.877 | 9.302 |  | 3.8 | 0.0 | 3.8 | 22T20 | 1969.456 | T12-200 | 879.3560 | 10.3 | 13.3 | 18.0 | -100.0 | G40T2 | C570008337 C570008338 | 9 9
DD19-2 | SGBM31 | Aug 22 2016 4:30AM | Aug 24 2016 8:10PM | 39.214 | 32.275 | 13.60 | 3.80 | 22.773 | 6.939 | 9.502 |  | 3.8 | 0.0 | 3.8 | 22T20 | 1980.307 | T12-200 | 882.5322 | 12 | 13.6 | 17.0 | 25.0 | G40T2 | c570008148 c570008149 | 10 7
DD19-3 | SGBM31 | Aug 27 2016 12:00PM | Aug 29 2016 11:00PM | 39.146 | 32.275 | 13.50 | 2.60 | 24.122 | 6.871 | 8.153 |  | 2.6 | 0.0 | 2.6 | 22T20 | 1907.121 | T12-200 | 861.4101 | 9.3 | 11.7 | 15.0 | 28.4 | G40T2 | C590065060 C590065970 C590065972 | 2 7 6
DD19-4 | SGBM31 | Sep 6 2016 12:12PM | Sep 10 2016 7:20PM | 39.050 | 32.275 | 10.40 | 3.81 | 27.070 | 6.775 | 5.205 |  | 3.8 | 0.0 | 3.8 | 22T20 | 1747.186 | T12-200 | 819.6395 | 7.3 | 7.5 | 12.0 | -100.0 | G40T2 | c570008430 c570008431 | 7 5
CBP1 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP2 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP3 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP4 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP5 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP6 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP7 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP8 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP9 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP10 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP11 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP12 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP13 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP14 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP15 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP16 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP17 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP18 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP19 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP20 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP21 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP22 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP23 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP24 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP25 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP26 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP27 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP28 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP29 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP30 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP31 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP32 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP33 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP34 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP35 | SGBM02 | Sep 5 2016 4:00PM | Sep 9 2016 7:15PM | 43.546 | 42.075 | 16.20 | 3.20 | 25.114 | 1.471 | 16.961 |  | 3.2 | 0.0 | 3.2 | 25T25 | 4886.005 | T10-125 | 1112.9553 | 12+7 | 24.3 | 30.0 | 23.6 | G40T2 | C570008413 C570008414 C570008417 | 12 9 9
CBP36 | SGBM02 | Sep 15 2016 8:00PM | Sep 19 2016 9:45PM | 43.425 | 42.075 | 16.30 | 3.10 | 25.128 | 1.350 | 16.947 |  | 3.1 | 0.0 | 3.1 | 25T25 | 4884.656 | T10-125 | 1112.6884 | 12+7.5 | 24.3 | 30.0 | -100.0 | G40T2 | C570008511 C570008512 C570008515 | 10 10 10
CBP37 | SGBM02 | Sep 21 2016 9:30AM | Sep 22 2016 9:50PM | 43.626 | 42.075 | 15.90 | 3.00 | 26.462 | 1.551 | 15.613 |  | 3.0 | 0.0 | 3.0 | 25T25 | 4756.125 | T10-125 | 1087.3032 | 12+6.7 | 22.4 | 31.0 | -100.0 | G40T2 | C570008589 C570008590 C570008591 | 10 10 11
CBP38 | SGBM02 | Sep 24 2016 2:00PM | Sep 26 2016 8:30PM | 43.409 | 42.075 | 16.81 | 2.99 | 24.963 | 1.334 | 17.112 |  | 3.0 | 0.0 | 3.0 | 25T25 | 4900.554 | T10-125 | 1115.8338 | 12+7.4 | 24.5 | 31.0 | 26.5 | G40T2 | C570008621 C570008622 C570008623 | 10 10 11
CBP39 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP40 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP41 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP42 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP43 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP44 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP45 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP46 | SGBM02 | Sep 22 2016 5:30PM | Sep 24 2016 9:45PM | 43.387 | 42.075 | 16.40 | 3.31 | 24.877 | 1.312 | 17.198 |  | 3.3 | 0.0 | 3.3 | 25T25 | 4908.840 | T10-125 | 1117.4735 | 12+7 | 24.6 | 31.0 | -100.0 | G40T2 | C570008613 C570008614 C570008615 | 10 11 10
CBP47 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP48 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP49 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP50 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP51 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP52 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP53 | SGBM02 | Oct 1 2016 8:00PM | Oct 5 2016 1:30PM | 43.754 | 42.075 | 15.65 | 3.16 | 27.445 | 1.679 | 14.630 |  | 3.2 | 0.0 | 3.1 | 25T25 | 4661.413 | T10-125 | 1068.6543 | 12+6.7 | 20.9 | 31.0 | 32.5 | G40T2 | C570008741 C570008745 C570008749 | 10 10 11
CBP54 | SGBM02 | Sep 17 2016 4:00PM | Sep 21 2016 8:15PM | 43.487 | 42.075 | 15.50 | 3.00 | 26.165 | 1.412 | 15.910 |  | 3.0 | 0.0 | 3.0 | 25T25 | 4784.741 | T10-125 | 1092.9479 | 12+6.6 | 22.8 | 31.0 | -100.0 | G40T2 | C570008572 C570008575 C570008578 | 10 10 11
CBP55 | SGBM02 | Sep 9 2016 12:00PM | Sep 15 2016 4:00PM | 43.479 | 42.075 | 15.30 | 3.20 | 26.097 | 1.404 | 15.978 |  | 3.2 | 0.0 | 3.2 | 25T25 | 4791.293 | T10-125 | 1094.2408 | 12+6.5 | 22.9 | 30.0 | -100.0 | G40T2 | C570008455 C570008456 C570008458 | 10 12 8
CBP56 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP57 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP58 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP59 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP60 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP61 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP62 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP63 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP64 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP65 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP66 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP67 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP68 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP69 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP70 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP71 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP72 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP73 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP74 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP75 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP76 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP77 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP78 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP79 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP80 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP81 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP82 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP83 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP84 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP85 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP86 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP87 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP88 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP89 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP90 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP91 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP92 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP93 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP94 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP95 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP96 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP97 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP98 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP99 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP100 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP101 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP102 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP103 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP104 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP105 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP106 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP107 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP108 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP109 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP110 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP111 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP112 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP113 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP114 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP115 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP116 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP117 | SGBM10 | Sep 28 2016 6:50PM | Oct 2 2016 2:45AM | 44.213 | 42.075 | 17.70 | 3.00 | 25.980 | 2.138 | 16.095 |  | 3.0 | 0.0 | 3.0 | 25T25 | 4802.566 | T10-125 | 1096.4662 | 12+8.5 | 23.0 | 32.0 | 27.8 | G40T2 | C570008714 C570008716 C570008720 | 10 10 12
CBP118 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP119 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP120 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP121 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP122 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP123 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP124 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP125 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP126 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP127 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
CBP128 |  |  |  | 0.000 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | 7305.739 | T10-125 | 1596.6525 |  | 60.2 | 0.0 | 0.0 | G40T2
DD21-1 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD21-2 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD21-3 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD21-4 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD22-1 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD22-2 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD22-3 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)
DD22-4 |  |  |  | 0.000 | 32.275 |  |  | 0.000 | 0.000 | 32.275 |  | 0.0 | 0.0 | 0.0 | 22T20 | 3215.787 | T12-200 | 1269.7918 |  | 46.2 | 0.0 | 0.0 | G40T2(ice)

## 1500
Summary List for 18916523-MRT-v201
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
SB13-1 |  |  |  | 0.000 | 34.175 |  |  | 0.000 | 0.000 | 34.175 |  | 0.0 | 0.0 | 0.0 | 26T20 | 4114.644 | T12-175 | 1665.4374 |  | 60.4 | 0.0 | 0.0 | G40T2(ice)
SB13-2 |  |  |  | 0.000 | 34.175 |  |  | 0.000 | 0.000 | 34.175 |  | 0.0 | 0.0 | 0.0 | 26T20 | 4114.644 | T12-175 | 1665.4374 |  | 60.4 | 0.0 | 0.0 | G40T2(ice)
SB13-3 |  |  |  | 0.000 | 34.175 |  |  | 0.000 | 0.000 | 34.175 |  | 0.0 | 0.0 | 0.0 | 26T20 | 4114.644 | T12-175 | 1665.4374 |  | 60.4 | 0.0 | 0.0 | G40T2(ice)
SB13-4 |  |  |  | 0.000 | 34.175 |  |  | 0.000 | 0.000 | 34.175 |  | 0.0 | 0.0 | 0.0 | 26T20 | 4114.644 | T12-175 | 1665.4374 |  | 60.4 | 0.0 | 0.0 | G40T2(ice)