## 0
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
2/AO |  | Oct 8 2016 6:31PM |  | 66.560 | 65.85 | 0.00 | 0.00 | 66.560 | 0.710 | -0.710 |  | 0.0 | 0.0 | 0.0 | 12T16 | -13.453 | T10 - 150 | 0.0000 |  | 0.0 | 0.0 | 0.0 | G40T2

## 750
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
BP P9 |  |  |  | 0.000 | 68.35 |  |  | 0.000 | 0.000 | 68.350 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1522.472 | T10 - 150 | 0.0000 |  | 30.2 | 0.0 | 0.0 | G35T2
BP P12 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P16 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P18 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P21 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P22 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P24 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P27 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P28 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P29 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P30 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
BP P32 |  |  |  | 0.000 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1432.942 | T10 - 150 | 0.0000 |  | 28.1 | 0.0 | 0.0 | G35T2
4/AO |  | Oct 11 2016 8:30AM |  | 66.540 | 65.85 | 0.00 | 0.00 | 0.000 | 0.690 | 65.850 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1475.102 | T10 - 150 | 0.0000 |  | 29.1 | 0.0 | 0.0 | G40T2
6/AO |  |  |  | 0.000 | 65.85 |  |  | 0.000 | 0.000 | 65.850 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1475.102 | T10 - 150 | 0.0000 |  | 29.1 | 0.0 | 0.0 | G40T2
8/AO |  |  |  | 0.000 | 65.85 |  |  | 0.000 | 0.000 | 65.850 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1475.102 | T10 - 150 | 0.0000 |  | 29.1 | 0.0 | 0.0 | G40T2
11/AO |  |  |  | 0.000 | 64.65 |  |  | 0.000 | 0.000 | 64.650 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1452.364 | T10 - 150 | 0.0000 |  | 28.6 | 0.0 | 0.0 | G40T2
14-15/AO |  |  |  | 0.000 | 64.65 |  |  | 0.000 | 0.000 | 64.650 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1452.364 | T10 - 150 | 0.0000 |  | 28.6 | 0.0 | 0.0 | G40T2
17/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
20/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
22/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
25/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
26-27/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
28/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
29/AO |  |  |  | 0.000 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1486.944 | T10 - 150 | 0.0000 |  | 29.4 | 0.0 | 0.0 | G40T2
7/P1 |  |  |  | 0.000 | 68 |  |  | 0.000 | 0.000 | 68.000 |  | 0.0 | 0.0 | 0.0 | 12T16 | 1515.840 | T10 - 150 | 0.0000 |  | 30.0 | 0.0 | 0.0 | G40T2

## 1200
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
C1 |  | Jul 30 2016 11:00AM | Aug 8 2016 6:50PM | 71.780 | 70.793 | 11.80,14.70 | 1.80,2.20 | 55.461 | 0.987 | 15.332 |  | 3.8 | 0.0 | 3.8 | 24T32 | 8141.043 | 2T16 - 100 , T12 -175 | 0.0000 | 12+5.5 | 17.3 | 20.0 | 15.3 | G35T2 | c15002317 c150023179 | 10 10
C2 | SGBM05 | Aug 11 2016 2:10PM | Aug 17 2016 5:05PM | 71.641 | 71.15 | 14.70 | 2.20 | 56.870 | 0.491 | 14.280 |  | 2.2 | 0.0 | 2.2 | 24T32 | 7981.652 | 2T16 - 100 , T12 -175 | 0.0000 | 12+6.4 | 16.2 | 21.0 | 3.8 | G35T2 | C150023655 C150023663 | 12 9
C3 | SGBM05 | Aug 24 2016 7:45AM | Aug 27 2016 11:35AM | 71.780 | 71.507 | 14.00,16.80 | 1.80,2.10 | 53.950 | 0.273 | 17.557 |  | 3.9 | 0.0 | 2.1 | 24T32 | 8478.157 | 2T16 - 100 , T12 -175 | 0.0000 | 19 | 19.9 | 26.0 | 30.9 | G35T2 | C150024163 C150024164 C150024165 | 9 9 8
C4 |  | Sep 1 2016 11:30AM | Sep 7 2016 1:20PM | 71.930 | 71.863 | 14.00 | 2.20 | 56.670 | -71.863 | 15.193 |  | 2.2 | 0.0 | 2.2 | 24T32 | 8119.983 | 2T16 - 100 , T12 -175 | 0.0000 | 12+5.6 | 17.2 | 22.0 | 4.8 | G35T2 | C150024629 C150024634 | 12 10
C5 |  | Aug 18 2016 10:53AM | Aug 23 2016 5:05PM | 71.584 | 72.22 | 14.30,17.70 | 1.50,2.10 | 52.952 | -0.636 | 19.268 |  | 3.6 | 0.0 | 2.0 | 24T32 | 8737.394 | 2T16 - 100 , T12 -175 | 0.0000 | 12+9.3 | 21.8 | 24.0 | 10.1 | G35T2 | C150023956 C150023962 C150023965 | 8 8 8
C6 |  | Jul 26 2016 7:30AM | Aug 11 2016 11:20AM | 71.830 | 72.577 | 12.50,12.70,16.50 | 0.20,1.90,2.00 | 54.270 | -0.747 | 18.307 |  | 3.9 | 0.0 | 2.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 8+12 | 20.7 | 24.0 | 3.3 | G35T2 | 1 2 3 | 9 8 7
C7 |  | Aug 27 2016 4:45PM | Sep 3 2016 12:30PM | 71.620 | 72.934 | 15.70 | 2.20 | 55.134 | -72.934 | 17.800 |  | 2.2 | 0.0 | 2.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 12+7.9 | 20.1 | 26.0 | -15.6 | G35T2 | C150024476 C150024477 C150024480 | 9 8 9
C8 |  | Sep 5 2016 4:30PM | Sep 14 2016 10:56AM | 71.580 | 73.29 | 13.00 | 2.40 | 57.346 | -1.710 | 15.944 |  | 2.4 | 0.0 | 2.4 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 12+4.6 | 18.0 | 21.0 | 3.0 | G35T2 | C150024864 C150024865 | 12 9
C9 |  | Sep 21 2016 8:00AM | Oct 5 2016 4:35PM | 71.670 | 73.647 | 12.90,17.00 | 1.30,1.50 | 54.260 | -1.977 | 19.387 |  | 2.8 | 0.0 | 1.5 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 5+12+4.5 | 21.9 | 23.0 | 4.9 | G35T2 | C150025689 C150025689 | 12 11
C10 |  | Sep 20 2016 3:30PM | Sep 26 2016 3:40PM | 71.650 | 74.004 | 17.00 | 1.70 | 54.190 | -2.354 | 19.814 |  | 1.7 | 0.0 | 1.5 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 5+12+4.5 | 22.4 | 24.0 | 1.6 | G35T2 | C150025351 C150025352 | 12 12
C11 | SGBM05 | Aug 9 2016 7:30AM | Sep 5 2016 1:35PM | 71.860 | 74.175 | 16.60 | 2.00 | 53.860 | -2.315 | 20.315 |  | 1.4 | 0.0 | 2.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 3.6+12+4.6 | 23.0 | 26.0 | -21.7 | G35T2 | C150024519 C150024521 C150024522 | 9 9 8
C12 |  | Sep 8 2016 9:00AM | Sep 17 2016 6:10PM | 71.570 | 74.175 | 13.20,15.00,16.10 | 0.60,0.80,1.65 | 54.850 | -2.605 | 19.325 |  | 3.0 | 0.0 | 1.5 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 5+12+3.4 | 21.9 | 25.0 | 3.1 | G35T2 | C150025011 C150025013 C150025014 | 9 8 8
C13 |  | Sep 27 2016 7:00AM | Oct 1 2016 2:14PM | 71.570 | 74.175 | 13.00,15.00 | 1.00,1.50 | 56.110 | -2.605 | 18.065 |  | 2.5 | 0.0 | 1.5 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 5+12+2.5 | 20.4 | 21.0 | -20.4 | G35T2 | Pending Pending | 12 9
C14 |  |  |  | 0.000 | 74.175 |  |  | 0.000 | 0.000 | 74.175 |  | 0.0 | 0.0 | 0.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 |  | 83.9 | 0.0 | 0.0 | G35T2
C15 |  |  |  | 0.000 | 74.175 |  |  | 0.000 | 0.000 | 74.175 |  | 0.0 | 0.0 | 0.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 |  | 83.9 | 0.0 | 0.0 | G35T2
C16 |  |  |  | 0.000 | 74.175 |  |  | 0.000 | 0.000 | 74.175 |  | 0.0 | 0.0 | 0.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 |  | 83.9 | 0.0 | 0.0 | G35T2
C17 |  | Sep 15 2016 3:30PM | Sep 26 2016 3:00PM | 71.430 | 73.675 | 10.00,13.70 | 0.00,1.70 | 57.100 | -2.245 | 16.575 |  | 1.7 | 0.0 | 1.5 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 | 5+12 | 18.7 | 19.0 | 1.3 | G35T2 | C150025345 C150025346 | 10 9
C18 |  |  |  | 0.000 | 73.675 |  |  | 0.000 | 0.000 | 73.675 |  | 0.0 | 0.0 | 0.0 | 15X2T32 , 15T20 | 0.000 | 2T16 - 100 , T12 -175 | 0.0000 |  | 83.3 | 0.0 | 0.0 | G35T2
C19 |  |  |  | 0.000 | 73.675 |  |  | 0.000 | 0.000 | 73.675 |  | 0.0 | 0.0 | 0.0 | 24T32 | 16980.707 | 2T16 - 100 , T12 -175 | 0.0000 |  | 83.3 | 0.0 | -100.0 | G35T2
C20 |  |  |  | 0.000 | 73.675 |  |  | 0.000 | 0.000 | 73.675 |  | 0.0 | 0.0 | 0.0 | 24T32 | 16980.707 | 2T16 - 100 , T12 -175 | 0.0000 |  | 83.3 | 0.0 | 0.0 | G35T2
C21 | SGBM05 | Oct 11 2016 2:32PM |  | 0.000 | 73.175 | 0.00 | 10.00 | -10.000 | -73.175 | 83.175 |  | 0.0 | 0.0 | 0.0 | 24T32 | 18420.071 | 2T16 - 100 , T12 -175 | 0.0000 |  | 94.1 | 0.0 | -100.0 | G35T2
C22 | SGBM05 | Sep 23 2016 4:00PM |  | 71.500 | 73.175 | 0.00 | 0.00 | 68.240 | 0.000 | 4.935 |  | 0.0 | 0.0 | 1.5 | 24T32 | 6565.773 | 2T16 - 100 , T12 -175 | 0.0000 |  | 5.6 | 0.0 | -100.0 | G35T2
C23 |  |  |  | 0.000 | 73.175 |  |  | 0.000 | 0.000 | 73.175 |  | 0.0 | 0.0 | 0.0 | 24T32 | 16904.951 | 2T16 - 100 , T12 -175 | 0.0000 |  | 82.8 | 0.0 | 0.0 | G35T2
C24 |  |  |  | 0.000 | 73.175 |  |  | 0.000 | 0.000 | 73.175 |  | 0.0 | 0.0 | 0.0 | 24T32 | 16904.951 | 2T16 - 100 , T12 -175 | 0.0000 |  | 82.8 | 0.0 | 0.0 | G35T2
3/P-1 |  |  |  | 0.000 | 67.4 |  |  | 0.000 | 0.000 | 67.400 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3380.886 | T12 -250 | 0.0000 |  | 76.2 | 0.0 | 0.0 | G40T2
3/P-2 |  |  |  | 0.000 | 67.4 |  |  | 0.000 | 0.000 | 67.400 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3380.886 | T12 -250 | 0.0000 |  | 76.2 | 0.0 | 0.0 | G40T2
29/P |  |  |  | 0.000 | 64.55 |  |  | 0.000 | 0.000 | 64.550 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3275.465 | T12 -250 | 0.0000 |  | 73.0 | 0.0 | 0.0 | G40T2
30/P |  |  |  | 0.000 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3319.853 | T12 -250 | 0.0000 |  | 74.4 | 0.0 | 0.0 | G40T2
32/P |  |  |  | 0.000 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3319.853 | T12 -250 | 0.0000 |  | 74.4 | 0.0 | 0.0 | G40T2
29/N |  |  |  | 0.000 | 64.55 |  |  | 0.000 | 0.000 | 64.550 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3275.465 | T12 -250 | 0.0000 |  | 73.0 | 0.0 | 0.0 | G40T2
30/N |  |  |  | 0.000 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3319.853 | T12 -250 | 0.0000 |  | 74.4 | 0.0 | 0.0 | G40T2
32/N |  |  |  | 0.000 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | 3319.853 | T12 -250 | 0.0000 |  | 74.4 | 0.0 | 0.0 | G40T2

## 1350
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
1/H |  | Oct 11 2016 5:27PM |  | 0.000 | 63.175 | 0.00 | 0.00 | 0.000 | 0.000 | 63.175 |  | 0.0 | 0.0 | 0.0 | 18T20 | 4002.688 | T12 -250 | 0.0000 |  | 90.4 | 0.0 | 0.0 | G40T2
5/N |  |  |  | 0.000 | 67.9 |  |  | 0.000 | 0.000 | 67.900 |  | 0.0 | 0.0 | 0.0 | 18T20 | 4212.421 | T12 -250 | 0.0000 |  | 97.2 | 0.0 | 0.0 | G40T2
7/N |  |  |  | 0.000 | 67.9 |  |  | 0.000 | 0.000 | 67.900 |  | 0.0 | 0.0 | 0.0 | 18T20 | 4212.421 | T12 -250 | 0.0000 |  | 97.2 | 0.0 | 0.0 | G40T2

## 1500
Summary List for 1891652500-CK3
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
1/P |  |  |  | 0.000 | 67.8 |  |  | 0.000 | 0.000 | 67.800 |  | 0.0 | 0.0 | 0.0 | 23T20 | 5547.020 | T12 -250 | 0.0000 |  | 119.8 | 0.0 | 0.0 | G40T2
5/P-1 |  |  |  | 0.000 | 66.3 |  |  | 0.000 | 0.000 | 66.300 |  | 0.0 | 0.0 | 0.0 | 23T20 | 5461.943 | T12 -250 | 0.0000 |  | 117.2 | 0.0 | 0.0 | G40T2
5/P-2 |  |  |  | 0.000 | 66.3 |  |  | 0.000 | 0.000 | 66.300 |  | 0.0 | 0.0 | 0.0 | 23T20 | 5461.943 | T12 -250 | 0.0000 |  | 117.2 | 0.0 | 0.0 | G40T2