## 750
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
14 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
15 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
16 |  | Sep 24 2016 4:05PM | Sep 28 2016 7:07PM | 11.219 | 9.875 | 13.00,18.10 | 0.70,7.10 | -10.557 | 1.344 | 20.432 | 1.6,2.9,1.1,0.4,1.9 | 7.8 | 0.0 | 0.7 | 12T16 | 0.000 | R8-175 | 281.2788 | 12 | 9.0 | 16.0 | 77.2 | 40 TREMIE 2 | 2436995 2436996 | 8 8
19 |  | Aug 22 2016 6:33PM | Aug 23 2016 9:55PM | 11.230 | 6.275 | 12.80 | 4.10 | -4.926 | 1.655 | 11.201 |  | 4.1 | 0.0 | 3.7 | 12T16 | 439.613 | R8-175 | 239.9814 | 16.8 | 4.9 | 12.0 | 61.6 | 40 TREMIE 2 | 2412829 2412832 | 8 4
20 |  | Sep 6 2016 7:00AM | Sep 8 2016 3:18PM | 11.158 | 6.275 | 14.50 | 7.30 | -6.008 | 1.583 | 12.283 |  | 7.3 | 0.0 | 2.9 | 12T16 | 460.114 | R8-175 | 244.7207 | 12 | 5.4 | 8.0 | 1.1 | 40 TREMIE 2 | 2418596 | 8
21 |  | Sep 14 2016 4:33PM | Sep 19 2016 8:15PM | 11.138 | 6.275 | 15.60 | 5.10 | -6.653 | 1.563 | 12.928 |  | 5.1 | 0.0 | 2.9 | 12T16 | 472.336 | R8-175 | 247.5661 | 12 | 5.7 | 9.0 | 3.3 | 40 TREMIE 2 | Pending | 9
22 |  | Sep 22 2016 8:25AM | Sep 23 2016 10:50AM | 11.101 | 6.275 | 14.70 | 4.20 | -5.750 | 4.826 | 12.025 |  | 4.2 | 0.0 | 2.9 | 12T16 | 455.226 | R8-175 | 243.5864 | 12 | 5.3 | 10.0 | 4.7 | 40 TREMIE 2 | 2430076 | 10
23 |  | Sep 26 2016 7:30AM | Sep 30 2016 4:50PM | 11.101 | 6.275 | 19.00 | 18.20 | -15.921 | 4.826 | 22.196 |  | 18.2 | 0.0 | 2.9 | 12T16 | 647.946 | R8-175 | 289.2940 | 12 | 9.8 | 18.0 | -100.0 | 40 TREMIE 2 | 2437177 2437178 | 9 9
24 | SGBM19 | Oct 8 2016 3:15PM |  | 11.051 | 6.275 | 10.70,24.20 | 6.70,2.70 | -14.593 | 4.776 | 20.868 | 1.0,7.0,0.3,1.9,6.8,7.5,1.2 | 9.4 | 0.0 | 2.9 | 12T16 | 622.783 | R8-175 | 283.2579 |  | 9.2 | 0.0 | -9.2 | 40 TREMIE 2
25 |  | Oct 4 2016 3:23PM | Oct 7 2016 9:00PM | 11.125 | 6.275 | 29.90 | 9.80 | -22.432 | 4.850 | 28.707 |  | 9.8 | 0.0 | 2.9 | 12T16 | 771.316 | R8-175 | 319.0117 | 12 | 12.7 | 25.0 | 97.1 | 40 TREMIE 2 | 2437696 2437697 2437705 2437707 | 9 9 3 4
26 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
27 |  | Sep 21 2016 10:38AM | Sep 21 2016 8:40PM | 11.156 | 9.875 | 11.30 | 5.80 | -2.265 | 1.281 | 12.140 |  | 5.8 | 0.0 | 2.9 | 12T16 | 457.405 | R8-175 | 244.0917 | 12 | 5.4 | 9.0 | -100.0 | 40 TREMIE 2 | 2429978 | 9
28 |  | Oct 3 2016 7:30AM | Oct 4 2016 4:52PM | 9.875 | 9.875 | 16.80 | 6.20 | -8.739 | 0.000 | 18.614 |  | 6.2 | 0.0 | 2.9 | 12T16 | 580.074 | R8-175 | 273.0433 | 12 | 8.2 | 13.0 | 4.8 | 40 TREMIE 2 | 2437440 2437445 | 9 4
29 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 414.488 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
30 |  | Sep 24 2016 7:40AM | Sep 24 2016 8:10PM | 11.111 | 9.875 | 11.40 | 2.40 | -1.002 | 1.236 | 10.877 |  | 2.4 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 238.5719 | 12 | 4.8 | 9.0 | 87.3 | 40 TREMIE 2 | 2430205 | 9
31 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
32 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
62 |  | Oct 7 2016 10:35AM | Oct 8 2016 7:25PM | 7.743 | 6.275 | 10.00 | 4.40 | -3.543 | 1.468 | 9.818 |  | 4.4 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 234.0051 | 12 | 4.3 | 10.5 | -100.0 | 40 TREMIE 2 | 2437772 | 10.5
63 | SGBM18 | Oct 11 2016 10:25AM |  | 7.728 | 6.275 | 9.00 | 0.50 | -0.756 | 1.453 | 7.031 |  | 0.5 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 222.4474 |  | 3.1 | 0.0 | -100.0 | 40 TREMIE 2
64 |  | Oct 9 2016 7:30AM | Oct 10 2016 5:13PM | 7.662 | 6.275 | 13.80 | 6.20 | -7.696 | 1.387 | 13.971 |  | 6.2 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 252.1929 | 12 | 6.2 | 9.5 | 53.9 | 40 TREMIE 2 | 2437830 | 9.5
66 | SGBM01 | Aug 24 2016 7:00PM | Sep 1 2016 11:05AM | 11.278 | 9.875 | 22.90 | 1.80 | -12.462 | 1.403 | 22.337 |  | 1.8 | 0.0 | 1.6 | 12T16 | 0.000 | R8-175 | 289.9355 | 12 | 9.9 | 21.0 | -8.8 | 40 TREMIE 2 | 2418002 2418003 2418021 | 9 7 5
67 |  | Sep 19 2016 5:30PM | Sep 21 2016 11:32AM | 11.075 | 9.875 | 20.90,29.60 | 1.10,7.50 | -19.293 | 1.200 | 29.168 | 5.9 | 8.6 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 321.1215 | 12 | 12.9 | 24.0 | -100.0 | 40 TREMIE 2 | 2429422 2429427 2429426 2429438 | 8 6 7 3
68 |  | Oct 9 2016 7:30AM |  | 11.164 | 9.875 | 14.00 | 8.60 | -4.692 | 1.289 | 14.567 |  | 8.6 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 254.8488 |  | 6.4 | 0.0 | -6.4 | 40 TREMIE 2
69 |  | Oct 5 2016 7:30AM | Oct 8 2016 11:15PM | 11.213 | 9.875 | 13.50 | 11.90 | -8.368 | 1.338 | 18.243 |  | 11.9 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 271.3665 | 12 | 8.1 | 19.0 | -100.0 | 40 TREMIE 2 | 2437793 2437794 2437795 | 3 9.5 6.5
70 |  | Sep 30 2016 3:15PM | Oct 3 2016 5:14PM | 11.185 | 9.875 | 15.30 | 8.60 | -7.973 | 1.310 | 17.848 | 2.9 | 8.6 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 269.5827 | 12 | 7.9 | 14.0 | 77.5 | 40 TREMIE 2 | 2437363 2437363 | 6 8
72 |  | Aug 1 2016 4:25PM | Aug 4 2016 7:25PM | 11.123 | 10.075 | 20.80 | 13.60 | -17.000 | 1.048 | 27.075 |  | 13.6 | 0.0 | 3.8 | 12T16 | 740.393 | R8-175 | 311.5480 | 12 | 12.0 | 16.0 | -24.8 | 40 TREMIE 2 | 2408956 2408957 | 9 7
76 |  | Oct 9 2016 9:50AM | Oct 10 2016 5:55PM | 7.803 | 6.275 | 12.40 | 2.90 | -5.453 | 1.528 | 11.728 |  | 2.9 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 242.2837 | 12 | 5.2 | 9.5 | 4.3 | 40 TREMIE 2 | 2437836 | 9.5
77 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
78 |  | Oct 11 2016 1:00PM |  | 7.663 | 6.275 | 10.00 | 3.50 | -2.844 | 1.388 | 9.119 |  | 3.5 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 231.0315 |  | 4.0 | 0.0 | -4.0 | 40 TREMIE 2
79 |  | Oct 7 2016 8:00AM | Oct 8 2016 7:15PM | 7.736 | 6.275 | 8.40 | 10.50 | -6.469 | 1.461 | 12.744 |  | 10.5 | 0.0 | 1.5 | 12T16 | 0.000 | R8-175 | 246.7530 | 12 | 5.6 | 9.5 | 68.7 | 40 TREMIE 2 | 2437771 | 9.5
138 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
139 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
140 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
141 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
156 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 12T16 | 418.277 | R8-175 | 235.1073 |  | 4.5 | 0.0 | 0.0 | 40 TREMIE 2
157 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
158 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
159 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
160 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
161 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
162 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
163 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
164 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 12T16 | 346.275 | R8-175 | 219.5123 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
171 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 414.488 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
172 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 414.488 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
173 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 414.488 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
174 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | -100.0 | 40 TREMIE 2
175 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
176 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 234.2493 |  | 4.4 | 0.0 | 0.0 | 40 TREMIE 2
184 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
185 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
186 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
187 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
188 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
189 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
190 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
191 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | 0.000 | R8-175 | 219.8930 |  | 2.8 | 0.0 | 0.0 | 40 TREMIE 2
PTP 1 | SGBM01 | Jul 13 2016 9:00AM | Jun 11 2016 6:38PM | 10.729 | 11.507 | 27.30 | 3.00 | -18.793 | -0.778 | 30.300 |  | 3.0 | 0.0 | 3.0 | 12T16 | 801.500 | R8-175 | 326.3042 | 30 | 13.4 | 17.0 | 6.6 | G50T3 | 17082328 17082335 | 10 7
PTP 1a | SGBM01 | Jul 13 2016 9:00AM | Jul 14 2016 5:40PM | 10.900 | 11.736 | 15.40 | 3.00 | -4.764 | -0.836 | 16.500 |  | 3.0 | 0.0 | 3.0 | 12T16 | 540.018 | R8-175 | 263.5097 | 18.3 | 7.3 | 12.0 | 3.9 | G50T3 | 17083026 17083033 | 10 2
KS8 | SGBM05 | Jul 16 2016 9:20AM | Jul 18 2016 11:05AM | 10.867 | 10.867 | 22.20 | 0.50 | -10.949 | -0.869 | 21.816 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 9.6 | 14.0 | -100.0 | G20P | 2393251 2393254 | 9 5
KS12 | SGBM01 | Jul 16 2016 9:00AM | Jul 18 2016 11:20AM | 10.943 | 10.943 | 19.00 | 0.60 | -7.531 | -0.793 | 18.474 |  | 0.6 | 0.0 | 0.5 | na | NaN | na | NaN |  | 8.2 | 13.0 | -100.0 | G20P | 32393254 2393257 | 4 9
KS15 | SGBM01 | Jul 18 2016 10:05AM | Jul 19 2016 12:30PM | 11.021 | 11.736 | 12.20 | 0.50 | -0.827 | -0.715 | 12.563 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 5.6 | 9.0 | -100.0 | G20P | 2393364 | 9
KS2 | SGBM05 | Jul 18 2016 9:35AM | Jul 19 2016 11:55AM | 10.872 | 11.736 | 12.20 | 0.50 | -0.849 | -0.864 | 12.585 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 5.6 | 9.0 | -100.0 | G20P | 2393362 | 9
KS4 | SGBM05 | Jul 18 2016 9:05AM | Jul 19 2016 10:14AM | 10.912 | 11.736 | 13.00 | 0.50 | -1.747 | -0.824 | 13.483 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 6.0 | 9.0 | -100.0 | G20P | 2393354 | 9
KS1 | SGBM01 | Jul 15 2016 10:00AM | Jul 16 2016 4:10PM | 10.894 | 11.736 | 27.30 | 0.50 | -16.009 | -0.842 | 27.745 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 12.3 | 21.0 | 8.7 | G20P | 2393159 2393164 2393170 | 7 9 5
KS3 | SGBM05 | Jul 19 2016 3:50PM | Jul 20 2016 10:54PM | 10.852 | 10.852 | 14.60 | 0.50 | -3.355 | -0.884 | 14.207 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 6.3 | 10.0 | -100.0 | G20P | 2403019 | 10
KS5 | SGBM05 | Jul 21 2016 8:25AM | Jul 21 2016 4:15PM | 10.881 | 10.881 | 16.60 | 0.50 | -5.286 | -0.419 | 16.167 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 7.1 | 11.0 | 50.1 | G20P | 2403089 2403101 | 8 3
KS6 | SGBM05 | Jul 19 2016 3:15PM | Jul 20 2016 8:45PM | 10.901 | 11.736 | 16.80 | 0.50 | -5.544 | -0.835 | 17.280 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 7.6 | 10.0 | -100.0 | G20P | 2402993 | 10
KS7 | SGBM05 | Jul 15 2016 9:04AM | Jul 15 2016 6:20PM | 10.901 | 11.736 | 23.60 | 0.50 | -12.390 | -0.835 | 24.126 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 10.7 | 12.0 | -100.0 | G20P | 2393059 2393062 | 8 4
KS9 | SGBM01 | Jul 19 2016 2:05PM | Jul 20 2016 3:45PM | 10.887 | 11.3 | 22.70 | 0.50 | -11.465 | -0.413 | 22.765 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 10.1 | 15.0 | -100.0 | G20P | 2402971 2402986 | 10 5
KS10 | SGBM05 | Jul 15 2016 1:21PM | Jul 15 2016 6:55PM | 10.945 | 11.736 | 13.00 | 0.50 | -1.773 | -0.791 | 13.509 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 6.0 | 10.0 | -100.0 | G20P | 2393062 2393072 | 4 6
KS11 | SGBM01 | Jul 21 2016 8:35AM | Jul 21 2016 5:10PM | 11.000 | 11.3 | 17.30 | 0.50 | -6.071 | -0.300 | 17.371 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 7.7 | 11.0 | -100.0 | G20P | 2403096 2403101 | 5 6
KS13 | SGBM01 | Jul 20 2016 11:00AM | Jul 20 2016 6:55PM | 11.039 | 11.736 | 19.30 | 0.50 | -7.746 | -0.697 | 19.482 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 8.6 | 12.0 | -100.0 | G20P | 2402986 2402993 | 4 8
KS14 | SGBM01 | Jul 18 2016 5:00PM | Jul 19 2016 2:10PM | 10.926 | 11.524 | 21.30 | 0.50 | -10.046 | -0.598 | 21.570 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 9.5 | 14.0 | -100.0 | G20P | 2393371 2393377 | 7 7
KS16 | SGBM01 | Jul 15 2016 3:40PM | Jul 16 2016 5:45PM | 11.039 | 11.736 | 12.40 | 0.50 | -0.933 | -0.697 | 12.669 |  | 0.5 | 0.0 | 0.5 | na | NaN | na | NaN |  | 5.6 | 6.0 | -100.0 | G20P | 2393170 2393172 | 3 3
217 |  | Jul 30 2016 9:00AM | Aug 5 2016 6:40PM | 11.386 | 10.075 | 16.60 | 1.80 | -6.345 | 1.311 | 16.420 |  | 1.8 | 0.0 | 1.7 | 12T16 | 538.502 | R8-175 | 263.1501 | 12 | 7.3 | 12.0 | 65.4 | 40 TREMIE 2 | 2409038 | 12
KS17 |  | Sep 8 2016 9:52AM | Sep 8 2016 8:25PM | 11.255 | 11.255 | 26.40 | 0.80 | -15.278 | 11.255 | 26.533 |  | 0.8 | 0.0 | 0.8 | na | NaN | na | NaN |  | 11.7 | 16.0 | 53.5 | G20P | 2418620 2418622 | 10 6
KS18 |  | Sep 3 2016 5:09PM | Sep 5 2016 10:30PM | 11.122 | 11.213 | 20.70 | 2.70 | -9.422 | 11.122 | 20.635 |  | 2.7 | 0.0 | 0.5 | na | NaN | na | NaN | 0.0 | 9.1 | 14.0 | -1.3 | G20P | 2418339 2418346 | 9 5
KS19 |  | Sep 10 2016 8:47AM | Sep 10 2016 3:18PM | 11.153 | 11.153 | 15.30 | 3.70 | -6.622 | 11.153 | 17.775 |  | 3.7 | 0.0 | 0.8 | na | NaN | na | NaN |  | 7.9 | 13.0 | 10.1 | G20P | 2418763 2418766 | 8 5
KS20 |  | Sep 15 2016 9:33AM | Sep 17 2016 9:49PM | 11.156 | 11.171 | 20.90 | 1.00 | -9.844 | 11.156 | 21.015 |  | 1.0 | 0.0 | 0.8 | na | NaN | na | NaN |  | 9.3 | 13.0 | -100.0 | G20P | 2429102 2429103 | 9 4
KS21 |  | Sep 13 2016 7:00AM | Sep 14 2016 2:45PM | 11.138 | 11.138 | 20.60 | 1.10 | -9.753 | 11.138 | 20.891 |  | 1.1 | 0.0 | 0.8 | na | NaN | na | NaN |  | 9.2 | 15.0 | 248.1 | G20P | 2418863 2418866 | 9 6
KS22 |  | Sep 17 2016 8:10AM | Sep 17 2016 9:50PM | 11.171 | 11.171 | 20.80 | 2.40 | -10.093 | 11.171 | 21.264 |  | 2.4 | 0.0 | 0.8 | na | NaN | na | NaN |  | 9.4 | 13.0 | -100.0 | G20P | 2429103 2429104 | 4 9
KS23 |  | Sep 8 2016 10:40AM | Sep 9 2016 8:55PM | 11.057 | 11.087 | 19.40 | 0.80 | -8.356 | 11.057 | 19.443 |  | 0.8 | 0.0 | 0.8 | na | NaN | na | NaN |  | 8.6 | 12.0 | 4.8 | G20P | 2418696 2418698 | 9 3
KS24 |  | Sep 3 2016 4:00PM | Sep 5 2016 11:55PM | 11.122 | 10.978 | 20.00 | 1.60 | -9.577 | 0.144 | 20.555 |  | 1.6 | 0.0 | 0.5 | na | NaN | na | NaN |  | 9.1 | 14.0 | 54.2 | G20P | 2418346 2418352 | 4.5 9.5
KS25 | SGBM01 | Sep 1 2016 2:40PM | Sep 2 2016 7:50PM | 11.453 | 11.453 | 13.20 | 2.10 | -1.844 | 11.453 | 13.297 |  | 2.1 | 0.0 | 0.0 | na | NaN | na | NaN |  | 5.9 | 9.0 | -100.0 | G20P | Pending | 9
KS26 |  | Sep 6 2016 10:48AM | Sep 7 2016 2:55PM | 11.708 | 11.708 | 13.10 | 2.20 | -1.379 | 11.708 | 13.087 |  | 2.2 | 0.0 | 0.8 | na | NaN | na | NaN |  | 5.8 | 9.0 | -0.6 | G20P | 2418526 | 9
KS27 |  | Sep 15 2016 1:07PM | Sep 15 2016 8:10PM | 11.289 | 11.289 | 14.50 | 1.90 | -3.203 | 11.289 | 14.492 |  | 1.9 | 0.0 | 0.8 | na | NaN | na | NaN |  | 6.4 | 10.0 | -100.0 | G20P | 2428969 | 10
KS28 |  | Sep 13 2016 7:00AM | Sep 13 2016 5:40PM | 11.260 | 11.26 | 13.60 | 0.80 | -2.417 | 11.260 | 13.677 |  | 0.8 | 0.0 | 0.8 | na | NaN | na | NaN |  | 6.0 | 10.0 | 836.3 | G20P | 2418825 | 10
KS29 |  | Sep 14 2016 11:05AM | Sep 14 2016 5:50PM | 11.266 | 11.266 | 14.00 | 1.00 | -3.190 | 11.266 | 14.456 |  | 1.0 | 0.0 | 0.8 | na | NaN | na | NaN |  | 6.4 | 10.0 | -1.4 | G20P | 2418886 | 10
KS30 |  | Sep 9 2016 2:43PM | Sep 10 2016 10:35AM | 11.153 | 11.153 | 14.20 | 1.20 | -3.222 | 0.000 | 14.375 |  | 1.2 | 0.0 | 0.8 | na | NaN | na | NaN |  | 6.4 | 11.0 | 10.2 | G20P | 2418743 2418746 | 7 4
KS31 |  | Sep 6 2016 10:13AM | Sep 6 2016 7:50PM | 11.322 | 11.322 | 16.10 | 1.00 | -4.963 | 11.322 | 16.285 |  | 1.0 | 0.0 | 0.8 | na | NaN | na | NaN |  | 7.2 | 10.0 | -2.2 | G20P | 2418419 | 10
KS32 |  | Sep 1 2016 10:30AM | Sep 2 2016 6:15PM | 11.531 | 11.531 | 15.20 | 3.00 | -3.922 | 11.531 | 15.453 |  | 3.0 | 0.0 | 0.0 | na | NaN | na | NaN |  | 6.8 | 9.0 | -100.0 | G20P | 2418065 | 9
4a |  | Oct 3 2016 1:40PM | Oct 4 2016 8:04PM | 11.554 | 9.875 | 23.20 | 6.20 | -13.886 | 1.679 | 23.761 |  | 6.2 | 0.0 | 2.9 | 12T16 | 677.599 | R8-175 | 296.4205 | 12 | 10.5 | 17.0 | -100.0 | 40 TREMIE 2 | 2437456 2437457 | 9 8

## 900
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
18 |  | Aug 11 2016 9:15AM | Aug 13 2016 8:50PM | 11.169 | 9.075 | 26.70 | 4.30 | -18.997 | 2.094 | 28.072 |  | 4.3 | 0.0 | 4.2 | 14T16 | 0.000 | R8-175 | 388.5723 | 12 | 17.9 | 23.0 | 28.8 | 40 TREMIE 2 | 2410533 2410534 2410536 | 9 8 6
33 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
34 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
35 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
36 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
37 |  | Oct 6 2016 10:00AM | Oct 11 2016 2:00PM | 10.803 | 10.075 | 12.60 | 6.50 | -5.712 | 0.728 | 15.787 |  | 6.5 | 0.0 | 2.7 | 14T16 | 0.000 | R8-175 | 319.9816 | 12 | 10.0 | 16.0 | 6.0 | 40 TREMIE 2 | 2437885 2437886 | 7.5 8.5
40 |  | Sep 24 2016 10:25AM | Sep 29 2016 4:26PM | 8.100 | 6.475 | 7.50 | 6.80 | -3.489 | 1.625 | 9.964 |  | 6.8 | 0.0 | 1.3 | 14T16 | 0.000 | R8-175 | 288.4183 | 12 | 6.3 | 10.0 | 3.7 | 40 TREMIE 2 | 2437103 | 10
43 |  | Aug 15 2016 1:00PM | Aug 17 2016 3:20PM | 7.626 | 6.475 | 14.50 | 3.50 | -9.497 | -2.449 | 15.972 |  | 3.5 | 0.0 | 3.5 | 14T16 | 0.000 | R8-175 | 321.0020 | 12 | 10.2 | 14.0 | -12.4 | 40 TREMIE 2 | 2410810 2410811 | 7 7
44 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
45 |  | Sep 27 2016 5:50PM | Sep 28 2016 4:00PM | 10.902 | 10.075 | 17.60 | 1.70 | -7.214 | 0.827 | 17.289 |  | 1.7 | 0.0 | 1.3 | 14T16 | 0.000 | R8-175 | 328.2838 | 12 | 11.0 | 17.0 | -100.0 | 40 TREMIE 2 | 2436980 2436981 2436988 | 8 6 3
51 |  | Aug 24 2016 1:00PM | Aug 25 2016 4:20PM | 7.786 | 10.075 | 7.80 | 4.70 | -2.857 | -2.289 | 12.932 |  | 4.7 | 0.0 | 3.5 | 14T16 | 604.201 | R8-175 | 304.3409 | 10.3 | 8.2 | 15.0 | -8.2 | 40 TREMIE 2 | 2412945 2412953 | 8.5 6.5
52 |  | Aug 26 2016 4:13PM | Aug 27 2016 5:24PM | 7.746 | 5.975 | 10.30 | 1.30 | -3.234 | -2.329 | 9.209 |  | 1.3 | 0.0 | 1.3 | 14T16 | 0.000 | R8-175 | 284.4621 | 12 | 5.9 | 14.0 | -100.0 | 40 TREMIE 2 | 2413158 2413161 | 7.5 6.5
53 |  | Aug 18 2016 5:00PM | Aug 22 2016 7:30PM | 7.573 | 5.975 | 12.00 | 1.80 | -5.230 | -2.502 | 11.205 |  | 1.8 | 0.0 | 1.8 | 14T16 | 0.000 | R8-175 | 295.0171 | 12 | 7.1 | 14.0 | 43.8 | 40 TREMIE 2 | 2412760 2412762 | 7 7
59 |  | Sep 25 2016 9:36AM | Sep 29 2016 7:15PM | 7.812 | 6.475 | 12.50 | 2.70 | -5.483 | 1.337 | 11.958 |  | 2.7 | 0.0 | 1.3 | 14T16 | 582.670 | R8-175 | 299.0655 | 12 | 7.6 | 10.0 | 31.4 | 40 TREMIE 2 | 2437120 | 10
60 |  | Sep 23 2016 5:24PM | Sep 24 2016 2:27PM | 7.739 | 6.475 | 16.80 | 2.50 | -9.759 | 1.264 | 16.234 |  | 2.5 | 0.0 | 1.3 | 14T16 | 677.195 | R8-175 | 322.4481 | 12 | 10.3 | 15.0 | 4.7 | 40 TREMIE 2 | 2430172 2430173 | 7 8
61 |  | Sep 17 2016 4:53PM | Sep 20 2016 5:40PM | 7.160 | 6.475 | 14.00 | 8.20 | -10.233 | 0.685 | 16.708 |  | 8.2 | 0.0 | 2.7 | 14T16 | 0.000 | R8-175 | 325.0678 | 12 | 10.6 | 14.0 | -100.0 | 40 TREMIE 2 | 2429401 2429402 | 8 6
81 |  | Jul 30 2016 3:20PM | Aug 8 2016 8:05PM | 10.999 | 10.075 | 24.90 | 2.90 | -15.649 | 0.924 | 25.724 |  | 2.9 | 0.0 | 2.9 | 14T16 | 0.000 | R8-175 | 375.3815 | 12 | 16.4 | 26.0 | 58.9 | 40 TREMIE 2 | 2409212 2409210 2409213 | 8 10 8
82 |  | Jul 21 2016 5:50PM | Jul 26 2016 1:15PM | 11.021 | 10.075 | 23.90 | 7.20 | -18.996 | 0.946 | 29.071 |  | 7.2 | 0.0 | 7.2 | 14T16 | 0.000 | R8-175 | 394.1909 | 12 | 18.5 | 28.0 | 51.4 | 40 TREMIE 2 | 2403380 2403383 2403388 2403390 | 8 8 8 4
85 |  | Aug 19 2016 8:25AM | Aug 19 2016 8:10PM | 10.737 | 10.075 | 12.10 | 3.20 | -3.732 | 0.662 | 13.807 |  | 3.2 | 0.0 | 3.1 | 14T16 | 0.000 | R8-175 | 309.1100 | 12 | 8.8 | 15.0 | -8.9 | 40 TREMIE 2 | 2412501 2412504 | 8 7
86 |  | Aug 9 2016 7:00AM | Aug 10 2016 2:30PM | 10.643 | 10.075 | 12.20 | 2.60 | -3.196 | 0.568 | 13.271 |  | 2.6 | 0.0 | 3.0 | 14T16 | 0.000 | R8-175 | 306.1856 | 12 | 8.4 | 11.0 | 30.3 | 40 TREMIE 2 | 2409315 2409318 | 8 3
90 |  | Sep 2 2016 7:00AM | Sep 3 2016 5:35PM | 11.031 | 10.075 | 12.70 | 8.00 | -3.954 | 0.956 | 14.029 |  | 8.0 | 0.0 | 2.7 | 14T16 | 0.000 | R8-175 | 310.3239 | 12 | 8.9 | 12.0 | -8.9 | 40 TREMIE 2 | 2418190 2418191 | 7 5
91 |  | Sep 5 2016 7:12PM | Sep 7 2016 8:10PM | 11.013 | 10.075 | 14.40,20.60,27.20 | 3.10,2.40,4.00 | -19.394 | 0.938 | 29.469 | 5.5,3.1,1.3 | 9.5 | 0.0 | 3.5 | 14T16 | 969.768 | R8-175 | 396.4303 | 12 | 18.7 | 25.0 | -100.0 | 40 TREMIE 2 | 2418545 2418549 2418558 | 10 9 6
94 |  | Jul 26 2016 7:10PM | Aug 4 2016 2:35PM | 11.123 | 10.075 | 12.00 | 5.00 | -5.100 | 1.048 | 15.175 |  | 5.0 | 0.0 | 5.0 | 14T16 | 653.785 | R8-175 | 316.6112 | 12 | 9.7 | 14.0 | 45.0 | 40 TREMIE 2 | 2403930 2403933 | 7 7
95 |  | Aug 12 2016 11:20AM | Aug 15 2016 9:10PM | 10.798 | 10.075 | 15.40 | 4.60 | -8.295 | 0.723 | 18.370 |  | 4.6 | 0.0 | 4.6 | 14T16 | 0.000 | R8-175 | 334.2811 | 12 | 11.7 | 16.0 | 36.9 | 40 TREMIE 2 | 2410656 2410657 | 10 6
96 |  | Sep 9 2016 3:18PM | Sep 13 2016 2:17PM | 10.969 | 10.075 | 14.50 | 5.80 | -5.676 | 0.894 | 15.751 |  | 5.8 | 0.0 | 2.7 | 14T16 | 0.000 | R8-175 | 319.7832 | 12 | 10.0 | 15.0 | 5.0 | 40 TREMIE 2 | c660002482 c660002483 | 8 7
101 |  | Aug 16 2016 3:15PM | Aug 17 2016 7:45PM | 10.451 | 10.075 | 13.50 | 3.40 | -5.433 | 0.376 | 15.508 |  | 3.4 | 0.0 | 3.8 | 14T16 | 0.000 | R8-175 | 318.4441 | 12 | 9.9 | 16.0 | -9.9 | 40 TREMIE 2 | 2410835 2410836 | 8 8
114 |  | Oct 1 2016 2:50PM | Oct 1 2016 8:27PM | 10.863 | 10.075 | 13.50 | 1.50 | -3.371 | 0.788 | 13.446 |  | 1.5 | 0.0 | 1.3 | 14T16 | 0.000 | R8-175 | 307.1393 | 12 | 8.6 | 14.0 | 63.6 | 40 TREMIE 2 | 2437300 2437301 | 6 8
119 |  | Aug 1 2016 4:40PM | Aug 4 2016 4:23PM | 10.523 | 10.075 | 15.90,19.90 | 1.60,6.10 | -11.885 | 0.448 | 21.960 |  | 7.7 | 0.0 | 2.0 | 14T16 | 0.000 | R8-175 | 354.2933 | 12 | 14.0 | 18.0 | 28.8 | 40 TREMIE 2 | 2403940 2403941 | 9 9
127 |  | Aug 15 2016 2:25PM | Aug 18 2016 7:20PM | 10.496 | 10.075 | 14.10 | 4.10 | -6.730 | 0.421 | 16.805 |  | 4.1 | 0.0 | 3.5 | 14T16 | 689.818 | R8-175 | 325.6043 | 12 | 10.7 | 14.0 | 30.9 | 40 TREMIE 2 | 2410906 2410907 | 8 6
143 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
148 |  | Aug 17 2016 8:00PM | Aug 20 2016 3:40PM | 10.461 | 10.075 | 22.80 | 2.70 | -14.290 | 0.386 | 24.365 |  | 2.7 | 0.0 | 2.7 | 14T16 | 0.000 | R8-175 | 367.7581 | 12 | 15.5 | 20.0 | 4.5 | 40 TREMIE 2 | 2412572 2412576 | 12 8
149 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | -100.0 | 40 TREMIE 2
150 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
151 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
152 |  | Oct 3 2016 7:30AM | Oct 4 2016 2:27PM | 10.424 | 10.075 | 19.10 | 6.60 | -11.601 | 0.349 | 21.676 |  | 6.6 | 0.0 | 3.5 | 14T16 | 0.000 | R8-175 | 352.7059 | 12 | 13.8 | 18.0 | -13.8 | 40 TREMIE 2 | 2437421 2437422 | 9 9
153 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
154 |  | Oct 9 2016 7:30AM | Oct 10 2016 11:20PM | 10.300 | 10.075 | 15.00 | 2.30 | -5.050 | 0.225 | 15.125 |  | 2.3 | 0.0 | 1.3 | 14T16 | 0.000 | R8-175 | 316.3362 | 12 | 9.6 | 12.0 | 24.7 | 40 TREMIE 2 | 2437864 2437869 | 9 3
155 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
165 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
166 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
167 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
168 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 269.8341 |  | 4.0 | 0.0 | 0.0 | 40 TREMIE 2
169 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
177 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 541.044 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
178 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
192 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
193 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
194 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 289.0041 |  | 6.4 | 0.0 | 0.0 | 40 TREMIE 2
200 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 463.673 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
201 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
202 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
203 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
204 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
205 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
208 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
209 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
210 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
211 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
212 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
213 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 271.2471 |  | 4.2 | 0.0 | 0.0 | 40 TREMIE 2
214 |  | Aug 17 2016 9:40AM | Aug 19 2016 4:55PM | 13.129 | 10.075 | 41.30 | 3.70 | -31.070 | 3.054 | 41.145 |  | 3.7 | 0.0 | 3.7 | 14T16 | 1227.878 | R8-175 | 462.2845 | 12 | 26.2 | 34.0 | 29.9 | 40 TREMIE 2 | 2412479 2412480 2412481 2412482 | 8.5 8.5 8 9
216 |  | Sep 9 2016 3:01PM | Sep 10 2016 1:30PM | 11.905 | 10.075 | 20.60 | 0.90 | -8.921 | 1.830 | 18.996 |  | 0.9 | 0.0 | 0.7 | 14T16 | 738.252 | R8-175 | 337.7610 | 12 | 12.1 | 21.0 | -12.1 | 40 TREMIE 2 | 2418753 2418756 2418769 | 9 9 3
PTP-2 | SGBM17 | Aug 20 2016 11:34AM | Aug 22 2016 9:20PM | 11.389 | 11 | 17.40 | 3.60 | -8.906 | 0.389 | 19.906 |  | 3.6 | 0.0 | 3.5 | 14T16 | 0.000 | R8-175 | 342.8278 | 21 | 12.7 | 20.0 | 7.3 | G50 | 0171788 0171789 | 10 10
7. |  | Aug 25 2016 7:00AM | Aug 26 2016 4:55PM | 11.432 | 9.075 | 19.80 | 6.90 | -12.614 | 2.357 | 21.689 |  | 6.9 | 0.0 | 4.5 | 14T16 | 797.783 | R8-175 | 352.7786 | 12 | 13.8 | 26.0 | 88.4 | 40 TREMIE 2 | 2413046 2413047 2413048 2413060 | 7 8 6 5
7a |  | Aug 29 2016 2:25PM | Sep 2 2016 8:27PM | 11.417 | 9.075 | 18.30 | 4.60 | -10.532 | 2.342 | 19.607 |  | 4.6 | 0.0 | 4.6 | 14T16 | 751.759 | R8-175 | 341.1620 | 12 | 12.5 | 21.0 | -39.9 | 40 TREMIE 2 | 2418087 2418091 2418093 | 7.5 7.5 6

## 1000
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
1 |  | Aug 17 2016 7:00AM | Aug 18 2016 1:35PM | 12.418 | 12.475 | 23.00 | 2.30 | -12.312 | 2.343 | 24.787 |  | 2.3 | 0.0 | 2.3 | 14T16 | 0.000 | R8-175 | 416.1790 | 12 | 19.5 | 34.0 | 0.4 | 40 TREMIE 2 | 2410876 2410882 2410881 2410889 | 11 9 7 7
2 |  | Aug 23 2016 7:00AM | Aug 24 2016 8:25PM | 12.077 | 10.075 | 22.00 | 6.50 | -13.753 | 2.002 | 23.828 | 4.5 | 6.5 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 410.1343 | 12 | 18.7 | 30.0 | -62.6 | 40 TREMIE 2 | 2412883 2412885 2412886 2412887 | 7 7 8 8
8 |  | Sep 7 2016 5:45PM | Sep 9 2016 6:50PM | 11.375 | 6.275 | 26.10 | 8.10 | -17.993 | 1.800 | 24.268 |  | 8.1 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 412.9070 | 12 | 19.1 | 32.0 | -21.6 | 40 TREMIE 2 | 2418683 2418686 2418687 2418699 | 10 8 8 6
9 |  | Sep 20 2016 1:03PM | Sep 23 2016 9:45PM | 11.311 | 6.275 | 20.60,29.30 | 14.80,7.10 | -20.037 | 5.036 | 26.312 | 3.1,0.1,2.8 | 16.9 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 425.8022 | 12 | 20.7 | 41.0 | 91.1 | 40 TREMIE 2 | 2430115 2430116 2430117 2430118 2430122 2430123 | 6 7 9.5 7.5 6 5
10 |  | Sep 13 2016 10:50AM | Sep 19 2016 11:59AM | 11.305 | 6.275 | 16.20 | 12.60 | -8.079 | 5.030 | 14.354 |  | 9.6 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 350.9387 | 12 | 11.3 | 23.0 | 11.7 | 40 TREMIE 2 | 2429207 2429210 2429216 | 8 8 7
11 |  | Sep 26 2016 11:04AM |  | 11.273 | 6.275 | 22.60,24.80 | 6.80,13.50 | -22.254 | 4.998 | 28.529 |  | 20.3 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 439.8121 | 12 | 22.4 | 0.0 | -22.4 | 40 TREMIE 2
12 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 303.4095 |  | 4.9 | 0.0 | 0.0 | 40 TREMIE 2
13 |  | Sep 2 2016 5:50PM | Sep 5 2016 7:55PM | 11.262 | 6.275 | 18.20 | 4.70 | -10.725 | 1.687 | 17.000 |  | 4.7 | 0.0 | 4.7 | 14T16 | 0.000 | R8-175 | 367.3327 | 12 | 13.4 | 23.0 | 4.8 | 40 TREMIE 2 | 2418328 2418329 2418337 | 7 7 9
41 |  | Sep 21 2016 5:26PM | Sep 23 2016 8:15PM | 7.945 | 6.475 | 12.50 | 8.00 | -7.695 | 1.470 | 14.170 |  | 4.3 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 349.8054 | 12 | 11.1 | 21.0 | 9.9 | 40 TREMIE 2 | 2430109 2430108 2430114 | 5 7 9
54 |  | Jul 17 2016 2:10PM | Aug 19 2016 10:50AM | 10.075 | 10.075 | 15.80,20.50 | 0.80,4.40 | -13.142 | 0.000 | 23.217 | 1.5 | 5.2 | 0.0 | 4.4 | 14T16 | 0.000 | R8-175 | 406.2862 | 12 | 18.2 | 28.0 | 53.5 | 40 TREMIE 2 | 2412466 2412467 2412469 2412470 | 7 9 6 6
75 |  | Aug 15 2016 11:40AM | Aug 16 2016 7:42PM | 10.825 | 10.075 | 13.40 | 5.40 | -7.075 | 0.750 | 17.150 |  | 5.4 | 0.0 | 5.0 | 14T16 | 0.000 | R8-175 | 368.2666 | 12 | 13.5 | 19.0 | -13.5 | 40 TREMIE 2 | 2410733 2410734 | 9.5 9.5
83 |  | Aug 26 2016 3:33PM | Sep 1 2016 1:00PM | 10.938 | 10.075 | 30.10 | 6.60 | -22.629 | 0.863 | 32.704 |  | 6.6 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 466.2437 | 12 | 25.7 | 42.0 | -25.7 | 40 TREMIE 2 | 2418006 2418007 2418008 2418010 2418018 | 8 7 9 9 9
84 |  | Aug 20 2016 5:14PM | Aug 23 2016 8:10PM | 10.770 | 10.075 | 18.80 | 5.60 | -12.569 | 0.695 | 22.644 |  | 5.6 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 402.6798 | 12 | 17.8 | 31.0 | -100.0 | 40 TREMIE 2 | 2412822 2412821 2412825 2412829 | 8 9 9 5
89 |  | Aug 3 2016 5:15PM | Aug 8 2016 4:15PM | 11.113 | 10.075 | 20.50 | 5.90 | -14.521 | 1.038 | 24.596 |  | 3.8 | 0.0 | 5.9 | 14T16 | 0.000 | R8-175 | 414.9747 | 12 | 19.3 | 31.0 | 60.5 | 40 TREMIE 2 | 2409192 2409194 2409195 2409203 | 8 9 8 6
92 |  | Sep 14 2016 6:18PM | Sep 24 2016 4:15PM | 10.884 | 10.075 | 9.00,24.50,31.80 | 18.60,3.90,8.70 | -23.928 | 0.809 | 34.003 | 1.1,3.8,5.9,1.1 | 27.9 | 0.0 | 3.9 | 14T16 | 1105.366 | R8-175 | 474.4776 | 12 | 26.7 | 46.0 | 19.3 | 40 TREMIE 2 | 2430183 2430186 2430187 2430192 2430197 2430201 | 8 9 7 9 6 7
93 |  | Sep 1 2016 8:40AM | Sep 1 2016 9:15PM | 10.798 | 10.075 | 15.00 | 3.90 | -7.289 | 0.723 | 17.364 |  | 3.9 | 0.0 | 2.9 | 14T16 | 737.545 | R8-175 | 369.5995 | 12 | 13.6 | 16.0 | -37.7 | 40 TREMIE 2 | 2418030 2418029 | 8.5 7.5
110 |  | Aug 10 2016 11:20AM | Aug 13 2016 1:15PM | 10.502 | 10.075 | 25.00 | 6.50 | -20.056 | 0.427 | 30.131 |  | 6.5 | 0.0 | 6.4 | 14T16 | 0.000 | R8-175 | 449.9477 | 12 | 23.7 | 36.0 | 52.1 | 40 TREMIE 2 | 2410506 2410507 2410508 2398373 2410517 | 8 8 9 8 3
113 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 324.9650 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
120 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 576.414 | R8-175 | 324.9650 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
131 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 324.9650 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
144 |  |  |  | 0.000 | 10.075 |  |  | 0.000 | 0.000 | 10.075 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 324.9650 |  | 7.9 | 0.0 | 0.0 | 40 TREMIE 2
147 |  | Aug 22 2016 2:00PM | Aug 23 2016 6:10PM | 10.421 | 10.075 | 19.60 | 4.30 | -12.662 | 0.346 | 22.737 |  | 4.3 | 0.0 | 3.9 | 14T16 | 0.000 | R8-175 | 403.2649 | 12 | 17.9 | 26.0 | -17.9 | 40 TREMIE 2 | 2412810 2412811 2412812 | 8.5 9 8.5
195 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 304.9984 |  | 5.2 | 0.0 | 0.0 | 40 TREMIE 2
136 |  | Aug 9 2016 7:00AM | Aug 12 2016 8:40PM | 10.391 | 10.075 | 15.10,22.50 | 1.60,6.90 | -18.106 | 0.316 | 28.181 | 5.8 | 8.5 | 0.0 | 5.8 | 14T16 | 0.000 | R8-175 | 437.6116 | 12 | 22.1 | 32.0 | 44.6 | 40 TREMIE 2 | 2410462 2410464 2410467 2410470 | 8 8 9 7
199 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 304.9984 |  | 5.2 | 0.0 | 0.0 | 40 TREMIE 2
207 |  |  |  | 0.000 | 6.575 |  |  | 0.000 | 0.000 | 6.575 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 304.9984 |  | 5.2 | 0.0 | 0.0 | 40 TREMIE 2

## 1200
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
3 |  | Aug 19 2016 6:10PM | Aug 20 2016 7:28PM | 11.930 | 12.275 | 15.60 | 2.80 | -5.659 | 2.055 | 17.934 |  | 2.8 | 0.0 | 2.3 | 16T16 | 0.000 | R8-175 | 455.7890 | 12 | 20.3 | 25.0 | 42.3 | 40 TREMIE 2 | 2412601 2412602 2412603 | 9 8.5 7.5
4 |  | Aug 3 2016 11:20AM | Aug 10 2016 5:00PM | 11.509 | 9.875 | 23.60 | 6.30 | -17.396 | 1.634 | 27.271 |  | 6.3 | 0.0 | 6.0 | 16T16 | 1174.043 | R8-175 | 527.4957 | 12 | 30.8 | 49.0 | 18.1 | 40 TREMIE 2 | 2409328 2409329 2409332 2409334 2409339 2409347 | 7 8 9 8 10 7
6 |  | Jul 26 2016 5:10PM | Aug 13 2016 10:50AM | 11.312 | 9.875 | 22.00 | 5.00 | -14.959 | 1.437 | 24.834 |  | 5.0 | 0.0 | 5.2 | 16T16 | 0.000 | R8-175 | 508.7044 | 12 | 28.1 | 45.0 | 16.9 | 40 TREMIE 2 | 2410497 2410498 2410499 2410501 2410505 2410504 2398372 | 6 7 8 6 4 8 6
7 |  | Jul 19 2016 5:05PM |  | 11.567 | 9.875 | 23.30 | 9.20 | -20.102 | 0.000 | 29.977 |  | 3.9 | 0.0 | 6.0 | 16T16 | 1242.408 | R8-175 | 548.3985 |  | 33.9 | 0.0 | -33.9 | 40 TREMIE 2
17 |  | Aug 15 2016 8:30AM | Aug 17 2016 1:30PM | 11.250 | 9.875 | 12.00 | 3.40 | -3.264 | 1.375 | 13.139 |  | 3.4 | 0.0 | 3.0 | 16T16 | 0.000 | R8-175 | 419.5392 | 12 | 14.9 | 22.0 | 7.1 | 40 TREMIE 2 | 2410801 2410803 2410804 | 8 8 6
38 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 16T16 | 643.600 | R8-175 | 370.5999 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
39 |  | Oct 7 2016 5:00PM | Oct 10 2016 8:15PM | 8.234 | 6.275 | 7.20 | 16.80 | -5.563 | 1.959 | 11.838 |  | 10.5 | 0.0 | 3.3 | 16T16 | 784.144 | R8-175 | 409.8590 | 12 | 13.4 | 20.0 | 6.6 | 40 TREMIE 2 | 2437847 2437848 | 9 11
46 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 16T16 | 643.600 | R8-175 | 370.5999 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
47 |  |  |  | 0.000 | 6.275 |  |  | 0.000 | 0.000 | 6.275 |  | 0.0 | 0.0 | 0.0 | 16T16 | 643.600 | R8-175 | 370.5999 |  | 7.1 | 0.0 | 0.0 | 40 TREMIE 2
48 |  | Oct 1 2016 3:00PM | Oct 7 2016 7:53PM | 7.989 | 6.275 | 13.00 | 11.80 | -9.730 | 1.714 | 16.005 | 5.0 | 8.1 | 0.0 | 3.3 | 16T16 | 889.419 | R8-175 | 441.1260 | 12 | 18.1 | 26.0 | 43.6 | 40 TREMIE 2 | 2437688 2437689 2437691 | 9 9 8
49 |  | Sep 5 2016 8:18AM | Sep 8 2016 4:20PM | 7.894 | 9.875 | 9.00 | 21.30 | -6.849 | -1.981 | 16.724 |  | 13.8 | 0.0 | 0.0 | 16T16 | 907.584 | R8-175 | 446.5815 | 12 | 18.9 | 24.0 | 5.1 | 40 TREMIE 2 | 2418601 2418602 2418604 | 8 9 7
50 |  | Sep 30 2016 7:50AM | Oct 4 2016 3:10PM | 7.769 | 6.275 | 6.00,15.50,12.00 | 6.00,11.50,10.10 | -11.556 | 1.494 | 17.831 | 3.5 | 24.6 | 0.0 | 4.7 | 16T16 | 0.000 | R8-175 | 455.0041 | 12 | 20.2 | 31.0 | 10.8 | 40 TREMIE 2 | 2437427 2437429 2437432 2437445 | 9 8 9 5
55 |  | Aug 27 2016 4:20PM | Sep 3 2016 6:00PM | 8.269 | 6.275 | 17.00,18.30 | 1.30,15.00 | -14.118 | 1.994 | 20.393 |  | 9.7 | 0.0 | 3.3 | 16T16 | 0.000 | R8-175 | 474.5813 | 12 | 23.1 | 35.0 | 30.1 | 40 TREMIE 2 | 2418192 2418193 2418194 2418197 2418204 | 6 9 8 7 5
65 |  | Aug 8 2016 11:00AM | Aug 10 2016 9:50PM | 11.376 | 9.875 | 17.60 | 5.20 | -10.591 | 1.501 | 20.466 |  | 3.9 | 0.0 | 5.2 | 16T16 | 1002.122 | R8-175 | 475.1405 | 12 | 23.1 | 31.0 | 33.9 | 40 TREMIE 2 | 2409355 2409356 2409357 2409358 | 8 9 8 6
71 |  | Aug 27 2016 7:00AM | Aug 27 2016 7:03PM | 11.180 | 9.875 | 19.90 | 3.20 | -9.856 | 1.305 | 19.731 |  | 3.2 | 0.0 | 1.8 | 16T16 | 0.000 | R8-175 | 469.5131 | 12 | 22.3 | 30.0 | -22.3 | 40 TREMIE 2 | 2413176 2413178 2413181 2413148 | 9 7 6 8
73 | SGBM23 | Jul 26 2016 6:25PM | Jul 30 2016 1:34PM | 11.018 | 10.075 | 13.00 | 4.90 | -5.859 | 0.943 | 15.934 |  | 4.0 | 0.0 | 4.9 | 14T16 | 776.672 | R8-175 | 440.5880 | 12 | 18.0 | 25.0 | 38.7 | 40 TREMIE 2 | 2403653 2403652 2403654 | 8.5 9.5 7
74 | SGBM23 | Aug 1 2016 3:00PM | Aug 6 2016 5:00PM | 10.841 | 10.075 | 14.00 | 4.50 | -5.188 | 0.766 | 15.263 |  | 3.5 | 0.0 | 4.2 | 14T16 | 761.839 | R8-175 | 435.5105 | 12 | 17.3 | 28.0 | 62.2 | 40 TREMIE 2 | 2409119 2409123 2409124 | 10 9 9
80 |  | Sep 8 2016 9:50AM | Sep 14 2016 7:25PM | 7.787 | 6.275 | 17.50 | 13.00 | -14.369 | 1.512 | 20.644 |  | 8.6 | 0.0 | 4.7 | 16T16 | 0.000 | R8-175 | 476.5043 | 12 | 23.4 | 32.0 | 8.6 | 40 TREMIE 2 | 2418895 2418897 2418898 2418900 | 8 10 9 5
87 |  | Aug 11 2016 9:35AM | Aug 15 2016 2:57PM | 11.266 | 9.875 | 17.60 | 7.20 | -12.775 | 1.391 | 22.650 |  | 7.0 | 0.0 | 7.2 | 16T16 | 1057.298 | R8-175 | 491.8998 | 12 | 25.6 | 34.0 | 8.4 | 40 TREMIE 2 | 2410639 2410640 2410641 2410642 | 9 9 8.5 7.5
100 |  | Sep 13 2016 5:14PM | Sep 14 2016 4:05PM | 10.710 | 9.875 | 11.50 | 3.10 | -1.292 | 0.835 | 11.167 |  | 3.1 | 0.0 | 1.3 | 14T16 | 0.000 | R8-175 | 404.9077 | 12 | 12.6 | 17.0 | -100.0 | 40 TREMIE 2 | 2418871 2418872 | 8 9
102 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 734.551 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
105 |  | Oct 4 2016 9:15AM | Oct 5 2016 4:35PM | 10.927 | 9.875 | 15.50 | 3.20 | -6.999 | 1.052 | 16.874 |  | 3.2 | 0.0 | 3.3 | 16T16 | 0.000 | R8-175 | 447.7212 | 12 | 19.1 | 27.0 | 41.5 | 40 TREMIE 2 | 2437520 2437522 2437524 | 9 9 9
107 |  | Sep 14 2016 2:31PM | Sep 17 2016 2:25PM | 10.843 | 8.875 | 13.30 | 14.70 | -7.640 | 1.118 | 16.515 |  | 0.0 | 0.0 | 4.7 | 16T16 | 0.000 | R8-175 | 444.9944 | 12 | 18.7 | 25.0 | -3.6 | 40 TREMIE 2 | 2429046 2429048 2429051 | 9 9 7
97 |  | Sep 25 2016 2:33PM | Sep 27 2016 7:00PM | 10.917 | 9.875 | 12.60,15.20 | 1.00,2.40 | -4.764 | 1.042 | 14.639 | 0.7,0.2,0.5,0.9,0.2 | 2.3 | 0.0 | 1.3 | 16T16 | 0.000 | R8-175 | 430.8011 | 12 | 16.6 | 26.0 | 9.4 | 40 TREMIE 2 | 2430414 2430417 2430424 | 9.5 10.5 6
98 |  | Sep 28 2016 11:30AM | Oct 4 2016 10:40AM | 10.833 | 9.875 | 13.60,14.80 | 0.70,13.40 | -8.645 | 0.958 | 18.520 |  | 9.8 | 0.0 | 4.7 | 16T16 | 952.958 | R8-175 | 460.2585 | 12 | 20.9 | 30.0 | 43.2 | 40 TREMIE 2 | 2437389 2437390 2437394 2437399 | 9 6 9 6
99 |  | Aug 24 2016 2:00PM | Aug 26 2016 8:54PM | 10.771 | 9.875 | 12.60,18.30 | 5.20,5.30 | -11.118 | 0.696 | 20.993 | 3.1 | 10.5 | 0.0 | 3.3 | 16T16 | 1015.436 | R8-175 | 479.1796 | 12 | 23.7 | 34.0 | -100.0 | 40 TREMIE 2 | 2413067 2413068 2413069 2413070 | 8 9 9 8
104 |  | Sep 24 2016 2:34PM | Sep 26 2016 11:24AM | 10.980 | 9.875 | 17.10 | 10.20 | -11.320 | 1.105 | 21.195 |  | 9.2 | 0.0 | 1.9 | 16T16 | 0.000 | R8-175 | 480.7288 | 12 | 24.0 | 36.0 | 50.2 | 40 TREMIE 2 | 2430256 2430257 2430258 2430259 2430266 | 9 9 7 6 5
106 |  | Sep 19 2016 10:52AM | Sep 23 2016 6:10PM | 10.879 | 9.875 | 19.20,25.40 | 6.80,4.10 | -15.584 | 1.004 | 25.459 | 0.8,1.5,0.4 | 7.3 | 0.0 | 1.9 | 16T16 | 1128.265 | R8-175 | 513.5201 | 12 | 28.8 | 45.0 | -100.0 | 40 TREMIE 2 | 2430102 2430104 2430105 2430106 2430107 2430109 | 8 8 9 8 7 5
108 |  | Sep 20 2016 10:07AM | Sep 22 2016 8:53PM | 10.722 | 8.875 | 16.00,16.80 | 0.80,10.90 | -10.675 | 1.847 | 19.550 |  | 7.0 | 0.0 | 4.7 | 16T16 | 0.000 | R8-175 | 468.1285 | 12 | 22.1 | 30.0 | 4.9 | 40 TREMIE 2 | 2430051 2430057 Pending 2430061 | 9 9 9 3
109 |  | Sep 17 2016 1:30PM | Sep 19 2016 1:48PM | 10.645 | 9.875 | 16.50 | 2.70 | -7.170 | 0.770 | 17.045 |  | 1.2 | 0.0 | 1.9 | 16T16 | 915.694 | R8-175 | 449.0212 | 12 | 19.3 | 27.0 | -100.0 | 40 TREMIE 2 | 2429218 2429221 2429223 2429216 | 8 8 8 3
111 |  | Jul 26 2016 10:00AM | Aug 3 2016 9:00PM | 11.274 | 9.875 | 22.50 | 8.10 | -18.614 | 1.399 | 28.489 |  | 6.0 | 0.0 | 8.1 | 16T16 | 1204.815 | R8-175 | 536.9000 | 12 | 32.2 | 42.0 | 30.3 | 40 TREMIE 2 | 2403891 2403892 2403894 2403895 2403896 | 9 9 9 11 4
115 |  | Sep 1 2016 6:30PM | Sep 5 2016 1:30PM | 10.839 | 9.875 | 13.80 | 5.90 | -7.096 | 0.964 | 16.971 |  | 3.4 | 0.0 | 4.7 | 16T16 | 913.824 | R8-175 | 448.4585 | 12 | 19.2 | 28.0 | -19.2 | 40 TREMIE 2 | 2418285 2418286 2418291 2418299 | 8 9 8 3
116 |  | Aug 27 2016 10:00AM | Aug 30 2016 2:05PM | 10.840 | 9.875 | 25.50 | 11.30 | -19.040 | 0.965 | 28.915 |  | 0.0 | 0.0 | 4.7 | 18T16 | 0.000 | R8-175 | 540.1910 | 12 | 32.7 | 45.0 | -24.7 | 40 TREMIE 2 | 2413378 2413382 2413384 2413385 2413397 2413399 | 8 6 9 8 8 6
117 |  | Aug 23 2016 3:20PM | Aug 25 2016 12:50PM | 10.638 | 9.975 | 26.70 | 5.60 | -20.529 | 0.763 | 30.504 |  | 0.0 | 0.0 | 4.7 | 18T16 | 0.000 | R8-175 | 552.4732 | 12 | 34.5 | 45.0 | -73.9 | 40 TREMIE 2 | 2412928 2412929 2412930 2412933 2412934 | 9 9 9 9 9
118 |  | Aug 18 2016 1:00PM | Aug 20 2016 5:50PM | 10.640 | 9.875 | 15.10 | 4.70 | -8.410 | 0.765 | 18.285 |  | 4.7 | 0.0 | 4.7 | 16T16 | 947.021 | R8-175 | 458.4654 | 12 | 20.7 | 27.0 | -20.7 | 40 TREMIE 2 | 2412588 2412591 2412594 | 9 9 9
121 |  | Oct 9 2016 11:30AM |  | 10.677 | 9.875 | 0.00 | 0.00 | 5.745 | 0.802 | 4.130 |  | 0.0 | 0.0 | 3.3 | 16T16 | 589.409 | R8-175 | 358.4015 |  | 4.7 | 0.0 | -100.0 | 40 TREMIE 2
122 |  | Sep 26 2016 1:15PM | Oct 8 2016 9:20PM | 10.721 | 8.975 | 15.00,14.50 | 12.60,10.00 | -12.449 | 1.746 | 21.424 |  | 18.6 | 0.0 | 3.3 | 16T16 | 1026.325 | R8-175 | 482.4854 | 12 | 24.2 | 35.0 | -24.2 | 40 TREMIE 2 | 2437784 2437785 2437786 2437788 2437793 | 6.5 8 8 7.5 5
123 |  | Sep 29 2016 10:25AM | Oct 5 2016 12:57PM | 10.671 | 8.975 | 21.70 | 15.40 | -15.728 | 1.696 | 24.703 |  | 10.6 | 0.0 | 3.3 | 16T16 | 1109.165 | R8-175 | 507.6954 | 12 | 27.9 | 32.0 | -100.0 | 40 TREMIE 2 | 2437508 2437510 2437511 2437513 | 9 8 9 6
124 |  | Sep 1 2016 7:50AM | Sep 3 2016 2:00PM | 10.549 | 8.975 | 25.00,27.60 | 0.90,7.90 | -20.641 | 1.674 | 29.616 |  | 5.4 | 0.0 | 3.3 | 16T16 | 1233.287 | R8-175 | 545.6081 | 12 | 33.5 | 40.0 | -33.5 | 40 TREMIE 2 | 2418163 2418164 2418169 2418174 2418177 | 10 9 9 7 5
125 |  | Aug 25 2016 8:36AM | Aug 27 2016 11:25AM | 10.632 | 8.975 | 28.60 | 6.80 | -20.883 | 1.757 | 29.858 |  | 6.8 | 0.0 | 3.8 | 16T16 | 1239.401 | R8-175 | 547.4786 | 12 | 33.8 | 45.0 | -33.7 | 40 TREMIE 2 | 2413108 2413112 2413114 2413115 2413127 | 8 9 10 9 9
126 |  | Sep 5 2016 8:50AM | Sep 6 2016 8:30PM | 10.729 | 9.875 | 29.40 | 9.10 | -21.283 | 0.854 | 31.158 | 17.0 | 6.1 | 0.0 | 3.3 | 16T16 | 1272.245 | R8-175 | 557.5312 | 12 | 35.2 | 42.0 | -35.2 | 40 TREMIE 2 | c660002413 c660002414 c660002415 c660002416 | 11 11 10 10
128 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 734.551 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
130 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 0.000 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
132 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 734.551 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
135 |  | Sep 10 2016 1:33PM | Sep 13 2016 7:18PM | 10.560 | 9.875 | 14.40 | 8.50 | -8.177 | 0.685 | 18.052 |  | 6.0 | 0.0 | 3.3 | 16T16 | 941.135 | R8-175 | 456.6885 | 12 | 20.4 | 27.0 | 32.2 | 40 TREMIE 2 | C660002484 C660002485 C660002486 | 9 9 9
137 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 0.000 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
142 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 0.000 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
145 |  |  |  | 0.000 | 9.875 |  |  | 0.000 | 0.000 | 9.875 |  | 0.0 | 0.0 | 0.0 | 16T16 | 734.551 | R8-175 | 395.4803 |  | 11.2 | 0.0 | 0.0 | 40 TREMIE 2
146 |  | Sep 27 2016 11:02AM | Sep 29 2016 2:30PM | 10.426 | 9.875 | 16.50 | 11.40 | -9.793 | 0.551 | 19.668 |  | 6.3 | 0.0 | 4.7 | 16T16 | 981.961 | R8-175 | 469.0311 | 12 | 22.2 | 28.0 | 25.9 | 40 TREMIE 2 | 2437094 2437095 2437099 | 9 9.5 9.5
170 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 14T16 | 0.000 | R8-175 | 371.2427 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
179 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 16T16 | 0.000 | R8-175 | 371.2427 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
183 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 16T16 | 646.127 | R8-175 | 371.2427 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
196 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 16T16 | 0.000 | R8-175 | 371.2427 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
197 | SGBM20 | Oct 9 2016 9:35AM |  | 9.098 | 6.375 | 10.10 | 12.30 | -5.214 | 2.723 | 11.589 |  | 8.7 | 0.0 | 4.7 | 16T16 | 777.853 | R8-175 | 408.0179 |  | 13.1 | 0.0 | -13.1 | 40 TREMIE 2
198 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 16T16 | 646.127 | R8-175 | 371.2427 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
206 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 16T16 | 0.000 | R8-175 | 371.2427 |  | 7.2 | 0.0 | 0.0 | 40 TREMIE 2
215 |  | Aug 20 2016 2:00PM | Aug 22 2016 4:58PM | 12.726 | 10.075 | 20.30 | 2.20 | -8.911 | 2.651 | 18.986 |  | 2.2 | 0.0 | 1.9 | 16T16 | 964.731 | R8-175 | 463.8171 | 12 | 21.5 | 34.0 | -25.5 | 40 TREMIE 2 | 2412741 2412742 2412746 2412745 | 8.5 7.5 9 9
107a |  | Sep 8 2016 8:37AM | Sep 9 2016 4:13PM | 10.739 | 8.875 | 20.70 | 8.20 | -14.899 | 1.864 | 23.774 |  | 8.2 | 0.0 | 4.7 | 16T16 | 1085.695 | R8-175 | 500.5435 | 12 | 26.9 | 36.0 | -100.0 | 40 TREMIE 2 | 2418673 2418674 2418675 2418679 | 9 9 9 9
108a |  | Sep 6 2016 6:04PM | Sep 7 2016 8:50PM | 10.608 | 8.875 | 17.10 | 7.70 | -10.767 | 1.733 | 19.642 |  | 7.7 | 0.0 | 4.7 | 16T16 | 981.304 | R8-175 | 468.8322 | 12 | 22.2 | 30.0 | -22.2 | 40 TREMIE 2 | 2418546 2418551 2418556 2418552 | 8 9 7 6

## 1350
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
5 |  | Jul 20 2016 11:50AM | Jul 26 2016 8:35PM | 11.420 | 9.875 | 27.50 | 10.50 | -25.884 | 1.545 | 35.759 |  | 6.8 | 0.0 | 10.5 | 18T16 | 0.000 | R8-175 | 673.8442 | 12 | 51.2 | 65.5 | -54.1 | 40 TREMIE 2 | 2403404 2403405 2403408 2403407 2403406 2403409 2403410 2403419 | 8.5 7.5 7.5 8.5 7.5 7.5 8.5 10
42 |  | Sep 14 2016 4:33PM | Sep 17 2016 5:50PM | 7.845 | 6.275 | 11.40 | 12.10 | -8.598 | 1.570 | 14.873 |  | 6.6 | 0.0 | 5.7 | 22T16 | 0.000 | R8-175 | 491.4100 | 12 | 21.3 | 30.0 | 8.7 | 40 TREMIE 2 | 2429076 2429077 2429079 2429083 | 8 6 7.5 8.5
56 |  | Sep 20 2016 10:39AM | Sep 22 2016 7:35PM | 7.954 | 6.275 | 9.50 | 18.30 | -9.787 | 1.679 | 16.062 |  | 11.5 | 0.0 | 5.3 | 18T16 | 0.000 | R8-175 | 501.6257 | 12 | 23.0 | 33.0 | 43.5 | 40 TREMIE 2 | 2430040 2430041 2430044 2430049 | 9 9 9 6
57 |  | Aug 23 2016 6:00PM | Aug 26 2016 9:26PM | 8.039 | 6.275 | 16.50 | 9.70 | -13.358 | -1.836 | 19.633 |  | 7.9 | 0.0 | 5.7 | 18T16 | 0.000 | R8-175 | 532.5320 | 12 | 28.1 | 35.5 | -33.3 | 40 TREMIE 2 | 2413071 2413072 2413073 2413076 | 8 9 9.5 9
58 |  | Aug 18 2016 1:00PM | Aug 22 2016 1:00PM | 7.855 | 6.275 | 18.20 | 6.30 | -15.837 | -2.020 | 22.112 |  | 6.3 | 0.0 | 6.3 | 18T16 | 0.000 | R8-175 | 554.1204 | 12 | 31.7 | 38.0 | 1.2 | 40 TREMIE 2 | 2412721 2412722 2412728 2412729 2412731 | 9 8 8 7 6
88 | SGBM05 | Jul 28 2016 8:20AM | Aug 1 2016 11:20AM | 11.133 | 9.875 | 19.90 | 7.90 | -15.932 | 1.258 | 25.807 |  | 4.3 | 0.0 | 7.9 | 18T16 | 0.000 | R8-175 | 586.4247 | 12 | 36.9 | 45.0 | 21.8 | 40 TREMIE 2 | 2403714 2403715 2403716 2403718 2403719 | 10 10 9 8 8
103 |  | Oct 6 2016 4:25PM | Oct 10 2016 9:38PM | 11.094 | 9.975 | 18.60,19.50 | 0.90,26.40 | -22.613 | 1.119 | 32.588 |  | 21.5 | 0.0 | 5.3 | 18T16 | 0.000 | R8-175 | 645.9455 | 12 | 46.7 | 56.5 | 21.1 | 40 TREMIE 2 | 2437854 2437855 2437857 2437858 2437859 24378863 2437866 2437869 | 6 6 7.5 9 9 8 9 2
112 |  | Aug 13 2016 8:00PM | Aug 17 2016 4:40PM | 11.094 | 9.875 | 21.20 | 6.40 | -15.845 | 1.219 | 25.720 |  | 3.1 | 0.0 | 6.8 | 18T16 | 0.000 | R8-175 | 585.6627 | 12 | 36.8 | 44.0 | 19.5 | 40 TREMIE 2 | 2410815 2410816 2410819 2410822 2410821 | 9 9 9 9 8
129 |  |  |  | 0.000 | 9.975 |  |  | 0.000 | 0.000 | 9.975 |  | 0.0 | 0.0 | 0.0 | 18T16 | 0.000 | R8-175 | 450.1020 |  | 14.3 | 0.0 | 0.0 | 40 TREMIE 2
180 |  | Oct 4 2016 11:40AM | Oct 8 2016 11:55AM | 9.848 | 6.375 | 9.60,25.60 | 2.30,13.90 | -20.948 | 3.473 | 27.323 | 1.3,11.3,1.1,7.7,1.0 | 9.1 | 0.0 | 5.3 | 18T16 | 0.000 | R8-175 | 599.7099 | 12 | 39.1 | 56.0 | 16.9 | 40 TREMIE 2 | C660002747 C660002748 C660002749 C660002750 C660002751 C660002752 | 10 10 10 10 10 6
181 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 18T16 | 0.000 | R8-175 | 421.7452 |  | 9.1 | 0.0 | 0.0 | 40 TREMIE 2
182 |  |  |  | 0.000 | 6.375 |  |  | 0.000 | 0.000 | 6.375 |  | 0.0 | 0.0 | 0.0 | 18T16 | 0.000 | R8-175 | 421.7452 |  | 9.1 | 0.0 | 0.0 | 40 TREMIE 2

## 1500
Summary List for 18916526-RC8
Pile Details |  |  |  | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage |  |  |  |  | Concrete
Pile No. | Rig Number (last rig to operate on pile) | Boring Start Date | Concrete Start Date | Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Thickness | Toe Level (mRL) | Bored Depth PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Reinforcement Content | Main Steel Bar Weight | Helical/Spiral | Helical Link (KG) | Cage Length | Theoretical | Actual | Wastage (%) | Grade | DO Number | Concrete Volume
133 | SGBM23 | Oct 10 2016 6:10PM |  | 10.552 | 9.725 | 10.40 | 7.30 | -2.870 | 0.827 | 12.595 |  | 4.9 | 0.0 | 5.8 | 22T16 | 0.000 | R8-175 | 528.5340 |  | 22.3 | 0.0 | -22.3 | 40 TREMIE 2
134 |  | Sep 23 2016 5:30PM | Sep 26 2016 3:15PM | 10.530 | 9.725 | 17.10 | 11.30 | -11.794 | 0.805 | 21.519 |  | 7.0 | 0.0 | 5.8 | 22T16 | 0.000 | R8-175 | 614.6991 | 12 | 38.0 | 52.0 | 14.0 | 40 TREMIE 2 | 2430279 2430280 2430282 2430284 2430285 2430286 | 10 8 8 9 8 9