## 1000
Summary List for 000-RMMS TEST PROJECT
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [8 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T25 Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | R10 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
TEST 2 | SGBM11 | Dec 6 2016 7:00AM | Dec 6 2016 5:45PM | Dec 6 2016 6:30PM | Dec 6 2016 9:00PM | 0 | 0 | -12.00 | 7.00 | -19.000 | 19.000 | 19.000 | 4.0 | 7.0 | 0.0 | 6.0 | 25T25(2) | 2312.4000 | 2312.4 | - | R10-185(2) | 31.1474 | 31.1 | 12+12 | - | 14.9 | 24.0 | 60.8 | G4 | 765 098 Pending | 8 8 8
TEST 1 | SGBM11 | Dec 5 2016 7:00AM | Dec 5 2016 3:15PM | Dec 5 2016 4:30PM | Dec 5 2016 7:45PM | 0 | 0 | -8.00 -16.00 | 6.00 6.00 | -20.000 | 22.000 | 20.000 | 2.0 | 10.0 | 0.0 | 6.0 | 20T25(1), 35T20(1) | 1960.6800 | 925.0 | 1035.7 | R10-185(2) | 31.1428 | 31.1 | 12+12 | - | 15.7 | 22.0 | 40.0 | G5 | 48383282 654 655r | 8 8 6
Total | [10 empty] | 41.000 | 39.000 | 6.0 | 17.0 | 0.0 | 12.0 |  | 4273.1 | 3237.4 | 1035.7 |  | 62.3 | 62.3 |  |  | 30.6 | 46.0