## 750
Summary List for 1891651800-Parcel F
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [8 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T16 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T10 Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
Na/42-1b | SGBM20 | Apr 11 2016 10:55AM | Apr 11 2016 6:30PM | Apr 11 2016 8:25PM | Apr 11 2016 9:20PM | 52.897 | 50.575 | 52.06 | 0.00 | 30.064 | 22.833 | 20.511 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.1 | 12.0 | -100.0 | G35T2 | pj7749 pj7750 | 7 5
Na/42-1a | SGBM20 | Apr 11 2016 10:20AM | Apr 11 2016 3:55PM | Apr 11 2016 7:21PM | Apr 11 2016 8:15PM | 52.027 | 50.575 | 52.89 | 0.00 | 43.891 | 21.136 | 6.684 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | 7.324 | 3.0 | 12.0 | 6.3 | G35T2 | pj7745 pj7746 | 8 4
J/18-2 | SGBM31 | Apr 2 2016 8:00AM | Apr 4 2016 2:00PM | Apr 4 2016 6:50PM | Apr 4 2016 7:25PM | 55.29 | 51.375 | 56.24 | 0.00 | 24.638 | 30.652 | 26.737 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 13.0 | -100.0 | G45T2 | pj7582 pj7583 | 7 6
Ka/18-2 | SGBM19 | Apr 2 2016 9:20AM | Apr 4 2016 4:30PM | Apr 4 2016 6:00PM | Apr 4 2016 6:45PM | 55.94 | 51.375 | 56.54 | 0.00 | 24.637 | 31.303 | 26.738 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 13.0 | -100.0 | G35T2 | pj7579 pj7581 | 7 6
Ka/18-1 | SGBM19 | Apr 1 2016 4:30PM | Apr 4 2016 11:45AM | Apr 4 2016 5:05PM | Apr 4 2016 5:55PM | 55.675 | 51.375 | 56.56 | 0.00 | 47.555 | 31.120 | 3.820 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | 4.460 | 1.7 | 13.0 | -100.0 | G35T2 | pj7575 pj7576 | 7 6
G/18-2 | SGBM19 | Apr 1 2016 5:20PM | Apr 2 2016 4:00PM | Apr 2 2016 4:35PM | Apr 2 2016 5:25PM | 54.66 | 51.375 | 55.49 | 0.00 | 24.486 | 30.174 | 26.889 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 13.0 | -100.0 | G45T2 | pj7549 pj7551 | 7 6
H/18-1 | SGBM19 | Apr 1 2016 6:00AM | Apr 2 2016 12:15PM | Apr 2 2016 3:00PM | Apr 2 2016 3:25PM | 55.16 | 50.575 | 55.89 | 0.00 | 23.586 | 31.574 | 26.989 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 14.0 | -100.0 | G45T2 | pj7541 pj7543 | 7 7
R/8a-1 | SGBM19 | Mar 29 2016 2:30PM | Mar 30 2016 5:10PM | Mar 30 2016 9:00PM | Mar 30 2016 9:45PM | 55.93 | 55.075 | 56.81 | 0.00 | 28.306 | 84.430 | 26.769 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 16.0 | -100.0 | G35T2 | pj7462 pj7463 | 8 8
R/9-1 | SGBM19 | Mar 29 2016 1:00PM | Mar 30 2016 1:45PM | Mar 30 2016 6:10PM | Mar 30 2016 6:50PM | 55.781 | 54.475 | 56.62 | 0.00 | 27.619 | 28.162 | 26.856 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 16.0 | -100.0 | G35T2 | pj7449 pj7451 | 8 8
M/6-1 | SGBM31 | Mar 29 2016 10:40AM | Mar 29 2016 8:35PM | Mar 29 2016 11:15PM | Mar 30 2016 12:25AM | 55.86 | 55.075 | 56.76 | 0.00 | 28.460 | 27.400 | 26.615 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 17.0 | -100.0 | G35T2 | pj7428 pj7431 | 10 7
L/18-1 | SGBM31 | Mar 28 2016 9:00AM | Mar 29 2016 12:00PM | Mar 29 2016 6:00PM | Mar 29 2016 6:55PM | 55.773 | 52.175 | 56.59 | 0.00 | 31.787 | 23.986 | 20.388 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.0 | 13.0 | -100.0 | G35T2 | pj7389 pj7392 | 7 6
H/18-3 | SGBM19 | Mar 28 2016 9:40AM | Mar 29 2016 11:50AM | Mar 29 2016 3:20PM | Mar 29 2016 3:55PM | 54.943 | 50.575 | 55.89 | 0.00 | 23.692 | 87.143 | 26.883 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 16.0 | -100.0 | G45T2 | pj7377 pj7378 | 8 8
J/18-1 | SGBM19 | Mar 26 2016 11:10AM | Mar 28 2016 4:30PM | Mar 29 2016 12:45AM | Mar 29 2016 1:45AM | 55.336 | 51.375 | 56.18 | 0.00 | 24.582 | 86.936 | 26.793 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 13.0 | -100.0 | G45T2 | pj7372 pj7373 | 7 6
R/10-1 | SGBM31 | Mar 26 2016 4:15PM | Mar 28 2016 10:00AM | Mar 28 2016 1:40PM | Mar 28 2016 2:40PM | 55.823 | 54.475 | 56.17 | 0.00 | 27.174 | 84.823 | 27.301 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.1 | 14.0 | -100.0 | G35T2 | pj7334 pj7335 | 7 7
G/18-1 | SGBM19 | Mar 26 2016 10:30AM | Mar 26 2016 6:00PM | Mar 26 2016 9:20PM | Mar 26 2016 10:25PM | 54.644 | 51.375 | 55.45 | 0.00 | 23.652 | 30.992 | 27.723 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 18.0 | -100.0 | G45T2 | pj7298 pj7299 | 9 9
R/12-1 | SGBM31 | Mar 25 2016 8:00AM | Mar 26 2016 5:00PM | Mar 26 2016 7:30PM | Mar 26 2016 9:15PM | 55.72 | 54.475 | 56.58 | 0.00 | 27.483 | 28.237 | 26.992 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 14.0 | -100.0 | G35T2 | pj7287 pj7295 | 7 7
R/11-1 | SGBM31 | Mar 24 2016 8:10PM | Mar 25 2016 7:00PM | Mar 26 2016 3:20PM | Mar 26 2016 3:55PM | 55.705 | 54.475 | 56.47 | 0.00 | 26.975 | 85.205 | 27.500 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 14.0 | 15.2 | G35T2 | pj7268 pj7269 | 7 7
R/13-1 | SGBM22 | Mar 25 2016 8:40AM | Mar 25 2016 8:30PM | Mar 25 2016 11:30PM | Mar 26 2016 12:25AM | 55.78 | 54.475 | 56.64 | 0.00 | 27.336 | 28.444 | 27.139 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 14.0 | -12.0 | G35T2 | pj7233 pj7238 | 7 7
Ga/Yb-1 | SGBM31 | Mar 24 2016 3:00PM | Mar 25 2016 2:30PM | Mar 25 2016 4:20PM | Mar 25 2016 5:45PM | 55.456 | 54.475 | 56.45 | 0.00 | 31.349 | 24.107 | 23.126 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | -100.0 | G35T2 | pj7194 pj7198 | 7 7
H/Yb-1 | SGBM31 | Mar 24 2016 2:30PM | Mar 24 2016 9:00PM | Mar 24 2016 10:30PM | Mar 24 2016 11:37PM | 55.605 | 54.475 | 56.49 | 0.00 | 31.395 | 24.210 | 23.080 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 15.0 | -100.0 | G35T2 | pj7173 pj7174 | 8 7
L/Yb-1 | SGBM31 | Mar 23 2016 5:00PM | Mar 23 2016 9:05PM | Mar 23 2016 10:30PM | Mar 23 2016 11:30PM | 55.578 | 54.475 | 56.39 | 0.00 | 31.091 | 24.487 | 23.384 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 13.0 | -100.0 | G35T2 | pj7124 pj7125 | 7 6
M/Yb-1 | SGBM31 | Mar 23 2016 2:00PM | Mar 23 2016 6:00PM | Mar 23 2016 9:05PM | Mar 23 2016 10:16PM | 55.72 | 55.075 | 56.64 | 0.00 | 31.440 | 24.280 | 23.635 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.4 | 13.0 | 24.5 | G35T2 | pj7122 pj7123 | 7 6
K/Yb-1 | SGBM31 | Mar 22 2016 3:30PM | Mar 23 2016 12:00PM | Mar 23 2016 3:15PM | Mar 23 2016 4:40PM | 55.699 | 54.475 | 56.53 | 0.00 | 31.425 | 24.274 | 23.050 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | -100.0 | G35T2 | pj7102 pj7103 | 7 7
J/Yb-1 | SGBM31 | Mar 21 2016 11:00AM | Mar 22 2016 11:00AM | Mar 22 2016 10:00PM | Mar 22 2016 10:55PM | 55.73 | 54.475 | 56.47 | 0.00 | 32.169 | 23.561 | 22.306 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 17.0 | 72.5 | G35T2 | pj7070 pj7071 | 8 9
Q/13a-1 | SGBM23 | Mar 19 2016 3:15PM | Mar 19 2016 8:15PM | Mar 19 2016 9:15PM | Mar 19 2016 10:26PM | 55.855 | 55.075 | 56.68 | 0.00 | 28.283 | 84.255 | 26.792 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 14.0 | 18.3 | G35T2 | pj6962 pj6963 | 7 7
P/2-1 | SGBM31 | Mar 18 2016 11:00AM | Mar 19 2016 10:15AM | Mar 19 2016 9:00PM | Mar 19 2016 10:17PM | 55.674 | 55.075 | 56.52 | 0.00 | 27.524 | 28.150 | 27.551 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 16.0 | -100.0 | G35T2 | pj6960 pj6961 | 8 8
P/10-1 | SGBM23 | Mar 17 2016 2:00PM | Mar 18 2016 6:00PM | Mar 18 2016 8:50PM | Mar 18 2016 10:13PM | 55.9 | 51.075 | 56.70 | 0.00 | 23.896 | 32.800 | 27.179 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 20.0 | -12.0 | G35T2 | pj6923 pj6926 | 10 10
L/2-1 | SGBM19 | Mar 17 2016 11:00AM | Mar 18 2016 6:00PM | Mar 18 2016 5:10PM | Mar 18 2016 6:56PM | 55.58 | 55.075 | 0.00 | 0.00 | -29.200 | 84.780 | 84.275 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 37.2 | 17.0 | -100.0 | G35T2 | pj6907 pj6912 | 8 9
J/2-1 | SGBM31 | Mar 17 2016 1:00PM | Mar 17 2016 7:00PM | Mar 18 2016 3:15PM | Mar 18 2016 4:20PM | 55.47 | 55.075 | 56.24 | 0.00 | 27.137 | 28.333 | 27.938 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 16.0 | -100.0 | G35T2 | pj6903 pj6904 | 8 8
P/7-1 | SGBM20 | Mar 16 2016 5:55PM | Mar 17 2016 1:55PM | Mar 17 2016 5:10PM | Mar 17 2016 6:15PM | 55.98 | 55.075 | 56.91 | 0.00 | 28.108 | 27.872 | 26.967 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 15.0 | 25.9 | G35T2 | c480018578 c480018581 | 10 5
K/2-1 | SGBM31 | Mar 16 2016 1:00PM | Mar 16 2016 8:15PM | Mar 17 2016 1:30PM | Mar 17 2016 3:00PM | 55.508 | 55.075 | 56.42 | 0.00 | 27.125 | 28.383 | 27.950 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 16.0 | -100.0 | G35T2 | pj6853 pj6857 | 8 8
H/2-1 | SGBM22 | Mar 16 2016 11:10AM | Mar 16 2016 6:50PM | Mar 17 2016 11:00AM | Mar 17 2016 12:35PM | 55.45 | 55.075 | 0.00 | 0.00 | -29.200 | 84.650 | 84.275 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 37.2 | 16.0 | -100.0 | G35T2 | pj6850 pj6851 | 8 8
T1b/50-1 | SGBM31 | Mar 15 2016 9:30AM | Mar 15 2016 5:00PM | Mar 15 2016 6:30PM | Mar 15 2016 7:26PM | 51.777 | 51.175 | 52.29 | 0.00 | 25.189 | 78.877 | 25.986 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 15.0 | 30.6 | G45T2 | pj6748 pj6750 | 7 8
P/9-1 | SGBM20 | Mar 14 2016 4:00PM | Mar 15 2016 11:30AM | Mar 15 2016 2:30PM | Mar 15 2016 4:05PM | 55.78 | 55.075 | 56.71 | 0.00 | 28.906 | 26.874 | 26.169 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.6 | 15.0 | -100.0 | G35T2 | pj6732 pj6738 | 8 7
T1b/49-1 | SGBM31 | Mar 14 2016 2:00PM | Mar 14 2016 6:55PM | Mar 14 2016 9:35PM | Mar 14 2016 10:51PM | 51.777 | 51.175 | 52.53 | 0.00 | 24.926 | 79.377 | 26.249 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.6 | 15.0 | 29.3 | G45T2 | 1 2 | 8 7
Tb/45-1 | SGBM31 | Mar 14 2016 8:30AM | Mar 14 2016 1:00PM | Mar 14 2016 8:25PM | Mar 14 2016 9:27PM | 51.827 | 50.575 | 52.68 | 0.00 | 25.077 | 26.750 | 25.498 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 15.0 | -100.0 | G35T2 | 1 2 | 8 7
Tb/44-1 | SGBM31 | Mar 12 2016 10:00AM | Mar 12 2016 7:50PM | Mar 12 2016 10:55PM | Mar 12 2016 11:41PM | 51.972 | 50.575 | 52.80 | 0.00 | 31.297 | 20.675 | 19.278 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
Tb/43-1 | SGBM31 | Mar 12 2016 9:00AM | Mar 12 2016 5:30PM | Mar 12 2016 9:55PM | Mar 12 2016 10:52PM | 52.062 | 50.575 | 52.81 | 0.00 | 29.910 | 22.152 | 20.665 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.1 | 13.0 | -9.1 | G35T2 | 1 2 | 7 6
Tb/42-1 | SGBM31 | Mar 12 2016 11:20AM | Mar 12 2016 2:50PM | Mar 12 2016 8:50PM | Mar 12 2016 9:46PM | 52.23 | 50.575 | 52.94 | 0.00 | 30.841 | 21.389 | 19.734 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
P/8-1 | SGBM20 | Mar 12 2016 8:00AM | Mar 12 2016 4:45PM | Mar 12 2016 8:30PM | Mar 12 2016 9:15PM | 55.884 | 55.075 | 56.81 | 0.00 | 29.413 | 26.471 | 25.662 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 16.0 | -100.0 | G35T2 | pj6672 pj6675 | 8 8
Ta/42-1 | SGBM31 | Mar 11 2016 8:30AM | Mar 11 2016 12:00PM | Mar 11 2016 9:20PM | Mar 11 2016 10:46PM | 52.273 | 50.575 | 53.12 | 0.00 | 30.420 | 21.853 | 20.155 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.9 | 13.0 | -8.9 | G35T2 | 1 2 | 7 6
Tb/41-1 | SGBM31 | Mar 9 2016 10:15AM | Mar 10 2016 3:10PM | Mar 10 2016 9:50PM | Mar 10 2016 10:31PM | 52.289 | 50.575 | 53.13 | 0.00 | 31.535 | 20.754 | 19.040 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 15.0 | -100.0 | G35T2 | 1 2 | 9 6
Na/47-1 | SGBM31 | Mar 10 2016 10:00AM | Mar 10 2016 1:55PM | Mar 10 2016 7:25PM | Mar 10 2016 8:42PM | 51.937 | 50.175 | 52.81 | 0.00 | 25.612 | 26.325 | 24.563 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.9 | 14.0 | -10.8 | G35T2 | PJ6566 PJ6569 | 7 7
Na/41-1 | SGBM31 | Mar 9 2016 10:40AM | Mar 9 2016 4:00PM | Mar 10 2016 12:25AM | Mar 10 2016 1:31AM | 51.992 | 51.375 | 52.82 | 0.00 | 30.624 | 74.192 | 20.751 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.2 | 13.0 | -9.2 | G45T2 | 1 2 | 6 7
Na/42-1 | SGBM31 | Mar 9 2016 9:00AM | Mar 9 2016 7:17PM | Mar 9 2016 10:55PM | Mar 10 2016 12:15AM | 52.091 | 51.375 | 52.91 | 0.00 | 30.914 | 21.177 | 20.461 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.0 | 13.0 | -9.0 | G45T2 | pj6531 Pending | 7 6
Na/43-1 | SGBM31 | Mar 8 2016 1:15PM | Mar 8 2016 5:00PM | Mar 9 2016 12:05AM | Mar 9 2016 1:46AM | 52.058 | 51.375 | 52.71 | 0.00 | 29.706 | 22.352 | 21.669 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.6 | 14.0 | -100.0 | G45T2 | 1 2 | 8 6
Na/45-1 | SGBM31 | Mar 7 2016 1:25PM | Mar 8 2016 11:30AM | Mar 8 2016 9:08PM | Mar 8 2016 10:32PM | 52.088 | 51.375 | 52.83 | 0.00 | 27.933 | 24.155 | 23.442 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.4 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Ta/41-1 | SGBM15 | Mar 7 2016 9:45AM | Mar 8 2016 10:40AM | Mar 8 2016 7:54PM | Mar 8 2016 9:01PM | 52.477 | 50.575 | 53.36 | 0.00 | 30.860 | 21.617 | 19.715 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 12.0 | -100.0 | G35T2 | pj6462 pj6465 | 6 6
J/4-11 | SGBM22 | Mar 8 2016 1:00PM | Mar 8 2016 4:00PM | Mar 8 2016 6:37PM | Mar 8 2016 8:50PM | 55.49 | 54.275 | 56.38 | 0.00 | 47.379 | 29.111 | 6.896 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | 7.536 | 3.0 | 18.0 | -100.0 | G35T2 | PJ7756 PJ7789\n | 8 10
Na/44-1 | SGBM31 | Mar 7 2016 2:15PM | Mar 7 2016 6:25PM | Mar 7 2016 11:40PM | Mar 8 2016 12:52AM | 52.176 | 51.375 | 52.84 | 0.00 | 28.843 | 23.333 | 22.532 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.0 | 13.0 | -100.0 | G45T2 | pj6423 pj6424 | 7 6
N/59-6 | SGBM31 | Mar 4 2016 8:30AM | Mar 7 2016 1:00PM | Mar 7 2016 10:10PM | Mar 7 2016 11:47PM | 52.038 | 49.075 | 52.86 | 0.00 | 17.261 | 87.638 | 31.814 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.1 | 17.0 | 20.9 | G45T2 | pj6416 pj6419 | 8 9
Ta/45-1 | SGBM15 | Mar 4 2016 10:00AM | Mar 5 2016 9:15AM | Mar 5 2016 8:20PM | Mar 5 2016 9:22PM | 51.923 | 50.575 | 52.40 | 0.00 | 23.899 | 28.024 | 26.676 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 15.0 | -100.0 | G35T2 | 1 2 | 8 7
Ta/44-1 | SGBM31 | Mar 4 2016 10:30AM | Mar 5 2016 9:40AM | Mar 5 2016 4:25PM | Mar 5 2016 7:52PM | 51.963 | 50.575 | 52.87 | 0.00 | 30.071 | 21.892 | 20.504 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.1 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
Ta/43-1 | SGBM31 | Mar 4 2016 11:15AM | Mar 5 2016 1:34PM | Mar 5 2016 5:25PM | Mar 5 2016 6:30PM | 52.12 | 50.575 | 52.96 | 0.00 | 29.959 | 22.161 | 20.616 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.1 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
J/4-7 | SGBM22 | Mar 5 2016 8:12AM | Mar 5 2016 12:00PM | Mar 5 2016 1:25PM | Mar 5 2016 2:38PM | 55.555 | 54.275 | 56.28 | 0.00 | 26.279 | 29.276 | 27.996 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 18.0 | -100.0 | G35T2 | C480017867 C480017870 | 10 8
N/59-7 | SGBM31 | Mar 4 2016 9:15AM | Mar 4 2016 4:18PM | Mar 4 2016 8:10PM | Mar 4 2016 9:52PM | 52.062 | 49.075 | 52.94 | 0.00 | 17.440 | 87.562 | 31.635 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.0 | 18.0 | 28.8 | G45T2 | 1 2 | 8 10
J/4-12 | SGBM22 | Mar 4 2016 8:10AM | Mar 4 2016 12:00PM | Mar 4 2016 4:25PM | Mar 4 2016 6:38PM | 55.524 | 54.275 | 56.73 | 0.00 | 26.433 | 29.091 | 27.842 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 17.0 | -100.0 | G35T2 | PJ6336 PJ6338 | 9 8
T1b/51-1 | SGBM15 | Mar 3 2016 9:30AM | Mar 3 2016 3:20PM | Mar 3 2016 10:00PM | Mar 3 2016 11:16PM | 51.899 | 51.375 | 52.69 | 0.00 | 24.391 | 27.508 | 26.984 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
T/59-3 | SGBM31 | Mar 3 2016 8:30AM | Mar 3 2016 12:55PM | Mar 3 2016 8:15PM | Mar 3 2016 9:31PM | 52.031 | 49.075 | 52.88 | 0.00 | 23.380 | 28.651 | 25.695 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.4 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
T/59-6 | SGBM31 | Mar 3 2016 11:50AM | Mar 3 2016 4:40PM | Mar 3 2016 6:55PM | Mar 3 2016 8:12PM | 52.011 | 49.075 | 52.80 | 0.00 | 23.297 | 28.714 | 25.778 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.4 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
J/4-9 | SGBM22 | Mar 3 2016 8:11AM | Mar 3 2016 12:36PM | Mar 3 2016 3:00PM | Mar 3 2016 4:32PM | 55.5 | 54.275 | 56.30 | 0.00 | 26.700 | 28.800 | 27.575 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 17.0 | -100.0 | G35T2 | PJ6290 PJ6292 | 9 8
N/60a-1 | SGBM31 | Mar 2 2016 10:35AM | Mar 2 2016 6:55PM | Mar 3 2016 12:20AM | Mar 3 2016 1:45AM | 51.951 | 51.375 | 0.00 | 0.00 | -30.000 | 81.951 | 81.375 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 36.0 | 17.0 | -100.0 | G45T2 | 1 2 3 | 8 7 2
N/59-3 | SGBM31 | Mar 2 2016 9:30AM | Mar 2 2016 3:30PM | Mar 2 2016 9:50PM | Mar 2 2016 11:21PM | 52.136 | 49.075 | 52.93 | 0.00 | 17.134 | 35.002 | 31.941 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.1 | 18.0 | -100.0 | G45T2 | 1 2 3 | 9 7 2
J/4-5 | SGBM22 | Mar 2 2016 11:15AM | Mar 2 2016 3:26PM | Mar 2 2016 8:45PM | Mar 2 2016 10:10PM | 55.48 | 54.275 | 56.20 | 0.00 | 26.196 | 29.284 | 28.079 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 17.0 | -12.4 | G35T2 | PJ6264 PJ6266 | 9 8
P/49a-1 | SGBM15 | Mar 2 2016 8:40AM | Mar 2 2016 5:30PM | Mar 2 2016 7:45PM | Mar 2 2016 9:01PM | 51.943 | 50.575 | 52.80 | 0.00 | 25.101 | 26.842 | 25.474 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 14.0 | -100.0 | G35T2 | pj6258 pj6262 | 7 7
N/59-1 | SGBM31 | Mar 1 2016 2:40PM | Mar 2 2016 9:20AM | Mar 2 2016 7:30PM | Mar 2 2016 9:00PM | 52.14 | 49.075 | 53.15 | 0.00 | 17.547 | 34.593 | 31.528 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.9 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
T1b/52-1 | SGBM23 | Mar 1 2016 5:00PM | Mar 2 2016 11:30AM | Mar 2 2016 3:15PM | Mar 2 2016 4:46PM | 51.934 | 51.375 | 52.82 | 0.00 | 24.322 | 27.612 | 27.053 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
T/59-2 | SGBM15 | Feb 29 2016 2:40PM | Mar 1 2016 3:46PM | Mar 2 2016 12:00AM | Mar 2 2016 1:50AM | 52.041 | 49.075 | 52.77 | 0.00 | 23.671 | 28.370 | 25.404 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
N/59-8 | SGBM31 | Feb 29 2016 11:45AM | Mar 1 2016 12:05PM | Mar 1 2016 9:55PM | Mar 1 2016 10:46PM | 51.994 | 49.075 | 52.81 | 0.00 | 17.607 | 34.387 | 31.468 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.9 | 17.0 | -100.0 | G45T2 | pj6226 pj6228 | 8 9
J/4-6 | SGBM22 | Mar 1 2016 1:10PM | Mar 1 2016 4:50PM | Mar 1 2016 6:50PM | Mar 1 2016 8:10PM | 55.53 | 54.275 | 56.36 | 0.00 | 26.363 | 29.167 | 27.912 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 17.0 | -100.0 | G35T2 | C520125653 C480017657 | 7 10
J/4-1 | SGBM22 | Mar 1 2016 8:10AM | Mar 1 2016 12:44PM | Mar 1 2016 5:55PM | Mar 1 2016 7:35PM | 55.54 | 54.275 | 56.46 | 0.00 | 26.459 | 29.081 | 27.816 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 17.0 | -100.0 | G35T2 | C480017647 C520125652 | 7 10
T1b/53-1 | SGBM23 | Feb 29 2016 5:25PM | Mar 1 2016 11:30AM | Mar 1 2016 4:20PM | Mar 1 2016 6:00PM | 51.983 | 51.375 | 52.69 | 0.00 | 24.995 | 26.988 | 26.380 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.7 | 15.0 | -100.0 | G45T2 | pj6211 pj6214 | 8 7
T/59-8 | SGBM15 | Feb 29 2016 2:15PM | Mar 1 2016 10:10AM | Mar 1 2016 2:45PM | Mar 1 2016 3:55PM | 52.073 | 49.075 | 52.87 | 0.00 | 23.167 | 28.906 | 25.908 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.4 | 15.0 | -100.0 | G45T2 | pj6206 pj6207 | 8 7
N/59-2 | SGBM31 | Feb 29 2016 11:20AM | Feb 29 2016 4:40PM | Feb 29 2016 8:40PM | Feb 29 2016 10:10PM | 52.138 | 49.075 | 53.01 | 0.00 | 17.908 | 34.230 | 31.167 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
M/8-1 | SGBM22 | Feb 27 2016 10:00AM | Feb 27 2016 5:00PM | Feb 27 2016 7:45PM | Feb 27 2016 9:45PM | 55.936 | 55.075 | 56.97 | 0.00 | 28.372 | 27.564 | 26.703 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 20.0 | -100.0 | G35T2 | PJ6140 PJ6146 | 10 10
T1b/54-1 | SGBM31 | Feb 27 2016 8:30AM | Feb 27 2016 12:35PM | Feb 27 2016 3:50PM | Feb 27 2016 5:35PM | 51.95 | 51.075 | 52.82 | 0.00 | 24.324 | 27.626 | 26.751 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 15.0 | -100.0 | G45T2 | pj6117 pj6126 | 8 7
T/49a-1 | SGBM23 | Feb 26 2016 4:20PM | Feb 27 2016 10:45AM | Feb 27 2016 2:15PM | Feb 27 2016 3:25PM | 51.947 | 51.375 | 0.00 | 0.00 | -29.300 | 81.247 | 80.675 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 35.6 | 16.0 | -32.7 | G45T2 | pj6107 pj6112 | 8 8
T/59-1 | SGBM31 | Feb 26 2016 11:00AM | Feb 26 2016 6:50PM | Feb 27 2016 2:30AM | Feb 27 2016 3:46AM | 51.95 | 49.075 | 52.71 | 0.00 | 23.309 | 28.641 | 25.766 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.4 | 16.0 | -11.4 | G45T2 | 1 2 | 8 8
T/59-7 | SGBM31 | Feb 26 2016 10:30AM | Feb 26 2016 4:55PM | Feb 27 2016 2:30AM | Feb 27 2016 3:45AM | 52.073 | 49.075 | 52.97 | 0.00 | 23.575 | 28.498 | 25.500 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 16.0 | -11.3 | G45T2 | 1 2 | 8 8
J/4-2 | SGBM22 | Feb 26 2016 12:05PM | Feb 26 2016 4:50PM | Feb 26 2016 7:05PM | Feb 26 2016 10:54PM | 55.51 | 54.275 | 56.33 | 0.00 | 26.329 | 29.181 | 27.946 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 19.0 | -100.0 | G35T2 | PJ6060 PJ6064 PJ6074 | 8 9 2
N/59-5 | SGBM31 | Feb 25 2016 11:30AM | Feb 26 2016 10:05AM | Feb 26 2016 4:30PM | Feb 26 2016 6:00PM | 52.081 | 49.075 | 52.97 | 0.00 | 17.469 | 34.612 | 31.606 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.0 | 19.0 | -14.0 | G45T2 | pj6045 pj6050 | 10 9
J/4-3 | SGBM22 | Feb 25 2016 10:00AM | Feb 25 2016 7:00PM | Feb 25 2016 9:40PM | Feb 25 2016 10:55PM | 55.55 | 54.275 | 56.43 | 0.00 | 26.429 | 29.121 | 27.846 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 17.0 | -100.0 | G35T2 | PJ6025 PJ6028 | 8 9
N/59-4 | SGBM31 | Feb 25 2016 10:50AM | Feb 25 2016 4:05PM | Feb 25 2016 9:30PM | Feb 25 2016 10:40PM | 52.039 | 49.075 | 52.79 | 0.00 | 17.794 | 34.245 | 31.281 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 17.0 | -100.0 | G45T2 | pj6024 pj6027 | 9 8
T/59-4 | SGBM31 | Feb 24 2016 11:30AM | Feb 25 2016 9:46AM | Feb 25 2016 6:15PM | Feb 25 2016 7:10PM | 52.078 | 49.075 | 52.91 | 0.00 | 23.709 | 28.369 | 25.366 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 15.0 | -11.2 | G45T2 | pj6008 pj6009 | 8 7
T/59-5 | SGBM31 | Feb 24 2016 10:40AM | Feb 24 2016 6:00PM | Feb 24 2016 10:40PM | Feb 25 2016 12:20AM | 52.014 | 49.075 | 52.87 | 0.00 | 23.768 | 28.246 | 25.307 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 16.0 | 4.8 | G45T2 | 1 2 | 6 10
P/60a-1 | SGBM23 | Feb 23 2016 5:30PM | Feb 24 2016 10:36AM | Feb 24 2016 7:25PM | Feb 24 2016 8:00PM | 52.273 | 51.375 | 52.99 | 0.00 | 28.995 | 23.278 | 22.380 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 12.0 | 2.1 | G45T2 | PJ5957 PJ5958 | 6 6
Q/62-1 | SGBM31 | Feb 24 2016 9:40AM | Feb 24 2016 1:35PM | Feb 24 2016 4:10PM | Feb 24 2016 5:55PM | 50.744 | 49.925 | 51.55 | 0.00 | 27.650 | 23.094 | 22.275 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 12.0 | -100.0 | G45T2 | PJ5946 PJ5949 | 6 6
T1b/56-1 | SGBM08 | Feb 23 2016 10:00AM | Feb 23 2016 4:30PM | Feb 23 2016 11:50PM | Feb 24 2016 1:15AM | 51.922 | 51.375 | 52.63 | 0.00 | 26.231 | 25.691 | 25.144 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 12.0 | -100.0 | G45T2 | 1 2 | 7 5
R/62-1 | SGBM31 | Feb 20 2016 5:25PM | Feb 23 2016 6:18PM | Feb 23 2016 11:15PM | Feb 24 2016 12:30AM | 50.568 | 49.925 | 0.00 | 0.00 | -22.600 | 73.168 | 72.525 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 32.0 | 12.0 | -62.6 | G45T2 | 1 2 | 6 6
M/7-1 | SGBM22 | Feb 23 2016 12:05PM | Feb 23 2016 4:46PM | Feb 23 2016 10:20PM | Feb 23 2016 11:20PM | 55.896 | 55.075 | 56.81 | 0.00 | 28.315 | 27.581 | 26.760 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 16.0 | -100.0 | G35T2 | PJ5927 PJ5930 | 8 8
S/60a-1 | SGBM23 | Feb 23 2016 10:10AM | Feb 23 2016 5:20PM | Feb 23 2016 9:20PM | Feb 23 2016 10:25PM | 52.043 | 51.375 | 52.88 | 0.00 | 32.281 | 19.762 | 19.094 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 12.0 | 3.6 | G45T2 | 1 2 | 6 6
Q/49a-1 | SGBM08 | Feb 22 2016 3:00PM | Feb 23 2016 10:46AM | Feb 23 2016 6:40PM | Feb 23 2016 9:07PM | 51.931 | 51.375 | 52.85 | 0.00 | 26.253 | 25.678 | 25.122 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 17.0 | -100.0 | G45T2 | pj5910 pj5906 pj5919 | 7 8 2
T/60a-1 | SGBM23 | Feb 23 2016 9:25AM | Feb 23 2016 2:15PM | Feb 23 2016 7:45PM | Feb 23 2016 8:45PM | 52.062 | 50.375 | 52.90 | 0.00 | 26.097 | 25.965 | 24.278 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 14.0 | -100.0 | G45T2 | PJ5911 PJ5913 | 7 7
T1b/61-1 | SGBM31 | Feb 22 2016 4:00PM | Feb 22 2016 6:45PM | Feb 22 2016 11:00PM | Feb 22 2016 11:43PM | 51.996 | 50.775 | 52.85 | 0.00 | 32.255 | 19.741 | 18.520 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.2 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
X1/Ya-2 | SGBM21 | Feb 22 2016 3:40PM | Feb 22 2016 6:50PM | Feb 22 2016 7:10PM | Feb 22 2016 8:40PM | 55.999 | 54.175 | 56.89 | 0.00 | 27.891 | 28.108 | 26.284 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 17.0 | -11.6 | G35T2 | PJ5858 PJ5861 | 9 8
S/49a-1 | SGBM08 | Feb 19 2016 10:00AM | Feb 22 2016 11:45AM | Feb 22 2016 6:20PM | Feb 22 2016 7:31PM | 52.029 | 51.375 | 52.80 | 0.00 | 22.899 | 29.130 | 28.476 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.6 | 15.0 | 19.2 | G45T2 | PJ5851 PJ5855 | 8 7
AE/56-1 | SGBM31 | Feb 22 2016 9:37AM | Feb 22 2016 1:47PM | Feb 22 2016 4:25PM | Feb 22 2016 6:15PM | 49.581 | 48.475 | 50.43 | 0.00 | 23.430 | 26.153 | 25.045 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 16.0 | -100.0 | G45T2 | PJ5842 PJ5847 | 8 8
Q/62a-1 | SGBM05 | Feb 20 2016 8:45AM | Feb 20 2016 4:00PM | Feb 20 2016 11:45PM | Feb 22 2016 12:40AM | 50.709 | 50.775 | 51.06 | 0.00 | 22.064 | 28.645 | 28.711 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.7 | 14.0 | -12.7 | G45T2 | 1 2 | 7 7
X3/Ya-2 | SGBM21 | Feb 20 2016 9:12AM | Feb 20 2016 1:20PM | Feb 20 2016 7:05PM | Feb 20 2016 10:15PM | 55.698 | 54.175 | 56.51 | 0.00 | 47.513 | 28.185 | 6.662 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 2.9 | 22.0 | -100.0 | G35T2 | PJ5809 PJ5818 PJ5825 | 10 7 5
R/49a-1 | SGBM08 | Feb 19 2016 8:15AM | Feb 20 2016 12:00PM | Feb 20 2016 8:30PM | Feb 20 2016 9:15PM | 52.042 | 51.375 | 52.92 | 0.00 | 21.821 | 30.221 | 29.554 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.1 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
AC/55-1 | SGBM31 | Feb 20 2016 10:25AM | Feb 20 2016 3:05PM | Feb 20 2016 5:15PM | Feb 20 2016 6:55PM | 49.617 | 49.075 | 50.49 | 0.00 | 23.994 | 25.623 | 25.081 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G45T2 | PJ5797 PJ5802 | 8 7
AD/53-1 | SGBM20 | Feb 20 2016 10:00AM | Feb 20 2016 1:47PM | Feb 20 2016 2:25PM | Feb 20 2016 3:55PM | 49.905 | 49.075 | 51.17 | 0.00 | 23.867 | 26.038 | 25.208 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G45T2 | PJ5781 PJ5783 | 7 8
P/62a-1 | SGBM05 | Feb 18 2016 2:00PM | Feb 19 2016 3:44PM | Feb 19 2016 11:10PM | Feb 20 2016 12:23AM | 50.516 | 50.775 | 51.52 | 0.00 | 20.216 | 30.300 | 30.559 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.5 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
AE/55-1 | SGBM31 | Feb 19 2016 9:25AM | Feb 19 2016 4:00PM | Feb 19 2016 5:50PM | Feb 19 2016 7:25PM | 49.608 | 48.475 | 50.40 | 0.00 | 23.405 | 26.203 | 25.070 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G45T2 | PJ5746 PJ5750 | 8 7
AD/52-1 | SGBM20 | Feb 19 2016 9:15AM | Feb 19 2016 3:30PM | Feb 19 2016 5:05PM | Feb 19 2016 6:30PM | 49.796 | 49.075 | 50.81 | 0.00 | 23.811 | 25.985 | 25.264 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 15.0 | -100.0 | G45T2 | PJ5741 PJ5745 | 8 7
T1b/57-1 | SGBM05 | Feb 17 2016 2:15PM | Feb 18 2016 11:45AM | Feb 18 2016 8:50PM | Feb 18 2016 10:10PM | 51.914 | 51.375 | 52.74 | 0.00 | 25.342 | 26.572 | 26.033 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
AE/52-1 | SGBM20 | Feb 17 2016 10:10AM | Feb 18 2016 1:05PM | Feb 18 2016 6:40PM | Feb 18 2016 9:00PM | 49.956 | 48.475 | 50.84 | 0.00 | 23.440 | 26.516 | 25.035 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 16.0 | -100.0 | G45T2 | PJ5702 PJ5709 | 8 8
X3/Ya-1 | SGBM21 | Feb 18 2016 8:15AM | Feb 18 2016 1:23PM | Feb 18 2016 5:45PM | Feb 18 2016 7:27PM | 55.694 | 54.175 | 56.46 | 0.00 | 27.959 | 27.735 | 26.216 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 16.0 | -100.0 | G35T2 | PJ5696 PJ5703 | 8 8
AE/53-1 | SGBM31 | Feb 18 2016 9:15AM | Feb 18 2016 2:20PM | Feb 18 2016 3:50PM | Feb 18 2016 5:40PM | 49.925 | 49.075 | 50.72 | 0.00 | 23.518 | 26.407 | 25.557 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 15.0 | -100.0 | G45T2 | PJ5687 PJ5690 | 8 7
X0/Ya-2 | SGBM21 | Feb 17 2016 10:10AM | Feb 17 2016 3:05PM | Feb 17 2016 11:05PM | Feb 18 2016 1:16AM | 56.099 | 54.175 | 57.15 | 0.00 | 28.154 | 27.945 | 26.021 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.5 | 17.0 | -100.0 | G35T2 | PJ5661 PJ5668 | 8 9
R/62a-1 | SGBM05 | Feb 16 2016 9:15AM | Feb 17 2016 11:17AM | Feb 17 2016 11:30PM | Feb 18 2016 12:35AM | 50.514 | 50.775 | 51.19 | 0.00 | 22.390 | 28.124 | 28.385 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
AE/54-1 | SGBM31 | Feb 17 2016 10:20AM | Feb 17 2016 3:45PM | Feb 17 2016 4:40PM | Feb 17 2016 5:53PM | 49.824 | 48.475 | 50.65 | 0.00 | 23.447 | 26.377 | 25.028 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G45T2 | PJ5638 PJ5642 | 8 7
X2/Ya-1 | SGBM17 | Feb 16 2016 10:35AM | Feb 16 2016 3:45PM | Feb 16 2016 9:35PM | Feb 16 2016 11:51PM | 55.865 | 54.175 | 56.90 | 0.00 | 27.895 | 27.970 | 26.280 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 20.0 | -100.0 | G35T2 | PJ5617 PJ5619 PJ5626 | 8 8 4
AA/62a-1 | SGBM31 | Feb 15 2016 3:35PM | Feb 16 2016 3:35PM | Feb 16 2016 7:45PM | Feb 16 2016 8:50PM | 48.568 | 47.855 | 49.56 | 0.00 | 23.364 | 25.204 | 24.491 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.8 | 14.0 | -100.0 | G35T2 | PJ5605 PJ5608 | 7 7
N/62a-1 | SGBM08 | Feb 13 2016 1:15PM | Feb 15 2016 3:00PM | Feb 15 2016 11:20PM | Feb 16 2016 12:17AM | 51.323 | 50.775 | 51.78 | 0.00 | 26.179 | 76.923 | 24.596 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.9 | 13.0 | -10.9 | G45T2 | 1 2 | 7 6
R/58-1 | SGBM05 | Jan 16 2016 2:05PM | Feb 15 2016 4:05PM | Feb 15 2016 7:15PM | Feb 15 2016 8:30PM | 51.923 | 51.375 | 52.81 | 0.00 | 23.810 | 28.113 | 27.565 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 13.0 | 6.7 | G45T2 | 1 2 | 7 6
X1/Ya-1 | SGBM21 | Feb 15 2016 8:39AM | Feb 15 2016 1:48PM | Feb 15 2016 4:10PM | Feb 15 2016 6:22PM | 55.949 | 54.175 | 56.72 | 0.00 | 28.115 | 27.834 | 26.060 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.5 | 17.0 | -11.5 | G35T2 | PJ5523 PJ5528 | 8 9
AC/54-1 | SGBM31 | Feb 13 2016 8:20AM | Feb 13 2016 2:00PM | Feb 13 2016 4:55PM | Feb 13 2016 6:20PM | 49.592 | 49.075 | 50.34 | 0.00 | 23.336 | 26.256 | 25.739 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.4 | 13.0 | -100.0 | G45T2 | PJ5483 PJ5487 | 7 6
Xa/Ya-2 | SGBM21 | Feb 13 2016 8:15AM | Feb 13 2016 1:15PM | Feb 13 2016 3:05PM | Feb 13 2016 5:33PM | 56.016 | 54.175 | 56.92 | 0.00 | 27.716 | 28.300 | 26.459 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.7 | 19.0 | -11.7 | G35T2 | PJ5473 PJ5475 PJ5482 | 8 8 3
N/49-1 | SGBM08 | Feb 11 2016 4:15PM | Feb 13 2016 10:30AM | Feb 13 2016 2:55PM | Feb 13 2016 4:22PM | 51.696 | 51.375 | 52.56 | 0.00 | 22.062 | 29.634 | 29.313 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.0 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
X0/Ya-1 | SGBM21 | Feb 12 2016 9:32AM | Feb 12 2016 2:34PM | Feb 12 2016 7:35PM | Feb 12 2016 8:35PM | 55.879 | 54.175 | 56.47 | 0.00 | 27.465 | 28.414 | 26.710 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.8 | 18.0 | -100.0 | G35T2 | PJ5446 PJ5449 | 10 8
U/63-1 | SGBM20 | Feb 12 2016 9:40AM | Feb 12 2016 1:20PM | Feb 12 2016 5:30PM | Feb 12 2016 7:00PM | 50.429 | 51.375 | 51.51 | 0.00 | 30.915 | 19.514 | 20.460 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.0 | 12.0 | -9.0 | G45T2 | 1 2 | 6 6
S/62a-1 | SGBM05 | Feb 10 2016 8:30AM | Feb 11 2016 3:45PM | Feb 11 2016 10:45PM | Feb 12 2016 12:08AM | 50.531 | 49.775 | 50.77 | 0.00 | 22.671 | 27.860 | 27.104 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Xa/Ya-1 | SGBM21 | Feb 11 2016 9:32AM | Feb 11 2016 2:43PM | Feb 11 2016 8:50PM | Feb 11 2016 11:11PM | 56.215 | 54.175 | 57.92 | 0.00 | 27.923 | 28.292 | 26.252 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 21.0 | -100.0 | G35T2 | PJ5412 PJ5418 PJ5421 | 8 8 5
T2a/62-1 | SGBM20 | Feb 11 2016 3:05PM | Feb 11 2016 5:45PM | Feb 11 2016 6:30PM | Feb 11 2016 7:20PM | 51.399 | 51.375 | 52.21 | 0.00 | 33.411 | 17.988 | 17.964 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.9 | 10.0 | -100.0 | G45T2 | 1 | 10
M/5-1 | SGBM17 | Feb 11 2016 10:00AM | Feb 11 2016 3:00PM | Feb 11 2016 5:35PM | Feb 11 2016 7:15PM | 55.615 | 55.075 | 56.62 | 0.00 | 27.115 | 28.500 | 27.960 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 17.0 | -100.0 | G35T2 | PJ5401 PJ5405 | 10 7
AE/57-1 | SGBM31 | Feb 10 2016 5:30PM | Feb 11 2016 11:43AM | Feb 11 2016 2:30PM | Feb 11 2016 4:00PM | 49.626 | 48.475 | 50.53 | 0.00 | 22.835 | 26.791 | 25.640 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
T2a/61-1 | SGBM20 | Feb 10 2016 4:25PM | Feb 11 2016 10:45AM | Feb 11 2016 12:25PM | Feb 11 2016 2:20PM | 51.908 | 51.375 | 52.78 | 0.00 | 28.182 | 23.726 | 23.193 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Q/49-1 | SGBM05 | Feb 4 2016 12:55PM | Feb 10 2016 3:00PM | Feb 10 2016 8:00PM | Feb 10 2016 9:03PM | 51.88 | 51.375 | 52.76 | 0.00 | 22.160 | 29.720 | 29.215 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.9 | 18.0 | -12.9 | G45T2 | 1 2 | 8 10
AAa/62a-1 | SGBM31 | Feb 10 2016 8:00AM | Feb 10 2016 2:13PM | Feb 10 2016 6:10PM | Feb 10 2016 7:25PM | 48.563 | 46.475 | 49.34 | 0.00 | 22.239 | 26.324 | 24.236 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 15.0 | -100.0 | G35T2 | 5354 5358 | 8 7
Xa/Y0-2 | SGBM21 | Feb 10 2016 8:18AM | Feb 10 2016 1:47PM | Feb 10 2016 4:45PM | Feb 10 2016 6:37PM | 55.208 | 54.175 | 56.89 | 0.00 | 27.894 | 27.314 | 26.281 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 16.0 | -100.0 | G35T2 | PJ5345 PJ5350 | 8 8
Xa/Y1-2 | SGBM21 | Feb 4 2016 11:05AM | Feb 4 2016 3:46PM | Feb 4 2016 10:00PM | Feb 4 2016 11:58PM | 56.11 | 54.175 | 57.06 | 0.00 | 28.061 | 28.049 | 26.114 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.5 | 16.0 | -100.0 | G35T2 | PJ5309 PJ5314 | 8 8
M/4-1 | SGBM17 | Feb 4 2016 12:00PM | Feb 4 2016 6:00PM | Feb 4 2016 8:30PM | Feb 4 2016 10:25PM | 55.783 | 55.075 | 56.54 | 0.00 | 26.541 | 29.242 | 28.534 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.6 | 17.0 | -100.0 | G35T2 | PJ5302 PJ5307 | 8 9
T2a/54-1 | SGBM20 | Feb 4 2016 10:03AM | Feb 4 2016 3:35PM | Feb 4 2016 5:25PM | Feb 4 2016 7:00PM | 51.852 | 51.375 | 52.76 | 0.00 | 24.761 | 27.091 | 26.614 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 15.0 | -100.0 | G45T2 | 5287 5291 | 8 7
M7b/62a-1 | SGBM08 | Feb 2 2016 9:45AM | Feb 4 2016 11:48AM | Feb 4 2016 4:55PM | Feb 4 2016 6:02PM | 51.273 | 48.5 | 52.22 | 0.00 | 24.723 | 26.550 | 23.777 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.5 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
Xa/Y0-1 | SGBM21 | Feb 3 2016 10:05AM | Feb 3 2016 3:12PM | Feb 3 2016 9:00PM | Feb 3 2016 10:51PM | 56.167 | 54.175 | 57.62 | 0.00 | 28.022 | 28.145 | 26.153 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 16.0 | -100.0 | G35T2 | PJ5349 PJ5252 | 8 8
T/62a-1 | SGBM08 | Feb 2 2016 11:35AM | Feb 3 2016 9:00AM | Feb 3 2016 8:30PM | Feb 3 2016 9:32PM | 50.569 | 48.5 | 51.65 | 0.00 | 30.145 | 20.424 | 18.355 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
AAa/62-1 | SGBM31 | Feb 2 2016 3:05PM | Feb 3 2016 12:00PM | Feb 3 2016 2:30PM | Feb 3 2016 4:10PM | 49.297 | 47.075 | 50.14 | 0.00 | 23.038 | 26.259 | 24.037 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 15.0 | -100.0 | G35T2 | PJ5219 PJ5222 | 7 8
Xa/Y1-1 | SGBM21 | Feb 2 2016 11:00AM | Feb 2 2016 3:25PM | Feb 2 2016 8:05PM | Feb 2 2016 9:50PM | 55.961 | 54.175 | 56.66 | 0.00 | 27.860 | 28.101 | 26.315 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.6 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
AE/45-1 | SGBM22 | Dec 29 2015 7:10PM | Dec 30 2015 7:25PM | Jan 31 2016 1:35AM | Jan 31 2016 3:05AM | 49.282 | 48.475 | 50.18 | 0.00 | 19.381 | 29.901 | 29.094 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.9 | 16.0 | -100.0 | G45T2 | PJ3760 PJ3762 | 8 8
Ta/62a-1 | SGBM08 | Jan 29 2016 3:30PM | Jan 30 2016 5:18PM | Jan 30 2016 10:45PM | Jan 31 2016 12:32AM | 50.937 | 48.5 | 50.58 | 0.00 | 30.077 | 20.860 | 18.423 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 12.0 | -100.0 | G45T2 | 1 2 | 10 2
Xa/Y2-2 | SGBM21 | Jan 30 2016 9:00AM | Jan 30 2016 5:00PM | Jan 30 2016 8:20PM | Jan 30 2016 10:40PM | 55.839 | 54.275 | 56.43 | 0.00 | 28.933 | 27.500 | 25.342 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.2 | 21.0 | 87.6 | G35T2 | 1 2 | 11 10
M7a/62b-1 | SGBM08 | Jan 27 2016 1:30PM | Jan 30 2016 5:47PM | Jan 30 2016 8:10PM | Jan 30 2016 10:07PM | 51.542 | 48.5 | 52.46 | 0.00 | 25.462 | 26.080 | 23.038 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | 25.2 | G45T2 | 1 2 | 11 3
T2a/57-1 | SGBM20 | Jan 29 2016 4:50PM | Jan 30 2016 12:18PM | Jan 30 2016 5:45PM | Jan 30 2016 8:00PM | 51.833 | 51.375 | 52.79 | 0.00 | 26.591 | 25.242 | 24.784 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.0 | 15.0 | -100.0 | G45T2 | PJ5132 PJ5139 | 8 7
Xa/Y3-2 | SGBM21 | Jan 29 2016 1:30PM | Jan 29 2016 6:00PM | Jan 29 2016 10:40PM | Jan 30 2016 1:35AM | 55.904 | 54.275 | 56.84 | 0.00 | 29.140 | 26.764 | 25.135 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.1 | 21.0 | -100.0 | G35T2 | 1 2 3 | 8 8 5
Xa/Y2-1 | SGBM21 | Jan 29 2016 9:00AM | Jan 29 2016 12:43PM | Jan 29 2016 5:30PM | Jan 29 2016 7:05PM | 55.961 | 54.275 | 56.73 | 0.00 | 29.030 | 26.931 | 25.245 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.2 | 19.0 | 70.3 | G35T2 | 1 2 3 | 8 7 4
M/2-1 | SGBM19 | Jan 28 2016 9:00AM | Jan 28 2016 3:00PM | Jan 28 2016 7:35PM | Jan 28 2016 10:30PM | 55.722 | 55.075 | 56.49 | 0.00 | 24.694 | 31.028 | 30.381 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.4 | 20.0 | -100.0 | G35T2 | 1 2 3 | 8 8 4
AB/57-1 | SGBM31 | Jan 28 2016 8:10AM | Jan 28 2016 12:48PM | Jan 28 2016 3:35PM | Jan 28 2016 4:35PM | 49.521 | 49.075 | 50.40 | 0.00 | 23.104 | 26.417 | 25.971 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 15.0 | -100.0 | G45T2 | PJ5011 PJ5012 | 8 7
Xa/Y3-1 | SGBM21 | Jan 27 2016 12:00PM | Jan 27 2016 4:00PM | Jan 27 2016 8:00PM | Jan 27 2016 10:45PM | 55.818 | 54.275 | 56.58 | 0.00 | 29.083 | 26.735 | 25.192 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 11.1 | 18.0 | -100.0 | G35T2 | 1 2 3 | 7 6 5
Na/46-1 | SGBM01 | Jan 26 2016 12:00PM | Jan 27 2016 10:30AM | Jan 27 2016 6:25PM | Jan 27 2016 9:01PM | 51.809 | 50.575 | 52.56 | 0.00 | 27.463 | 24.346 | 23.112 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
T2a/53-1 | SGBM20 | Jan 27 2016 10:16AM | Jan 27 2016 3:00PM | Jan 27 2016 7:45PM | Jan 27 2016 9:00PM | 51.92 | 51.375 | 52.80 | 0.00 | 27.001 | 24.919 | 24.374 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.8 | 16.0 | -100.0 | G45T2 | PJ4971 PJ4974 | 8 8
Tb/62a-1 | SGBM08 | Jan 26 2016 11:45AM | Jan 27 2016 9:00AM | Jan 27 2016 3:30PM | Jan 27 2016 4:56PM | 50.502 | 48.5 | 50.95 | 0.00 | 30.246 | 20.256 | 18.254 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
Xa/Y4-1 | SGBM21 | Jan 27 2016 9:00AM | Jan 27 2016 12:00PM | Jan 27 2016 1:45PM | Jan 27 2016 4:19PM | 55.915 | 54.275 | 56.29 | 0.00 | 29.793 | 26.122 | 24.482 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.8 | 16.0 | -100.0 | G35T2 | 1 2 3 | 7 6 3
N/2-1 | SGBM19 | Jan 26 2016 1:00PM | Jan 26 2016 6:00PM | Jan 26 2016 11:50PM | Jan 27 2016 1:30AM | 55.763 | 55.075 | 56.60 | 0.00 | 24.795 | 30.968 | 30.280 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.4 | 17.0 | -100.0 | G35T2 | 1 2 | 9 8
Y/63-1 | SGBM31 | Jan 26 2016 8:22AM | Jan 26 2016 2:15PM | Jan 26 2016 11:40PM | Jan 27 2016 1:00AM | 49.65 | 49.075 | 50.39 | 0.00 | 18.890 | 30.760 | 30.185 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.3 | 15.0 | -100.0 | G45T2 | PJ4928 PJ4934 | 7 8
Xa/Y5-2 | SGBM19 | Jan 26 2016 11:00AM | Jan 26 2016 3:35PM | Jan 26 2016 7:05PM | Jan 26 2016 8:40PM | 55.72 | 54.275 | 56.45 | 0.00 | 29.754 | 25.966 | 24.521 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.8 | 17.0 | -100.0 | G35T2 | 1 2 | 8 9
M7/54-1 | SGBM08 | Jan 22 2016 4:15PM | Jan 26 2016 8:40AM | Jan 26 2016 2:15PM | Jan 26 2016 3:38PM | 52.084 | 50.925 | 52.91 | 0.00 | 19.607 | 32.477 | 31.318 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
AE/57a-1 | SGBM31 | Jan 23 2016 3:20PM | Jan 26 2016 10:00AM | Jan 26 2016 10:55AM | Jan 26 2016 12:40PM | 49.59 | 48.475 | 50.40 | 0.00 | 23.396 | 26.194 | 25.079 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 19.0 | 71.5 | G45T2 | PJ4873 PJ4874 PJ4876 | 8 7 4
M/3-1 | SGBM19 | Jan 23 2016 7:40AM | Jan 23 2016 3:00PM | Jan 23 2016 6:15PM | Jan 23 2016 7:50PM | 55.733 | 55.075 | 56.52 | 0.00 | 27.116 | 28.617 | 27.959 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 15.0 | -100.0 | G35T2 | 1 2 | 8 7
X5/Y9-1 | SGBM21 | Jan 23 2016 10:30AM | Jan 23 2016 1:31PM | Jan 23 2016 4:10PM | Jan 23 2016 6:00PM | 55.967 | 54.475 | 56.44 | 0.00 | 33.035 | 22.932 | 21.440 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.5 | 11.0 | -100.0 | G35T2 | 1 2 | 6 5
M/1-1 | SGBM19 | Jan 22 2016 11:00AM | Jan 22 2016 3:42PM | Jan 23 2016 12:10AM | Jan 23 2016 1:50AM | 55.696 | 55.075 | 56.29 | 0.00 | 27.290 | 28.406 | 27.785 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 15.0 | -12.3 | G35T2 | 1 2 | 8 7
Xa/Y6-2 | SGBM21 | Jan 22 2016 2:00PM | Jan 22 2016 4:58PM | Jan 23 2016 12:45AM | Jan 23 2016 1:50AM | 55.771 | 54.275 | 56.46 | 0.00 | 30.160 | 25.611 | 24.115 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.7 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
AE/58-1 | SGBM31 | Jan 22 2016 8:45AM | Jan 22 2016 5:00PM | Jan 22 2016 6:55PM | Jan 22 2016 10:15PM | 49.577 | 48.475 | 49.84 | 0.00 | 17.342 | 32.235 | 31.133 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 20.0 | -100.0 | G45T2 | 1 2 3 | 10 7 3
M7/52-1 | SGBM08 | Jan 20 2016 1:30PM | Jan 21 2016 5:50PM | Jan 22 2016 4:50PM | Jan 22 2016 6:13PM | 52.02 | 51.375 | 52.85 | 0.00 | 20.155 | 31.865 | 31.220 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 18.0 | -100.0 | G45T2 | 1 2 | 8 10
Xa/Y7-2 | SGBM21 | Jan 21 2016 1:00PM | Jan 22 2016 8:14AM | Jan 22 2016 10:25AM | Jan 22 2016 11:35AM | 55.715 | 54.275 | 56.93 | 0.00 | 30.128 | 25.587 | 24.147 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.7 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
Xa/Y5-1 | SGBM21 | Jan 21 2016 12:00PM | Jan 21 2016 4:13PM | Jan 21 2016 7:00PM | Jan 21 2016 9:15PM | 55.746 | 54.275 | 56.58 | 0.00 | 29.879 | 25.867 | 24.396 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.8 | 17.0 | -100.0 | G35T2 | 1 2 3 | 8 7 2
N/1-1 | SGBM19 | Jan 21 2016 9:10AM | Jan 21 2016 5:00PM | Jan 21 2016 6:45PM | Jan 21 2016 8:30PM | 55.68 | 55.075 | 56.51 | 0.00 | 27.012 | 28.668 | 28.063 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 16.0 | 29.0 | G35T2 | 1 2 | 8 8
Xa/Y8-2 | SGBM21 | Jan 18 2016 8:40AM | Jan 19 2016 12:47PM | Jan 20 2016 10:40PM | Jan 21 2016 1:05AM | 55.885 | 54.275 | 56.68 | 0.00 | 30.081 | 25.804 | 24.194 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.7 | 17.0 | 59.0 | G35T2 | 1 2 | 12 5
W/63-1 | SGBM31 | Jan 20 2016 8:43AM | Jan 20 2016 6:00PM | Jan 20 2016 9:05PM | Jan 20 2016 10:30PM | 49.843 | 49.075 | 50.81 | 0.00 | 22.113 | 27.730 | 26.962 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
M6a/54-1 | SGBM08 | Jan 19 2016 11:35AM | Jan 20 2016 10:40AM | Jan 20 2016 7:55PM | Jan 20 2016 9:02PM | 51.948 | 51.275 | 52.76 | 0.00 | 20.160 | 31.788 | 31.115 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.7 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
V/63-1 | SGBM31 | Jan 20 2016 8:29AM | Jan 20 2016 5:00PM | Jan 20 2016 6:55PM | Jan 20 2016 8:35PM | 50.491 | 49.075 | 51.33 | 0.00 | 23.832 | 26.659 | 25.243 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
Xa/Y4-2 | SGBM21 | Jan 20 2016 10:00AM | Jan 20 2016 2:23PM | Jan 20 2016 5:45PM | Jan 20 2016 6:55PM | 55.787 | 54.275 | 56.41 | 0.00 | 30.013 | 25.774 | 24.262 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.7 | 17.0 | 58.6 | G35T2 | 1 2 | 11 6
Xa/Y9-2 | SGBM20 | Jan 18 2016 8:00AM | Jan 18 2016 1:36PM | Jan 18 2016 10:00PM | Jan 19 2016 1:13AM | 55.87 | 54.275 | 56.61 | 0.00 | 31.213 | 81.240 | 23.062 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.2 | 18.0 | -10.2 | G35T2 | 1 2 3 4 | 6 6 3 3
X/63-1 | SGBM22 | Jan 18 2016 9:13AM | Jan 18 2016 2:27PM | Jan 18 2016 8:00PM | Jan 18 2016 9:40PM | 49.94 | 49.075 | 50.69 | 0.00 | 20.788 | 29.152 | 28.287 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
AAa/59-1 | SGBM22 | Jan 16 2016 8:39AM | Jan 16 2016 2:00PM | Jan 15 2016 7:15PM | Jan 16 2016 8:08PM | 49.68 | 48.475 | 50.56 | 0.00 | 17.058 | 32.622 | 31.417 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.9 | 18.0 | -100.0 | G35T2 | PJ4502 PJ4507 | 8 10
Xa/Y7-1 | SGBM03 | Jan 16 2016 8:00AM | Jan 16 2016 1:20PM | Jan 16 2016 3:30PM | Jan 16 2016 4:42PM | 55.756 | 54.275 | 56.47 | 0.00 | 30.072 | 25.684 | 24.203 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
U/36a-1 | SGBM20 | Jan 16 2016 8:30AM | Jan 16 2016 12:13PM | Jan 16 2016 2:35PM | Jan 16 2016 4:07PM | 52.213 | 51.325 | 0.00 | 0.00 | -18.500 | 70.713 | 69.825 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 30.9 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
Xa/Y6-1 | SGBM03 | Jan 14 2016 4:45PM | Jan 15 2016 2:15PM | Jan 15 2016 6:35PM | Jan 15 2016 7:54PM | 55.837 | 54.275 | 56.41 | 0.00 | 30.011 | 25.826 | 24.264 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 13.0 | 21.3 | G35T2 | 1 2 | 7 6
U/37a-1 | SGBM20 | Jan 15 2016 9:00AM | Jan 15 2016 1:35PM | Jan 15 2016 5:00PM | Jan 15 2016 5:47PM | 52.329 | 51.325 | 0.00 | 0.00 | -19.100 | 71.429 | 70.425 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 31.1 | 10.0 | -100.0 | G45T2 | 1 | 10
U/38a-1 | SGBM03 | Jan 13 2016 5:00PM | Jan 14 2016 7:10PM | Jan 15 2016 1:00AM | Jan 15 2016 2:57AM | 52.345 | 51.325 | 53.25 | 0.00 | 33.247 | 19.098 | 18.078 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 12.0 | 50.2 | G45T2 | 1 2 | 5 7
AAa/61-1 | SGBM22 | Jan 13 2016 3:59PM | Jan 14 2016 4:00PM | Jan 14 2016 11:25PM | Jan 15 2016 12:40AM | 49.365 | 47.075 | 50.29 | 0.00 | 15.890 | 33.475 | 31.185 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 17.0 | -100.0 | G35T2 | 1 2 | 8 9
U/33a-1 | SGBM20 | Jan 13 2016 3:00PM | Jan 14 2016 3:48PM | Jan 14 2016 9:35PM | Jan 14 2016 10:30PM | 52.345 | 51.325 | 53.25 | 0.00 | 36.047 | 16.275 | 15.278 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.8 | 9.0 | -100.0 | G45T2 | PJ4404 | 9
Xa/Y9-1 | SGBM21 | Jan 13 2016 9:50AM | Jan 14 2016 1:00PM | Jan 14 2016 5:10PM | Jan 14 2016 7:08PM | 55.859 | 54.275 | 56.54 | 0.00 | 31.241 | 24.618 | 23.034 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 10.2 | 12.0 | -10.2 | G35T2 | 1 2 | 6 6
Xa/Y8-1 | SGBM21 | Jan 13 2016 9:00AM | Jan 14 2016 8:30AM | Jan 14 2016 10:50AM | Jan 14 2016 12:33PM | 55.797 | 54.275 | 56.61 | 0.00 | 30.107 | 25.690 | 24.168 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 13.0 | -10.7 | G35T2 | 1 2 | 7 6
U/34-1 | SGBM03 | Jan 12 2016 8:10AM | Jan 12 2016 10:41AM | Jan 12 2016 8:00PM | Jan 12 2016 8:55PM | 52.393 | 51.325 | 53.28 | 0.00 | 36.783 | 15.610 | 14.542 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.4 | 9.0 | -100.0 | G45T2 | 1 | 9
AAa/60-1 | SGBM22 | Jan 11 2016 10:40AM | Jan 12 2016 4:13PM | Jan 12 2016 5:40PM | Jan 12 2016 7:20PM | 49.632 | 47.075 | 50.50 | 0.00 | 15.896 | 33.736 | 31.179 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.8 | 17.0 | -100.0 | G35T2 | 1 2 | 8 9
Ta/40-1 | SGBM03 | Jan 11 2016 10:30AM | Jan 11 2016 4:45PM | Jan 11 2016 9:05PM | Jan 11 2016 10:45PM | 52.171 | 51.325 | 53.06 | 0.00 | 27.360 | 24.811 | 23.965 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
U/37-1 | SGBM03 | Jan 11 2016 8:30AM | Jan 11 2016 1:45PM | Jan 11 2016 7:40PM | Jan 11 2016 9:10PM | 52.386 | 51.375 | 53.24 | 0.00 | 30.239 | 22.147 | 21.136 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
X6/Y8a-1 | SGBM21 | Jan 9 2016 3:00PM | Jan 9 2016 5:25PM | Jan 9 2016 9:30PM | Jan 9 2016 10:32PM | 55.787 | 55.075 | 56.62 | 0.00 | 33.923 | 21.864 | 21.152 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 11.5 | -100.0 | G35T2 | 1 | 11.5
Fa/33-1b | SGBM16 | Jan 9 2016 8:00AM | Jan 9 2016 10:15AM | Jan 9 2016 8:10PM | Jan 9 2016 10:00PM | 52.392 | 50.175 | 53.09 | 0.00 | 37.492 | 14.900 | 12.683 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.6 | 8.0 | -100.0 | G35T2 | 1 2 | 2 6
Ua/41-2 | SGBM22 | Jan 9 2016 9:35AM | Jan 9 2016 5:30PM | Jan 9 2016 8:05PM | Jan 9 2016 9:45PM | 52.034 | 50.525 | 52.93 | 0.00 | 24.433 | 27.601 | 26.092 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Fa/33-1a | SGBM03 | Jan 9 2016 1:00PM | Jan 9 2016 3:15PM | Jan 9 2016 8:10PM | Jan 9 2016 8:40PM | 52.46 | 50.175 | 53.10 | 0.00 | 37.304 | 15.156 | 12.871 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.7 | 9.0 | -100.0 | G35T2 | 1 | 9
ER-7 | SGBM03 | Jan 8 2016 9:00AM | Jan 9 2016 11:18AM | Jan 9 2016 2:02PM | Jan 9 2016 4:37PM | 60.324 | 57.375 | 60.32 | 0.00 | 29.724 | 30.600 | 27.651 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 19.0 | -100.0 | G35T2 | 1 2 3 | 8 9 2
U/35-1 | SGBM20 | Jan 8 2016 8:40AM | Jan 8 2016 3:45PM | Jan 8 2016 9:27PM | Jan 8 2016 10:36PM | 52.306 | 51.375 | 53.09 | 0.00 | 29.689 | 22.617 | 21.686 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.6 | 12.0 | -9.6 | G45T2 | 1 2 | 6 6
ER-10 | SGBM21 | Jan 8 2016 11:00AM | Jan 8 2016 6:20PM | Jan 8 2016 7:40PM | Jan 8 2016 10:33PM | 59.524 | 57.375 | 0.00 | 0.00 | -30.300 | 89.824 | 87.675 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 38.7 | 23.0 | -53.5 | G35T2 | 1 2 3 | 8 10 5
M4/59-1 | SGBM08 | Jan 7 2016 5:45PM | Jan 8 2016 4:30PM | Jan 8 2016 6:03PM | Jan 8 2016 7:15PM | 51.765 | 51.075 | 52.52 | 0.00 | 19.124 | 32.641 | 31.951 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.1 | 17.0 | 20.4 | G45T2 | 1 2 3 | 7 5 5
ER-4 | SGBM03 | Jan 8 2016 9:00AM | Jan 8 2016 12:33PM | Jan 8 2016 4:22PM | Jan 8 2016 6:43PM | 59.362 | 57.375 | 59.82 | 0.00 | 29.222 | 30.140 | 28.153 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 18.0 | -100.0 | G35T2 | 1 2 3 | 8 8 2
M3/60a-1 | SGBM08 | Jan 5 2016 1:00PM | Jan 7 2016 10:50AM | Jan 7 2016 9:40PM | Jan 7 2016 10:50PM | 51.835 | 51.375 | 52.71 | 0.00 | 24.314 | 27.521 | 27.061 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 16.0 | 33.8 | G45T2 | 1 2 | 8 8
M5/60a-1 | SGBM08 | Jan 5 2016 1:45PM | Jan 7 2016 8:20AM | Jan 7 2016 9:40PM | Jan 7 2016 10:47PM | 51.786 | 51.375 | 52.69 | 0.00 | 24.287 | 27.499 | 27.088 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
Ua/40-1 | SGBM23 | Jan 7 2016 11:00AM | Jan 7 2016 3:00PM | Jan 7 2016 8:10PM | Jan 7 2016 9:43PM | 52.106 | 51.325 | 52.97 | 0.00 | 26.267 | 25.839 | 25.058 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
ER-6 | SGBM03 | Jan 7 2016 9:25AM | Jan 7 2016 2:00PM | Jan 7 2016 5:55PM | Jan 7 2016 8:46PM | 59.44 | 57.375 | 60.24 | 0.00 | 29.935 | 29.505 | 27.440 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.1 | 17.0 | -100.0 | G35T2 | 1 2 3 | 8 7 2
ER-9 | SGBM21 | Jan 7 2016 9:30AM | Jan 7 2016 1:35PM | Jan 7 2016 4:09PM | Jan 7 2016 5:35PM | 59.358 | 57.375 | 60.33 | 0.00 | 29.731 | 29.627 | 27.644 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
ER-19 | SGBM03 | Jan 6 2016 1:00PM | Jan 6 2016 5:00PM | Jan 6 2016 10:37PM | Jan 7 2016 12:10AM | 59.358 | 57.375 | 59.81 | 0.00 | 29.205 | 30.153 | 28.170 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 19.0 | -100.0 | G35T2 | 1 2 3 | 8 7 4
M4/60-1 | SGBM08 | Jan 5 2016 2:50PM | Jan 6 2016 11:35AM | Jan 6 2016 9:40PM | Jan 6 2016 10:45PM | 51.86 | 51.375 | 52.70 | 0.00 | 20.003 | 31.857 | 31.372 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.9 | 15.0 | -100.0 | G45T2 | 1 2 | 7 8
ER-14 | SGBM03 | Jan 6 2016 9:00AM | Jan 6 2016 12:25PM | Jan 6 2016 3:38PM | Jan 6 2016 5:20PM | 59.593 | 57.375 | 60.44 | 0.00 | 29.643 | 29.950 | 27.732 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 17.0 | -100.0 | G35T2 | 1 2 | 8 9
Ua/41-1 | SGBM22 | Jan 4 2016 5:20PM | Jan 6 2016 10:15AM | Jan 6 2016 2:15PM | Jan 6 2016 3:40PM | 52.102 | 50.525 | 52.89 | 0.00 | 24.491 | 27.611 | 26.034 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 14.0 | -100.0 | G45T2 | PJ4028 PJ4031 | 7 7
ER-3 | SGBM03 | Jan 5 2016 2:00PM | Jan 5 2016 5:52PM | Jan 5 2016 11:40PM | Jan 6 2016 1:30AM | 59.447 | 57.375 | 60.13 | 0.00 | 29.627 | 29.820 | 27.748 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 21.0 | -100.0 | G35T2 | 1 2 3 | 8 9 4
ER-17 | SGBM21 | Jan 5 2016 1:00PM | Jan 5 2016 4:50PM | Jan 5 2016 8:15PM | Jan 5 2016 9:30PM | 59.5 | 57.375 | 59.95 | 0.00 | 29.348 | 30.152 | 28.027 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
N/44-1 | SGBM08 | Jan 4 2016 1:28PM | Jan 5 2016 9:20AM | Jan 5 2016 3:20PM | Jan 5 2016 5:05PM | 52.06 | 50.575 | 53.09 | 0.00 | 24.093 | 27.967 | 26.482 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.7 | 14.0 | -11.7 | G45T2 | PJ3973 PJ3975 | 7 7
ER-13 | SGBM03 | Jan 5 2016 9:00AM | Jan 5 2016 12:05PM | Jan 5 2016 2:00PM | Jan 5 2016 3:10PM | 59.585 | 57.375 | 60.21 | 0.00 | 29.610 | 29.975 | 27.765 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 17.0 | -100.0 | G35T2 | 1 2 | 9 8
N/41-1 | SGBM01 | Jan 4 2016 3:10PM | Jan 4 2016 7:05PM | Jan 4 2016 11:30PM | Jan 5 2016 12:15AM | 52.033 | 50.575 | 52.86 | 0.00 | 32.260 | 19.773 | 18.315 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 10.0 | -8.1 | G45T2 | PJ3951 | 10
ER-16 | SGBM21 | Jan 4 2016 3:00PM | Jan 4 2016 6:20PM | Jan 4 2016 9:45PM | Jan 4 2016 11:10PM | 59.454 | 57.375 | 60.40 | 0.00 | 29.598 | 29.856 | 27.777 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 18.0 | 46.7 | G35T2 | 1 2 | 10 8
ER-2 | SGBM03 | Jan 4 2016 3:00PM | Jan 4 2016 6:30PM | Jan 4 2016 7:20PM | Jan 4 2016 9:00PM | 59.407 | 57.375 | 60.18 | 0.00 | 29.578 | 29.829 | 27.797 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 19.0 | 54.7 | G35T2 | 1 2 3 | 8 7 4
N/45-1 | SGBM08 | Jan 2 2016 4:45PM | Jan 4 2016 8:50AM | Jan 4 2016 1:00PM | Jan 4 2016 3:00PM | 51.888 | 50.575 | 52.82 | 0.00 | 23.524 | 28.364 | 27.051 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 15.0 | -11.9 | G45T2 | PJ3899 PJ3903 | 8 7
M/41-1 | SGBM01 | Jan 4 2016 12:26PM | Jan 4 2016 3:35PM | Jan 4 2016 10:10PM | Jan 4 2016 1:15PM | 51.896 | 50.575 | 52.73 | 0.00 | 27.134 | 24.762 | 23.441 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.4 | 13.0 | -10.3 | G45T2 | PJ3945 PJ3948 | 7 6
ER-12 | SGBM03 | Jan 2 2016 4:00PM | Jan 2 2016 7:10PM | Jan 2 2016 11:45PM | Jan 3 2016 1:10AM | 59.762 | 57.375 | 60.38 | 0.00 | 29.785 | 29.977 | 27.590 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 17.0 | -100.0 | G35T2 | 1 2 | 8 9
ER-18 | SGBM21 | Jan 2 2016 1:00PM | Jan 2 2016 5:42PM | Jan 2 2016 9:35PM | Jan 2 2016 10:30PM | 59.5 | 57.375 | 60.24 | 0.00 | 29.742 | 29.758 | 27.633 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 17.0 | -100.0 | G35T2 | 1 2 | 8 9
M/45-1 | SGBM08 | Dec 31 2015 2:00PM | Jan 2 2016 3:47PM | Jan 2 2016 8:00PM | Jan 2 2016 9:10PM | 51.833 | 50.575 | 52.74 | 0.00 | 23.437 | 28.396 | 27.138 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
ER-5 | SGBM03 | Jan 2 2016 12:00PM | Jan 2 2016 3:55PM | Jan 2 2016 5:45PM | Jan 2 2016 8:15PM | 59.528 | 57.375 | 60.20 | 0.00 | 29.703 | 29.825 | 27.672 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 21.0 | 71.8 | G35T2 | 1 2 3 | 10 7 4
ER-20 | SGBM21 | Jan 2 2016 12:00PM | Jan 2 2016 3:00PM | Jan 2 2016 4:05PM | Jan 2 2016 5:30PM | 59.429 | 57.375 | 59.76 | 0.00 | 29.659 | 29.770 | 27.716 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 17.0 | -100.0 | G35T2 | PJ3857 PJ3859 | 9 8
Ma/22a-1 | SGBM16 | Jan 2 2016 8:30AM | Jan 2 2016 10:45AM | Jan 2 2016 12:10PM | Jan 2 2016 1:15PM | 53.362 | 52.775 | 54.29 | 0.00 | 36.491 | 16.871 | 16.284 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.2 | 10.0 | -100.0 | G45T2 | 1 | 10
ER-11 | SGBM03 | Dec 31 2015 3:00PM | Dec 31 2015 8:00PM | Dec 31 2015 11:10PM | Jan 1 2016 12:45AM | 59.568 | 57.375 | 60.19 | 0.00 | 29.695 | 29.873 | 27.680 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 18.0 | -100.0 | G35T2 | 1 2 | 10 8
ER-15 | SGBM21 | Dec 31 2015 9:00AM | Dec 31 2015 1:50PM | Dec 31 2015 8:25PM | Dec 31 2015 10:45PM | 59.6 | 57.375 | 60.45 | 0.00 | 29.650 | 29.950 | 27.725 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.3 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
Ma/61-1 | SGBM08 | Dec 30 2015 4:00PM | Dec 31 2015 2:03PM | Dec 31 2015 7:00PM | Dec 31 2015 8:10PM | 51.9 | 50.075 | 52.78 | 0.00 | 21.780 | 30.120 | 28.295 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 16.0 | -12.5 | G45T2 | PJ3807 PJ3810 | 8 8
ER-8 | SGBM21 | Dec 31 2015 9:00AM | Dec 31 2015 1:00PM | Dec 31 2015 3:00PM | Dec 31 2015 5:35PM | 59.45 | 57.375 | 60.22 | 0.00 | 29.725 | 29.725 | 27.650 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 16.0 | 31.0 | G35T2 | 1 2 3 | 6 5 5
ER-1 | SGBM03 | Dec 30 2015 10:00PM | Dec 31 2015 11:00AM | Dec 31 2015 2:25PM | Dec 31 2015 5:05PM | 59.498 | 57.375 | 60.24 | 0.00 | 29.238 | 30.260 | 28.137 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 19.0 | -100.0 | G35T2 | 1 2 3 | 8 6 5
N/46-1 | SGBM08 | Dec 29 2015 2:35PM | Dec 29 2015 6:16PM | Dec 29 2015 7:52PM | Dec 29 2015 8:53PM | 51.643 | 50.575 | 52.67 | 0.00 | 22.165 | 29.478 | 28.410 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.6 | 16.0 | 27.5 | G45T2 | PJ3684 PJ3688 | 8 8
R/6-1 | SGBM21 | Dec 28 2015 10:00PM | Dec 29 2015 9:00AM | Dec 29 2015 11:07AM | Dec 29 2015 12:17PM | 55.741 | 55.075 | 56.43 | 0.00 | 35.933 | 19.808 | 19.142 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
N/31-1 | SGBM20 | Dec 28 2015 6:00PM | Dec 28 2015 8:25PM | Dec 28 2015 10:14PM | Dec 28 2015 11:10PM | 52.082 | 51.375 | 52.83 | 0.00 | 35.232 | 16.850 | 16.143 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.1 | 11.0 | -7.1 | G45T2 | 1 2 | 6 5
AE/46-1 | SGBM22 | Dec 26 2015 8:40AM | Dec 28 2015 8:22AM | Dec 28 2015 1:30PM | Dec 28 2015 2:35PM | 50.013 | 48.475 | 50.55 | 0.00 | 23.852 | 26.161 | 24.623 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.9 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
M/46-1 | SGBM08 | Dec 23 2015 11:00AM | Dec 26 2015 1:32PM | Dec 26 2015 8:21PM | Dec 26 2015 9:36PM | 51.587 | 50.575 | 52.60 | 0.00 | 22.505 | 29.082 | 28.070 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 15.0 | -12.4 | G45T2 | PJ3551 PJ3554 | 8 7
X0/Y1-1 | SGBM21 | Dec 26 2015 8:00AM | Dec 26 2015 2:15PM | Dec 26 2015 5:29PM | Dec 26 2015 8:09PM | 56.316 | 54.475 | 56.95 | 0.00 | 23.448 | 32.868 | 31.027 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.7 | 19.0 | -100.0 | G35T2 | 1 2 3 | 10 5 4
X10/Y1-1 | SGBM20 | Dec 22 2015 9:00PM | Dec 23 2015 8:00PM | Dec 24 2015 12:23AM | Dec 24 2015 4:14AM | 55.749 | 55.075 | 56.28 | 0.00 | 24.781 | 87.249 | 30.294 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.4 | 19.0 | -100.0 | G35T2 | 1 2 3 | 7 9 3
N/47-1 | SGBM08 | Dec 23 2015 1:15PM | Dec 23 2015 5:55PM | Dec 24 2015 1:51AM | Dec 24 2015 3:39AM | 51.69 | 50.575 | 52.61 | 0.00 | 22.206 | 29.484 | 28.369 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 23.0 | -12.5 | G45T2 | C520124371 C520124375 C520124376 | 6 10 7
X0/Y3-1 | SGBM21 | Dec 23 2015 8:00AM | Dec 23 2015 12:00PM | Dec 23 2015 10:36PM | Dec 24 2015 2:05AM | 55.61 | 55.075 | 56.46 | 0.00 | 30.963 | 24.647 | 24.112 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 19.0 | -100.0 | G35T2 | 1 2 3 | 11 3 5
N/42-1 | SGBM08 | Dec 21 2015 5:35PM | Dec 23 2015 11:30AM | Dec 23 2015 8:41PM | Dec 23 2015 9:12PM | 51.82 | 50.575 | 52.45 | 0.00 | 24.046 | 27.774 | 26.529 |  | 0.0 | 0.0 | 0.0 | 16T20+8T20 | - | - | T10-225 | - | - | - | 12 | - | 11.7 | 20.0 | -100.0 | G35T2 | C520124352 C520124354 | 10 10
X0/Y2-1 | SGBM21 | Dec 21 2015 8:45PM | Dec 22 2015 6:00PM | Dec 22 2015 10:38PM | Dec 23 2015 1:22AM | 55.636 | 55.075 | 56.33 | 0.00 | 29.926 | 25.710 | 25.149 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 18.0 | -100.0 | G35T2 | 1 2 | 11 7
N/43-1 | SGBM08 | Dec 21 2015 4:40PM | Dec 21 2015 11:30PM | Dec 22 2015 9:29PM | Dec 22 2015 10:44PM | 51.871 | 50.575 | 52.77 | 0.00 | 23.573 | 28.298 | 27.002 |  | 0.0 | 0.0 | 0.0 | 16T20+8T20 | - | - | T10-225 | - | - | - | 12 | - | 11.9 | 20.0 | -100.0 | G35T2 | 1 2 | 12 8
X0/Y4-1 | SGBM21 | Dec 19 2015 2:45PM | Dec 22 2015 11:00AM | Dec 22 2015 3:57PM | Dec 22 2015 7:51PM | 55.695 | 54.625 | 56.39 | 0.00 | 25.593 | 30.800 | 29.032 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.8 | 20.0 | 55.9 | G35T2 | 1 2 3 | 7 7 6
Ma/62-1 | SGBM08 | Dec 19 2015 5:21PM | Dec 21 2015 2:30PM | Dec 21 2015 8:26PM | Dec 21 2015 10:15PM | 52.356 | 50.075 | 53.16 | 0.00 | 20.156 | 32.200 | 29.919 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.2 | 18.0 | 36.2 | G45T2 | 1 2 | 8 10
X0/Y5-1 | SGBM21 | Dec 19 2015 2:00PM | Dec 21 2015 12:50PM | Dec 21 2015 6:14PM | Dec 21 2015 8:32PM | 55.749 | 54.625 | 56.44 | 0.00 | 25.841 | 29.908 | 28.784 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.7 | 17.0 | -100.0 | G35T2 | 1 2 3 | 7 7 3
X9/Y1-1 | SGBM21 | Dec 17 2015 4:19PM | Dec 19 2015 6:47PM | Dec 20 2015 1:16AM | Dec 20 2015 3:03AM | 55.557 | 55.075 | 56.30 | 0.00 | 23.703 | 31.854 | 31.372 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.9 | 21.0 | -100.0 | G35T2 | 1 2 3 | 9 10 2
X0/Y9-1 | SGBM21 | Dec 18 2015 7:15PM | Dec 19 2015 1:47PM | Dec 19 2015 8:12PM | Dec 19 2015 8:56PM | 56.246 | 54.475 | 0.00 | 0.00 | -24.400 | 80.646 | 78.875 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 34.9 | 12.0 | -100.0 | G35T2 | 1 | 12
S/31-1 | SGBM01 | Dec 17 2015 10:00AM | Dec 18 2015 12:45PM | Dec 18 2015 5:09PM | Dec 18 2015 6:05PM | 52.055 | 51.375 | 52.91 | 0.00 | 33.106 | 18.949 | 18.269 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
AB/32-1 | SGBM22 | Dec 19 2015 8:30AM | Dec 19 2015 3:00PM | Dec 18 2015 4:17PM | Dec 18 2015 6:00PM | 49.658 | 48.475 | 50.97 | 0.00 | 32.169 | 17.489 | 16.306 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.2 | 11.0 | -100.0 | G35T2 | 1 | 11
X0/Y8-1 | SGBM03 | Dec 17 2015 3:35PM | Dec 18 2015 12:30PM | Dec 18 2015 4:52PM | Dec 18 2015 5:40PM | 55.933 | 55.075 | 56.66 | 0.00 | 26.956 | 29.700 | 28.119 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 17.0 | -100.0 | G35T2 | Pending 2 | 9 8
X8/Y1-1 | SGBM21 | Dec 17 2015 5:00PM | Dec 18 2015 12:00PM | Dec 18 2015 3:37PM | Dec 18 2015 5:09PM | 55.428 | 54.975 | 0.00 | 0.00 | -33.200 | 88.628 | 88.175 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 39.0 | 20.0 | -100.0 | G35T2 | 1 2 3 | 7 7 6
X0/Y6-1 | SGBM03 | Dec 17 2015 2:15PM | Dec 18 2015 4:35PM | Dec 18 2015 8:19PM | Dec 18 2015 10:25AM | 55.761 | 54.625 | 56.18 | 0.00 | 29.579 | 26.182 | 25.046 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 20.0 | -100.0 | G35T2 | 1 2 3 | 8 9 3
X0/Y7-1 | SGBM03 | Dec 17 2015 2:55PM | Dec 17 2015 10:05PM | Dec 18 2015 1:04AM | Dec 18 2015 3:33AM | 55.747 | 55.075 | 56.51 | 0.00 | 27.014 | 28.733 | 28.061 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 20.0 | 61.3 | G35T2 | 1 2 3 | 8 8 4
F/40-1 | SGBM08 | Dec 17 2015 4:20PM | Dec 17 2015 9:15PM | Dec 18 2015 1:58AM | Dec 18 2015 2:55AM | 52 | 51.375 | 52.79 | 0.00 | 25.790 | 79.000 | 25.585 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.3 | 15.0 | 32.7 | G45T2 | 1 2 | 7 8
X7/Y1-1 | SGBM21 | Dec 17 2015 9:30AM | Dec 17 2015 4:30PM | Dec 17 2015 6:00PM | Dec 17 2015 8:00PM | 55.519 | 55.075 | 56.19 | 0.00 | 21.895 | 33.624 | 33.180 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.7 | 21.0 | -100.0 | G35T2 | 3281 3282 3289 | 6 8 7
X8/Y9-1 | SGBM21 | Dec 16 2015 8:00AM | Dec 16 2015 7:14PM | Dec 16 2015 8:47PM | Dec 16 2015 10:07PM | 55.138 | 54.475 | 56.14 | 0.00 | 35.138 | 20.000 | 19.337 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 11.0 | -100.0 | G35T2 | 1 2 | 6 5
X9/Y9-1 | SGBM21 | Dec 16 2015 10:00AM | Dec 16 2015 4:17PM | Dec 16 2015 5:36PM | Dec 16 2015 7:11PM | 55.682 | 54.475 | 56.34 | 0.00 | 36.338 | 19.344 | 18.137 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
X10/Y9-1 | SGBM21 | Dec 16 2015 9:10AM | Dec 16 2015 1:33PM | Dec 16 2015 3:37PM | Dec 16 2015 4:21PM | 55.525 | 54.475 | 56.33 | 0.00 | 35.833 | 19.692 | 18.642 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.2 | 10.0 | -100.0 | G35T2 | 1 2 | 5 5
N/30-1 | SGBM20 | Dec 14 2015 2:30PM | Dec 15 2015 3:45PM | Dec 16 2015 12:05PM | Dec 16 2015 1:26PM | 52.038 | 51.375 | 52.85 | 0.00 | 33.255 | 18.783 | 18.120 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 10.0 | -100.0 | G45T2 | 1 2 | 5 5
Q/31-1 | SGBM20 | Dec 15 2015 8:00AM | Dec 15 2015 10:55AM | Dec 15 2015 10:58PM | Dec 16 2015 12:50AM | 52.075 | 51.375 | 52.96 | 0.00 | 33.156 | 18.919 | 18.219 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 11.0 | -100.0 | G45T2 | 1 | 11
X7/Y9-1 | SGBM21 | Dec 15 2015 2:00PM | Dec 15 2015 7:32PM | Dec 15 2015 9:07PM | Dec 15 2015 10:38PM | 55.979 | 54.475 | 56.77 | 0.00 | 32.372 | 24.300 | 22.103 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
X6/Y9-1 | SGBM21 | Dec 15 2015 8:00AM | Dec 15 2015 1:26PM | Dec 15 2015 6:43PM | Dec 15 2015 7:28PM | 55.799 | 54.475 | 0.00 | 0.00 | -19.300 | 75.099 | 73.775 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 32.6 | 11.0 | -100.0 | G35T2 | 1 2 | 6 5
X4/Y9-1 | SGBM21 | Dec 14 2015 1:35PM | Dec 14 2015 10:00PM | Dec 15 2015 1:45AM | Dec 15 2015 3:10AM | 55.756 | 54.475 | 56.42 | 0.00 | 33.317 | 22.439 | 21.158 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 11.5 | -100.0 | G35T2 | 1 | 11.5
X3/Y9-1 | SGBM21 | Dec 14 2015 1:00PM | Dec 14 2015 6:30PM | Dec 14 2015 11:30PM | Dec 15 2015 12:30AM | 55.727 | 54.475 | 56.40 | 0.00 | 32.198 | 23.529 | 22.277 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
Ma/63-1 | SGBM02 | Dec 12 2015 5:01PM | Dec 14 2015 2:00PM | Dec 14 2015 10:46PM | Dec 14 2015 11:53PM | 52.279 | 50.075 | 53.25 | 0.00 | 20.652 | 31.627 | 29.423 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.0 | 17.0 | 30.8 | G45T2 | 1 2 3 | 6 6 5
X1/Y1-1 | SGBM18 | Dec 8 2015 4:00PM | Dec 14 2015 2:49PM | Dec 14 2015 7:36PM | Dec 14 2015 9:05PM | 55.742 | 54.475 | 47.40 42.40 40.40 | 0.00 0.00 0.00 | 24.898 | 30.844 | 29.577 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.1 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
Ma/64-1 | SGBM02 | Dec 12 2015 5:05PM | Dec 12 2015 10:00PM | Dec 13 2015 12:58AM | Dec 13 2015 3:15AM | 52.154 | 50.075 | 53.22 | 0.00 | 20.724 | 31.430 | 29.351 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.0 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
F/41-1 | SGBM08 | Dec 11 2015 11:32AM | Dec 11 2015 11:11PM | Dec 12 2015 5:08PM | Dec 12 2015 6:00PM | 52.008 | 51.375 | 52.89 | 0.00 | 25.090 | 26.918 | 26.285 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.6 | 16.0 | 37.8 | G45T2 | 1 2 | 8 8
X6/Y1-1 | SGBM18 | Dec 10 2015 4:22PM | Dec 11 2015 8:05PM | Dec 12 2015 3:00PM | Dec 12 2015 5:04PM | 55.505 | 55.075 | 56.20 | 0.00 | 21.901 | 33.604 | 33.174 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.7 | 18.0 | -100.0 | G35T2 | 1 2 3 | 6 6 6
Ea/40-1 | SGBM08 | Dec 11 2015 11:35AM | Dec 11 2015 7:30PM | Dec 12 2015 2:42PM | Dec 12 2015 4:10PM | 51.976 | 51.375 | 52.79 | 0.00 | 26.192 | 25.784 | 25.183 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | 34.8 | G45T2 | 1 2 | 8 7
T/15-1 | SGBM03 | Dec 11 2015 5:00PM | Dec 11 2015 8:35PM | Dec 12 2015 3:10AM | Dec 12 2015 4:00AM | 55.805 | 54.475 | 56.58 | 0.00 | 34.180 | 21.625 | 20.295 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.0 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
X1/Y9-1 | SGBM21 | Dec 11 2015 8:00AM | Dec 11 2015 6:39PM | Dec 12 2015 1:10AM | Dec 12 2015 2:50AM | 55.998 | 54.475 | 47.71 | 0.00 | 33.313 | 23.400 | 21.162 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.4 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
X2/Y9-1 | SGBM21 | Dec 10 2015 7:30PM | Dec 11 2015 12:36PM | Dec 11 2015 10:30PM | Dec 12 2015 12:01AM | 55.73 | 54.475 | -9.00 | 0.00 | -21.100 | 21.100 | 75.575 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 33.4 | 11.0 | -100.0 | G35T2 | 1 2 | 6 5
La/63-1 | SGBM02 | Dec 10 2015 8:05PM | Dec 11 2015 11:00AM | Dec 11 2015 9:45PM | Dec 11 2015 10:50PM | 52.343 | 50.075 | 53.24 | 0.00 | 20.943 | 31.400 | 29.132 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.9 | 17.0 | 4.1 | G45T2 | 1 2 | 10 7
T/19-1 | SGBM03 | Dec 10 2015 6:30PM | Dec 11 2015 11:47AM | Dec 11 2015 7:45PM | Dec 11 2015 8:56PM | 55.92 | 54.475 | 47.73 | 0.00 | 36.231 | 19.689 | 18.244 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
H/37-1 | SGBM08 | Dec 10 2015 3:46PM | Dec 10 2015 8:44PM | Dec 11 2015 4:33PM | Dec 11 2015 5:35PM | 52.056 | 51.075 | 52.93 | 0.00 | 29.629 | 22.427 | 21.446 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.5 | 13.0 | 37.2 | G45T2 | PJ2952 PJ2955 | 7 6
H/18-4 | SGBM20 | Nov 11 2015 4:25PM | Nov 13 2015 8:45PM | Nov 11 2015 3:17PM | Dec 11 2015 4:30PM | 53.671 | 50.575 | 45.37 | 0.00 | 23.970 | 29.701 | 26.605 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 14.0 | -100.0 | G45T2 | 1 2 3 | 5 5 4
X1/Y3-1 | SGBM21 | Dec 3 2015 8:00AM | Dec 10 2015 4:30PM | Dec 10 2015 8:10PM | Dec 11 2015 12:50AM | 55.766 | 55.075 | 47.67 40.67 | 0.00 0.00 | 30.866 | 24.900 | 24.209 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 18.0 | -100.0 | G45T2 | 1 2 3 4 | 7 8 2 1
La/64-1 | SGBM02 | Dec 10 2015 1:20PM | Dec 10 2015 6:25PM | Dec 10 2015 8:30PM | Dec 10 2015 11:35PM | 52.334 | 50.075 | 42.23 | 0.00 | 20.834 | 31.500 | 29.241 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.9 | 21.0 | -100.0 | G45T2 | PJ2913 PJ2917 PJN2924 | 9 8 4
Ea/41-1 | SGBM08 | Dec 10 2015 9:53AM | Dec 10 2015 3:00PM | Dec 10 2015 8:09PM | Dec 10 2015 10:20PM | 51.94 | 51.375 | 41.75 | 0.00 | 23.952 | 27.988 | 27.423 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.1 | 18.0 | 48.6 | G45T2 | 1 2 3 | 9 7 2
T/16-1 | SGBM03 | Dec 7 2015 8:00AM | Dec 10 2015 4:25PM | Dec 10 2015 7:57PM | Dec 10 2015 8:40PM | 55.827 | 54.475 | 47.59 37.29 | 0.00 0.00 | 35.186 | 20.641 | 19.289 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
X10/Y8-1 | SGBM21 | Dec 9 2015 1:15PM | Dec 10 2015 10:30AM | Dec 10 2015 1:08PM | Dec 10 2015 2:12PM | 55.758 | 55.075 | 47.50 | 0.00 | 31.899 | 23.859 | 23.176 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 12.0 | 17.2 | G35T2 | 1 2 | 6 6
Ka/64-1 | SGBM02 | Dec 5 2015 9:58AM | Dec 9 2015 7:15PM | Dec 10 2015 11:41AM | Dec 10 2015 12:50PM | 52.241 | 49.775 | 42.19 | 0.00 | 19.690 | 32.551 | 30.085 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.3 | 21.0 | 58.0 | G35T2 | 1 2 3 | 7 7 7
Ea/42-1 | SGBM08 | Dec 9 2015 9:10AM | Dec 9 2015 2:45PM | Dec 9 2015 7:58PM | Dec 9 2015 8:51PM | 51.825 | 50.775 | 52.67 | 0.00 | 28.666 | 23.159 | 22.109 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
Ea/43-1 | SGBM08 | Dec 8 2015 3:06PM | Dec 9 2015 8:30AM | Dec 9 2015 6:32PM | Dec 9 2015 7:30PM | 51.76 | 50.775 | 43.62 | 0.00 | 27.623 | 24.137 | 23.152 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
T/18-1 | SGBM20 | Dec 8 2015 10:15AM | Dec 8 2015 8:30PM | Dec 8 2015 10:10PM | Dec 8 2015 11:46PM | 55.664 | 54.475 | 47.46 | 0.00 | 36.162 | 19.502 | 18.313 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 9.0 | 0.9 | G45T2 | 1 2 | 7 2
X8/Y8-1 | SGBM21 | Dec 8 2015 3:05PM | Dec 8 2015 6:55PM | Dec 8 2015 8:07PM | Dec 8 2015 8:35PM | 55.42 | 54.975 | 47.20 | 0.00 | 32.900 | 78.720 | 22.075 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 12.0 | 2.2 | G35T2 | 1 | 12
Da/46-1 | SGBM08 | Dec 7 2015 2:25PM | Dec 8 2015 1:15PM | Dec 8 2015 6:00PM | Dec 8 2015 7:40PM | 51.7 | 50.775 | 43.55 23.55 | 0.00 0.00 | 15.648 | 36.052 | 35.127 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.5 | 22.0 | 41.7 | G45T2 | PJ2767 PJ2769 PJ2771 | 8 7 7
X6/Y8-1 | SGBM21 | Dec 7 2015 3:10PM | Dec 8 2015 1:40PM | Dec 8 2015 3:22PM | Dec 8 2015 3:56PM | 55.583 | 55.075 | 47.24 | 0.00 | 32.742 | 22.841 | 22.333 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 12.0 | -9.9 | G35T2 | 1 2 | 6 6
X7/Y8-1 | SGBM21 | Dec 7 2015 3:55PM | Dec 8 2015 9:30AM | Dec 8 2015 10:52AM | Dec 8 2015 11:50AM | 55.324 | 54.975 | 47.02 37.72 | 0.00 0.00 | 32.719 | 78.624 | 22.256 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 12.0 | 2.2 | G35T2 | 1 2 | 6 6
R/23-2 | SGBM21 | Dec 7 2015 8:00AM | Dec 7 2015 11:56AM | Dec 7 2015 9:43PM | Dec 7 2015 11:33PM | 50.346 | 48.275 | 42.11 | 0.00 | 30.114 | 20.232 | 18.161 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 10.0 | -100.0 | G45T2 | 1 2 3 | 6 3 1
Da/47-1 | SGBM08 | Dec 4 2015 5:43PM | Dec 7 2015 12:10PM | Dec 7 2015 7:12PM | Dec 7 2015 10:37PM | 51.76 | 50.775 | 41.61 25.61 22.41 | 0.00 0.00 0.00 | 14.314 | 37.446 | 36.461 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.1 | 22.0 | -100.0 | G45T2 | PJ2719 PJ2721 PJ2727 | 8 7 7
X2/Y8-1 | SGBM18 | Dec 4 2015 4:45PM | Dec 7 2015 10:43AM | Dec 7 2015 12:05PM | Dec 7 2015 2:56PM | 55.708 | 55.075 | 47.27 | 0.00 | 31.766 | 23.942 | 23.309 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
X1/Y8-1 | SGBM18 | Dec 4 2015 4:00PM | Dec 5 2015 7:37PM | Dec 5 2015 9:32PM | Dec 5 2015 10:47PM | 55.748 | 55.075 | 47.40 | 0.00 | 30.195 | 25.553 | 24.880 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.0 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
La/62-1 | SGBM02 | Dec 4 2015 4:34PM | Dec 5 2015 9:25PM | Dec 5 2015 7:40PM | Dec 5 2015 9:15PM | 52.166 | 50.075 | 42.96 | 0.00 | 15.660 | 36.506 | 34.415 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.2 | 20.0 | -100.0 | G45T2 | PJ2654 PJ2657 | 12 8
T/17-1 | SGBM03 | Dec 4 2015 5:30PM | Dec 5 2015 4:22PM | Dec 5 2015 6:04PM | Dec 5 2015 6:50PM | 55.798 | 54.475 | 47.65 | 0.00 | 36.350 | 19.448 | 18.125 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
E/45-1 | SGBM08 | Dec 3 2015 11:19AM | Dec 4 2015 5:00PM | Dec 5 2015 1:31AM | Dec 5 2015 3:35AM | 51.673 | 50.775 | 42.70 22.70 | 0.00 0.00 | 16.502 | 35.171 | 34.273 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.1 | 20.0 | -100.0 | G45T2 | PJ2624 PJ2625 PJ2628 | 8 6 6
AE/44-1 | SGBM22 | Dec 4 2015 8:00AM | Dec 4 2015 1:50PM | Dec 4 2015 4:59PM | Dec 4 2015 7:30PM | 49.239 | 48.475 | 50.12 | 0.00 | 19.721 | 29.518 | 28.754 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.7 | 16.0 | -12.7 | G45T2 | 1 2 | 8 8
Ea/44-1 | SGBM08 | Dec 3 2015 3:30PM | Dec 3 2015 7:40PM | Dec 4 2015 12:13AM | Dec 4 2015 3:40AM | 51.816 | 50.775 | 52.63 | 0.00 | 25.434 | 26.382 | 25.341 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
AE/43-1 | SGBM22 | Dec 3 2015 4:10PM | Dec 3 2015 10:48PM | Dec 3 2015 10:50PM | Dec 4 2015 2:35AM | 49.192 | 48.475 | 41.09 | 0.00 | 20.193 | 28.999 | 28.282 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 18.0 | -12.5 | G45T2 | PJ2560 PJ2562 PJ2563 PJ2565 | 6 5 5 2
AF/45-1 | SGBM22 | Dec 3 2015 8:30AM | Dec 3 2015 2:45PM | Dec 3 2015 4:50PM | Dec 3 2015 6:30PM | 49.263 | 48.475 | 41.02 | 0.00 | 24.224 | 25.039 | 24.251 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
M/53-1 | SGBM02 | Dec 2 2015 8:35AM | Dec 2 2015 11:45AM | Dec 3 2015 2:11AM | Dec 3 2015 4:00AM | 51.857 | 51.375 | 43.53 | 0.00 | 24.528 | 28.000 | 26.847 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 16.0 | 34.9 | G45T2 | 1 2 | 8 8
Da/45-1 | SGBM08 | Dec 2 2015 1:10PM | Dec 2 2015 6:25PM | Dec 3 2015 12:13AM | Dec 3 2015 3:40AM | 51.733 | 50.775 | 52.38 | 0.00 | 23.283 | 80.833 | 27.492 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.1 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 5 4
AE/41-1 | SGBM22 | Dec 1 2015 4:00PM | Dec 2 2015 8:21AM | Dec 2 2015 11:01PM | Dec 3 2015 12:50AM | 49.317 | 48.475 | 50.17 | 0.00 | 20.972 | 28.345 | 27.503 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
AE/42-1 | SGBM22 | Dec 2 2015 8:30AM | Dec 2 2015 1:47PM | Dec 2 2015 6:40PM | Dec 2 2015 8:00PM | 49.177 | 48.475 | 50.19 | 0.00 | 20.991 | 28.186 | 27.484 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.1 | 15.0 | -12.1 | G45T2 | 1 2 | 7 8
Q/18-1 | SGBM20 | Dec 1 2015 8:00AM | Dec 1 2015 9:36PM | Dec 2 2015 3:17PM | Dec 2 2015 4:20PM | 55.82 | 55.075 | 47.67 | 0.00 | 41.770 | 14.900 | 13.305 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.9 | 9.0 | -100.0 | G45T2 | 1 2 | 7 2
Q/17-1 | SGBM20 | Dec 1 2015 8:00AM | Dec 1 2015 8:17PM | Dec 2 2015 12:41PM | Dec 2 2015 2:00PM | 55.765 | 55.075 | -9.00 | 0.00 | -15.700 | 71.465 | 70.775 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 31.3 | 8.0 | -100.0 | G45T2 | 1 2 | 6 2
M/54-1 | SGBM02 | Dec 1 2015 1:00PM | Dec 1 2015 5:07PM | Dec 2 2015 3:25AM | Dec 2 2015 4:50AM | 51.645 | 51.375 | 52.58 | 0.00 | 24.684 | 26.961 | 26.691 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
F/49-1 | SGBM08 | Nov 30 2015 11:46AM | Dec 1 2015 4:06PM | Dec 2 2015 2:06AM | Dec 2 2015 4:20AM | 51.809 | 51.075 | 43.65 26.65 25.65 | 0.00 0.00 0.00 | 14.750 | 37.059 | 36.325 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.1 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
AEa/42-1 | SGBM22 | Dec 1 2015 9:30AM | Dec 1 2015 5:02PM | Dec 2 2015 1:29AM | Dec 2 2015 3:30AM | 49.393 | 49.075 | 40.96 | 0.00 | 26.958 | 22.435 | 22.117 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 13.0 | -9.8 | G45T2 | 1 2 | 7 6
M/55-1 | SGBM02 | Dec 1 2015 8:00AM | Dec 1 2015 11:50AM | Dec 1 2015 9:30PM | Dec 1 2015 11:25PM | 51.625 | 51.375 | 52.40 | 0.00 | 24.398 | 27.227 | 26.977 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.9 | 17.0 | -100.0 | G45T2 | 1 2 3 | 8 7 2
R/23-1 | SGBM21 | Dec 1 2015 8:00AM | Dec 1 2015 1:05PM | Dec 1 2015 4:34PM | Dec 1 2015 5:50PM | 50.242 | 48.275 | 41.90 | 0.00 | 30.102 | 20.140 | 18.173 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
AF/43-1 | SGBM22 | Nov 29 2015 10:05AM | Nov 30 2015 11:45AM | Nov 30 2015 9:13PM | Dec 1 2015 12:00AM | 49.663 | 48.475 | 41.41 34.21 | 0.00 0.00 | 25.412 | 24.251 | 23.063 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
Q/58-1 | SGBM19 | Nov 30 2015 8:40AM | Nov 30 2015 5:09PM | Nov 30 2015 8:28PM | Nov 30 2015 11:25PM | 52.265 | 51.375 | 43.87 | 0.00 | 22.772 | 29.493 | 28.603 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.6 | 26.0 | -100.0 | G45T2 | PJ2380 PJ2381 PJ2384 PJ2393 | 7 7 6 6
AF/44-1 | SGBM22 | Nov 30 2015 10:06AM | Nov 30 2015 5:03PM | Nov 30 2015 7:24PM | Nov 30 2015 10:00PM | 49.834 | 48.475 | 41.47 | 0.00 | 25.466 | 24.368 | 23.009 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
F/48-1 | SGBM08 | Nov 28 2015 10:29AM | Nov 30 2015 10:57AM | Nov 30 2015 4:23PM | Nov 30 2015 5:45PM | 51.493 | 51.075 | 36.22 25.22 | 0.00 0.00 | 14.719 | 36.774 | 36.356 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.1 | 22.0 | 5.9 | G45T2 | 1 2 3 | 7 8 7
AE/40-1 | SGBM22 | Nov 28 2015 3:00PM | Nov 28 2015 9:00PM | Nov 28 2015 11:03PM | Nov 29 2015 1:00AM | 49.532 | 48.475 | 41.51 | 0.00 | 20.907 | 28.625 | 27.568 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 15.0 | -100.0 | G45T2 | PJ2328 PJ2330 | 7 8
AF/42-1 | SGBM22 | Nov 28 2015 8:30AM | Nov 28 2015 3:00PM | Nov 28 2015 4:57PM | Nov 28 2015 6:55PM | 49.776 | 48.475 | 41.35 | 0.00 | 25.153 | 24.623 | 23.322 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
E/46-1 | SGBM08 | Nov 26 2015 7:30PM | Nov 27 2015 10:10PM | Nov 28 2015 6:03PM | Nov 28 2015 6:50PM | 51.575 | 50.775 | 40.58 | 0.00 | 15.576 | 35.999 | 35.199 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.6 | 22.0 | 6.4 | G35T2 | 1 2 | 11 11
AEa/40-1 | SGBM22 | Nov 27 2015 11:15AM | Nov 27 2015 6:15PM | Nov 28 2015 12:44AM | Nov 28 2015 3:15AM | 49.411 | 49.075 | 41.39 | 0.00 | 26.889 | 22.522 | 22.186 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
AEa/41-1 | SGBM22 | Nov 27 2015 2:20PM | Nov 27 2015 8:00PM | Nov 28 2015 12:44AM | Nov 28 2015 2:15AM | 49.465 | 49.075 | 50.09 | 0.00 | 26.589 | 22.876 | 22.486 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 13.0 | -9.9 | G35T2 | 1 2 | 7 6
AEa/38-1 | SGBM19 | Nov 26 2015 11:10AM | Nov 26 2015 6:55PM | Nov 27 2015 3:13AM | Nov 27 2015 6:50AM | 49.539 | 49.075 | 41.42 | 0.00 | 26.923 | 22.616 | 22.152 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 15.0 | -100.0 | G35T2 | 1 2 3 | 4 6 5
AEa/39-1 | SGBM19 | Nov 26 2015 9:25AM | Nov 26 2015 4:33PM | Nov 27 2015 1:49AM | Nov 27 2015 5:00AM | 49.477 | 49.075 | 41.34 | 0.00 | 27.038 | 22.439 | 22.037 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.7 | 13.0 | -100.0 | G35T2 | 1 2 3 | 5 6 2
AF/40-1 | SGBM22 | Nov 26 2015 9:20AM | Nov 26 2015 3:41PM | Nov 27 2015 12:08AM | Nov 27 2015 3:15AM | 49.492 | 48.475 | 50.34 | 0.00 | 25.837 | 23.655 | 22.638 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.0 | 13.0 | -100.0 | G35T2 | 1 2 3 | 7 5 1
AF/41-1 | SGBM22 | Nov 26 2015 11:35AM | Nov 26 2015 5:35PM | Nov 26 2015 10:19PM | Nov 26 2015 11:50PM | 49.561 | 48.475 | 50.25 | 0.00 | 25.548 | 24.013 | 22.927 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.1 | 12.0 | 18.5 | G35T2 | 1 2 | 6 6
Ca/50-1 | SGBM15 | Nov 25 2015 8:00AM | Nov 26 2015 12:20PM | Nov 26 2015 5:14PM | Nov 26 2015 6:50PM | 51.581 | 50.775 | 52.56 | 0.00 | 17.561 | 34.020 | 33.214 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.7 | 20.0 | -100.0 | G35T2 | 1 2 3 | 7 7 6
AF/37-1 | SGBM19 | Nov 25 2015 1:42PM | Nov 25 2015 9:00PM | Nov 25 2015 11:59PM | Nov 26 2015 2:40AM | 49.317 | 48.475 | 40.90 | 0.00 | 23.475 | 25.842 | 25.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.0 | 17.0 | -100.0 | G45T2 | 2157 2162 2169 | 7 7 3
AF/38-1 | SGBM22 | Nov 25 2015 2:43PM | Nov 25 2015 9:53PM | Nov 25 2015 11:08PM | Nov 26 2015 12:15AM | 49.364 | 48.475 | 41.24 | 0.00 | 22.436 | 26.928 | 26.039 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 14.0 | -11.5 | G45T2 | 2152 2153 | 7 7
AF/39-1 | SGBM22 | Nov 24 2015 7:49PM | Nov 25 2015 2:00PM | Nov 25 2015 10:23PM | Nov 25 2015 11:55PM | 49.406 | 48.475 | 41.17 36.77 | 0.00 0.00 | 26.475 | 22.931 | 22.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.7 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
X2/Y1-1 | SGBM18 | Nov 25 2015 9:00AM | Nov 25 2015 2:13PM | Nov 25 2015 8:49PM | Nov 25 2015 10:18PM | 55.675 | 54.375 | 56.46 | 0.00 | 23.363 | 32.312 | 31.012 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.7 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 5 6
Ca/51-1 | SGBM08 | Nov 23 2015 12:36PM | Nov 24 2015 6:56PM | Nov 24 2015 9:12PM | Nov 24 2015 10:00PM | 51.566 | 50.775 | 40.54 27.54 | 0.00 0.00 | 10.741 | 40.825 | 40.034 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.7 | 24.0 | -17.7 | G45T2 | 1 2 3 | 8 8 8
AF/35-1 | SGBM22 | Nov 24 2015 8:00AM | Nov 24 2015 11:08AM | Nov 24 2015 2:30PM | Nov 24 2015 4:50PM | 49.465 | 48.475 | 50.16 | 0.00 | 30.158 | 19.307 | 18.317 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 11.0 | -8.1 | G45T2 | 1 2 | 6 5
AF/36-1 | SGBM22 | Nov 23 2015 10:10AM | Nov 23 2015 6:35PM | Nov 23 2015 11:00PM | Nov 24 2015 1:20AM | 49.47 | 48.475 | 41.35 | 0.00 | 24.047 | 25.423 | 24.428 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.8 | 15.0 | -10.8 | G45T2 | 1 2 | 7 8
AF/32a-1 | SGBM22 | Nov 23 2015 5:30PM | Nov 23 2015 8:34PM | Nov 23 2015 9:25PM | Nov 23 2015 10:40PM | 49.462 | 48.475 | 41.42 | 0.00 | 30.119 | 19.343 | 18.356 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 11.0 | -8.1 | G45T2 | 1 2 | 5.5 5.5
B/59-1 | SGBM02 | Nov 21 2015 5:50PM | Nov 23 2015 9:20AM | Nov 23 2015 6:23PM | Nov 23 2015 7:30PM | 51.46 | 51.275 | 40.17 20.17 | 0.00 0.00 | 16.970 | 34.490 | 34.305 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.2 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
Aa/61-1 | SGBM02 | Nov 21 2015 7:30PM | Nov 22 2015 10:00AM | Nov 22 2015 3:20PM | Nov 22 2015 5:00PM | 51.468 | 51.075 | 52.01 | 0.00 | 23.710 | 27.758 | 27.365 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.1 | 17.0 | -100.0 | G35T2 | 1 2 3 | 6 6 5
C/54-1 | SGBM02 | Nov 21 2015 8:40AM | Nov 21 2015 3:40PM | Nov 21 2015 7:31PM | Nov 21 2015 9:00PM | 51.515 | 51.375 | 40.32 | 0.00 | 12.319 | 40.000 | 39.056 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.3 | 24.0 | -17.3 | G45T2 | 1 2 3 4 | 7 7 6 4
Q/22-1 | SGBM21 | Nov 19 2015 6:20PM | Nov 21 2015 10:55AM | Nov 21 2015 3:07PM | Nov 21 2015 4:00PM | 53.605 | 52.775 | 45.53 | 0.00 | 36.735 | 16.870 | 16.040 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.1 | 9.0 | -100.0 | G35T2 | 1 2 | 5 4
X6a/Y4-1 | SGBM05 | Nov 20 2015 7:00PM | Nov 21 2015 1:45PM | Nov 21 2015 2:46PM | Nov 21 2015 3:54PM | 55.662 | 51.075 | 47.20 | 0.00 | 25.702 | 29.960 | 25.373 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 14.0 | 24.9 | G45T2 | 1 2 | 7 7
AE/39-1 | SGBM22 | Nov 20 2015 6:00PM | Nov 21 2015 1:37PM | Nov 21 2015 2:50PM | Nov 21 2015 3:44PM | 49.502 | 48.775 | 50.28 | 0.00 | 22.582 | 26.920 | 26.193 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.6 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
B/58-1 | SGBM02 | Nov 20 2015 9:25AM | Nov 20 2015 9:20PM | Nov 21 2015 1:21PM | Nov 21 2015 2:20PM | 51.483 | 51.275 | 40.41 32.91 22.41 | 0.00 0.00 0.00 | 16.211 | 87.683 | 35.064 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.5 | 22.0 | 6.5 | G45T2 | 1 2 3 | 8 7 7
Aa/57-1 | SGBM02 | Nov 20 2015 7:50AM | Nov 20 2015 4:25PM | Nov 20 2015 9:01PM | Nov 20 2015 11:35PM | 51.714 | 51.275 | 52.37 | 0.00 | 43.374 | 31.840 | 7.901 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | 8.541 | 3.5 | 20.0 | -100.0 | G35T2 | 1 2 3 | 8 7 5
B/62-1 | SGBM02 | Nov 19 2015 2:54PM | Nov 19 2015 7:50PM | Nov 20 2015 4:44PM | Nov 20 2015 6:20PM | 51.43 | 51.075 | 43.12 | 0.00 | 19.003 | 84.550 | 32.072 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.2 | 20.0 | -100.0 | G45T2 | 1 2 3 | 8 7 5
C/52-1 | SGBM02 | Nov 18 2015 6:01PM | Nov 19 2015 2:00PM | Nov 19 2015 10:30PM | Nov 20 2015 12:15AM | 51.56 | 51.275 | 40.46 30.46 | 0.00 0.00 | 11.056 | 41.400 | 40.219 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.8 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 6 6
X8/Y6a-1 | SGBM18 | Nov 19 2015 1:00PM | Nov 19 2015 5:10PM | Nov 19 2015 9:44PM | Nov 19 2015 10:40PM | 55.576 | 54.625 | 56.28 | 0.00 | 47.281 | 25.995 | 7.344 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | 7.984 | 3.2 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
B/60-1 | SGBM08 | Nov 18 2015 12:50PM | Nov 19 2015 1:15PM | Nov 19 2015 7:25PM | Nov 19 2015 9:00PM | 51.6 | 51.275 | 40.37 28.37 | 0.00 0.00 | 18.074 | 85.900 | 33.201 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.7 | 20.0 | -100.0 | G45T2 | 1 2 3 | 8 8 4
N/23-1 | SGBM21 | Nov 18 2015 6:10PM | Nov 19 2015 11:20AM | Nov 19 2015 4:05PM | Nov 19 2015 5:20PM | 53.169 | 52.775 | 45.10 | 0.00 | 32.602 | 20.567 | 20.173 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.9 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
Aca/31a-1 | SGBM22 | Nov 19 2015 8:10AM | Nov 19 2015 11:45AM | Nov 19 2015 3:12PM | Nov 19 2015 4:03PM | 49.539 | 48.475 | 50.33 | 0.00 | 27.028 | 22.511 | 21.447 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.5 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
AD/31a-1 | SGBM19 | Nov 18 2015 6:25PM | Nov 18 2015 9:45PM | Nov 19 2015 3:43AM | Nov 19 2015 4:35AM | 49.475 | 48.475 | 41.40 | 0.00 | 30.895 | 16.660 | 17.580 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.8 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
AF/31a-1 | SGBM22 | Nov 18 2015 5:20PM | Nov 18 2015 8:32PM | Nov 19 2015 2:22AM | Nov 19 2015 4:15AM | 49.351 | 48.475 | 50.22 | 0.00 | 30.222 | 19.129 | 18.253 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.1 | 11.0 | -100.0 | G45T2 | 1 2 | 6 5
Ba/54-1 | SGBM02 | Nov 17 2015 8:30AM | Nov 18 2015 2:28PM | Nov 18 2015 6:27PM | Nov 18 2015 8:00PM | 51.751 | 51.275 | 43.69 37.69 | 0.00 0.00 | 13.194 | 91.231 | 38.081 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.8 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
X6a/Y4-5 | SGBM21 | Nov 18 2015 10:00AM | Nov 18 2015 2:10PM | Nov 18 2015 4:55PM | Nov 18 2015 6:20PM | 55.787 | 51.075 | 56.50 | 0.00 | 25.902 | 29.885 | 25.173 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 14.0 | -11.1 | G45T2 | 1 2 | 7 7
B/57-1 | SGBM08 | Nov 17 2015 9:15AM | Nov 18 2015 10:45AM | Nov 18 2015 12:35PM | Nov 18 2015 2:05PM | 51.713 | 51.275 | 43.50 39.00 21.50 | 0.00 0.00 0.00 | 14.698 | 37.015 | 36.577 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.2 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
Na/20a-1 | SGBM05 | Nov 18 2015 8:00AM | Nov 18 2015 9:47AM | Nov 18 2015 11:29AM | Nov 18 2015 12:10PM | 53.735 | 53.675 | 54.43 | 0.00 | 38.234 | 15.501 | 15.441 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 6.8 | 8.0 | -100.0 | G35T2 | 1 | 8
AE/38-1 | SGBM19 | Nov 17 2015 4:10PM | Nov 17 2015 8:55PM | Nov 18 2015 3:40AM | Nov 18 2015 4:31AM | 49.52 | 48.775 | 50.17 | 0.00 | 22.774 | 26.746 | 26.001 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 15.0 | -11.5 | G45T2 | 1 2 | 8 7
AE/35a-1 | SGBM22 | Nov 17 2015 1:00PM | Nov 17 2015 5:37PM | Nov 18 2015 1:51AM | Nov 18 2015 3:51AM | 49.632 | 48.775 | 50.38 | 0.00 | 24.684 | 24.948 | 24.091 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 15.0 | 40.9 | G45T2 | 1 2 | 8 7
Aa/56-1 | SGBM02 | Nov 17 2015 11:55AM | Nov 17 2015 5:50PM | Nov 17 2015 8:55PM | Nov 17 2015 11:35PM | 51.77 | 50.775 | 52.55 | 0.00 | 18.650 | 33.120 | 32.125 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.2 | 20.0 | -100.0 | G35T2 | 1 2 3 4 | 6 6 6 2
X9/Y2-1 | SGBM21 | Nov 17 2015 8:00AM | Nov 17 2015 1:00PM | Nov 17 2015 8:30PM | Nov 17 2015 10:20PM | 55.631 | 55.075 | 47.34 | 0.00 | 24.939 | 30.692 | 30.136 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.3 | 16.0 | -13.3 | G45T2 | 1 2 | 8 8
P/22-1 | SGBM05 | Nov 14 2015 12:00PM | Nov 17 2015 9:47AM | Nov 17 2015 5:30PM | Nov 17 2015 6:10PM | 53.493 | 52.775 | 45.40 | 0.00 | 36.801 | 17.600 | 15.974 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.1 | 8.0 | -100.0 | G45T2 | 1 | 8
L/18a-1 | SGBM20 | Nov 14 2015 6:22PM | Nov 16 2015 5:00PM | Nov 17 2015 1:35PM | Nov 17 2015 2:20PM | 53.648 | 52.175 | 45.39 | 0.00 | 39.894 | 68.148 | 12.281 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.4 | 8.0 | -100.0 | G45T2 | 1 2 | 5 3
M/18a-1 | SGBM05 | Nov 14 2015 4:22PM | Nov 17 2015 12:05PM | Nov 17 2015 12:25PM | Nov 17 2015 1:30PM | 55.559 | 52.175 | 47.44 | 0.00 | 39.739 | 15.820 | 12.436 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.5 | 8.0 | -100.0 | G35T2 | 1 | 8
B/63-1 | SGBM02 | Nov 15 2015 8:30AM | Nov 16 2015 1:00PM | Nov 17 2015 10:27AM | Nov 17 2015 11:35AM | 51.668 | 51.075 | 43.55 | 0.00 | 23.850 | 27.818 | 27.225 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 17.0 | -100.0 | G35T2 | 1 2 3 | 6 6 5
AE/37-1 | SGBM19 | Nov 17 2015 3:20PM | Nov 17 2015 7:45PM | Nov 18 2015 1:02AM | Nov 17 2015 1:45AM | 49.576 | 48.775 | 50.39 | 0.00 | 23.690 | 25.886 | 25.085 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -11.1 | G45T2 | 1 2 | 8 7
Aa/59-1 | SGBM08 | Nov 15 2015 2:00PM | Nov 16 2015 11:51AM | Nov 16 2015 10:22PM | Nov 16 2015 11:35PM | 51.535 | 51.275 | 43.28 28.28 | 0.00 0.00 | 16.881 | 35.400 | 34.394 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.2 | 17.0 | 11.9 | G45T2 | 1 2 3 | 6 6 5
G/31-8 | SGBM20 | Nov 15 2015 10:10AM | Nov 16 2015 1:15PM | Nov 16 2015 7:12PM | Nov 16 2015 8:15PM | 52.128 | 48.175 | 43.95 | 0.00 | 30.248 | 74.828 | 17.927 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.9 | 11.0 | 38.9 | G45T2 | 1 2 | 7 4
AA/52-1 | SGBM19 | Nov 16 2015 8:00AM | Nov 16 2015 11:37AM | Nov 16 2015 4:59PM | Nov 16 2015 7:30PM | 49.372 | 49.075 | 50.26 | 0.00 | 25.756 | 23.616 | 23.319 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 16.0 | -100.0 | G35T2 | 1 2 3 | 7 7 2
Fa/33-1 | SGBM20 | Nov 15 2015 9:30AM | Nov 16 2015 9:30AM | Nov 16 2015 12:19PM | Nov 16 2015 12:50PM | 52.348 | 50.775 | 44.28 | 0.00 | 38.084 | 67.548 | 12.691 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T12-225 | 97.7432 | - | 97.7432 | 12 | - | 5.6 | 8.0 | -100.0 | G45T2 | 1 | 8
Aa/60-1 | SGBM02 | Nov 9 2015 6:15PM | Nov 15 2015 2:00PM | Nov 15 2015 7:57PM | Nov 15 2015 9:55PM | 51.69 | 51.275 | 37.38 34.38 28.88 | 0.00 0.00 0.00 | 23.179 | 28.511 | 28.096 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 18.0 | 45.0 | G35T2 | 1 2 3 | 6 6 6
B/55-1 | SGBM18 | Nov 14 2015 1:25PM | Nov 14 2015 7:20PM | Nov 15 2015 12:30AM | Nov 15 2015 1:55AM | 51.707 | 51.275 | 52.51 | 0.00 | 13.507 | 38.200 | 37.768 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.7 | 22.0 | -100.0 | G45T2 | 1 2 | 10 12
C/63-1 | SGBM02 | Nov 14 2015 12:00PM | Nov 14 2015 5:36PM | Nov 14 2015 10:09PM | Nov 14 2015 11:20PM | 51.71 | 51.375 | 38.46 | 0.00 | 18.058 | 33.652 | 33.317 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.7 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
AC/53-1 | SGBM22 | Nov 14 2015 3:10PM | Nov 14 2015 7:55PM | Nov 14 2015 9:25PM | Nov 14 2015 10:25PM | 49.31 | 49.075 | 41.96 | 0.00 | 25.709 | 23.601 | 23.366 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
X7/Y7-1 | SGBM21 | Nov 11 2015 6:50PM | Nov 14 2015 5:15PM | Nov 14 2015 8:49PM | Nov 14 2015 10:20PM | 55.537 | 55.075 | 46.88 | 0.00 | 32.777 | 22.760 | 22.298 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
Fa/31-1 | SGBM20 | Nov 12 2015 7:20PM | Nov 14 2015 1:40PM | Nov 14 2015 9:12PM | Nov 14 2015 9:30PM | 52.235 | 50.775 | 44.06 | 0.00 | 29.560 | 23.500 | 21.215 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T12-225 | 97.7432 | - | 97.7432 | 12 | - | 9.4 | 8.0 | -100.0 | G35T2 | 1 | 8
Fa/32-1 | SGBM20 | Nov 14 2015 9:00AM | Nov 14 2015 3:37PM | Nov 14 2015 6:55PM | Nov 14 2015 7:30PM | 52.222 | 50.775 | 44.00 | 0.00 | 37.700 | 15.300 | 13.075 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T12-225 | 97.7432 | - | 97.7432 | 12 | - | 5.8 | 8.0 | -100.0 | G45T2 | 1 | 8
AD/46-1 | SGBM19 | Nov 13 2015 10:30AM | Nov 14 2015 1:20PM | Nov 14 2015 2:43PM | Nov 14 2015 4:15PM | 43.37 | 49.075 | 41.24 26.24 | 0.00 0.00 | 20.811 | 22.559 | 28.264 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 16.0 | -12.5 | G45T2 | 1 2 3 | 6 6 4
Aa/58-1 | SGBM08 | Nov 9 2015 7:15PM | Nov 12 2015 9:25AM | Nov 12 2015 4:00PM | Nov 14 2015 11:57AM | 51.646 | 51.275 | 43.54 17.54 | 0.00 0.00 | 15.942 | 35.704 | 35.333 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.6 | 23.0 | 13.4 | G45T2 | C520123284 C480011635 | 12 11
Ba/53-1 | SGBM08 | Nov 13 2015 9:20AM | Nov 13 2015 6:40PM | Nov 14 2015 12:27AM | Nov 14 2015 2:05AM | 51.76 | 51.075 | 37.56 | 0.00 | 18.060 | 33.700 | 33.015 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.6 | 21.0 | -100.0 | G35T2 | 1 2 3 | 7 7 7
X10/Y7-1 | SGBM03 | Nov 11 2015 9:37AM | Nov 13 2015 5:20PM | Nov 13 2015 10:54PM | Nov 13 2015 11:55PM | 55.7 | 55.075 | 47.14 | 0.00 | 36.144 | 19.556 | 18.931 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
Aa/62-1 | SGBM02 | Nov 12 2015 6:15PM | Nov 13 2015 5:20PM | Nov 13 2015 10:40PM | Nov 13 2015 11:25PM | 51.64 | 51.375 | 43.38 37.38 | 0.00 0.00 | 19.175 | 32.465 | 32.200 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 14.2 | 20.0 | -100.0 | G45T2 | 1 2 | 11 9
ACa/46a-1 | SGBM19 | Nov 13 2015 2:45PM | Nov 13 2015 7:30PM | Nov 13 2015 7:42PM | Nov 13 2015 8:48PM | 49.34 | 49.075 | 41.27 | 0.00 | 25.900 | 23.440 | 23.175 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
X3/Y2-1 | SGBM21 | Nov 12 2015 7:00PM | Nov 13 2015 12:10PM | Nov 13 2015 6:57PM | Nov 13 2015 8:00PM | 55.772 | 55.075 | 47.55 36.55 28.05 | 0.00 0.00 0.00 | 25.146 | 30.626 | 29.929 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.2 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
X6a/Y4-2 | SGBM21 | Nov 9 2015 5:30PM | Nov 12 2015 12:00PM | Nov 12 2015 8:28PM | Nov 12 2015 10:00PM | 55.722 | 51.075 | 47.47 | 0.00 | 25.869 | 29.853 | 25.206 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 17.0 | -100.0 | G45T2 | 1 2 3 | 8 2 7
Aba/35-1 | SGBM19 | Nov 12 2015 12:36PM | Nov 12 2015 4:34PM | Nov 12 2015 8:12PM | Nov 12 2015 9:49PM | 49.653 | 48.775 | 41.58 | 0.00 | 32.511 | 17.142 | 16.264 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.2 | 12.0 | -16.5 | G35T2 | 1 2 | 6 6
K/18-2 | SGBM20 | Nov 12 2015 2:00PM | Nov 12 2015 6:00PM | Nov 12 2015 7:15PM | Nov 12 2015 8:30PM | 53.735 | 51.375 | 54.62 | 0.00 | 24.617 | 29.118 | 26.758 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 14.0 | 18.4 | G45T2 | 1 2 | 8 6
AD/36-1 | SGBM19 | Nov 9 2015 3:10PM | Nov 12 2015 3:00PM | Nov 12 2015 4:40PM | Nov 12 2015 6:50PM | 49.581 | 49.075 | 41.19 | 0.00 | 29.588 | 19.993 | 19.487 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 14.0 | -100.0 | G35T2 | 1 2 | 6 8
AC/52-1 | SGBM22 | Nov 11 2015 4:30PM | Nov 12 2015 10:26AM | Nov 12 2015 4:20PM | Nov 12 2015 5:15PM | 49.329 | 49.075 | 41.00 29.00 | 0.00 0.00 | 25.668 | 24.431 | 23.407 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
X6/Y7-1 | SGBM03 | Nov 7 2015 7:52PM | Nov 11 2015 6:20PM | Nov 12 2015 3:07PM | Nov 12 2015 5:00PM | 55.639 | 55.075 | 47.16 | 0.00 | 32.961 | 22.678 | 22.114 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 15.0 | -100.0 | G45T2 | 1 2 | 5 10
Ca/52-1 | SGBM02 | Nov 11 2015 11:10AM | Nov 11 2015 8:02PM | Nov 12 2015 12:40PM | Nov 12 2015 1:56PM | 51.895 | 51.275 | 43.65 | 0.00 | 11.245 | 40.650 | 40.030 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.7 | 29.0 | -17.7 | G45T2 | C480011623 C480011625 C480011626 | 9 10 10
G/31-4 | SGBM20 | Nov 12 2015 5:05PM | Nov 12 2015 9:40PM | Nov 11 2015 11:50PM | Nov 12 2015 1:05AM | 52.241 | 48.175 | 44.03 | 0.00 | 30.226 | 22.015 | 17.949 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.9 | 11.0 | -100.0 | G45T2 | 1 2 | 5.5 5.5
G/31-5 | SGBM20 | Nov 11 2015 8:00AM | Nov 11 2015 3:40PM | Nov 11 2015 8:45PM | Nov 11 2015 9:50PM | 52.185 | 48.175 | 44.07 | 0.00 | 30.570 | 22.500 | 17.605 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.8 | 11.0 | -7.8 | G45T2 | 1 2 | 7 4
E/63-1 | SGBM23 | Nov 9 2015 3:36PM | Nov 11 2015 11:42AM | Nov 11 2015 6:30PM | Nov 11 2015 9:00PM | 51.76 | 51.375 | 43.56 | 0.00 | 15.165 | 36.595 | 36.210 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 16.0 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 2
AD/35-1 | SGBM19 | Nov 11 2015 8:14AM | Nov 11 2015 10:29AM | Nov 11 2015 7:27PM | Nov 11 2015 8:28PM | 49.65 | 49.075 | 41.59 | 0.00 | 30.293 | 19.357 | 18.782 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.3 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
AD/37-1 | SGBM22 | Nov 9 2015 2:50PM | Nov 11 2015 10:40AM | Nov 11 2015 6:05PM | Nov 11 2015 6:50PM | 49.492 | 49.075 | 41.16 | 0.00 | 28.764 | 20.728 | 20.311 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.0 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
X3/Y3-1 | SGBM21 | Nov 7 2015 7:30PM | Nov 9 2015 3:00PM | Nov 11 2015 3:40PM | Nov 11 2015 5:50PM | 55.908 | 55.075 | 47.79 | 0.00 | 26.786 | 30.000 | 28.289 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.5 | 15.0 | -100.0 | G45T2 | 1 2 3 | 6 7 2
AD/38-1 | SGBM22 | Nov 10 2015 1:35PM | Nov 11 2015 8:14AM | Nov 11 2015 11:10AM | Nov 11 2015 12:00PM | 49.453 | 49.075 | 50.25 | 0.00 | 27.847 | 21.606 | 21.228 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.4 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
H/18-2 | SGBM20 | Nov 9 2015 11:00AM | Nov 9 2015 3:45PM | Nov 9 2015 8:33PM | Nov 9 2015 9:40PM | 53.676 | 50.575 | 45.43 | 0.00 | 23.926 | 29.750 | 26.649 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.8 | 15.0 | -11.8 | G45T2 | 1 2 | 8 7
D/63-1 | SGBM17 | Oct 31 2015 12:40PM | Nov 7 2015 11:30AM | Nov 9 2015 6:20PM | Nov 9 2015 8:23PM | 51.89 | 51.375 | 43.73 29.73 | 0.00 0.00 | 17.031 | 34.859 | 34.344 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.2 | 20.0 | 4.8 | G45T2 | PJ1376 PJ1377 PJ1378 PJ1383 | 6 6 6 2
Aa/63-1 | SGBM18 | Nov 9 2015 12:05PM | Nov 9 2015 4:10PM | Nov 9 2015 5:22PM | Nov 9 2015 6:20PM | 51.75 | 50.775 | 52.81 | 0.00 | 23.713 | 28.037 | 27.062 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.0 | 16.0 | -100.0 | G45T2 | 1 2 3 | 6 6 4
G/31-3 | SGBM22 | Nov 7 2015 11:05AM | Nov 7 2015 2:30PM | Nov 7 2015 11:05PM | Nov 7 2015 11:58PM | 52.1 | 48.175 | 43.99 | 0.00 | 30.490 | 21.610 | 17.685 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.8 | 11.0 | -7.8 | G45T2 | 1 2 | 6 5
H/59-6 | SGBM08 | Nov 2 2015 8:50AM | Nov 7 2015 9:15PM | Nov 7 2015 6:20PM | Nov 7 2015 7:00PM | 52 | 50.575 | 43.79 25.29 17.79 | 0.00 0.00 0.00 | 10.291 | 41.709 | 40.284 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.8 | 18.0 | -17.8 | G45T2 | PJ1376 PJ1377 PJ1378 | 6 6 6
X2/Y7-1 | SGBM20 | Nov 6 2015 7:30PM | Nov 7 2015 11:35AM | Nov 7 2015 2:41PM | Nov 7 2015 3:30PM | 55.768 | 55.075 | 47.28 | 0.00 | 30.982 | 24.786 | 24.093 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
AA/46-1 | SGBM02 | Nov 6 2015 4:00PM | Nov 6 2015 7:55PM | Nov 7 2015 2:15AM | Nov 7 2015 3:05AM | 49.419 | 49.075 | 50.42 | 0.00 | 27.025 | 22.394 | 22.050 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.7 | 13.0 | -100.0 | G35T2 | 1 2 | 6 7
Aba/45-1 | SGBM22 | Nov 6 2015 3:00PM | Nov 6 2015 7:52PM | Nov 7 2015 12:15AM | Nov 7 2015 2:15AM | 49.512 | 49.075 | 50.21 | 0.00 | 26.812 | 22.700 | 22.263 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 13.0 | 32.2 | G45T2 | 1 2 | 5 8
Aca/46-1 | SGBM22 | Nov 6 2015 2:00PM | Nov 6 2015 5:44PM | Nov 6 2015 11:58PM | Nov 7 2015 12:50AM | 49.454 | 49.075 | 50.23 | 0.00 | 26.030 | 23.424 | 23.045 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
G/33-3 | SGBM22 | Nov 7 2015 6:30PM | Nov 7 2015 9:00PM | Nov 7 2015 11:55PM | Nov 7 2015 12:50AM | 52.205 | 50.775 | 43.99 | 0.00 | 37.985 | 14.220 | 12.790 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.7 | 10.0 | -100.0 | G35T2 | 1 2 | 6 4
H/59-3 | SGBM08 | Nov 2 2015 9:35AM | Nov 6 2015 9:30PM | Nov 6 2015 10:25PM | Nov 6 2015 11:40PM | 51.99 | 50.575 | 43.81 37.81 24.81 | 0.00 0.00 0.00 | 10.510 | 41.480 | 40.065 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.7 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
X4/Y2-1 | SGBM21 | Nov 5 2015 12:30PM | Nov 6 2015 7:05PM | Nov 6 2015 9:00PM | Nov 6 2015 11:30PM | 55.702 | 55.075 | 47.42 42.92 | 0.00 0.00 | 24.925 | 30.777 | 30.150 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 13.3 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 9 2
X4/Y7-1 | SGBM21 | Nov 5 2015 7:00PM | Nov 6 2015 12:05PM | Nov 6 2015 9:11PM | Nov 6 2015 10:40PM | 55.704 | 55.075 | 47.22 | 0.00 | 32.815 | 23.400 | 22.260 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
H/35-1 | SGBM20 | Nov 6 2015 8:00AM | Nov 6 2015 8:50PM | Nov 6 2015 9:15PM | Nov 6 2015 10:25PM | 52.178 | 51.375 | 43.97 | 0.00 | 32.874 | 19.501 | 18.501 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.2 | 12.0 | -8.2 | G45T2 | 1 2 | 6 6
G/31-7 | SGBM20 | Nov 6 2015 2:30PM | Nov 6 2015 6:43PM | Nov 6 2015 7:00PM | Nov 6 2015 8:35PM | 52.134 | 48.175 | 44.02 | 0.00 | 30.320 | 22.700 | 17.855 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.9 | 12.0 | -7.9 | G45T2 | 1 2 3 | 5 5 2
Aba/43-1 | SGBM22 | Nov 6 2015 8:45AM | Nov 6 2015 12:05PM | Nov 6 2015 6:44PM | Nov 6 2015 8:00PM | 49.553 | 49.075 | 50.40 | 0.00 | 28.005 | 21.548 | 21.070 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 14.0 | -100.0 | G45T2 | 1 2 3 | 6 5 3
J/55-2a | SGBM23 | Nov 6 2015 8:10AM | Nov 6 2015 4:15PM | Nov 6 2015 6:05PM | Nov 6 2015 7:00PM | 51.88 | 49.375 | 43.67 25.67 | 0.00 0.00 | 14.974 | 36.906 | 34.401 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.2 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 7 8
G/33-2 | SGBM20 | Nov 6 2015 8:30AM | Nov 6 2015 11:15AM | Nov 6 2015 11:37AM | Nov 6 2015 12:32PM | 52.273 | 50.775 | 44.13 | 0.00 | 37.832 | 15.300 | 12.943 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.7 | 8.0 | -100.0 | G35T2 | 1 | 8
AD/43-1 | SGBM02 | Nov 5 2015 9:20AM | Nov 5 2015 12:30PM | Nov 6 2015 2:40AM | Nov 6 2015 5:30AM | 49.592 | 49.075 | 50.44 | 0.00 | 26.844 | 22.748 | 22.231 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
AD/44-1 | SGBM22 | Nov 5 2015 3:50PM | Nov 5 2015 8:18PM | Nov 6 2015 1:00AM | Nov 6 2015 3:30AM | 49.516 | 49.075 | 50.32 | 0.00 | 26.718 | 22.798 | 22.357 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 14.0 | -100.0 | G45T2 | 1 2 3 | 6 6 2
AD/45-1 | SGBM22 | Nov 5 2015 12:20PM | Nov 5 2015 5:00PM | Nov 6 2015 1:00AM | Nov 6 2015 2:20AM | 49.42 | 49.075 | 50.15 | 0.00 | 25.555 | 23.865 | 23.520 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.4 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
G/31-2 | SGBM20 | Nov 5 2015 12:08PM | Nov 5 2015 7:30PM | Nov 5 2015 10:28PM | Nov 5 2015 11:15PM | 52.162 | 48.175 | 43.96 | 0.00 | 30.663 | 22.300 | 17.512 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.7 | 12.0 | -7.7 | G45T2 | Pending 2 | 6 6
AB/45-2 | SGBM02 | Nov 4 2015 7:15PM | Nov 5 2015 8:11AM | Nov 5 2015 3:43PM | Nov 5 2015 5:20PM | 49.538 | 48.275 | 50.35 | 0.00 | 20.655 | 28.883 | 27.620 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.2 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
J/55-2b | SGBM15 | Nov 4 2015 5:00PM | Nov 5 2015 11:16AM | Nov 5 2015 3:02PM | Nov 5 2015 4:21PM | 51.882 | 49.375 | 43.73 37.73 | 0.00 0.00 | 15.232 | 36.650 | 34.143 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.1 | 23.0 | 52.5 | G45T2 | PJ1253 PJ1255 PJ1258 | 8 8 7
X4/Y3-1 | SGBM21 | Nov 4 2015 5:52PM | Nov 5 2015 11:22AM | Nov 5 2015 12:52PM | Nov 5 2015 2:50PM | 55.909 | 55.075 | 47.42 37.12 | 0.00 0.00 | 27.022 | 28.887 | 28.053 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 12.4 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
H/59-7 | SGBM08 | Nov 2 2015 8:26AM | Nov 4 2015 10:00PM | Nov 5 2015 12:35PM | Nov 5 2015 2:25PM | 51.93 | 50.575 | 43.81 29.21 | 0.00 0.00 | 10.311 | 42.500 | 40.264 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.8 | 22.5 | 26.5 | G45T2 | C480011361 C480011364 | 11.5 11
AB/43-2 | SGBM22 | Nov 4 2015 10:45AM | Nov 4 2015 4:13PM | Nov 4 2015 11:40PM | Nov 5 2015 3:00AM | 49.582 | 48.275 | 50.46 | 0.00 | 23.259 | 26.323 | 25.016 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 7 4
AD/42-1 | SGBM22 | Nov 4 2015 12:20PM | Nov 4 2015 4:03PM | Nov 4 2015 9:54PM | Nov 5 2015 12:15AM | 49.566 | 49.075 | 50.40 | 0.00 | 26.998 | 22.568 | 22.077 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 13.0 | -100.0 | G45T2 | 1 2 | 6 7
G/31-9 | SGBM20 | Nov 4 2015 11:17AM | Nov 4 2015 6:36PM | Nov 4 2015 11:08PM | Nov 5 2015 12:10AM | 52.22 | 48.175 | 44.15 | 0.00 | 30.245 | 22.900 | 17.930 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.9 | 11.0 | -7.9 | G45T2 | 1 2 | 7 4
X3/Y7-1 | SGBM21 | Nov 4 2015 11:15AM | Nov 4 2015 5:57PM | Nov 4 2015 9:30PM | Nov 4 2015 11:20PM | 55.712 | 55.075 | 47.47 42.47 | 0.00 0.00 | 31.966 | 23.746 | 23.109 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
Aba/44-1 | SGBM19 | Nov 4 2015 8:00AM | Nov 4 2015 11:50AM | Nov 4 2015 1:58PM | Nov 4 2015 3:20PM | 49.663 | 49.075 | 42.48 | 0.00 | 27.983 | 15.680 | 21.092 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 12.0 | 28.8 | G35T2 | 1 2 | 6 6
X5/Y7-1 | SGBM21 | Nov 3 2015 7:12PM | Nov 4 2015 10:35AM | Nov 4 2015 12:40PM | Nov 4 2015 2:00PM | 55.739 | 55.075 | 47.27 40.87 | 0.00 0.00 | 32.570 | 23.700 | 22.505 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.9 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
AB/45-1 | SGBM19 | Nov 2 2015 5:40PM | Nov 3 2015 6:40PM | Nov 4 2015 3:40AM | Nov 4 2015 4:40AM | 49.531 | 48.275 | 41.41 32.41 29.41 | 0.00 0.00 0.00 | 23.339 | 26.192 | 24.936 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.0 | 14.0 | -11.0 | G45T2 | 1 2 | 7 7
Aba/42-1 | SGBM19 | Nov 3 2015 11:20AM | Nov 3 2015 5:25PM | Nov 4 2015 1:09AM | Nov 4 2015 2:50AM | 49.468 | 49.075 | 41.62 | 0.00 | 30.573 | 18.895 | 18.502 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.2 | 15.0 | -100.0 | G45T2 | 1 2 3 | 4 6 5
H/59-2 | SGBM08 | Oct 31 2015 5:35PM | Nov 3 2015 3:35PM | Nov 3 2015 8:50PM | Nov 3 2015 10:10PM | 51.923 | 50.575 | 43.82 36.82 | 0.00 0.00 | 10.223 | 94.523 | 40.352 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.8 | 22.0 | -100.0 | G45T2 | 1 2 | 10 12
G/31-6 | SGBM20 | Nov 3 2015 9:40AM | Nov 3 2015 4:42PM | Nov 3 2015 8:19PM | Nov 3 2015 9:30PM | 52.148 | 48.175 | 43.96 | 0.00 | 30.563 | 22.400 | 17.612 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.8 | 12.0 | -100.0 | G45T2 | 1 2 | 5 7
AB/44-1 | SGBM22 | Nov 2 2015 5:20PM | Nov 3 2015 10:10AM | Nov 3 2015 4:33PM | Nov 3 2015 6:50PM | 49.707 | 48.275 | 41.48 29.48 | 0.00 0.00 | 24.179 | 25.528 | 24.096 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 17.0 | -100.0 | G45T2 | 1 2 3 | 4 7 6
AB/43-1 | SGBM19 | Nov 2 2015 6:00PM | Nov 3 2015 12:00PM | Nov 3 2015 2:38PM | Nov 3 2015 5:20PM | 49.445 | 48.275 | 41.33 35.33 | 0.00 0.00 | 25.279 | 24.166 | 22.996 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 17.0 | -100.0 | G35T2 | 1 2 3 | 7 7 3
X3/Y6-1 | SGBM21 | Nov 2 2015 5:46PM | Nov 3 2015 9:25AM | Nov 3 2015 12:05PM | Nov 3 2015 1:30PM | 55.707 | 55.075 | 47.44 32.44 | 0.00 0.00 | 30.842 | 24.865 | 24.233 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.7 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
G/33-1 | SGBM20 | Nov 2 2015 5:58PM | Nov 2 2015 9:15PM | Nov 2 2015 10:04PM | Nov 2 2015 11:20PM | 52.211 | 50.775 | 43.96 | 0.00 | 37.563 | 15.400 | 13.212 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.8 | 9.0 | 54.2 | G35T2 | 1 2 | 8 1
AD/41-1 | SGBM22 | Oct 30 2015 2:40PM | Nov 2 2015 3:55PM | Nov 2 2015 9:14PM | Nov 2 2015 10:40PM | 49.635 | 49.075 | 41.52 | 0.00 | 27.577 | 22.058 | 21.498 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.5 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
X6a/Y4-6 | SGBM21 | Nov 2 2015 10:04AM | Nov 2 2015 4:00PM | Nov 2 2015 9:11PM | Nov 2 2015 10:30PM | 55.864 | 51.075 | 47.41 | 0.00 | 25.906 | 30.500 | 25.169 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
AD/40-1 | SGBM22 | Nov 1 2015 3:15PM | Nov 2 2015 12:10PM | Nov 2 2015 5:13PM | Nov 2 2015 7:30PM | 49.59 | 49.075 | 41.38 32.38 | 0.00 0.00 | 26.998 | 22.592 | 22.077 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
AD/39-1 | SGBM22 | Nov 2 2015 8:40AM | Nov 2 2015 3:00PM | Nov 2 2015 4:21PM | Nov 2 2015 5:45PM | 49.53 | 49.075 | 41.37 | 0.00 | 27.525 | 22.005 | 21.550 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.5 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
X5/Y6-1 | SGBM21 | Oct 31 2015 2:45PM | Nov 2 2015 9:33AM | Nov 2 2015 12:10PM | Nov 2 2015 1:30PM | 55.72 | 55.075 | 47.50 35.60 | 0.00 0.00 | 31.700 | 24.800 | 23.375 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
G/33-4 | SGBM20 | Oct 31 2015 3:55PM | Oct 31 2015 5:57PM | Oct 31 2015 7:56PM | Oct 31 2015 9:00PM | 52.244 | 50.775 | 43.86 | 0.00 | 37.763 | 15.100 | 13.012 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 5.7 | 10.0 | -100.0 | G45T2 | 1 2 | 7 3
H/59-5 | SGBM01 | Oct 26 2015 10:25AM | Oct 31 2015 12:08PM | Oct 31 2015 1:31PM | Oct 31 2015 4:00PM | 51.94 | 50.575 | 44.83 37.83 29.83 27.83 23.83 | 0.00 0.00 0.00 0.00 1.00 | 9.830 | 42.110 | 40.745 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 18.0 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 3
X6a/Y4-3 | SGBM21 | Oct 30 2015 5:15PM | Oct 31 2015 11:30AM | Oct 31 2015 12:00PM | Oct 31 2015 1:30PM | 55.857 | 51.075 | 47.54 35.54 | 0.00 0.00 | 25.745 | 30.800 | 25.330 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
AB/41-1 | SGBM19 | Oct 30 2015 8:00AM | Oct 30 2015 12:45PM | Oct 31 2015 5:18AM | Oct 31 2015 8:00AM | 49.495 | 48.275 | 50.31 | 0.00 | 23.208 | 26.287 | 25.067 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G35T2 | 1 2 3 | 7 6 2
AB/40-2 | SGBM19 | Oct 30 2015 6:30PM | Oct 30 2015 8:20PM | Oct 31 2015 4:20AM | Oct 31 2015 5:55AM | 49.535 | 48.275 | 50.45 | 0.00 | 23.252 | 26.283 | 25.023 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
AB/39-2 | SGBM19 | Oct 30 2015 4:10PM | Oct 30 2015 6:08PM | Oct 31 2015 1:50AM | Oct 31 2015 4:00AM | 49.641 | 48.275 | 50.58 | 0.00 | 23.180 | 26.461 | 25.095 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G35T2 | 1 2 3 | 5 5 5
H/59-1 | SGBM01 | Oct 21 2015 3:15PM | Oct 29 2015 8:41PM | Oct 30 2015 7:00PM | Oct 30 2015 9:00PM | 51.95 | 50.575 | 44.75 25.75 | 0.00 0.00 | 9.848 | 42.102 | 40.727 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 18.0 | 26.0 | -100.0 | G45T2 | 1 2 3 | 11 8 7
AB/44-2 | SGBM19 | Oct 30 2015 11:00AM | Oct 30 2015 3:19PM | Oct 30 2015 6:08PM | Oct 30 2015 8:00PM | 49.607 | 48.275 | 50.54 | 0.00 | 22.236 | 27.371 | 26.039 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.5 | 16.0 | -100.0 | G35T2 | 1 2 3 | 7 6 3
AB/42-2 | SGBM19 | Oct 29 2015 3:00PM | Oct 29 2015 7:48PM | Oct 30 2015 6:39AM | Oct 30 2015 10:00AM | 49.496 | 48.275 | 50.30 | 0.00 | 22.999 | 26.497 | 25.276 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 15.0 | -100.0 | G35T2 | 1 2 3 | 5 8 2
AB/41-2 | SGBM19 | Oct 29 2015 3:20PM | Oct 29 2015 7:52PM | Oct 30 2015 4:08AM | Oct 30 2015 6:20AM | 49.489 | 48.275 | 50.35 | 0.00 | 23.246 | 26.243 | 25.029 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 16.0 | -100.0 | G35T2 | 1 2 3 | 7 7 2
AB/36-1 | SGBM19 | Oct 29 2015 6:40PM | Oct 29 2015 9:10PM | Oct 30 2015 1:13AM | Oct 30 2015 2:45AM | 49.598 | 48.275 | 50.60 | 0.00 | 26.198 | 23.400 | 22.077 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 11.0 | -100.0 | G35T2 | 1 | 11
AB/38-1 | SGBM19 | Oct 28 2015 4:10PM | Oct 28 2015 8:11PM | Oct 29 2015 12:10AM | Oct 29 2015 3:00AM | 49.552 | 48.275 | 50.37 | 0.00 | 23.273 | 26.279 | 25.002 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.0 | 15.0 | -100.0 | G35T2 | 1 2 3 | 7 6 2
H/59-8 | SGBM17 | Oct 26 2015 11:35AM | Oct 27 2015 4:45PM | Oct 28 2015 10:00PM | Oct 29 2015 12:40AM | 51.953 | 50.575 | 43.83 33.63 | 0.00 0.00 | 10.132 | 41.821 | 40.443 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.9 | 20.0 | -100.0 | G45T2 | 1 2 | 11 9
AB/39-1 | SGBM19 | Oct 28 2015 1:45PM | Oct 28 2015 6:08PM | Oct 28 2015 11:13PM | Oct 29 2015 12:20AM | 49.558 | 48.275 | 50.50 | 0.00 | 23.202 | 26.356 | 25.073 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 13.0 | -100.0 | G35T2 | 1 2 | 6 7
X6a/Y4-7 | SGBM21 | Oct 28 2015 5:45PM | Oct 28 2015 10:05PM | Oct 28 2015 9:57PM | Oct 28 2015 11:33PM | 55.797 | 51.075 | 47.62 | 0.00 | 26.022 | 29.775 | 25.053 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
H/59-4 | SGBM01 | Oct 26 2015 10:55AM | Oct 28 2015 3:12PM | Oct 28 2015 9:33PM | Oct 28 2015 11:05PM | 51.91 | 50.575 | 44.79 34.79 | 0.00 0.00 | 10.388 | 41.522 | 40.187 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 17.8 | 24.0 | -17.8 | G45T2 | 1 2 | 12 12
AB/40-1 | SGBM19 | Oct 28 2015 11:45AM | Oct 28 2015 5:10PM | Oct 28 2015 9:09PM | Oct 28 2015 10:55PM | 49.526 | 48.275 | 50.40 | 0.00 | 23.204 | 26.322 | 25.071 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -100.0 | G35T2 | 1 2 3 | 6 6 3
H/53-1 | SGBM01 | Oct 27 2015 8:00PM | Oct 28 2015 8:24AM | Oct 28 2015 1:54PM | Oct 28 2015 3:23PM | 51.945 | 51.375 | 52.74 | 0.00 | 16.237 | 35.708 | 35.138 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 15.5 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
AB/36-2 | SGBM19 | Oct 27 2015 4:20PM | Oct 27 2015 7:31PM | Oct 27 2015 10:30PM | Oct 28 2015 1:45AM | 49.598 | 48.275 | 50.58 | 0.00 | 26.176 | 23.422 | 22.099 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 15.0 | -100.0 | G35T2 | 1 2 3 | 4 7 4
AB/38-2 | SGBM19 | Oct 27 2015 1:00PM | Oct 27 2015 5:54PM | Oct 27 2015 9:39PM | Oct 27 2015 10:45PM | 49.598 | 48.275 | 50.53 | 0.00 | 23.235 | 26.363 | 25.040 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
X6a/Y4-4 | SGBM21 | Oct 24 2015 5:40PM | Oct 25 2015 12:30PM | Oct 26 2015 2:54PM | Oct 26 2015 4:20PM | 55.839 | 51.075 | 47.60 | 0.00 | 26.002 | 29.837 | 25.073 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 15.0 | -11.1 | G45T2 | 1 2 | 7.5 7.5
Aba/36-1 | SGBM08 | Oct 25 2015 8:00PM | Oct 26 2015 10:25AM | Oct 26 2015 1:13PM | Oct 26 2015 2:40PM | 49.649 | 49.075 | 50.56 | 0.00 | 27.062 | 22.587 | 22.013 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.7 | 13.0 | -100.0 | G45T2 | 1 2 | 7 6
Aba/38-1 | SGBM08 | Oct 24 2015 3:50PM | Oct 24 2015 6:30PM | Oct 24 2015 10:08PM | Oct 24 2015 11:30PM | 49.591 | 49.075 | 50.48 | 0.00 | 27.982 | 21.609 | 21.093 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 12.0 | -100.0 | G45T2 | 1 2 | 5 7
Aba/40-1 | SGBM08 | Oct 24 2015 12:00PM | Oct 24 2015 4:29PM | Oct 24 2015 9:05PM | Oct 24 2015 10:20PM | 49.498 | 49.075 | 50.36 | 0.00 | 27.856 | 21.642 | 21.219 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.4 | 14.0 | -100.0 | G45T2 | 1 2 3 | 6 6 2
AB/31-1 | SGBM22 | Oct 23 2015 6:00PM | Oct 23 2015 9:40PM | Oct 24 2015 2:52AM | Oct 24 2015 4:00AM | 50.144 | 48.475 | 50.87 | 0.00 | 27.567 | 22.577 | 20.908 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.2 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
Aba/39-1 | SGBM08 | Oct 21 2015 5:50PM | Oct 21 2015 9:35PM | Oct 22 2015 3:00AM | Oct 22 2015 5:00AM | 49.505 | 49.075 | 50.40 | 0.00 | 28.003 | 21.502 | 21.072 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 11.0 | 18.1 | G45T2 | 1 2 | 5.5 5.5
Aba/37-1 | SGBM08 | Oct 21 2015 12:00PM | Oct 21 2015 3:40PM | Oct 22 2015 2:14AM | Oct 22 2015 3:50AM | 49.63 | 49.075 | 50.48 | 0.00 | 29.982 | 19.648 | 19.093 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
AB/25-1 | SGBM22 | Oct 21 2015 12:30PM | Oct 21 2015 4:00PM | Oct 21 2015 7:09PM | Oct 21 2015 8:10PM | 49.891 | 48.475 | 50.03 | 0.00 | 27.835 | 22.056 | 20.640 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.1 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
X1/Y2-1 | SGBM09 | Oct 21 2015 8:00AM | Oct 21 2015 2:15PM | Oct 21 2015 5:33PM | Oct 21 2015 7:20PM | 55.76 | 55.075 | 56.48 | 0.00 | 29.878 | 25.882 | 25.197 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 5 4
AB/24a-1 | SGBM22 | Oct 20 2015 5:30PM | Oct 20 2015 9:50PM | Oct 20 2015 11:18PM | Oct 21 2015 1:20AM | 49.63 | 48.475 | 50.48 | 0.00 | 34.280 | 15.350 | 14.195 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.3 | 10.0 | -100.0 | G35T2 | 1 2 | 5 5
Za/20-1 | SGBM22 | Oct 20 2015 2:20PM | Oct 20 2015 5:20PM | Oct 20 2015 6:59PM | Oct 20 2015 8:40PM | 49.786 | 48.475 | 50.52 | 0.00 | 29.416 | 20.370 | 19.059 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
ABa/21-1 | SGBM22 | Oct 20 2015 11:10AM | Oct 20 2015 4:10PM | Oct 20 2015 7:32PM | Oct 20 2015 8:30PM | 49.732 | 48.475 | 50.34 | 0.00 | 28.938 | 20.794 | 19.537 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 12.0 | 39.0 | G45T2 | 1 2 | 6 6
X1/Y4-1 | SGBM09 | Oct 20 2015 10:00AM | Oct 20 2015 3:00PM | Oct 20 2015 4:26PM | Oct 20 2015 7:00PM | 55.69 | 55.075 | 56.30 | 0.00 | 31.803 | 23.887 | 23.272 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
ABa/22-1 | SGBM03 | Oct 19 2015 3:20PM | Oct 19 2015 6:09PM | Oct 20 2015 2:30AM | Oct 20 2015 3:55AM | 49.721 | 48.475 | 50.15 | 0.00 | 28.753 | 20.968 | 19.722 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
ABa/23-1 | SGBM03 | Oct 19 2015 6:00PM | Oct 19 2015 10:00PM | Oct 20 2015 1:00AM | Oct 20 2015 2:00AM | 49.683 | 48.475 | 50.55 | 0.00 | 28.846 | 20.837 | 19.629 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
ABa/24-1 | SGBM22 | Oct 19 2015 6:00PM | Oct 19 2015 10:00PM | Oct 19 2015 11:39PM | Oct 20 2015 1:20AM | 49.772 | 48.475 | 50.22 | 0.00 | 34.924 | 14.848 | 13.551 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.0 | 9.0 | -100.0 | G45T2 | 1 2 | 4.5 4.5
AB/42-1 | SGBM08 | Oct 19 2015 8:50AM | Oct 19 2015 1:33PM | Oct 19 2015 7:25PM | Oct 19 2015 8:45PM | 49.78 | 48.275 | 50.35 | 0.00 | 23.245 | 26.535 | 25.030 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.1 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
AA/31-2 | SGBM03 | Oct 19 2015 11:00AM | Oct 19 2015 3:40PM | Oct 19 2015 4:47PM | Oct 19 2015 5:40PM | 50.065 | 47.825 | 50.89 | 0.00 | 27.287 | 22.778 | 20.538 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.1 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
X1/Y5-1 | SGBM09 | Oct 17 2015 9:00AM | Oct 17 2015 1:25PM | Oct 17 2015 3:41PM | Oct 17 2015 6:45PM | 55.677 | 55.075 | 56.39 | 0.00 | 31.988 | 23.689 | 23.087 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 16.0 | 56.8 | G45T2 | 1 2 3 | 7 6 3
Aba/41-1 | SGBM08 | Oct 16 2015 11:30AM | Oct 16 2015 3:00PM | Oct 16 2015 6:20PM | Oct 16 2015 9:30PM | 49.813 | 49.075 | 50.68 | 0.00 | 27.984 | 21.829 | 21.091 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 13.0 | -100.0 | G45T2 | 1 2 3 | 3 7 3
X2/Y5-1 | SGBM09 | Oct 16 2015 2:00PM | Oct 16 2015 5:40PM | Oct 16 2015 8:12PM | Oct 16 2015 9:00PM | 55.633 | 55.075 | 56.14 | 0.00 | 32.942 | 22.691 | 22.133 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
X2/Y3-1 | SGBM09 | Oct 16 2015 9:00AM | Oct 16 2015 1:03PM | Oct 16 2015 3:56PM | Oct 16 2015 7:00PM | 55.851 | 55.075 | 56.61 | 0.00 | 31.911 | 23.940 | 23.164 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
AA/45-1 | SGBM08 | Oct 15 2015 2:50PM | Oct 15 2015 6:40PM | Oct 16 2015 12:36AM | Oct 16 2015 2:00AM | 49.643 | 49.075 | 50.73 | 0.00 | 28.031 | 21.612 | 21.044 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
V/20-1 | SGBM03 | Oct 15 2015 8:10AM | Oct 15 2015 3:20PM | Oct 15 2015 7:48PM | Oct 15 2015 10:50PM | 49.831 | 48.475 | 50.24 | 0.00 | 26.244 | 23.587 | 22.231 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.8 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 10 2
X2/Y2-1 | SGBM09 | Oct 15 2015 9:00AM | Oct 15 2015 1:20PM | Oct 15 2015 5:11PM | Oct 15 2015 7:00PM | 55.831 | 55.075 | 56.62 | 0.00 | 31.021 | 24.810 | 24.054 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 14.0 | -10.6 | G45T2 | 1 2 | 7 7
X1/Y7-1 | SGBM09 | Oct 13 2015 12:00PM | Oct 13 2015 4:20PM | Oct 13 2015 10:10PM | Oct 14 2015 1:30AM | 55.709 | 55.075 | 56.48 | 0.00 | 28.882 | 26.827 | 26.193 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.6 | 13.0 | -11.6 | G45T2 | 1 2 | 7 6
AA/44-1 | SGBM08 | Oct 13 2015 1:00PM | Oct 13 2015 5:47PM | Oct 13 2015 10:44PM | Oct 14 2015 12:20AM | 49.712 | 49.075 | 50.82 | 0.00 | 29.019 | 20.693 | 20.056 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.9 | 10.0 | -100.0 | G35T2 | 1 2 | 7 3
AA/40-1 | SGBM19 | Oct 13 2015 2:20PM | Oct 13 2015 6:24PM | Oct 13 2015 9:58PM | Oct 13 2015 11:55PM | 49.83 | 49.075 | 50.67 | 0.00 | 25.065 | 24.765 | 24.010 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.6 | 16.0 | -100.0 | G35T2 | 1 2 | 10 6
AA/26-1 | SGBM22 | Oct 13 2015 8:00AM | Oct 13 2015 11:40AM | Oct 13 2015 8:08PM | Oct 13 2015 9:25PM | 49.789 | 49.075 | 50.71 | 0.00 | 34.608 | 15.181 | 14.467 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.4 | 9.0 | -100.0 | G35T2 | 1 2 | 7 2
AA/43-1 | SGBM08 | Oct 13 2015 1:00PM | Oct 13 2015 3:40PM | Oct 13 2015 7:34PM | Oct 13 2015 8:50PM | 49.646 | 49.075 | 50.53 | 0.00 | 30.025 | 19.621 | 19.050 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 10.0 | -100.0 | G35T2 | 1 2 | 7 3
AA/31-1 | SGBM22 | Oct 13 2015 10:10AM | Oct 13 2015 2:00PM | Oct 13 2015 5:16PM | Oct 13 2015 7:40PM | 49.812 | 47.825 | 50.85 | 0.00 | 27.849 | 21.963 | 19.976 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.8 | 13.0 | -100.0 | G35T2 | 1 2 | 6 7
AA/24-1 | SGBM22 | Oct 12 2015 8:00AM | Oct 12 2015 6:00PM | Oct 12 2015 8:12PM | Oct 12 2015 9:50PM | 49.686 | 49.075 | 50.53 | 0.00 | 29.233 | 20.453 | 19.842 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.8 | 13.0 | -100.0 | G35T2 | 1 2 | 6 7
X1/Y6-1 | SGBM09 | Oct 12 2015 8:40AM | Oct 12 2015 2:23PM | Oct 12 2015 7:38PM | Oct 12 2015 9:20PM | 55.731 | 55.075 | 56.47 | 0.00 | 31.965 | 23.766 | 23.110 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.2 | 13.0 | -100.0 | G45T2 | 1 2 | 6 7
AA/22-1 | SGBM20 | Oct 9 2015 2:00PM | Oct 10 2015 6:30PM | Oct 10 2015 10:40PM | Oct 10 2015 11:45PM | 49.816 | 49.075 | 50.63 | 0.00 | 29.635 | 20.181 | 19.440 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 10.0 | -8.6 | G35T2 | 1 | 10
AA/23-1 | SGBM19 | Oct 10 2015 8:00AM | Oct 10 2015 1:55PM | Oct 10 2015 6:26PM | Oct 10 2015 7:50PM | 49.898 | 49.075 | 50.53 | 0.00 | 29.730 | 20.168 | 19.345 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 10.0 | -100.0 | G35T2 | 1 2 | 7 3
X6a/Y4-8 | SGBM09 | Oct 10 2015 9:00AM | Oct 10 2015 3:05PM | Oct 10 2015 5:10PM | Oct 10 2015 7:25PM | 55.824 | 51.075 | 56.60 | 0.00 | 25.799 | 30.025 | 25.276 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 11.2 | 14.0 | -11.2 | G45T2 | 1 2 | 7 7
AA/27-1 | SGBM20 | Oct 9 2015 7:15PM | Oct 10 2015 2:30PM | Oct 10 2015 5:45PM | Oct 10 2015 7:15PM | 49.815 | 49.075 | 50.63 | 0.00 | 34.134 | 15.681 | 14.941 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.6 | 10.0 | 51.5 | G35T2 | 1 2 | 7 3
AA/29-1 | SGBM19 | Oct 9 2015 9:00PM | Oct 10 2015 10:20AM | Oct 10 2015 12:39AM | Oct 10 2015 1:47AM | 49.957 | 49.075 | 50.93 | 0.00 | 34.526 | 15.431 | 14.549 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.4 | 10.0 | -100.0 | G35T2 | 1 | 10
AA/28-1 | SGBM19 | Oct 9 2015 8:00AM | Oct 9 2015 11:00AM | Oct 10 2015 12:29AM | Oct 10 2015 1:32AM | 50.036 | 49.075 | 50.95 | 0.00 | 34.449 | 15.587 | 14.626 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 6.5 | 10.0 | -100.0 | G35T2 | 1 | 10
Sa/40-1 | SGBM21 | Oct 9 2015 2:00PM | Oct 9 2015 4:31PM | Oct 9 2015 5:42PM | Oct 9 2015 7:15PM | 52.45 | 50.775 | 53.30 | 0.00 | 32.775 | 19.675 | 18.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 10.0 | -100.0 | G45T2 | 1 2 | 7 3
R/40-1 | SGBM21 | Oct 7 2015 6:00PM | Oct 7 2015 8:35PM | Oct 8 2015 11:45AM | Oct 8 2015 12:45PM | 52.436 | 50.775 | 53.44 | 0.00 | 33.775 | 18.661 | 17.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.5 | 10.0 | -7.5 | G45T2 | 1 | 10
X2/Y4-1 | SGBM09 | Oct 7 2015 12:00PM | Oct 7 2015 4:40PM | Oct 7 2015 9:03PM | Oct 8 2015 12:15AM | 55.701 | 55.075 | 56.48 | 0.00 | 31.776 | 23.925 | 23.299 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 10.3 | 14.0 | -10.3 | G35T2 | 1 2 | 7 7
Q/40-1 | SGBM21 | Oct 7 2015 12:00PM | Oct 7 2015 3:29PM | Oct 7 2015 8:12PM | Oct 7 2015 9:50PM | 52.253 | 50.775 | 53.15 | 0.00 | 29.775 | 22.478 | 21.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 14.0 | -9.3 | G45T2 | 1 2 | 7 7
T/22-1 | SGBM22 | Oct 7 2015 8:00AM | Oct 7 2015 1:30PM | Oct 7 2015 6:50PM | Oct 7 2015 8:00PM | 49.837 | 49.075 | 50.55 | 0.00 | 29.954 | 19.883 | 19.121 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.4 | 10.0 | -100.0 | G45T2 | 1 2 | 3 7
AA/39-1 | SGBM21 | Oct 7 2015 8:00AM | Oct 7 2015 11:00AM | Oct 7 2015 4:35PM | Oct 7 2015 5:30PM | 49.635 | 49.075 | 50.55 | 0.00 | 28.947 | 20.688 | 20.128 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.9 | 12.0 | -100.0 | G35T2 | 1 2 | 5 7
AA/38-1 | SGBM21 | Oct 6 2015 8:45PM | Oct 7 2015 10:41AM | Oct 7 2015 3:32PM | Oct 7 2015 5:00PM | 49.653 | 49.075 | 50.59 | 0.00 | 29.491 | 20.162 | 19.584 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 11.0 | -100.0 | G35T2 | 1 | 11
S/40-1 | SGBM21 | Oct 7 2015 8:00AM | Oct 7 2015 10:52AM | Oct 7 2015 12:20PM | Oct 7 2015 2:00PM | 52.498 | 50.775 | 53.26 | 0.00 | 32.775 | 19.723 | 18.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.0 | 10.0 | -100.0 | G45T2 | 1 | 10
AA/37-1 | SGBM21 | Oct 6 2015 8:45PM | Oct 7 2015 8:14AM | Oct 7 2015 11:50AM | Oct 7 2015 1:45PM | 49.619 | 49.075 | 50.55 | 0.00 | 29.346 | 20.273 | 19.729 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 14.0 | -100.0 | G35T2 | 1 2 | 7 7
AA/36-1 | SGBM21 | Oct 6 2015 8:45PM | Oct 7 2015 8:17AM | Oct 7 2015 11:01AM | Oct 7 2015 12:30PM | 49.625 | 49.075 | 50.54 | 0.00 | 29.540 | 20.085 | 19.535 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 12.0 | -100.0 | G35T2 | 1 2 | 6 6
P/40-1 | SGBM08 | Oct 5 2015 7:00PM | Oct 6 2015 10:32AM | Oct 6 2015 2:32PM | Oct 6 2015 3:40PM | 52.08 | 50.775 | 52.80 | 0.00 | 29.775 | 22.305 | 21.000 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.3 | 12.0 | -100.0 | G45T2 | 1 2 | 8 4
X2/Y6-1 | SGBM09 | Oct 3 2015 6:00PM | Oct 3 2015 9:00PM | Oct 3 2015 11:30PM | Oct 4 2015 1:15AM | 55.618 | 55.075 | 56.42 | 0.00 | 47.418 | 21.700 | 7.657 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | 8.297 | 3.4 | 19.0 | -100.0 | G45T2 | 1 2 3 | 5 9 5
Y/27a-5 | SGBM22 | Oct 1 2015 8:20AM | Oct 2 2015 11:00AM | Oct 2 2015 7:05PM | Oct 2 2015 8:20PM | 49.915 | 46.525 | 50.58 | 0.00 | 27.075 | 22.840 | 19.450 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 11.0 | -100.0 | G45T2 | 1 | 11
L/33-1 | SGBM20 | Sep 30 2015 5:00PM | Oct 1 2015 1:15PM | Oct 1 2015 2:38PM | Oct 1 2015 4:10PM | 52.1 | 50.225 | 43.87 | 0.00 | 29.774 | 22.326 | 20.451 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 9.0 | 16.0 | 7.0 | G45T2 | 1 2 | 8 8
Y/27a-3 | SGBM22 | Sep 30 2015 10:10AM | Sep 30 2015 3:40PM | Sep 30 2015 11:07PM | Oct 1 2015 12:30AM | 49.926 | 46.525 | 50.66 | 0.00 | 27.161 | 22.765 | 19.364 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 12.0 | -100.0 | G45T2 | 1 2 | 9 3
Y/27a-7 | SGBM22 | Sep 29 2015 8:20AM | Sep 30 2015 9:00AM | Sep 30 2015 1:21PM | Sep 30 2015 2:30PM | 49.814 | 46.525 | 50.56 | 0.00 | 26.760 | 23.054 | 19.765 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 10.0 | -100.0 | G45T2 | 1 2 | 4 6
Y/26a-2 | SGBM22 | Sep 28 2015 4:00PM | Sep 29 2015 3:00PM | Sep 29 2015 11:27PM | Sep 30 2015 12:30AM | 49.794 | 46.525 | 50.75 | 0.00 | 26.748 | 23.046 | 19.777 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 12.0 | -100.0 | G45T2 | 1 2 | 9 3
Y/26a-6 | SGBM22 | Sep 28 2015 4:30PM | Sep 29 2015 9:10AM | Sep 29 2015 12:59PM | Sep 29 2015 2:15PM | 49.791 | 46.525 | 50.72 | 0.00 | 27.116 | 22.675 | 19.409 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/27a-6 | SGBM22 | Sep 25 2015 1:00PM | Sep 28 2015 1:30PM | Sep 28 2015 7:16PM | Sep 28 2015 8:40PM | 49.812 | 46.525 | 50.74 | 0.00 | 27.135 | 22.677 | 19.390 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 12.0 | -100.0 | G45T2 | 1 2 | 10 2
Y/27a-1 | SGBM22 | Sep 25 2015 11:00AM | Sep 26 2015 9:00AM | Sep 26 2015 2:05PM | Sep 26 2015 3:30PM | 49.972 | 46.525 | 50.85 | 0.00 | 27.349 | 22.623 | 19.176 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 11.0 | -100.0 | G45T2 | 1 | 11
Y/26a-5 | SGBM22 | Sep 24 2015 12:45PM | Sep 25 2015 9:00AM | Sep 25 2015 5:40PM | Sep 25 2015 7:10PM | 49.819 | 46.525 | 50.64 | 0.00 | 27.241 | 22.578 | 19.284 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/26a-4 | SGBM22 | Sep 23 2015 11:00AM | Sep 23 2015 3:56PM | Sep 23 2015 7:47PM | Sep 23 2015 9:00PM | 49.931 | 46.525 | 50.89 | 0.00 | 27.089 | 22.842 | 19.436 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 10.0 | -100.0 | G45T2 | 1 | 10
Y/26a-1 | SGBM22 | Sep 22 2015 4:40PM | Sep 22 2015 7:45PM | Sep 23 2015 1:53AM | Sep 23 2015 3:40AM | 49.896 | 46.525 | 50.73 | 0.00 | 26.834 | 23.062 | 19.691 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 14.5 | -100.0 | G45T2 | 1 2 | 11.5 3
Y/27a-2 | SGBM22 | Sep 21 2015 3:00PM | Sep 22 2015 8:18AM | Sep 22 2015 5:52PM | Sep 22 2015 7:00PM | 49.897 | 46.525 | 50.65 | 0.00 | 27.147 | 22.750 | 19.378 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 17.0 | -100.0 | G45T2 | 1 | 17
K/33-1 | SGBM20 | Sep 21 2015 6:00PM | Sep 22 2015 11:18AM | Sep 22 2015 12:15PM | Sep 22 2015 2:05PM | 51.957 | 50.225 | 43.72 34.72 | 0.00 0.00 | 30.724 | 21.233 | 19.501 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 15.0 | -100.0 | G45T2 | c480009015 c480009018 c480009019 | 2 11 2
Y/26a-8 | SGBM22 | Sep 21 2015 8:45AM | Sep 21 2015 12:35PM | Sep 21 2015 6:00PM | Sep 21 2015 8:00PM | 49.745 | 46.525 | 50.63 | 0.00 | 27.135 | 22.610 | 19.390 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 15.0 | -100.0 | G45T2 | 1 2 | 4 11
Y/26a-3 | SGBM16 | Sep 18 2015 8:00AM | Sep 18 2015 11:40AM | Sep 18 2015 8:00PM | Sep 18 2015 9:50PM | 49.867 | 46.525 | 50.58 | 0.00 | 26.783 | 23.084 | 19.742 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.7 | 12.0 | -100.0 | G45T2 | 1 2 | 11 1
Y/27a-4 | SGBM16 | Sep 18 2015 8:00AM | Sep 18 2015 11:35AM | Sep 18 2015 7:17PM | Sep 18 2015 8:25PM | 49.871 | 46.525 | 50.65 | 0.00 | 27.247 | 22.624 | 19.278 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 12.0 | -100.0 | G45T2 | 1 | 12
Y/27a-8 | SGBM16 | Sep 17 2015 8:00AM | Sep 17 2015 11:38AM | Sep 17 2015 9:13PM | Sep 17 2015 10:55PM | 49.801 | 46.525 | 50.62 | 0.00 | 27.124 | 22.677 | 19.401 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.6 | 12.0 | -100.0 | G45T2 | 1 | 12
Y/26a-7 | SGBM22 | Sep 17 2015 8:00AM | Sep 17 2015 12:00PM | Sep 17 2015 8:55PM | Sep 17 2015 9:50PM | 49.798 | 46.525 | 50.64 | 0.00 | 27.244 | 22.554 | 19.281 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 8.5 | 10.0 | -100.0 | G45T2 | 1 | 10
V/27-1 | SGBM08 | Sep 11 2015 4:00PM | Sep 14 2015 4:15PM | Sep 14 2015 6:45PM | Sep 14 2015 7:45PM | 49.817 | 48.775 | 42.55 39.55 | 0.00 0.00 | 31.246 | 18.571 | 17.529 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.7 | 9.0 | -7.7 | G35T2 | 1 | 9
W/27-1 | SGBM16 | Aug 11 2015 8:30AM | Aug 13 2015 1:00PM | Aug 13 2015 4:30PM | Aug 13 2015 5:50PM | 49.655 | 49.075 | 41.32 | 0.00 | 32.385 | 17.270 | 16.690 |  | 0.0 | 0.0 | 0.0 | 11T16 | 208.428 | 208.428 | T10-225 | 97.7432 | 97.7432 | - | 12 | - | 7.4 | 8.0 | -7.4 | G35T2 | 1 | 8
K/18-1 | [5 empty] | 0 | 51.375 |  |  | 0.000 | 0.000 | 51.375 |  | 0.0 | 0.0 | 0.0 | 11T16 | - | - | T10-225 | - | - | - |  | - | 22.7 | 0.0 | 0.0 | G35T2
Total | [10 empty] | 15819.950 | 13668.162 | 0.0 | 0.0 | 0.0 | 0.0 |  | 103797.1 | 103797.1 |  | 48676.1 | 48382.9 | 293.2 |  |  | 6039.2 | 7862.0

## 900
Summary List for 1891651800-Parcel F
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [8 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | T16 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
Ka/16-2 | SGBM20 | Apr 4 2016 8:30AM | Apr 4 2016 12:30PM | Apr 4 2016 2:55PM | Apr 4 2016 4:30PM | 55.737 | 49.525 | 56.57 | 0.00 | 20.074 | 35.663 | 29.451 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 22.0 | 28.1 | G35T2 | pj7567 pj7568 pj7569 | 8 7 7
K/10-3 | SGBM20 | Apr 2 2016 9:00AM | Apr 2 2016 4:45PM | Apr 2 2016 6:20PM | Apr 2 2016 7:40PM | 55.892 | 50.075 | 56.73 | 0.00 | 47.730 | 35.162 | 2.345 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 1.5 | 23.0 | -100.0 | G35T2 | pj7555 pj7557 pj7558 | 7 8 8
J/13-9 | SGBM31 | Apr 2 2016 10:00AM | Apr 2 2016 2:30PM | Apr 2 2016 4:10PM | Apr 2 2016 5:20PM | 55.63 | 54.675 | 56.47 | 0.00 | 25.474 | 30.156 | 29.201 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | pj7545 pj7547 pj7550 | 8 7 7
L/17-1 | SGBM23 | Apr 2 2016 8:00AM | Apr 2 2016 1:15PM | Apr 2 2016 2:00PM | Apr 2 2016 2:45PM | 55.63 | 49.525 | 56.50 | 0.00 | 19.804 | 35.826 | 29.721 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 22.0 | -100.0 | G35T2 | pj7534 pj7536 pj7538 | 8 7 7
K/16-1 | SGBM19 | Mar 31 2016 1:00PM | Apr 1 2016 7:30PM | Apr 1 2016 10:45PM | Apr 1 2016 11:50PM | 55.773 | 49.525 | 56.57 | 0.00 | 19.866 | 35.907 | 29.659 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 26.0 | -100.0 | G35T2 | pj7529 pj7530 pj7532 | 10 8 8
K/10-2 | SGBM20 | Apr 1 2016 4:30PM | Apr 1 2016 8:10PM | Apr 1 2016 8:45PM | Apr 1 2016 10:45PM | 55.83 | 50.075 | 56.01 | 0.00 | 20.910 | 34.920 | 29.165 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 26.0 | -100.0 | G35T2 | pj7523 pj7524 pj7528 | 9 8 9
K/17-1 | SGBM31 | Apr 1 2016 9:00AM | Apr 1 2016 4:35PM | Apr 1 2016 9:25PM | Apr 1 2016 10:25PM | 55.665 | 49.525 | 56.46 | 0.00 | 20.260 | 35.405 | 29.265 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 21.0 | -100.0 | G35T2 | pj7525 pj7527 | 10 11
Ka/16-1 | SGBM23 | Mar 31 2016 2:00PM | Apr 1 2016 4:00PM | Apr 1 2016 7:05PM | Apr 1 2016 8:25PM | 55.69 | 49.525 | 56.51 | 0.00 | 20.515 | 35.175 | 29.010 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 21.0 | -100.0 | G35T2 | pj7520 pj7521 | 11 10
J/13-10 | SGBM19 | Apr 1 2016 8:00AM | Apr 1 2016 12:00PM | Apr 1 2016 4:00PM | Apr 1 2016 4:50PM | 55.72 | 54.675 | 55.56 | 0.00 | 24.558 | 31.162 | 30.117 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 22.0 | -19.2 | G35T2 | pj7504 pj7505 pj7507 | 8 7 7
L/17-2 | SGBM23 | Mar 29 2016 8:30AM | Mar 31 2016 1:30PM | Mar 31 2016 8:00PM | Mar 31 2016 8:45PM | 55.68 | 49.525 | 56.40 | 0.00 | 18.800 | 36.880 | 30.725 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.5 | 22.0 | -100.0 | G35T2 | pj7491 pj7492 pj7493 | 8 7 7
J/13-4 | SGBM19 | Mar 30 2016 10:40AM | Mar 31 2016 11:15AM | Mar 31 2016 2:10PM | Mar 31 2016 3:50PM | 55.73 | 54.675 | 56.63 | 0.00 | 25.130 | 30.600 | 29.545 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.8 | 23.0 | -100.0 | G35T2 | pj7472 pj7474 pj7476 | 8 8 7
K/10-1 | SGBM20 | Mar 19 2016 1:15PM | Mar 31 2016 10:00AM | Mar 31 2016 1:50PM | Mar 31 2016 3:40PM | 55.9 | 50.075 | 56.66 | 0.00 | 20.963 | 34.937 | 29.112 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 26.0 | -100.0 | G35T2 | pj7471 pj7473 pj7475 | 10 8 8
J/13-7 | SGBM19 | Mar 30 2016 11:20AM | Mar 30 2016 8:00PM | Mar 30 2016 9:30PM | Mar 30 2016 10:40PM | 55.62 | 54.675 | 56.63 | 0.00 | 25.630 | 29.990 | 29.045 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G35T2 | pj7465 pj7466 pj7467 | 8 8 7
X10a/Yb-1 | SGBM20 | Mar 30 2016 8:30AM | Mar 30 2016 2:30PM | Mar 30 2016 7:20PM | Mar 30 2016 8:30PM | 55.67 | 55.075 | 56.30 | 0.00 | 27.000 | 84.970 | 28.075 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.9 | 16.0 | -100.0 | G35T2 | pj7454 pj7455 | 8 8
N/5-1 | SGBM20 | Mar 29 2016 11:20AM | Mar 29 2016 7:30PM | Mar 29 2016 10:00PM | Mar 29 2016 10:45PM | 55.755 | 55.075 | 56.47 | 0.00 | 24.571 | 31.184 | 30.504 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 23.0 | -100.0 | G35T2 | pj7416 pj7422 pj7423 | 8 7 8
X11/Yb-1 | SGBM20 | Mar 28 2016 1:00PM | Mar 29 2016 9:55AM | Mar 29 2016 5:15PM | Mar 29 2016 6:45PM | 55.665 | 55.075 | 56.76 | 0.00 | 27.363 | 28.302 | 27.712 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.6 | 26.0 | -100.0 | G35T2 | pj7384 pj7387 pj7390 | 10 8 8
J/13-8 | SGBM23 | Mar 26 2016 6:00PM | Mar 29 2016 10:30AM | Mar 29 2016 4:50PM | Mar 29 2016 6:05PM | 55.456 | 54.675 | 56.20 | 0.00 | 24.997 | 30.459 | 29.678 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 23.0 | -100.0 | G35T2 | pj7381 pj7382 pj7385 | 8 8 7
N/Yb-1 | SGBM20 | Mar 26 2016 9:00AM | Mar 28 2016 4:20PM | Mar 28 2016 8:35PM | Mar 28 2016 10:05PM | 55.545 | 55.075 | 56.37 | 0.00 | 26.970 | 28.575 | 28.105 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 26.0 | -100.0 | G35T2 | pj7357 pj7358 pj7361 | 10 8 8
J/13-3 | SGBM31 | Mar 26 2016 5:10PM | Mar 28 2016 7:15PM | Mar 28 2016 8:00PM | Mar 28 2016 9:35PM | 55780 | 54.675 | 56.37 | 0.00 | 25.570 | 55754.400 | 29.105 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G35T2 | pj7354 pj7355 pj7360 | 8 7 7
R/14-1 | SGBM31 | Mar 26 2016 3:40PM | Mar 28 2016 3:30PM | Mar 28 2016 6:50PM | Mar 28 2016 8:05PM | 55.774 | 54.475 | 56.73 | 0.00 | 25.226 | 30.548 | 29.249 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 24.0 | -100.0 | G35T2 | pj7350 pj7351 pj7352 | 8 8 8
X11/Ya-1 | SGBM20 | Mar 24 2016 11:15AM | Mar 26 2016 2:00PM | Mar 26 2016 7:00PM | Mar 26 2016 8:50PM | 55.555 | 55.075 | 56.60 | 0.00 | 27.405 | 28.150 | 27.670 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.6 | 28.0 | -100.0 | G35T2 | pj7285 pj7289 pj7291 | 7 10 11
N/Ya-1 | SGBM20 | Mar 25 2016 11:00AM | Mar 25 2016 4:30PM | Mar 26 2016 12:00AM | Mar 26 2016 1:25AM | 55.555 | 55.075 | 56.66 | 0.00 | 28.860 | 26.695 | 26.215 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 25.0 | -100.0 | G35T2 | pj7236 pj7240 pj7245 | 10 8 7
J/13-5 | SGBM23 | Mar 24 2016 4:30PM | Mar 25 2016 7:00PM | Mar 25 2016 10:20PM | Mar 25 2016 11:15PM | 55.65 | 54.675 | 0.00 | 0.00 | -31.200 | 86.850 | 85.875 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 54.6 | 23.0 | -100.0 | G35T2 | pj7225 pj7227 pj7230 | 8 8 7
J/13-2 | SGBM23 | Mar 24 2016 5:25PM | Mar 25 2016 3:15PM | Mar 25 2016 8:15PM | Mar 25 2016 9:30PM | 55.66 | 54.675 | 56.55 | 0.00 | 24.951 | 87.260 | 29.724 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 23.0 | -18.9 | G35T2 | pj7211 pj7213 pj7217 | 8 8 7
G/16-1 | SGBM23 | Mar 23 2016 5:40PM | Mar 24 2016 5:40PM | Mar 25 2016 1:00AM | Mar 25 2016 2:40AM | 55.49 | 51.075 | 56.29 | 0.00 | 25.490 | 30.000 | 25.585 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.3 | 25.0 | -100.0 | G35T2 | pj7178 pj7179 pj7180 pj7181 | 8 8 7 2
G/12-2 | SGBM20 | Mar 23 2016 5:00PM | Mar 24 2016 2:30PM | Mar 24 2016 11:10PM | Mar 25 2016 12:31AM | 55.481 | 49.875 | 56.23 | 0.00 | 20.734 | 34.747 | 29.141 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G35T2 | pj7175 pj7176 pj7177 | 8 8 7
X10a/Ya-1 | SGBM20 | Mar 24 2016 10:30AM | Mar 24 2016 6:45PM | Mar 24 2016 7:40PM | Mar 24 2016 9:25PM | 55.481 | 55.075 | 56.64 | 0.00 | 27.540 | 27.941 | 27.535 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.5 | 24.0 | -100.0 | G35T2 | pj7157 pj7162 pj7164 | 8 8 8
J/13-6 | SGBM20 | Mar 23 2016 10:50AM | Mar 23 2016 8:10PM | Mar 24 2016 1:00AM | Mar 24 2016 2:10AM | 55.746 | 54.675 | 56.47 | 0.00 | 25.375 | 31.100 | 29.300 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | pj7133 pj7134 pj7135 | 8 8 7
J/13-1 | SGBM20 | Mar 23 2016 11:45AM | Mar 23 2016 5:00PM | Mar 23 2016 11:10PM | Mar 24 2016 12:40AM | 55.72 | 54.675 | 56.45 | 0.00 | 25.451 | 30.269 | 29.224 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | 23.7 | G35T2 | pj7126 pj7128 pj7131 | 8 8 7
G/9-2 | SGBM19 | Mar 22 2016 4:00PM | Mar 22 2016 9:10PM | Mar 23 2016 4:30AM | Mar 23 2016 6:10AM | 55.918 | 53.275 | 55.66 | 0.00 | 23.160 | 32.758 | 30.115 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 24.0 | -100.0 | G35T2 | pj7095 pj7096 pj7097 | 8 8 8
G/11-1 | SGBM20 | Mar 22 2016 4:40PM | Mar 22 2016 9:30PM | Mar 23 2016 3:35AM | Mar 23 2016 4:50AM | 55.83 | 49.875 | 56.36 | 0.00 | 20.761 | 35.069 | 29.114 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G35T2 | Pending pj7093 pj7094 | 8 8 7
G/12-1 | SGBM23 | Mar 22 2016 8:50AM | Mar 22 2016 6:00PM | Mar 23 2016 2:30AM | Mar 23 2016 3:40AM | 55.435 | 49.875 | 56.08 | 0.00 | 20.682 | 34.753 | 29.193 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 25.0 | -100.0 | G35T2 | pj7088 pj7089 pj7090 | 8 8 9
G/9-1 | SGBM31 | Mar 19 2016 2:15PM | Mar 21 2016 5:00PM | Mar 22 2016 2:40AM | Mar 22 2016 4:14AM | 55.9 | 53.275 | 56.59 | 0.00 | 24.192 | 31.708 | 29.083 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G35T2 | pj7049 pj7050 pj7051 | 8 7 7
G/11-2 | SGBM23 | Mar 19 2016 1:00PM | Mar 21 2016 11:30AM | Mar 21 2016 10:30PM | Mar 22 2016 12:06AM | 55.845 | 49.875 | 56.74 | 0.00 | 20.536 | 35.309 | 29.339 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 21.0 | -100.0 | G35T2 | pj7032 pj7037 | 10 11
P/13a-2 | SGBM20 | Mar 21 2016 10:00AM | Mar 21 2016 5:45PM | Mar 21 2016 9:05PM | Mar 21 2016 11:06PM | 56.091 | 53.875 | 56.61 | 0.00 | 25.409 | 87.291 | 28.466 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | 27.0 | G35T2 | pj7023 pj7026 pj7030 | 8 8 7
Pa/7-1 | SGBM23 | Mar 19 2016 9:10AM | Mar 19 2016 3:05PM | Mar 19 2016 6:00PM | Mar 19 2016 7:20PM | 55.286 | 55.075 | 56.92 | 0.00 | 26.019 | 86.186 | 29.056 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -18.5 | G35T2 | pj6948 pj6950 pj6952 | 8 7 7
P/13a-1 | SGBM20 | Mar 18 2016 3:55PM | Mar 19 2016 10:00AM | Mar 19 2016 1:45PM | Mar 19 2016 3:35PM | 55.9 | 53.875 | 56.78 | 0.00 | 23.777 | 32.123 | 30.098 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.1 | 22.0 | -100.0 | G35T2 | pj6932 pj6933 pj6935 | 8 7 7
N/7-1 | SGBM19 | Mar 17 2016 3:00PM | Mar 18 2016 5:30PM | Mar 18 2016 6:25PM | Mar 18 2016 7:52PM | 55.975 | 55.075 | 57.13 | 0.00 | 25.625 | 30.350 | 29.450 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 22.0 | -100.0 | G35T2 | pj6913 pj6915 pj6918 | 8 8 6
P/5-1 | SGBM20 | Mar 16 2016 6:30PM | Mar 17 2016 7:30PM | Mar 17 2016 9:10PM | Mar 17 2016 10:35PM | 55.73 | 55.075 | 56.53 | 0.00 | 24.833 | 30.897 | 30.242 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 22.0 | -100.0 | G35T2 | pj6885 pj6887 | 11 11
N/13a-1 | SGBM23 | Mar 17 2016 11:30AM | Mar 17 2016 5:00PM | Mar 17 2016 8:00PM | Mar 17 2016 9:13PM | 55.77 | 55.075 | 0.00 | 0.00 | -31.000 | 86.770 | 86.075 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 54.8 | 22.0 | -100.0 | G35T2 | pj6877 pj6881 | 11 11
G/8-1 | SGBM19 | Mar 17 2016 11:20AM | Mar 17 2016 3:50PM | Mar 17 2016 5:35PM | Mar 17 2016 7:40PM | 55.81 | 53.275 | 56.71 | 0.00 | 24.210 | 31.600 | 29.065 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G35T2 | c480018582 c480018585 c480018588 | 3 10 10
Pa/8-1 | SGBM20 | Mar 15 2016 4:45PM | Mar 16 2016 5:45PM | Mar 16 2016 10:35PM | Mar 16 2016 11:57PM | 55.779 | 55.075 | 56.55 | 0.00 | 25.553 | 30.226 | 29.522 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.8 | 22.0 | -100.0 | G35T2 | pj6808 pj6810 pj6811 | 8 7 7
G/8-2 | SGBM19 | Mar 16 2016 9:00AM | Mar 16 2016 7:15PM | Mar 16 2016 10:30PM | Mar 16 2016 11:55PM | 55.895 | 53.275 | 56.79 | 0.00 | 24.188 | 31.707 | 29.087 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G35T2 | pj6807 pj6800 pj6812 | 8 7 7
J/9-17 | SGBM19 | Mar 15 2016 9:30AM | Mar 16 2016 2:15PM | Mar 16 2016 8:30PM | Mar 16 2016 10:16PM | 55.92 | 51.025 | 56.88 | 0.00 | 21.785 | 34.135 | 29.240 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | pj6802 pj6806 pj6804 | 8 7 8
N/13-1 | SGBM23 | Mar 15 2016 5:00PM | Mar 16 2016 11:45AM | Mar 16 2016 5:25PM | Mar 16 2016 7:07PM | 55.898 | 55.075 | 56.76 | 0.00 | 23.261 | 32.637 | 31.814 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 32.0 | -20.2 | G35T2 | pj6784 pj6788 pj6791 pj6794 | 8 8 8 8
J/9-6 | SGBM19 | Mar 15 2016 10:00AM | Mar 15 2016 7:30PM | Mar 15 2016 11:10PM | Mar 16 2016 12:25AM | 55.92 | 51.025 | 56.96 | 0.00 | 23.062 | 32.858 | 27.963 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 22.0 | -100.0 | G35T2 | pj6768 pj6769 pj6770 | 8 7 7
J/9-14 | SGBM22 | Mar 15 2016 9:30AM | Mar 15 2016 4:00PM | Mar 15 2016 9:30PM | Mar 15 2016 11:25PM | 55.9 | 51.025 | 56.84 | 0.00 | 22.843 | 33.057 | 28.182 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 26.0 | 45.0 | G35T2 | pj6762 pj6763 pj6765 pj6767 | 8 7 7 4
G/6-2 | SGBM22 | Mar 15 2016 9:00AM | Mar 15 2016 4:30PM | Mar 15 2016 7:15PM | Mar 15 2016 9:05PM | 55.307 | 53.275 | 56.08 | 0.00 | 24.977 | 30.330 | 28.298 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 24.0 | -100.0 | G35T2 | pj6753 pj6755 pj6758 | 8 7 9
P/6-1 | SGBM20 | Mar 14 2016 6:00PM | Mar 15 2016 12:30PM | Mar 15 2016 6:55PM | Mar 15 2016 7:55PM | 55.986 | 55.075 | 56.80 | 0.00 | 26.604 | 29.382 | 28.471 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | -100.0 | G35T2 | pj6751 pj6752 pj6754 | 7 8 8
N/10-1 | SGBM23 | Mar 14 2016 2:30PM | Mar 15 2016 11:30AM | Mar 15 2016 3:35PM | Mar 15 2016 5:05PM | 55.982 | 51.075 | 56.77 | 0.00 | 22.374 | 33.608 | 28.701 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 21.0 | -100.0 | G35T2 | pj6739 pj6742 | 11 10
G/4-1 | SGBM17 | Mar 15 2016 8:00AM | Mar 15 2016 12:15PM | Mar 15 2016 2:10PM | Mar 15 2016 3:35PM | 55.356 | 53.275 | 56.12 | 0.00 | 47.120 | 31.636 | 6.155 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 3.9 | 24.0 | -100.0 | G35T2 | pj6729 pj6731 pj6735 | 8 8 8
G/5-1 | SGBM17 | Mar 14 2016 9:30AM | Mar 14 2016 6:30PM | Mar 14 2016 11:00PM | Mar 15 2016 12:10AM | 55.4 | 53.275 | 56.27 | 0.00 | 24.071 | 31.329 | 29.204 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | pj6721 pj6722 pj6723 | 8 8 7
J/9-19 | SGBM19 | Mar 14 2016 9:00AM | Mar 14 2016 6:30PM | Mar 14 2016 10:00PM | Mar 14 2016 11:00PM | 55.936 | 51.025 | 56.79 | 0.00 | 22.486 | 33.450 | 28.539 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 22.0 | -100.0 | G35T2 | pj6718 pj6719 pj6720 | 8 7 7
G/6-1 | SGBM17 | Mar 14 2016 11:00AM | Mar 14 2016 4:15PM | Mar 14 2016 8:35PM | Mar 14 2016 9:55PM | 55.45 | 53.275 | 56.14 | 0.00 | 24.539 | 30.911 | 28.736 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 23.0 | -100.0 | G35T2 | pj6712 pj6714 pj6715 | 8 8 7
P/13-1 | SGBM23 | Mar 14 2016 8:00AM | Mar 14 2016 6:30PM | Mar 14 2016 7:30PM | Mar 14 2016 8:45PM | 55.852 | 55.075 | 56.42 | 0.00 | 25.922 | 29.930 | 29.153 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G35T2 | pj6705 pj6706 pj6709 | 8 8 7
J/7-4 | SGBM19 | Mar 14 2016 9:00AM | Mar 14 2016 4:15PM | Mar 14 2016 5:30PM | Mar 14 2016 6:55PM | 55.92 | 54.275 | 56.78 | 0.00 | 25.578 | 30.342 | 28.697 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 22.0 | 20.5 | G35T2 | pj6699 pj6700 pj6701 | 8 7 7
J/9-7 | SGBM19 | Mar 14 2016 8:30AM | Mar 14 2016 1:00PM | Mar 14 2016 3:10PM | Mar 14 2016 4:25PM | 55.805 | 51.025 | 56.78 | 0.00 | 22.783 | 33.022 | 28.242 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 22.0 | -100.0 | G35T2 | pj6692 pj6693 pj6695 | 8 7 7
K/12-2 | SGBM23 | Mar 11 2016 5:00PM | Mar 12 2016 7:30PM | Mar 12 2016 9:50PM | Mar 12 2016 11:10PM | 55.605 | 54.075 | 56.47 | 0.00 | 25.967 | 29.638 | 28.108 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 23.0 | -100.0 | G35T2 | pj6680 pj6683 pj6685 | 8 8 7
J/9-13 | SGBM19 | Mar 12 2016 9:30AM | Mar 12 2016 7:15PM | Mar 12 2016 9:30PM | Mar 12 2016 11:00PM | 55.888 | 51.025 | 56.76 | 0.00 | 22.665 | 33.223 | 28.360 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 22.0 | 21.9 | G35T2 | pj6678 pj6682 pj6686 | 8 7 7
J/7-6 | SGBM17 | Mar 12 2016 9:30AM | Mar 12 2016 5:55PM | Mar 12 2016 8:00PM | Mar 12 2016 9:30PM | 55.931 | 54.275 | 56.90 | 0.00 | 26.201 | 29.730 | 28.074 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 24.0 | -100.0 | G35T2 | pj6668 pj6670 pj6676 | 8 8 8
J/7-3 | SGBM17 | Mar 11 2016 1:00PM | Mar 12 2016 12:30PM | Mar 12 2016 7:05PM | Mar 12 2016 8:35PM | 55.895 | 54.275 | 56.60 | 0.00 | 26.005 | 29.890 | 28.270 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 22.0 | -100.0 | G35T2 | pj6661 pj6664 pj6667 | 8 7 7
K/11-3 | SGBM23 | Mar 11 2016 10:00AM | Mar 12 2016 2:00PM | Mar 12 2016 4:15PM | Mar 12 2016 5:40PM | 55.88 | 50.075 | 56.70 | 0.00 | 21.800 | 34.080 | 28.275 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 22.0 | -100.0 | G35T2 | pj6643 pj6644 pj6649 | 8 7 7
G/5-2 | SGBM17 | Mar 11 2016 3:00PM | Mar 12 2016 12:30PM | Mar 12 2016 2:00PM | Mar 12 2016 3:15PM | 55.31 | 53.275 | 56.37 | 0.00 | 23.966 | 31.344 | 29.309 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | 23.3 | G35T2 | pj6636 pj6637 pj6639 | 8 8 7
Tc/44-1 | SGBM31 | Mar 9 2016 9:30AM | Mar 10 2016 6:15PM | Mar 10 2016 10:55PM | Mar 11 2016 12:37AM | 51.966 | 50.575 | 52.56 | 0.00 | 23.058 | 28.908 | 27.517 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 23.0 | -100.0 | G35T2 | 1 2 3 | 8 8 7
J/7-2 | SGBM19 | Mar 10 2016 1:00PM | Mar 10 2016 6:00PM | Mar 10 2016 8:20PM | Mar 10 2016 10:41PM | 55.922 | 54.275 | 56.70 | 0.00 | 24.999 | 30.923 | 29.276 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | PJ8120 PJ8122 PJ8126 | 8 7 7
J/7-7 | SGBM19 | Mar 10 2016 1:31PM | Mar 10 2016 5:00PM | Mar 10 2016 6:40PM | Mar 10 2016 8:15PM | 55.93 | 54.275 | 57.00 | 0.00 | 24.999 | 30.931 | 29.276 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ7789 PJ8900 PJ8990 | 8 8 7
Tc/42-1 | SGBM15 | Mar 8 2016 10:30AM | Mar 8 2016 4:45PM | Mar 8 2016 10:46PM | Mar 9 2016 12:11AM | 52.092 | 50.575 | 52.64 | 0.00 | 22.440 | 29.652 | 28.135 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
J/7-8 | SGBM19 | Mar 8 2016 1:00PM | Mar 8 2016 5:00PM | Mar 8 2016 6:18PM | Mar 8 2016 8:00PM | 55.965 | 54.275 | 56.78 | 0.00 | 47.785 | 30.980 | 6.490 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 4.1 | 22.0 | -100.0 | G35T2 | pj5579 pj5603 | 11 11
Tc/41-1 | SGBM15 | Mar 7 2016 10:30AM | Mar 7 2016 4:00PM | Mar 7 2016 8:15PM | Mar 7 2016 10:16PM | 52.089 | 50.575 | 52.83 | 0.00 | 22.333 | 29.756 | 28.242 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 24.0 | -100.0 | G35T2 | pj6405 pj6408 Pending | 8 8 8
Tc/43-1 | SGBM15 | Mar 5 2016 9:50AM | Mar 5 2016 3:25PM | Mar 5 2016 9:30PM | Mar 5 2016 11:32PM | 52.02 | 50.575 | 52.76 | 0.00 | 22.758 | 29.262 | 27.817 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.7 | 25.0 | -100.0 | G35T2 | 1 2 3 | 10 8 7
M/12-1 | SGBM20 | Mar 5 2016 12:17PM | Mar 5 2016 4:00PM | Mar 5 2016 4:35PM | Mar 5 2016 5:55PM | 55.77 | 55.075 | 56.60 | 0.00 | 25.903 | 29.867 | 29.172 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 21.0 | -100.0 | G35T2 | C480017882 C480017884 C480017886 | 3 10 8
J/7-1 | SGBM19 | Mar 5 2016 8:10AM | Mar 5 2016 12:21PM | Mar 5 2016 2:30PM | Mar 5 2016 4:27PM | 55.95 | 54.275 | 56.71 | 0.00 | 24.914 | 31.036 | 29.361 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 25.0 | -100.0 | G35T2 | C480017873 C480017874 C480017875 | 10 10 5
J/9-4 | SGBM19 | Mar 4 2016 3:15PM | Mar 4 2016 7:50PM | Mar 4 2016 9:55PM | Mar 4 2016 11:33PM | 55.9 | 51.025 | 56.63 | 0.00 | 21.629 | 34.271 | 29.396 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 23.0 | -100.0 | G35T2 | PJ6347 PJ6349 PJ6350 | 8 8 7
L/11-2 | SGBM20 | Mar 4 2016 1:15PM | Mar 4 2016 6:00PM | Mar 4 2016 9:20PM | Mar 4 2016 11:00PM | 55.75 | 49.875 | 56.43 | 0.00 | 20.226 | 35.524 | 29.649 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 22.0 | -100.0 | G35T2 | PJ6345 PJ6346 PJ6348 | 8 7 7
K/7-3 | SGBM19 | Mar 4 2016 1:12PM | Mar 4 2016 5:00PM | Mar 4 2016 7:20PM | Mar 4 2016 9:11PM | 55.94 | 54.075 | 56.74 | 0.00 | 24.735 | 31.205 | 29.340 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 23.0 | -100.0 | G35T2 | PJ6340 PJ6341 PJ6343 | 8 8 7
J/9-1 | SGBM23 | Mar 3 2016 2:00PM | Mar 3 2016 5:25PM | Mar 3 2016 7:25PM | Mar 3 2016 9:40PM | 55.951 | 51.025 | 56.79 | 0.00 | 21.794 | 34.157 | 29.231 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 26.0 | -100.0 | G35T2 | PJ6311 PJ6313 PJ6316 PJ6318 | 8 7 7 4
M/9-1 | SGBM23 | Mar 3 2016 8:12AM | Mar 3 2016 12:20PM | Mar 3 2016 2:45PM | Mar 3 2016 4:55PM | 55.72 | 55.075 | 56.80 | 0.00 | 25.796 | 29.924 | 29.279 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 24.0 | -18.6 | G35T2 | PJ6289 PJ6291 PJ6293 | 8 8 8
T1/51-1 | SGBM23 | Mar 2 2016 12:00PM | Mar 2 2016 5:05PM | Mar 2 2016 10:40PM | Mar 2 2016 11:52PM | 51.927 | 50.175 | 52.58 | 0.00 | 24.383 | 27.544 | 25.792 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.4 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
K/11-1 | SGBM20 | Mar 2 2016 11:17AM | Mar 2 2016 4:10PM | Mar 2 2016 9:30PM | Mar 2 2016 11:00PM | 55.643 | 50.075 | 56.69 | 0.00 | 20.785 | 34.858 | 29.290 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -18.6 | G35T2 | PJ6268 PJ6269 PJ6272 | 8 7 7
J/9-8 | SGBM19 | Mar 2 2016 1:25PM | Mar 2 2016 5:50PM | Mar 2 2016 6:15PM | Mar 2 2016 8:00PM | 55.92 | 51.025 | 56.81 | 0.00 | 21.814 | 34.106 | 29.211 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | PJ6254 PJ6255 PJ6256 | 8 7 7
M/10-1 | SGBM20 | Mar 2 2016 8:15AM | Mar 2 2016 1:06PM | Mar 2 2016 2:05PM | Mar 2 2016 3:40PM | 55.984 | 51.075 | 56.73 | 0.00 | 21.726 | 34.258 | 29.349 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 22.0 | -100.0 | G35T2 | PJ6242 PJ6243 PJ6245 | 8 7 7
J/9-10 | SGBM19 | Mar 1 2016 2:10PM | Mar 2 2016 9:10AM | Mar 2 2016 10:50AM | Mar 2 2016 12:25PM | 55.93 | 51.025 | 56.76 | 0.00 | 21.965 | 33.965 | 29.060 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G35T2 | PJ6239 PJ6240 PJ6241 | 8 8 7
L/11-1 | SGBM19 | Mar 1 2016 8:12AM | Mar 1 2016 1:13PM | Mar 1 2016 6:40PM | Mar 1 2016 8:00PM | 55.5 | 49.875 | 56.51 | 0.00 | 20.515 | 34.985 | 29.360 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 23.0 | -100.0 | G35T2 | C480017652 C48001753 C520125653 | 10 10 3
K/7-2 | SGBM19 | Mar 1 2016 8:30AM | Mar 1 2016 11:30AM | Mar 1 2016 11:30AM | Mar 1 2016 2:42PM | 55.915 | 54.075 | 56.61 | 0.00 | 23.913 | 32.002 | 30.162 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 25.0 | 30.3 | G35T2 | PJ6200 PJ6203 PJ6204 | 9 8 8
J/9-5 | SGBM19 | Feb 29 2016 3:10PM | Feb 29 2016 7:45PM | Feb 29 2016 11:20PM | Mar 1 2016 12:45AM | 55.91 | 51.025 | 56.82 | 0.00 | 21.819 | 34.091 | 29.206 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ6196 PJ6197 PJ6198 | 8 8 7
T/51-2 | SGBM23 | Feb 27 2016 10:55AM | Feb 29 2016 5:30PM | Feb 29 2016 10:30PM | Mar 1 2016 12:07AM | 52.052 | 50.175 | 52.56 | 0.00 | 18.756 | 33.296 | 31.419 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.0 | 25.0 | -100.0 | G35T2 | 1 2 3 | 8 9 8
J/9-2 | SGBM19 | Feb 29 2016 11:10AM | Feb 29 2016 5:45PM | Feb 29 2016 8:05PM | Feb 29 2016 10:08PM | 55.95 | 51.025 | 56.75 | 0.00 | 21.750 | 34.200 | 29.275 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | PJ6180 PJ6185 PJ6189 | 8 7 7
P/51-3 | SGBM15 | Feb 27 2016 2:00PM | Feb 29 2016 10:47AM | Feb 29 2016 6:30PM | Feb 29 2016 8:32PM | 51.965 | 48.775 | 52.83 | 0.00 | 13.533 | 38.432 | 35.242 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.4 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 10 2
K/12-1 | SGBM20 | Feb 29 2016 11:15AM | Feb 29 2016 4:00PM | Feb 29 2016 5:30PM | Feb 29 2016 7:01PM | 55.7 | 54.075 | 56.51 | 0.00 | 24.810 | 30.890 | 29.265 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ6170 PJ6172 PJ6173 | 8 8 7
T/52-1 | SGBM23 | Feb 27 2016 10:50AM | Feb 27 2016 4:30PM | Feb 27 2016 8:00PM | Feb 27 2016 9:35PM | 51.981 | 49.725 | 52.56 | 0.00 | 18.456 | 33.525 | 31.269 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 26.0 | -19.9 | G45T2 | 1 2 3 | 10 8 8
J/9-11 | SGBM19 | Feb 27 2016 10:00AM | Feb 27 2016 5:00PM | Feb 27 2016 6:20PM | Feb 27 2016 7:40PM | 55.94 | 51.025 | 56.74 | 0.00 | 21.740 | 34.200 | 29.285 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | PJ6131 PJ6133 PJ6136 | 8 7 7
T1/50-1 | SGBM23 | Feb 27 2016 8:30AM | Feb 27 2016 12:55PM | Feb 27 2016 5:45PM | Feb 27 2016 7:36PM | 51.921 | 51.375 | 52.33 | 0.00 | 22.834 | 29.087 | 28.541 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 23.0 | -18.1 | G45T2 | 1 2 3 | 8 8 7
K/7-1 | SGBM19 | Feb 27 2016 8:00AM | Feb 27 2016 1:00PM | Feb 27 2016 2:30PM | Feb 27 2016 4:45PM | 55.93 | 54.075 | 56.67 | 0.00 | 24.872 | 31.058 | 29.203 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ6109 PJ6113 PJ6118 | 8 8 7
L/12-2 | SGBM20 | Feb 27 2016 8:30AM | Feb 27 2016 12:30PM | Feb 27 2016 1:35PM | Feb 27 2016 3:43PM | 55.7 | 53.875 | 56.70 | 0.00 | 24.701 | 30.999 | 29.174 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ6103 6106 PJ6110 | 8 8 7
J/9-3 | SGBM17 | Feb 26 2016 4:00PM | Feb 27 2016 10:00AM | Feb 27 2016 10:20AM | Feb 27 2016 11:50AM | 55.94 | 51.025 | 56.76 | 0.00 | 21.664 | 34.276 | 29.361 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 22.0 | -100.0 | G35T2 | PJ6105 PJ6099 PJ6100 | 8 7 7
T/51-1 | SGBM15 | Feb 25 2016 3:50PM | Feb 26 2016 11:05AM | Feb 27 2016 1:40AM | Feb 27 2016 4:57AM | 51.901 | 50.175 | 52.65 | 0.00 | 19.249 | 32.652 | 30.926 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.7 | 41.0 | -23.8 | G35T2 | 1 2 3 4 5 | 10 8 8 8 7
T/50-1 | SGBM15 | Feb 25 2016 3:25PM | Feb 26 2016 5:30PM | Feb 26 2016 7:45PM | Feb 26 2016 10:10PM | 51.993 | 51.375 | 52.81 | 0.00 | 20.415 | 31.578 | 30.960 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.7 | 24.0 | -19.7 | G45T2 | pj6063 pj6068 pj6073 | 8 8 8
X3a/Yb-1 | SGBM19 | Feb 26 2016 8:12AM | Feb 26 2016 12:25PM | Feb 26 2016 5:25PM | Feb 26 2016 7:32PM | 55.616 | 55.075 | 56.70 | 0.00 | 27.696 | 27.920 | 27.379 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 24.0 | -17.4 | G35T2 | PJ6051 PJ6054 PJ6059 | 10 6 8
T/49-1 | SGBM23 | Feb 25 2016 1:30PM | Feb 25 2016 5:45PM | Feb 25 2016 11:10PM | Feb 26 2016 12:21AM | 51.88 | 51.375 | 52.75 | 0.00 | 21.150 | 30.730 | 30.225 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 9 8
P/51-2 | SGBM23 | Feb 24 2016 2:00PM | Feb 25 2016 12:45PM | Feb 25 2016 5:15PM | Feb 25 2016 6:40PM | 51.942 | 48.775 | 52.84 | 0.00 | 14.037 | 37.905 | 34.738 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.1 | 27.0 | -22.1 | G45T2 | pj6004 pj6005 pj6007 | 10 9 8
L/12-1 | SGBM20 | Feb 25 2016 8:30AM | Feb 25 2016 1:00PM | Feb 25 2016 2:50PM | Feb 25 2016 3:55PM | 55.718 | 53.875 | 56.72 | 0.00 | 24.620 | 31.098 | 29.255 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ5989 PJ5990 PJ5993 | 8 8 7
P/51-4 | SGBM23 | Feb 24 2016 1:30PM | Feb 24 2016 6:10PM | Feb 24 2016 10:00PM | Feb 24 2016 11:00PM | 51.954 | 48.775 | 52.55 | 0.00 | 13.851 | 38.103 | 34.924 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.2 | 26.0 | 17.0 | G45T2 | 1 2 3 | 8 8 10
T/53-1 | SGBM15 | Feb 23 2016 11:30AM | Feb 24 2016 11:40AM | Feb 24 2016 6:00PM | Feb 24 2016 7:10PM | 51.888 | 49.825 | 52.70 | 0.00 | 18.002 | 33.886 | 31.823 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 25.0 | 4.8 | G45T2 | PJ5951 PJ5952 PJ5954 | 9 8 8
T/52-2 | SGBM15 | Feb 23 2016 10:50AM | Feb 23 2016 5:40PM | Feb 23 2016 10:10PM | Feb 24 2016 12:05AM | 51.947 | 49.725 | 52.72 | 0.00 | 18.322 | 33.625 | 31.403 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.0 | 26.0 | -20.0 | G45T2 | 1 2 3 | 10 8 8
L/10-2 | SGBM19 | Feb 23 2016 8:14AM | Feb 23 2016 1:50PM | Feb 23 2016 5:10PM | Feb 23 2016 6:55PM | 55.95 | 49.875 | 57.01 | 0.00 | 20.710 | 35.240 | 29.165 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | PJ5899 PJ5902 PJ5904 | 7 8 7
S/51-2 | SGBM23 | Feb 22 2016 10:15AM | Feb 23 2016 12:15PM | Feb 23 2016 4:50PM | Feb 23 2016 6:15PM | 51.827 | 49.775 | 52.45 | 0.00 | 16.651 | 35.176 | 33.124 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 27.0 | -100.0 | G45T2 | PJ5897 PJ5898 PJ5903 | 10 9 8
T1/52-1 | SGBM23 | Feb 22 2016 9:45AM | Feb 22 2016 6:00PM | Feb 22 2016 11:45PM | Feb 23 2016 1:05AM | 51.998 | 51.375 | 52.80 | 0.00 | 21.299 | 30.699 | 30.076 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.1 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 10 7
X3a/Ya-1 | SGBM17 | Feb 22 2016 5:35PM | Feb 22 2016 8:50PM | Feb 22 2016 9:40PM | Feb 22 2016 11:55PM | 55.687 | 55.075 | 56.60 | 0.00 | 27.602 | 28.085 | 27.473 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.5 | 28.0 | -17.5 | G35T2 | PJ5871 PJ5876 PJ5881 | 10 10 8
T/53-2 | SGBM23 | Feb 20 2016 1:00PM | Feb 22 2016 2:15PM | Feb 22 2016 7:20PM | Feb 22 2016 9:35PM | 51.931 | 49.825 | 52.69 | 0.00 | 17.893 | 34.038 | 31.932 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.3 | 28.0 | -100.0 | G45T2 | PJ5859 PJ5860 PJ5862 pj5868 | 8 8 10 2
L/5-2 | SGBM17 | Feb 22 2016 12:15PM | Feb 22 2016 3:39PM | Feb 22 2016 3:50PM | Feb 22 2016 5:04PM | 55.65 | 53.875 | 56.73 | 0.00 | 23.726 | 31.924 | 30.149 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 26.0 | -100.0 | G35T2 | PJ5840 PJ5843 PJ5843 | 10 8 8
S/51-1 | SGBM15 | Feb 20 2016 2:00PM | Feb 20 2016 6:05PM | Feb 20 2016 10:35PM | Feb 20 2016 11:55PM | 51.789 | 49.775 | 52.67 | 0.00 | 14.673 | 37.116 | 35.102 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 26.0 | -22.3 | G45T2 | 1 2 3 | 10 8 8
R/60-1 | SGBM23 | Feb 20 2016 2:20PM | Feb 20 2016 6:05PM | Feb 20 2016 9:00PM | Feb 20 2016 10:25PM | 52.029 | 50.175 | 52.60 | 0.00 | 21.101 | 30.928 | 29.074 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
L/10-1 | SGBM19 | Feb 20 2016 8:25AM | Feb 20 2016 2:15PM | Feb 20 2016 7:30PM | Feb 20 2016 9:27PM | 55.96 | 49.875 | 56.82 | 0.00 | 20.521 | 35.439 | 29.354 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 24.0 | -100.0 | G35T2 | PJ5813 PJ5817 PJ5820 | 8 8 8
P/60-1 | SGBM23 | Feb 19 2016 11:00AM | Feb 20 2016 12:20PM | Feb 20 2016 4:40PM | Feb 20 2016 8:11PM | 52.169 | 50.175 | 52.85 | 0.00 | 18.454 | 33.715 | 31.721 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 29.0 | -100.0 | G45T2 | 1 2 3 4 | 7 10 10 2
X0/Y0-1 | SGBM03 | Feb 20 2016 8:00AM | Feb 20 2016 1:00PM | Feb 20 2016 1:30PM | Feb 20 2016 4:10PM | 55.923 | 54.975 | 56.94 | 0.00 | 47.941 | 34.982 | 7.034 |  | 0.0 | 0.0 | 0.0 | 14T25+7T25 | - | - | T12-175 | - | - | - | 12 | - | 4.5 | 31.5 | -100.0 | G35T2 | PJ5778 PJ5777 PJ5780 PJ5786 | 8 8 10.5 5
Q/60-1 | SGBM23 | Feb 19 2016 11:30AM | Feb 19 2016 6:00PM | Feb 19 2016 9:15PM | Feb 19 2016 11:32PM | 52.229 | 50.175 | 53.00 | 0.00 | 19.196 | 33.033 | 30.979 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.7 | 27.0 | -100.0 | G45T2 | 1 2 3 | 10 9 8
Ta/61a-1 | SGBM23 | Feb 18 2016 2:00PM | Feb 19 2016 10:55AM | Feb 19 2016 7:00PM | Feb 19 2016 9:00PM | 52.105 | 49.775 | 52.85 | 0.00 | 23.054 | 29.051 | 26.721 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.0 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 7 8
L/9-1 | SGBM17 | Feb 19 2016 8:12AM | Feb 19 2016 1:18PM | Feb 19 2016 4:25PM | Feb 19 2016 6:30PM | 55.965 | 53.875 | 56.89 | 0.00 | 24.689 | 31.276 | 29.186 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 27.0 | -100.0 | G35T2 | PJ5738 PJ5739 PJ5473 PJ5748 | 8 8 7 4
T1b/60-1 | SGBM23 | Feb 18 2016 1:25PM | Feb 18 2016 6:00PM | Feb 19 2016 12:10AM | Feb 19 2016 1:05AM | 51.982 | 50.775 | 52.63 | 0.00 | 24.333 | 27.649 | 26.442 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
S/60-1 | SGBM15 | Feb 17 2016 9:55AM | Feb 18 2016 6:00PM | Feb 18 2016 10:00PM | Feb 18 2016 11:30PM | 51.948 | 50.175 | 52.73 | 0.00 | 21.228 | 30.720 | 28.947 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.4 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 8 9
R/60-2 | SGBM15 | Feb 17 2016 10:30AM | Feb 18 2016 12:00PM | Feb 18 2016 8:15PM | Feb 18 2016 10:35PM | 52.033 | 50.175 | 52.91 | 0.00 | 19.910 | 32.123 | 30.265 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 9 8
L/8-2 | SGBM17 | Feb 18 2016 9:00AM | Feb 18 2016 3:00PM | Feb 18 2016 7:00PM | Feb 18 2016 9:55PM | 55.9 | 53.875 | 56.99 | 0.00 | 24.695 | 31.205 | 29.180 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ5704 PJ5712 PJ5717 | 8 8 7
T/54-1 | SGBM23 | Feb 17 2016 5:15PM | Feb 18 2016 11:35AM | Feb 18 2016 6:10PM | Feb 18 2016 8:35PM | 52.057 | 49.825 | 52.85 | 0.00 | 19.350 | 32.707 | 30.475 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 9 8 8 2
L/7-1 | SGBM17 | Feb 18 2016 8:00AM | Feb 18 2016 1:00PM | Feb 18 2016 1:30PM | Feb 18 2016 3:00PM | 55.98 | 53.875 | 56.82 | 0.00 | 24.320 | 31.660 | 29.555 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.8 | 23.0 | -100.0 | G35T2 | PJ5680 PJ5681 PJ5684 | 8 8 7
T1/60-1 | SGBM23 | Feb 17 2016 11:13AM | Feb 17 2016 5:00PM | Feb 18 2016 12:45AM | Feb 18 2016 2:45AM | 51.999 | 49.775 | 52.87 | 0.00 | 23.371 | 28.628 | 26.404 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 22.0 | 31.0 | G45T2 | 1 2 3 | 8 7 7
T1b/59-1 | SGBM23 | Feb 16 2016 11:00AM | Feb 17 2016 10:45AM | Feb 17 2016 9:50PM | Feb 17 2016 11:15PM | 51.918 | 51.375 | 52.84 | 0.00 | 24.837 | 27.081 | 26.538 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 21.0 | -100.0 | G45T2 | 1 2 | 10.5 10.5
Q/60-2 | SGBM15 | Feb 17 2016 10:50AM | Feb 17 2016 4:45PM | Feb 17 2016 8:30PM | Feb 17 2016 10:47PM | 52.218 | 50.175 | 52.97 | 0.00 | 19.673 | 32.545 | 30.502 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 8 8
X5a/Yb-1 | SGBM21 | Feb 17 2016 8:35AM | Feb 17 2016 2:00PM | Feb 17 2016 5:25PM | Feb 17 2016 8:00PM | 55.652 | 55.075 | 57.15 | 0.00 | 27.946 | 27.706 | 27.129 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.3 | 26.0 | -100.0 | G35T2 | PJ5643 PJ5645 PJ5650 PJ5655 | 8 7 7 4
T1b/58-1 | SGBM23 | Feb 17 2016 10:55AM | Feb 17 2016 2:10PM | Feb 17 2016 5:55PM | Feb 17 2016 7:32PM | 51.938 | 51.375 | 52.42 | 0.00 | 24.324 | 27.614 | 27.051 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 23.0 | 33.6 | G45T2 | 1 2 3 | 7 8 8
Q/59-1 | SGBM05 | Feb 16 2016 12:10PM | Feb 16 2016 6:30PM | Feb 16 2016 10:40PM | Feb 17 2016 12:25AM | 52.134 | 51.375 | 52.99 | 0.00 | 20.788 | 31.346 | 30.587 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.5 | 27.0 | 38.7 | G45T2 | 1 2 3 4 | 7 7 7 6
S/60-2 | SGBM15 | Feb 16 2016 12:25PM | Feb 16 2016 6:00PM | Feb 16 2016 9:55PM | Feb 16 2016 11:41PM | 51.895 | 50.175 | 52.74 | 0.00 | 21.844 | 30.051 | 28.331 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
P/60-2 | SGBM05 | Feb 15 2016 2:00PM | Feb 16 2016 2:32PM | Feb 16 2016 8:50PM | Feb 16 2016 9:57PM | 52.112 | 50.175 | 52.94 | 0.00 | 18.838 | 33.274 | 31.337 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 25.0 | -19.9 | G45T2 | 1 2 3 | 8 8 9
T1b/55-1 | SGBM23 | Feb 16 2016 11:20AM | Feb 16 2016 4:15PM | Feb 16 2016 8:25PM | Feb 16 2016 9:51PM | 51.931 | 51.075 | 52.44 | 0.00 | 21.935 | 29.996 | 29.140 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
L/8-1 | SGBM17 | Feb 16 2016 9:15AM | Feb 16 2016 4:00PM | Feb 16 2016 7:00PM | Feb 16 2016 9:00PM | 55.996 | 53.875 | 56.93 | 0.00 | 24.728 | 31.268 | 29.147 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 25.0 | -100.0 | G35T2 | PJ5600 PJ5602 PJ5606 | 8 9 8
T1/61-1 | SGBM15 | Feb 15 2016 11:25AM | Feb 16 2016 11:50AM | Feb 16 2016 7:05PM | Feb 16 2016 8:36PM | 52.023 | 49.775 | 52.91 | 0.00 | 23.410 | 28.613 | 26.365 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 23.0 | -16.8 | G45T2 | 1 2 3 | 8 7 8
X4/Ya-1 | SGBM03 | Feb 16 2016 8:25AM | Feb 16 2016 1:44PM | Feb 16 2016 6:05PM | Feb 16 2016 8:08PM | 55.669 | 55.075 | 56.45 | 0.00 | 27.452 | 28.217 | 27.623 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.6 | 24.0 | -100.0 | G35T2 | PJ5595 PJ5599 PJ5603 | 8 8 8
S/49-1 | SGBM23 | Feb 15 2016 2:45PM | Feb 16 2016 10:30AM | Feb 16 2016 5:10PM | Feb 16 2016 6:51PM | 52.05 | 51.375 | 52.51 | 0.00 | 21.009 | 31.041 | 30.366 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 10 8
Z/63-1 | SGBM31 | Feb 15 2016 10:15AM | Feb 16 2016 3:00PM | Feb 16 2016 4:45PM | Feb 16 2016 6:40PM | 49.145 | 48.155 | 50.09 | 0.00 | 14.292 | 34.853 | 33.863 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.5 | 25.0 | -100.0 | G45T2 | PJ5585 PJ5588 PJ5594 | 9 8 8
X6/Yb-1 | SGBM03 | Feb 15 2016 10:40AM | Feb 15 2016 3:38PM | Feb 15 2016 9:00PM | Feb 15 2016 11:13PM | 55.614 | 55.075 | 56.64 | 0.00 | 27.538 | 28.076 | 27.537 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.5 | 24.0 | -17.5 | G35T2 | PJ5550 PJ5551 PJ5557 | 8 8 8
Q/61-1 | SGBM05 | Feb 15 2016 1:15PM | Feb 15 2016 6:30PM | Feb 15 2016 9:20PM | Feb 15 2016 11:12PM | 52.1 | 49.725 | 52.67 | 0.00 | 19.166 | 32.934 | 30.559 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 24.0 | -19.4 | G45T2 | 1 2 3 | 8 8 8
T1/56-1 | SGBM15 | Feb 15 2016 1:50PM | Feb 15 2016 5:45PM | Feb 15 2016 7:45PM | Feb 15 2016 9:12PM | 51.816 | 51.375 | 52.44 | 0.00 | 22.336 | 29.480 | 29.039 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 8 7
R/49-1 | SGBM23 | Feb 13 2016 3:30PM | Feb 15 2016 2:00PM | Feb 15 2016 6:50PM | Feb 15 2016 8:02PM | 51.905 | 51.375 | 52.65 | 0.00 | 20.155 | 31.750 | 31.220 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 10 8
T/57-1 | SGBM15 | Feb 13 2016 2:35PM | Feb 15 2016 11:10AM | Feb 15 2016 5:25PM | Feb 15 2016 7:02PM | 51.995 | 50.175 | 52.58 | 0.00 | 20.182 | 31.813 | 29.993 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.1 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 8 7
P/51-5 | SGBM01 | Feb 13 2016 8:30AM | Feb 15 2016 12:10PM | Feb 15 2016 4:20PM | Feb 15 2016 5:57PM | 51.842 | 48.775 | 52.58 | 0.00 | 43.585 | 37.457 | 5.190 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 3.3 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
L/9-2 | SGBM17 | Feb 15 2016 8:00AM | Feb 15 2016 12:30PM | Feb 15 2016 2:00PM | Feb 15 2016 3:30PM | 55.965 | 53.875 | 57.00 | 0.00 | 24.701 | 31.264 | 29.174 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | PJ5519 PJ5520 PJ5521 | 8 8 7
R/61-2 | SGBM01 | Feb 12 2016 8:30AM | Feb 13 2016 3:30PM | Feb 13 2016 8:10PM | Feb 13 2016 9:31PM | 52.024 | 49.725 | 52.12 | 0.00 | 19.121 | 32.903 | 30.604 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 9 8
P/51-1 | SGBM23 | Feb 13 2016 8:00AM | Feb 13 2016 3:10PM | Feb 13 2016 7:15PM | Feb 13 2016 9:13PM | 51.803 | 48.775 | 52.72 | 0.00 | 13.920 | 37.883 | 34.855 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.2 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
P/61-2 | SGBM05 | Feb 10 2016 5:40PM | Feb 13 2016 12:05PM | Feb 13 2016 6:45PM | Feb 13 2016 8:07PM | 52.188 | 49.725 | 52.93 | 0.00 | 18.528 | 33.660 | 31.197 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.8 | 25.0 | -100.0 | G45T2 | 1 2 3 | 7 10 8
T/55-2 | SGBM20 | Feb 13 2016 9:40AM | Feb 13 2016 2:15PM | Feb 13 2016 5:30PM | Feb 13 2016 7:48PM | 51.938 | 50.175 | 52.48 | 0.00 | 19.682 | 32.256 | 30.493 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 3
P/49-1 | SGBM23 | Feb 11 2016 5:30PM | Feb 13 2016 11:55AM | Feb 13 2016 4:10PM | Feb 13 2016 6:44PM | 51.919 | 51.375 | 52.57 | 0.00 | 18.167 | 33.752 | 33.208 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
X4a/Ya-1 | SGBM03 | Feb 13 2016 8:14AM | Feb 13 2016 1:00PM | Feb 13 2016 1:20PM | Feb 13 2016 5:25PM | 55.78 | 55.075 | 56.87 | 0.00 | 27.770 | 28.010 | 27.305 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 28.0 | -100.0 | G35T2 | PJ5464 PJ5466 PJ5469 PJ5482 | 8 8 8 4
M7a/61-1 | SGBM01 | Feb 5 2016 4:50PM | Feb 13 2016 11:50AM | Feb 13 2016 1:10PM | Feb 13 2016 2:52PM | 51.772 | 49.775 | 52.57 | 0.00 | 16.967 | 34.805 | 32.808 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.9 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 10 8
R/50-1 | SGBM23 | Feb 11 2016 5:05PM | Feb 12 2016 6:05PM | Feb 12 2016 8:20PM | Feb 12 2016 9:47PM | 51.716 | 50.975 | 52.62 | 0.00 | 18.322 | 33.394 | 32.653 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.8 | 25.0 | -100.0 | G45T2 | 1 2 3 | 7 10 8
AB/56-1 | SGBM31 | Feb 11 2016 4:40PM | Feb 12 2016 1:17PM | Feb 12 2016 7:45PM | Feb 12 2016 9:00PM | 49.407 | 49.075 | 50.17 | 0.00 | 16.171 | 33.236 | 32.904 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.9 | 24.0 | 14.6 | G35T2 | 1 2 3 | 8 8 8
S/50-1 | SGBM23 | Feb 11 2016 4:45PM | Feb 12 2016 11:30AM | Feb 12 2016 6:20PM | Feb 12 2016 7:41PM | 51.841 | 51.075 | 52.58 | 0.00 | 19.181 | 32.660 | 31.894 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.3 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
L/6-2 | SGBM17 | Feb 11 2016 6:00PM | Feb 12 2016 1:00PM | Feb 12 2016 3:15PM | Feb 12 2016 4:40PM | 55.639 | 53.875 | 56.09 | 0.00 | 24.293 | 31.346 | 29.582 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.8 | 23.0 | -100.0 | G35T2 | PJ5430 PJ5431 PJ5432 | 8 8 7
X5a/Ya-1 | SGBM03 | Feb 12 2016 1:35PM | Feb 12 2016 6:22PM | Feb 12 2016 10:30AM | Feb 12 2016 12:22PM | 55.685 | 55.075 | 56.75 | 0.00 | 27.752 | 27.933 | 27.323 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 26.0 | -100.0 | G35T2 | PJ5424 PJ5425 PJ5426 | 8 8 10
L/7-2 | SGBM17 | Feb 11 2016 10:00AM | Feb 11 2016 4:00PM | Feb 11 2016 9:15PM | Feb 11 2016 10:35PM | 55.994 | 53.875 | 56.98 | 0.00 | 24.577 | 31.417 | 29.298 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -18.6 | G35T2 | 5415 5417 5420 | 7 8 8
Q/61-2 | SGBM05 | Feb 5 2016 4:00PM | Feb 11 2016 5:45PM | Feb 11 2016 9:00PM | Feb 11 2016 10:32PM | 52.026 | 49.725 | 52.99 | 0.00 | 18.887 | 33.139 | 30.838 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.6 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 9 8
T/57-2 | SGBM23 | Feb 10 2016 10:50AM | Feb 11 2016 4:03PM | Feb 11 2016 6:25PM | Feb 11 2016 8:03PM | 51.973 | 50.175 | 52.73 | 0.00 | 20.627 | 31.346 | 29.548 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.8 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
S/55-1 | SGBM23 | Feb 10 2016 11:15AM | Feb 11 2016 10:50AM | Feb 11 2016 5:05PM | Feb 11 2016 7:18PM | 51.949 | 50.375 | 52.57 | 0.00 | 18.867 | 33.082 | 31.508 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.0 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 4
X7/Yb-1 | SGBM03 | Feb 11 2016 8:12AM | Feb 11 2016 1:15PM | Feb 11 2016 3:30PM | Feb 11 2016 5:12PM | 55.54 | 55.075 | 56.64 | 0.00 | 27.640 | 27.900 | 27.435 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.5 | 24.0 | -100.0 | G35T2 | PJ5390 PJ5391 PJ5393 | 8 8 8
S/61-1 | SGBM05 | Feb 5 2016 4:15PM | Feb 10 2016 4:00PM | Feb 11 2016 12:35AM | Feb 11 2016 1:52AM | 52.01 | 48.575 | 52.61 | 0.00 | 20.112 | 31.898 | 28.463 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | -18.1 | G45T2 | 1 2 3 | 8 8 7
X5/Ya-1 | SGBM03 | Feb 10 2016 11:31AM | Feb 10 2016 4:27PM | Feb 10 2016 10:10PM | Feb 11 2016 1:00AM | 56.154 | 55.075 | 56.74 | 0.00 | 27.944 | 28.210 | 27.131 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.3 | 24.0 | -100.0 | G35T2 | PJ5370 PJ5373 PJ5377 | 8 8 8
T1/58-1 | SGBM23 | Feb 5 2016 4:25PM | Feb 10 2016 11:00AM | Feb 10 2016 6:30PM | Feb 10 2016 10:21PM | 51.977 | 51.375 | 52.70 | 0.00 | 23.304 | 28.673 | 28.071 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 23.0 | -100.0 | G45T2 | 1 2 3 | 7 8 8
U/62-1 | SGBM20 | Feb 10 2016 10:45AM | Feb 10 2016 3:25PM | Feb 10 2016 7:20PM | Feb 10 2016 9:25PM | 51.141 | 51.375 | 51.89 | 0.00 | 21.891 | 29.250 | 29.484 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.8 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 8 7
L/4-2 | SGBM19 | Feb 10 2016 10:00AM | Feb 10 2016 2:00PM | Feb 10 2016 4:10PM | Feb 10 2016 6:00PM | 55.672 | 53.875 | 56.58 | 0.00 | 23.581 | 32.091 | 30.294 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 23.0 | -100.0 | G35T2 | PJ5343 PJ5349 PJ5344 | 7 8 8
Q/51-2 | SGBM23 | Feb 4 2016 3:00PM | Feb 5 2016 8:30AM | Feb 5 2016 5:35PM | Feb 5 2016 8:23PM | 51.894 | 50.175 | 52.37 | 0.00 | 15.573 | 36.321 | 34.602 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.0 | 34.0 | 12.0 | G45T2 | 1 2 3 4 | 10 8 9 7
L/6-1 | SGBM19 | Feb 4 2016 2:00PM | Feb 5 2016 11:00AM | Feb 5 2016 3:30PM | Feb 5 2016 4:50PM | 55.827 | 53.875 | 56.92 | 0.00 | 24.619 | 31.208 | 29.256 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G35T2 | PJ5329 PJ5330 PJ5331 | 8 7 7
X8a/Yb-1 | SGBM03 | Feb 4 2016 7:05PM | Feb 5 2016 10:55AM | Feb 5 2016 11:50AM | Feb 5 2016 2:20PM | 55.528 | 55.075 | 56.82 | 0.00 | 27.820 | 27.708 | 27.255 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.3 | 25.0 | -100.0 | G35T2 | PJ5321 PJ5323 PJ5326 | 9 8 8
T/56-1 | SGBM23 | Feb 3 2016 5:25PM | Feb 4 2016 3:03PM | Feb 4 2016 8:50PM | Feb 4 2016 10:53PM | 51.915 | 50.175 | 52.48 | 0.00 | 19.879 | 32.036 | 30.296 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 27.0 | -19.3 | G45T2 | 1 2 3 4 | 8 8 8 3
T/58-1 | SGBM23 | Feb 3 2016 5:00PM | Feb 4 2016 10:55AM | Feb 4 2016 7:25PM | Feb 4 2016 8:32PM | 52.092 | 51.375 | 52.78 | 0.00 | 22.682 | 29.410 | 28.693 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 26.0 | -18.3 | G45T2 | 1 2 3 | 8 10 8
L/5-1 | SGBM19 | Feb 4 2016 8:00AM | Feb 4 2016 3:00PM | Feb 4 2016 5:30PM | Feb 4 2016 7:50PM | 55.69 | 53.875 | 56.49 | 0.00 | 23.693 | 31.997 | 30.182 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 26.0 | -100.0 | G35T2 | PJ5288 PJ5289 PJ5293 PJ5298 | 7 8 7 4
P/59-1 | SGBM15 | Feb 3 2016 4:00PM | Feb 4 2016 12:45PM | Feb 4 2016 6:00PM | Feb 4 2016 7:39PM | 52.093 | 50.375 | 52.89 | 0.00 | 17.692 | 34.401 | 32.683 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.8 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
X6/Ya-1 | SGBM03 | Feb 4 2016 8:13AM | Feb 4 2016 1:00PM | Feb 4 2016 3:50PM | Feb 4 2016 5:50PM | 55.685 | 55.075 | 56.64 | 0.00 | 27.740 | 27.945 | 27.335 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 24.0 | -100.0 | G35T2 | PJ5279 PJ5280 PJ5283 | 8 8 8
R/59-1 | SGBM01 | Feb 3 2016 4:10PM | Feb 4 2016 10:30AM | Feb 4 2016 2:55PM | Feb 4 2016 4:57PM | 52.058 | 51.375 | 52.75 | 0.00 | 21.652 | 30.406 | 29.723 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 25.0 | -18.9 | G45T2 | 1 2 3 4 | 7 7 8 3
S/61-2 | SGBM05 | Feb 3 2016 9:45AM | Feb 3 2016 5:05PM | Feb 4 2016 12:35AM | Feb 4 2016 1:47AM | 52.037 | 48.575 | 52.58 | 0.00 | 19.980 | 32.057 | 28.595 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 22.0 | -100.0 | G45T2 | 1 2 3 4 | 7 2 7 6
T2a/56-1 | SGBM20 | Feb 3 2016 9:30AM | Feb 3 2016 2:39PM | Feb 3 2016 11:25PM | Feb 4 2016 1:11AM | 51.075 | 51.375 | 52.59 | 0.00 | 23.788 | 27.287 | 27.587 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.6 | 21.0 | -100.0 | G45T2 | PJ5261 PJ5262 PJ5264 | 8 6.5 6.5
M7/60a-1 | SGBM01 | Feb 2 2016 9:00AM | Feb 3 2016 11:45AM | Feb 3 2016 10:30PM | Feb 4 2016 12:18AM | 51.863 | 49.775 | 52.52 | 0.00 | 17.323 | 34.540 | 32.452 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.6 | 25.0 | -100.0 | G35T2 | 1 2 3 | 10 8 7
T1/59-1 | SGBM23 | Feb 2 2016 3:55PM | Feb 3 2016 2:45PM | Feb 3 2016 10:15PM | Feb 3 2016 11:42PM | 52.03 | 50.375 | 52.71 | 0.00 | 23.510 | 28.520 | 26.865 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 21.0 | -100.0 | G45T2 | 2 2 3 | 7 7 7
M6/58-1 | SGBM15 | Feb 2 2016 3:35PM | Feb 3 2016 1:20PM | Feb 3 2016 8:15PM | Feb 3 2016 9:47PM | 52.037 | 49.875 | 52.84 | 0.00 | 16.643 | 35.394 | 33.232 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
L/3-2 | SGBM19 | Feb 3 2016 8:00AM | Feb 3 2016 4:00PM | Feb 3 2016 6:40PM | Feb 3 2016 8:25PM | 55.687 | 53.875 | 56.73 | 0.00 | 23.627 | 32.060 | 30.248 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 24.0 | -19.2 | G35T2 | PJ5236 PJ5238 PJ5242 | 8 8 8
S/55-2 | SGBM23 | Feb 2 2016 4:00PM | Feb 3 2016 10:45AM | Feb 3 2016 5:10PM | Feb 3 2016 7:13PM | 51.941 | 50.375 | 52.71 | 0.00 | 18.308 | 33.633 | 32.067 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.4 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
R/61-1 | SGBM05 | Feb 2 2016 8:30AM | Feb 3 2016 9:20AM | Feb 3 2016 3:40PM | Feb 3 2016 5:04PM | 52.035 | 49.725 | 52.75 | 0.00 | 20.447 | 31.588 | 29.278 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G45T2 | 1 2 3 | 7 8 8
L/4-1 | SGBM19 | Feb 2 2016 9:30AM | Feb 3 2016 1:00PM | Feb 3 2016 2:10PM | Feb 3 2016 3:45PM | 55.72 | 53.875 | 56.60 | 0.00 | 23.500 | 32.220 | 30.375 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 23.0 | -19.3 | G35T2 | PJ5216 PJ5217 PJ5221 | 8 8 7
R/51-1b | SGBM23 | Feb 2 2016 8:45AM | Feb 2 2016 4:30PM | Feb 2 2016 10:45PM | Feb 3 2016 12:02AM | 51.786 | 49.775 | 52.18 | 0.00 | 15.984 | 35.802 | 33.791 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.5 | 25.0 | -21.5 | G35T2 | 1 2 3 | 8 9 8
P/61-1 | SGBM05 | Feb 2 2016 9:15AM | Feb 2 2016 4:15PM | Feb 2 2016 10:00PM | Feb 2 2016 11:27PM | 52.044 | 49.725 | 52.66 | 0.00 | 18.762 | 33.282 | 30.963 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.7 | 24.0 | -19.7 | G45T2 | 1 2 3 | 8 8 8
X6a/Yb-1 | SGBM03 | Feb 2 2016 10:00AM | Feb 2 2016 3:10PM | Feb 2 2016 7:50PM | Feb 2 2016 10:40PM | 55.628 | 55.075 | 56.55 | 0.00 | 27.549 | 28.079 | 27.526 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.5 | 30.0 | -100.0 | G35T2 | 1 2 3 4 | 8 8 8 6
T1/57-1 | SGBM01 | Jan 29 2016 5:30PM | Feb 2 2016 2:45PM | Feb 2 2016 6:50PM | Feb 2 2016 9:37PM | 51.892 | 51.375 | 52.48 | 0.00 | 23.877 | 28.015 | 27.498 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 8 6
U/60-1 | SGBM31 | Jan 30 2016 2:50PM | Feb 2 2016 3:30PM | Feb 2 2016 7:05PM | Feb 2 2016 8:10PM | 51.029 | 45.875 | 52.60 | 0.00 | 20.502 | 30.527 | 25.373 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 22.0 | -100.0 | G45T2 | C480016181 C480016182 | 11 11
T2a/59-1 | SGBM31 | Jan 30 2016 3:20PM | Feb 2 2016 10:21AM | Feb 2 2016 3:45PM | Feb 2 2016 5:35PM | 51.96 | 51.375 | 52.83 | 0.00 | 25.028 | 26.932 | 26.347 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | -100.0 | G45T2 | Pending PJ5180 PJ5183 | 7 7 7
X9/Yb-1 | SGBM03 | Feb 2 2016 9:00AM | Feb 2 2016 12:21PM | Feb 2 2016 3:20PM | Feb 2 2016 5:35PM | 55.645 | 55.075 | 56.94 | 0.00 | 27.737 | 27.908 | 27.338 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
N/6-1 | SGBM19 | Feb 2 2016 9:00AM | Feb 2 2016 1:00PM | Feb 2 2016 2:40PM | Feb 2 2016 5:00PM | 55.8 | 55.075 | 56.86 | 0.00 | 25.857 | 29.943 | 29.218 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
T/55-1 | SGBM01 | Jan 29 2016 5:30PM | Jan 30 2016 5:00PM | Jan 31 2016 12:20AM | Jan 31 2016 1:52AM | 51.991 | 50.175 | 52.45 | 0.00 | 17.947 | 34.044 | 32.228 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 22.0 | -100.0 | G45T2 | 1 2 3 | 10 10 2
P/59-2 | SGBM05 | Jan 30 2016 9:40AM | Jan 30 2016 3:25PM | Jan 30 2016 10:00PM | Jan 30 2016 11:42PM | 52.023 | 50.375 | 52.69 | 0.00 | 17.793 | 34.230 | 32.582 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.7 | 27.0 | -100.0 | G45T2 | 1 2 3 | 10 7 10
M6/57-1 | SGBM15 | Jan 29 2016 5:35PM | Jan 30 2016 1:03PM | Jan 30 2016 8:45PM | Jan 30 2016 10:32PM | 52.02 | 50.075 | 52.78 | 0.00 | 16.583 | 35.437 | 33.492 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.3 | 27.0 | -100.0 | G45T2 | 1 2 3 | 11 8 8
V/56-1 | SGBM17 | Dec 30 2015 8:40AM | Dec 30 2015 2:13PM | Jan 30 2016 8:55PM | Jan 30 2016 10:09PM | 49.412 | 48.775 | 50.44 | 0.00 | 22.740 | 26.672 | 26.035 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 22.0 | -100.0 | G45T2 | C480014278 C170014207 C170014210 | 11 8 3
M1/15-1 | SGBM17 | Jan 30 2016 10:00AM | Jan 30 2016 3:00PM | Jan 30 2016 8:10PM | Jan 30 2016 9:10PM | 55.735 | 54.625 | 56.46 | 0.00 | 29.460 | 26.275 | 25.165 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 18.0 | -16.0 | G45T2 | 5144 5150 | 10 8
X7a/Yb-1 | SGBM03 | Jan 30 2016 8:00AM | Jan 30 2016 2:00PM | Jan 30 2016 5:05PM | Jan 30 2016 7:45PM | 55.665 | 55.075 | 57.26 | 0.00 | 27.963 | 27.702 | 27.112 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12+6 | - | 17.3 | 24.0 | -100.0 | G35T2 | 5128 5130 5140 | 8 8 8
AA/62-1 | SGBM17 | Jan 29 2016 3:27PM | Jan 30 2016 1:45PM | Jan 30 2016 3:10PM | Jan 30 2016 6:10PM | 49.276 | 47.075 | 50.17 | 0.00 | 14.371 | 34.905 | 32.704 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.8 | 26.0 | -100.0 | G35T2 | 5114 5117 5120 5222 | 8 8 8 2
L/3-1 | SGBM19 | Jan 29 2016 12:10PM | Jan 30 2016 1:30PM | Jan 30 2016 2:30PM | Jan 30 2016 5:25PM | 55.635 | 53.875 | 56.69 | 0.00 | 23.392 | 32.243 | 30.483 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 26.0 | -100.0 | G35T2 | 1 2 3 4 | 8 8 7 3
Q/51-1 | SGBM01 | Jan 29 2016 9:05AM | Jan 30 2016 10:44AM | Jan 30 2016 3:20PM | Jan 30 2016 5:02PM | 51.843 | 50.175 | 52.53 | 0.00 | 14.529 | 37.314 | 35.646 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.7 | 27.0 | -100.0 | G45T2 | 1 2 3 | 9 9 9
N/3-1 | SGBM03 | Jan 29 2016 12:00PM | Jan 29 2016 6:00PM | Jan 30 2016 12:05AM | Jan 30 2016 3:00AM | 55.722 | 55.075 | 56.49 | 0.00 | 24.794 | 30.928 | 30.281 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 29.0 | -100.0 | G35T2 | 1 2 3 4 | 7 8 8 6
T2a/60-1 | SGBM17 | Jan 28 2016 3:30PM | Jan 29 2016 2:17PM | Jan 30 2016 12:45AM | Jan 30 2016 2:19AM | 52.012 | 51.375 | 52.83 | 0.00 | 25.634 | 26.378 | 25.741 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.4 | 22.0 | -100.0 | G45T2 | PJ5102 PJ5104 PJ5106 | 8 7 7
P/54-2 | SGBM01 | Jan 29 2016 8:20AM | Jan 29 2016 3:50PM | Jan 29 2016 8:40PM | Jan 29 2016 11:22PM | 51.982 | 50.175 | 52.78 | 0.00 | 15.778 | 36.204 | 34.397 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 9 3
T2a/52-1 | SGBM20 | Jan 28 2016 3:00PM | Jan 29 2016 1:35PM | Jan 29 2016 9:10PM | Jan 29 2016 10:40PM | 51.811 | 51.375 | 52.63 | 0.00 | 24.426 | 27.385 | 26.949 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 21.0 | -100.0 | G45T2 | PJ5087 PJ5088 PJ5091 | 7 7 7
X9a/Yb-1 | SGBM03 | Jan 29 2016 11:00AM | Jan 29 2016 2:25PM | Jan 29 2016 5:55PM | Jan 29 2016 10:10PM | 55.669 | 55.075 | 56.78 | 0.00 | 27.783 | 27.886 | 27.292 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 25.0 | 44.0 | G35T2 | 1 2 3 4 | 4 8 8 5
M7/60-1 | SGBM15 | Jan 27 2016 3:35PM | Jan 28 2016 2:45PM | Jan 29 2016 12:35AM | Jan 29 2016 3:22AM | 51.964 | 49.775 | 52.62 | 0.00 | 16.724 | 35.240 | 33.051 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 26.0 | -100.0 | G35T2 | 1 2 3 | 8 10 8
X6a/Ya-1 | SGBM03 | Jan 28 2016 12:00PM | Jan 28 2016 4:35PM | Jan 28 2016 11:10PM | Jan 29 2016 1:05AM | 55.801 | 55.075 | 56.88 | 0.00 | 27.681 | 28.120 | 27.394 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 25.0 | -100.0 | G35T2 | 1 2 3 | 8 10 7
M6/58-2 | SGBM15 | Jan 28 2016 8:30AM | Jan 28 2016 12:55PM | Jan 28 2016 10:10PM | Jan 28 2016 11:55PM | 51.992 | 49.875 | 52.66 | 0.00 | 16.356 | 35.636 | 33.519 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.3 | 27.0 | -100.0 | G45T2 | 5041 5042 5048 | 10 8 9
T/56-2 | SGBM01 | Jan 27 2016 2:40PM | Jan 28 2016 10:55AM | Jan 28 2016 8:25PM | Jan 28 2016 10:12PM | 51.905 | 50.175 | 52.47 | 0.00 | 21.172 | 30.733 | 29.003 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
T2a/55-1 | SGBM20 | Jan 28 2016 8:35AM | Jan 28 2016 2:00PM | Jan 28 2016 7:40PM | Jan 28 2016 9:25PM | 51.827 | 51.375 | 52.49 | 0.00 | 23.288 | 28.539 | 28.087 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 23.0 | -100.0 | G45T2 | PJ5028 PJ5632 PJ5036 | 8 8 7
T/54-2 | SGBM23 | Jan 27 2016 3:05PM | Jan 28 2016 11:35AM | Jan 28 2016 6:30PM | Jan 28 2016 7:59PM | 51.978 | 49.825 | 52.88 | 0.00 | 19.582 | 32.396 | 30.243 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 8 9
T2a/58-1 | SGBM17 | Jan 28 2016 8:15AM | Jan 28 2016 1:18PM | Jan 28 2016 4:10PM | Jan 28 2016 5:40PM | 51.909 | 51.375 | 52.87 | 0.00 | 24.569 | 27.340 | 26.806 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 21.0 | -100.0 | G45T2 | PJ5014 PJ5015 PJ5017 | 7 7 7
X7a/Ya-1 | SGBM03 | Jan 27 2016 11:20AM | Jan 28 2016 10:00AM | Jan 28 2016 1:35PM | Jan 28 2016 4:10PM | 55.808 | 55.075 | 56.74 | 0.00 | 27.744 | 28.064 | 27.331 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12+6 | - | 17.4 | 25.0 | -100.0 | G35T2 | 5007 5008 5009 | 9 8 8
M6/57-2 | SGBM15 | Jan 27 2016 11:45AM | Jan 27 2016 4:50PM | Jan 28 2016 3:00AM | Jan 28 2016 4:42AM | 51.994 | 50.075 | 52.70 | 0.00 | 16.404 | 35.590 | 33.671 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.4 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 8 10
P/55-1 | SGBM23 | Jan 26 2016 3:40PM | Jan 27 2016 3:23PM | Jan 28 2016 1:32AM | Jan 28 2016 3:32AM | 51.89 | 50.175 | 52.72 | 0.00 | 15.418 | 36.472 | 34.757 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.1 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
U/60-2 | SGBM17 | Jan 27 2016 9:34AM | Jan 27 2016 2:38PM | Jan 27 2016 10:40PM | Jan 27 2016 11:55PM | 51.982 | 45.875 | 52.86 | 0.00 | 20.559 | 31.423 | 25.316 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 19.0 | -100.0 | G45T2 | PJ4990 PJ4994 | 10 9
AA/61-1 | SGBM23 | Jan 27 2016 9:26AM | Jan 27 2016 4:35PM | Jan 27 2016 9:00PM | Jan 27 2016 10:50PM | 49.553 | 48.155 | 50.36 | 0.00 | 14.063 | 35.490 | 34.092 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 26.0 | -21.6 | G35T2 | 4988 4980 4984 | 8 10 8
P/59-3 | SGBM01 | Jan 26 2016 4:45PM | Jan 27 2016 12:00PM | Jan 27 2016 8:15PM | Jan 27 2016 9:42PM | 52.114 | 50.375 | 52.76 | 0.00 | 18.156 | 33.958 | 32.219 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 10 8
X8a/Ya-1 | SGBM03 | Jan 27 2016 9:00AM | Jan 27 2016 1:30PM | Jan 27 2016 5:10PM | Jan 27 2016 7:55PM | 55.84 | 55.075 | 57.02 | 0.00 | 27.518 | 28.322 | 27.557 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.5 | 25.0 | 42.6 | G35T2 | 1 2 3 | 8 9 8
R/51-1a | SGBM23 | Jan 26 2016 9:35AM | Jan 27 2016 10:15AM | Jan 27 2016 2:05PM | Jan 27 2016 3:48PM | 51.931 | 49.775 | 52.50 | 0.00 | 15.797 | 36.134 | 33.978 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.6 | 27.0 | -21.6 | G35T2 | 1 2 3 | 10 8 9
U/59-2 | SGBM17 | Jan 26 2016 10:50AM | Jan 26 2016 6:00PM | Jan 26 2016 10:30PM | Jan 27 2016 12:00AM | 51.976 | 50.175 | 52.97 | 0.00 | 24.367 | 27.609 | 25.808 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.4 | 23.0 | -100.0 | G45T2 | 1 2 3 | 7 8 8
S/55-3 | SGBM05 | Jan 26 2016 9:45AM | Jan 26 2016 3:30PM | Jan 26 2016 10:15PM | Jan 26 2016 11:38PM | 51.987 | 50.375 | 52.66 | 0.00 | 18.660 | 33.327 | 31.715 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 27.0 | -100.0 | G45T2 | 1 2 3 | 10 8 9
P/54-1 | SGBM23 | Jan 26 2016 9:00AM | Jan 26 2016 3:30PM | Jan 26 2016 8:45PM | Jan 26 2016 10:23PM | 51.933 | 50.175 | 52.49 | 0.00 | 18.488 | 33.445 | 31.687 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 27.0 | -100.0 | G45T2 | 1 2 3 | 7 10 10
X10/Yb-1 | SGBM03 | Jan 26 2016 8:00AM | Jan 26 2016 2:00PM | Jan 26 2016 4:40PM | Jan 26 2016 7:00PM | 55.637 | 55.075 | 56.57 | 0.00 | 27.470 | 28.167 | 27.605 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12+6 | - | 17.6 | 24.0 | 36.6 | G35T2 | 4890 4893 4895 | 8 8 8
U/58-2 | SGBM17 | Jan 23 2016 1:47PM | Jan 26 2016 10:00AM | Jan 26 2016 2:40PM | Jan 26 2016 4:30PM | 51.919 | 50.175 | 52.81 | 0.00 | 23.806 | 28.113 | 26.369 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
P/57-1 | SGBM08 | Jan 22 2016 4:50PM | Jan 26 2016 8:40AM | Jan 26 2016 12:10PM | Jan 26 2016 1:34PM | 52.063 | 50.175 | 52.77 | 0.00 | 16.273 | 35.790 | 33.902 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.6 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
Q/52-1 | SGBM23 | Jan 23 2016 11:10AM | Jan 23 2016 3:35PM | Jan 23 2016 8:05PM | Jan 23 2016 9:32PM | 51.859 | 50.175 | 52.39 | 0.00 | 14.886 | 36.973 | 35.289 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.5 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 10 8
X7/Ya-1 | SGBM03 | Jan 23 2016 10:00AM | Jan 23 2016 1:50PM | Jan 23 2016 4:20PM | Jan 23 2016 6:30PM | 55.64 | 55.075 | 56.24 | 0.00 | 27.445 | 28.195 | 27.630 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.6 | 24.0 | 36.5 | G35T2 | 1 2 3 | 8 8 8
N/58-1 | SGBM05 | Jan 21 2016 3:45PM | Jan 23 2016 9:45AM | Jan 23 2016 4:25PM | Jan 23 2016 5:57PM | 52.153 | 50.175 | 52.74 | 0.00 | 15.937 | 36.216 | 34.238 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.8 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 9 8
U/56-1 | SGBM17 | Jan 22 2016 4:47PM | Jan 23 2016 12:00PM | Jan 23 2016 2:45PM | Jan 23 2016 4:45PM | 51.786 | 51.375 | 52.56 | 0.00 | 23.265 | 28.521 | 28.110 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 21.0 | 17.4 | G45T2 | 1 2 3 | 7 7 7
P/53-1 | SGBM23 | Jan 21 2016 11:40AM | Jan 23 2016 10:05AM | Jan 23 2016 1:15PM | Jan 23 2016 2:42PM | 51.968 | 50.175 | 52.79 | 0.00 | 13.995 | 37.973 | 36.180 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.0 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
T2a/51-1 | SGBM20 | Jan 22 2016 2:36PM | Jan 23 2016 9:24AM | Jan 23 2016 11:15AM | Jan 23 2016 12:15PM | 51.776 | 51.325 | 52.59 | 0.00 | 24.994 | 26.782 | 26.331 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | -100.0 | G35T2 | 4807 4808 4809 | 7 7 7
P/55-2 | SGBM23 | Jan 21 2016 11:30AM | Jan 22 2016 12:05PM | Jan 23 2016 1:10AM | Jan 23 2016 1:37AM | 52.078 | 50.175 | 52.59 | 0.00 | 15.192 | 36.886 | 34.983 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
P/52-2 | SGBM23 | Jan 21 2016 11:30AM | Jan 22 2016 12:05PM | Jan 22 2016 11:25PM | Jan 23 2016 12:52AM | 51.988 | 50.175 | 52.59 | 0.00 | 15.192 | 36.796 | 34.983 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 27.0 | -100.0 | G45T2 | Pending 2 3 4 | 7 7 7 6
U/59-1 | SGBM20 | Jan 22 2016 8:44AM | Jan 22 2016 5:15PM | Jan 22 2016 6:40PM | Jan 22 2016 8:20PM | 51.918 | 50.175 | 52.78 | 0.00 | 24.577 | 27.341 | 25.598 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.3 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
X9a/Ya-1 | SGBM03 | Jan 22 2016 10:00AM | Jan 22 2016 2:09PM | Jan 22 2016 4:40PM | Jan 22 2016 7:10PM | 55.789 | 55.075 | 56.68 | 0.00 | 27.984 | 27.805 | 27.091 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.2 | 26.0 | -100.0 | G35T2 | 1 2 3 | 10 8 8
R/53-1 | SGBM23 | Jan 21 2016 12:35PM | Jan 21 2016 4:15PM | Jan 22 2016 12:35AM | Jan 22 2016 2:37AM | 51.802 | 50.175 | 52.61 | 0.00 | 15.807 | 35.995 | 34.368 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 6 8
Q/52-2 | SGBM23 | Jan 20 2016 11:05AM | Jan 21 2016 10:00AM | Jan 21 2016 11:35PM | Jan 22 2016 12:32AM | 51.79 | 50.175 | 52.67 | 0.00 | 15.873 | 35.917 | 34.302 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.8 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
P/57-2 | SGBM23 | Jan 20 2016 12:00PM | Jan 21 2016 11:40AM | Jan 21 2016 10:00PM | Jan 21 2016 10:57PM | 52.077 | 50.175 | 52.97 | 0.00 | 15.871 | 36.206 | 34.304 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.8 | 26.0 | 19.1 | G45T2 | 1 2 3 | 10 8 8
U/57-2 | SGBM17 | Jan 21 2016 8:43AM | Jan 21 2016 6:00PM | Jan 21 2016 9:30PM | Jan 21 2016 10:40PM | 51.86 | 50.175 | 52.66 | 0.00 | 23.457 | 28.403 | 26.718 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.0 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
U/52-2 | SGBM17 | Jan 21 2016 8:30AM | Jan 21 2016 4:20PM | Jan 21 2016 5:35PM | Jan 21 2016 7:50PM | 51.889 | 50.175 | 52.89 | 0.00 | 23.791 | 28.098 | 26.384 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 8 7
V/46-2 | SGBM20 | Jan 21 2016 8:42AM | Jan 21 2016 4:47PM | Jan 21 2016 6:00PM | Jan 21 2016 7:50PM | 50.249 | 47.775 | 51.04 | 0.00 | 21.042 | 29.207 | 26.733 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.0 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
R/52-1 | SGBM23 | Jan 20 2016 11:30AM | Jan 20 2016 3:50PM | Jan 21 2016 1:35AM | Jan 21 2016 2:59AM | 51.884 | 49.775 | 52.43 | 0.00 | 15.630 | 88.684 | 34.145 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 32.0 | 10.3 | G45T2 | 1 2 3 | 11 10 11
V/46-1 | SGBM20 | Jan 20 2016 8:32AM | Jan 20 2016 5:35PM | Jan 20 2016 11:35PM | Jan 21 2016 1:00AM | 50.285 | 47.775 | 51.26 | 0.00 | 21.263 | 29.022 | 26.512 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
U/53-1 | SGBM17 | Jan 20 2016 9:12AM | Jan 20 2016 5:56PM | Jan 20 2016 9:30PM | Jan 20 2016 11:25PM | 51.842 | 50.175 | 52.55 | 0.00 | 23.851 | 27.991 | 26.324 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 21.0 | -100.0 | G45T2 | 1 2 3 | 4 10 7
Q/54-1 | SGBM23 | Jan 19 2016 11:35AM | Jan 20 2016 9:40AM | Jan 20 2016 3:10PM | Jan 20 2016 6:58PM | 51.914 | 51.375 | 52.82 | 0.00 | 16.520 | 35.394 | 34.855 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.2 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 8 9 8 2
X8/Ya-1 | SGBM03 | Jan 20 2016 10:00AM | Jan 20 2016 1:08PM | Jan 20 2016 5:20PM | Jan 20 2016 6:55PM | 55.64 | 55.075 | 56.24 | 0.00 | 27.845 | 27.795 | 27.230 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.3 | 27.0 | -100.0 | G35T2 | 1 2 3 | 11 11 5
V/62-1 | SGBM31 | Jan 18 2016 1:58PM | Jan 19 2016 5:15PM | Jan 19 2016 9:30PM | Jan 19 2016 10:30PM | 50.781 | 47.075 | 51.66 | 0.00 | 19.660 | 31.121 | 27.415 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.4 | 21.0 | -100.0 | G35T2 | 4623 4625 4627 | 7 7 7
M5b/56-1 | SGBM23 | Jan 19 2016 11:05AM | Jan 19 2016 3:35PM | Jan 19 2016 7:45PM | Jan 19 2016 9:18PM | 51.905 | 51.375 | 52.71 | 0.00 | 17.706 | 34.199 | 33.669 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.4 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 3
U/54-1 | SGBM19 | Jan 19 2016 8:40AM | Jan 19 2016 4:36PM | Jan 19 2016 6:40PM | Jan 19 2016 8:45PM | 51.925 | 50.175 | 52.65 | 0.00 | 23.954 | 27.971 | 26.221 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
X9/Ya-1 | SGBM03 | Jan 19 2016 11:00AM | Jan 19 2016 6:00PM | Jan 19 2016 8:55PM | Jan 19 2016 7:50PM | 55.872 | 55.075 | 56.53 | 0.00 | 27.932 | 27.940 | 27.143 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12+6 | - | 17.3 | 27.0 | -100.0 | G35T2 | 4620 4622 4626 | 10 8 9
P/52-1 | SGBM23 | Jan 16 2016 4:50PM | Jan 19 2016 10:15AM | Jan 19 2016 3:20PM | Jan 19 2016 5:51PM | 51.953 | 50.175 | 52.81 | 0.00 | 16.112 | 35.841 | 34.063 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 29.0 | -21.7 | G45T2 | 1 2 3 4 | 8 10 8 3
P/53-2 | SGBM08 | Jan 16 2016 5:10PM | Jan 19 2016 10:30AM | Jan 19 2016 1:25PM | Jan 19 2016 2:47PM | 52.041 | 50.175 | 52.75 | 0.00 | 15.946 | 36.095 | 34.229 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.8 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 10 8
N/58-2 | SGBM05 | Jan 12 2016 11:55AM | Jan 18 2016 5:40PM | Jan 18 2016 9:35PM | Jan 18 2016 11:32PM | 52.052 | 50.175 | 52.93 | 0.00 | 17.132 | 34.920 | 33.043 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 27.0 | -100.0 | G45T2 | 1 2 3 | 9 8 10
P/50-1 | SGBM23 | Jan 16 2016 5:30PM | Jan 18 2016 3:45PM | Jan 18 2016 8:20PM | Jan 18 2016 9:31PM | 51.911 | 51.175 | 52.42 | 0.00 | 17.322 | 34.589 | 33.853 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 8 9
X10/Ya-1 | SGBM03 | Jan 16 2016 8:30AM | Jan 18 2016 11:20AM | Jan 18 2016 7:05PM | Jan 18 2016 9:22PM | 55.963 | 55.075 | 56.67 | 0.00 | 27.770 | 28.193 | 27.305 |  | 0.0 | 0.0 | 0.0 | 14T32+7T25 | - | - | T16-90+T12-250 | - | - | - | 12 | - | 17.4 | 27.0 | -100.0 | G35T2 | 1 2 3 | 9 10 8
U/57-1 | SGBM17 | Jan 18 2016 8:32AM | Jan 18 2016 1:10PM | Jan 18 2016 6:50PM | Jan 18 2016 8:00PM | 51.859 | 50.175 | 52.71 | 0.00 | 23.811 | 28.048 | 26.364 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
U/58-1 | SGBM17 | Jan 18 2016 8:23AM | Jan 18 2016 3:30PM | Jan 18 2016 4:55PM | Jan 18 2016 6:20PM | 51.986 | 50.175 | 52.82 | 0.00 | 23.218 | 28.768 | 26.957 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 21.0 | -100.0 | G45T2 | 4544 4546 4547 | 7 7 7
U/52-1 | SGBM17 | Jan 18 2016 8:23AM | Jan 18 2016 1:20PM | Jan 18 2016 4:20PM | Jan 18 2016 5:30PM | 52.599 | 50.175 | 51.83 | 0.00 | 22.930 | 29.669 | 27.245 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
U/53-2 | SGBM19 | Jan 16 2016 3:49PM | Jan 18 2016 12:25PM | Jan 18 2016 2:35PM | Jan 18 2016 3:30PM | 51.835 | 50.175 | 52.64 | 0.00 | 23.840 | 27.995 | 26.335 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
R/53-2 | SGBM05 | Jan 13 2016 5:00PM | Jan 16 2016 11:05AM | Jan 16 2016 9:00PM | Jan 16 2016 10:15PM | 51.898 | 50.175 | 52.58 | 0.00 | 16.777 | 35.121 | 33.398 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 10 7
N/53-1 | SGBM08 | Jan 15 2016 2:30PM | Jan 16 2016 11:45AM | Jan 16 2016 7:20PM | Jan 16 2016 9:15PM | 52.048 | 50.175 | 52.78 | 0.00 | 15.985 | 36.063 | 34.190 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.8 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
U/54-2 | SGBM19 | Jan 15 2016 4:39PM | Jan 16 2016 2:30PM | Jan 16 2016 4:40PM | Jan 16 2016 6:00PM | 51.827 | 50.175 | 52.75 | 0.00 | 23.746 | 28.081 | 26.429 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | -100.0 | G45T2 | PJ4492 PJ4493 PJ4494 | 7 7 7
R/52-2 | SGBM05 | Jan 13 2016 4:45PM | Jan 15 2016 4:35PM | Jan 15 2016 11:35PM | Jan 16 2016 1:23AM | 51.884 | 49.775 | 52.64 | 0.00 | 16.442 | 35.442 | 33.333 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
R/37-1 | SGBM20 | Jan 15 2016 10:00AM | Jan 15 2016 5:15PM | Jan 15 2016 8:05PM | Jan 15 2016 9:33PM | 52.802 | 50.175 | 53.55 | 0.00 | 29.651 | 23.151 | 20.524 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
W/46-1 | SGBM19 | Jan 15 2016 9:34AM | Jan 15 2016 1:40PM | Jan 15 2016 7:05PM | Jan 15 2016 8:35PM | 49.911 | 47.425 | 50.73 | 0.00 | 21.333 | 28.578 | 26.092 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 21.0 | -100.0 | G45T2 | PJ4443 PJ4445 PJ4446 | 7 7 7
M5/60-1 | SGBM08 | Jan 13 2016 4:13PM | Jan 15 2016 10:55AM | Jan 15 2016 5:35PM | Jan 15 2016 7:30PM | 51.802 | 51.375 | 52.35 | 0.00 | 18.248 | 33.554 | 33.127 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 24.0 | 13.9 | G45T2 | 1 2 3 | 8 8 8
Ua/45-2 | SGBM23 | Jan 15 2016 8:35AM | Jan 15 2016 12:47PM | Jan 15 2016 6:15PM | Jan 15 2016 7:00PM | 51.148 | 50.125 | 52.08 | 0.00 | 24.084 | 27.064 | 26.041 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
Ua/39-2 | SGBM23 | Jan 14 2016 3:25PM | Jan 15 2016 10:00AM | Jan 15 2016 11:00AM | Jan 15 2016 12:20PM | 52.595 | 50.125 | 52.81 | 0.00 | 23.109 | 29.486 | 27.016 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 22.0 | 28.0 | G35T2 | 1 2 3 | 8 7 7
R/51-1 | SGBM05 | Jan 13 2016 4:30PM | Jan 14 2016 3:50PM | Jan 15 2016 1:15AM | Jan 15 2016 2:50AM | 51.881 | 49.775 | 52.45 | 0.00 | 16.554 | 35.327 | 33.221 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 27.0 | -100.0 | G45T2 | 1 2 3 | 8 10 9
N/52-1 | SGBM05 | Jan 12 2016 12:45PM | Jan 14 2016 10:55AM | Jan 15 2016 12:05AM | Jan 15 2016 1:35AM | 52.041 | 49.575 | 52.85 | 0.00 | 15.553 | 36.488 | 34.022 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.6 | 26.0 | 20.1 | G45T2 | 1 2 3 | 8 10 8
M6/60-1 | SGBM08 | Jan 13 2016 4:50PM | Jan 14 2016 2:15PM | Jan 14 2016 6:40PM | Jan 14 2016 8:33PM | 51.864 | 51.375 | 52.52 | 0.00 | 18.122 | 33.742 | 33.253 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
Z1/56b-1 | SGBM23 | Dec 13 2015 3:13PM | Jan 14 2016 3:55PM | Jan 14 2016 5:00PM | Jan 14 2016 7:50PM | 49.454 | 48.475 | 50.29 | 0.00 | 17.190 | 32.264 | 31.285 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 27.0 | -100.0 | G35T2 | 1 2 3 4 | 8 8 8 3
R/37-3 | SGBM20 | Jan 13 2016 5:00PM | Jan 14 2016 12:00PM | Jan 14 2016 12:35PM | Jan 14 2016 2:12PM | 52.64 | 50.175 | 53.53 | 0.00 | 29.930 | 22.710 | 20.245 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 18.0 | 39.7 | G45T2 | 1 2 | 10 8
M4/60a-1 | SGBM08 | Jan 11 2016 9:00AM | Jan 13 2016 4:25PM | Jan 13 2016 9:05PM | Jan 13 2016 10:25PM | 51.836 | 51.375 | 52.66 | 0.00 | 14.556 | 37.280 | 36.819 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.4 | 25.0 | 6.7 | G45T2 | 1 2 3 | 10 7 8
V/61-2 | SGBM17 | Jan 12 2016 4:36PM | Jan 13 2016 5:59PM | Jan 13 2016 7:10PM | Jan 13 2016 9:30PM | 49.517 | 47.575 | 50.42 | 0.00 | 19.915 | 29.602 | 27.660 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.6 | 24.0 | -100.0 | G45T2 | 1 2 3 | 10 7 7
N/38-1 | SGBM20 | Jan 12 2016 8:10AM | Jan 12 2016 11:53AM | Jan 12 2016 9:25PM | Jan 12 2016 10:35PM | 51.987 | 50.175 | 52.69 | 0.00 | 29.690 | 22.297 | 20.485 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 17.0 | -13.0 | G45T2 | 1 2 3 | 6 6 5
Ua/45-1 | SGBM31 | Jan 12 2016 10:19AM | Jan 12 2016 5:45PM | Jan 12 2016 8:25PM | Jan 12 2016 9:55PM | 51.829 | 50.125 | 52.49 | 0.00 | 24.089 | 27.740 | 26.036 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
M6/61-1 | SGBM08 | Jan 11 2016 8:25AM | Jan 12 2016 9:35AM | Jan 12 2016 7:15PM | Jan 12 2016 9:10PM | 51.854 | 51.375 | 52.36 | 0.00 | 21.164 | 30.690 | 30.211 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 22.0 | 14.5 | G35T2 | 1 2 3 | 8 7 7
N/53-2 | SGBM23 | Jan 11 2016 2:55PM | Jan 12 2016 10:15AM | Jan 12 2016 4:35PM | Jan 12 2016 6:30PM | 52.068 | 50.175 | 52.80 | 0.00 | 15.800 | 36.268 | 34.375 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
W/46-2 | SGBM31 | Jan 11 2016 9:36AM | Jan 12 2016 12:40PM | Jan 12 2016 4:30PM | Jan 12 2016 6:05PM | 50.005 | 47.425 | 50.75 | 0.00 | 22.154 | 27.851 | 25.271 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
R/37-2 | SGBM20 | Jan 12 2016 10:30AM | Jan 12 2016 2:00PM | Jan 12 2016 5:00PM | Jan 12 2016 5:58PM | 52.7 | 50.175 | 53.59 | 0.00 | 30.086 | 22.614 | 20.089 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 17.0 | -100.0 | G45T2 | 1 2 | 7 10
N/36-2 | SGBM20 | Jan 11 2016 2:30PM | Jan 12 2016 10:18AM | Jan 12 2016 11:45AM | Jan 12 2016 12:41PM | 52.006 | 49.725 | 52.73 | 0.00 | 32.434 | 19.572 | 17.291 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.0 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
M7/55-1 | SGBM15 | Jan 9 2016 11:35AM | Jan 11 2016 1:15PM | Jan 11 2016 8:10PM | Jan 11 2016 10:32PM | 52.031 | 50.925 | 52.83 | 0.00 | 15.628 | 36.403 | 35.297 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 5 10 10
AA/56a-1 | SGBM05 | Jan 11 2016 9:08AM | Jan 11 2016 5:30PM | Jan 11 2016 8:00PM | Jan 11 2016 10:00PM | 49.379 | 48.475 | 50.35 | 0.00 | 17.349 | 32.030 | 31.126 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 19.8 | 25.0 | -100.0 | G35T2 | 1 2 3 | 9 11 5
N/38-2 | SGBM20 | Jan 11 2016 9:00AM | Jan 11 2016 2:15PM | Jan 11 2016 7:00PM | Jan 11 2016 8:25PM | 51.93 | 50.175 | 52.72 | 0.00 | 29.922 | 22.008 | 20.253 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 17.0 | -100.0 | G45T2 | 1 2 | 10 7
V/61-1 | SGBM17 | Jan 9 2016 10:23AM | Jan 11 2016 11:45AM | Jan 11 2016 12:25PM | Jan 11 2016 2:45PM | 49.493 | 47.575 | 50.37 | 0.00 | 20.167 | 29.326 | 27.408 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.4 | 27.0 | -100.0 | G45T2 | 1 2 4 4 | 8 8 8 3
Ua/39-1 | SGBM23 | Jan 9 2016 10:36AM | Jan 9 2016 3:40PM | Jan 9 2016 11:05PM | Jan 10 2016 12:15AM | 52.261 | 50.125 | 52.91 | 0.00 | 23.111 | 29.150 | 27.014 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
M7/53-1 | SGBM01 | Jan 9 2016 11:10AM | Jan 9 2016 5:10PM | Jan 9 2016 9:50PM | Jan 9 2016 11:47PM | 52.03 | 50.925 | 52.57 | 0.00 | 16.670 | 35.360 | 34.255 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.8 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
N/50-1 | SGBM01 | Jan 6 2016 6:25PM | Jan 9 2016 10:15AM | Jan 9 2016 5:15PM | Jan 9 2016 8:55PM | 51.723 | 51.375 | 52.56 | 0.00 | 15.058 | 36.665 | 36.317 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.1 | 27.0 | 16.8 | G45T2 | 1 2 3 | 7 7 13
Ua/43-2 | SGBM19 | Jan 9 2016 8:07AM | Jan 9 2016 3:17PM | Jan 9 2016 4:45PM | Jan 9 2016 8:35PM | 51.893 | 50.125 | 52.77 | 0.00 | 23.073 | 28.820 | 27.052 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 23.0 | -100.0 | G45T2 | 1 2 3 | 7 8 8
AA/56b-1 | SGBM05 | Jan 8 2016 3:37PM | Jan 9 2016 12:50PM | Jan 9 2016 3:10PM | Jan 9 2016 4:50PM | 49.474 | 48.475 | 50.40 | 0.00 | 17.398 | 32.076 | 31.077 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 19.8 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
N/36-1 | SGBM16 | Jan 8 2016 5:00PM | Jan 9 2016 11:00AM | Jan 9 2016 1:20PM | Jan 9 2016 2:14PM | 51.76 | 49.725 | 52.53 | 0.00 | 32.535 | 19.225 | 17.190 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.9 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Ua/42-2 | SGBM19 | Jan 8 2016 8:20AM | Jan 8 2016 5:10PM | Jan 8 2016 9:44PM | Jan 9 2016 12:00AM | 52.008 | 50.125 | 52.78 | 0.00 | 22.078 | 29.930 | 28.047 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 24.0 | 34.5 | G45T2 | PJ4174 PJ4179 PJ4183 | 8 8 8
Ua/44-2 | SGBM22 | Jan 8 2016 8:10AM | Jan 8 2016 4:50PM | Jan 8 2016 7:19PM | Jan 8 2016 9:08PM | 51.958 | 50.125 | 52.73 | 0.00 | 23.034 | 28.924 | 27.091 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 24.0 | 39.2 | G45T2 | PJ4157 PJ4161 PJ4167 | 8 8 8
U/36-1 | SGBM20 | Jan 8 2016 8:00AM | Jan 8 2016 12:30PM | Jan 8 2016 5:20PM | Jan 8 2016 5:52PM | 52.242 | 51.375 | 53.01 | 0.00 | 27.812 | 24.430 | 23.563 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.0 | 18.0 | -15.0 | G45T2 | 1 2 | 8 10
N/52-2 | SGBM01 | Jan 6 2016 6:20PM | Jan 7 2016 3:45PM | Jan 7 2016 11:25PM | Jan 8 2016 1:57AM | 51.985 | 49.575 | 52.85 | 0.00 | 15.152 | 36.833 | 34.423 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 8 10
R/36-2 | SGBM20 | Jan 7 2016 9:00AM | Jan 7 2016 4:05PM | Jan 7 2016 7:35PM | Jan 7 2016 8:43PM | 52.47 | 49.725 | 53.00 | 0.00 | 30.200 | 75.270 | 19.525 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.4 | 16.0 | 28.8 | G45T2 | 1 2 | 8 8
G/30-1a | SGBM16 | Jan 7 2016 8:00AM | Jan 7 2016 4:45PM | Jan 7 2016 6:30PM | Jan 7 2016 7:37PM | 52.266 | 49.575 | 53.07 | 0.00 | 29.468 | 22.798 | 20.107 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 18.0 | -100.0 | G35T2 | 1 2 | 8 10
Ua/38-2 | SGBM23 | Jan 7 2016 8:34AM | Jan 7 2016 1:05PM | Jan 7 2016 5:10PM | Jan 7 2016 6:30PM | 52.573 | 50.125 | 53.20 | 0.00 | 24.704 | 27.869 | 25.421 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.2 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
G/30-1b | SGBM16 | Jan 7 2016 8:45AM | Jan 7 2016 1:00PM | Jan 7 2016 5:00PM | Jan 7 2016 6:13PM | 52.266 | 49.575 | 52.56 | 0.00 | 29.363 | 75.466 | 20.212 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 17.0 | -100.0 | G35T2 | 1 2 | 9 8
AA/60-1 | SGBM23 | Jan 6 2016 11:00AM | Jan 7 2016 1:40PM | Jan 7 2016 3:47PM | Jan 7 2016 5:30PM | 49.679 | 47.075 | 50.42 | 0.00 | 12.923 | 36.756 | 34.152 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 26.0 | -100.0 | G35T2 | 4090 4092 4094 | 10 8 8
Z1/56a-1 | SGBM23 | Jan 6 2016 10:20AM | Jan 7 2016 8:15AM | Jan 7 2016 1:35PM | Jan 7 2016 3:15PM | 49.502 | 48.475 | 50.38 | 0.00 | 17.376 | 32.126 | 31.099 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 19.8 | 24.0 | 4.2 | G35T2 | 1 2 3 | 8 8 8
Ua/43-1 | SGBM17 | Jan 6 2016 8:15AM | Jan 6 2016 7:22PM | Jan 6 2016 11:00PM | Jan 7 2016 12:40AM | 52.949 | 50.125 | 52.72 | 0.00 | 23.119 | 29.830 | 27.006 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 23.0 | -100.0 | G45T2 | PJ4068 PJ4070 PJ4075 | 8 8 7
M7/51-1 | SGBM01 | Jan 5 2016 5:45PM | Jan 6 2016 4:35PM | Jan 6 2016 8:40PM | Jan 6 2016 10:23PM | 51.846 | 50.775 | 52.72 | 0.00 | 16.915 | 34.931 | 33.860 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 9 7
Ua/44-1 | SGBM19 | Jan 6 2016 8:50AM | Jan 6 2016 2:18PM | Jan 6 2016 7:28PM | Jan 6 2016 9:45PM | 51.965 | 50.125 | 52.72 | 0.00 | 23.124 | 28.841 | 27.001 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 25.0 | -100.0 | G45T2 | C480014604 C520124663 C4800114612 | 7 9 9
N/34-2 | SGBM16 | Jan 6 2016 1:00PM | Jan 6 2016 3:30PM | Jan 6 2016 5:37PM | Jan 6 2016 7:20PM | 51.93 | 50.175 | 52.51 | 0.00 | 33.513 | 18.417 | 16.662 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.6 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
Ma/51-1 | SGBM01 | Jan 5 2016 6:00PM | Jan 6 2016 10:00AM | Jan 6 2016 2:27PM | Jan 6 2016 3:46PM | 51.89 | 50.775 | 52.79 | 0.00 | 16.392 | 35.498 | 34.383 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 26.0 | -100.0 | G45T2 | 1 2 3 | 10 8 8
T/36-1 | SGBM20 | Jan 5 2016 1:45PM | Jan 6 2016 11:30AM | Jan 6 2016 1:44PM | Jan 6 2016 2:38PM | 52.382 | 51.375 | 53.19 | 0.00 | 29.095 | 23.287 | 22.280 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
N/35-2 | SGBM16 | Jan 5 2016 5:30PM | Jan 6 2016 10:30AM | Jan 6 2016 10:47AM | Jan 6 2016 11:50AM | 51.73 | 49.875 | 0.00 | 0.00 | -19.100 | 70.830 | 68.975 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 43.9 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
Y/51-1 | SGBM17 | Jan 5 2016 2:30PM | Jan 5 2016 8:00PM | Jan 6 2016 1:15AM | Jan 6 2016 3:10AM | 49.52 | 48.075 | 49.52 | 0.00 | 19.920 | 29.600 | 28.155 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 25.0 | -17.9 | G45T2 | PJ4021 PJ4022 PJ4023 | 8 10 7
Ua/42-1 | SGBM16 | Jan 4 2016 4:30PM | Jan 5 2016 12:15PM | Jan 5 2016 7:20PM | Jan 5 2016 9:00PM | 51.971 | 50.125 | 52.96 | 0.00 | 22.056 | 29.915 | 28.069 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 25.0 | 40.0 | G45T2 | 1 2 3 | 5 10 10
S/35-2 | SGBM20 | Jan 5 2016 1:00PM | Jan 5 2016 5:15PM | Jan 5 2016 7:20PM | Jan 5 2016 8:31PM | 52.32 | 49.725 | 53.15 | 0.00 | 29.246 | 23.074 | 20.479 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
T/33-1 | SGBM16 | Jan 5 2016 11:00AM | Jan 5 2016 5:25PM | Jan 5 2016 6:37PM | Jan 5 2016 7:44PM | 52.274 | 51.375 | 0.00 | 0.00 | -23.200 | 75.474 | 74.575 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 47.4 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
P/35-2 | SGBM20 | Jan 5 2016 1:00PM | Jan 5 2016 4:08PM | Jan 5 2016 4:25PM | Jan 5 2016 5:42PM | 51.93 | 49.875 | 52.74 | 0.00 | 33.540 | 18.390 | 16.335 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.4 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
N/34-1 | SGBM20 | Jan 4 2016 6:50PM | Jan 5 2016 10:17AM | Jan 5 2016 11:05AM | Jan 5 2016 12:32PM | 51.785 | 50.175 | 52.69 | 0.00 | 33.790 | 17.995 | 16.385 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.4 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
AA/56-1 | SGBM05 | Jan 4 2016 8:30AM | Jan 4 2016 3:35PM | Jan 4 2016 8:30PM | Jan 4 2016 10:26PM | 49.424 | 47.525 | 50.20 | 0.00 | 16.402 | 33.022 | 31.123 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.8 | 24.0 | -100.0 | G35T2 | PJ3935 PJ3937 PJ3941 | 8 8 8
P/34-1 | SGBM16 | Jan 4 2016 3:10PM | Jan 4 2016 5:50PM | Jan 4 2016 7:35PM | Jan 4 2016 8:50PM | 51.928 | 50.075 | 52.71 | 0.00 | 33.314 | 18.614 | 16.761 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.7 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
X/51-1 | SGBM22 | Jan 2 2016 4:20PM | Jan 4 2016 1:00PM | Jan 4 2016 4:55PM | Jan 4 2016 6:11PM | 49.502 | 48.075 | 50.37 | 0.00 | 21.870 | 27.632 | 26.205 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 25.0 | -100.0 | G45T2 | C520124608 C480014442 C520124609 | 12 11 2
N/35-1 | SGBM16 | Jan 4 2016 1:30PM | Jan 4 2016 3:40PM | Jan 4 2016 4:20PM | Jan 4 2016 5:30PM | 52.002 | 49.875 | 52.75 | 0.00 | 33.546 | 18.456 | 16.329 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.4 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
J/39-5 | SGBM23 | Jan 2 2016 5:00PM | Jan 2 2016 9:15PM | Jan 4 2016 12:50PM | Jan 4 2016 3:44PM | 51.979 | 50.675 | 52.93 | 0.00 | 23.427 | 28.552 | 27.248 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 23.0 | -17.3 | G45T2 | PJ3898 PJ3901 PJ3909 | 10 9 4
R/35-2 | SGBM16 | Jan 4 2016 11:00AM | Jan 4 2016 12:55PM | Jan 4 2016 2:10PM | Jan 4 2016 3:10PM | 52.338 | 49.875 | 53.11 | 0.00 | 31.714 | 20.624 | 18.161 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.6 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
R/31-1 | SGBM20 | Jan 4 2016 8:00AM | Jan 4 2016 10:30AM | Jan 4 2016 11:00AM | Jan 4 2016 12:30PM | 51.994 | 51.375 | 52.67 | 0.00 | 29.875 | 22.119 | 21.500 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.7 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
S/35-1 | SGBM16 | Jan 2 2016 1:30PM | Jan 2 2016 6:00PM | Jan 2 2016 9:35PM | Jan 2 2016 10:33PM | 52.265 | 49.725 | 53.19 | 0.00 | 29.588 | 22.677 | 20.137 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 17.0 | -100.0 | G45T2 | 1 2 | 8 9
T/35-1 | SGBM20 | Dec 31 2015 7:00PM | Jan 2 2016 5:00PM | Jan 2 2016 7:11PM | Jan 2 2016 8:12PM | 52.27 | 51.375 | 0.00 | 0.00 | -24.000 | 76.270 | 75.375 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 48.0 | 18.0 | -62.5 | G45T2 | 1 2 | 10 8
T/34-1 | SGBM20 | Jan 2 2016 8:00AM | Jan 2 2016 1:00PM | Jan 2 2016 6:08PM | Jan 2 2016 6:52PM | 52.42 | 51.375 | 53.18 | 0.00 | 29.977 | 22.443 | 21.398 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
P/34-2 | SGBM01 | Dec 31 2015 4:30PM | Jan 2 2016 10:55AM | Jan 2 2016 3:55PM | Jan 2 2016 4:35PM | 50.075 | 50.075 | 52.67 | 0.00 | 33.470 | 16.605 | 16.605 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.6 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Y/51-2 | SGBM22 | Dec 31 2015 8:00AM | Jan 2 2016 11:00AM | Jan 2 2016 2:30PM | Jan 2 2016 4:18PM | 49.635 | 48.075 | 50.29 | 0.00 | 20.889 | 28.746 | 27.186 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 23.0 | -17.3 | G45T2 | PJ3849 PJ3852 PJ3855 | 8 8 7
Ma/60-2 | SGBM08 | Dec 31 2015 4:25PM | Jan 2 2016 9:45AM | Jan 2 2016 11:30AM | Jan 2 2016 1:15PM | 51.882 | 49.875 | 52.73 | 0.00 | 14.430 | 37.452 | 35.445 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.6 | 26.0 | -22.6 | G45T2 | PJ3837 PJ3838 PJ3839 | 10 8 8
Qa/21-2 | SGBM16 | Dec 31 2015 10:35AM | Dec 31 2015 4:48PM | Jan 1 2016 12:55AM | Jan 1 2016 2:30AM | 50.525 | 50.075 | 51.40 | 0.00 | 26.496 | 24.029 | 23.579 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.0 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
R/32-2 | SGBM20 | Dec 31 2015 2:20PM | Dec 31 2015 6:05PM | Dec 31 2015 11:45PM | Jan 1 2016 1:01AM | 52.127 | 49.875 | 52.97 | 0.00 | 28.670 | 23.457 | 21.205 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
S/25-2 | SGBM16 | Dec 31 2015 9:50AM | Dec 31 2015 2:00PM | Dec 31 2015 11:25PM | Jan 1 2016 12:47AM | 50.691 | 47.425 | 51.44 | 0.00 | 29.139 | 21.552 | 18.286 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.6 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
W/51-1 | SGBM17 | Dec 31 2015 8:20AM | Dec 31 2015 1:30PM | Dec 31 2015 8:05PM | Dec 31 2015 9:15PM | 49.376 | 47.625 | 50.21 | 0.00 | 21.514 | 27.862 | 26.111 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 26.0 | -100.0 | G45T2 | C480014337 C480014338 C480014340 | 5 10 11
T/27-1 | SGBM01 | Dec 31 2015 8:00AM | Dec 31 2015 12:49PM | Dec 31 2015 7:23PM | Dec 31 2015 8:20PM | 52.154 | 51.375 | 0.00 | 0.00 | -20.100 | 72.254 | 71.475 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 45.5 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
T/28-1 | SGBM01 | Dec 31 2015 9:30AM | Dec 31 2015 3:14PM | Dec 31 2015 5:43PM | Dec 31 2015 6:39PM | 52.083 | 51.375 | 52.83 | 0.00 | 32.628 | 19.455 | 18.747 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.9 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
AA/56-2 | SGBM17 | Dec 30 2015 1:20PM | Dec 31 2015 1:27PM | Dec 31 2015 4:30PM | Dec 31 2015 6:10PM | 49.445 | 47.525 | 50.28 | 0.00 | 16.675 | 32.770 | 30.850 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.6 | 26.0 | -100.0 | G35T2 | C480014316 C480014317 C480014321 | 11 11 4
T/31-1 | SGBM20 | Dec 29 2015 5:45PM | Dec 31 2015 1:52PM | Dec 31 2015 2:40PM | Dec 31 2015 5:02PM | 52.078 | 51.375 | 0.00 | 0.00 | -22.000 | 74.078 | 73.375 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 46.7 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 9 7
T/32-1 | SGBM20 | Dec 29 2015 5:00PM | Dec 31 2015 9:35AM | Dec 31 2015 2:07PM | Dec 31 2015 3:26PM | 52.174 | 51.375 | 53.06 | 0.00 | 31.062 | 21.112 | 20.313 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 17.0 | 31.5 | G45T2 | 1 2 | 8 9
M/44-1 | SGBM15 | Dec 30 2015 11:28AM | Dec 31 2015 9:20AM | Dec 31 2015 1:30PM | Dec 31 2015 3:00PM | 51.9 | 50.575 | 52.56 | 0.00 | 22.255 | 29.645 | 28.320 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 22.0 | -100.0 | G45T2 | PJ3782 PJ3783 PJ3787 | 8 7 7
J/39-4 | SGBM23 | Dec 30 2015 8:00AM | Dec 30 2015 1:10PM | Dec 31 2015 4:22AM | Dec 31 2015 5:23AM | 51.99 | 50.675 | 52.84 | 0.00 | 24.137 | 27.853 | 26.538 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 18.0 | -16.9 | G45T2 | PJ3771 PJ3772 | 8 10
M/40-1 | SGBM15 | Dec 30 2015 8:20AM | Dec 30 2015 5:21PM | Dec 31 2015 3:05AM | Dec 31 2015 4:16AM | 51.884 | 50.575 | 52.80 | 0.00 | 24.301 | 27.583 | 26.274 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 18.0 | -16.7 | G45T2 | PJ3768 PJ3770 | 10 8
Ua/38-1 | SGBM16 | Dec 30 2015 2:20PM | Dec 30 2015 6:40PM | Dec 31 2015 2:30AM | Dec 31 2015 4:05AM | 52.412 | 50.125 | 53.24 | 0.00 | 25.125 | 27.287 | 25.000 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.9 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
J/39-8 | SGBM23 | Dec 30 2015 8:45AM | Dec 30 2015 2:00PM | Dec 31 2015 2:20AM | Dec 31 2015 4:03AM | 51.996 | 50.675 | 52.65 | 0.00 | 23.647 | 28.349 | 27.028 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 18.0 | -17.2 | G45T2 | Pending PJ3766 | 8 10
K/47-2 | SGBM23 | Dec 30 2015 1:50PM | Dec 30 2015 7:03PM | Dec 31 2015 12:00AM | Dec 31 2015 2:43AM | 51.537 | 50.375 | 52.35 | 0.00 | 19.150 | 32.387 | 31.225 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 22.0 | -19.9 | G45T2 | PJ3752 PJ3754 PJ3761 | 8 7 7
N/33-1 | SGBM20 | Dec 30 2015 10:00AM | Dec 30 2015 3:48PM | Dec 30 2015 9:55PM | Dec 30 2015 11:30PM | 52.04 | 50.175 | 52.70 | 0.00 | 32.202 | 19.838 | 17.973 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.4 | 15.0 | -100.0 | G45T2 | 1 2 | 10 5
S/25-1 | SGBM01 | Dec 30 2015 9:00AM | Dec 30 2015 5:44PM | Dec 30 2015 9:25PM | Dec 30 2015 10:51PM | 50.478 | 47.425 | 51.50 | 0.00 | 29.004 | 21.474 | 18.421 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.7 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
Qa/21-1 | SGBM01 | Dec 29 2015 6:30PM | Dec 30 2015 1:00PM | Dec 30 2015 6:30PM | Dec 30 2015 8:07PM | 50.793 | 50.075 | 51.44 | 0.00 | 28.939 | 21.854 | 21.136 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 17.0 | -100.0 | G35T2 | 1 2 | 10 7
X/46-1 | SGBM22 | Dec 29 2015 9:15AM | Dec 29 2015 3:23PM | Dec 29 2015 11:55PM | Dec 30 2015 1:39AM | 49.649 | 48.775 | 50.41 | 0.00 | 22.010 | 27.639 | 26.765 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.0 | 20.0 | -100.0 | G35T2 | PJ3709 PJ3711 PJ3713 | 8 6 6
R/35-1 | SGBM03 | Dec 28 2015 2:15PM | Dec 29 2015 4:19PM | Dec 30 2015 12:05AM | Dec 30 2015 1:17AM | 52.26 | 49.875 | 53.03 | 0.00 | 31.728 | 20.532 | 18.147 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.5 | 17.0 | -11.5 | G45T2 | 1 2 | 8 9
M/47-1 | SGBM08 | Dec 28 2015 1:30PM | Dec 29 2015 4:36PM | Dec 29 2015 10:55PM | Dec 30 2015 12:18AM | 51.68 | 50.575 | 52.58 | 0.00 | 18.885 | 32.795 | 31.690 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 23.0 | -20.2 | G45T2 | PJ3702 PJ3705 PJ3708 | 8 8 7
Z/62-1 | SGBM17 | Dec 28 2015 4:30PM | Dec 29 2015 6:00PM | Dec 29 2015 10:00PM | Dec 29 2015 11:53PM | 49.664 | 47.705 | 50.51 | 0.00 | 15.911 | 33.753 | 31.794 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.2 | 27.0 | -100.0 | G45T2 | PJ3697 PJ3698 PJ3706 | 10 9 8
M/37-1 | SGBM15 | Dec 29 2015 9:50AM | Dec 29 2015 1:23PM | Dec 29 2015 9:36PM | Dec 29 2015 11:10PM | 51.821 | 51.375 | 52.74 | 0.00 | 32.144 | 19.677 | 19.231 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 15.0 | 22.6 | G45T2 | PJ3694 PJ3699 | 8 7
T/29-1 | SGBM01 | Dec 29 2015 8:00AM | Dec 29 2015 7:00PM | Dec 29 2015 9:30PM | Dec 29 2015 10:01PM | 52.035 | 51.375 | 52.79 | 0.00 | 31.790 | 20.245 | 19.585 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 16.0 | -12.5 | G45T2 | 1 2 | 8 8
T/30-1 | SGBM01 | Dec 29 2015 10:10AM | Dec 29 2015 3:48PM | Dec 29 2015 7:00PM | Dec 29 2015 9:02PM | 52.026 | 51.375 | 52.72 | 0.00 | 30.720 | 74.026 | 20.655 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 16.0 | -13.1 | G45T2 | 1 2 | 8 8
R/5-1 | SGBM21 | Dec 28 2015 10:00AM | Dec 29 2015 12:17PM | Dec 29 2015 6:03PM | Dec 29 2015 8:21PM | 55.686 | 55.075 | 56.36 | 0.00 | 27.963 | 27.523 | 27.112 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 23.0 | -100.0 | G35T2 | 1 2 3 | 8 8 7
Ma/60-1 | SGBM23 | Dec 28 2015 1:50PM | Dec 29 2015 1:01PM | Dec 29 2015 4:46PM | Dec 29 2015 6:11PM | 51.818 | 49.875 | 52.62 | 0.00 | 14.815 | 37.003 | 35.060 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 25.0 | -22.3 | G45T2 | PJ3665 PJ3668 PJ3671 | 7 8 10
Z/61-2 | SGBM17 | Dec 28 2015 6:30PM | Dec 29 2015 1:19PM | Dec 29 2015 4:17PM | Dec 29 2015 6:10PM | 49.533 | 46.505 | 50.37 | 0.00 | 13.865 | 35.668 | 32.640 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.8 | 25.0 | -100.0 | G45T2 | PJ3661 PJ3663 PJ3669 | 8 10 7
N/27-1 | SGBM01 | Dec 28 2015 4:15PM | Dec 28 2015 9:30PM | Dec 29 2015 10:33AM | Dec 29 2015 11:26AM | 51.984 | 51.075 | 0.00 | 0.00 | -22.000 | 73.984 | 73.075 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 46.5 | 17.0 | -100.0 | G45T2 | 1 2 | 8 9
W/51-2 | SGBM22 | Dec 28 2015 10:45AM | Dec 28 2015 6:05PM | Dec 29 2015 1:36AM | Dec 29 2015 3:55AM | 49.478 | 47.625 | 50.07 | 0.00 | 21.173 | 28.305 | 26.452 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 22.0 | -100.0 | G45T2 | PJ3634 PJ3635 PJ3636 | 7 8 7
X/51-2 | SGBM05 | Dec 28 2015 1:30PM | Dec 28 2015 7:56PM | Dec 29 2015 12:27AM | Dec 29 2015 2:15AM | 49.478 | 48.075 | 50.17 | 0.00 | 21.271 | 28.207 | 26.804 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 22.0 | -100.0 | G45T2 | PJ3631 PJ3632 PJ3633 | 8 7 7
J/39-3 | SGBM15 | Dec 28 2015 9:00AM | Dec 28 2015 2:05PM | Dec 28 2015 10:27PM | Dec 29 2015 12:11AM | 51.964 | 50.675 | 52.90 | 0.00 | 24.401 | 27.563 | 26.274 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 19.0 | -100.0 | G45T2 | PJ3624 PJ3627 | 10 9
N/33-2 | SGBM20 | Dec 26 2015 5:40PM | Dec 28 2015 11:30AM | Dec 28 2015 9:30PM | Dec 28 2015 10:46PM | 51.998 | 50.175 | 52.86 | 0.00 | 32.856 | 19.142 | 17.319 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.0 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
J/39-2 | SGBM15 | Dec 28 2015 8:45AM | Dec 28 2015 12:40PM | Dec 28 2015 8:53PM | Dec 28 2015 10:14PM | 51.92 | 50.675 | 51.92 | 0.00 | 23.520 | 28.400 | 27.155 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 19.0 | 10.0 | G45T2 | PJ3616 PJ3619 | 10 9
R/5-2 | SGBM21 | Dec 28 2015 10:45AM | Dec 28 2015 3:00PM | Dec 28 2015 7:42PM | Dec 28 2015 9:30PM | 55.75 | 55.075 | 56.42 | 0.00 | 28.019 | 84.150 | 27.056 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
J/47-1 | SGBM08 | Dec 26 2015 4:40PM | Dec 28 2015 1:24PM | Dec 28 2015 4:50PM | Dec 28 2015 7:55PM | 51.59 | 50.375 | 52.13 | 0.00 | 17.732 | 33.858 | 32.643 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.8 | 24.0 | 15.6 | G45T2 | PJ3586 PJ3590 PJ3595 PJ3605 | 8 7 7 2
Y/51-3 | SGBM05 | Dec 26 2015 3:20PM | Dec 28 2015 2:18PM | Dec 28 2015 4:16PM | Dec 28 2015 6:27PM | 49.578 | 48.075 | 50.36 | 0.00 | 19.159 | 30.419 | 28.916 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.4 | 28.0 | 106.5 | G45T2 | PJ3583 PJ3585 PJ3588 PJ3593 | 8 8 7 5
Ua/35-1 | SGBM16 | Dec 28 2015 8:15AM | Dec 28 2015 11:50AM | Dec 28 2015 4:25PM | Dec 28 2015 6:20PM | 52.218 | 51.3725 | 53.03 | 0.00 | 29.325 | 22.893 | 22.047 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.0 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
P/32-2 | SGBM20 | Dec 26 2015 6:15PM | Dec 28 2015 9:48AM | Dec 28 2015 2:31PM | Dec 28 2015 3:32PM | 52.077 | 49.875 | 52.82 | 0.00 | 29.720 | 22.357 | 20.155 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
R/21-1 | SGBM03 | Dec 26 2015 5:44PM | Dec 28 2015 9:00AM | Dec 28 2015 10:54AM | Dec 28 2015 12:20PM | 50.528 | 47.875 | 0.00 | 0.00 | -24.600 | 75.128 | 72.475 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 46.1 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
Z/55-1 | SGBM19 | Dec 23 2015 4:30PM | Dec 26 2015 5:15PM | Dec 26 2015 7:51PM | Dec 26 2015 9:20PM | 49.564 | 47.625 | 50.43 | 0.00 | 18.226 | 31.338 | 29.399 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 23.0 | -100.0 | G45T2 | PJ3547 PJ3549 PJ3553 | 8 8 7
Z/54-1 | SGBM19 | Dec 26 2015 8:00AM | Dec 26 2015 12:32PM | Dec 26 2015 2:45PM | Dec 26 2015 4:37PM | 49.484 | 47.425 | 50.05 | 0.00 | 18.347 | 31.137 | 29.078 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 8 7
S/30-1 | SGBM03 | Dec 23 2015 3:00PM | Dec 23 2015 6:35PM | Dec 26 2015 3:45PM | Dec 26 2015 4:32PM | 51.997 | 51.375 | 52.78 | 0.00 | 32.180 | 19.817 | 19.195 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 16.0 | -100.0 | G45T2 | 1 2 | 9 7
Z/45-1 | SGBM16 | Dec 22 2015 2:10PM | Dec 26 2015 5:00PM | Dec 26 2015 2:45PM | Dec 26 2015 4:13PM | 49.484 | 47.425 | 50.05 | 0.00 | 18.347 | 31.137 | 29.078 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G45T2 | PJ3512 PJ3515 PJ3517 | 8 8 7
P/31-1 | SGBM20 | Dec 24 2015 1:05PM | Dec 24 2015 4:15PM | Dec 26 2015 1:41PM | Dec 26 2015 3:20PM | 52.051 | 51.375 | 52.93 | 0.00 | 31.134 | 20.917 | 20.241 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 19.0 | -100.0 | G45T2 | 1 2 3 | 8 8 3
P/26-1 | SGBM20 | Dec 24 2015 4:45PM | Dec 25 2015 11:40AM | Dec 26 2015 11:45AM | Dec 26 2015 12:47PM | 52 | 51.275 | 52.82 | 0.00 | 32.124 | 19.876 | 19.151 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
N/29-1 | SGBM20 | Dec 24 2015 10:40AM | Dec 25 2015 8:18AM | Dec 25 2015 2:38PM | Dec 25 2015 3:47PM | 51.903 | 51.075 | 52.70 | 0.00 | 30.700 | 21.203 | 20.375 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 18.0 | -100.0 | G45T2 | 1 2 3 | 8 8 2
N/28-1 | SGBM20 | Dec 24 2015 10:00AM | Dec 24 2015 1:45PM | Dec 25 2015 1:27PM | Dec 25 2015 2:20PM | 51.928 | 51.075 | 52.51 | 0.00 | 30.810 | 21.118 | 20.265 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
R/21-2 | SGBM20 | Dec 23 2015 8:00AM | Dec 23 2015 3:36PM | Dec 24 2015 12:44PM | Dec 24 2015 2:17PM | 80.357 | 47.875 | 51.15 | 0.00 | 26.247 | 54.110 | 21.628 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.8 | 19.0 | -100.0 | G45T2 | 1 2 3 | 8 7 4
K/44-3 | SGBM23 | Dec 23 2015 1:55PM | Dec 23 2015 9:30PM | Dec 24 2015 1:14AM | Dec 24 2015 2:53AM | 51.787 | 50.375 | 52.67 | 0.00 | 21.065 | 30.722 | 29.310 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 24.0 | -18.6 | G45T2 | C520124369 C520124370 C520124371 | 10 10 4
X/51-3 | SGBM19 | Dec 22 2015 10:20AM | Dec 23 2015 2:51PM | Dec 24 2015 12:53AM | Dec 24 2015 2:45AM | 49.28 | 48.075 | 50.13 | 0.00 | 22.029 | 27.251 | 26.046 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 20.0 | -100.0 | G45T2 | C520124367 C520124372 | 8 12
W/51-3 | SGBM22 | Dec 22 2015 10:00AM | Dec 23 2015 12:47PM | Dec 23 2015 11:04PM | Dec 24 2015 1:40AM | 49.182 | 47.625 | 49.92 | 0.00 | 21.521 | 27.661 | 26.104 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 25.0 | -100.0 | G45T2 | C480013953 C520124360 C520124367 | 11 12 2
S/21-1 | SGBM20 | Dec 22 2015 6:10PM | Dec 23 2015 11:44AM | Dec 23 2015 10:46PM | Dec 24 2015 12:26AM | 50.371 | 47.425 | 51.03 | 0.00 | 26.232 | 24.139 | 21.193 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
J/39-6 | SGBM15 | Dec 22 2015 5:10PM | Dec 23 2015 12:49PM | Dec 23 2015 9:29PM | Dec 23 2015 11:50PM | 51.925 | 50.675 | 52.67 | 0.00 | 24.370 | 27.555 | 26.305 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 22.0 | -100.0 | G45T2 | C520124355 C520124356 C520124359 | 10 2 10
R/32-1 | SGBM01 | Dec 22 2015 12:04PM | Dec 23 2015 10:47AM | Dec 23 2015 7:39PM | Dec 23 2015 9:41PM | 52.007 | 49.875 | 52.63 | 0.00 | 28.630 | 23.277 | 21.245 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
P/32-1 | SGBM01 | Dec 23 2015 9:30AM | Dec 23 2015 12:00PM | Dec 23 2015 1:55PM | Dec 23 2015 3:10PM | 52.055 | 49.875 | 52.90 | 0.00 | 30.702 | 21.353 | 19.173 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
Z/53-2 | SGBM16 | Dec 22 2015 1:20PM | Dec 22 2015 8:50PM | Dec 23 2015 6:30AM | Dec 23 2015 9:24AM | 49.448 | 47.425 | 50.33 | 0.00 | 18.331 | 31.117 | 29.094 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 26.0 | -100.0 | G45T2 | C480013883 C480013885 C520124340 | 6 10 10
K/47-1 | SGBM23 | Dec 22 2015 4:45PM | Dec 22 2015 7:34PM | Dec 23 2015 6:00AM | Dec 23 2015 7:30AM | 51.57 | 50.375 | 52.45 | 0.00 | 18.746 | 32.824 | 31.629 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.1 | 23.0 | 4.4 | G45T2 | 1 2 3 | 10 11 2
M/42-1 | SGBM08 | Dec 21 2015 3:00PM | Dec 22 2015 7:30PM | Dec 23 2015 6:12AM | Dec 23 2015 7:00AM | 51.85 | 50.575 | 52.48 | 0.00 | 24.183 | 27.667 | 26.392 |  | 0.0 | 0.0 | 0.0 | 16T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 19.0 | 25.1 | G35T2 | 1 2 | 11 8
K/46-3 | SGBM23 | Dec 22 2015 4:50PM | Dec 22 2015 10:30PM | Dec 23 2015 3:25AM | Dec 23 2015 5:00AM | 51.58 | 50.075 | 52.51 | 0.00 | 19.009 | 33.500 | 31.066 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.8 | 23.0 | 16.4 | G45T2 | 1 2 3 | 3 10 10
M/43-1 | SGBM08 | Dec 21 2015 4:10PM | Dec 22 2015 5:00PM | Dec 23 2015 1:17AM | Dec 23 2015 2:35AM | 51.897 | 50.575 | 52.80 | 0.00 | 23.398 | 28.499 | 27.177 |  | 0.0 | 0.0 | 0.0 | 16T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 20.0 | 15.7 | G35T2 | 1 2 | 10 10
S/34-2 | SGBM01 | Dec 22 2015 11:25AM | Dec 22 2015 3:49PM | Dec 23 2015 12:53AM | Dec 23 2015 2:26AM | 52.202 | 49.725 | 53.12 | 0.00 | 29.624 | 22.578 | 20.101 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 20.0 | -100.0 | G45T2 | 1 2 | 11 9
P/35-1 | SGBM01 | Dec 21 2015 7:25PM | Dec 22 2015 10:20AM | Dec 22 2015 3:17PM | Dec 22 2015 4:05PM | 51.826 | 49.875 | 0.00 | 0.00 | -19.000 | 70.826 | 68.875 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 43.8 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
K/44-1 | SGBM23 | Dec 19 2015 8:01PM | Dec 21 2015 10:15PM | Dec 22 2015 1:58PM | Dec 22 2015 3:25PM | 51.835 | 50.375 | 52.68 | 0.00 | 21.183 | 30.652 | 29.192 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 24.0 | 29.2 | G45T2 | 1 2 3 | 8 9 7
Z/55-3 | SGBM17 | Dec 21 2015 3:00PM | Dec 21 2015 9:25PM | Dec 22 2015 3:04AM | Dec 22 2015 5:40AM | 49.495 | 47.625 | 50.20 | 0.00 | 17.697 | 31.798 | 29.928 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.0 | 31.0 | -100.0 | G45T2 | C480013789 C520124305 C480013791 | 10 10 11
Z/54-2 | SGBM05 | Dec 18 2015 1:40PM | Dec 21 2015 7:00PM | Dec 22 2015 1:26AM | Dec 22 2015 3:25AM | 49.51 | 47.425 | 50.37 | 0.00 | 18.367 | 31.143 | 29.058 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | 29.8 | G45T2 | C480013781 C480013783 C480013786 | 9 10 5
AA/59-1 | SGBM22 | Dec 19 2015 9:20AM | Dec 21 2015 9:30PM | Dec 22 2015 1:05AM | Dec 22 2015 2:40AM | 49.829 | 48.475 | 50.61 | 0.00 | 14.312 | 35.517 | 34.163 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 31.0 | -100.0 | G35T2 | 1 2 3 | 10 10 11
Z/60-2 | SGBM16 | Dec 21 2015 10:00AM | Dec 21 2015 5:30PM | Dec 21 2015 10:17PM | Dec 22 2015 1:30AM | 49.63 | 46.505 | 50.37 | 0.00 | 13.465 | 36.165 | 33.040 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 31.0 | -100.0 | G45T2 | PJ3471 PJ3472 PJ3474 PJ3476 PJ3477 | 7 8 6 6 4
N/32-1 | SGBM01 | Dec 21 2015 6:00PM | Dec 21 2015 8:40PM | Dec 21 2015 10:30PM | Dec 22 2015 12:30AM | 51.876 | 49.875 | 52.75 | 0.00 | 32.749 | 19.127 | 17.126 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.9 | 17.0 | -100.0 | G45T2 | 1 2 | 6 11
Q/30-1 | SGBM01 | Dec 21 2015 3:00PM | Dec 21 2015 5:55PM | Dec 21 2015 8:34PM | Dec 21 2015 9:57PM | 51.696 | 51.375 | 52.59 | 0.00 | 30.994 | 20.702 | 20.381 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
R/30-1 | SGBM01 | Dec 19 2015 6:00PM | Dec 21 2015 3:45PM | Dec 21 2015 6:59PM | Dec 21 2015 7:52PM | 51.724 | 51.375 | 52.44 | 0.00 | 30.839 | 20.885 | 20.536 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 16.0 | -13.1 | G45T2 | 1 2 | 8 8
Z/60-1 | SGBM17 | Dec 19 2015 9:00AM | Dec 19 2015 4:00PM | Dec 19 2015 9:54PM | Dec 20 2015 7:10AM | 49.586 | 46.505 | 50.21 | 0.00 | 13.314 | 36.272 | 33.191 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 31.0 | -100.0 | G45T2 | C520124232 C520124234 C480013709 | 10 10 11
R/29-1 | SGBM01 | Dec 19 2015 5:00PM | Dec 19 2015 7:33PM | Dec 20 2015 12:26AM | Dec 20 2015 1:32AM | 51.836 | 51.375 | 52.53 | 0.00 | 32.126 | 19.710 | 19.249 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 17.0 | -100.0 | G45T2 | 1 2 | 10 7
Ka/62-1 | SGBM08 | Dec 19 2015 8:51AM | Dec 19 2015 5:15PM | Dec 19 2015 10:44PM | Dec 20 2015 12:40AM | 52.026 | 49.775 | 52.78 | 0.00 | 11.483 | 40.543 | 38.292 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.4 | 29.0 | -100.0 | G45T2 | 1 2 3 | 11 6 12
Ma/54-1 | SGBM23 | Dec 19 2015 9:10AM | Dec 19 2015 5:15PM | Dec 19 2015 10:26PM | Dec 19 2015 11:55PM | 51.856 | 51.375 | 52.66 | 0.00 | 16.260 | 35.596 | 35.115 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 24.0 | 7.4 | G45T2 | 1 2 3 | 10 10 4
Z/61-1 | SGBM19 | Dec 19 2015 8:33AM | Dec 19 2015 4:00PM | Dec 19 2015 9:05PM | Dec 19 2015 10:25PM | 49.684 | 46.505 | 50.44 | 0.00 | 13.540 | 36.144 | 32.965 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 22.0 | 4.9 | G45T2 | C520124229 C520124231 | 10 12
P/30-1 | SGBM01 | Dec 18 2015 11:00AM | Dec 19 2015 4:15PM | Dec 19 2015 8:22PM | Dec 19 2015 9:37PM | 51.909 | 51.375 | 52.67 | 0.00 | 31.270 | 20.639 | 20.105 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 16.0 | -100.0 | G45T2 | 1 2 | 12 4
J/39-7 | SGBM15 | Dec 18 2015 10:56AM | Dec 19 2015 11:50AM | Dec 19 2015 6:15PM | Dec 19 2015 7:13PM | 51.9 | 50.675 | 52.65 | 0.00 | 24.651 | 27.249 | 26.024 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 23.0 | -100.0 | G45T2 | 1 2 | 12 11
Ma/53-1 | SGBM23 | Dec 19 2015 9:50AM | Dec 19 2015 12:55PM | Dec 19 2015 4:18PM | Dec 19 2015 5:30PM | 51.86 | 51.375 | 52.67 | 0.00 | 16.865 | 34.995 | 34.510 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.0 | 26.0 | 18.4 | G45T2 | 1 2 3 | 6 10 10
Ma/52-1 | SGBM23 | Dec 18 2015 10:38AM | Dec 19 2015 9:30AM | Dec 19 2015 3:03PM | Dec 19 2015 5:00PM | 51.977 | 51.375 | 52.78 | 0.00 | 17.276 | 34.701 | 34.099 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 27.0 | -100.0 | G45T2 | 1 2 3 | 11.5 11.5 4
X10/Y2-1 | SGBM21 | Dec 18 2015 4:45PM | Dec 19 2015 9:00AM | Dec 19 2015 1:55PM | Dec 19 2015 3:57PM | 55.747 | 55.075 | 56.34 | 0.00 | 26.139 | 29.608 | 28.936 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.4 | 26.0 | -100.0 | G35T2 | 1 2 3 | 10 8 8
S/27-1 | SGBM03 | Dec 17 2015 3:35PM | Dec 18 2015 9:50PM | Dec 19 2015 11:22AM | Dec 19 2015 12:09PM | 52.108 | 51.375 | 52.75 | 0.00 | 32.752 | 19.356 | 18.623 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.8 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
AA/58-1 | SGBM16 | Dec 18 2015 4:30PM | Dec 18 2015 9:25PM | Dec 19 2015 2:42AM | Dec 19 2015 5:05AM | 49.642 | 48.475 | 50.56 | 0.00 | 15.361 | 34.281 | 33.114 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 30.0 | -100.0 | G35T2 | 1 2 3 4 | 10 8 8 4
J/39-1 | SGBM15 | Dec 18 2015 10:08AM | Dec 18 2015 8:30PM | Dec 18 2015 11:56PM | Dec 19 2015 1:12AM | 51.772 | 50.675 | 52.61 | 0.00 | 24.514 | 27.258 | 26.161 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 19.0 | 14.1 | G45T2 | 1 2 3 | 7 6 6
R/20-3 | SGBM20 | Dec 18 2015 8:00AM | Dec 18 2015 12:14PM | Dec 18 2015 11:37PM | Dec 19 2015 1:08AM | 54.357 | 50.475 | 55.09 | 0.00 | 30.294 | 24.063 | 20.181 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
N/20-2 | SGBM20 | Dec 18 2015 1:00PM | Dec 18 2015 4:35PM | Dec 18 2015 9:03PM | Dec 18 2015 10:30PM | 54.167 | 51.575 | 54.82 | 0.00 | 30.420 | 23.747 | 21.155 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
H/40-3 | SGBM15 | Dec 18 2015 9:35AM | Dec 18 2015 6:45PM | Dec 18 2015 9:38PM | Dec 18 2015 10:20PM | 51.824 | 50.375 | 52.41 | 0.00 | 23.311 | 28.513 | 27.064 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
Z/53-1 | SGBM17 | Dec 18 2015 9:30AM | Dec 18 2015 6:00PM | Dec 18 2015 8:06PM | Dec 18 2015 10:01PM | 49.478 | 47.425 | 50.23 | 0.00 | 17.227 | 32.251 | 30.198 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 23.0 | -100.0 | G45T2 | PJ3377 PJ3380 PJ3385 | 8 8 7
X/57-1 | SGBM17 | Dec 17 2015 9:00AM | Dec 18 2015 4:30PM | Dec 18 2015 5:51PM | Dec 18 2015 8:15PM | 49.5 | 48.075 | 50.38 | 0.00 | 19.378 | 30.122 | 28.697 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 28.0 | -100.0 | G45T2 | PJ3365 PJ3366 PJ3368 PJ3375 | 8 7 7 6
S/32-2 | SGBM01 | Dec 17 2015 1:00PM | Dec 18 2015 10:40AM | Dec 18 2015 6:45PM | Dec 18 2015 7:59PM | 52.119 | 49.725 | 52.72 | 0.00 | 28.520 | 23.599 | 21.205 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 | 10 7
K/46-2 | SGBM15 | Dec 17 2015 1:23PM | Dec 17 2015 8:50PM | Dec 18 2015 3:53PM | Dec 18 2015 6:00PM | 51.56 | 50.075 | 52.54 | 0.00 | 18.836 | 32.724 | 31.239 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 25.0 | 15.7 | G45T2 | 1 2 3 4 | 8 8 7 2
S/34-1 | SGBM20 | Dec 17 2015 1:45PM | Dec 17 2015 9:08PM | Dec 18 2015 3:02PM | Dec 18 2015 4:07PM | 52.187 | 49.725 | 0.00 | 0.00 | -26.000 | 78.187 | 75.725 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 48.2 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
K/44-2 | SGBM15 | Dec 17 2015 1:43PM | Dec 17 2015 5:55PM | Dec 17 2015 3:42AM | Dec 18 2015 6:35AM | 51.955 | 50.375 | 52.70 | 0.00 | 21.099 | 30.856 | 29.276 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 3
W/62-1 | SGBM22 | Dec 17 2015 9:10AM | Dec 17 2015 3:38PM | Dec 18 2015 2:30AM | Dec 18 2015 5:00AM | 49.672 | 49.075 | 50.72 | 0.00 | 23.015 | 26.657 | 26.060 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 24.0 | -100.0 | G45T2 | PJ3329 PJ3331 PJ3336 | 8 8 8
N/32-2 | SGBM01 | Dec 17 2015 6:00PM | Dec 17 2015 8:25PM | Dec 18 2015 1:15AM | Dec 18 2015 2:05AM | 52.043 | 49.875 | 53.01 | 0.00 | 32.709 | 19.334 | 17.166 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.9 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Q/32-1 | SGBM20 | Dec 17 2015 1:00PM | Dec 17 2015 4:07PM | Dec 17 2015 11:04PM | Dec 18 2015 12:20AM | 52.102 | 51.075 | 52.95 | 0.00 | 30.954 | 21.148 | 20.121 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
R/20-1 | SGBM03 | Dec 17 2015 1:00PM | Dec 17 2015 4:50PM | Dec 17 2015 8:02PM | Dec 17 2015 9:10PM | 54.3 | 50.475 | 55.00 | 0.00 | 30.300 | 24.000 | 20.175 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
K/41-2 | SGBM08 | Dec 16 2015 5:36PM | Dec 17 2015 3:56PM | Dec 17 2015 7:32PM | Dec 17 2015 8:55PM | 51.85 | 50.375 | 52.65 | 0.00 | 23.846 | 28.004 | 26.529 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
Z/55-2 | SGBM19 | Dec 16 2015 4:06PM | Dec 17 2015 2:10PM | Dec 17 2015 5:44PM | Dec 17 2015 8:30PM | 49.534 | 47.625 | 50.42 | 0.00 | 18.618 | 30.916 | 29.007 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G45T2 | PJ3279 PJ3285 PJ3291 | 10 6 6
K/39-3 | SGBM08 | Dec 16 2015 4:31PM | Dec 16 2015 9:40PM | Dec 17 2015 2:15PM | Dec 17 2015 4:40PM | 51.845 | 50.375 | 52.50 | 0.00 | 26.100 | 25.745 | 24.275 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.4 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
X/62-1 | SGBM22 | Dec 16 2015 9:20AM | Dec 16 2015 2:24PM | Dec 17 2015 12:50AM | Dec 17 2015 2:40AM | 49.954 | 49.075 | 50.60 | 0.00 | 20.195 | 29.759 | 28.880 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.4 | 22.0 | -100.0 | G45T2 | PJ3241 PJ3243 PJ3247 | 7 8 7
K/37-1 | SGBM08 | Dec 15 2015 8:44PM | Dec 16 2015 3:20PM | Dec 17 2015 12:18AM | Dec 17 2015 1:30AM | 51.954 | 51.375 | 52.78 | 0.00 | 31.076 | 20.878 | 20.299 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 14.0 | 1.1 | G45T2 | 1 2 | 7 7
S/32-1 | SGBM01 | Dec 16 2015 10:30AM | Dec 16 2015 5:30PM | Dec 16 2015 10:46PM | Dec 17 2015 12:16AM | 51.989 | 49.725 | 52.85 | 0.00 | 28.555 | 23.334 | 21.170 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
Z/56-2 | SGBM19 | Dec 15 2015 6:00PM | Dec 16 2015 3:00PM | Dec 16 2015 7:12PM | Dec 16 2015 10:45PM | 49.387 | 46.175 | 50.13 | 0.00 | 13.828 | 35.559 | 32.347 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.6 | 25.0 | 21.5 | G45T2 | PJ3209 PJ3210 PJ3214 | 9 8 8
K/36-1 | SGBM08 | Dec 15 2015 9:30PM | Dec 16 2015 10:30AM | Dec 16 2015 9:00PM | Dec 16 2015 10:00PM | 52.034 | 51.375 | 52.87 | 0.00 | 32.965 | 19.069 | 18.410 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.7 | 14.0 | -100.0 | G45T2 | 1 2 | 7 7
Y/62-1 | SGBM19 | Dec 16 2015 8:00AM | Dec 16 2015 3:00PM | Dec 16 2015 8:09PM | Dec 16 2015 9:40PM | 49.837 | 49.075 | 50.61 | 0.00 | 19.013 | 30.824 | 30.062 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.1 | 22.0 | -100.0 | G45T2 | PJ3213 PJ3215 PJ3217 | 7 8 7
R/27-1 | SGBM01 | Dec 15 2015 8:00AM | Dec 15 2015 9:38PM | Dec 16 2015 7:55PM | Dec 16 2015 9:06PM | 52.047 | 51.375 | 52.87 | 0.00 | 33.370 | 18.677 | 18.005 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.5 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
K/47-3 | SGBM15 | Dec 15 2015 10:15AM | Dec 15 2015 8:45PM | Dec 16 2015 7:00PM | Dec 16 2015 8:30PM | 51.471 | 50.375 | 52.39 | 0.00 | 18.988 | 32.483 | 31.387 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.0 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
P/27-1 | SGBM01 | Dec 15 2015 8:00AM | Dec 15 2015 3:30PM | Dec 16 2015 3:00PM | Dec 16 2015 3:58PM | 51.818 | 51.375 | 52.52 | 0.00 | 32.224 | 19.594 | 19.151 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
P/29-1 | SGBM01 | Dec 15 2015 11:30AM | Dec 15 2015 6:00PM | Dec 16 2015 1:30PM | Dec 16 2015 2:37PM | 51.9 | 51.375 | 52.76 | 0.00 | 31.262 | 21.500 | 20.113 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
F/38-1 | SGBM08 | Dec 15 2015 10:52AM | Dec 15 2015 7:00PM | Dec 15 2015 11:19PM | Dec 16 2015 12:25AM | 52.068 | 51.375 | 52.62 | 0.00 | 26.015 | 26.053 | 25.360 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 20.0 | 24.0 | G45T2 | 1 2 3 | 7 7 6
Q/29-1 | SGBM01 | Dec 15 2015 8:00AM | Dec 15 2015 10:46AM | Dec 15 2015 10:02PM | Dec 15 2015 11:55PM | 52 | 51.375 | 56.61 | 0.00 | 35.206 | 16.794 | 16.169 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.3 | 18.0 | -100.0 | G45T2 | 1 2 | 11 7
Y/55-2 | SGBM19 | Dec 15 2015 9:10AM | Dec 15 2015 4:10PM | Dec 15 2015 10:08PM | Dec 15 2015 11:55PM | 49.324 | 48.075 | 50.13 | 0.00 | 19.027 | 30.297 | 29.048 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -18.5 | G45T2 | PJ3167 PJ3169 PJ3170 | 8 6 8
X/55-1 | SGBM22 | Dec 15 2015 8:00AM | Dec 15 2015 4:21PM | Dec 15 2015 8:13PM | Dec 15 2015 9:58PM | 49.491 | 48.075 | 50.35 | 0.00 | 20.854 | 28.637 | 27.221 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 23.0 | -17.3 | G45T2 | PJ3155 PJ3156 PJ3161 | 8 8 7
N/20-1 | SGBM03 | Dec 15 2015 10:30AM | Dec 15 2015 5:44PM | Dec 15 2015 7:41PM | Dec 15 2015 9:10PM | 54.555 | 51.575 | 55.24 | 0.00 | 30.339 | 24.216 | 21.236 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
F/42-1 | SGBM23 | Dec 14 2015 5:16PM | Dec 15 2015 4:15PM | Dec 15 2015 7:18PM | Dec 15 2015 9:05PM | 51.936 | 51.375 | 52.55 | 0.00 | 20.847 | 31.089 | 30.528 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 22.0 | 13.3 | G45T2 | 1 2 3 | 7 8 7
K/39-2 | SGBM08 | Dec 14 2015 4:15PM | Dec 15 2015 9:30AM | Dec 15 2015 5:45PM | Dec 15 2015 7:00PM | 51.912 | 50.375 | 52.77 | 0.00 | 26.269 | 25.643 | 24.106 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.3 | 19.0 | 23.9 | G45T2 | 1 2 3 | 7 6 6
K/41-3 | SGBM15 | Dec 14 2015 3:40PM | Dec 15 2015 9:45AM | Dec 15 2015 4:31PM | Dec 15 2015 6:00PM | 51.824 | 50.375 | 52.73 | 0.00 | 23.926 | 27.898 | 26.449 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 21.0 | 24.8 | G45T2 | 1 2 3 | 7 7 7
W/56-1 | SGBM22 | Dec 14 2015 3:00PM | Dec 14 2015 9:50PM | Dec 15 2015 1:00AM | Dec 15 2015 4:20AM | 49.603 | 49.075 | 50.37 | 0.00 | 22.467 | 27.136 | 26.608 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 22.0 | -100.0 | G45T2 | C480013262 C480013271 | 11 11
Z/59-1 | SGBM19 | Dec 14 2015 8:30AM | Dec 14 2015 6:00PM | Dec 14 2015 11:30PM | Dec 15 2015 1:50AM | 49.543 | 47.425 | 50.38 | 0.00 | 14.285 | 35.258 | 33.140 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 22.0 | -100.0 | G45T2 | C480013254 C480013260 | 11 11
Z/58-1 | SGBM16 | Dec 14 2015 9:20AM | Dec 14 2015 5:28PM | Dec 14 2015 9:45PM | Dec 14 2015 11:00PM | 49.502 | 47.425 | 50.35 | 0.00 | 16.152 | 33.350 | 31.273 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 25.0 | -100.0 | G45T2 | PJ3104 PJ3106 PJ3108 PJ3109 | 8 7 8 2
N/18-1 | SGBM03 | Dec 14 2015 1:00PM | Dec 14 2015 4:45PM | Dec 14 2015 9:04PM | Dec 14 2015 10:41PM | 55.38 | 53.875 | 56.20 | 0.00 | 32.497 | 22.883 | 21.378 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
P/28-1 | SGBM01 | Dec 12 2015 5:15PM | Dec 14 2015 1:35PM | Dec 14 2015 7:30PM | Dec 14 2015 8:35PM | 51.991 | 51.375 | 52.82 | 0.00 | 32.218 | 19.773 | 19.157 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 15.0 | -100.0 | G45T2 | 1 2 | 10 5
Fa/36-1 | SGBM08 | Dec 12 2015 3:00PM | Dec 14 2015 3:00PM | Dec 14 2015 7:29PM | Dec 14 2015 8:15PM | 51.99 | 51.375 | 52.73 | 0.00 | 29.928 | 22.062 | 21.447 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 16.0 | 17.3 | G45T2 | 1 2 | 8 8
J/36-1 | SGBM08 | Dec 12 2015 12:31PM | Dec 12 2015 9:10PM | Dec 14 2015 6:11PM | Dec 14 2015 7:29PM | 52.016 | 51.375 | 52.70 | 0.00 | 31.800 | 72.916 | 19.575 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 15.0 | 20.4 | G45T2 | 1 2 | 8 7
Q/27-1 | SGBM01 | Dec 12 2015 6:20PM | Dec 14 2015 10:30AM | Dec 14 2015 4:20PM | Dec 14 2015 5:12PM | 52.106 | 51.375 | 52.79 | 0.00 | 32.294 | 19.812 | 19.081 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.1 | 15.0 | 23.6 | G45T2 | 1 2 | 10 5
X/55-2 | SGBM19 | Dec 11 2015 6:00PM | Dec 12 2015 6:25PM | Dec 13 2015 5:25AM | Dec 13 2015 7:05AM | 49.627 | 48.075 | 50.33 | 0.00 | 20.326 | 29.301 | 27.749 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.7 | 21.0 | -100.0 | G45T2 | PJ3076 PJ3079 PJ3080 | 7 7 7
J/37-1 | SGBM08 | Dec 12 2015 11:49AM | Dec 12 2015 5:55PM | Dec 13 2015 5:12AM | Dec 13 2015 6:15AM | 51.967 | 51.375 | 52.75 | 0.00 | 30.053 | 74.667 | 21.322 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
Fa/37-1 | SGBM23 | Dec 12 2015 1:05PM | Dec 12 2015 5:00PM | Dec 13 2015 3:12AM | Dec 13 2015 4:55AM | 51.938 | 51.075 | 52.62 | 0.00 | 27.120 | 25.500 | 23.955 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.2 | 18.0 | 18.1 | G35T2 | 1 2 3 | 6 6 6
S/15-1 | SGBM03 | Dec 12 2015 1:00PM | Dec 12 2015 5:00PM | Dec 13 2015 3:05AM | Dec 13 2015 4:50AM | 56 | 53.275 | 56.69 | 0.00 | 31.090 | 24.910 | 22.185 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.1 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
Q/28-1 | SGBM01 | Dec 12 2015 4:30PM | Dec 12 2015 10:00PM | Dec 13 2015 1:04AM | Dec 13 2015 3:22AM | 52.067 | 51.375 | 52.77 | 0.00 | 32.273 | 72.567 | 19.102 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
K/45-1 | SGBM15 | Dec 12 2015 12:00PM | Dec 12 2015 4:51PM | Dec 12 2015 12:40AM | Dec 13 2015 2:15AM | 51.75 | 50.375 | 52.63 | 0.00 | 20.028 | 31.722 | 30.347 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 24.0 | 24.3 | G45T2 | 1 2 3 | 8 8 8
X10/Y4-1 | SGBM20 | Dec 12 2015 12:45PM | Dec 12 2015 8:42PM | Dec 12 2015 10:56PM | Dec 13 2015 1:50AM | 55.102 | 54.975 | 55.85 | 0.00 | 25.555 | 29.447 | 29.420 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 27.0 | -100.0 | G35T2 | 1 2 3 4 | 7 8 7 5
X/57-2 | SGBM22 | Dec 11 2015 6:00PM | Dec 12 2015 3:20PM | Dec 13 2015 12:00AM | Dec 13 2015 1:35AM | 49.67 | 48.075 | 50.37 | 0.00 | 20.571 | 29.099 | 27.504 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 22.0 | 25.7 | G45T2 | PJ3052 PJ3054 PJ3057 | 8 6 8
K/46-1 | SGBM15 | Dec 11 2015 11:52AM | Dec 12 2015 11:51AM | Dec 12 2015 10:30PM | Dec 13 2015 12:10AM | 51.67 | 50.075 | 52.61 | 0.00 | 19.806 | 31.864 | 30.269 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
Z/58-2 | SGBM16 | Dec 12 2015 9:20AM | Dec 12 2015 5:49PM | Dec 12 2015 8:44PM | Dec 12 2015 11:04PM | 49.602 | 47.425 | 50.56 | 0.00 | 15.260 | 34.342 | 32.165 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 30.0 | -100.0 | G45T2 | C480013185 C480013186 C480013190 | 10 10 10
X11/Y8-1 | SGBM21 | Dec 11 2015 8:00PM | Dec 12 2015 1:18PM | Dec 12 2015 7:38PM | Dec 12 2015 10:30PM | 55.791 | 55.075 | 56.42 | 0.00 | 28.416 | 83.791 | 26.659 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.0 | 22.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 6 2
N/18-2 | SGBM20 | Dec 12 2015 1:05PM | Dec 12 2015 4:50PM | Dec 12 2015 8:08PM | Dec 12 2015 9:32PM | 55.358 | 53.875 | 56.12 | 0.00 | 32.318 | 23.040 | 21.557 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.7 | 16.0 | -100.0 | G45T2 | 1 2 | 11 5
K/63a-1 | SGBM02 | Dec 11 2015 12:15PM | Dec 12 2015 3:00PM | Dec 12 2015 6:45PM | Dec 12 2015 9:00PM | 52.106 | 51.375 | 52.91 | 0.00 | 12.106 | 40.000 | 39.269 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.0 | 28.0 | 8.1 | G45T2 | 1 2 3 4 | 7 7 7 7
K/39-1 | SGBM23 | Dec 11 2015 8:00PM | Dec 12 2015 12:35PM | Dec 12 2015 7:44PM | Dec 12 2015 9:00PM | 51.951 | 50.375 | 52.60 | 0.00 | 25.004 | 79.251 | 25.371 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 20.0 | -16.1 | G45T2 | 1 2 | 9 11
Z/56-3 | SGBM19 | Dec 11 2015 12:12PM | Dec 12 2015 1:00PM | Dec 12 2015 6:11PM | Dec 12 2015 8:50PM | 49.538 | 46.175 | 50.28 | 0.00 | 14.281 | 35.257 | 31.894 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.3 | 25.0 | 23.2 | G45T2 | PJ3030 PJ3033 PJ3035 | 7 11 7
N/17-1 | SGBM03 | Dec 11 2015 4:00PM | Dec 12 2015 11:43AM | Dec 12 2015 3:58PM | Dec 12 2015 4:52PM | 55.694 | 53.875 | 56.51 | 0.00 | 30.707 | 24.987 | 23.168 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.7 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
R/25-2 | SGBM01 | Dec 11 2015 7:00PM | Dec 12 2015 11:47AM | Dec 12 2015 2:54PM | Dec 12 2015 4:00PM | 50.304 | 50.075 | 0.00 | 0.00 | -19.200 | 69.504 | 69.275 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 44.1 | 15.0 | -44.1 | G45T2 | 2 2 | 8 7
X/54-3 | SGBM22 | Dec 10 2015 6:26PM | Dec 11 2015 2:15PM | Dec 12 2015 3:00AM | Dec 12 2015 5:04AM | 49.482 | 48.075 | 50.38 | 0.00 | 20.978 | 28.504 | 27.097 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 20.0 | -100.0 | G45T2 | PJ3003 PJ3005 PJ3007 | 7 7 6
K/63-1 | SGBM02 | Dec 11 2015 11:45AM | Dec 11 2015 7:50PM | Dec 12 2015 12:15AM | Dec 12 2015 3:00AM | 52.094 | 51.375 | 52.89 | 0.00 | 12.094 | 40.000 | 39.281 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.0 | 27.0 | 12.0 | G45T2 | 1 2 3 4 | 7 7 6 7
J/48-7 | SGBM15 | Dec 11 2015 2:15PM | Dec 11 2015 7:15PM | Dec 11 2015 11:20PM | Dec 12 2015 12:45AM | 51.326 | 50.675 | 52.20 | 0.00 | 18.397 | 32.929 | 32.278 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 23.0 | 12.0 | G45T2 | 1 2 3 | 8 8 7
Y/54-3 | SGBM19 | Dec 10 2015 6:00PM | Dec 11 2015 1:15PM | Dec 11 2015 9:30PM | Dec 11 2015 11:55PM | 49.477 | 48.075 | 50.22 | 0.00 | 20.023 | 29.454 | 28.052 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 22.0 | -100.0 | G45T2 | PJ2977 PJ2979 PJ2985 | 8 7 7
Z/59-2 | SGBM17 | Dec 10 2015 7:10PM | Dec 11 2015 3:00PM | Dec 11 2015 6:25PM | Dec 11 2015 9:15PM | 49.755 | 47.425 | 50.58 | 0.00 | 14.375 | 35.380 | 33.050 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 27.0 | -100.0 | G45T2 | PJ2962 PJ2964 PJ2968 PJ2975 | 8 8 9 2
K/41-1 | SGBM15 | Dec 10 2015 8:30PM | Dec 11 2015 11:44AM | Dec 11 2015 6:35PM | Dec 11 2015 7:59PM | 51.954 | 50.375 | 52.63 | 0.00 | 23.833 | 28.121 | 26.542 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 20.0 | 18.4 | G45T2 | PJ2963 PJ2966 3 | 7 7 6
P/19-1 | SGBM20 | Dec 10 2015 6:14PM | Dec 11 2015 12:30PM | Dec 11 2015 6:00PM | Dec 11 2015 7:45PM | 55.78 | 51.575 | 47.60 | 0.00 | 31.095 | 24.685 | 20.480 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
X5/Y1-1 | SGBM18 | Dec 10 2015 3:30PM | Dec 11 2015 12:18PM | Dec 11 2015 4:23PM | Dec 11 2015 6:02PM | 55.549 | 54.475 | 47.24 37.24 | 0.00 0.00 | 20.443 | 35.106 | 34.032 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 29.0 | -100.0 | G35T2 | 1 2 3 | 11 10 8
Z/56-5 | SGBM19 | Dec 10 2015 9:50AM | Dec 10 2015 9:13PM | Dec 11 2015 5:28AM | Dec 11 2015 7:10AM | 49.562 | 46.175 | 50.40 | 0.00 | 14.904 | 34.658 | 31.271 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.9 | 23.0 | 50.8 | G45T2 | PJ2947 PJ2948 PJ2949 | 8 7 8
Ga/36-1 | SGBM15 | Dec 10 2015 1:50PM | Dec 10 2015 7:00PM | Dec 11 2015 1:07AM | Dec 11 2015 3:51AM | 52.062 | 51.075 | 53.04 | 0.00 | 30.339 | 21.723 | 20.736 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 18.0 | -100.0 | G45T2 | 1 2 3 | 8 8 2
Ga/37-1 | SGBM15 | Dec 10 2015 1:42PM | Dec 10 2015 9:00PM | Dec 10 2015 10:44PM | Dec 11 2015 1:15AM | 52.071 | 51.375 | 53.01 | 0.00 | 27.805 | 24.266 | 23.570 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.0 | 21.0 | -100.0 | G45T2 | 1 2 3 | 4 9 8
Z/56-1 | SGBM19 | Dec 10 2015 8:30AM | Dec 10 2015 7:55PM | Dec 10 2015 9:50PM | Dec 11 2015 12:40AM | 49.623 | 46.175 | 50.39 | 0.00 | 14.289 | 35.334 | 31.886 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.3 | 28.0 | 38.0 | G45T2 | PJ2920 PJ2922 PJ2923 PJ2928 | 8 3 9 8
W/53-1 | SGBM22 | Dec 10 2015 8:40AM | Dec 10 2015 3:30PM | Dec 10 2015 6:30PM | Dec 10 2015 8:05PM | 49.545 | 47.625 | 50.36 | 0.00 | 20.756 | 28.789 | 26.869 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 22.0 | -100.0 | G45T2 | PJ2901 PJ2903 PJ2906 | 7 8 7
X3/Y1-1 | SGBM18 | Dec 9 2015 10:15AM | Dec 10 2015 10:50AM | Dec 10 2015 4:35PM | Dec 10 2015 6:25PM | 55.634 | 54.475 | 47.15 30.15 | 0.00 0.00 | 21.446 | 34.700 | 33.029 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 30.0 | -100.0 | G35T2 | 1 2 3 4 | 8 7 8 7
K/43-1 | SGBM15 | Dec 9 2015 10:49AM | Dec 10 2015 12:28PM | Dec 10 2015 3:34PM | Dec 10 2015 5:41PM | 51.82 | 50.375 | 41.63 | 0.00 | 22.130 | 29.690 | 28.245 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 21.0 | 16.9 | G45T2 | PJ2890 PJ2892 PJ2895 | 7 7 7
K/45-3 | SGBM15 | Dec 9 2015 9:55AM | Dec 10 2015 10:00AM | Dec 10 2015 1:53PM | Dec 10 2015 3:20PM | 51.647 | 50.375 | 43.53 | 0.00 | 20.225 | 31.422 | 30.150 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.2 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
Y/56a-3 | SGBM17 | Dec 9 2015 10:40AM | Dec 9 2015 10:20PM | Dec 10 2015 2:39AM | Dec 10 2015 4:30AM | 49.578 | 46.175 | 50.44 | 0.00 | 17.941 | 31.637 | 28.234 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 28.0 | 10.0 | G45T2 | PJ2866 PJ2869 PJ2870 PJ2871 | 8 8 7 5
K/42-3 | SGBM08 | Dec 9 2015 10:09AM | Dec 9 2015 10:25PM | Dec 10 2015 2:27AM | Dec 10 2015 3:01AM | 51.82 | 50.375 | 43.40 | 0.00 | 43.405 | 28.515 | 6.970 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 4.4 | 22.0 | 45.2 | G45T2 | PJ2862 PJ2863 PJ2864 PJ2868 | 4 7 5 6
X/55-3 | SGBM22 | Dec 9 2015 10:40AM | Dec 9 2015 8:51PM | Dec 10 2015 12:16AM | Dec 10 2015 2:55AM | 49.52 | 48.075 | 50.47 | 0.00 | 19.674 | 29.846 | 28.401 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | -100.0 | G45T2 | PJ2852 PJ2855 PJ2860 | 8 8 7
J/48-3 | SGBM15 | Dec 9 2015 9:20AM | Dec 9 2015 7:33PM | Dec 9 2015 10:36PM | Dec 10 2015 1:24AM | 51.504 | 50.675 | 43.32 30.32 | 0.00 0.00 | 18.224 | 33.280 | 32.451 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.6 | 27.0 | 30.8 | G45T2 | PJ2843 PJ2844 PJ2845 PJ2856 | 7 9 8 3
X11/Y8-2 | SGBM21 | Dec 9 2015 11:30AM | Dec 9 2015 6:00PM | Dec 9 2015 11:20PM | Dec 10 2015 1:00AM | 55.694 | 55.075 | 47.69 | 0.00 | 29.094 | 26.600 | 25.981 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.5 | 22.0 | -100.0 | G35T2 | 1 2 3 | 8 7 7
Z/56-4 | SGBM19 | Dec 9 2015 11:30AM | Dec 9 2015 8:50PM | Dec 9 2015 11:00PM | Dec 10 2015 1:00AM | 49.6 | 46.175 | 50.45 | 0.00 | 14.552 | 35.048 | 31.623 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.1 | 26.0 | -100.0 | G45T2 | PJ2846 PJ2847 PJ2850 | 8 9 9
J/63-1 | SGBM02 | Dec 8 2015 8:22PM | Dec 9 2015 2:05PM | Dec 9 2015 9:50PM | Dec 10 2015 12:20AM | 51.979 | 51.275 | 43.83 | 0.00 | 43.829 | 41.150 | 7.446 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 4.7 | 30.0 | 47.7 | G45T2 | C480012952 C480012961 C480012964 | 10 10 10
Y/55-3 | SGBM17 | Dec 9 2015 11:35AM | Dec 9 2015 5:30PM | Dec 9 2015 7:42PM | Dec 9 2015 10:40PM | 49.447 | 48.075 | 50.29 | 0.00 | 18.786 | 30.661 | 29.289 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 26.0 | -100.0 | G45T2 | PJ2830 PJ2832 PJ2837 PJ2842 | 9 7 7 3
P/18-2 | SGBM20 | Dec 8 2015 10:30AM | Dec 9 2015 7:40PM | Dec 9 2015 9:05PM | Dec 9 2015 10:06PM | 55.684 | 53.875 | 47.53 | 0.00 | 32.527 | 23.157 | 21.348 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 18.0 | -100.0 | G45T2 | 1 2 | 9 9
X9/Y8-1 | SGBM21 | Dec 8 2015 2:00PM | Dec 9 2015 10:00AM | Dec 9 2015 8:23PM | Dec 9 2015 9:58PM | 55.655 | 55.075 | 47.37 35.37 | 0.00 0.00 | 29.966 | 25.689 | 25.109 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 20.0 | -100.0 | G35T2 | 1 2 3 | 7 7 6
X4/Y1-1 | SGBM18 | Dec 8 2015 3:05PM | Dec 9 2015 10:00AM | Dec 9 2015 5:47PM | Dec 9 2015 7:27PM | 55.559 | 54.775 | 47.10 26.10 | 0.00 0.00 | 20.603 | 34.956 | 34.172 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 28.0 | -21.7 | G35T2 | 1 2 3 4 | 7 6 7 8
N/19-1 | SGBM20 | Dec 8 2015 11:20AM | Dec 9 2015 1:30PM | Dec 9 2015 3:19PM | Dec 9 2015 4:42PM | 55.404 | 51.575 | 47.11 | 0.00 | 30.410 | 24.994 | 21.165 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
N/17-2 | SGBM20 | Dec 7 2015 4:50PM | Dec 9 2015 10:47AM | Dec 9 2015 11:55AM | Dec 9 2015 12:59PM | 55.646 | 53.875 | 47.39 | 0.00 | 30.487 | 81.546 | 23.388 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.9 | 19.0 | 4.1 | G45T2 | 1 2 3 | 7 7 5
X/57-3 | SGBM22 | Dec 8 2015 2:30PM | Dec 8 2015 10:00PM | Dec 9 2015 1:17AM | Dec 9 2015 3:40AM | 49.628 | 48.075 | 50.42 | 0.00 | 20.525 | 29.103 | 27.550 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 19.0 | 1.5 | G45T2 | PJ2794 PJ2796 PJ2797 | 7 6 6
K/43-3 | SGBM15 | Dec 8 2015 1:30PM | Dec 8 2015 9:20PM | Dec 9 2015 12:00AM | Dec 9 2015 1:25AM | 51.9 | 50.375 | 43.75 | 0.00 | 22.050 | 29.850 | 28.325 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 23.0 | -100.0 | G45T2 | PJ2791 PJ2792 PJ2793 | 7 8 8
Y/55a-4 | SGBM19 | Dec 7 2015 8:30AM | Dec 8 2015 4:00PM | Dec 8 2015 11:02PM | Dec 9 2015 1:15AM | 49.393 | 46.175 | 50.39 | 0.00 | 17.793 | 31.600 | 28.382 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | -100.0 | G45T2 | C480012886 C480012890 | 11.5 11.5
K/62-1 | SGBM02 | Dec 7 2015 1:50PM | Dec 8 2015 7:40PM | Dec 8 2015 9:20PM | Dec 9 2015 12:25AM | 52.031 | 51.375 | 43.66 37.66 22.66 | 0.00 0.00 0.00 | 12.258 | 39.773 | 39.117 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.9 | 28.0 | -100.0 | G45T2 | PJ2780 PJ2789 PJ2790 | 8 8 12
Y/56a-5 | SGBM19 | Dec 7 2015 3:30PM | Dec 8 2015 5:30PM | Dec 8 2015 9:30PM | Dec 8 2015 10:35PM | 49.417 | 46.175 | 50.31 | 0.00 | 17.406 | 32.011 | 28.769 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 23.0 | -100.0 | G45T2 | C480012877 C480012880 | 11.5 11.5
K/42-2 | SGBM15 | Dec 8 2015 1:05PM | Dec 8 2015 6:50PM | Dec 8 2015 8:36PM | Dec 8 2015 10:05PM | 51.85 | 50.375 | 43.82 35.82 | 0.00 0.00 | 23.223 | 28.627 | 27.152 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 22.0 | -100.0 | G45T2 | PJ2778 PJ2779 PJ2781 | 7 7 8
J/47-2 | SGBM15 | Dec 7 2015 10:20AM | Dec 8 2015 11:50AM | Dec 8 2015 6:31PM | Dec 8 2015 8:40PM | 51.67 | 50.375 | 42.50 | 0.00 | 18.202 | 33.468 | 32.173 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 24.0 | -100.0 | G45T2 | PJ2770 PJ2773 PJ2775 | 8 8 8
Ka/63-1 | SGBM02 | Dec 7 2015 1:10PM | Dec 8 2015 11:37AM | Dec 8 2015 4:15PM | Dec 8 2015 6:50PM | 52.133 | 49.775 | 44.03 24.03 | 0.00 0.00 | 11.627 | 41.506 | 38.148 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.3 | 28.0 | 15.4 | G35T2 | PJ2758 PJ2760 PJ2763 PJ2765 | 7 7 7 7
Pa/17-1 | SGBM03 | Dec 7 2015 8:00AM | Dec 8 2015 11:40AM | Dec 8 2015 5:20PM | Dec 8 2015 6:43PM | 55.864 | 55.075 | 47.63 | 0.00 | 33.832 | 22.032 | 21.243 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G35T2 | 1 2 3 | 6 6 5
S/15-2 | SGBM20 | Dec 5 2015 3:55PM | Dec 7 2015 8:51PM | Dec 8 2015 1:35PM | Dec 8 2015 3:10PM | 55.864 | 53.275 | 47.49 | 0.00 | 31.085 | 24.779 | 22.190 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.1 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
X5/Y8-1 | SGBM21 | Dec 7 2015 12:00PM | Dec 8 2015 10:57AM | Dec 8 2015 12:50PM | Dec 8 2015 2:35PM | 55.703 | 55.075 | 47.40 | 0.00 | 30.902 | 24.801 | 24.173 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.4 | 19.0 | 3.6 | G35T2 | 1 2 3 | 6 6 7
N/15-1 | SGBM03 | Dec 5 2015 5:00PM | Dec 7 2015 9:42PM | Dec 8 2015 12:05PM | Dec 8 2015 1:08PM | 55.753 | 53.425 | 47.56 | 0.00 | 28.057 | 27.696 | 25.368 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 20.0 | -16.1 | G45T2 | 1 2 3 | 7 7 6
Y/56a-1 | SGBM19 | Dec 7 2015 8:30AM | Dec 7 2015 7:27PM | Dec 8 2015 2:53AM | Dec 8 2015 4:50AM | 49.449 | 46.175 | 50.27 | 0.00 | 21.174 | 28.275 | 25.001 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.9 | 23.0 | -15.9 | G45T2 | C480012831 C480012832 | 11.5 11.5
J/48-8 | SGBM15 | Dec 7 2015 9:15AM | Dec 7 2015 6:20PM | Dec 8 2015 1:34AM | Dec 8 2015 3:05AM | 51.34 | 50.675 | 42.20 | 0.00 | 42.197 | 33.143 | 8.478 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 5.4 | 24.0 | 45.2 | G45T2 | C480012825 C480012826 C480012827 | 10 10 4
K/45-2 | SGBM15 | Dec 7 2015 8:30AM | Dec 7 2015 9:47PM | Dec 8 2015 12:33AM | Dec 8 2015 1:40AM | 51.673 | 50.375 | 43.67 | 0.00 | 20.365 | 31.308 | 30.010 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.1 | 23.0 | 67.6 | G45T2 | C480012821 c480012823 C480012824 | 9 4 10
W/53-3 | SGBM17 | Dec 7 2015 4:25PM | Dec 7 2015 10:00PM | Dec 8 2015 12:11AM | Dec 8 2015 1:15AM | 49.589 | 47.625 | 50.41 | 0.00 | 21.306 | 28.283 | 26.319 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 22.0 | -16.7 | G45T2 | C480012822 C480012823 | 11 11
J/48-4 | SGBM15 | Dec 7 2015 9:33AM | Dec 7 2015 3:10PM | Dec 7 2015 10:44PM | Dec 8 2015 12:40AM | 51.49 | 50.675 | 43.33 | 0.00 | 18.232 | 33.258 | 32.443 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.6 | 24.0 | 16.3 | G45T2 | C480002816 C480012817 C480012821 | 11 11 2
N/19-2 | SGBM03 | Dec 7 2015 8:00AM | Dec 7 2015 3:05PM | Dec 7 2015 7:57PM | Dec 7 2015 10:40PM | 55.105 | 51.575 | 46.76 31.76 | 0.00 0.00 | 30.464 | 24.641 | 21.111 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 19.0 | -100.0 | G45T2 | 1 2 3 | 6 7 6
Y/55a-3 | SGBM19 | Dec 5 2015 10:40AM | Dec 7 2015 1:40PM | Dec 7 2015 5:30PM | Dec 7 2015 7:40PM | 49.37 | 46.175 | 49.37 | 0.00 | 17.070 | 32.300 | 29.105 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G45T2 | PJ2711 PJ2713 PJ2716 | 8 8 7
R/25-1 | SGBM21 | Dec 4 2015 8:00AM | Dec 7 2015 12:25PM | Dec 7 2015 6:16PM | Dec 7 2015 7:18PM | 50.177 | 50.075 | 42.10 | 0.00 | 31.896 | 18.281 | 18.179 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.6 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
Y/56a-4 | SGBM19 | Dec 5 2015 9:00AM | Dec 5 2015 4:50PM | Dec 6 2015 3:46AM | Dec 6 2015 5:50AM | 49.501 | 46.175 | 50.44 | 0.00 | 17.938 | 31.563 | 28.237 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 23.0 | -100.0 | G45T2 | PJ2689 PJ2690 PJ2691 | 8 8 7
K/61-1 | SGBM02 | Dec 5 2015 12:30PM | Dec 5 2015 7:10PM | Dec 6 2015 12:58AM | Dec 6 2015 4:00AM | 51.99 | 51.375 | 42.80 | 0.00 | 12.202 | 39.788 | 39.173 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.9 | 30.0 | -100.0 | G45T2 | PJ2679 PJ2681 PJ2684 PJ2688 | 10 8 9 3
J/61-1 | SGBM02 | Dec 5 2015 11:45AM | Dec 5 2015 10:45PM | Dec 5 2015 10:59PM | Dec 6 2015 12:54AM | 51.972 | 51.375 | 42.86 | 0.00 | 11.264 | 40.708 | 40.111 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.5 | 28.0 | -100.0 | G45T2 | PJ2669 PJ2673 PJ2675 | 12 9 7
J/47-3 | SGBM15 | Dec 4 2015 9:14PM | Dec 5 2015 5:40PM | Dec 5 2015 8:58PM | Dec 5 2015 10:58PM | 51.682 | 50.375 | 43.65 | 0.00 | 18.146 | 33.536 | 32.229 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 25.0 | -100.0 | G45T2 | C480012734 C480012737 C480012738 | 10 10 5
Y/56a-8 | SGBM17 | Dec 5 2015 8:30AM | Dec 5 2015 4:55PM | Dec 5 2015 8:41PM | Dec 5 2015 10:55PM | 49.549 | 46.175 | 50.13 | 0.00 | 17.628 | 31.921 | 28.547 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 23.0 | -18.2 | G45T2 | PJ2659 PJ2661 PJ2664 | 4 12 7
R/22-2 | SGBM21 | Dec 4 2015 10:40AM | Dec 5 2015 6:40PM | Dec 5 2015 9:23PM | Dec 5 2015 10:36PM | 50.241 | 47.875 | 41.96 | 0.00 | 26.662 | 23.579 | 21.213 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 | 10 8
Qa/17-1 | SGBM03 | Dec 5 2015 3:20PM | Dec 5 2015 5:35PM | Dec 5 2015 8:06PM | Dec 5 2015 9:30PM | 55.778 | 55.075 | 56.42 | 0.00 | 34.022 | 21.756 | 21.053 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 17.0 | -100.0 | G35T2 | 1 2 | 9 8
X4/Y8-1 | SGBM18 | Dec 4 2015 6:10PM | Dec 5 2015 4:45PM | Dec 5 2015 6:38PM | Dec 5 2015 8:34PM | 55.717 | 55.075 | 47.54 | 0.00 | 32.339 | 23.378 | 22.736 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.5 | 19.0 | -100.0 | G35T2 | 1 2 3 | 7 6 6
Y/46-1 | SGBM22 | Dec 4 2015 5:30PM | Dec 5 2015 12:28PM | Dec 5 2015 6:11PM | Dec 5 2015 8:10PM | 49.676 | 48.775 | 50.45 | 0.00 | 22.148 | 27.528 | 26.627 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 25.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 7 4
J/44-5 | SGBM23 | Dec 4 2015 7:38PM | Dec 5 2015 1:50PM | Dec 5 2015 5:41PM | Dec 5 2015 7:18PM | 51.616 | 47.825 | 43.36 | 0.00 | 14.557 | 37.059 | 33.268 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 27.0 | -100.0 | G45T2 | C480012721 C480012723 C480012727 | 11 11 5
X3/Y8-1 | SGBM18 | Dec 4 2015 5:30PM | Dec 5 2015 2:24PM | Dec 5 2015 3:17PM | Dec 5 2015 4:31PM | 55.698 | 54.775 | 47.21 | 0.00 | 30.709 | 24.989 | 24.066 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.3 | 19.0 | -100.0 | G35T2 | 1 2 3 | 7 6 6
S/21-2 | SGBM21 | Dec 4 2015 10:00PM | Dec 5 2015 8:45AM | Dec 5 2015 10:15AM | Dec 5 2015 11:50AM | 49.994 | 47.425 | 50.52 | 0.00 | 26.417 | 23.577 | 21.008 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 17.0 | -100.0 | G45T2 | 1 2 3 | 8 7 2
Y/55a-5 | SGBM19 | Dec 4 2015 8:30AM | Dec 4 2015 2:33PM | Dec 5 2015 2:04AM | Dec 5 2015 4:00AM | 49.592 | 46.175 | 50.01 | 0.00 | 18.012 | 31.580 | 28.163 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 23.0 | -100.0 | G45T2 | 1 2 3 | 9 7 7
K/43-2 | SGBM23 | Dec 4 2015 9:30AM | Dec 4 2015 7:20PM | Dec 5 2015 1:07AM | Dec 5 2015 2:25AM | 51.782 | 50.375 | 43.51 | 0.00 | 21.912 | 29.870 | 28.463 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 20.0 | -18.1 | G45T2 | PJ2620 PJ2622 PJ2623 | 8 6 6
Y/56a-7 | SGBM17 | Dec 4 2015 8:40AM | Dec 4 2015 3:15PM | Dec 4 2015 11:20PM | Dec 5 2015 1:30AM | 49.412 | 46.175 | 50.31 | 0.00 | 17.710 | 31.702 | 28.465 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 8 7 2
K/42-1 | SGBM23 | Dec 4 2015 8:30AM | Dec 4 2015 5:00PM | Dec 4 2015 10:04PM | Dec 4 2015 11:25PM | 51.86 | 50.375 | 43.65 34.65 25.65 | 0.00 0.00 0.00 | 23.054 | 28.806 | 27.321 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.4 | 20.0 | -100.0 | G45T2 | PJ2605 PJ2606 PJ2610 | 7 6 7
W/53-2 | SGBM19 | Dec 4 2015 1:30PM | Dec 4 2015 6:00PM | Dec 4 2015 7:06PM | Dec 4 2015 9:30PM | 49.45 | 47.625 | 50.22 | 0.00 | 21.321 | 28.129 | 26.304 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 23.0 | 37.4 | G45T2 | 1 2 3 | 9 7 7
P/18-1 | SGBM03 | Dec 3 2015 12:30PM | Dec 4 2015 12:00PM | Dec 4 2015 5:30PM | Dec 4 2015 6:38PM | 55.745 | 53.875 | 47.37 40.37 | 0.00 0.00 | 32.874 | 22.871 | 21.001 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 17.0 | -13.4 | G45T2 | 1 2 | 9 8
J/48-6 | SGBM15 | Dec 2 2015 4:53PM | Dec 3 2015 4:15PM | Dec 4 2015 5:40PM | Dec 4 2015 6:25PM | 51.416 | 50.675 | 43.33 | 0.00 | 18.229 | 33.187 | 32.446 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.6 | 23.0 | -100.0 | G45T2 | 1 2 3 | 7 7 9
N/15-2 | SGBM03 | Dec 3 2015 11:30AM | Dec 3 2015 8:51PM | Dec 4 2015 4:42PM | Dec 4 2015 6:05PM | 55.71 | 53.425 | 47.33 | 0.00 | 27.835 | 27.875 | 25.590 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.3 | 20.0 | 3.7 | G45T2 | 1 2 | 10 10
J/48-1 | SGBM15 | Dec 2 2015 4:09PM | Dec 3 2015 1:16PM | Dec 4 2015 1:52AM | Dec 4 2015 3:30AM | 51.519 | 50.675 | 43.44 | 0.00 | 18.443 | 33.076 | 32.232 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 24.0 | -100.0 | G45T2 | 1 2 3 | 10 7 7
H/40-2 | SGBM23 | Dec 2 2015 6:46PM | Dec 3 2015 3:47PM | Dec 3 2015 11:41PM | Dec 4 2015 1:20AM | 51.82 | 50.375 | 43.78 25.78 | 0.00 0.00 | 23.083 | 28.717 | 27.292 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.4 | 21.0 | -100.0 | G45T2 | 1 2 | 11 10
J/40-3 | SGBM08 | Dec 2 2015 7:31PM | Dec 3 2015 7:17PM | Dec 3 2015 10:55PM | Dec 4 2015 12:20AM | 51.645 | 50.375 | 40.62 | 0.00 | 24.022 | 27.623 | 26.353 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
X7/Y6-6 | SGBM18 | Dec 3 2015 8:00AM | Dec 3 2015 2:00PM | Dec 3 2015 8:12PM | Dec 3 2015 9:40PM | 55.515 | 53.875 | 56.13 | 0.00 | 28.835 | 26.680 | 25.040 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.9 | 20.0 | -100.0 | G35T2 | 1 2 3 | 8 7 5
Y/55-1 | SGBM17 | Dec 2 2015 4:00PM | Dec 3 2015 12:15PM | Dec 3 2015 6:48PM | Dec 3 2015 9:25PM | 49.162 | 48.075 | 41.20 28.10 | 0.00 0.00 | 19.001 | 30.161 | 29.074 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | -18.5 | G45T2 | PJ2549 PJ2551 PJ2552 | 6 7 11
S/23-1 | SGBM21 | Dec 2 2015 8:00AM | Dec 3 2015 11:20AM | Dec 3 2015 3:49PM | Dec 3 2015 5:12PM | 49.794 | 48.625 | 41.59 | 0.00 | 28.294 | 21.500 | 20.331 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 16.0 | -12.9 | G45T2 | 1 2 | 8 8
S/22-1 | SGBM21 | Dec 2 2015 9:40AM | Dec 2 2015 6:29PM | Dec 3 2015 2:38PM | Dec 3 2015 4:05PM | 49.763 | 48.625 | 41.64 | 0.00 | 30.138 | 19.625 | 18.487 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.8 | 16.0 | -11.8 | G45T2 | 1 2 | 8 8
J/44-8 | SGBM15 | Dec 2 2015 3:30PM | Dec 3 2015 8:30AM | Dec 3 2015 12:10PM | Dec 3 2015 1:46PM | 51.593 | 47.825 | 43.58 15.58 | 0.00 0.00 | 14.476 | 37.117 | 33.349 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 25.0 | -21.2 | G45T2 | 1 2 3 4 | 7 6 6 6
Y/56a-6 | SGBM17 | Dec 2 2015 1:20PM | Dec 2 2015 10:00PM | Dec 3 2015 12:39AM | Dec 3 2015 2:35AM | 49.57 | 46.175 | 41.47 | 0.00 | 17.466 | 32.104 | 28.709 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 23.0 | -100.0 | G45T2 | PJ2496 PJ2498 PJ2500 | 8 7 8
Y/56a-2 | SGBM17 | Dec 2 2015 11:30AM | Dec 2 2015 9:56PM | Dec 2 2015 10:16PM | Dec 3 2015 12:20AM | 49.51 | 46.175 | 41.28 | 0.00 | 17.677 | 31.833 | 28.498 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | 26.8 | G45T2 | PJ2484 PJ2487 PJ2490 | 9 7 7
M/15a-1 | SGBM20 | Dec 1 2015 8:00AM | Dec 2 2015 1:08PM | Dec 2 2015 5:16PM | Dec 2 2015 10:39PM | 55.669 | 54.625 | 47.40 | 0.00 | 27.995 | 84.069 | 26.630 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 20.0 | -16.9 | G45T2 | 1 2 3 | 7 7 6
M/18-2 | SGBM03 | Dec 1 2015 5:00PM | Dec 1 2015 9:55PM | Dec 2 2015 11:20AM | Dec 2 2015 12:56PM | 55.478 | 53.425 | -9.00 | 0.00 | -25.000 | 80.478 | 78.425 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 49.9 | 18.0 | -49.9 | G45T2 | 1 2 3 | 6 6 6
J/40-2 | SGBM23 | Dec 1 2015 11:50AM | Dec 1 2015 9:00PM | Dec 1 2015 11:52PM | Dec 2 2015 1:20AM | 51.75 | 50.375 | 43.67 | 0.00 | 23.371 | 28.379 | 27.004 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
M/52-1 | SGBM02 | Nov 30 2015 7:05PM | Dec 1 2015 10:50AM | Dec 1 2015 5:50PM | Dec 1 2015 8:45PM | 51.85 | 51.375 | 43.64 28.14 | 0.00 0.00 | 16.744 | 87.780 | 34.631 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.0 | 26.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 3 2
X/54-1 | SGBM19 | Nov 28 2015 8:30AM | Dec 1 2015 2:20PM | Dec 1 2015 6:10PM | Dec 1 2015 7:45PM | 49.317 | 48.075 | 41.17 34.87 | 0.00 0.00 | 20.475 | 28.842 | 27.600 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.6 | 21.0 | -100.0 | G45T2 | 1 2 | 11 10
Y/55a-8 | SGBM17 | Nov 28 2015 2:00PM | Dec 1 2015 11:54AM | Dec 1 2015 4:43PM | Dec 1 2015 6:15PM | 49.489 | 46.175 | 41.28 25.49 21.99 | 0.00 0.00 0.00 | 17.885 | 31.604 | 28.290 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 24.0 | -18.0 | G45T2 | PJ2419 PJ2421 PJ2422 | 8 8 8
G/31-1 | SGBM20 | Oct 31 2015 2:15PM | Oct 31 2015 8:08PM | Nov 1 2015 2:06PM | Dec 1 2015 3:00PM | 52.129 | 48.175 | 43.91 | 0.00 | 32.206 | 20.030 | 15.969 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.2 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
R/22-1 | SGBM21 | Nov 29 2015 10:00AM | Nov 30 2015 12:05PM | Dec 1 2015 11:55AM | Dec 1 2015 12:36PM | 50.335 | 47.875 | 41.72 | 0.00 | 26.723 | 23.612 | 21.152 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | 3.5 | G45T2 | 1 2 | 11 6
M/13a-1 | SGBM21 | Nov 30 2015 8:00AM | Nov 30 2015 1:14PM | Nov 30 2015 9:41PM | Dec 1 2015 12:40AM | 55.432 | 55.075 | 56.54 | 0.00 | 26.042 | 29.390 | 29.033 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
J/44-3 | SGBM15 | Nov 30 2015 1:30PM | Nov 30 2015 6:40PM | Nov 30 2015 9:57PM | Nov 30 2015 11:50PM | 51.638 | 47.825 | 43.63 | 0.00 | 14.435 | 37.203 | 33.390 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
La/53-1 | SGBM02 | Nov 28 2015 7:06PM | Nov 30 2015 2:40PM | Nov 30 2015 8:58PM | Nov 30 2015 10:55PM | 51.777 | 51.375 | 43.65 | 0.00 | 15.646 | 88.777 | 35.729 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.7 | 25.0 | 2.3 | G45T2 | 1 2 3 4 | 7 6 6 6
S/19-2 | SGBM20 | Nov 29 2015 1:00AM | Nov 30 2015 4:55PM | Nov 30 2015 8:23PM | Nov 30 2015 9:06PM | 55.967 | 53.875 | 47.76 | 0.00 | 33.763 | 22.204 | 20.112 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 16.0 | -12.8 | G45T2 | 1 2 | 8 8
H/40-1 | SGBM23 | Nov 27 2015 5:45PM | Nov 30 2015 10:36AM | Nov 30 2015 5:31PM | Nov 30 2015 7:05PM | 51.778 | 50.375 | 43.71 | 0.00 | 23.112 | 28.666 | 27.263 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
Kb/32a-1 | SGBM21 | Nov 28 2015 10:40AM | Nov 28 2015 8:00PM | Nov 29 2015 2:54PM | Nov 29 2015 3:48PM | 52.11 | 52.425 | 43.96 | 0.00 | 35.261 | 16.849 | 17.164 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 10.9 | 17.0 | -10.9 | G35T2 | 1 2 3 | 6 6 5
Ka/33b-1 | SGBM21 | Nov 28 2015 10:00AM | Nov 28 2015 1:05PM | Nov 29 2015 1:42PM | Nov 29 2015 2:52PM | 52.13 | 52.425 | 43.85 | 0.00 | 35.153 | 69.763 | 17.272 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 11.0 | 17.0 | 6.0 | G35T2 | 1 2 3 | 6 6 5
J/48-5 | SGBM15 | Nov 28 2015 9:45AM | Nov 28 2015 9:00PM | Nov 29 2015 2:28AM | Nov 29 2015 5:20AM | 51.491 | 50.675 | 43.14 26.14 | 0.00 0.00 | 18.244 | 33.900 | 32.431 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.6 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 8 7 8 4
J/40-1 | SGBM23 | Nov 28 2015 5:55PM | Nov 28 2015 8:58PM | Nov 29 2015 3:06AM | Nov 29 2015 4:15AM | 51.623 | 50.375 | 52.54 | 0.00 | 23.936 | 27.687 | 26.439 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.8 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
J/48-2 | SGBM15 | Nov 28 2015 10:16AM | Nov 28 2015 5:05PM | Nov 29 2015 12:27AM | Nov 29 2015 2:10AM | 51.52 | 50.675 | 43.52 | 0.00 | 18.120 | 33.400 | 32.555 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.7 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 7 8
La/55-1 | SGBM02 | Nov 27 2015 5:20PM | Nov 28 2015 6:41PM | Nov 28 2015 10:36PM | Nov 29 2015 12:50AM | 52.78 | 51.375 | 44.56 | 0.00 | 16.560 | 36.220 | 34.815 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.2 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 6 6 6
S/17-2 | SGBM20 | Nov 28 2015 10:30AM | Nov 28 2015 1:30PM | Nov 28 2015 7:45PM | Nov 28 2015 8:48PM | 55.866 | 53.875 | 47.63 | 0.00 | 33.629 | 22.237 | 20.246 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 16.0 | -12.9 | G45T2 | 1 2 3 | 6 5 5
Y/54-1 | SGBM19 | Nov 27 2015 6:00PM | Nov 29 2015 3:05PM | Nov 28 2015 5:07PM | Nov 28 2015 7:40PM | 49.249 | 48.075 | 41.06 34.26 | 0.00 0.00 | 19.356 | 29.893 | 28.719 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.3 | 23.0 | -18.3 | G45T2 | PJ2298 PJ2300 PJ2304 | 8 7 8
M/16-1 | SGBM20 | Nov 27 2015 8:30AM | Nov 27 2015 9:30PM | Nov 28 2015 3:35PM | Nov 28 2015 5:44PM | 55.584 | 54.625 | 47.32 | 0.00 | 30.316 | 25.268 | 24.309 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.5 | 18.0 | -15.5 | G45T2 | 1 2 3 | 6 6 6
J/44-15 | SGBM15 | Nov 27 2015 5:05PM | Nov 28 2015 9:18AM | Nov 28 2015 3:59PM | Nov 28 2015 4:45PM | 51.613 | 47.825 | 43.53 20.53 | 0.00 0.00 | 14.532 | 37.081 | 33.293 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 24.0 | 2.8 | G45T2 | c480012367 c480012368 | 12 12
La/54-1 | SGBM02 | Nov 26 2015 2:00PM | Nov 26 2015 5:30PM | Nov 27 2015 11:38PM | Nov 28 2015 2:35AM | 51.92 | 51.375 | 43.88 | 0.00 | 14.882 | 38.000 | 36.493 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.2 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 4 8 8 8
Y/55a-7 | SGBM19 | Nov 27 2015 2:02PM | Nov 27 2015 9:05PM | Nov 27 2015 10:50PM | Nov 28 2015 1:09AM | 49.516 | 46.175 | 41.35 | 0.00 | 17.849 | 31.667 | 28.326 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 23.0 | -100.0 | G45T2 | PJ2267 PJ2270 PJ2274 | 8 7 8
M/18-1 | SGBM21 | Nov 27 2015 9:45AM | Nov 27 2015 4:28PM | Nov 27 2015 11:05PM | Nov 28 2015 12:35AM | 55.565 | 53.425 | 47.39 | 0.00 | 31.088 | 25.300 | 22.337 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
M/17-1 | SGBM20 | Nov 27 2015 10:30AM | Nov 27 2015 6:55PM | Nov 27 2015 9:26PM | Nov 27 2015 10:40PM | 55.557 | 54.625 | 47.29 | 0.00 | 31.086 | 24.471 | 23.539 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.0 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
Ka/32a-1 | SGBM21 | Nov 26 2015 11:00AM | Nov 26 2015 8:15PM | Nov 27 2015 6:03PM | Nov 27 2015 8:54PM | 52.038 | 52.425 | 43.71 | 0.00 | 35.206 | 16.832 | 17.219 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 11.0 | 13.0 | 2.0 | G35T2 | 1 2 | 7 6
Kb/33b-1 | SGBM21 | Nov 26 2015 11:45AM | Nov 27 2015 4:30PM | Nov 27 2015 7:42PM | Nov 27 2015 8:15PM | 52.063 | 52.425 | 43.89 | 0.00 | 35.088 | 16.975 | 17.337 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 11.0 | 13.0 | -100.0 | G35T2 | 1 2 | 7 6
Y/55a-2 | SGBM17 | Nov 26 2015 1:20PM | Nov 27 2015 3:00PM | Nov 27 2015 5:16PM | Nov 27 2015 7:50PM | 49.475 | 46.175 | 41.30 | 0.00 | 17.803 | 31.672 | 28.372 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | -18.1 | G45T2 | PJ2239 PJ2243 PJ2248 | 8 8 7
P/17-2 | SGBM03 | Nov 26 2015 11:30AM | Nov 27 2015 9:43AM | Nov 27 2015 4:52PM | Nov 27 2015 6:13PM | 55.832 | 53.875 | 47.57 36.57 | 0.00 0.00 | 31.573 | 24.259 | 22.302 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 17.0 | 2.8 | G45T2 | 1 2 3 | 6 6 5
S/18-2 | SGBM03 | Nov 26 2015 10:57AM | Nov 26 2015 3:13PM | Nov 26 2015 8:44PM | Nov 26 2015 9:44PM | 55.923 | 53.875 | 47.92 | 0.00 | 33.623 | 22.300 | 20.252 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 16.0 | -12.9 | G45T2 | 1 2 | 8 8
R/17-2 | SGBM21 | Nov 25 2015 6:05PM | Nov 26 2015 8:10AM | Nov 26 2015 5:01PM | Nov 26 2015 6:25PM | 55.897 | 53.875 | 56.66 | 0.00 | 32.156 | 23.741 | 21.719 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.8 | 19.0 | -100.0 | G35T2 | 1 2 3 | 7 6 6
R/18-1 | SGBM20 | Nov 23 2015 4:45PM | Nov 25 2015 3:30PM | Nov 26 2015 2:26AM | Nov 26 2015 4:00AM | 55.94 | 53.875 | 47.63 | 0.00 | 33.635 | 23.000 | 20.240 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 20.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 2
La/60-1 | SGBM02 | Nov 24 2015 6:23PM | Nov 25 2015 5:16PM | Nov 26 2015 12:11AM | Nov 26 2015 2:35AM | 53.027 | 51.375 | 44.90 | 0.00 | 16.100 | 36.927 | 35.275 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.4 | 27.0 | 20.3 | G35T2 | 1 2 3 4 | 7 7 6 7
N/26-1 | SGBM21 | Nov 25 2015 1:30PM | Nov 25 2015 5:28PM | Nov 26 2015 1:20AM | Nov 26 2015 1:57AM | 53.317 | 51.375 | 45.21 | 0.00 | 31.714 | 22.500 | 19.661 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
G/50-1 | SGBM15 | Nov 24 2015 10:47AM | Nov 25 2015 1:21PM | Nov 25 2015 7:36PM | Nov 25 2015 9:40PM | 51.847 | 51.375 | 43.69 22.69 15.69 | 0.00 0.00 0.00 | 13.891 | 37.956 | 37.484 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.8 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
La/61-1 | SGBM02 | Nov 24 2015 5:42PM | Nov 25 2015 12:15PM | Nov 25 2015 7:00PM | Nov 25 2015 9:00PM | 52.874 | 50.075 | 44.77 | 0.00 | 13.268 | 39.606 | 36.807 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.4 | 26.0 | -23.4 | G45T2 | 1 2 3 4 | 7 7 7 5
Y/55a-6 | SGBM19 | Nov 25 2015 8:17AM | Nov 26 2015 5:14PM | Nov 25 2015 5:26PM | Nov 25 2015 7:10PM | 49.62 | 46.175 | 41.58 | 0.00 | 18.080 | 31.540 | 28.095 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 21.0 | 3.1 | G45T2 | 2121 2122 2126 | 7 7 7
F/50-1 | SGBM15 | Nov 24 2015 11:30AM | Nov 24 2015 5:47PM | Nov 25 2015 12:00PM | Nov 25 2015 1:40PM | 51.884 | 51.075 | 40.57 | 0.00 | 12.773 | 39.111 | 38.302 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.4 | 29.0 | -24.4 | G45T2 | 1 2 3 4 | 7 7 8 7
Y/55a-1 | SGBM19 | Nov 24 2015 3:05PM | Nov 25 2015 9:00AM | Nov 25 2015 10:05AM | Nov 25 2015 12:50PM | 49.435 | 46.175 | 41.36 18.36 | 0.00 0.00 | 18.175 | 31.260 | 28.000 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 25.0 | 40.3 | G45T2 | 2090 2091 2092 2095 | 8 7 7 3
F/45-1 | SGBM23 | Nov 23 2015 4:38PM | Nov 24 2015 5:25PM | Nov 24 2015 7:04PM | Nov 24 2015 8:30PM | 51.962 | 51.375 | -9.00 | 0.00 | -37.300 | 89.262 | 88.675 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 56.4 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
H/62-1a | SGBM02 | Nov 23 2015 10:03AM | Nov 24 2015 12:57PM | Nov 24 2015 3:40PM | Nov 24 2015 5:25PM | 52.856 | 50.175 | 44.65 | 0.00 | 9.345 | 43.511 | 40.830 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.0 | 30.0 | -100.0 | G35T2 | 1 2 3 4 | 7 8 8 7
F/47-1 | SGBM15 | Nov 21 2015 7:02PM | Nov 23 2015 8:35PM | Nov 24 2015 2:05PM | Nov 24 2015 3:24PM | 51.84 | 51.075 | 43.79 | 0.00 | 12.989 | 38.851 | 38.086 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.2 | 28.0 | 15.5 | G45T2 | 1 2 3 4 | 7 7 7 7
S/19-1 | SGBM21 | Nov 23 2015 5:25PM | Nov 24 2015 9:35AM | Nov 24 2015 2:03PM | Nov 24 2015 3:04PM | 55.696 | 53.875 | 47.67 39.17 | 0.00 0.00 | 33.171 | 22.525 | 20.704 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 16.0 | -13.2 | G45T2 | 1 2 | 8 8
F/43-1 | SGBM23 | Nov 23 2015 3:03PM | Nov 23 2015 9:04PM | Nov 24 2015 11:23AM | Nov 24 2015 1:00PM | 51.833 | 51.375 | 43.61 | 0.00 | 19.214 | 32.619 | 32.161 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.5 | 24.0 | -20.5 | G45T2 | 1 2 3 4 | 6 6 6 6
H/62-1b | SGBM02 | Nov 23 2015 10:45AM | Nov 23 2015 4:55PM | Nov 23 2015 9:51PM | Nov 23 2015 11:30PM | 52.822 | 50.175 | 44.71 11.71 | 0.00 0.00 | 9.808 | 43.014 | 40.367 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.7 | 33.0 | -25.7 | G35T2 | 1 2 3 4 5 | 7 7 7 6 6
Z/41-2 | SGBM19 | Nov 23 2015 12:05PM | Nov 23 2015 6:18PM | Nov 23 2015 7:56PM | Nov 23 2015 9:35PM | 49.573 | 47.725 | 41.30 | 0.00 | 19.702 | 29.871 | 28.023 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 28.0 | -17.8 | G45T2 | 1 2 3 4 | 7 7 7 7
F/46-1 | SGBM15 | Nov 21 2015 6:35PM | Nov 23 2015 1:45PM | Nov 23 2015 7:40PM | Nov 23 2015 9:25PM | 51.83 | 51.375 | 43.71 | 0.00 | 12.913 | 38.917 | 38.462 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.5 | 27.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 7 6
Kb/26a-1 | SGBM21 | Nov 21 2015 8:00PM | Nov 23 2015 2:00PM | Nov 23 2015 7:20PM | Nov 23 2015 8:10PM | 53.615 | 52.425 | 45.42 36.42 | 0.00 0.00 | 32.225 | 21.390 | 20.200 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
Kb/26b-1 | SGBM21 | Nov 24 2015 1:00AM | Nov 24 2015 8:13PM | Nov 23 2015 5:32PM | Nov 23 2015 6:40PM | 53.498 | 52.425 | 45.15 | 0.00 | 31.949 | 22.200 | 20.476 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 15.0 | 15.1 | G35T2 | 1 2 | 7 8
Ka/26b-1 | SGBM21 | Nov 21 2015 6:30PM | Nov 22 2015 11:43AM | Nov 23 2015 5:32PM | Nov 23 2015 6:30PM | 53.498 | 52.425 | 45.15 | 0.00 | 31.949 | 22.200 | 20.476 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
Ka/26a-1 | SGBM21 | Nov 21 2015 7:20PM | Nov 23 2015 2:00PM | Nov 23 2015 5:35PM | Nov 23 2015 6:24PM | 53.615 | 52.425 | 45.42 36.42 | 0.00 0.00 | 32.115 | 21.500 | 20.310 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 15.0 | -100.0 | G35T2 | 1 2 | 7 8
Z1/41a-1 | SGBM19 | Nov 23 2015 8:08AM | Nov 23 2015 1:35PM | Nov 23 2015 2:50PM | Nov 23 2015 4:05PM | 49.325 | 48.725 | 41.20 | 0.00 | 22.100 | 27.225 | 26.625 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12+6 | - | 16.9 | 20.0 | -16.9 | G35T2 | 1 2 3 | 7 7 6
H/50-1 | SGBM15 | Nov 20 2015 4:50PM | Nov 21 2015 5:08PM | Nov 21 2015 9:52PM | Nov 21 2015 11:50PM | 51.949 | 51.375 | 43.79 40.79 | 0.00 0.00 | 16.890 | 87.849 | 34.485 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 25.0 | 3.0 | G45T2 | 1 2 3 4 | 7 6 6 6
AA1/41b-1 | SGBM19 | Nov 21 2015 8:00AM | Nov 21 2015 12:20PM | Nov 21 2015 6:03PM | Nov 21 2015 9:30PM | 49.457 | 48.725 | 50.31 | 0.00 | 22.705 | 26.752 | 26.020 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 31.0 | -100.0 | G35T2 | 1 2 3 4 5 | 7 7 6 8 3
Q/21-1 | SGBM21 | Nov 20 2015 7:15PM | Nov 21 2015 5:20PM | Nov 21 2015 6:34PM | Nov 21 2015 7:30PM | 53.921 | 52.675 | 45.85 | 0.00 | 31.354 | 22.567 | 21.321 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
J/50-1 | SGBM15 | Nov 20 2015 5:16PM | Nov 21 2015 10:34AM | Nov 21 2015 2:14PM | Nov 21 2015 2:55PM | 51.93 | 51.375 | 43.77 33.77 | 0.00 0.00 | 18.169 | 86.530 | 33.206 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 24.0 | 2.9 | G45T2 | PJ1914 PJ1915 PJ1916 | 8 8 8
J/44-10 | SGBM23 | Nov 19 2015 6:10PM | Nov 20 2015 4:02PM | Nov 21 2015 12:15PM | Nov 21 2015 1:55PM | 51.73 | 47.825 | 43.60 29.60 27.60 23.60 | 0.00 0.00 0.00 0.00 | 14.797 | 89.530 | 33.028 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 26.0 | -1.0 | G45T2 | 1 2 3 4 | 7 6 7 6
Z1/41b-1 | SGBM19 | Nov 20 2015 6:00PM | Nov 20 2015 10:40PM | Nov 21 2015 12:29AM | Nov 21 2015 3:00AM | 49.366 | 48.725 | 49.99 | 0.00 | 21.886 | 27.480 | 26.839 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 22.0 | -100.0 | G35T2 | 1 2 3 4 | 6 8 7 1
F/51-1 | SGBM15 | Nov 18 2015 7:30PM | Nov 20 2015 4:26PM | Nov 20 2015 10:52PM | Nov 21 2015 1:20AM | 51.769 | 51.075 | 43.59 31.59 20.59 | 0.00 0.00 0.00 | 10.788 | 93.569 | 40.287 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.6 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 5 5 7
AA1/41a-1 | SGBM22 | Nov 20 2015 10:10AM | Nov 20 2015 5:22PM | Nov 20 2015 10:02PM | Nov 21 2015 12:30AM | 49.449 | 48.725 | 50.27 | 0.00 | 21.974 | 27.475 | 26.751 |  | 0.0 | 0.0 | 0.0 | 24T20+12T20 | - | - | T12-250 | - | - | - | 12 | - | 17.0 | 21.0 | -17.0 | G35T2 | 1 2 3 4 | 7 6 7 1
G/51-1 | SGBM15 | Nov 18 2015 7:08PM | Nov 19 2015 6:18PM | Nov 20 2015 7:54PM | Nov 20 2015 10:30PM | 51.937 | 51.375 | 43.85 | 0.00 | 12.855 | 91.937 | 38.520 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.5 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
S/17-1 | SGBM21 | Nov 19 2015 8:00PM | Nov 20 2015 5:10PM | Nov 20 2015 6:47PM | Nov 20 2015 7:45PM | 55.861 | 53.875 | 47.72 | 0.00 | 33.018 | 22.843 | 20.857 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.3 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
S/18-1 | SGBM21 | Nov 19 2015 8:25AM | Nov 20 2015 11:30AM | Nov 20 2015 3:00PM | Nov 20 2015 4:47PM | 55.915 | 53.875 | 47.72 | 0.00 | 33.217 | 22.698 | 20.658 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 16.0 | 2.9 | G45T2 | 1 2 | 8 8
R/20-2 | SGBM20 | Dec 19 2015 10:25AM | Dec 19 2015 6:47PM | Dec 19 2015 11:35PM | Nov 20 2015 1:30AM | 54.437 | 50.475 | 55.13 | 0.00 | 30.231 | 24.206 | 20.244 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 20.0 | 55.3 | G45T2 | 1 2 | 10 10
AE/31a-1 | SGBM22 | Nov 19 2015 2:10PM | Nov 19 2015 6:10PM | Nov 19 2015 8:40PM | Nov 19 2015 10:28PM | 49.38 | 48.475 | 50.21 | 0.00 | 23.808 | 25.572 | 24.667 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.7 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
P/19-2 | SGBM20 | Nov 19 2015 2:30PM | Nov 19 2015 6:15PM | Nov 19 2015 9:15PM | Nov 19 2015 10:18PM | 55.822 | 51.575 | 47.55 | 0.00 | 31.549 | 24.273 | 20.026 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.7 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
H/51-1 | SGBM15 | Nov 18 2015 6:50PM | Nov 19 2015 11:24AM | Nov 19 2015 5:55PM | Nov 19 2015 7:40PM | 52.053 | 51.375 | 43.94 | 0.00 | 14.935 | 38.000 | 36.440 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.2 | 27.0 | -100.0 | G45T2 | 1 2 3 | 9 9 9
E/47-1 | SGBM23 | Nov 18 2015 6:50PM | Nov 19 2015 9:50AM | Nov 19 2015 4:11PM | Nov 19 2015 6:20PM | 51.86 | 51.275 | 43.59 22.59 | 0.00 0.00 | 11.694 | 92.760 | 39.581 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.2 | 29.0 | 3.8 | G45T2 | C480011907 C170013571 C170013573 C480011913 | 11 8 8 2
Y/54-2 | SGBM17 | Nov 19 2015 10:26AM | Nov 19 2015 3:00PM | Nov 19 2015 3:25PM | Nov 19 2015 5:00PM | 49.227 | 48.075 | 40.95 | 0.00 | 19.952 | 29.275 | 28.123 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
X7/Y6-3 | SGBM18 | Nov 18 2015 8:00PM | Nov 19 2015 8:20AM | Nov 19 2015 12:50PM | Nov 19 2015 2:50PM | 55.555 | 53.875 | 56.28 | 0.00 | 28.781 | 26.774 | 25.094 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 22.0 | -100.0 | G35T2 | 1 2 3 | 8 7 7
J/44-13 | SGBM15 | Nov 18 2015 10:30AM | Nov 18 2015 6:40PM | Nov 19 2015 11:35AM | Nov 19 2015 1:10PM | 51.965 | 47.825 | 43.83 | 0.00 | 14.228 | 38.600 | 33.597 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.4 | 25.0 | -21.4 | G45T2 | 1 2 3 4 | 7 6 6 6
R/18-2 | SGBM20 | Nov 18 2015 5:55PM | Nov 19 2015 4:40PM | Nov 19 2015 10:54AM | Nov 19 2015 12:15PM | 55.903 | 53.875 | 47.71 | 0.00 | 33.909 | 21.994 | 19.966 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.7 | 18.0 | -12.7 | G45T2 | 1 2 3 | 6 6 6
X/54-2 | SGBM19 | Nov 18 2015 8:05AM | Nov 18 2015 6:15PM | Nov 19 2015 1:15AM | Nov 19 2015 5:30AM | 49.404 | 48.075 | 41.35 | 0.00 | 22.000 | 27.404 | 26.075 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 27.0 | -16.6 | G45T2 | 2 2 3 4 | 7 8 4 8
AE/36-1 | SGBM22 | Nov 18 2015 11:50AM | Nov 18 2015 9:15PM | Nov 19 2015 12:17AM | Nov 19 2015 1:45AM | 49.614 | 48.775 | 41.71 | 0.00 | 24.053 | 25.561 | 24.722 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.7 | 19.0 | 20.8 | G45T2 | 1 2 3 | 6 6 7
R/17-1 | SGBM20 | Nov 18 2015 5:00PM | Nov 18 2015 8:06PM | Nov 18 2015 9:18PM | Nov 18 2015 10:20PM | 55.83 | 53.875 | 56.57 | 0.00 | 32.370 | 23.460 | 21.505 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.7 | 16.0 | -100.0 | G35T2 | 1 2 | 8 8
X9a/Y4a-1 | SGBM20 | Nov 18 2015 1:00PM | Nov 18 2015 6:00PM | Nov 18 2015 8:27PM | Nov 18 2015 9:50PM | 55.789 | 55.075 | 56.53 | 0.00 | 26.533 | 29.256 | 28.542 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 22.0 | -18.2 | G45T2 | 1 2 3 | 8 7 7
J/44-16 | SGBM15 | Nov 17 2015 6:44PM | Nov 18 2015 10:26AM | Nov 18 2015 5:21PM | Nov 18 2015 8:05PM | 51.95 | 47.825 | 43.80 28.80 | 0.00 0.00 | 14.702 | 37.248 | 33.123 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 3
X10/Y5-1 | SGBM18 | Nov 17 2015 2:00PM | Nov 17 2015 8:00PM | Nov 18 2015 1:55AM | Nov 18 2015 3:35AM | 55.365 | 55.075 | 56.55 | 0.00 | 26.947 | 28.418 | 28.128 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 24.0 | -100.0 | G35T2 | 1 2 3 | 8 8 8
AB/52-2 | SGBM22 | Nov 16 2015 6:00PM | Nov 17 2015 2:58PM | Nov 17 2015 6:55PM | Nov 17 2015 9:00PM | 49.25 | 47.875 | 41.12 | 0.00 | 17.015 | 32.235 | 30.860 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.6 | 24.0 | -100.0 | G45T2 | PJ1707 PJ1709 PJ1711 | 8 8 8
J/44-6 | SGBM18 | Nov 17 2015 8:30AM | Nov 17 2015 2:30PM | Nov 17 2015 4:15PM | Nov 17 2015 6:00PM | 51.776 | 47.825 | 52.57 | 0.00 | 14.667 | 37.109 | 33.158 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 24.0 | -100.0 | G45T2 | 1 2 3 | 4 10 10
E/48-1 | SGBM23 | Nov 15 2015 4:00PM | Nov 16 2015 6:40PM | Nov 17 2015 2:40PM | Nov 17 2015 4:45PM | 51.955 | 51.275 | 43.87 | 0.00 | 10.674 | 42.200 | 40.601 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.8 | 33.0 | -100.0 | G45T2 | 1 2 3 4 | 7 10 10 6
P/24-1 | SGBM05 | Nov 15 2015 9:00AM | Nov 16 2015 8:10PM | Nov 17 2015 2:47PM | Nov 17 2015 4:15PM | 53.35 | 52.475 | 45.08 | 0.00 | 31.984 | 21.366 | 20.491 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 17.0 | -100.0 | G45T2 | 1 2 3 | 7 8 2
E/49-1 | SGBM23 | Nov 15 2015 2:00PM | Nov 16 2015 3:24PM | Nov 17 2015 1:08PM | Nov 17 2015 3:05PM | 51.95 | 51.275 | 43.90 | 0.00 | 11.300 | 40.650 | 39.975 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.4 | 33.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 10 3
P/21-1 | SGBM05 | Nov 15 2015 9:40AM | Nov 16 2015 4:35PM | Nov 17 2015 12:10PM | Nov 17 2015 1:30PM | 53.736 | 51.575 | 45.42 | 0.00 | 30.318 | 23.418 | 21.257 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
J/44-18 | SGBM15 | Nov 14 2015 6:30PM | Nov 16 2015 8:17PM | Nov 17 2015 12:42AM | Nov 17 2015 4:00AM | 51.809 | 47.825 | 43.66 | 0.00 | 14.761 | 37.048 | 33.064 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 27.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 6 6 6 3
J/44-12 | SGBM15 | Nov 14 2015 6:00PM | Nov 16 2015 1:30PM | Nov 16 2015 11:00PM | Nov 17 2015 1:30AM | 51.884 | 47.825 | 43.75 | 0.00 | 14.752 | 37.132 | 33.073 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.0 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 4
AB/55-1 | SGBM22 | Nov 15 2015 6:10PM | Nov 16 2015 7:30PM | Nov 16 2015 11:25PM | Nov 16 2015 7:30PM | 49.459 | 49.075 | 41.38 32.38 26.38 | 0.00 0.00 0.00 | 18.183 | 31.276 | 30.892 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.7 | 21.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 7 2
K/50-1 | SGBM15 | Nov 14 2015 4:50PM | Nov 16 2015 2:15PM | Nov 16 2015 4:55PM | Nov 16 2015 6:40PM | 50.272 | 51.375 | 52.94 | 0.00 | 19.242 | 31.030 | 32.133 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 20.4 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
J/44-2 | SGBM18 | Nov 14 2015 8:40PM | Nov 16 2015 8:20AM | Nov 16 2015 4:28PM | Nov 16 2015 6:30PM | 51.791 | 47.825 | 52.44 | 0.00 | 14.441 | 37.350 | 33.384 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.2 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 6 7 6
N/25-1 | SGBM05 | Nov 14 2015 9:00AM | Nov 14 2015 8:45PM | Nov 16 2015 11:50AM | Nov 16 2015 12:50PM | 53.323 | 52.475 | 45.16 | 0.00 | 32.162 | 21.161 | 20.313 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
AB/54-1 | SGBM19 | Nov 14 2015 2:10PM | Nov 14 2015 9:45PM | Nov 14 2015 6:40PM | Nov 14 2015 9:45PM | 49.403 | 49.075 | 41.40 | 0.00 | 18.588 | 30.815 | 30.487 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.4 | 25.0 | 28.9 | G45T2 | 2 2 3 4 | 7 6 6 6
X9/Y5-2 | SGBM21 | Nov 11 2015 6:25PM | Nov 14 2015 11:40AM | Nov 14 2015 4:51PM | Nov 14 2015 6:18PM | 55.865 | 54.075 | 47.55 40.55 | 0.00 0.00 | 26.852 | 29.700 | 27.223 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
Fa/35-1 | SGBM20 | Nov 14 2015 11:25AM | Nov 14 2015 3:44PM | Nov 14 2015 4:17PM | Nov 14 2015 5:00PM | 52.238 | 50.775 | 44.04 | 0.00 | 29.537 | 23.500 | 21.238 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
AB/53-1 | SGBM22 | Nov 13 2015 3:03PM | Nov 14 2015 12:19PM | Nov 14 2015 1:17PM | Nov 14 2015 2:30PM | 49.284 | 49.075 | 41.07 23.07 | 0.00 0.00 | 18.663 | 30.621 | 30.412 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.3 | 25.0 | 29.2 | G45T2 | 1 2 3 4 | 7 6 6 6
J/44-11 | SGBM23 | Nov 12 2015 1:00PM | Nov 13 2015 5:49PM | Nov 13 2015 9:25PM | Nov 13 2015 11:15PM | 0 | 47.825 | -9.00 | 0.00 | -38.000 | 38.000 | 85.825 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 54.6 | 25.0 | -54.6 | G45T2 | C170013492 C480011692 C520123331 | 3 11 11
P/25-1 | SGBM05 | Nov 12 2015 5:45PM | Nov 13 2015 6:00PM | Nov 13 2015 10:24PM | Nov 13 2015 11:10PM | 53.357 | 51.275 | 45.24 | 0.00 | 32.041 | 21.316 | 19.234 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 15.0 | -100.0 | G45T2 | 1 2 | 9 6
X7/Y6-5 | SGBM03 | Nov 13 2015 8:11AM | Nov 13 2015 12:05PM | Nov 13 2015 8:00PM | Nov 13 2015 10:00PM | 0 | 53.875 | -9.00 | 0.00 | -28.000 | 28.000 | 81.875 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - |  | - | 52.1 | 22.0 | -52.1 | G45T2 | pj1553 pj1556 pj1557 pj1560 | 7 7 6 2
J/44-1 | SGBM23 | Nov 12 2015 12:45PM | Nov 13 2015 1:15PM | Nov 13 2015 8:52PM | Nov 13 2015 9:43PM | 51.678 | 47.825 | 43.69 | 0.00 | 14.285 | 37.393 | 33.540 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.3 | 26.0 | -21.3 | G45T2 | C170013490 C170013491 C170013492 | 9 10 7
J/51-1 | SGBM18 | Nov 13 2015 8:45AM | Nov 13 2015 1:00PM | Nov 13 2015 4:58PM | Nov 13 2015 9:15PM | 52.14 | 51.375 | 52.11 | 0.00 | 16.314 | 35.826 | 35.061 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 29.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 7 6 6 4
J/44-7 | SGBM23 | Nov 12 2015 1:15PM | Nov 12 2015 9:30PM | Nov 13 2015 5:55PM | Nov 13 2015 6:36PM | 51.83 | 47.825 | 43.61 | 0.00 | 14.208 | 37.622 | 33.617 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.4 | 26.0 | -100.0 | G45T2 | C520123325 C520123326 C520123327 | 5 11 10
AB/52-1 | SGBM22 | Nov 12 2015 2:00PM | Nov 13 2015 3:30PM | Nov 13 2015 4:24PM | Nov 13 2015 6:24PM | 49.339 | 47.875 | 41.12 29.12 | 0.00 3.00 | 18.098 | 31.241 | 29.777 |  | 3.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.9 | 25.0 | 32.0 | G45T2 | 1 2 3 4 | 7 6 6 6
J/44-17 | SGBM23 | Nov 12 2015 1:48PM | Nov 12 2015 5:05PM | Nov 13 2015 5:18PM | Nov 13 2015 6:00PM | 51.775 | 47.825 | 43.63 | 0.00 | 14.632 | 38.000 | 33.193 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.1 | 31.0 | 9.9 | G45T2 | C520123323 C520123324 C520123325 | 11 10 10
N/24-1 | SGBM05 | Nov 12 2015 11:05AM | Nov 12 2015 9:30PM | Nov 13 2015 11:08AM | Nov 13 2015 11:55AM | 53.445 | 52.475 | 45.30 | 0.00 | 33.498 | 19.947 | 18.977 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.1 | 16.0 | -100.0 | G45T2 | 1 2 | 8 8
E/50-1 | SGBM15 | Nov 11 2015 2:30PM | Nov 12 2015 2:00PM | Nov 12 2015 10:50PM | Nov 13 2015 2:15AM | 51.959 | 51.275 | 43.78 | 0.00 | 8.884 | 43.075 | 42.391 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 27.0 | 31.0 | -100.0 | G45T2 | 1 2 3 | 7 12 12
Da/48-1 | SGBM23 | Nov 11 2015 4:53PM | Nov 12 2015 10:57AM | Nov 12 2015 7:00PM | Nov 12 2015 11:15PM | 51.988 | 50.775 | 37.79 23.79 | 0.00 0.00 | 9.686 | 94.996 | 41.089 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 29.0 | -100.0 | G45T2 | 1 2 3 4 | 2 11.5 11.5 4
D/63a-1 | SGBM02 | Nov 12 2015 10:45AM | Nov 12 2015 3:34PM | Nov 12 2015 6:00PM | Nov 12 2015 8:20PM | 0 | 51.375 | -15.00 | 0.00 | -30.300 | 30.300 | 81.675 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 52.0 | 21.0 | -52.0 | G45T2 | PJ1503 PJ1504 PJ1505 PJ1512 | 6 6 6 3
D/50-1 | SGBM15 | Nov 11 2015 1:25PM | Nov 11 2015 10:00PM | Nov 12 2015 5:00PM | Nov 12 2015 7:20PM | 51.815 | 51.275 | 43.67 | 0.00 | 8.965 | 42.850 | 42.310 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.9 | 31.0 | -100.0 | G45T2 | 1 2 3 | 11 11 9
M/19-1 | SGBM05 | Nov 11 2015 9:40PM | Nov 12 2015 9:40AM | Nov 12 2015 4:25PM | Nov 12 2015 6:00PM | 55.443 | 50.975 | 56.32 | 0.00 | 30.821 | 24.622 | 20.154 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 16.0 | 24.8 | G45T2 | 1 2 3 | 6 2 8
X9a/Y4-2 | SGBM21 | Nov 11 2015 9:47AM | Nov 11 2015 6:15PM | Nov 12 2015 2:10PM | Nov 12 2015 4:00PM | 55.723 | 53.875 | 47.27 28.77 | 0.00 0.00 | 24.273 | 32.000 | 29.602 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | - | T12-225 | - | - | - | 12 | - | 18.8 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 10 5
Q/24-1 | SGBM05 | Nov 11 2015 2:57PM | Nov 11 2015 7:35PM | Nov 12 2015 12:50PM | Nov 12 2015 2:30PM | 53.445 | 52.775 | 45.30 | 0.00 | 33.498 | 19.947 | 19.277 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.3 | 12.0 | -100.0 | G45T2 | 1 2 | 6 6
AB/46-2 | SGBM17 | Nov 11 2015 3:29PM | Nov 11 2015 6:18PM | Nov 12 2015 11:55AM | Nov 12 2015 1:46PM | 49.304 | 47.875 | 41.22 | 0.00 | 18.523 | 30.781 | 29.352 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.7 | 22.0 | -100.0 | G45T2 | C480011619 C480011620 | 11 11
X7/Y6-2 | SGBM03 | Nov 7 2015 6:15PM | Nov 9 2015 6:35PM | Nov 11 2015 7:44PM | Nov 11 2015 9:40PM | 55.683 | 53.875 | 47.32 | 0.00 | 28.924 | 27.400 | 24.951 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.9 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
L/28-1a | SGBM05 | Nov 11 2015 10:00AM | Nov 11 2015 12:55PM | Nov 11 2015 7:15PM | Nov 11 2015 8:30PM | 53.343 | 50.975 | 54.15 | 0.00 | 31.350 | 21.993 | 19.625 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 16.0 | -100.0 | G45T2 | 1 2 3 | 6 6 4
Ga/35-1 | SGBM20 | Nov 9 2015 8:05PM | Nov 11 2015 11:40AM | Nov 11 2015 5:15PM | Nov 11 2015 6:00PM | 52.235 | 51.375 | 44.00 | 0.00 | 31.800 | 20.435 | 19.575 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 15.0 | -100.0 | G45T2 | pj1463 pj1462 | 7 8
AB/33-1 | SGBM02 | Nov 9 2015 7:33PM | Nov 11 2015 11:00AM | Nov 11 2015 3:05PM | Nov 11 2015 5:05PM | 49.613 | 48.775 | 41.36 30.36 | 0.00 0.00 | 25.463 | 24.150 | 23.312 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.8 | 22.0 | -100.0 | G45T2 | PJ1454 PJ1455 PJ1461 | 7 8 7
Aca/35-1 | SGBM02 | Nov 9 2015 1:30PM | Nov 9 2015 5:02PM | Nov 11 2015 12:40PM | Nov 11 2015 3:00PM | 49.686 | 48.775 | 41.60 | 0.00 | 23.703 | 25.983 | 25.072 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 20.0 | -100.0 | G45T2 | PJ1442 PJ1444 PJ1446 PJ1452 | 6 6 6 2
P/21-2 | SGBM05 | Nov 9 2015 1:00PM | Nov 9 2015 5:40PM | Nov 11 2015 11:25AM | Nov 11 2015 1:00PM | 53.72 | 51.575 | 45.66 | 0.00 | 30.159 | 23.561 | 21.416 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 17.0 | 24.8 | G45T2 | 1 2 3 | 6 6 5
B/56-1 | SGBM17 | Nov 7 2015 6:40PM | Nov 9 2015 6:09PM | Nov 9 2015 9:21PM | Nov 9 2015 11:55PM | 51.857 | 51.275 | 40.67 | 0.00 | 11.967 | 39.890 | 39.308 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.0 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 2 7 9 7 7 3
E/63a-1 | SGBM23 | Nov 7 2015 11:45AM | Nov 7 2015 8:00PM | Nov 9 2015 10:17PM | Nov 9 2015 11:10PM | 51.66 | 51.375 | -9.00 -15.00 | 0.00 0.00 | -39.200 | 90.860 | 90.575 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 57.6 | 28.0 | -57.6 | G45T2 | PJ1396 PJ1397 PJ1399 PJ1400 | 7 7 7 7
G/63-1 | SGBM15 | Nov 5 2015 8:23PM | Nov 9 2015 5:05PM | Nov 9 2015 8:01PM | Nov 9 2015 10:00PM | 51.81 | 51.275 | 43.66 37.66 | 0.00 0.00 | 9.964 | 41.846 | 41.311 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.3 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 3 7 7 9 5
G/20-2 | SGBM20 | Nov 9 2015 10:20AM | Nov 9 2015 3:47PM | Nov 9 2015 6:00PM | Nov 9 2015 7:30PM | 53.505 | 50.975 | 45.15 | 0.00 | 27.755 | 26.400 | 23.220 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | - | T12-250 | - | - | - | 12 | - | 14.8 | 18.0 | -14.8 | G45T2 | 1 2 3 | 6 6 6
X9/Y5-3 | SGBM03 | Nov 7 2015 2:00PM | Nov 9 2015 10:45AM | Nov 9 2015 5:20PM | Nov 9 2015 6:35PM | 55.835 | 54.075 | 47.52 30.42 | 0.00 0.00 | 26.419 | 29.416 | 27.656 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.6 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
X5/Y3-5 | SGBM21 | Nov 7 2015 12:00PM | Nov 7 2015 5:13PM | Nov 9 2015 11:50AM | Nov 9 2015 1:20PM | 55.707 | 53.875 | 47.49 | 0.00 | 25.785 | 29.922 | 28.090 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 8 7
H/63-1 | SGBM15 | Nov 7 2015 10:28AM | Nov 7 2015 4:54PM | Nov 7 2015 8:10PM | Nov 7 2015 10:30PM | 51.6 | 51.375 | 43.31 34.31 20.01 | 0.00 0.00 0.00 | 9.412 | 42.188 | 41.963 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.7 | 33.0 | -26.7 | G45T2 | PJ1384 PJ1386 PJ1387 PJ1390 PJ1394 | 7 7 7 7 5
M/30-1 | SGBM20 | Nov 7 2015 1:40PM | Nov 7 2015 4:50PM | Nov 7 2015 8:48PM | Nov 7 2015 10:15PM | 52.016 | 51.075 | 43.88 | 0.00 | 32.985 | 19.031 | 18.090 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.5 | 16.0 | -11.5 | G45T2 | 1 2 3 | 7 4 5
X9a/Y4-1 | SGBM02 | Nov 7 2015 11:00AM | Nov 7 2015 3:20PM | Nov 7 2015 6:58PM | Nov 7 2015 9:00PM | 55.513 | 53.875 | 47.20 | 0.00 | 24.600 | 33.813 | 29.275 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | - | T12-225 | - | - | - | 12 | - | 18.6 | 27.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 3 6 7 5
C/57-1 | SGBM23 | Nov 6 2015 2:40PM | Nov 7 2015 10:56AM | Nov 7 2015 3:55PM | Nov 7 2015 4:55PM | 51.76 | 51.375 | 43.66 26.66 | 0.00 0.00 | 12.060 | 39.700 | 39.315 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.0 | 32.0 | 7.0 | G45T2 | pj1366 pj1367 pj1368 pj1369 pj1370 | 6 7 7 6 6
L/28-1b | SGBM05 | Nov 7 2015 8:00AM | Nov 7 2015 11:12AM | Nov 7 2015 2:25PM | Nov 7 2015 3:40PM | 53.447 | 50.975 | 54.23 | 0.00 | 31.226 | 22.221 | 19.749 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 16.0 | -100.0 | G45T2 | 1 2 3 | 6 5 5
B/61-1 | SGBM15 | Nov 6 2015 11:37AM | Nov 6 2015 7:25PM | Nov 7 2015 11:20AM | Nov 7 2015 12:30PM | 51.52 | 51.075 | 43.32 | 0.00 | 15.720 | 35.800 | 35.355 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.5 | 28.0 | 5.5 | G45T2 | pj1352 pj1353 pj1354 pj1357 | 7 7 7 7
AB/46-1 | SGBM19 | Nov 6 2015 3:10PM | Nov 6 2015 8:10PM | Nov 7 2015 2:45AM | Nov 7 2015 4:45AM | 49.412 | 47.875 | 50.33 | 0.00 | 18.833 | 30.579 | 29.042 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 27.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 7 6
Aca/45-1 | SGBM02 | Nov 6 2015 8:40AM | Nov 6 2015 12:30PM | Nov 6 2015 9:09PM | Nov 6 2015 11:20PM | 49.443 | 49.075 | 50.24 | 0.00 | 20.044 | 29.399 | 29.031 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 6
X7/Y6-4 | SGBM03 | Nov 5 2015 2:00PM | Nov 6 2015 4:07PM | Nov 6 2015 5:40PM | Nov 6 2015 8:00PM | 55.704 | 53.875 | 47.33 36.33 | 0.00 0.00 | 28.733 | 27.600 | 25.142 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 2
G/20-1 | SGBM05 | Nov 5 2015 2:00PM | Nov 6 2015 3:55PM | Nov 6 2015 5:35PM | Nov 6 2015 6:30PM | 53.46 | 50.975 | 45.19 34.19 | 0.00 0.00 | 27.390 | 26.070 | 23.585 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | - | T12-250 | - | - | - | 12 | - | 15.0 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
C/56-1 | SGBM15 | Nov 5 2015 11:34AM | Nov 5 2015 9:10PM | Nov 6 2015 3:00PM | Nov 6 2015 5:00PM | 51.92 | 51.375 | 40.79 32.79 | 0.00 0.00 | 11.291 | 40.629 | 40.084 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.5 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 8 8 4
T1/55-1 | SGBM19 | Nov 5 2015 5:20PM | Nov 5 2015 9:00PM | Nov 5 2015 10:42PM | Nov 6 2015 2:00AM | 51.307 | 51.375 | 52.85 | 0.00 | 22.448 | 28.859 | 28.927 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.4 | 44.0 | -100.0 | G45T2 | Pending 2 3 4 | 11 11 11 11
G/30-1 | SGBM20 | Nov 5 2015 8:15AM | Nov 5 2015 5:40PM | Nov 5 2015 6:25PM | Nov 5 2015 7:30PM | 52.101 | 49.575 | 43.80 | 0.00 | 29.502 | 22.599 | 20.073 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 12.8 | 15.0 | -100.0 | G45T2 | 1 2 | 4 11
C/60-1 | SGBM18 | Nov 4 2015 7:15PM | Nov 5 2015 1:15PM | Nov 5 2015 5:38PM | Nov 5 2015 7:25PM | 51.92 | 51.375 | 43.69 | 0.00 | 14.685 | 37.235 | 36.690 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.3 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 4
X8/Y7-1 | SGBM03 | Nov 4 2015 9:15AM | Nov 5 2015 12:35PM | Nov 5 2015 1:58PM | Nov 5 2015 4:50PM | 55.935 | 54.625 | 47.43 | 0.00 | 29.534 | 26.900 | 25.091 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 22.0 | -100.0 | G45T2 | 1 2 3 4 | 7 8 5 2
M/27-1 | SGBM05 | Nov 4 2015 12:12PM | Nov 5 2015 11:34AM | Nov 5 2015 2:30PM | Nov 5 2015 3:40PM | 53.204 | 51.375 | 45.06 | 0.00 | 31.155 | 22.900 | 20.220 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 16.0 | -12.9 | G45T2 | 1 2 | 8 8
K/35-1 | SGBM20 | Nov 4 2015 9:40AM | Nov 4 2015 8:25PM | Nov 5 2015 12:50AM | Nov 5 2015 2:35AM | 52.036 | 51.375 | 43.90 | 0.00 | 30.399 | 21.637 | 20.976 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.3 | 17.0 | -13.3 | G45T2 | 1 2 3 | 7 8 2
X9/Y5-1 | SGBM03 | Nov 4 2015 10:00AM | Nov 4 2015 9:12PM | Nov 5 2015 12:00AM | Nov 5 2015 2:00AM | 55.859 | 54.075 | 47.63 | 0.00 | 26.628 | 29.231 | 27.447 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
C/58-1 | SGBM15 | Nov 4 2015 11:47AM | Nov 4 2015 4:11PM | Nov 4 2015 10:30PM | Nov 5 2015 1:25AM | 51.77 | 51.375 | 43.57 | 0.00 | 11.670 | 92.670 | 39.705 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.3 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 7 9 8 8
C/55-1 | SGBM23 | Nov 3 2015 6:20PM | Nov 4 2015 12:10PM | Nov 4 2015 8:45PM | Nov 4 2015 10:30PM | 51.89 | 51.375 | 43.82 37.82 | 0.00 0.00 | 11.220 | 40.670 | 40.155 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.5 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
X5a/Y4-5 | SGBM03 | Nov 4 2015 8:30AM | Nov 4 2015 5:04PM | Nov 4 2015 7:20PM | Nov 4 2015 10:00PM | 55.766 | 51.075 | 47.47 | 0.00 | 22.070 | 33.696 | 29.005 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 5
M/28-1 | SGBM05 | Nov 4 2015 11:27AM | Nov 4 2015 4:34PM | Nov 4 2015 7:45PM | Nov 4 2015 9:00PM | 53.048 | 51.375 | 44.76 | 0.00 | 31.265 | 22.500 | 20.110 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 17.0 | -12.8 | G45T2 | 1 2 3 | 6 6 5
E/62-1 | SGBM17 | Nov 3 2015 3:15PM | Nov 4 2015 3:50PM | Nov 4 2015 5:25PM | Nov 4 2015 8:20PM | 51.848 | 51.375 | 43.70 33.70 | 0.00 0.00 | 12.304 | 39.544 | 39.071 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.9 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 3 7
J/35-1 | SGBM20 | Nov 4 2015 8:40AM | Nov 4 2015 11:40AM | Nov 4 2015 6:15PM | Nov 4 2015 7:15PM | 52.027 | 51.375 | 43.91 | 0.00 | 30.610 | 21.417 | 20.765 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 17.0 | -13.2 | G45T2 | 1 2 3 | 6 6 5
Aca/43-1 | SGBM22 | Nov 4 2015 9:30AM | Nov 4 2015 4:00PM | Nov 4 2015 4:30PM | Nov 4 2015 7:10PM | 49.623 | 49.075 | 41.49 | 0.00 | 20.994 | 28.629 | 28.081 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 13 | - | 17.9 | 26.0 | -100.0 | G45T2 | 1a 2a 3a 4a | 7 7 6 6
C/62-1 | SGBM15 | Nov 3 2015 4:48PM | Nov 4 2015 10:28AM | Nov 4 2015 4:27PM | Nov 4 2015 5:34PM | 51.8 | 51.375 | 43.52 29.52 | 0.00 0.00 | 17.322 | 34.478 | 34.053 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 21.7 | 27.0 | 5.3 | G45T2 | PJ1190 PJ1192 PJ1193 PJ1195 | 7 7 7 6
L/35-1 | SGBM20 | Nov 3 2015 5:25PM | Nov 3 2015 9:20PM | Nov 4 2015 10:20AM | Nov 4 2015 12:05PM | 51.945 | 51.075 | 43.87 | 0.00 | 29.865 | 22.080 | 21.210 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -13.5 | G45T2 | 1 2 3 | 6 6 6
L/20-1 | SGBM05 | Nov 3 2015 10:10AM | Nov 3 2015 9:13PM | Nov 4 2015 12:14AM | Nov 4 2015 2:15AM | 53.698 | 51.275 | 45.34 | 0.00 | 31.441 | 22.900 | 19.834 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 19.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 5 2
X4/Y6-1 | SGBM21 | Nov 2 2015 6:30PM | Nov 3 2015 3:37PM | Nov 4 2015 12:35AM | Nov 4 2015 1:40AM | 55.757 | 55.075 | 47.48 | 0.00 | 28.778 | 27.700 | 26.297 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
C/59-1 | SGBM23 | Nov 3 2015 10:45AM | Nov 3 2015 5:20PM | Nov 3 2015 10:29PM | Nov 4 2015 1:00AM | 51.814 | 51.375 | 43.51 18.51 | 0.00 0.00 | 13.507 | 38.307 | 37.868 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.1 | 37.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 10 5
X5/Y3-4 | SGBM03 | Nov 3 2015 10:00AM | Nov 3 2015 5:34PM | Nov 3 2015 9:56PM | Nov 4 2015 12:00AM | 55.827 | 53.875 | 47.53 | 0.00 | 18.828 | 37.700 | 35.047 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.3 | 21.0 | -100.0 | G45T2 | 1 2 | 12 9
G/19-1 | SGBM05 | Nov 3 2015 11:00AM | Nov 3 2015 5:56PM | Nov 3 2015 10:11PM | Nov 3 2015 11:20PM | 53.643 | 52.175 | 45.41 | 0.00 | 28.411 | 26.000 | 23.764 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.1 | 18.0 | -15.1 | G45T2 | 1 2 3 | 6 6 6
J/20-2 | SGBM05 | Nov 3 2015 9:15AM | Nov 3 2015 2:55PM | Nov 3 2015 5:35PM | Nov 3 2015 9:00PM | 53.508 | 51.575 | 45.27 | 0.00 | 28.270 | 26.000 | 23.305 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.8 | 21.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 5 2
Aca/44-1 | SGBM02 | Nov 3 2015 10:10AM | Nov 3 2015 3:40PM | Nov 3 2015 11:12PM | Nov 3 2015 7:10PM | 49.66 | 49.075 | 41.45 | 0.00 | 21.429 | 28.231 | 27.646 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.6 | 27.0 | 53.5 | G45T2 | 1 2 3 4 | 7 7 7 6
C/61-1 | SGBM18 | Nov 2 2015 1:40PM | Nov 3 2015 8:21AM | Nov 3 2015 1:12PM | Nov 3 2015 4:25PM | 51.88 | 51.375 | 52.64 | 0.00 | 16.443 | 35.437 | 34.932 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.2 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 6 7 4
G/34-1 | SGBM20 | Nov 3 2015 8:00AM | Nov 3 2015 12:56PM | Nov 3 2015 3:04PM | Nov 3 2015 3:55PM | 52.167 | 50.775 | 43.99 | 0.00 | 29.785 | 23.200 | 20.990 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 17.0 | -100.0 | G45T2 | 1 2 | 8 9
H/63a-1 | SGBM17 | Nov 2 2015 11:55AM | Nov 3 2015 8:35AM | Nov 3 2015 11:01AM | Nov 3 2015 1:15PM | 52.032 | 50.725 | -9.00 -42.00 | 0.00 0.00 | -42.800 | 94.832 | 93.525 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 59.5 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 7 7
M/19-2 | SGBM05 | Nov 2 2015 12:07PM | Nov 2 2015 7:32PM | Nov 3 2015 12:24AM | Nov 3 2015 1:20AM | 55.443 | 51.575 | 47.32 | 0.00 | 31.421 | 24.900 | 20.154 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 17.0 | -100.0 | G45T2 | 1 2 3 | 7 8 2
Aca/42-1 | SGBM08 | Oct 30 2015 4:10PM | Nov 2 2015 12:30PM | Nov 2 2015 7:00PM | Nov 2 2015 8:50PM | 49.616 | 49.075 | 41.57 29.57 26.57 | 0.00 0.00 0.00 | 21.614 | 28.002 | 27.461 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
G/30-2 | SGBM20 | Nov 2 2015 11:00AM | Nov 2 2015 6:02PM | Nov 2 2015 6:45PM | Nov 2 2015 8:25PM | 52.162 | 49.575 | 43.96 | 0.00 | 29.163 | 23.800 | 20.412 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.0 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
C/53-1 | SGBM17 | Nov 2 2015 10:45AM | Nov 2 2015 3:45PM | Nov 2 2015 5:20PM | Nov 2 2015 7:55PM | 51.91 | 51.375 | 43.75 | 0.00 | 9.746 | 42.164 | 41.629 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.5 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 4 2
X7/Y6-1 | SGBM21 | Oct 31 2015 3:30PM | Nov 2 2015 12:20PM | Nov 2 2015 2:59PM | Nov 2 2015 5:00PM | 55.715 | 53.875 | 47.47 | 0.00 | 28.769 | 27.700 | 25.106 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.0 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
D/61-1 | SGBM20 | Oct 31 2015 3:25PM | Nov 2 2015 8:22AM | Nov 2 2015 10:20AM | Nov 2 2015 11:25AM | 51.95 | 51.375 | 52.73 | 0.00 | 15.334 | 36.616 | 36.041 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.9 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 6 7 7 8
D/55-1 | SGBM20 | Oct 31 2015 9:00AM | Nov 2 2015 8:21AM | Nov 2 2015 10:20AM | Nov 2 2015 11:20AM | 51.96 | 51.375 | 52.80 | 0.00 | 10.201 | 41.759 | 41.174 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.2 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 6 7 6
X5/Y3-3 | SGBM03 | Oct 30 2015 6:39PM | Oct 31 2015 7:43PM | Oct 31 2015 8:10PM | Oct 31 2015 9:35PM | 55.702 | 53.875 | 47.51 | 0.00 | 25.708 | 29.994 | 28.167 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
F/63-1 | SGBM23 | Oct 31 2015 8:00AM | Oct 31 2015 12:10PM | Oct 31 2015 5:56PM | Oct 31 2015 7:50PM | 51.91 | 51.275 | 52.66 | 0.00 | 10.863 | 41.047 | 40.412 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.7 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 2 10 10 6
X5a/Y4-1 | SGBM03 | Oct 30 2015 6:19PM | Oct 31 2015 1:51PM | Oct 31 2015 2:58PM | Oct 31 2015 5:40PM | 55.828 | 51.075 | 47.61 | 0.00 | 21.811 | 34.017 | 29.264 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -18.6 | G45T2 | 1 2 3 4 | 6 6 6 5
D/59-1 | SGBM23 | Oct 30 2015 8:10PM | Oct 31 2015 8:49AM | Oct 31 2015 12:24PM | Oct 31 2015 2:20PM | 51.8 | 51.375 | 52.65 | 0.00 | 12.947 | 38.853 | 38.428 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.4 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
M/26-1 | SGBM20 | Oct 29 2015 8:44PM | Oct 30 2015 8:50PM | Oct 31 2015 10:49AM | Oct 31 2015 12:35PM | 53.34 | 51.375 | 45.14 | 0.00 | 30.840 | -54063.400 | 20.535 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
D/54-1 | SGBM17 | Oct 30 2015 8:00AM | Oct 30 2015 5:27PM | Oct 30 2015 9:55PM | Oct 31 2015 12:40AM | 52.03 | 51.375 | 52.87 | 0.00 | 10.371 | 41.659 | 41.004 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 2 11 11 11
F/62-1 | SGBM15 | Oct 30 2015 11:45AM | Oct 30 2015 5:50PM | Oct 30 2015 8:35PM | Oct 30 2015 11:00PM | 51.903 | 51.275 | 52.73 | 0.00 | 10.033 | 41.870 | 41.242 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.2 | 29.0 | 10.5 | G45T2 | 1 2 3 | 10 10 9
T/26-1 | SGBM22 | Oct 30 2015 3:20PM | Oct 30 2015 6:30PM | Oct 30 2015 7:50PM | Oct 30 2015 10:50PM | 52.24 | 51.375 | 52.88 | 0.00 | 32.775 | 19.465 | 18.600 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.8 | 15.0 | 3.2 | G45T2 | 1 2 3 | 7 6 2
M/23-1 | SGBM20 | Oct 30 2015 8:55AM | Oct 30 2015 4:57PM | Oct 30 2015 8:47PM | Oct 30 2015 10:00PM | 53.56 | 52.775 | 45.64 | 0.00 | 32.736 | 21.900 | 20.039 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.7 | 18.0 | -12.8 | G45T2 | 1 2 3 | 6 6 6
D/60-1 | SGBM23 | Oct 30 2015 8:00AM | Oct 30 2015 12:56PM | Oct 30 2015 3:35PM | Oct 30 2015 7:35PM | 51.93 | 51.375 | 52.75 | 0.00 | 14.352 | 37.578 | 37.023 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.6 | 30.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 3
U/27-1 | SGBM22 | Oct 29 2015 3:20PM | Oct 29 2015 8:12PM | Oct 30 2015 3:54AM | Oct 30 2015 6:12AM | 52.045 | 51.375 | 52.96 | 0.00 | 32.655 | 19.390 | 18.720 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.9 | 20.0 | -11.9 | G45T2 | 1 2 3 | 7 6 7
U/33-1 | SGBM03 | Oct 29 2015 5:30PM | Oct 29 2015 10:00PM | Oct 30 2015 1:02AM | Oct 30 2015 2:15AM | 52.018 | 51.325 | 53.23 | 0.00 | 30.027 | 21.991 | 21.298 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 18.0 | -13.6 | G45T2 | 1 2 3 | 6 6 6
G/22-2 | SGBM20 | Oct 28 2015 6:10PM | Oct 29 2015 7:20PM | Oct 29 2015 11:09PM | Oct 30 2015 1:15AM | 52.313 | 49.575 | 44.16 | 0.00 | 26.260 | 79.213 | 23.315 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.8 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
K/19-1 | SGBM05 | Oct 29 2015 8:40AM | Oct 29 2015 5:47PM | Oct 29 2015 9:16PM | Oct 29 2015 10:30PM | 53.46 | 52.775 | 45.35 | 0.00 | 32.155 | 22.200 | 20.620 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 16.0 | -13.1 | G45T2 | 1 2 3 | 6 6 4
D/56-1 | SGBM17 | Oct 28 2015 3:00PM | Oct 29 2015 2:15PM | Oct 29 2015 8:27PM | Oct 29 2015 10:10PM | 51.91 | 51.375 | 52.81 | 0.00 | 11.205 | 40.705 | 40.170 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.6 | 30.0 | -100.0 | G45T2 | 1 2 3 | 9 11 10
J/22-4 | SGBM20 | Oct 28 2015 8:00AM | Oct 29 2015 3:55PM | Oct 29 2015 7:47PM | Oct 29 2015 9:40PM | 52.406 | 50.575 | 44.17 | 0.00 | 27.365 | 25.041 | 23.210 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 14.8 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
Ka/61-1 | SGBM17 | Oct 28 2015 5:20PM | Oct 29 2015 11:20AM | Oct 29 2015 1:29PM | Oct 29 2015 5:35PM | 52.03 | 49.775 | 52.85 | 0.00 | 12.550 | 39.480 | 37.225 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.7 | 29.0 | -100.0 | G45T2 | C480011008 C170013243 C170013244 C480011021 | 11 8 8 2
X5/Y3-6 | SGBM21 | Oct 28 2015 6:55PM | Oct 29 2015 2:20PM | Oct 29 2015 2:47PM | Oct 29 2015 4:20PM | 55.831 | 53.875 | 47.56 | 0.00 | 25.761 | 30.070 | 28.114 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 7 8
Y/25-3a | SGBM03 | Oct 28 2015 7:50PM | Oct 29 2015 11:30AM | Oct 29 2015 1:12PM | Oct 29 2015 2:30PM | 49.818 | 47.475 | 50.77 | 0.00 | 24.070 | 25.748 | 23.405 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.9 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
T/20-1 | SGBM22 | Oct 28 2015 3:20PM | Oct 28 2015 10:00PM | Oct 28 2015 11:59PM | Oct 29 2015 1:35AM | 49.812 | 47.275 | 50.62 | 0.00 | 26.017 | 23.795 | 21.258 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 8 3
L/20-2 | SGBM19 | Oct 26 2015 9:30AM | Oct 28 2015 5:20PM | Oct 28 2015 8:25PM | Oct 28 2015 10:00PM | 53.569 | 51.275 | 45.24 | 0.00 | 31.544 | 22.025 | 19.731 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 16.0 | -100.0 | G45T2 | 1 2 3 | 6 6 4
E/54-1 | SGBM15 | Oct 28 2015 9:40AM | Oct 28 2015 3:02PM | Oct 28 2015 5:40PM | Oct 28 2015 8:30PM | 51.83 | 51.375 | 52.68 | 0.00 | 10.182 | 41.648 | 41.193 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.2 | 33.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 10 3
G/29-2 | SGBM20 | Oct 28 2015 10:31AM | Oct 28 2015 3:10PM | Oct 28 2015 5:03PM | Oct 28 2015 7:00PM | 52.151 | 49.575 | 43.98 | 0.00 | 29.278 | 22.873 | 20.297 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 12.9 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
X5a/Y4-2 | SGBM21 | Oct 27 2015 7:30PM | Oct 28 2015 5:44PM | Oct 28 2015 5:16PM | Oct 28 2015 6:40PM | 55.776 | 51.075 | 47.53 | 0.00 | 21.928 | 34.600 | 29.147 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 23.0 | -18.5 | G45T2 | 1 2 3 4 | 6 6 6 5
F/52-1 | SGBM23 | Oct 27 2015 8:30PM | Oct 28 2015 10:20AM | Oct 28 2015 12:25PM | Oct 28 2015 2:20PM | 51.895 | 51.075 | 52.78 | 0.00 | 10.577 | 41.318 | 40.498 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.8 | 30.0 | 16.4 | G45T2 | 1 2 3 | 10 10 10
H/32-2 | SGBM20 | Oct 27 2015 3:55PM | Oct 28 2015 9:25AM | Oct 28 2015 11:12AM | Oct 28 2015 12:45PM | 52.069 | 50.175 | 43.90 33.90 | 0.00 0.00 | 29.303 | 75.665 | 20.872 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.3 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
AB/31a-1 | SGBM03 | Oct 27 2015 4:20PM | Oct 27 2015 9:50PM | Oct 28 2015 1:57AM | Oct 28 2015 3:10AM | 49.647 | 48.475 | 50.40 | 0.00 | 24.801 | 24.846 | 23.674 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.1 | 18.0 | -100.0 | G35T2 | 1 2 3 | 6 6 6
U/25-2 | SGBM20 | Oct 27 2015 2:30PM | Oct 27 2015 9:30PM | Oct 28 2015 12:22AM | Oct 28 2015 2:30AM | 50.066 | 47.575 | 50.63 | 0.00 | 29.128 | 20.938 | 18.447 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.7 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 8 3
X5/Y3-1 | SGBM21 | Oct 27 2015 2:30PM | Oct 27 2015 6:20PM | Oct 27 2015 9:00PM | Oct 27 2015 10:20PM | 55.838 | 53.875 | 56.60 | 0.00 | 25.701 | 30.137 | 28.174 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
L/60-1 | SGBM15 | Oct 27 2015 11:20AM | Oct 27 2015 5:00PM | Oct 27 2015 8:05PM | Oct 27 2015 10:00PM | 52.06 | 51.075 | 52.88 | 0.00 | 14.576 | 37.484 | 36.499 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.2 | 27.0 | -100.0 | G45T2 | 1 2 3 | 11 11 5
K/52-1 | SGBM23 | Oct 27 2015 8:10AM | Oct 27 2015 2:31PM | Oct 27 2015 6:37PM | Oct 27 2015 8:00PM | 52.162 | 51.275 | 53.03 | 0.00 | 16.434 | 35.728 | 34.841 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.2 | 29.0 | -100.0 | G45T2 | 1 2 3 | 7 11 11
Y/25-3b | SGBM22 | Oct 27 2015 10:00AM | Oct 27 2015 3:00PM | Oct 27 2015 5:19PM | Oct 27 2015 6:55PM | 49.813 | 47.475 | 50.71 | 0.00 | 24.206 | 25.607 | 23.269 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.8 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
H/29-1 | SGBM20 | Oct 26 2015 5:20PM | Oct 27 2015 11:50AM | Oct 27 2015 4:32PM | Oct 27 2015 6:05PM | 52.171 | 50.375 | 43.92 | 0.00 | 30.315 | 21.856 | 20.060 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 17.0 | 33.2 | G45T2 | 1 2 3 | 7 7 3
X3/Y4-1 | SGBM21 | Oct 27 2015 8:05AM | Oct 27 2015 12:59PM | Oct 27 2015 3:00PM | Oct 27 2015 4:40PM | 55.749 | 54.725 | 47.45 | 0.00 | 25.551 | 30.198 | 29.174 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 2
L/59-1 | SGBM15 | Oct 26 2015 8:50PM | Oct 27 2015 10:50AM | Oct 27 2015 1:43PM | Oct 27 2015 3:50PM | 52.18 | 51.075 | 53.08 | 0.00 | 15.677 | 36.503 | 35.398 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 5 10 10
J/22-6 | SGBM20 | Oct 24 2015 5:13PM | Oct 27 2015 10:18AM | Oct 27 2015 12:00PM | Oct 27 2015 2:20PM | 52.361 | 50.575 | 44.07 | 0.00 | 27.172 | 25.900 | 23.403 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 14.9 | 20.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 2
T/20-2 | SGBM22 | Oct 26 2015 12:00PM | Oct 26 2015 6:10PM | Oct 26 2015 9:28PM | Oct 26 2015 11:10PM | 49.937 | 47.275 | 50.50 | 0.00 | 25.704 | 24.233 | 21.571 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.7 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
G/52-1 | SGBM23 | Oct 26 2015 10:40AM | Oct 26 2015 3:20PM | Oct 26 2015 7:43PM | Oct 26 2015 9:40PM | 51.964 | 51.375 | 52.84 | 0.00 | 12.841 | 39.123 | 38.534 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 24.5 | 27.0 | -100.0 | G45T2 | 1 2 3 | 5 11 11
J/52-1 | SGBM01 | Oct 26 2015 9:00AM | Oct 26 2015 2:29PM | Oct 26 2015 7:13PM | Oct 26 2015 8:15PM | 52.089 | 51.375 | 52.92 | 0.00 | 15.723 | 36.366 | 35.652 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.7 | 28.0 | -100.0 | G45T2 | 1 2 3 | 11 11 6
G/23-2 | SGBM20 | Oct 24 2015 3:41PM | Oct 26 2015 4:45PM | Oct 26 2015 5:38PM | Oct 26 2015 8:00PM | 52.078 | 49.575 | 43.83 32.83 | 0.00 0.00 | 28.529 | 24.300 | 21.046 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.4 | 18.0 | -100.0 | G45T2 | 1 2 3 | 5 8 5
H/52-1 | SGBM23 | Oct 25 2015 6:15PM | Oct 26 2015 8:22AM | Oct 26 2015 3:35PM | Oct 26 2015 5:40PM | 52.034 | 51.375 | 52.94 | 0.00 | 13.945 | 38.089 | 37.430 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 23.8 | 27.0 | 13.4 | G45T2 | 1 2 3 | 11 11 5
Z/40-3 | SGBM08 | Oct 26 2015 8:00AM | Oct 26 2015 2:18PM | Oct 26 2015 4:16PM | Oct 26 2015 5:35PM | 49.587 | 46.175 | 50.37 | 0.00 | 17.172 | 32.415 | 29.003 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
U/25-1 | SGBM22 | Oct 24 2015 8:00PM | Oct 26 2015 9:00AM | Oct 26 2015 11:57AM | Oct 26 2015 1:10PM | 49.937 | 47.575 | 50.74 | 0.00 | 29.345 | 20.592 | 18.230 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.6 | 15.0 | -100.0 | G45T2 | 1 2 | 7 8
X5a/Y4-6 | SGBM21 | Oct 25 2015 9:00PM | Oct 26 2015 9:02AM | Oct 26 2015 10:35AM | Oct 26 2015 12:45PM | 56.607 | 51.075 | 55.86 | 0.00 | 21.261 | 35.346 | 29.814 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 19.0 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 8 2
H/34-1 | SGBM20 | Oct 23 2015 7:00PM | Oct 24 2015 3:00PM | Oct 24 2015 8:00PM | Oct 24 2015 9:50PM | 52.155 | 51.375 | 43.93 | 0.00 | 30.428 | 22.500 | 20.947 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.3 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
L/53-1 | SGBM23 | Oct 23 2015 1:30PM | Oct 24 2015 8:18AM | Oct 24 2015 8:15PM | Oct 24 2015 9:30PM | 52.037 | 51.075 | 52.91 | 0.00 | 16.710 | 35.327 | 34.365 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 10 5
H/32-1 | SGBM20 | Oct 23 2015 6:10PM | Oct 24 2015 11:45AM | Oct 24 2015 6:30PM | Oct 24 2015 8:10PM | 52.069 | 50.175 | 43.76 | 0.00 | 29.655 | 23.100 | 20.520 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 5 6
X5/Y3-2 | SGBM21 | Oct 24 2015 10:00AM | Oct 24 2015 3:10PM | Oct 24 2015 5:13PM | Oct 24 2015 7:00PM | 55.849 | 53.875 | 56.60 | 0.00 | 25.699 | 30.150 | 28.176 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 7 8
T/25-1 | SGBM22 | Oct 24 2015 10:10AM | Oct 24 2015 2:10PM | Oct 24 2015 4:47PM | Oct 24 2015 6:50PM | 50.06 | 48.775 | 50.87 | 0.00 | 30.366 | 19.694 | 18.409 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.7 | 15.0 | 28.1 | G45T2 | 1 2 3 | 6 6 3
Z/40-2 | SGBM08 | Oct 24 2015 8:00AM | Oct 24 2015 1:00PM | Oct 24 2015 3:12PM | Oct 24 2015 6:12PM | 49.669 | 46.175 | 50.56 | 0.00 | 17.164 | 32.505 | 29.011 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 7 7 4
Z/33-1 | SGBM22 | Oct 23 2015 10:40AM | Oct 23 2015 1:18PM | Oct 23 2015 3:17PM | Oct 24 2015 4:15PM | 49.533 | 48.775 | 50.51 | 0.00 | 26.015 | 23.518 | 22.760 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.5 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 7 4
J/20-1 | SGBM19 | Oct 23 2015 9:45AM | Oct 24 2015 10:10AM | Oct 24 2015 1:59PM | Oct 24 2015 4:10PM | 53.475 | 51.575 | 45.27 31.07 | 0.00 0.00 | 28.473 | 25.800 | 23.102 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.7 | 19.0 | -14.7 | G45T2 | 1 2 3 4 | 4 6 6 3
AB/28-1 | SGBM03 | Oct 23 2015 5:40PM | Oct 23 2015 9:40PM | Oct 24 2015 1:23AM | Oct 24 2015 2:10AM | 49.781 | 48.475 | 50.61 | 0.00 | 26.013 | 23.768 | 22.462 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.3 | 20.0 | -100.0 | G35T2 | 1 2 3 | 8 6 6
H/29-3 | SGBM20 | Oct 23 2015 3:30PM | Oct 23 2015 6:09PM | Oct 23 2015 8:54PM | Oct 23 2015 11:00PM | 52.168 | 50.375 | 43.97 | 0.00 | 30.165 | 22.800 | 20.210 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 17.0 | -12.8 | G45T2 | 1 2 3 | 6 6 5
L/54-1 | SGBM23 | Oct 23 2015 2:30PM | Oct 23 2015 6:30PM | Oct 23 2015 9:19PM | Oct 23 2015 10:40PM | 52.058 | 51.075 | 52.94 | 0.00 | 16.342 | 35.716 | 34.733 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 22.1 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 11 5
L/55-1 | SGBM23 | Oct 23 2015 11:20AM | Oct 23 2015 3:26PM | Oct 23 2015 6:25PM | Oct 23 2015 8:10PM | 52.075 | 51.075 | 52.92 | 0.00 | 17.025 | 35.050 | 34.050 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.7 | 23.0 | -100.0 | G45T2 | 1 2 3 | 2 12 9
X5a/Y4-8 | SGBM21 | Oct 23 2015 11:00AM | Oct 23 2015 4:23PM | Oct 23 2015 5:01PM | Oct 23 2015 7:30PM | 55.914 | 51.075 | 56.62 | 0.00 | 22.017 | 33.897 | 29.058 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 25.0 | -100.0 | G45T2 | 1 2 3 4 5 | 4 6 6 6 3
J/22-3 | SGBM20 | Oct 22 2015 5:15PM | Oct 23 2015 12:00PM | Oct 23 2015 3:45PM | Oct 23 2015 5:20PM | 52.393 | 50.575 | 44.00 | 0.00 | 27.303 | 25.700 | 23.272 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 14.8 | 21.0 | -100.0 | G45T2 | 1 2 3 4 | 3 6 6 6
L/56-1 | SGBM23 | Oct 22 2015 9:00PM | Oct 23 2015 9:30AM | Oct 23 2015 11:12AM | Oct 23 2015 1:15PM | 51.12 | 50.775 | 52.97 | 0.00 | 16.368 | 34.752 | 34.407 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 21.9 | 25.0 | -21.9 | G45T2 | 1 2 3 4 | 7 7 7 4
G/22-1 | SGBM20 | Oct 22 2015 4:40PM | Oct 23 2015 9:00AM | Oct 23 2015 10:40AM | Oct 23 2015 12:40PM | 52.273 | 49.575 | 44.04 29.04 | 0.00 0.00 | 25.939 | 27.100 | 23.636 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.0 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
Aca/40-1 | SGBM08 | Oct 22 2015 12:20PM | Oct 22 2015 4:50PM | Oct 23 2015 3:08AM | Oct 23 2015 5:55AM | 49.515 | 49.075 | 50.39 | 0.00 | 20.990 | 28.525 | 28.085 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 18.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 5 1
Z/45-2 | SGBM08 | Oct 22 2015 11:00AM | Oct 22 2015 4:02PM | Oct 22 2015 7:28PM | Oct 22 2015 9:20PM | 49.772 | 47.425 | 50.59 | 0.00 | 20.386 | 29.386 | 27.039 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 7 5
V/33-1 | SGBM22 | Oct 22 2015 10:30AM | Oct 22 2015 2:18PM | Oct 22 2015 6:54PM | Oct 22 2015 8:00PM | 49.325 | 48.775 | 50.31 | 0.00 | 27.015 | 22.310 | 21.760 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.8 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
F/54-1 | SGBM23 | Oct 22 2015 8:10AM | Oct 22 2015 4:00PM | Oct 22 2015 5:07PM | Oct 22 2015 7:40PM | 51.776 | 51.375 | 52.62 | 0.00 | 10.923 | 40.853 | 40.452 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.7 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 4 11 11 2
G/29-1 | SGBM20 | Oct 22 2015 11:30AM | Oct 22 2015 4:00PM | Oct 22 2015 5:32PM | Oct 22 2015 7:10PM | 51.959 | 49.575 | 43.77 | 0.00 | 29.074 | 22.885 | 20.501 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.0 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
E/61-1 | SGBM15 | Oct 22 2015 8:00AM | Oct 22 2015 1:56PM | Oct 22 2015 2:42PM | Oct 22 2015 6:10PM | 51.96 | 51.375 | 52.78 | 0.00 | 12.082 | 39.878 | 39.293 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.0 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 2 10 10 6
X3/Y5-1 | SGBM21 | Oct 22 2015 8:00AM | Oct 22 2015 12:53PM | Oct 22 2015 3:20PM | Oct 22 2015 4:40PM | 55.636 | 54.725 | 56.15 | 0.00 | 26.651 | 28.985 | 28.074 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
L/29-2 | SGBM20 | Oct 21 2015 12:30PM | Oct 22 2015 9:20AM | Oct 22 2015 11:48AM | Oct 22 2015 1:20PM | 52.722 | 49.875 | 44.60 32.60 | 0.00 0.00 | 29.102 | 23.620 | 20.773 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 18.0 | -13.2 | G35T2 | 1 2 3 | 7 6 5
V/41-1 | SGBM19 | Oct 21 2015 2:20PM | Oct 21 2015 7:40PM | Oct 21 2015 10:58PM | Oct 22 2015 1:30AM | 49.466 | 47.275 | 50.19 | 0.00 | 18.689 | 30.777 | 28.586 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 4 7 7 7
J/22-1 | SGBM20 | Oct 21 2015 9:30AM | Oct 21 2015 6:00PM | Oct 21 2015 8:00PM | Oct 21 2015 10:30PM | 52.441 | 50.575 | 44.47 | 0.00 | 26.968 | 26.500 | 23.607 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 15.0 | 18.0 | -15.0 | G45T2 | 1 2 3 | 6 6 6
G/23-1 | SGBM20 | Oct 20 2015 3:37PM | Oct 21 2015 4:05PM | Oct 21 2015 5:04PM | Oct 21 2015 6:40PM | 52.034 | 49.575 | 43.92 29.92 | 0.00 0.00 | 28.317 | 23.717 | 21.258 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
G/24-1 | SGBM20 | Oct 19 2015 8:40PM | Oct 21 2015 10:45AM | Oct 21 2015 2:54PM | Oct 21 2015 4:30PM | 52.185 | 49.575 | 43.91 | 0.00 | 28.114 | 24.800 | 21.461 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.7 | 17.0 | -13.7 | G45T2 | 1 2 3 | 7 7 3
W/33-1 | SGBM22 | Oct 21 2015 8:00AM | Oct 21 2015 11:49AM | Oct 21 2015 3:10PM | Oct 21 2015 4:10PM | 49.52 | 48.775 | 50.51 | 0.00 | 27.308 | 22.212 | 21.467 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.7 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
D/53-1 | SGBM17 | Oct 20 2015 8:00PM | Oct 21 2015 12:00PM | Oct 21 2015 2:11PM | Oct 21 2015 4:00PM | 51.912 | 51.375 | 52.75 | 0.00 | 10.248 | 41.664 | 41.127 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.2 | 30.0 | -100.0 | G45T2 | 1 2 3 | 9 11 10
Y/33-1 | SGBM22 | Oct 20 2015 1:10PM | Oct 20 2015 6:35PM | Oct 21 2015 2:24AM | Oct 21 2015 3:51AM | 49.736 | 48.775 | 50.57 | 0.00 | 27.373 | 22.363 | 21.402 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 6 6
X/33-1 | SGBM03 | Oct 20 2015 4:00PM | Oct 20 2015 10:00PM | Oct 21 2015 12:41AM | Oct 21 2015 2:10AM | 49.651 | 48.775 | 50.57 | 0.00 | 27.571 | 22.080 | 21.204 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 3 | 6 6 6
X7/Y5-1 | SGBM21 | Oct 20 2015 8:13AM | Oct 20 2015 2:00PM | Oct 21 2015 12:18AM | Oct 21 2015 2:00AM | 55.805 | 54.075 | 47.53 | 0.00 | 27.933 | 27.872 | 26.142 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
G/28-1 | SGBM20 | Oct 20 2015 2:30PM | Oct 20 2015 8:55PM | Oct 20 2015 10:35PM | Oct 20 2015 11:55PM | 0 | 49.575 | -9.00 | 0.00 | -24.500 | 24.500 | 74.075 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 47.1 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 5 6
X5a/Y4-7 | SGBM21 | Oct 20 2015 8:30AM | Oct 20 2015 7:00PM | Oct 20 2015 8:20PM | Oct 20 2015 10:40PM | 55.843 | 51.075 | 47.60 | 0.00 | 21.903 | 33.940 | 29.172 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 5
Aca/41-1 | SGBM08 | Oct 20 2015 12:20PM | Oct 20 2015 4:00PM | Oct 20 2015 1:08PM | Oct 20 2015 3:55PM | 49.583 | 49.075 | 50.47 | 0.00 | 21.067 | 28.516 | 28.008 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 18.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 5 1
Aca/39-1 | SGBM08 | Oct 19 2015 6:00PM | Oct 19 2015 9:52PM | Oct 20 2015 4:22AM | Oct 20 2015 6:55AM | 49.515 | 49.075 | 50.39 | 0.00 | 20.990 | 28.525 | 28.085 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
Aca/37-1 | SGBM08 | Oct 19 2015 3:25PM | Oct 19 2015 8:06PM | Oct 20 2015 3:04AM | Oct 20 2015 5:00AM | 49.59 | 49.075 | 50.47 | 0.00 | 23.074 | 26.516 | 26.001 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.5 | 20.0 | -100.0 | G45T2 | 1 2 3 | 7 7 6
G/27-2 | SGBM20 | Oct 19 2015 3:50PM | Oct 19 2015 8:20PM | Oct 19 2015 11:07PM | Oct 20 2015 1:35AM | 52.238 | 49.575 | 43.89 | 0.00 | 28.289 | 23.949 | 21.286 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.5 | 21.0 | -13.5 | G45T2 | 1 2 3 4 | 6 6 6 3
X6/Y5-1 | SGBM21 | Oct 19 2015 12:25PM | Oct 19 2015 7:00PM | Oct 19 2015 9:17PM | Oct 19 2015 10:30PM | 55.753 | 54.075 | 47.32 | 0.00 | 28.023 | 28.300 | 26.052 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 22.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 4 4
AA/32-2 | SGBM03 | Oct 19 2015 12:30PM | Oct 19 2015 4:20PM | Oct 19 2015 6:14PM | Oct 19 2015 7:50PM | 49.728 | 47.875 | 50.47 | 0.00 | 25.172 | 24.556 | 22.703 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.4 | 21.0 | -100.0 | G35T2 | 1 2 3 | 7 7 7
X/41-1 | SGBM19 | Oct 18 2015 8:00AM | Oct 19 2015 11:45AM | Oct 19 2015 5:26PM | Oct 19 2015 7:25PM | 49.859 | 47.475 | 41.37 30.57 | 0.00 0.00 | 19.769 | 30.090 | 27.706 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.6 | 21.0 | -17.6 | G45T2 | 1 2 3 | 7 7 7
E/53-1 | SGBM18 | Oct 18 2015 7:45PM | Oct 19 2015 1:30PM | Oct 19 2015 4:54PM | Oct 19 2015 6:25PM | 51.732 | 51.375 | 52.67 | 0.00 | 10.275 | 41.457 | 41.100 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.2 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 4 7 4 7 6 4
H/56-8 | SGBM17 | Oct 17 2015 5:20PM | Oct 20 2015 2:10PM | Oct 19 2015 3:53PM | Oct 19 2015 6:05PM | 51.782 | 46.875 | 44.30 29.30 21.30 | 0.00 0.00 0.00 | 5.799 | 45.983 | 41.076 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 31.0 | -26.1 | G45T2 | 1 2 3 4 5 | 7 6 7 7 4
Z/20-1 | SGBM08 | Oct 19 2015 10:00AM | Oct 19 2015 2:20PM | Oct 19 2015 3:40PM | Oct 19 2015 5:20PM | 49.912 | 48.475 | 50.42 | 0.00 | 26.220 | 23.692 | 22.255 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 7 4
Aca/36a-1 | SGBM08 | Oct 17 2015 3:30PM | Oct 17 2015 6:05PM | Oct 17 2015 10:07PM | Oct 17 2015 11:56PM | 49.588 | 49.075 | 50.51 | 0.00 | 24.015 | 25.573 | 25.060 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.9 | 20.0 | -100.0 | G45T2 | 1 2 | 9 11
G/28-2 | SGBM20 | Oct 16 2015 1:55PM | Oct 17 2015 8:10PM | Oct 17 2015 8:43PM | Oct 17 2015 11:00PM | 51.978 | 49.575 | 52.72 | 0.00 | 28.220 | 23.758 | 21.355 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.6 | 18.0 | -100.0 | G45T2 | 1 2 3 4 | 3 7 4 4
H/29-2 | SGBM20 | Oct 16 2015 2:40PM | Oct 17 2015 4:25PM | Oct 17 2015 7:34PM | Oct 17 2015 9:30PM | 52.139 | 50.375 | 43.88 | 0.00 | 30.379 | 21.760 | 19.996 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.7 | 18.0 | 41.5 | G45T2 | 1 2 3 | 7 7 4
H/36-1 | SGBM23 | Oct 17 2015 1:30PM | Oct 17 2015 4:20PM | Oct 17 2015 6:48PM | Oct 17 2015 8:50PM | 52.069 | 51.375 | 43.96 | 0.00 | 31.460 | 20.609 | 19.915 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.7 | 18.0 | -100.0 | G45T2 | 1 2 | 11 7
Aca/38-1 | SGBM08 | Oct 17 2015 9:45AM | Oct 17 2015 3:00PM | Oct 17 2015 5:43PM | Oct 17 2015 8:00PM | 49.553 | 49.075 | 50.32 | 0.00 | 22.017 | 27.536 | 27.058 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 21.0 | 22.0 | G45T2 | 1 2 3 | 7 7 7
G/24-2 | SGBM20 | Oct 17 2015 10:50AM | Oct 17 2015 1:35PM | Oct 17 2015 2:40PM | Oct 17 2015 4:30PM | 52.115 | 49.575 | 53.01 | 0.00 | 27.515 | 24.600 | 22.060 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 14.0 | 20.0 | 42.5 | G45T2 | 1 2 3 | 6 7 7
X7/Y5-2 | SGBM21 | Oct 17 2015 8:30AM | Oct 17 2015 12:10PM | Oct 17 2015 1:21PM | Oct 17 2015 3:50PM | 55.78 | 54.075 | 56.56 | 0.00 | 28.064 | 27.716 | 26.011 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.5 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
H/56-14 | SGBM18 | Oct 17 2015 8:00AM | Oct 17 2015 12:40PM | Oct 17 2015 1:04PM | Oct 17 2015 3:00PM | 51.57 | 46.875 | 52.60 | 0.00 | 5.805 | 45.765 | 41.070 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
G/27-1 | SGBM20 | Oct 16 2015 1:20PM | Oct 17 2015 10:20AM | Oct 17 2015 12:35PM | Oct 17 2015 2:00PM | 52.027 | 49.575 | 43.79 | 0.00 | 28.288 | 23.739 | 21.287 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
AA/32-1 | SGBM22 | Oct 16 2015 6:20PM | Oct 16 2015 10:00PM | Oct 16 2015 11:43PM | Oct 17 2015 1:05AM | 49.736 | 47.875 | 50.81 | 0.00 | 25.210 | 24.526 | 22.665 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.4 | 18.0 | -100.0 | G35T2 | 1 2 3 | 4 7 7
X6/Y5-3 | SGBM21 | Oct 16 2015 1:00PM | Oct 16 2015 5:45PM | Oct 16 2015 8:24PM | Oct 16 2015 11:10PM | 55.75 | 54.075 | 56.38 | 0.00 | 27.877 | 27.873 | 26.198 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 23.0 | 38.0 | G45T2 | 1 2 3 4 | 3 6 7 7
H/56-10 | SGBM18 | Oct 16 2015 8:00AM | Oct 16 2015 4:00PM | Oct 16 2015 5:50PM | Oct 16 2015 7:20PM | 51.777 | 46.875 | 52.54 | 0.00 | 5.345 | 46.432 | 41.530 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.4 | 29.5 | -100.0 | G45T2 | 1 2 3 | 8 11 10.5
G/53-1 | SGBM18 | Oct 16 2015 8:30AM | Oct 16 2015 1:30PM | Oct 16 2015 3:12PM | Oct 16 2015 5:30PM | 51.9 | 51.375 | 52.79 | 0.00 | 12.086 | 39.814 | 39.289 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.0 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 6 4 9 11
H/33-1 | SGBM20 | Oct 16 2015 8:00AM | Oct 16 2015 10:43AM | Oct 16 2015 12:36PM | Oct 16 2015 2:10PM | 52.192 | 51.375 | 53.02 | 0.00 | 30.524 | 21.668 | 20.851 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.3 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 7 4
J/22-2 | SGBM20 | Oct 15 2015 6:15PM | Oct 15 2015 9:55PM | Oct 15 2015 11:44PM | Oct 16 2015 12:35AM | 52.434 | 50.575 | 44.12 | 0.00 | 27.415 | 25.019 | 23.160 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 14.7 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
Y/40a-5 | SGBM19 | Oct 15 2015 1:15PM | Oct 15 2015 7:50PM | Oct 15 2015 10:50PM | Oct 16 2015 12:30AM | 49.54 | 46.175 | 41.55 | 0.00 | 18.152 | 31.388 | 28.023 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 21.0 | -17.8 | G45T2 | 1 2 3 | 7 7 7
W/20-1 | SGBM03 | Oct 15 2015 9:50AM | Oct 15 2015 4:45PM | Oct 15 2015 9:22PM | Oct 15 2015 10:55PM | 49.738 | 48.475 | 50.84 | 0.00 | 26.738 | 23.000 | 21.737 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.8 | 20.0 | -100.0 | G45T2 | 1 2 | 9 11
G/26-1 | SGBM20 | Oct 15 2015 12:00PM | Oct 15 2015 3:30PM | Oct 15 2015 6:21PM | Oct 15 2015 8:20PM | 52.147 | 49.575 | 52.82 | 0.00 | 28.424 | 23.723 | 21.151 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 7 4
L/30-1 | SGBM20 | Oct 13 2015 11:30AM | Oct 15 2015 10:40AM | Oct 15 2015 11:05AM | Oct 15 2015 12:30PM | 53.37 | 49.875 | 44.12 | 0.00 | 29.124 | 24.246 | 20.751 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 17.0 | -13.2 | G35T2 | 1 2 3 | 6 6 5
X7/Y5-3 | SGBM21 | Oct 13 2015 2:45PM | Oct 13 2015 7:20PM | Oct 13 2015 9:20PM | Oct 13 2015 11:40PM | 55.828 | 54.075 | 56.57 | 0.00 | 27.871 | 27.957 | 26.204 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 26.0 | -16.7 | G45T2 | 1 2 3 | 11 11 4
Y/40a-3 | SGBM19 | Oct 13 2015 8:00AM | Oct 13 2015 5:50PM | Oct 13 2015 8:44PM | Oct 13 2015 10:30PM | 49.606 | 46.175 | 41.44 36.74 | 0.00 0.00 | 17.937 | 31.669 | 28.238 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 21.0 | -18.0 | G45T2 | 1 2 3 | 7 7 7
T/21-1 | SGBM22 | Oct 13 2015 8:10AM | Oct 13 2015 2:15PM | Oct 13 2015 6:55PM | Oct 13 2015 8:55PM | 49.827 | 49.075 | 50.63 | 0.00 | 27.831 | 21.996 | 21.244 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 22.0 | -100.0 | G45T2 | 1 2 3 4 | 4 7 4 7
J/22-7 | SGBM20 | Oct 13 2015 8:00AM | Oct 13 2015 3:00PM | Oct 13 2015 4:55PM | Oct 13 2015 7:35PM | 52.477 | 50.575 | -9.00 | 0.00 | -26.300 | 78.777 | 76.875 |  | 0.0 | 0.0 | 0.0 | 9T20 | - | - | T12-250 | - | - | - |  | - | 48.9 | 18.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 2 2
AA/41-1 | SGBM19 | Oct 13 2015 8:10AM | Oct 13 2015 12:30PM | Oct 13 2015 3:28PM | Oct 13 2015 5:20PM | 49.572 | 48.725 | 50.44 | 0.00 | 22.639 | 26.933 | 26.086 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 18.0 | -100.0 | G35T2 | 1 2 3 | 7 7 4
X6/Y5-2 | SGBM21 | Oct 13 2015 10:30AM | Oct 13 2015 2:35PM | Oct 13 2015 4:18PM | Oct 13 2015 5:20PM | 55.813 | 54.075 | 56.58 | 0.00 | 27.877 | 27.936 | 26.198 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 21.0 | -16.7 | G45T2 | 1 2 3 | 7 7 7
G/25-1 | SGBM20 | Oct 12 2015 9:00PM | Oct 13 2015 12:00PM | Oct 13 2015 2:32PM | Oct 13 2015 5:00PM | 52.027 | 49.575 | 43.84 | 0.00 | 28.182 | 23.845 | 21.393 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.6 | 18.0 | -13.6 | G45T2 | 1 2 3 | 7 7 4
K/34-1 | SGBM20 | Oct 12 2015 2:00PM | Oct 12 2015 7:00PM | Oct 13 2015 1:18AM | Oct 13 2015 3:00AM | 52.082 | 51.375 | 43.90 | 0.00 | 30.097 | 21.985 | 21.278 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 16.0 | -13.5 | G45T2 | 1 2 3 | 7 7 2
X/41-2 | SGBM19 | Oct 12 2015 3:00PM | Oct 12 2015 7:30PM | Oct 13 2015 12:31AM | Oct 13 2015 2:00AM | 49.958 | 47.475 | 50.54 | 0.00 | 20.038 | 29.920 | 27.437 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.5 | 19.0 | -100.0 | G45T2 | 1 2 3 | 7 7 5
AA/42-1 | SGBM08 | Oct 12 2015 1:00PM | Oct 12 2015 5:35PM | Oct 12 2015 9:35PM | Oct 13 2015 12:20AM | 49.533 | 48.725 | 50.48 | 0.00 | 22.678 | 26.855 | 26.047 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 19.0 | -100.0 | G35T2 | 1 2 | 7 12
X5a/Y4-4 | SGBM21 | Oct 12 2015 9:30AM | Oct 12 2015 4:00PM | Oct 12 2015 9:41PM | Oct 12 2015 11:55PM | 55.827 | 51.075 | 56.71 | 0.00 | 21.908 | 33.919 | 29.167 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 26.0 | -18.6 | G45T2 | 1 2 3 4 | 7 7 7 5
H/56-4 | SGBM18 | Oct 10 2015 7:00PM | Oct 12 2015 4:30PM | Oct 12 2015 7:33PM | Oct 12 2015 10:20PM | 51.815 | 46.875 | 52.70 | 0.00 | 5.798 | 46.017 | 41.077 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 35.0 | -100.0 | G45T2 | 1 1 3 4 | 5 10 9 11
J/34-1 | SGBM20 | Oct 11 2015 8:03AM | Oct 12 2015 11:15AM | Oct 12 2015 11:50AM | Oct 12 2015 1:10PM | 52.082 | 51.375 | 43.90 30.40 | 0.00 0.00 | 30.202 | 21.880 | 21.173 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
J/33-1 | SGBM09 | Oct 10 2015 5:00PM | Oct 10 2015 8:00PM | Oct 10 2015 9:59PM | Oct 10 2015 11:00PM | 52.072 | 51.375 | 43.82 | 0.00 | 30.522 | 21.550 | 20.853 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.3 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
F/53-1 | SGBM18 | Oct 9 2015 7:30PM | Oct 10 2015 2:00PM | Oct 10 2015 4:00PM | Oct 10 2015 6:00PM | 51.882 | 51.375 | 52.61 | 0.00 | 11.310 | 40.572 | 40.065 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.5 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 10 10
J/22-8 | SGBM20 | Oct 10 2015 10:30AM | Oct 10 2015 2:05PM | Oct 10 2015 2:13PM | Oct 10 2015 3:45PM | 52.373 | 50.575 | 44.13 | 0.00 | 27.435 | 24.938 | 23.140 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 14.7 | 16.0 | 8.7 | G45T2 | 1 2 3 | 7 7 2
H/56-17 | SGBM18 | Oct 9 2015 9:40AM | Oct 9 2015 6:45PM | Oct 10 2015 10:33AM | Oct 10 2015 12:00PM | 51.869 | 46.875 | 44.67 | 0.00 | 5.768 | 46.101 | 41.107 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.2 | 31.0 | -26.1 | G45T2 | 1 2 3 4 | 9 10 10 2
G/26-2 | SGBM20 | Oct 9 2015 7:00PM | Oct 9 2015 11:10PM | Oct 9 2015 11:15PM | Oct 10 2015 1:00AM | 52.041 | 49.575 | 43.86 | 0.00 | 28.261 | 23.780 | 21.314 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.6 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
AA/21-1 | SGBM20 | Oct 9 2015 9:20AM | Oct 9 2015 6:25PM | Oct 9 2015 9:27PM | Oct 9 2015 10:20PM | 49.832 | 48.775 | 50.54 | 0.00 | 26.338 | 23.494 | 22.437 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.3 | 18.0 | 26.1 | G35T2 | 1 2 | 10 8
T/24-1 | SGBM22 | Oct 8 2015 12:00PM | Oct 8 2015 6:50PM | Oct 9 2015 12:00AM | Oct 9 2015 3:20AM | 49.795 | 49.075 | 50.42 | 0.00 | 28.918 | 20.877 | 20.157 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 17.0 | -100.0 | G45T2 | 1 2 | 5 12
L/34-1 | SGBM21 | Oct 8 2015 7:30PM | Oct 8 2015 10:37PM | Oct 8 2015 10:45PM | Oct 9 2015 1:30AM | 52.032 | 51.075 | 43.91 | 0.00 | 29.707 | 22.325 | 21.368 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
H/56-19 | SGBM18 | Oct 7 2015 9:50AM | Oct 7 2015 12:50PM | Oct 8 2015 8:05PM | Oct 8 2015 11:30PM | 51.854 | 46.875 | 43.63 | 0.00 | 5.826 | 46.028 | 41.049 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 31.0 | -26.1 | G45T2 | 1 2 3 | 11 10 10
Z/31-2 | SGBM19 | Oct 8 2015 10:00AM | Oct 8 2015 5:30PM | Oct 8 2015 10:13PM | Oct 8 2015 11:00PM | 50.01 | 47.425 | 50.82 | 0.00 | 26.223 | 23.787 | 21.202 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G45T2 | 1 2 | 7 11
N/40-1 | SGBM21 | Oct 8 2015 2:00PM | Oct 8 2015 5:43PM | Oct 8 2015 7:10PM | Oct 8 2015 8:45PM | 52.01 | 50.575 | 52.63 | 0.00 | 28.375 | 23.635 | 22.200 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.1 | 16.0 | -100.0 | G45T2 | 1 2 3 | 2 7 7
X5a/Y4-3 | SGBM09 | Oct 8 2015 8:00AM | Oct 8 2015 1:00PM | Oct 8 2015 4:15PM | Oct 8 2015 6:00PM | 55.802 | 51.075 | 56.57 | 0.00 | 21.871 | 33.931 | 29.204 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 21.0 | -18.6 | G45T2 | 1 2 3 | 7 7 7
L/31-2 | SGBM20 | Oct 8 2015 10:00AM | Oct 8 2015 1:40PM | Oct 8 2015 2:40PM | Oct 8 2015 5:00PM | 52.266 | 49.875 | 43.91 | 0.00 | 29.109 | 23.157 | 20.766 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 16.0 | -13.2 | G35T2 | 1 2 3 | 7 7 2
T/23-1 | SGBM22 | Oct 7 2015 12:00PM | Oct 7 2015 7:05PM | Oct 8 2015 1:20AM | Oct 8 2015 4:10AM | 49.795 | 49.075 | 50.42 | 0.00 | 28.918 | 20.877 | 20.157 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.8 | 18.0 | -100.0 | G45T2 | 1 2 | 8 10
AA/30-1 | SGBM19 | Oct 7 2015 8:30AM | Oct 7 2015 3:00PM | Oct 7 2015 5:25PM | Oct 7 2015 7:50PM | 50.107 | 48.725 | 50.91 | 0.00 | 26.414 | 23.693 | 22.311 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 18.0 | -100.0 | G35T2 | 1 2 3 | 7 7 4
G/25-2 | SGBM23 | Oct 7 2015 8:00AM | Oct 7 2015 12:19PM | Oct 7 2015 1:19PM | Oct 7 2015 5:00PM | 51.998 | 49.575 | 43.90 | 0.00 | 28.395 | 23.603 | 21.180 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-225 | - | - | - | 12 | - | 13.5 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
L/30-2 | SGBM20 | Oct 6 2015 11:00AM | Oct 6 2015 4:30PM | Oct 6 2015 7:59PM | Oct 6 2015 10:20PM | 52.375 | 49.875 | 44.26 | 0.00 | 28.665 | 23.710 | 21.210 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 18.0 | -100.0 | G35T2 | 1 2 3 | 7 7 4
P/17-1 | SGBM09 | Oct 6 2015 8:00AM | Oct 6 2015 1:23PM | Oct 6 2015 7:32PM | Oct 6 2015 9:00PM | 55.789 | 53.875 | 56.54 | 0.00 | 31.737 | 24.052 | 22.138 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.1 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
L/32-1 | SGBM20 | Oct 5 2015 8:00PM | Oct 6 2015 2:15PM | Oct 6 2015 4:36PM | Oct 6 2015 7:00PM | 52.21 | 49.825 | 44.08 | 0.00 | 29.085 | 23.125 | 20.740 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 16.0 | 2.8 | G45T2 | 1 2 3 | 7 7 2
Y/40a-4 | SGBM03 | Oct 6 2015 8:00AM | Oct 6 2015 12:00PM | Oct 6 2015 3:40PM | Oct 6 2015 6:00PM | 49.583 | 46.175 | 50.48 | 0.00 | 17.676 | 31.907 | 28.499 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
Z/31-1 | SGBM22 | Oct 5 2015 8:30AM | Oct 6 2015 7:35PM | Oct 6 2015 2:05PM | Oct 6 2015 3:30PM | 50.051 | 47.425 | 50.95 | 0.00 | 26.254 | 23.797 | 21.171 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 3 10 4
H/56-16 | SGBM18 | Oct 5 2015 1:00PM | Oct 5 2015 10:00PM | Oct 6 2015 11:25AM | Oct 6 2015 1:50PM | 51.9 | 46.875 | 43.72 | 0.00 | 5.825 | 46.075 | 41.050 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 30.0 | -26.1 | G45T2 | 1 2 3 4 5 | 7 7 7 7 2
Z/40-4 | SGBM21 | Oct 3 2015 8:00AM | Oct 5 2015 8:12AM | Oct 5 2015 3:28PM | Oct 5 2015 5:10PM | 49.654 | 46.175 | 50.47 | 0.00 | 16.969 | 32.685 | 29.206 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -18.6 | G45T2 | 1 2 3 | 9 9 4
N/39-1 | SGBM08 | Oct 3 2015 8:00PM | Oct 5 2015 8:12AM | Oct 5 2015 12:12PM | Oct 5 2015 2:10PM | 51.99 | 51.375 | 52.74 | 0.00 | 29.436 | 22.554 | 21.939 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.0 | 19.0 | -100.0 | G45T2 | 1 2 3 | 11 7 1
Y/39a-4 | SGBM21 | Oct 3 2015 2:00PM | Oct 5 2015 8:41AM | Oct 5 2015 12:30PM | Oct 5 2015 2:00PM | 49.65 | 46.175 | 50.24 | 0.00 | 18.136 | 31.514 | 28.039 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 22.0 | -17.8 | G45T2 | 1 2 | 11 11
H/56-13 | SGBM17 | Oct 2 2015 5:00PM | Oct 3 2015 2:50PM | Oct 3 2015 8:07PM | Oct 3 2015 10:30PM | 51.846 | 46.875 | 46.62 33.02 | 0.00 0.00 | 5.817 | 46.029 | 41.058 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 5 10 12 3
Y/40a-8 | SGBM21 | Oct 2 2015 4:10PM | Oct 2 2015 9:40PM | Oct 3 2015 5:10PM | Oct 3 2015 7:15PM | 49.573 | 46.175 | 42.46 | 0.00 | 18.061 | 31.512 | 28.114 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 23.0 | -100.0 | G45T2 | 1 2 3 | 10 11 2
Z/32-1 | SGBM19 | Oct 2 2015 8:30AM | Oct 3 2015 3:00PM | Oct 3 2015 4:53PM | Oct 3 2015 6:30PM | 49.939 | 47.575 | 50.82 | 0.00 | 25.316 | 24.623 | 22.259 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 19.0 | -100.0 | G45T2 | 1 2 | 12 7
Y/40a-2 | SGBM03 | Oct 2 2015 11:40AM | Oct 2 2015 9:00PM | Oct 3 2015 3:34PM | Oct 3 2015 5:30PM | 49.605 | 46.175 | 42.33 | 0.00 | 17.325 | 32.280 | 28.850 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.4 | 25.0 | -100.0 | G45T2 | 1 2 4 | 9 12 4
P/36-2 | SGBM08 | Oct 2 2015 8:00PM | Oct 3 2015 10:10AM | Oct 3 2015 3:51PM | Oct 3 2015 5:20PM | 51.898 | 49.725 | 52.83 | 0.00 | 32.725 | 19.173 | 17.000 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.8 | 18.0 | -10.8 | G45T2 | 1 2 | 12 6
X/41-3 | SGBM21 | Oct 2 2015 10:30AM | Oct 2 2015 5:25PM | Oct 3 2015 12:30PM | Oct 3 2015 2:41PM | 49.552 | 47.475 | 42.42 34.42 | 0.00 0.00 | 19.524 | 30.028 | 27.951 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 22.0 | -100.0 | G45T2 | 1 2 3 | 5 5 12
L/31-1 | SGBM20 | Oct 3 2015 9:00AM | Oct 3 2015 12:09PM | Oct 3 2015 12:45PM | Oct 3 2015 2:00PM | 52.215 | 49.875 | 43.89 | 0.00 | 29.192 | 23.023 | 20.683 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 15.0 | -100.0 | G35T2 | 1 2 | 8 7
Z/41-3 | SGBM21 | Oct 1 2015 7:05PM | Oct 2 2015 10:15AM | Oct 2 2015 7:53PM | Oct 2 2015 9:40PM | 49.671 | 47.725 | 42.51 28.51 | 0.00 0.00 | 21.214 | 28.457 | 26.511 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 9 5
L/32-2 | SGBM20 | Oct 1 2015 8:00PM | Oct 2 2015 5:30PM | Oct 2 2015 7:21PM | Oct 2 2015 9:00PM | 52.141 | 49.825 | 43.96 | 0.00 | 29.056 | 23.085 | 20.769 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 15.0 | -13.2 | G45T2 | 1 2 | 10 5
Z/40-5 | SGBM21 | Oct 1 2015 2:40PM | Oct 1 2015 8:15PM | Oct 2 2015 6:07PM | Oct 2 2015 7:05PM | 49.597 | 46.175 | 42.55 | 0.00 | 17.152 | 32.445 | 29.023 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.5 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
S/38-2 | SGBM08 | Oct 1 2015 10:00PM | Oct 2 2015 10:50AM | Oct 2 2015 5:11PM | Oct 2 2015 6:30PM | 52.635 | 49.575 | 53.41 | 0.00 | 26.575 | 26.060 | 23.000 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.6 | 18.0 | -100.0 | G45T2 | 1 2 | 7 11
Y/39a-6 | SGBM21 | Oct 1 2015 9:40AM | Oct 1 2015 3:35PM | Oct 1 2015 6:55PM | Oct 1 2015 9:20PM | 49.647 | 46.175 | 42.47 | 0.00 | 17.966 | 31.681 | 28.209 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 22.0 | -17.9 | G45T2 | 1 2 3 | 11 9 2
P/36-1 | SGBM16 | Sep 30 2015 7:10PM | Oct 1 2015 10:50AM | Oct 1 2015 5:07PM | Oct 1 2015 6:25PM | 51.974 | 49.725 | 52.65 | 0.00 | 32.653 | 19.321 | 17.072 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 10.9 | 16.0 | -100.0 | G45T2 | 1 2 | 9 7
Z/32-2 | SGBM19 | Sep 30 2015 8:30AM | Oct 1 2015 2:20PM | Oct 1 2015 4:42PM | Oct 1 2015 5:50PM | 49.939 | 47.575 | 50.81 | 0.00 | 25.207 | 24.732 | 22.368 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 18.0 | -100.0 | G45T2 | 1 2 | 8 10
Y/32-3 | SGBM22 | Sep 30 2015 3:00PM | Oct 1 2015 8:45AM | Oct 1 2015 2:00PM | Oct 1 2015 3:30PM | 49.793 | 48.075 | 50.56 | 0.00 | 26.859 | 22.934 | 21.216 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 17.0 | -100.0 | G45T2 | 1 2 | 9 8
Y/40a-6 | SGBM21 | Sep 30 2015 5:10PM | Oct 1 2015 8:30AM | Oct 1 2015 11:05AM | Oct 1 2015 12:45PM | 49.592 | 46.175 | 42.46 17.96 | 0.00 0.00 | 17.658 | 31.934 | 28.517 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 26.0 | -18.1 | G45T2 | 1 2 3 | 11 10 5
Z/26-2 | SGBM19 | Sep 30 2015 11:30AM | Sep 30 2015 7:49PM | Sep 30 2015 11:25PM | Oct 1 2015 3:00AM | 49.99 | 48.075 | 50.61 | 0.00 | 26.106 | 23.884 | 21.969 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 14.0 | 20.0 | -100.0 | G45T2 | 1 2 3 | 6 11 3
R/39-1 | SGBM08 | Sep 30 2015 11:00AM | Sep 30 2015 4:00PM | Oct 1 2015 12:21AM | Oct 1 2015 2:45AM | 52.65 | 51.375 | 53.40 | 0.00 | 28.298 | 24.352 | 23.077 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.7 | 18.0 | -14.7 | G45T2 | 1 2 | 7 11
H/56-18 | SGBM17 | Sep 25 2015 6:45PM | Sep 29 2015 6:00PM | Sep 30 2015 8:05PM | Sep 30 2015 11:30PM | 51.922 | 46.875 | 46.59 | 0.00 | 5.789 | 46.133 | 41.086 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 34.0 | -100.0 | G45T2 | 1 2 3 4 | 4 11 11 8
W/43-1 | SGBM03 | Sep 29 2015 4:45PM | Sep 30 2015 2:00PM | Sep 30 2015 8:11PM | Sep 30 2015 9:15PM | 49.611 | 48.075 | 42.44 22.44 | 0.00 0.00 | 19.439 | 30.172 | 28.636 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 22.0 | -18.2 | G45T2 | 1 2 | 11 11
W/42-1 | SGBM03 | Sep 29 2015 5:00PM | Sep 29 2015 10:40PM | Sep 30 2015 5:12PM | Sep 30 2015 7:00PM | 49.582 | 47.375 | 42.35 | 0.00 | 19.352 | 30.230 | 28.023 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 23.0 | -17.8 | G45T2 | 1 2 3 | 4 7 12
Y/39a-3 | SGBM21 | Sep 29 2015 3:15PM | Sep 29 2015 10:15PM | Sep 30 2015 1:42PM | Sep 30 2015 6:10PM | 49.627 | 46.175 | 42.69 | 0.00 | 17.795 | 31.832 | 28.380 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 23.0 | -18.1 | G45T2 | 1 2 3 4 | 4 5 10 4
R/36-1 | SGBM08 | Sep 29 2015 1:30PM | Sep 29 2015 5:50PM | Sep 30 2015 1:51PM | Sep 30 2015 3:20PM | 52.427 | 49.725 | 53.21 | 0.00 | 30.708 | 21.719 | 19.017 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.1 | 14.0 | -100.0 | G45T2 | 1 2 | 11 3
Z/40-1 | SGBM21 | Sep 28 2015 8:20PM | Sep 29 2015 2:25PM | Sep 30 2015 12:47PM | Sep 30 2015 2:10PM | 49.694 | 46.175 | 42.61 36.61 | 0.00 0.00 | 17.008 | 32.686 | 29.167 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 22.0 | -18.6 | G45T2 | 1 2 | 11 11
S/38-1 | SGBM16 | Sep 29 2015 1:00PM | Sep 29 2015 4:30PM | Sep 29 2015 11:57PM | Sep 30 2015 1:30AM | 52.693 | 49.575 | 53.53 | 0.00 | 26.526 | 26.167 | 23.049 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.7 | 17.0 | -100.0 | G45T2 | 1 2 | 11 6
Q/37-3 | SGBM16 | Sep 29 2015 8:00AM | Sep 29 2015 11:00AM | Sep 29 2015 6:00PM | Sep 29 2015 7:20PM | 52.725 | 50.175 | 53.47 | 0.00 | 30.968 | 21.757 | 19.207 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 16.0 | -12.2 | G45T2 | 1 2 | 8 8
Y/40a-1 | SGBM08 | Sep 28 2015 2:30PM | Sep 29 2015 8:18AM | Sep 29 2015 3:12PM | Sep 29 2015 5:00PM | 49.611 | 46.175 | 50.48 | 0.00 | 17.777 | 31.834 | 28.398 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.1 | 22.0 | -100.0 | G45T2 | 1 2 3 | 9 8 5
Y/32-1 | SGBM19 | Sep 28 2015 5:30PM | Sep 29 2015 9:00AM | Sep 29 2015 2:27PM | Sep 29 2015 4:20PM | 49.816 | 48.075 | 50.66 | 0.00 | 27.061 | 22.755 | 21.014 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 16.0 | -100.0 | G45T2 | 1 2 3 | 2 11 3
H/56-6 | SGBM18 | Sep 28 2015 10:00AM | Sep 28 2015 4:15PM | Sep 29 2015 4:43AM | Sep 29 2015 6:50AM | 51.964 | 46.875 | 52.81 | 0.00 | 5.806 | 46.158 | 41.069 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 38.0 | -100.0 | G45T2 | 1 2 3 4 | 11 9 9 9
H/56-2 | SGBM18 | Sep 26 2015 3:10PM | Sep 28 2015 2:30PM | Sep 28 2015 8:23PM | Sep 28 2015 10:30PM | 51.936 | 46.875 | 46.70 9.80 | 0.00 0.00 | 5.802 | 46.134 | 41.073 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 31.0 | -100.0 | G45T2 | 1 2 3 4 | 11 9 2 9
Z/26-1 | SGBM19 | Sep 26 2015 5:00PM | Sep 28 2015 2:15PM | Sep 28 2015 8:57PM | Sep 28 2015 10:30PM | 50.737 | 48.075 | 50.01 | 0.00 | 26.312 | 24.425 | 21.763 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 13.8 | 20.0 | -100.0 | G45T2 | 1 2 | 9 11
Y/39a-5 | SGBM21 | Sep 28 2015 11:00AM | Sep 28 2015 4:14PM | Sep 28 2015 6:40PM | Sep 28 2015 9:00PM | 49.607 | 46.175 | 50.30 | 0.00 | 17.997 | 31.610 | 28.178 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.9 | 25.0 | -100.0 | G45T2 | 1 2 3 | 7 11 7
W/43-3 | SGBM03 | Sep 26 2015 4:30PM | Sep 28 2015 11:00AM | Sep 28 2015 4:00PM | Sep 28 2015 5:20PM | 49.551 | 47.375 | 50.52 | 0.00 | 20.516 | 29.035 | 26.859 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
W/42-3 | SGBM21 | Sep 25 2015 11:19AM | Sep 26 2015 10:05AM | Sep 26 2015 6:20PM | Sep 26 2015 7:55PM | 49.519 | 48.075 | 42.38 22.38 | 0.00 0.00 | 19.483 | 30.036 | 28.592 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 19.0 | -100.0 | G45T2 | c520121907 c520121910 | 7 12
X/45-1 | SGBM03 | Sep 25 2015 4:05PM | Sep 26 2015 9:55AM | Sep 26 2015 5:30PM | Sep 26 2015 7:00PM | 49.61 | 47.775 | 42.29 25.29 | 0.00 0.00 | 21.495 | 28.115 | 26.280 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 23.0 | -100.0 | G45T2 | c520121904 c520121908 | 12 11
Y/37-1 | SGBM21 | Sep 23 2015 7:00PM | Sep 25 2015 12:35PM | Sep 25 2015 8:10PM | Sep 25 2015 9:45PM | 49.374 | 48.075 | 42.53 33.53 | 0.00 0.00 | 21.930 | 27.444 | 26.145 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 20.0 | -100.0 | G45T2 | c1700012734 c1700012735 | 10 10
Y/40a-7 | SGBM21 | Sep 23 2015 9:00AM | Sep 23 2015 6:30PM | Sep 25 2015 6:45PM | Sep 25 2015 8:10PM | 49.549 | 46.175 | 42.52 | 0.00 | 17.822 | 31.727 | 28.353 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.0 | 27.0 | 49.7 | G45T2 | c1700012730 c520121866 c170012731 | 9 12 6
Y/32-2 | SGBM19 | Sep 24 2015 4:00PM | Sep 25 2015 9:31AM | Sep 25 2015 5:09PM | Sep 25 2015 6:30PM | 49.768 | 48.075 | 50.60 | 0.00 | 26.905 | 22.863 | 21.170 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
Q/37-2 | SGBM16 | Sep 23 2015 4:30PM | Sep 25 2015 8:35AM | Sep 25 2015 12:00PM | Sep 25 2015 2:00PM | 52.588 | 50.175 | 45.48 31.48 | 0.00 0.00 | 30.983 | 21.605 | 19.192 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 15.0 | -100.0 | G45T2 | a1 a2 | 11 4
H/56-15 | SGBM17 | Sep 23 2015 8:00AM | Sep 23 2015 3:30PM | Sep 23 2015 9:22PM | Sep 24 2015 12:15AM | 52 | 46.875 | 52.88 | 0.00 | 5.778 | 46.222 | 41.097 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.1 | 51.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 11 11 11 8
Z/26-3 | SGBM19 | Sep 22 2015 6:05PM | Sep 23 2015 9:38AM | Sep 23 2015 3:40PM | Sep 23 2015 5:30PM | 49.928 | 48.075 | 51.05 | 0.00 | 27.049 | 22.879 | 21.026 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 13.4 | 16.0 | -100.0 | G45T2 | 1 2 | 11 5
Y/39a-2 | SGBM21 | Sep 22 2015 1:11PM | Sep 22 2015 9:55PM | Sep 23 2015 1:30PM | Sep 23 2015 2:40PM | 49.66 | 46.175 | 42.58 | 0.00 | 17.585 | 32.075 | 28.590 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.2 | 22.0 | -100.0 | G45T2 | c480009097 c480009098 | 11 11
Y/39a-7 | SGBM21 | Sep 21 2015 5:25PM | Sep 22 2015 11:40AM | Sep 22 2015 7:20PM | Sep 22 2015 10:25PM | 49.553 | 46.175 | 42.45 26.45 | 0.00 0.00 | 18.150 | 31.403 | 28.025 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.8 | 20.0 | -100.0 | G45T2 | c480009053 c480009060 | 11 9
X/45-3 | SGBM21 | Sep 21 2015 10:00AM | Sep 21 2015 5:35PM | Sep 22 2015 11:25AM | Sep 22 2015 12:45PM | 49.686 | 47.775 | 42.44 | 0.00 | 21.536 | 28.150 | 26.239 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 18.0 | 7.8 | G45T2 | c480009011 c480009013 | 7 11
H/56-12 | SGBM17 | Sep 17 2015 5:00PM | Sep 21 2015 9:00AM | Sep 21 2015 2:40PM | Sep 21 2015 6:40PM | 51.93 | 46.875 | 46.85 32.85 5.85 | 0.00 0.00 0.00 | 3.853 | 48.077 | 43.022 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 27.4 | 51.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 9 11 11 11
Y/38-3 | SGBM21 | Sep 19 2015 1:05PM | Sep 19 2015 8:15PM | Sep 21 2015 2:25PM | Sep 21 2015 4:00PM | 49.686 | 48.075 | 42.67 | 0.00 | 21.965 | 27.721 | 26.110 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 21.0 | -100.0 | G45T2 | c480008961 c480008963 c480008965 | 9 11 1
W/43-2 | SGBM03 | Sep 19 2015 8:46AM | Sep 19 2015 5:40PM | Sep 21 2015 1:30PM | Sep 21 2015 2:45PM | 49.541 | 47.375 | 42.37 | 0.00 | 20.373 | 29.168 | 27.002 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.2 | 22.0 | -100.0 | G45T2 | c480008956 c480008957 | 11 11
W/42-2 | SGBM21 | Sep 19 2015 9:00AM | Sep 19 2015 5:55PM | Sep 21 2015 12:15PM | Sep 21 2015 1:55PM | 49.464 | 47.375 | 42.30 | 0.00 | 19.503 | 29.961 | 27.872 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.7 | 22.0 | -100.0 | G45T2 | c480008951 c480008952 | 11 11
H/23-1 | SGBM15 | Sep 18 2015 11:30AM | Sep 19 2015 5:00PM | Sep 19 2015 5:25PM | Sep 19 2015 8:40PM | 52.944 | 50.375 | 43.30 | 0.00 | 28.500 | 24.444 | 21.875 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.9 | 18.0 | -100.0 | G45T2 | c480008894 c480008896 | 12 6
X/45-2 | SGBM19 | Sep 18 2015 9:50AM | Sep 18 2015 6:50PM | Sep 19 2015 2:35PM | Sep 19 2015 4:00PM | 49.629 | 47.775 | 42.48 | 0.00 | 21.579 | 28.050 | 26.196 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 25.0 | -100.0 | G45T2 | c480008877 c480008879 c480008880 | 3 11 11
L/28-2 | SGBM15 | Sep 18 2015 8:00AM | Sep 18 2015 4:00PM | Sep 18 2015 7:20PM | Sep 18 2015 10:00PM | 53.548 | 50.975 | 45.18 | 0.00 | 31.816 | 21.732 | 19.159 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 17.0 | -100.0 | G35T2 | 1 2 3 | 5 10 2
Y/39a-1 | SGBM21 | Sep 17 2015 5:00PM | Sep 18 2015 10:45AM | Sep 18 2015 4:00PM | Sep 18 2015 6:05PM | 49.67 | 46.175 | 42.47 26.47 | 0.00 0.00 | 18.368 | 31.302 | 27.807 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.7 | 22.0 | -100.0 | G45T2 | c480008823 c520121719 c520121721 | 9 9 4
Y/39a-8 | SGBM03 | Sep 17 2015 2:45PM | Sep 18 2015 8:35AM | Sep 18 2015 3:35PM | Sep 18 2015 4:50PM | 49.516 | 46.175 | 42.42 18.42 | 0.00 0.00 | 18.317 | 31.199 | 27.858 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.7 | 22.0 | -100.0 | G45T2 | c480008819 c520121716 c480008823 | 11 9 2
Q/37-1 | SGBM16 | Sep 17 2015 3:30PM | Sep 18 2015 10:40AM | Sep 18 2015 12:30PM | Sep 18 2015 2:30PM | 52.681 | 50.175 | 45.44 | 0.00 | 30.435 | 22.246 | 19.740 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 18.0 | 43.3 | G45T2 | a1 a2 a3 | 10 3 5
F/59-3 | SGBM17 | Sep 12 2015 10:30AM | Sep 17 2015 11:30AM | Sep 17 2015 10:00PM | Sep 18 2015 12:50AM | 51.935 | 50.375 | 46.77 20.97 | 0.00 0.00 | 8.372 | 43.563 | 42.003 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.7 | 34.0 | -100.0 | G45T2 | 1 2 3 4 | 6 10 9 9
U/20-1 | SGBM22 | Sep 16 2015 2:30PM | Sep 17 2015 5:05PM | Sep 17 2015 7:03PM | Sep 17 2015 8:42PM | 49.782 | 48.475 | 50.67 | 0.00 | 27.074 | 22.708 | 21.401 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 18.0 | -100.0 | G45T2 | 1 2 3 | 7 7 4
H/23-3 | SGBM15 | Sep 15 2015 1:40PM | Sep 17 2015 2:46PM | Sep 17 2015 5:00PM | Sep 17 2015 6:01PM | 52.233 | 50.375 | 43.88 | 0.00 | 29.726 | 22.507 | 20.649 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 16.0 | 2.9 | G45T2 | 1 2 | 8 8
Z/23-2 | SGBM16 | Sep 14 2015 6:00PM | Sep 15 2015 1:30PM | Sep 15 2015 6:46PM | Sep 15 2015 8:00PM | 49.851 | 47.875 | 50.85 | 0.00 | 26.548 | 23.303 | 21.327 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 16.0 | -100.0 | G35T2 | 1 2 | 6 10
Z/22-2 | SGBM08 | Sep 14 2015 4:30PM | Sep 15 2015 1:45PM | Sep 15 2015 5:32PM | Sep 15 2015 7:20PM | 49.841 | 47.875 | 50.85 | 0.00 | 26.448 | 23.393 | 21.427 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 16.0 | -100.0 | G35T2 | 1 2 | 11 5
L/29-1 | SGBM20 | Sep 14 2015 11:00AM | Sep 15 2015 11:15AM | Sep 15 2015 11:55AM | Sep 15 2015 1:00PM | 53.625 | 49.875 | 44.63 | 0.00 | 29.325 | 24.300 | 20.550 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.1 | 16.0 | 22.4 | G35T2 | c480008644 c480008645 | 11 5
W/44-1 | SGBM19 | Sep 12 2015 4:20PM | Sep 14 2015 2:15PM | Sep 14 2015 7:00PM | Sep 14 2015 11:00PM | 49.645 | 47.625 | 42.50 33.50 | 0.00 0.00 | 20.299 | 29.346 | 27.326 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.4 | 26.0 | -100.0 | G35T2 | c520121605 c480008622 c480008632 | 9 10 7
W/23-3 | SGBM16 | Sep 14 2015 11:28AM | Sep 14 2015 2:35PM | Sep 14 2015 6:20PM | Sep 14 2015 10:30PM | 49.713 | 48.075 | 42.70 | 0.00 | 28.398 | 21.315 | 19.677 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 18.0 | -100.0 | G35T2 | 1 2 3 | 6 11 1
Z/24-2 | SGBM16 | Sep 12 2015 10:00AM | Sep 14 2015 10:50AM | Sep 14 2015 4:45PM | Sep 14 2015 7:30PM | 49.919 | 47.875 | 42.90 | 0.00 | 24.902 | 25.017 | 22.973 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.6 | 23.0 | -14.6 | G35T2 | 1 2 3 | 11 2 10
H/23-2 | SGBM15 | Sep 12 2015 5:00PM | Sep 14 2015 3:00PM | Sep 14 2015 5:45PM | Sep 14 2015 7:00PM | 52.243 | 50.375 | 43.96 | 0.00 | 28.957 | 23.286 | 21.418 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 18.0 | -0.2 | G45T2 | c520121603 c170012592 c480008619 | 6 8 4
Z/25-1 | SGBM16 | Sep 11 2015 2:30PM | Sep 12 2015 10:00AM | Sep 12 2015 4:54PM | Sep 12 2015 6:25PM | 50.098 | 47.875 | 50.79 | 0.00 | 26.586 | 23.512 | 21.289 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 15.0 | -100.0 | G35T2 | 1 2 | 4 11
Z/22-1 | SGBM08 | Sep 11 2015 11:00AM | Sep 12 2015 2:30PM | Sep 12 2015 4:16PM | Sep 12 2015 6:00PM | 49.807 | 47.875 | 50.71 | 0.00 | 26.609 | 23.198 | 21.266 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 16.0 | -100.0 | G35T2 | 1 2 | 9 7
Z/25-2 | SGBM16 | Sep 11 2015 2:30PM | Sep 12 2015 10:00AM | Sep 12 2015 4:10PM | Sep 12 2015 5:50PM | 49.927 | 47.875 | 50.85 | 0.00 | 26.745 | 23.182 | 21.130 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 16.0 | -100.0 | G35T2 | 1 2 | 6 10
L/28-1 | SGBM20 | Sep 11 2015 4:00PM | Sep 12 2015 11:15AM | Sep 12 2015 1:35PM | Sep 12 2015 4:30PM | 53.524 | 50.975 | 45.05 | 0.00 | 31.250 | 22.274 | 19.725 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 15.0 | -100.0 | G35T2 | c52012154 c520121551 c520121554 | 3 11 1
D/62-1 | SGBM18 | Sep 11 2015 10:00AM | Sep 11 2015 3:05PM | Sep 11 2015 6:30PM | Sep 11 2015 8:25PM | 51.743 | 51.375 | 52.50 | 0.00 | 11.903 | 39.840 | 39.472 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 25.1 | 34.0 | 19.5 | G45T2 | 1 2 3 4 5 | 7 7 7 9 4
J/22-5 | SGBM20 | Sep 10 2015 8:30AM | Sep 11 2015 11:15AM | Sep 11 2015 11:50AM | Sep 11 2015 1:30PM | 53.481 | 50.575 | 45.21 | 0.00 | 26.114 | 27.367 | 24.461 |  | 0.0 | 0.0 | 0.0 | 9T20 | 266.328 | 266.328 | T12-250 | 115.6759 | 115.6759 | - | 12 | - | 15.6 | 27.0 | -100.0 | G45T2 | c480008436 c170012571 c480008438 | 11 10 6
F/59-2 | SGBM23 | Aug 25 2015 3:20PM | Sep 11 2015 9:29AM | Sep 11 2015 11:15AM | Sep 11 2015 1:15PM | 51.942 | 50.375 | 47.21 12.21 | 0.00 0.00 | 8.310 | 43.632 | 42.065 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.8 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 11 8 11 2
Z/24-1 | SGBM08 | Sep 9 2015 8:30AM | Sep 10 2015 7:35PM | Sep 10 2015 7:30PM | Sep 10 2015 11:30PM | 49.917 | 47.875 | 41.79 | 0.00 | 27.069 | 22.848 | 20.806 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 20.0 | -100.0 | G35T2 | 1 2 | 9 11
Z/23-1 | SGBM08 | Sep 10 2015 12:00PM | Sep 10 2015 5:00PM | Sep 10 2015 9:50PM | Sep 10 2015 10:55PM | 49.858 | 47.875 | 50.59 | 0.00 | 26.289 | 23.569 | 21.586 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.7 | 15.0 | -100.0 | G35T2 | 1 2 | 4 11
W/44-3 | SGBM19 | Sep 9 2015 8:05AM | Sep 10 2015 9:30AM | Sep 10 2015 2:15PM | Sep 10 2015 4:20PM | 49.59 | 47.625 | 42.55 21.55 | 0.00 0.00 | 20.453 | 29.137 | 27.172 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.3 | 27.0 | 56.2 | G35T2 | c480008348 c480008353 c480008359 | 11 11 5
V/26-2 | SGBM16 | Sep 8 2015 3:00PM | Sep 10 2015 9:00AM | Sep 10 2015 1:00PM | Sep 10 2015 3:05PM | 49.907 | 47.575 | 50.66 | 0.00 | 28.462 | 21.445 | 19.113 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 18.0 | -100.0 | G35T2 | 1 2 | 7 11
W/40-1 | SGBM19 | Sep 8 2015 9:55AM | Sep 8 2015 7:40PM | Sep 9 2015 11:00AM | Sep 9 2015 1:30PM | 49.398 | 49.075 | 42.28 | 0.00 | 19.885 | 29.513 | 29.190 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 18.6 | 23.0 | 23.8 | G35T2 | c480008265 c480008266 c480008272 | 11 11 1
U/22-1 | SGBM18 | Sep 8 2015 10:00AM | Sep 8 2015 2:15PM | Sep 8 2015 5:40PM | Sep 8 2015 8:30PM | 49.772 | 49.075 | 50.74 | 0.00 | 28.740 | 21.032 | 20.335 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.9 | 18.0 | -100.0 | G45T2 | 1 2 3 | 5 10 3
W/44-2 | SGBM03 | Aug 25 2015 4:50PM | Sep 8 2015 2:20PM | Sep 8 2015 3:40PM | Sep 8 2015 5:20PM | 49.551 | 47.625 | 42.33 34.33 | 0.00 0.00 | 20.728 | 28.823 | 26.897 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 17.1 | 20.0 | -100.0 | G35T2 | c480008233 c480008235 | 12 8
V/28-2 | SGBM16 | Aug 24 2015 5:30PM | Aug 25 2015 11:50AM | Aug 25 2015 2:26PM | Aug 25 2015 3:30PM | 49.798 | 47.575 | 50.69 | 0.00 | 28.288 | 21.510 | 19.287 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.3 | 15.0 | -100.0 | G35T2 | 1 2 | 4 11
Y/37-3 | SGBM19 | Aug 22 2015 5:25PM | Aug 24 2015 12:20PM | Aug 24 2015 5:10PM | Aug 24 2015 7:30PM | 49.623 | 48.075 | 42.61 35.61 | 0.00 0.00 | 21.813 | 27.810 | 26.262 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.7 | 18.0 | -100.0 | G45T2 | C480007524 c520121155 | 10 8
Y/38-1 | SGBM19 | Aug 22 2015 8:20AM | Aug 22 2015 5:05PM | Aug 24 2015 4:55PM | Aug 24 2015 6:35PM | 49.705 | 48.075 | 42.56 | 0.00 | 22.058 | 27.647 | 26.017 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 18.0 | -16.6 | G45T2 | c520121153 c480007523 c480007524 | 6 11 1
W/23-2 | SGBM16 | Aug 22 2015 1:00PM | Aug 24 2015 11:00AM | Aug 24 2015 4:30PM | Aug 24 2015 5:35PM | 49.779 | 48.075 | 50.65 | 0.00 | 28.345 | 21.434 | 19.730 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 16.0 | -100.0 | G35T2 | 1 2 | 11 5
K/27-2 | SGBM15 | Aug 21 2015 8:00AM | Aug 22 2015 1:00PM | Aug 22 2015 3:30PM | Aug 22 2015 6:00PM | 53.5 | 51.425 | 45.25 37.25 | 0.00 0.00 | 29.700 | 23.800 | 21.725 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.8 | 23.0 | -13.8 | G45T2 | 1 2 3 | 5 11 7
L/25-2 | SGBM15 | Aug 20 2015 6:00PM | Aug 21 2015 9:00AM | Aug 22 2015 11:50AM | Aug 22 2015 2:00PM | 53.445 | 50.975 | 45.18 33.18 | 0.00 0.00 | 32.011 | 21.434 | 18.964 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.1 | 19.0 | -12.1 | G35T2 | 1 2 | 11 8
Y/37-2 | SGBM19 | Aug 19 2015 2:40PM | Aug 20 2015 1:40PM | Jul 21 2015 5:30PM | Aug 21 2015 6:40PM | 49.564 | 48.075 | 44.41 36.41 | 0.00 0.00 | 21.507 | 78.464 | 26.568 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.9 | 19.0 | -100.0 | G45T2 | c480007388 c520121107 | 8 11
K/26-1 |  | Aug 19 2015 4:00PM | Aug 20 2015 4:00PM | Aug 21 2015 6:15AM | Aug 21 2015 5:30PM | 53.497 | 51.425 | 45.26 36.26 28.96 | 0.00 0.00 0.00 | 28.963 | 24.534 | 22.462 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.3 | 22.0 | -100.0 | G45T2 | c480007386 c480007387 | 11 11
L/23-2 | SGBM20 | Aug 20 2015 4:00PM | Aug 21 2015 8:12AM | Aug 21 2015 11:40AM | Aug 21 2015 2:00PM | 53.378 | 51.275 | 54.25 | 0.00 | 31.548 | 21.830 | 19.727 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 17.0 | -100.0 | G35T2 | 1 2 | 11 6
V/26-1 | SGBM16 | Aug 20 2015 2:00PM | Aug 21 2015 8:20AM | Aug 21 2015 10:25AM | Aug 21 2015 11:30AM | 49.778 | 47.575 | 50.80 | 0.00 | 28.196 | 21.582 | 19.379 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.3 | 19.0 | -100.0 | G35T2 | 1 2 | 11 8
V/28-1 | SGBM16 | Aug 19 2015 9:30AM | Aug 20 2015 11:06AM | Aug 20 2015 1:50PM | Aug 20 2015 3:20PM | 49.799 | 47.575 | 50.67 | 0.00 | 28.374 | 21.425 | 19.201 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.2 | 18.0 | -100.0 | G35T2 | 1 2 | 7 11
Y/38-2 | SGBM03 | Aug 18 2015 5:25PM | Aug 19 2015 12:50PM | Aug 20 2015 11:45AM | Aug 20 2015 2:04PM | 49.598 | 48.075 | 42.50 38.00 | 0.00 -0.50 | 22.001 | 27.597 | 26.074 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.6 | 18.0 | -100.0 | G45T2 | c480007333 c480007334 c480007340 | 3 11 4
L/22-2 | SGBM15 | Aug 18 2015 3:30PM | Aug 19 2015 11:30AM | Aug 19 2015 3:00PM | Aug 19 2015 6:03PM | 53.384 | 51.275 | 45.24 37.24 | 0.00 0.00 | 31.544 | 20.980 | 19.731 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 16.0 | 27.4 | G35T2 | 1 2 3 | 11 3 2
V/32-2 | SGBM16 | Aug 17 2015 3:00PM | Aug 19 2015 8:30AM | Aug 19 2015 3:00PM | Aug 19 2015 4:30PM | 49.795 | 47.575 | 41.61 31.41 | 0.00 0.00 | 27.927 | 21.868 | 19.648 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
L/24-2 | SGBM15 | Aug 18 2015 6:00PM | Aug 19 2015 12:30PM | Aug 19 2015 1:44PM | Aug 19 2015 3:00PM | 53.394 | 50.975 | 45.15 | 0.00 | 31.452 | 21.942 | 19.523 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.4 | 15.0 | -100.0 | G35T2 | C480007292 C480007293 | 11 4
X/35-2 | SGBM19 | Aug 18 2015 1:20PM | Aug 19 2015 9:30AM | Aug 19 2015 1:20PM | Aug 19 2015 2:20PM | 49.617 | 48.075 | 42.37 28.97 | 0.00 0.00 | 26.967 | 22.650 | 21.108 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 15.0 | -100.0 | G35T2 | c480007289 c480007291 | 11 4
K/27-1 | SGBM20 | Aug 18 2015 5:00PM | Aug 19 2015 10:15AM | Aug 19 2015 10:24AM | Aug 19 2015 12:29PM | 53.517 | 51.425 | 45.23 | 0.00 | 28.728 | 24.789 | 22.697 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.4 | 22.0 | -100.0 | G45T2 | C170012392 C170012391 C480007284 | 8 10 4
X/38-3 | SGBM19 | Aug 17 2015 3:10PM | Aug 18 2015 12:40PM | Aug 18 2015 1:35PM | Aug 18 2015 2:35PM | 49.617 | 48.075 | 42.43 31.43 | 0.00 0.00 | 22.629 | 26.988 | 25.446 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.2 | 18.0 | 11.2 | G35T2 | c480007227 c480007229 | 12 6
L/25-1 | SGBM15 | Aug 17 2015 5:45PM | Aug 18 2015 9:00AM | Aug 18 2015 10:15AM | Aug 18 2015 11:00AM | 53.414 | 50.975 | 45.19 32.19 | 0.00 0.00 | 31.289 | 22.125 | 19.686 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 15.0 | -100.0 | G35T2 | c480007216 c480007217 | 11.5 3.5
X/35-1 | SGBM19 | Aug 17 2015 8:05AM | Aug 17 2015 3:00PM | Aug 17 2015 4:40PM | Aug 17 2015 7:00PM | 49.602 | 48.075 | 42.51 | 0.00 | 27.015 | 22.587 | 21.060 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 15.0 | 11.9 | G35T2 | c480007170 c480007178 | 11 4
V/32-1 | SGBM18 | Aug 15 2015 4:00PM | Aug 17 2015 11:30AM | Aug 17 2015 3:10PM | Aug 17 2015 5:35PM | 49.789 | 47.575 | 41.83 38.43 | 0.00 0.00 | 28.061 | 21.728 | 19.514 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.4 | 17.0 | -100.0 | G35T2 | 1 2 | 11 6
K/26-2 | SGBM15 | Aug 14 2015 12:10PM | Aug 14 2015 6:15PM | Aug 15 2015 6:15PM | Aug 15 2015 8:55PM | 53.489 | 51.425 | 45.26 | 0.00 | 29.059 | 24.430 | 22.366 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 14.2 | 22.0 | -100.0 | G45T2 | c480007117 c480007115 c480007115 | 4 12 6
X/38-1 | SGBM03 | Aug 15 2015 8:05AM | Aug 15 2015 4:45PM | Aug 15 2015 6:30PM | Aug 15 2015 8:20PM | 49.604 | 48.075 | 42.38 | 0.00 | 22.679 | 26.925 | 25.396 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.2 | 20.0 | -100.0 | G35T2 | c480007117 c480007119 c480007124 | 6 12 2
W/23-1 | SGBM18 | Aug 12 2015 11:30AM | Aug 15 2015 9:45AM | Aug 15 2015 3:34PM | Aug 15 2015 6:15PM | 49.768 | 48.075 | 41.64 32.94 | 0.00 0.00 | 29.914 | 19.854 | 18.161 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 11.6 | 13.0 | -100.0 | G35T2 | 1 2 | 11 2
L/23-1 | SGBM20 | Aug 14 2015 12:10PM | Aug 15 2015 9:00AM | Aug 15 2015 3:40PM | Aug 15 2015 5:30PM | 53.394 | 51.275 | 45.11 31.71 | 0.00 0.00 | 31.614 | 21.780 | 19.661 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 17.0 | -100.0 | G35T2 | c480007103 c480007110 | 11.5 5.5
L/24-1 | SGBM20 | Aug 13 2015 4:00PM | Aug 14 2015 12:00PM | Aug 14 2015 3:30PM | Aug 14 2015 5:30PM | 53.407 | 50.975 | 45.26 | 0.00 | 31.155 | 22.252 | 19.820 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 15.0 | -100.0 | G35T2 | c480007004 c480007008 | 11 4
X/38-2 | SGBM19 | Aug 13 2015 8:05AM | Aug 13 2015 3:45PM | Aug 13 2015 7:40PM | Aug 13 2015 9:20PM | 49.624 | 48.075 | 42.46 | 0.00 | 22.757 | 26.867 | 25.318 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 16.1 | 18.0 | -100.0 | G35T2 | c480006990 c480006987 | 11 7
L/22-1 | SGBM15 | Aug 12 2015 5:15PM | Aug 13 2015 10:00AM | Aug 13 2015 10:30AM | Aug 13 2015 11:30AM | 53.395 | 51.275 | 45.13 34.13 | 0.00 0.00 | 31.430 | 21.965 | 19.845 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.6 | 17.0 | -100.0 | G35T2 | c480006949 c480006950 | 10 7
X/35-3 | SGBM03 | Aug 12 2015 9:30AM | Aug 12 2015 1:45PM | Aug 12 2015 5:05PM | Aug 12 2015 5:55PM | 49.627 | 48.075 | 50.33 | 0.00 | 26.727 | 22.900 | 21.348 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 17.0 | -100.0 | G35T2 | 1 2 | 10 7
Y/22-2 | SGBM17 | Jul 11 2015 10:20AM | Jul 11 2015 5:00PM | Aug 11 2015 10:19PM | Aug 11 2015 11:40PM | 49.785 | 48.575 | 42.54 | 0.00 | 24.737 | 23.048 | 23.838 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 15.2 | 18.0 | -100.0 | G35T2 | 1 2 | 10 8
Y/29-3 | SGBM16 | Aug 8 2015 8:30AM | Aug 8 2015 2:00PM | Aug 8 2015 5:25PM | Aug 8 2015 6:50PM | 49.893 | 48.075 | 41.77 32.37 | 0.00 0.00 | 27.651 | 22.242 | 20.424 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.0 | 22.0 | -13.0 | G35T2 | 1 2 | 11 11
Y/29-2 | SGBM20 | Aug 6 2015 7:40AM | Aug 6 2015 3:00PM | Aug 6 2015 5:15PM | Aug 6 2015 7:30PM | 49.904 | 48.075 | 50.57 | 0.00 | 26.274 | 23.630 | 21.801 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.9 | 18.0 | -100.0 | G35T2 | 1 2 | 8 10
F/59-1 | SGBM17 | Aug 4 2015 8:00AM | Aug 5 2015 7:00PM | Aug 5 2015 9:50PM | Aug 5 2015 10:40PM | 51.98 | 50.375 | 44.74 | 0.00 | 8.335 | 43.645 | 42.040 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - | 12 | - | 26.7 | 38.0 | -100.0 | G45T2 | c480006473 c480006470 c480006475 c480006476 | 11 5 11 11
Y/29-1 | SGBM16 | Aug 4 2015 9:30AM | Aug 4 2015 5:00PM | Aug 4 2015 9:35PM | Aug 4 2015 11:30PM | 49.951 | 48.075 | 41.88 34.58 | 0.00 0.00 | 27.305 | 22.646 | 20.770 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 16.5 | -13.2 | G35T2 | 1 2 3 | 4 11 1.5
Y/26-3 | SGBM17 | Jul 24 2015 11:00AM | Jul 24 2015 4:30PM | Jul 25 2015 2:50AM | Jul 25 2015 4:20AM | 49.812 | 48.575 | 50.61 | 0.00 | 27.512 | 22.300 | 21.063 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
Y/24-3 | SGBM16 | Jul 23 2015 3:30PM | Jul 23 2015 8:20PM | Jul 24 2015 1:20AM | Jul 24 2015 2:50AM | 49.796 | 48.575 | 50.47 | 0.00 | 27.372 | 22.424 | 21.203 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.5 | 16.0 | -100.0 | G35T2 | 1 2 | 11 5
X/24-3 | SGBM17 | Jul 22 2015 8:30AM | Jul 22 2015 2:10PM | Jul 23 2015 1:30AM | Jul 23 2015 3:05AM | 49.779 | 48.575 | 50.50 | 0.00 | 27.200 | 22.579 | 21.375 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 17.0 | -100.0 | G35T2 | 1 2 | 11 6
Y/24-2 | SGBM16 | Jul 15 2015 10:30AM | Jul 21 2015 5:30PM | Jul 21 2015 4:30PM | Jul 21 2015 9:20PM | 49.718 | 48.575 | 42.52 | 0.00 | 42.518 | 21.700 | 6.057 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 3.9 | 17.0 | 30.0 | G35T2 | C480005644 C480005648 C480005649 | 2 11 4
X/24-2 | SGBM17 | Jul 15 2015 10:30AM | Jul 21 2015 4:30PM | Jul 21 2015 6:30PM | Jul 21 2015 7:30PM | 49.586 | 48.575 | 42.39 | 0.00 | 28.886 | 20.700 | 19.689 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.5 | 16.0 | -100.0 | G35T2 | C480005645 C480005644 | 11 5
Y/22-3 | SGBM16 | Jul 19 2015 9:00AM | Jul 20 2015 10:30AM | Jul 20 2015 6:20PM | Jul 20 2015 7:50PM | 49.68 | 48.575 | 50.48 | 0.00 | 26.680 | 23.000 | 21.895 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.9 | 16.0 | -100.0 | G35T2 | 1 2 | 11 5
X/24-1 | SGBM18 | Jul 14 2015 11:15AM | Jul 14 2015 3:50PM | Jul 14 2015 3:30PM | Jul 14 2015 4:30PM | 49.756 | 48.575 | 42.51 | 0.00 | 29.008 | 20.748 | 19.567 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 12.4 | 16.0 | -100.0 | G35T2 | C480005581 C480005583 | 10 6
Y/26-2 | SGBM16 | Jul 13 2015 9:45AM | Jul 13 2015 3:15PM | Jul 13 2015 7:00PM | Jul 13 2015 8:34PM | 49.873 | 48.575 | 42.53 | 0.00 | 27.827 | 22.046 | 20.748 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.2 | 16.0 | -100.0 | G35T2 | C480005535 C480005539 | 6 10
Y/24-1 | SGBM16 | Jul 10 2015 4:00PM | Jul 10 2015 6:30PM | Jul 10 2015 9:30PM | Jul 10 2015 10:20PM | 49.805 | 48.575 | 42.69 | 0.00 | 27.188 | 22.617 | 21.387 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.6 | 17.0 | 24.9 | G35T2 | c520120553 c520120552 | 8 9
Y/26-1 | SGBM17 | Jul 10 2015 11:00AM | Jul 10 2015 4:30PM | Jul 10 2015 8:49PM | Jul 10 2015 9:25PM | 50.064 | 48.575 | 42.65 | 0.00 | 27.555 | 22.509 | 21.020 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.4 | 18.0 | 34.6 | G35T2 | c520120550 c520120551 | 9 9
Y/22-1 | SGBM16 | Jul 9 2015 10:40AM | Jul 9 2015 3:00PM | Jul 9 2015 3:05PM | Jul 9 2015 4:00PM | 49.85 | 48.575 | 42.14 | 0.00 | 26.842 | 23.008 | 21.733 |  | 0.0 | 0.0 | 0.0 | 9T20 + 8T20 | - | - | T12-250 | - | - | - | 12 | - | 13.8 | 18.0 | -100.0 | G35T2 | c480005311 c480005312 | 10 8
J/7-5 | [5 empty] | 0 | 54.275 |  |  | 0.000 | 0.000 | 54.275 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 34.5 | 0.0 | 0.0 | G35T2
J/9-9 | [5 empty] | 0 | 51.025 |  |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 32.5 | 0.0 | 0.0 | G35T2
J/9-12 | [5 empty] | 0 | 51.025 |  |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 32.5 | 0.0 | 0.0 | G35T2
J/9-15 | [5 empty] | 0 | 51.025 |  |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 32.5 | 0.0 | 0.0 | G35T2
J/9-16 | [5 empty] | 0 | 51.025 |  |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 32.5 | 0.0 | 0.0 | G35T2
J/9-18 | [5 empty] | 0 | 51.025 |  |  | 0.000 | 0.000 | 51.025 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 32.5 | 0.0 | 0.0 | G35T2
K/17-2 | [5 empty] | 0 | 49.525 |  |  | 0.000 | 0.000 | 49.525 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 31.5 | 0.0 | 0.0 | G35T2
K/16-2 | [5 empty] | 0 | 49.525 |  |  | 0.000 | 0.000 | 49.525 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 31.5 | 0.0 | 0.0 | G35T2
Na/Yb-1 | [5 empty] | 0 | 55.075 |  |  | 0.000 | 0.000 | 55.075 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 35.0 | 0.0 | 0.0 | G35T2
L/16-1 | [5 empty] | 0 | 50.725 |  |  | 0.000 | 0.000 | 50.725 |  | 0.0 | 0.0 | 0.0 | 9T20+8T20 | - | - | T12-250 | - | - | - |  | - | 32.3 | 0.0 | 0.0 | G35T2
Total | [10 empty] | 33214.882 | 28591.451 | 0.0 | 3.0 | 0.0 | 0.0 |  | 2663.3 | 2663.3 |  | 1156.8 | 1156.8 |  |  |  | 18191.5 | 22043.5

## 1050
Summary List for 1891651800-Parcel F
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [6 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
H/11-3 | SGBM20 | Apr 1 2016 1:00PM | Apr 2 2016 11:30AM | Apr 2 2016 2:10PM | Apr 2 2016 3:50PM | 55.83 | 49.475 | 56.55 | 0.00 | 17.646 | 38.184 | 31.829 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 37.0 | 8.8 | G35T2 | pj7535 pj7537 pj7540 pj7542 | 10 10 10 7
H/12-2 | SGBM20 | Apr 1 2016 8:10AM | Apr 1 2016 3:00PM | Apr 1 2016 5:09PM | Apr 1 2016 6:45PM | 55.78 | 53.375 | 55.58 | 0.00 | 20.382 | 35.398 | 32.993 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 32.0 | -28.6 | G35T2 | pj7508 pj7500 pj7512 pj7515 | 8 8 8 8
H/15-2 | SGBM31 | Mar 30 2016 9:20AM | Mar 31 2016 6:00PM | Mar 31 2016 9:00PM | Mar 31 2016 10:10PM | 55.64 | 49.375 | 56.40 | 0.00 | 17.497 | 38.143 | 31.878 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 31.0 | -100.0 | G35T2 | pj7497 Pending pj7499 pj7500 | 8 8 7 8
H/11-1 | SGBM20 | Mar 30 2016 8:40AM | Mar 31 2016 3:50PM | Mar 31 2016 5:30PM | Mar 31 2016 6:45PM | 55.74 | 49.475 | 56.63 | 0.00 | 17.332 | 38.408 | 32.143 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 32.0 | -100.0 | G35T2 | pj7482 pj7483 pj7485 pj7489 | 8 8 8 8
J/17-1 | SGBM31 | Mar 30 2016 10:00AM | Mar 31 2016 1:45PM | Mar 31 2016 5:00PM | Mar 31 2016 6:35PM | 55.641 | 51.075 | 56.56 | 0.00 | 19.056 | 36.585 | 32.019 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 31.0 | -100.0 | G35T2 | 7480 pj7478 pj7481 pj7487 | 7 8 8 8
G/14-2 | SGBM31 | Mar 30 2016 8:00AM | Mar 30 2016 7:05PM | Mar 30 2016 8:05PM | Mar 30 2016 9:20PM | 55.588 | 49.375 | 56.29 | 0.00 | 17.692 | 37.896 | 31.683 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 36.0 | -100.0 | G35T2 | pj7358 pj7459 pj7460 pj7461 | 10 8 10 8
K/15-2 | SGBM31 | Mar 29 2016 10:35AM | Mar 30 2016 1:45PM | Mar 30 2016 5:30PM | Mar 30 2016 6:20PM | 55.751 | 49.375 | 56.59 | 0.00 | 17.493 | 38.258 | 31.882 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 30.0 | -100.0 | G35T2 | pj7446 pj7447 pj7448 pj7450 | 9 7 7 7
J/15-2 | SGBM23 | Mar 29 2016 10:00AM | Mar 29 2016 7:30PM | Mar 29 2016 8:20PM | Mar 29 2016 10:05PM | 55.743 | 49.375 | 56.59 | 0.00 | 17.686 | 38.057 | 31.689 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 34.0 | -100.0 | G35T2 | pj7401 pj74102 pj7408 Pending | 8 10 8 8
H/12-1 | SGBM23 | Mar 26 2016 8:30AM | Mar 28 2016 5:00PM | Mar 28 2016 10:45PM | Mar 28 2016 11:55PM | 55.523 | 53.375 | 56.28 | 0.00 | 21.385 | 34.138 | 31.990 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 33.0 | -100.0 | G35T2 | pj7366 pj7367 pj7369 pj7370 | 11 7 8 7
G/14-1 | SGBM23 | Mar 25 2016 2:30PM | Mar 28 2016 11:00AM | Mar 28 2016 3:00PM | Mar 28 2016 4:25PM | 55.442 | 49.375 | 56.20 | 0.00 | 17.500 | 37.942 | 31.875 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 31.0 | 12.3 | G35T2 | pj7338 pj7339 pj7340 pj7341 | 8 8 8 7
G/17-1 | SGBM19 | Mar 25 2016 5:00PM | Mar 26 2016 1:45PM | Mar 26 2016 4:20PM | Mar 26 2016 6:05PM | 55.523 | 51.075 | 56.68 | 0.00 | 19.284 | 36.239 | 31.791 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.5 | 33.0 | -100.0 | G35T2 | pj7274 pj7275 pj7279 pj7280 pj7282 | 8 7 8 8 2
G/15-2 | SGBM19 | Mar 25 2016 11:20AM | Mar 26 2016 8:45AM | Mar 26 2016 10:05AM | Mar 26 2016 11:05AM | 55.46 | 49.375 | 56.51 | 0.00 | 17.511 | 94.460 | 31.864 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 39.0 | 41.3 | G35T2 | pj7265 pj7266 pj7267 | 18 11 10
J/15-1 | SGBM19 | Mar 24 2016 6:30PM | Mar 25 2016 4:15PM | Mar 26 2016 3:00AM | Mar 26 2016 5:45AM | 55.792 | 49.375 | 56.62 | 0.00 | 17.422 | 38.370 | 31.953 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 42.0 | 14.3 | G35T2 | pj7258 pj7259 pj7260 pj7261 pj7262 pj7263 pj7264 | 8 7 8 7 6 4 2
H/14-1 | SGBM23 | Mar 25 2016 3:30PM | Mar 25 2016 9:00PM | Mar 26 2016 1:20AM | Mar 26 2016 3:20AM | 55.532 | 53.375 | 56.28 | 0.00 | 21.283 | 34.249 | 32.092 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 33.0 | -27.8 | G35T2 | pj7248 pj7251 pj7256 | 11 11 11
H/11-2 | SGBM19 | Mar 24 2016 3:35PM | Mar 25 2016 9:20AM | Mar 25 2016 3:20PM | Mar 25 2016 4:40PM | 55.625 | 49.475 | 56.74 | 0.00 | 17.837 | 37.788 | 31.638 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 30.0 | 2.6 | G35T2 | pj7187 pj7191 pj7195 | 10 10 10
G/13-2 | SGBM19 | Mar 23 2016 6:25PM | Mar 24 2016 2:45PM | Mar 24 2016 9:30PM | Mar 24 2016 11:06PM | 55.475 | 49.375 | 56.43 | 0.00 | 17.530 | 37.945 | 31.845 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 33.0 | -100.0 | G35T2 | pj7168 pj7169 pj7171 pj7172 | 8 8 9 8
G/15-1 | SGBM23 | Mar 23 2016 7:00PM | Mar 24 2016 2:05PM | Mar 24 2016 7:00PM | Mar 24 2016 9:07PM | 55.502 | 49.375 | 56.31 | 0.00 | 17.307 | 38.195 | 32.068 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 34.0 | -100.0 | G35T2 | pj7154 pj7155 pj7158 Pending | 10 8 8 8
H/15-1 | SGBM19 | Mar 23 2016 1:00PM | Mar 24 2016 9:45AM | Mar 24 2016 4:30PM | Mar 24 2016 6:25PM | 55.64 | 49.375 | 56.60 | 0.00 | 17.801 | 37.839 | 31.574 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.3 | 33.0 | -100.0 | G35T2 | pj7146 pj7147 pj7148 pj7151 | 9 8 8 8
H/16-1 | SGBM23 | Mar 23 2016 1:45PM | Mar 24 2016 9:30AM | Mar 24 2016 2:30PM | Mar 24 2016 3:50PM | 55.6 | 51.075 | 0.00 | 0.00 | -37.300 | 92.900 | 88.375 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 76.5 | 33.0 | -100.0 | G35T2 | pj7141 pj7142 pj7143 pj7144 | 9 8 8 8
H/17-1 | SGBM23 | Mar 23 2016 2:15PM | Mar 23 2016 6:00PM | Mar 24 2016 2:40AM | Mar 24 2016 3:51AM | 55.57 | 51.075 | 56.30 | 0.00 | 19.296 | 36.274 | 31.779 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.5 | 30.0 | -100.0 | G35T2 | pj7136 pj7137 pj7138 pj7139 | 8 8 7 7
H/14-2 | SGBM19 | Mar 23 2016 11:50AM | Mar 23 2016 6:20PM | Mar 23 2016 11:25PM | Mar 24 2016 1:55AM | 55.67 | 53.375 | 56.61 | 0.00 | 21.413 | 34.257 | 31.962 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 32.0 | -100.0 | G35T2 | pj7127 pj7129 pj7130 pj7132 | 7 8 8 9
G/10-1 | SGBM23 | Mar 22 2016 5:20PM | Mar 23 2016 2:20PM | Mar 23 2016 7:20PM | Mar 23 2016 8:56PM | 55.847 | 49.375 | 56.42 | 0.00 | 16.915 | 38.932 | 32.460 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 33.0 | -100.0 | G35T2 | pj7118 pj7119 pj7120 pj7121 | 10 8 7 8
G/13-1 | SGBM23 | Mar 22 2016 9:30AM | Mar 22 2016 8:30PM | Mar 23 2016 1:00AM | Mar 23 2016 2:40AM | 55.49 | 49.375 | 0.00 | 0.00 | -38.800 | 94.290 | 88.175 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 76.4 | 37.0 | -100.0 | G35T2 | pj7082 pj7083 pj7084 pj7086 | 10 10 8 9
J/14-2 | SGBM20 | Mar 22 2016 9:00AM | Mar 22 2016 6:15PM | Mar 22 2016 11:00PM | Mar 23 2016 12:55AM | 55.777 | 53.375 | 56.59 | 0.00 | 21.791 | 33.986 | 31.584 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 32.0 | -100.0 | G35T2 | pj7073 pj7074 pj7076 pj7079 | 8 8 8 8
X11/Y2a-1 | SGBM19 | Mar 21 2016 3:30PM | Mar 22 2016 2:45PM | Mar 22 2016 5:50PM | Mar 22 2016 7:51PM | 55.69 | 55.075 | 55.57 | 0.00 | 21.974 | 33.716 | 33.101 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.7 | 33.0 | -100.0 | G35T2 | pj7059 pj7061 pj7062 pj7064 | 8 9 8 8
X11/Y3a-1 | SGBM31 | Mar 21 2016 4:10PM | Mar 21 2016 8:30PM | Mar 22 2016 3:30AM | Mar 22 2016 5:17AM | 55.605 | 55.075 | 56.61 | 0.00 | 25.009 | 87.205 | 30.066 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 23.0 | -11.7 | G35T2 | pj7052 pj7053 pj7054 | 8 8 7
Pa/6-1 | SGBM19 | Mar 21 2016 11:00AM | Mar 21 2016 5:45PM | Mar 22 2016 1:25AM | Mar 22 2016 2:56AM | 55.802 | 55.075 | 56.60 | 0.00 | 23.103 | 89.302 | 31.972 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 32.0 | 4.3 | G35T2 | pj7044 pj7045 pj7048 | 11 11 10
G/10-2 | SGBM23 | Mar 19 2016 1:35PM | Mar 21 2016 5:57PM | Mar 22 2016 12:00AM | Mar 22 2016 2:01AM | 55.86 | 49.375 | 56.78 | 0.00 | 17.076 | 38.784 | 32.299 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 36.0 | -100.0 | G35T2 | pj7039 pj7040 pj7042 pj7043 | 10 10 8 8
P/1-1 | SGBM19 | Mar 19 2016 3:00PM | Mar 21 2016 1:55PM | Mar 21 2016 7:00PM | Mar 21 2016 9:41PM | 55.765 | 55.075 | 56.65 | 0.00 | 23.050 | 32.715 | 32.025 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 38.0 | -100.0 | G35T2 | pj7009 pj7012 pj7016 pj7018 pj7025 | 8 10 8 8 4
Pa/5-1 | SGBM22 | Mar 18 2016 5:00PM | Mar 19 2016 3:45PM | Mar 19 2016 7:00PM | Mar 19 2016 8:56PM | 55.73 | 55.075 | 56.62 | 0.00 | 22.915 | 32.815 | 32.160 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 35.0 | -100.0 | G35T2 | pj6953 pj6954 pj6955 pj6957 | 10 8 9 8
X11/Y4a-1 | SGBM19 | Mar 18 2016 4:00PM | Mar 19 2016 12:05PM | Mar 19 2016 5:00PM | Mar 19 2016 6:50PM | 55.68 | 55.075 | 56.59 | 0.00 | 22.892 | 32.788 | 32.183 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 34.0 | -27.9 | G35T2 | pj6943 pj6945 pj6946 pj6947 | 8 10 8 8
Pa/12-1 | SGBM23 | Mar 15 2016 5:35PM | Mar 17 2016 10:00AM | Mar 17 2016 1:50PM | Mar 17 2016 4:40PM | 55.778 | 55.075 | 56.56 | 0.00 | 22.860 | 32.918 | 32.215 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 33.0 | -100.0 | G35T2 | pj6854 pj6855 pj6858 pj6860 | 8 8 9 8
G/3-1 | SGBM31 | Mar 16 2016 10:45AM | Mar 16 2016 5:00PM | Mar 16 2016 6:25PM | Mar 16 2016 8:01PM | 55.357 | 55.075 | 0.00 | 0.00 | -33.000 | 88.357 | 88.075 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 76.3 | 23.0 | -76.3 | G35T2 | pj6793 pj6798 pj6796 | 8 7 8
Pa/9-1 | SGBM20 | Mar 15 2016 5:30PM | Mar 16 2016 12:00PM | Mar 16 2016 3:20PM | Mar 16 2016 5:01PM | 55.773 | 55.075 | 56.57 | 0.00 | 23.567 | 32.206 | 31.508 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.3 | 31.0 | -100.0 | G35T2 | pj6773 pj6775 pj6776 pj6780 | 10 7 7 7
G/7-1 | SGBM23 | Mar 14 2016 1:00PM | Mar 15 2016 4:30PM | Mar 15 2016 8:30PM | Mar 15 2016 11:05PM | 55.868 | 52.775 | 56.76 | 0.00 | 21.660 | 34.208 | 31.115 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 32.0 | -100.0 | G35T2 | pj6760 pj6761 pj6764 pj6766 | 8 8 8 8
G/7-2 | SGBM20 | Mar 14 2016 10:00AM | Mar 14 2016 4:15PM | Mar 14 2016 7:10PM | Mar 14 2016 8:40PM | 55.84 | 52.775 | 56.74 | 0.00 | 21.541 | 34.299 | 31.234 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.0 | 34.0 | -100.0 | G35T2 | pj6702 pj6703 pj6704 pj6707 | 8 8 8 10
Tc/45-1 | SGBM31 | Mar 11 2016 2:30PM | Mar 11 2016 7:00PM | Mar 11 2016 11:20PM | Mar 12 2016 1:16AM | 51.673 | 50.575 | 52.38 | 0.00 | 22.082 | 81.973 | 28.493 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 35.0 | 10.3 | G35T2 | 1 2 3 4 | 10 9 8 8
J/11-2 | SGBM20 | Mar 8 2016 1:15PM | Mar 8 2016 6:38PM | Mar 8 2016 11:11PM | Mar 9 2016 1:55AM | 55.86 | 49.475 | 56.69 | 0.00 | 17.488 | 38.372 | 31.987 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 29.0 | -27.7 | G35T2 | PJ6480 PJ6483 PJ6486 PJ6489 PJ6426 | 1 10 8 8 2
J/8-6 | SGBM19 | Mar 8 2016 12:17PM | Mar 8 2016 4:30PM | Mar 8 2016 10:05PM | Mar 8 2016 11:55PM | 55.945 | 54.675 | 56.79 | 0.00 | 22.993 | 32.952 | 31.682 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 30.0 | -27.4 | G35T2 | PJ6475 PJ6477 PJ6480 | 11 10 9
H/3-1 | SGBM19 | Mar 5 2016 1:20PM | Mar 5 2016 5:49PM | Mar 5 2016 8:25PM | Mar 5 2016 10:23PM | 55.47 | 53.375 | 56.24 | 0.00 | 20.942 | 34.528 | 32.433 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 33.0 | -28.1 | G35T2 | PJ6369 PJ6370 PJ6372 PJ6374 | 8 9 8 8
K/14-1 | SGBM20 | Mar 5 2016 11:19AM | Mar 5 2016 4:44PM | Mar 5 2016 7:25PM | Mar 5 2016 9:14PM | 55.576 | 53.375 | 56.55 | 0.00 | 21.348 | 34.228 | 32.027 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 34.0 | -100.0 | G35T2 | C480017896 C480017897 C480017899 | 11.5 11.5 11
J/8-5 | SGBM23 | Mar 5 2016 8:15AM | Mar 5 2016 1:00PM | Mar 5 2016 3:30PM | Mar 5 2016 5:39PM | 55.975 | 54.675 | 56.66 | 0.00 | 22.962 | 33.013 | 31.713 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.5 | 35.0 | -100.0 | G35T2 | C480017876 C480017875 C480017879 C480017882 | 11.5 6.5 10 7
H/6-3 | SGBM23 | Mar 5 2016 6:00PM | Mar 5 2016 11:00PM | Mar 5 2016 10:05AM | Mar 5 2016 11:54AM | 55.44 | 53.475 | 56.26 | 0.00 | 21.058 | 34.382 | 32.417 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 34.0 | -100.0 | G35T2 | C480017859 C480017860 C480017863 | 11.5 11.5 11
J/11-3 | SGBM20 | Mar 4 2016 8:09AM | Mar 4 2016 12:40PM | Mar 4 2016 3:22PM | Mar 4 2016 7:00PM | 55.32 | 49.475 | 56.39 | 0.00 | 17.388 | 37.932 | 32.087 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 32.0 | -100.0 | G35T2 | PJ6332 PJ6331 PJ6337 PJ6339 | 8 8 8 8
L/14-1 | SGBM20 | Mar 3 2016 2:00PM | Mar 3 2016 7:00PM | Mar 3 2016 9:30PM | Mar 4 2016 12:14AM | 55.672 | 53.375 | 56.32 | 0.00 | 21.520 | 34.152 | 31.855 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 35.0 | -100.0 | G35T2 | PJ6320 PJ6322 PJ6326 PJ6329 | 9 8 10 8
H/3-2 | SGBM17 | Mar 3 2016 1:23PM | Mar 3 2016 5:53PM | Mar 3 2016 9:35PM | Mar 3 2016 11:44PM | 55.546 | 53.375 | 56.29 | 0.00 | 21.289 | 34.257 | 32.086 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 33.0 | -100.0 | G35T2 | PJ6321 PJ6323 PJ6325 PJ6328 | 8 8 9 8
H/6-2 | SGBM19 | Mar 3 2016 12:20PM | Mar 3 2016 4:15PM | Mar 3 2016 5:30PM | Mar 3 2016 8:13PM | 55.49 | 53.475 | 56.29 | 0.00 | 21.493 | 33.997 | 31.982 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 32.0 | 15.5 | G35T2 | PJ6303 PJ6304 PJ6306 PJ6309 | 8 8 8 8
J/8-4 | SGBM17 | Mar 2 2016 8:00AM | Mar 2 2016 12:50PM | Mar 2 2016 2:40PM | Mar 2 2016 5:10PM | 55.94 | 54.675 | 56.81 | 0.00 | 22.815 | 33.125 | 31.860 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 31.0 | -100.0 | G35T2 | PJ6244 PJ6246 PJ6249 PJ6251 | 8 8 8 7
T1/49-1 | SGBM23 | Mar 1 2016 11:40AM | Mar 1 2016 5:40PM | Mar 1 2016 10:30PM | Mar 2 2016 12:11AM | 51.838 | 51.375 | 52.75 | 0.00 | 20.750 | 31.088 | 30.625 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.5 | 30.0 | -100.0 | G45T2 | pj6229 pj6230 m67s6tri 4 | 8 8 7 7
L/13-1 | SGBM20 | Mar 1 2016 3:00PM | Mar 1 2016 7:00PM | Mar 1 2016 9:20PM | Mar 1 2016 10:35PM | 55.702 | 53.375 | 56.55 | 0.00 | 21.552 | 34.150 | 31.823 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 37.0 | -100.0 | G35T2 | C480017668 C520125659 C520125658 C480017670 | 7 10 10 10
J/6-2 | SGBM19 | Mar 1 2016 1:35PM | Mar 1 2016 6:00PM | Mar 1 2016 7:50PM | Mar 1 2016 9:54PM | 55.61 | 53.475 | 56.46 | 0.00 | 21.859 | 33.751 | 31.616 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 33.0 | -100.0 | G35T2 | C480017659 C480017661 C480017662 C480017668 | 9 11 10 3
J/14-1 | SGBM20 | Mar 1 2016 8:00AM | Mar 1 2016 1:29PM | Mar 1 2016 4:05PM | Mar 1 2016 6:32PM | 55.722 | 53.375 | 56.56 | 0.00 | 21.355 | 34.367 | 32.020 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 33.0 | -100.0 | G35T2 | C480017636 C480017640 C480017645 C480017647 | 10 10 10 3
L/14-2 | SGBM20 | Feb 29 2016 12:10PM | Feb 29 2016 5:55PM | Feb 29 2016 9:00PM | Feb 29 2016 10:40PM | 55.694 | 53.375 | 56.59 | 0.00 | 21.491 | 34.203 | 31.884 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 33.0 | -100.0 | G35T2 | PJ6187 PJ6188 PJ6191 PJ6192 | 8 8 8 9
J/8-1 | SGBM17 | Feb 29 2016 10:10AM | Feb 29 2016 3:25PM | Feb 29 2016 7:17PM | Feb 29 2016 10:00PM | 55.926 | 54.675 | 56.78 | 0.00 | 22.581 | 33.345 | 32.094 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 32.0 | -100.0 | G35T2 | PJ6178 PJ6179 PJ6183 PJ6186 | 8 8 8 8
S/52-1 | SGBM23 | Feb 27 2016 11:25AM | Feb 29 2016 11:15AM | Feb 29 2016 4:30PM | Feb 29 2016 6:40PM | 51.809 | 49.225 | 0.00 | 0.00 | -39.200 | 91.009 | 88.425 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 76.6 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 8 10
H/5-2 | SGBM17 | Feb 29 2016 8:12AM | Feb 29 2016 12:00PM | Feb 29 2016 2:15PM | Feb 29 2016 4:14PM | 55.425 | 53.375 | 56.31 | 0.00 | 21.012 | 34.413 | 32.363 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 35.0 | -100.0 | G35T2 | PJ6155 PJ6157 PJ6161 PJ6162 | 10 10 8 7
K/15-1 | SGBM20 | Feb 29 2016 8:00AM | Feb 29 2016 12:32PM | Feb 29 2016 1:30PM | Feb 29 2016 3:42PM | 55.676 | 49.375 | 56.57 | 0.00 | 17.171 | 38.505 | 32.204 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 30.0 | -100.0 | G35T2 | PJ6151 PJ6154 PJ6156 PJ6159 | 8 8 7 7
J/6-3 | SGBM17 | Feb 27 2016 8:00AM | Feb 27 2016 2:00PM | Feb 27 2016 3:30PM | Feb 27 2016 5:50PM | 55.59 | 53.475 | 56.43 | 0.00 | 21.933 | 33.657 | 31.542 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.3 | 29.0 | -100.0 | G35T2 | PJ6116 PJ6120 PJ6123 PJ6127 | 10 8 8 3
N/61-1 | SGBM23 | Feb 26 2016 8:30AM | Feb 26 2016 3:40PM | Feb 26 2016 10:30PM | Feb 27 2016 1:45AM | 51.717 | 50.925 | 52.44 | 0.00 | 15.342 | 88.817 | 35.583 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.8 | 37.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 10 7
L/15-1 | SGBM20 | Feb 26 2016 1:00PM | Feb 26 2016 6:00PM | Feb 26 2016 7:30PM | Feb 26 2016 10:10PM | 55.71 | 49.375 | 56.50 | 0.00 | 17.004 | 38.706 | 32.371 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 30.0 | -100.0 | G35T2 | PJ6062 PJ6065 PJ6071 | 10 10 10
H/6-1 | SGBM17 | Feb 26 2016 8:00AM | Feb 26 2016 1:00PM | Feb 26 2016 3:45PM | Feb 26 2016 6:00PM | 55.47 | 53.475 | 56.36 | 0.00 | 21.258 | 34.212 | 32.217 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 36.0 | -100.0 | G35T2 | PJ6041 PJ6043 PJ6046 PJ6049 | 8 10 10 8
J/12-2 | SGBM20 | Feb 25 2016 12:50PM | Feb 26 2016 12:00PM | Feb 26 2016 2:50PM | Feb 26 2016 4:30PM | 55.687 | 53.375 | 56.49 | 0.00 | 21.285 | 34.402 | 32.090 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 32.0 | -100.0 | G35T2 | PJ6037 PJ6038 PJ6040 PJ6044 | 8 8 8 8
S/52-2 | SGBM15 | Feb 24 2016 1:40PM | Feb 25 2016 11:10AM | Feb 25 2016 8:00PM | Feb 25 2016 10:12PM | 51.902 | 49.225 | 52.74 | 0.00 | 13.840 | 38.062 | 35.385 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 41.0 | -30.6 | G45T2 | pj6014 pj6015 pj6019 pj6021 pj6026 | 10 10 8 9 4
K/13-2 | SGBM20 | Feb 25 2016 1:00PM | Feb 25 2016 6:00PM | Feb 25 2016 7:30PM | Feb 25 2016 10:10PM | 55.71 | 53.375 | 56.52 | 0.00 | 21.516 | 34.194 | 31.859 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 32.0 | -100.0 | G35T2 | PJ6012 PJ6013 PJ6020 PJ6023 | 8 8 8 8
K/9-2 | SGBM19 | Feb 24 2016 5:10PM | Feb 25 2016 10:00AM | Feb 25 2016 10:30AM | Feb 25 2016 1:00PM | 55.926 | 53.375 | 56.84 | 0.00 | 21.341 | 34.585 | 32.034 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 37.0 | -100.0 | G35T2 | PJ5977 PJ5978 PJ5979 PJ5982 PJ5984 | 9 8 8 8 4
J/12-1 | SGBM20 | Feb 24 2016 10:15AM | Feb 24 2016 3:55PM | Feb 24 2016 7:45PM | Feb 24 2016 10:24PM | 55.63 | 53.375 | 56.44 | 0.00 | 21.439 | 34.191 | 31.936 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 32.0 | -100.0 | G35T2 | PJ5959 PJ5960 PJ5965 PJ5970 | 8 8 8 8
H/5-1 | SGBM17 | Feb 24 2016 8:00AM | Feb 24 2016 12:00PM | Feb 24 2016 1:45PM | Feb 24 2016 3:35PM | 55.498 | 53.375 | 56.38 | 0.00 | 21.077 | 34.421 | 32.298 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 34.0 | -100.0 | G35T2 | PJ5937 PJ5938 PJ5940 PJ5941 | 8 8 10 8
K/13-1 | SGBM20 | Feb 23 2016 9:10AM | Feb 23 2016 2:47PM | Feb 23 2016 7:55PM | Feb 23 2016 10:00PM | 55.691 | 53.375 | 56.53 | 0.00 | 21.530 | 34.161 | 31.845 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 33.0 | -100.0 | G35T2 | PJ5912 PJ5914 PJ5920 PJ5922 | 9 8 8 8
J/6-1 | SGBM17 | Feb 23 2016 9:05AM | Feb 23 2016 2:48PM | Feb 23 2016 6:50PM | Feb 23 2016 9:09PM | 55.625 | 53.475 | 56.49 | 0.00 | 21.490 | 34.135 | 31.985 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 30.0 | -100.0 | G35T2 | PJ5907 PJ5908 PJ5915 | 10 10 10
J/3-2 | SGBM17 | Feb 23 2016 8:17AM | Feb 23 2016 1:00PM | Feb 23 2016 3:30PM | Feb 23 2016 5:18PM | 55.576 | 53.375 | 56.48 | 0.00 | 21.082 | 34.494 | 32.293 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 30.0 | -100.0 | G35T2 | PJ5891 PJ5892 PJ5893 PJ5896 | 8 8 7 7
S/53-1 | SGBM15 | Feb 22 2016 10:59AM | Feb 22 2016 4:30PM | Feb 22 2016 9:05PM | Feb 22 2016 11:40PM | 51.821 | 49.675 | 52.77 | 0.00 | 12.773 | 39.048 | 36.902 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.0 | 36.0 | -100.0 | G45T2 | pj5867 pj5869 pj5872 pj5878 | 8 8 10 10
J/5-1 | SGBM17 | Feb 22 2016 8:45AM | Feb 22 2016 2:49PM | Feb 22 2016 8:00PM | Feb 22 2016 10:56PM | 55.587 | 53.375 | 56.49 | 0.00 | 21.194 | 34.393 | 32.181 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 43.0 | -100.0 | G35T2 | PJ5862 PJ5864 PJ5865 PJ5870 PJ5875 | 10 9 10 8 6
K/9-1 | SGBM17 | Feb 22 2016 8:30AM | Feb 22 2016 12:00PM | Feb 22 2016 1:45PM | Feb 22 2016 4:10PM | 55.908 | 53.375 | 56.78 | 0.00 | 21.283 | 34.625 | 32.092 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 35.0 | -100.0 | G35T2 | PJ5835 PJ5836 PJ5837 PJ5838 | 10 9 9 7
S/53-2 | SGBM15 | Feb 19 2016 4:50PM | Feb 20 2016 12:00PM | Feb 20 2016 5:25PM | Feb 20 2016 8:32PM | 51.869 | 49.675 | 52.67 | 0.00 | 13.773 | 38.096 | 35.902 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.1 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 7 8 7
K/6-1 | SGBM17 | Feb 20 2016 8:14AM | Feb 20 2016 2:14PM | Feb 20 2016 2:45PM | Feb 20 2016 5:51PM | 55.573 | 53.375 | 56.42 | 0.00 | 21.423 | 34.150 | 31.952 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 41.0 | -100.0 | G35T2 | PJ5782 PJ5784 PJ5787 PJ5792 PJ5795 | 8 7 8 8 10
T1/53-1 | SGBM15 | Feb 19 2016 8:30AM | Feb 19 2016 4:00PM | Feb 19 2016 9:00PM | Feb 19 2016 10:56PM | 51.944 | 51.025 | 52.55 | 0.00 | 18.948 | 32.996 | 32.077 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 33.0 | -100.0 | G45T2 | 2 2 3 4 | 8 8 8 9
J/3-1 | SGBM19 | Feb 19 2016 8:16AM | Feb 19 2016 2:33PM | Feb 19 2016 7:16PM | Feb 19 2016 9:10PM | 55.576 | 53.375 | 56.45 | 0.00 | 21.147 | 34.429 | 32.228 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 38.0 | -100.0 | G35T2 | PJ5753 PJ5755 PJ5757 PJ5959 | 10 10 10 8
K/6-2 | SGBM19 | Feb 18 2016 8:00AM | Feb 18 2016 12:00PM | Feb 18 2016 1:40PM | Feb 18 2016 5:10PM | 55.593 | 53.375 | 56.44 | 0.00 | 21.239 | 34.354 | 32.136 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 36.0 | -100.0 | G35T2 | PJ5686 PJ5688 PJ5689 PJ5691 | 10 10 8 8
K/8-2 | SGBM19 | Feb 17 2016 12:00PM | Feb 17 2016 6:00PM | Feb 18 2016 1:05AM | Feb 18 2016 3:30AM | 55.96 | 53.375 | 56.69 | 0.00 | 21.489 | 34.471 | 31.886 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 41.0 | -100.0 | G35T2 | PJ5668 PJ5669 PJ5672 PJ5673 PJ5675 | 9 9 10 9 4
K/3-2 | SGBM19 | Feb 17 2016 8:00AM | Feb 17 2016 1:00PM | Feb 17 2016 3:45PM | Feb 17 2016 5:30PM | 55.631 | 53.375 | 56.44 | 0.00 | 20.745 | 34.886 | 32.630 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.3 | 32.0 | -100.0 | G35T2 | PJ5631 PJ5633 PJ5637 PJ5641 | 8 8 8 8
K/4-2 | SGBM19 | Feb 15 2016 6:11PM | Feb 16 2016 10:45AM | Feb 16 2016 2:40PM | Feb 16 2016 6:10PM | 55.64 | 53.375 | 56.37 | 0.00 | 20.871 | 34.769 | 32.504 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 40.0 | -100.0 | G35T2 | PJ5576 PJ5577 PJ5578 5580 5584 PJ5591 | 8 8 8 6 6 4
K/8-1 | SGBM17 | Feb 15 2016 11:00AM | Feb 15 2016 6:00PM | Feb 15 2016 9:30PM | Feb 15 2016 11:45PM | 55.943 | 53.375 | 56.71 | 0.00 | 21.710 | 34.233 | 31.665 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 37.0 | -100.0 | G35T2 | PJ5554 PJ5558 PJ5560 PJ5563 PJ5566 | 8 7 8 7 7
K/5-2 | SGBM19 | Feb 15 2016 8:00AM | Feb 15 2016 1:00PM | Feb 15 2016 4:40PM | Feb 15 2016 6:40PM | 55.67 | 53.375 | 56.42 | 0.00 | 21.220 | 34.450 | 32.155 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 37.0 | -100.0 | G35T2 | PJ5526 PJ5527 PJ5530 PJ5533 PJ5536 | 8 8 7 7 7
M7/58-1 | SGBM05 | Feb 13 2016 12:55PM | Feb 13 2016 6:00PM | Feb 13 2016 9:40PM | Feb 13 2016 11:40PM | 52.049 | 50.925 | 52.88 | 0.00 | 14.485 | 37.564 | 36.440 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.6 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 8 7 6
K/4-1 | SGBM19 | Feb 12 2016 11:00AM | Feb 12 2016 5:00PM | Feb 12 2016 6:30PM | Feb 12 2016 9:08PM | 55.74 | 53.375 | 56.53 | 0.00 | 20.929 | 34.811 | 32.446 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 43.0 | -100.0 | G35T2 | PJ5437 PJ5438 PJ5441 PJ5445 PJ5448 PJ5455 | 7 8 8 8 8 4
M7/57-1 | SGBM01 | Feb 5 2016 3:15PM | Feb 10 2016 4:40PM | Feb 10 2016 11:15PM | Feb 11 2016 2:02AM | 52.102 | 50.925 | 52.86 | 0.00 | 13.263 | 38.839 | 37.662 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.6 | 43.0 | 4.4 | G45T2 | 1 2 3 4 5 6 | 10 10 6 7 6 4
S/59-2 | SGBM23 | Feb 4 2016 1:50PM | Feb 10 2016 1:50PM | Feb 10 2016 10:05PM | Feb 11 2016 12:02AM | 51.949 | 49.675 | 52.86 | 0.00 | 18.759 | 33.190 | 30.916 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.8 | 32.0 | -26.8 | G45T2 | 1 2 3 4 | 8 8 8 8
Q/50-1 | SGBM05 | Feb 4 2016 2:05PM | Feb 5 2016 8:30AM | Feb 5 2016 4:40PM | Feb 5 2016 6:07PM | 51.816 | 51.375 | 52.57 | 0.00 | 14.574 | 37.242 | 36.801 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.9 | 36.0 | -31.9 | G45T2 | 1 2 3 4 | 9 9 8 10
U/61-1 | SGBM31 | Feb 4 2016 8:45AM | Feb 5 2016 10:30AM | Feb 5 2016 11:30AM | Feb 5 2016 1:20PM | 51.38 | 47.075 | 52.68 | 0.00 | 19.580 | 31.800 | 27.495 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.8 | 29.0 | -100.0 | G45T2 | PJ5319 PJ5322 PJ5324 PJ5325 | 10 8 6 5
T1/54-1 | SGBM01 | Feb 3 2016 5:50PM | Feb 4 2016 2:02PM | Feb 4 2016 10:15PM | Feb 5 2016 12:32AM | 51.801 | 51.025 | 52.67 | 0.00 | 19.273 | 32.528 | 31.752 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.5 | 36.0 | -27.5 | G45T2 | 1 2 3 4 5 | 8 10 8 7 3
U/50-1 | SGBM20 | Feb 3 2016 10:30AM | Feb 3 2016 2:38PM | Feb 3 2016 6:55PM | Feb 3 2016 8:33PM | 51.328 | 51.375 | 52.21 | 0.00 | 22.905 | 28.423 | 28.470 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 28.0 | -100.0 | G45T2 | PJ5237 PJ5241 PJ5243 | 10 10 8
S/59-1 | SGBM15 | Jan 30 2016 2:00PM | Feb 2 2016 3:20PM | Feb 2 2016 8:05PM | Feb 2 2016 9:47PM | 52.013 | 49.675 | 52.86 | 0.00 | 18.658 | 33.355 | 31.017 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 33.0 | -26.9 | G45T2 | 1 2 3 | 11 11 11
V/51-1 | SGBM20 | Jan 30 2016 5:03PM | Feb 2 2016 1:15PM | Feb 2 2016 5:30PM | Feb 2 2016 8:30PM | 49.802 | 47.375 | 50.53 | 0.00 | 24.130 | 25.672 | 23.245 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 30.0 | -100.0 | G45T2 | PJ5187 PJ5190 PJ5194 PJ5202 | 10 10 8 2
V/57-1 | SGBM17 | Dec 29 2015 5:30PM | Dec 30 2015 8:55PM | Jan 31 2016 5:35AM | Jan 31 2016 8:00AM | 49.486 | 47.075 | 50.05 | 0.00 | 17.351 | 32.135 | 29.724 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.7 | 32.0 | -100.0 | G45T2 | PJ3773 PJ3774 PJ3775 PJ3776 | 8 10 7 7
Z/52-2 | SGBM05 | Dec 29 2015 9:20AM | Jan 30 2016 3:53PM | Jan 30 2016 10:10PM | Jan 31 2016 2:32AM | 49.525 | 46.925 | 50.32 | 0.00 | 12.418 | 37.107 | 34.507 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.9 | 34.0 | -100.0 | G45T2 | C170014211 C170014213 C170014214 C170014216 | 10 8 8 8
T/61-1 | SGBM05 | Jan 29 2016 9:40AM | Jan 30 2016 9:17AM | Jan 30 2016 4:20PM | Jan 30 2016 7:03PM | 52.045 | 49.775 | 52.85 | 0.00 | 20.549 | 31.496 | 29.226 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 34.0 | -100.0 | G45T2 | 2 2 3 4 5 | 8 8 8 7 3
M6/56-1 | SGBM15 | Jan 29 2016 8:30AM | Jan 29 2016 5:15PM | Jan 29 2016 11:00PM | Jan 30 2016 2:04AM | 52.04 | 51.375 | 52.92 | 0.00 | 14.522 | 37.518 | 36.853 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.9 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 7 8 7 7 5
V/51-2 | SGBM31 | Jan 29 2016 8:52AM | Jan 29 2016 2:00PM | Jan 29 2016 6:40PM | Jan 29 2016 9:00PM | 49.456 | 47.375 | 50.22 | 0.00 | 20.115 | 29.341 | 27.260 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.6 | 34.0 | -100.0 | G45T2 | PJ5073 PJN5074 PJ5077 PJ5079 PJ5083 | 8 8 8 7 3
S/57-1 | SGBM01 | Jan 28 2016 10:45AM | Jan 28 2016 5:58PM | Jan 28 2016 10:35PM | Jan 29 2016 2:02AM | 52.064 | 49.675 | 52.80 | 0.00 | 15.304 | 36.760 | 34.371 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.8 | 39.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 8 8
P/56-2 | SGBM15 | Jan 26 2016 3:00PM | Jan 27 2016 10:26AM | Jan 27 2016 10:25PM | Jan 28 2016 1:14AM | 52.094 | 49.675 | 52.91 | 0.00 | 11.814 | 40.280 | 37.861 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.8 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 8 8 8 8 2
T2a/50a-1 | SGBM20 | Jan 26 2016 1:57PM | Jan 27 2016 11:43AM | Jan 27 2016 3:20PM | Jan 27 2016 7:00PM | 51.735 | 51.325 | 52.43 | 0.00 | 22.631 | 29.104 | 28.694 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.8 | 31.0 | 24.8 | G35T2 | PJ4949 PJ4953 PJ4957 PJ4964 | 10 10 8 3
S/54-2 | SGBM15 | Jan 26 2016 10:35AM | Jan 26 2016 3:30PM | Jan 27 2016 12:15AM | Jan 27 2016 2:47AM | 51.978 | 49.675 | 52.85 | 0.00 | 13.845 | 38.133 | 35.830 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.0 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 7
S/57-2 | SGBM01 | Jan 23 2016 3:00PM | Jan 26 2016 10:30AM | Jan 26 2016 7:25PM | Jan 26 2016 11:20PM | 51.973 | 49.675 | 52.76 | 0.00 | 17.361 | 34.612 | 32.314 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 10 8 8 4
V/52-1 | SGBM20 | Jan 23 2016 1:57PM | Jan 26 2016 11:35AM | Jan 26 2016 7:00PM | Jan 26 2016 9:35PM | 49.407 | 47.375 | 50.13 | 0.00 | 19.633 | 29.774 | 27.742 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.0 | 37.0 | 54.0 | G45T2 | 1 2 3 4 5 | 8 8 7 8 6
M6/55-1 | SGBM01 | Jan 23 2016 9:20AM | Jan 23 2016 2:15PM | Jan 23 2016 7:15PM | Jan 23 2016 8:47PM | 51.902 | 51.275 | 52.62 | 0.00 | 14.721 | 37.181 | 36.554 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.7 | 36.0 | 13.7 | G45T2 | 1 2 3 4 5 | 7 7 8 7 7
P/56-1 | SGBM15 | Jan 22 2016 5:45PM | Jan 23 2016 2:57PM | Jan 23 2016 5:55PM | Jan 23 2016 7:47PM | 52.05 | 49.675 | 52.83 | 0.00 | 12.131 | 39.919 | 37.544 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.5 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 8 7
M7/59-1 | SGBM01 | Jan 21 2016 4:35PM | Jan 23 2016 9:30AM | Jan 23 2016 2:10PM | Jan 23 2016 4:47PM | 51.999 | 51.275 | 52.81 | 0.00 | 15.009 | 36.990 | 36.266 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.4 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 8 8 7
M5/58-1 | SGBM01 | Jan 21 2016 1:40PM | Jan 22 2016 10:57AM | Jan 22 2016 10:35PM | Jan 23 2016 1:12AM | 51.911 | 51.275 | 52.69 | 0.00 | 14.390 | 37.521 | 36.885 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.9 | 42.0 | 15.8 | G45T2 | 1 2 3 4 5 6 | 8 8 7 7 7 5
R/55-1 | SGBM15 | Jan 21 2016 12:30PM | Jan 22 2016 9:24AM | Jan 22 2016 5:00PM | Jan 22 2016 6:57PM | 51.922 | 51.375 | 52.68 | 0.00 | 14.578 | 37.344 | 36.797 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.9 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 8 8
M5b/57-1 | SGBM08 | Jan 20 2016 11:24AM | Jan 21 2016 2:00PM | Jan 21 2016 11:20PM | Jan 22 2016 1:38AM | 51.932 | 51.275 | 52.87 | 0.00 | 14.670 | 37.262 | 36.605 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.7 | 38.0 | -100.0 | G45T2 | Pending 2 3 4 5 | 8 8 8 7 7
S/56-1 | SGBM15 | Jan 20 2016 9:00AM | Jan 21 2016 10:00AM | Jan 21 2016 8:00PM | Jan 21 2016 9:37PM | 51.894 | 49.675 | 52.74 | 0.00 | 15.945 | 35.949 | 33.730 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.2 | 34.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 8 8
S/58-2 | SGBM01 | Jan 20 2016 3:35PM | Jan 21 2016 9:55AM | Jan 21 2016 5:45PM | Jan 21 2016 7:42PM | 52.069 | 49.675 | 52.93 | 0.00 | 18.228 | 33.141 | 31.447 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.2 | 34.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 10 8
Tb/40-1 | SGBM20 | Jan 21 2016 9:03AM | Jan 21 2016 2:15PM | Jan 21 2016 3:10PM | Jan 21 2016 4:05PM | 52.2 | 51.325 | 53.06 | 0.00 | 22.059 | 30.141 | 29.266 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 31.0 | 22.3 | G35T2 | 1 2 3 4 | 8 8 8 7
S/54-1 | SGBM15 | Jan 20 2016 9:40AM | Jan 20 2016 2:00PM | Jan 20 2016 10:55PM | Jan 21 2016 2:27AM | 51.972 | 49.675 | 52.61 | 0.00 | 13.314 | 37.658 | 36.361 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.5 | 50.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 10 9 11
N/57-2 | SGBM05 | Jan 19 2016 9:30AM | Jan 20 2016 10:40AM | Jan 20 2016 7:40PM | Jan 20 2016 10:20PM | 52.14 | 49.675 | 52.93 | 0.00 | 13.434 | 38.706 | 36.241 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.4 | 41.0 | 65.7 | G45T2 | 1 2 3 4 5 | 3 10 11 11 6
U/55-1 | SGBM17 | Jan 19 2016 4:24PM | Jan 20 2016 12:00PM | Jan 20 2016 3:25PM | Jan 20 2016 7:05PM | 51.827 | 51.375 | 52.64 | 0.00 | 21.940 | 29.887 | 29.435 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 7 7
M5/59-1 | SGBM01 | Jan 18 2016 5:30PM | Jan 20 2016 9:00AM | Jan 20 2016 2:25PM | Jan 20 2016 4:46PM | 51.851 | 51.075 | 52.66 | 0.00 | 13.861 | 37.990 | 37.214 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 8 7
N/56-2 | SGBM15 | Jan 19 2016 10:30AM | Jan 19 2016 5:40PM | Jan 19 2016 11:05PM | Jan 20 2016 1:02AM | 52.106 | 49.675 | 52.91 | 0.00 | 11.911 | 40.195 | 37.764 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.7 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 8 8 10
M6/59-1 | SGBM01 | Jan 18 2016 4:55PM | Jan 19 2016 3:20PM | Jan 19 2016 10:05PM | Jan 19 2016 11:57PM | 51.935 | 51.075 | 52.77 | 0.00 | 15.473 | 36.462 | 35.602 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.8 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 8 10 10 8
R/57-1 | SGBM15 | Jan 16 2016 11:40AM | Jan 19 2016 12:30PM | Jan 19 2016 5:45PM | Jan 19 2016 7:57PM | 51.878 | 51.375 | 52.66 | 0.00 | 17.258 | 34.620 | 34.117 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.5 | 33.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 9 8
V/52-2 | SGBM31 | Jan 19 2016 10:40AM | Jan 19 2016 4:00PM | Jan 19 2016 5:03PM | Jan 19 2016 7:35PM | 49.52 | 47.375 | 50.39 | 0.00 | 20.290 | 29.230 | 27.085 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.5 | 34.0 | -100.0 | G45T2 | 1 2 3 4 | 9 10 10 5
U/51-1 | SGBM17 | Jan 18 2016 1:15PM | Jan 19 2016 10:00AM | Jan 19 2016 3:30PM | Jan 19 2016 6:05PM | 51.817 | 51.375 | 52.45 | 0.00 | 23.248 | 28.569 | 28.127 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 29.0 | -100.0 | G45T2 | 1 2 3 4 | 8 7 7 7
S/58-1 | SGBM15 | Jan 16 2016 2:45PM | Jan 18 2016 6:05PM | Jan 18 2016 11:05PM | Jan 19 2016 12:42AM | 52.029 | 49.675 | 52.90 | 0.00 | 17.899 | 34.130 | 31.776 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.5 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 8
R/56-1 | SGBM15 | Jan 16 2016 11:05AM | Jan 18 2016 2:10PM | Jan 18 2016 7:20PM | Jan 18 2016 8:53PM | 51.985 | 51.375 | 52.90 | 0.00 | 15.203 | 36.782 | 36.172 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 8 10 8 9
M7/56-1 | SGBM05 | Jan 16 2016 8:45AM | Jan 16 2016 5:55PM | Jan 17 2016 1:05AM | Jan 17 2016 2:50AM | 52.133 | 50.925 | 52.92 | 0.00 | 13.717 | 38.416 | 37.208 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 8 7 7
P/58-1 | SGBM23 | Jan 16 2016 12:47PM | Jan 16 2016 5:15PM | Jan 16 2016 11:35PM | Jan 17 2016 1:20AM | 52.01 | 51.375 | 52.47 | 0.00 | 14.465 | 37.545 | 36.910 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.0 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 7 7 6
U/39-1 | SGBM20 | Jan 16 2016 8:36AM | Jan 16 2016 1:22PM | Jan 16 2016 11:05PM | Jan 17 2016 1:00AM | 52.34 | 51.325 | 53.16 | 0.00 | 22.159 | 30.181 | 29.166 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 29.0 | -100.0 | G35T2 | 1 2 3 4 | 8 7 7 7
R/54-1 | SGBM15 | Jan 16 2016 9:30AM | Jan 16 2016 4:15PM | Jan 16 2016 10:30PM | Jan 17 2016 12:00AM | 51.932 | 51.375 | 52.79 | 0.00 | 15.091 | 36.841 | 36.284 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.4 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 6
V/45-2 | SGBM31 | Jan 16 2016 8:37AM | Jan 16 2016 2:05PM | Jan 16 2016 7:00PM | Jan 16 2016 9:10PM | 50.55 | 47.275 | 51.41 | 0.00 | 19.110 | 31.440 | 28.165 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 31.0 | -100.0 | G45T2 | PJ4501 PJ4508 PJ4511 PJ4514 | 10 7 7 7
N/56-1 | SGBM23 | Jan 15 2016 10:40AM | Jan 16 2016 11:10AM | Jan 16 2016 5:20PM | Jan 16 2016 7:46PM | 52.153 | 49.675 | 52.88 | 0.00 | 12.485 | 39.668 | 37.190 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 41.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 8 8 7 7 4
V/53-1 | SGBM17 | Jan 15 2016 3:49PM | Jan 16 2016 11:52AM | Jan 16 2016 2:25PM | Jan 16 2016 5:00PM | 49.46 | 47.275 | 50.27 | 0.00 | 19.267 | 30.193 | 28.008 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 33.0 | -100.0 | G45T2 | PJ4479 PJ4482 PJ4483 PJ4485 PJ4490 | 8 8 7 7 3
L/45-1 | SGBM15 | Jan 7 2016 9:00AM | Jan 8 2016 3:50PM | Jan 8 2016 9:33PM | Jan 16 2016 12:13AM | 51.652 | 49.075 | 52.63 | 0.00 | 16.034 | 35.618 | 33.041 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
Q/55-1 | SGBM23 | Jan 12 2016 12:45PM | Jan 15 2016 12:05PM | Jan 15 2016 10:15PM | Jan 15 2016 11:55PM | 51.928 | 51.375 | 52.74 | 0.00 | 14.039 | 37.889 | 37.336 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.3 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 7
Q/53-1 | SGBM15 | Jan 13 2016 5:40PM | Jan 15 2016 5:45PM | Jan 15 2016 8:40PM | Jan 15 2016 11:00PM | 51.97 | 51.375 | 52.85 | 0.00 | 13.652 | 38.318 | 37.723 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.7 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 7
Q/57-1 | SGBM15 | Jan 12 2016 12:00PM | Jan 15 2016 11:40AM | Jan 15 2016 7:40PM | Jan 15 2016 9:50PM | 51.893 | 51.375 | 52.87 | 0.00 | 15.668 | 36.225 | 35.707 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.9 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
U/38-1 | SGBM03 | Jan 13 2016 5:35PM | Jan 14 2016 4:30PM | Jan 14 2016 11:05PM | Jan 15 2016 1:32AM | 52.366 | 51.325 | 53.21 | 0.00 | 22.910 | 29.456 | 28.415 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.6 | 32.0 | 30.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 5
S/56-2 | SGBM23 | Jan 13 2016 5:20PM | Jan 14 2016 4:05PM | Jan 14 2016 9:40PM | Jan 15 2016 12:05AM | 51.961 | 49.675 | 52.82 | 0.00 | 16.118 | 35.843 | 33.557 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.1 | 37.0 | -29.1 | G45T2 | 1 2 3 4 5 | 8 7 8 8 6
N/57-1 | SGBM23 | Jan 12 2016 10:45AM | Jan 14 2016 12:09PM | Jan 14 2016 8:35PM | Jan 14 2016 11:30PM | 52.109 | 49.675 | 53.01 | 0.00 | 12.608 | 39.501 | 37.067 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 40.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 10 7
Q/56-1 | SGBM15 | Jan 12 2016 12:00PM | Jan 14 2016 12:05PM | Jan 14 2016 6:45PM | Jan 14 2016 8:55PM | 51.895 | 51.375 | 52.74 | 0.00 | 14.139 | 37.756 | 37.236 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 7 8 7 6
V/45-1 | SGBM31 | Jan 13 2016 4:40PM | Jan 14 2016 4:00PM | Jan 14 2016 4:45PM | Jan 14 2016 7:00PM | 50.573 | 47.275 | 51.29 | 0.00 | 19.195 | 31.378 | 28.080 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 7 7
T/38-1 | SGBM03 | Jan 12 2016 4:00PM | Jan 14 2016 11:30AM | Jan 14 2016 3:00PM | Jan 14 2016 4:47PM | 52.289 | 51.325 | 53.15 | 0.00 | 24.047 | 81.389 | 27.278 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.6 | 30.0 | 6.4 | G45T2 | 1 2 3 4 5 | 7 7 7 6 3
N/55-2 | SGBM23 | Jan 11 2016 2:10PM | Jan 13 2016 4:30PM | Jan 13 2016 9:30PM | Jan 13 2016 11:56PM | 52.036 | 49.675 | 52.85 | 0.00 | 12.654 | 39.382 | 37.021 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 40.0 | 24.8 | G45T2 | 1 2 3 4 5 | 10 8 8 7 7
N/51-1 | SGBM05 | Jan 12 2016 1:41PM | Jan 12 2016 6:45PM | Jan 12 2016 10:23PM | Jan 13 2016 12:08AM | 51.968 | 50.775 | 52.86 | 0.00 | 13.059 | 38.909 | 37.716 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.7 | 39.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 8 8
N/54-2 | SGBM15 | Jan 11 2016 2:35PM | Jan 12 2016 10:05AM | Jan 12 2016 7:35PM | Jan 12 2016 9:35PM | 52.019 | 49.675 | 52.87 | 0.00 | 12.573 | 39.446 | 37.102 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 41.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 8 10
V/53-2 | SGBM17 | Jan 11 2016 3:46PM | Jan 12 2016 10:45AM | Jan 12 2016 2:25PM | Jan 12 2016 4:10PM | 49.56 | 47.275 | 50.47 | 0.00 | 19.267 | 30.293 | 28.008 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 30.0 | 23.7 | G45T2 | 1 2 3 4 | 8 8 7 7
Ta/39-1 | SGBM03 | Jan 11 2016 5:00PM | Jan 12 2016 11:00AM | Jan 12 2016 2:10PM | Jan 12 2016 3:52PM | 52.241 | 51.325 | 53.04 | 0.00 | 23.038 | 29.203 | 28.287 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
L/46-1 | SGBM23 | Jan 9 2016 9:55AM | Jan 11 2016 2:45PM | Jan 11 2016 4:40PM | Jan 11 2016 7:22PM | 51.731 | 49.075 | 52.66 | 0.00 | 15.159 | 36.572 | 33.916 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.4 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 10 8
N/37-2 | SGBM20 | Jan 11 2016 8:00AM | Jan 11 2016 11:30AM | Jan 11 2016 2:55PM | Jan 11 2016 4:30PM | 51.894 | 49.575 | 52.74 | 0.00 | 28.440 | 23.454 | 21.135 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 15.0 | -100.0 | G45T2 | 1 2 | 8 7
L/42-2 | SGBM15 | Jan 9 2016 9:10AM | Jan 9 2016 5:53PM | Jan 10 2016 12:25AM | Jan 10 2016 1:43AM | 51.81 | 49.075 | 52.71 | 0.00 | 19.710 | 32.100 | 29.365 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.4 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
S/37-2 | SGBM20 | Jan 9 2016 1:00PM | Jan 9 2016 4:00PM | Jan 9 2016 8:40PM | Jan 9 2016 10:00PM | 52.612 | 49.575 | 53.49 | 0.00 | 24.395 | 28.217 | 25.180 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 27.0 | -100.0 | G45T2 | 1 2 3 | 11.5 11.5 4
L/43-2 | SGBM15 | Jan 9 2016 10:55AM | Jan 9 2016 3:25PM | Jan 9 2016 7:45PM | Jan 9 2016 9:17PM | 51.857 | 49.075 | 52.75 | 0.00 | 18.853 | 33.004 | 30.222 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.2 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
T/37-1 | SGBM20 | Jan 9 2016 10:00AM | Jan 9 2016 2:54PM | Jan 9 2016 4:05PM | Jan 9 2016 5:46PM | 52.518 | 51.375 | 53.35 | 0.00 | 24.945 | 27.573 | 26.430 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.9 | 27.0 | -100.0 | G45T2 | 1 2 3 | 10 9 8
P/37-2 | SGBM16 | Jan 8 2016 8:30AM | Jan 8 2016 3:45PM | Jan 8 2016 10:34PM | Jan 8 2016 11:59PM | 52.012 | 49.475 | 52.89 | 0.00 | 27.889 | 24.123 | 21.586 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 23.0 | 23.0 | G45T2 | 1 2 3 | 8 8 7
P/37-1 | SGBM16 | Jan 8 2016 8:00AM | Jan 8 2016 3:58PM | Jan 8 2016 10:34PM | Jan 8 2016 11:51PM | 52.012 | 49.475 | 52.89 | 0.00 | 27.889 | 24.123 | 21.586 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 8 7
N/55-1 | SGBM23 | Jan 6 2016 5:10PM | Jan 8 2016 2:00PM | Jan 8 2016 7:50PM | Jan 8 2016 10:28PM | 51.89 | 49.675 | 52.33 | 0.00 | 12.330 | 39.560 | 37.345 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.3 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 8 7 7
W/60-2 | SGBM17 | Jan 8 2016 11:00AM | Jan 8 2016 4:56PM | Jan 8 2016 7:23PM | Jan 8 2016 9:40PM | 49.437 | 47.375 | 50.01 | 0.00 | 19.306 | 30.131 | 28.069 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 29.0 | -100.0 | G45T2 | 1 2 3 4 | 8 7 7 7
P/38-2 | SGBM16 | Jan 7 2016 5:05PM | Jan 8 2016 12:30PM | Jan 8 2016 6:39PM | Jan 8 2016 8:44PM | 51.913 | 49.475 | 52.80 | 0.00 | 26.299 | 78.413 | 23.176 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 28.0 | 39.5 | G45T2 | 1 2 3 4 | 8 9 8 3
W/61-2 | SGBM17 | Jan 7 2016 10:37AM | Jan 8 2016 11:25AM | Jan 8 2016 3:45PM | Jan 8 2016 6:30PM | 49.56 | 47.375 | 50.41 | 0.00 | 18.808 | 30.752 | 28.567 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 8 3
N/54-1 | SGBM23 | Jan 6 2016 5:00PM | Jan 8 2016 9:50AM | Jan 8 2016 11:30AM | Jan 8 2016 1:35PM | 51.765 | 49.675 | 52.69 | 0.00 | 12.486 | 39.279 | 37.189 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 8 7
L/44-1 | SGBM15 | Jan 7 2016 8:20AM | Jan 7 2016 2:50PM | Jan 7 2016 9:25PM | Jan 7 2016 11:43PM | 51.85 | 49.075 | 52.55 | 0.00 | 18.546 | 33.304 | 30.529 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.4 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 8
V/59-2 | SGBM17 | Jan 7 2016 4:40PM | Jan 7 2016 9:45PM | Jan 7 2016 8:20PM | Jan 7 2016 11:39PM | 49.392 | 47.075 | 50.00 | 0.00 | 17.303 | 32.089 | 29.772 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 34.0 | -100.0 | G45T2 | PJ4110 PJ4113 PJN4118 PJ4124 | 8 10 8 8
S/37-1 | SGBM20 | Jan 6 2016 4:00PM | Jan 7 2016 8:40AM | Jan 7 2016 10:55AM | Jan 7 2016 1:32PM | 52.72 | 49.575 | 53.54 | 0.00 | 24.440 | 28.280 | 25.135 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 8 7 7 6
V/58-2 | SGBM05 | Jan 6 2016 1:35PM | Jan 6 2016 9:30PM | Jan 7 2016 1:12AM | Jan 7 2016 4:03AM | 49.309 | 47.075 | 50.23 | 0.00 | 17.227 | 32.082 | 29.848 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 33.0 | -100.0 | G45T2 | PJ4075 PJ4077 PJ4078 PJ4079 | 8 8 7 10
L/46-2 | SGBM23 | Jan 5 2016 5:50PM | Jan 6 2016 6:35PM | Jan 6 2016 10:50PM | Jan 7 2016 12:50AM | 51.75 | 49.075 | 52.55 | 0.00 | 15.054 | 36.696 | 34.021 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.5 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 9 8 10 8
L/43-1 | SGBM15 | Jan 5 2016 11:05AM | Jan 6 2016 5:00PM | Jan 6 2016 9:10PM | Jan 6 2016 10:42PM | 51.87 | 49.075 | 52.69 | 0.00 | 18.689 | 33.181 | 30.386 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 8
V/60-2 | SGBM05 | Jan 6 2016 8:30AM | Jan 6 2016 2:00PM | Jan 6 2016 5:20PM | Jan 6 2016 8:19PM | 49.285 | 47.075 | 50.14 | 0.00 | 17.338 | 31.947 | 29.737 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 41.0 | -100.0 | G45T2 | C480014589 C480014T91 C480014593 C480014604 | 18 10 10 3
L/47-1 | SGBM23 | Jan 5 2016 2:35PM | Jan 6 2016 12:00PM | Jan 6 2016 5:19PM | Jan 6 2016 7:50PM | 51.65 | 49.075 | 52.59 | 0.00 | 15.889 | 36.700 | 33.186 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.7 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 8 10 9 8
L/47-2 | SGBM23 | Jan 5 2016 1:50PM | Jan 6 2016 12:00PM | Jan 6 2016 5:19PM | Jan 6 2016 7:50PM | 51.65 | 49.075 | 52.59 | 0.00 | 15.889 | 35.761 | 33.186 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.7 | 35.0 | 21.8 | G45T2 | 1 2 3 4 | 8 10 9 8
L/42-1 | SGBM15 | Jan 5 2016 10:40AM | Jan 6 2016 10:35AM | Jan 6 2016 3:17PM | Jan 6 2016 5:18PM | 51.86 | 49.075 | 52.78 | 0.00 | 19.676 | 32.184 | 29.399 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 8
M/49-1 | SGBM01 | Jan 4 2016 7:15PM | Jan 5 2016 4:00PM | Jan 5 2016 10:35PM | Jan 6 2016 1:20AM | 51.678 | 51.375 | 52.50 | 0.00 | 15.901 | 35.777 | 35.474 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.7 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 6 6 6
W/61-1 | SGBM19 | Jan 5 2016 3:30PM | Jan 5 2016 9:00PM | Jan 5 2016 10:30PM | Jan 6 2016 12:36AM | 49.693 | 47.375 | 50.60 | 0.00 | 18.900 | 30.793 | 28.475 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 33.0 | -24.7 | G45T2 | PJ4008 PJ4010 PJ4012 PJ4018 | 7 8 10 8
V/54-2 | SGBM05 | Jan 5 2016 1:30PM | Jan 5 2016 6:55PM | Jan 5 2016 9:25PM | Jan 5 2016 11:55PM | 49.159 | 47.375 | 50.28 | 0.00 | 18.684 | 30.475 | 28.691 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.8 | 30.0 | -24.8 | G45T2 | PJ4001 PJ4003 PJ4005 PJ4007 | 8 8 7 7
L/41-1 | SGBM15 | Jan 5 2016 10:10AM | Jan 5 2016 6:40PM | Jan 5 2016 8:55PM | Jan 5 2016 11:12PM | 51.88 | 49.075 | 52.80 | 0.00 | 20.501 | 31.379 | 28.574 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 7 7
M7/50-1 | SGBM01 | Jan 4 2016 7:35PM | Jan 5 2016 12:00PM | Jan 5 2016 8:15PM | Jan 5 2016 9:52PM | 51.783 | 51.175 | 52.68 | 0.00 | 15.479 | 36.304 | 35.696 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.9 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 9 8
W/60-1 | SGBM17 | Jan 5 2016 8:30AM | Jan 5 2016 1:30PM | Jan 5 2016 5:05PM | Jan 5 2016 8:24PM | 49.455 | 47.375 | 50.11 | 0.00 | 19.108 | 30.347 | 28.267 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 36.0 | -24.5 | G45T2 | C480014533 C480014535 C480014540 C480014543 | 11 10 10 5
L/40-1 | SGBM15 | Jan 5 2016 9:40AM | Jan 5 2016 3:20PM | Jan 5 2016 6:00PM | Jan 5 2016 7:33PM | 51.99 | 49.075 | 52.85 | 0.00 | 22.753 | 29.237 | 26.322 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.8 | 28.0 | -100.0 | G45T2 | 1 2 3 | 10 10 8
L/45-2 | SGBM23 | Jan 4 2016 3:50PM | Jan 5 2016 1:15PM | Jan 5 2016 5:25PM | Jan 5 2016 7:10PM | 51.76 | 49.075 | 52.57 | 0.00 | 16.271 | 35.489 | 32.804 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.4 | 34.0 | -28.4 | G45T2 | PJ3980 PJ3981 PJ3982 PJ3986 | 7 10 10 7
AA/57-1 | SGBM05 | Jan 4 2016 2:30PM | Jan 5 2016 1:00PM | Jan 5 2016 3:55PM | Jan 5 2016 5:18PM | 49.567 | 48.725 | 50.46 | 0.00 | 14.159 | 35.408 | 34.566 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 9 | - | 29.9 | 33.0 | -29.9 | G45T2 | C4800145526 C480014527 C480014532 | 11 11 11
L/38-1 | SGBM15 | Jan 4 2016 2:00PM | Jan 5 2016 8:45AM | Jan 5 2016 2:20PM | Jan 5 2016 4:05PM | 51.953 | 49.375 | 52.83 | 0.00 | 25.927 | 26.026 | 23.448 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 36.0 | -20.3 | G45T2 | PJ3968 PJ3969 PJ3970 | 18 8 10
L/44-2 | SGBM23 | Jan 4 2016 3:00PM | Jan 4 2016 9:00PM | Jan 5 2016 10:55AM | Jan 5 2016 12:34PM | 51.787 | 49.075 | 52.67 | 0.00 | 18.674 | 33.113 | 30.401 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 32.0 | -26.3 | G45T2 | PJ3956 PJ3957 PJ3960 PJ3963 | 9 8 8 7
Z/57-1 | SGBM19 | Jan 4 2016 8:30AM | Jan 4 2016 7:20PM | Jan 4 2016 11:10PM | Jan 5 2016 1:30AM | 49.524 | 48.625 | 50.35 | 0.00 | 15.853 | 33.671 | 32.772 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.4 | 35.0 | -100.0 | G35T2 | 1 2 3 4 | 10 8 8 9
L/41-2 | SGBM15 | Jan 2 2016 3:15PM | Jan 4 2016 6:10PM | Jan 4 2016 9:00PM | Jan 4 2016 11:40PM | 51.915 | 49.075 | 52.38 | 0.00 | 20.385 | 31.530 | 28.690 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.8 | 31.0 | -100.0 | G45T2 | 1 2 3 4 | 8 7 8 8
V/57-2 | SGBM17 | Jan 4 2016 11:30AM | Jan 4 2016 4:23PM | Jan 4 2016 7:30PM | Jan 4 2016 10:12PM | 49.524 | 47.075 | 50.24 | 0.00 | 16.535 | 32.989 | 30.540 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.4 | 33.0 | -26.4 | G45T2 | C480014454 C480014455 C480014458 | 10 11.5 11.5
L/40-2 | SGBM15 | Jan 2 2016 4:00PM | Jan 4 2016 1:40PM | Jan 4 2016 7:00PM | Jan 4 2016 9:20PM | 51.89 | 49.075 | 52.78 | 0.00 | 22.880 | 29.010 | 26.195 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.7 | 29.0 | -22.7 | G45T2 | PJ3925 PJ3927 PJ3928 PJ3931 | 8 7 7 7
V/58-1 | SGBM17 | Dec 31 2015 2:20PM | Jan 4 2016 1:30PM | Jan 4 2016 5:10PM | Jan 4 2016 7:35PM | 49.375 | 47.075 | 50.07 | 0.00 | 17.071 | 32.304 | 30.004 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 35.0 | -26.0 | G45T2 | C520124609 C480014443 C520124612 C521024613 | 7 11 9 8
L/39-1 | SGBM23 | Jan 4 2016 8:53AM | Jan 4 2016 2:10PM | Jan 4 2016 5:00PM | Jan 4 2016 7:18PM | 52.035 | 49.075 | 52.85 | 0.00 | 21.049 | 30.986 | 28.026 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 30.0 | -24.3 | G45T2 | PJ3918 PJ3920 PJ3921 PJ3923 | 8 8 7 7
L/36-1 | SGBM15 | Jan 2 2016 4:50PM | Jan 4 2016 9:37AM | Jan 4 2016 4:05PM | Jan 4 2016 6:08PM | 51.964 | 51.075 | 52.87 | 0.00 | 30.869 | 21.095 | 20.206 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.5 | 22.0 | -17.5 | G45T2 | PJ3912 PJ3915 PJ3917 | 8 7 7
V/55-2 | SGBM17 | Jan 2 2016 2:40PM | Jan 2 2016 8:10PM | Jan 2 2016 10:10PM | Jan 3 2016 12:15AM | 49.419 | 47.375 | 50.22 | 0.00 | 18.317 | 31.102 | 29.058 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 35.0 | -25.2 | G45T2 | C480014413 C480014414 C480014417 | 12 12 11
R/34-3 | SGBM01 | Jan 2 2016 11:45AM | Jan 2 2016 9:10PM | Jan 2 2016 10:10PM | Jan 2 2016 11:28PM | 52.203 | 48.825 | 52.83 | 0.00 | 26.534 | 25.669 | 22.291 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 9 8
L/38-2 | SGBM15 | Dec 31 2015 10:00AM | Jan 2 2016 5:24PM | Jan 2 2016 8:50PM | Jan 2 2016 10:05PM | 52.042 | 49.375 | 52.90 | 0.00 | 26.103 | 25.939 | 23.272 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.2 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 8 9
R/34-7 | SGBM01 | Jan 2 2016 11:00AM | Jan 2 2016 6:00PM | Jan 2 2016 7:15PM | Jan 2 2016 9:13PM | 52.223 | 48.825 | 52.92 | 0.00 | 26.324 | 25.899 | 22.501 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 8 8
V/60-1 | SGBM17 | Dec 31 2015 2:00PM | Jan 2 2016 1:25PM | Jan 2 2016 5:55PM | Jan 2 2016 8:43PM | 49.354 | 47.075 | 50.20 | 0.00 | 17.302 | 32.052 | 29.773 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 32.0 | -25.8 | G45T2 | C480014401 C480014403 C520124586 | 11 11 10
L/39-2 | SGBM15 | Dec 31 2015 9:25AM | Jan 2 2016 2:45PM | Jan 2 2016 6:35PM | Jan 2 2016 8:26PM | 51.947 | 49.075 | 52.90 | 0.00 | 23.899 | 28.048 | 25.176 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 27.0 | -21.8 | G45T2 | PJ3868 PJ3869 PJ3873 | 8 10 9
V/59-1 | SGBM05 | Dec 31 2015 5:00PM | Jan 2 2016 12:50PM | Jan 2 2016 4:50PM | Jan 2 2016 7:00PM | 49.305 | 47.075 | 50.04 | 0.00 | 17.337 | 31.968 | 29.738 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 33.0 | -100.0 | G45T2 | C480014395 C480014397 C48014399 | 11 11 11
L/49-1 | SGBM23 | Dec 31 2015 8:52AM | Jan 2 2016 2:30PM | Jan 2 2016 4:53PM | Jan 2 2016 6:35PM | 51.845 | 49.075 | 52.73 | 0.00 | 14.530 | 37.315 | 34.545 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.9 | 37.0 | -29.9 | G45T2 | PJ3860 PJ3862 PJ3863 PJ3865 | 10 9 8 10
L/37-1 | SGBM15 | Dec 31 2015 10:45AM | Jan 2 2016 11:05AM | Jan 2 2016 2:25PM | Jan 2 2016 4:10PM | 51.909 | 51.075 | 52.79 | 0.00 | 28.790 | 23.119 | 22.285 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 25.0 | -19.3 | G45T2 | PJ3848 PJ3850 PJ3854 | 8 9 8
H/46-2 | SGBM23 | Dec 31 2015 8:15AM | Jan 2 2016 9:45AM | Jan 2 2016 12:40PM | Jan 2 2016 3:05PM | 51.424 | 49.475 | 52.38 | 0.00 | 11.782 | 39.642 | 37.693 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.6 | 40.0 | 7.3 | G45T2 | PJ3841 PJ3842 PJ3843 PJ3845 PJ3847 | 8 10 8 7 7
P/33-2 | SGBM01 | Dec 31 2015 3:45PM | Dec 31 2015 7:22PM | Jan 1 2016 1:20AM | Jan 1 2016 2:44AM | 52.08 | 49.725 | 52.90 | 0.00 | 29.600 | 22.480 | 20.125 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.4 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
Ma/58-1 | SGBM15 | Dec 30 2015 3:33PM | Dec 31 2015 5:20PM | Dec 31 2015 8:45PM | Jan 1 2016 12:05AM | 51.85 | 51.375 | 52.72 | 0.00 | 15.324 | 36.526 | 36.051 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.2 | 34.0 | -31.2 | G45T2 | PJ3815 PJ3817 PJ3821 Pending | 8 10 8 8
V/54-1 | SGBM19 | Dec 31 2015 8:05AM | Dec 31 2015 1:45PM | Dec 31 2015 6:10PM | Dec 31 2015 8:40PM | 49.406 | 47.375 | 50.15 | 0.00 | 19.346 | 30.060 | 28.029 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 33.5 | -100.0 | G45T2 | C480014327 C480014330 C480014332 C480014337 | 6 11 11.5 5
Z/57-2 | SGBM05 | Dec 30 2015 6:50PM | Dec 31 2015 12:10PM | Dec 31 2015 5:10PM | Dec 31 2015 8:15PM | 49.519 | 48.625 | 50.41 | 0.00 | 14.906 | 34.613 | 33.719 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.2 | 34.0 | -100.0 | G35T2 | 1 2 3 4 | 7 11 11 5
G/42-3 | SGBM23 | Dec 30 2015 9:50AM | Dec 31 2015 10:25AM | Dec 31 2015 11:10AM | Dec 31 2015 1:05PM | 51.925 | 49.775 | 52.78 | 0.00 | 18.385 | 33.540 | 31.390 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.2 | 35.0 | -100.0 | G45T2 | PJ3777 PJ3778 PJ3779 PJ3780 PJ3781 | 8 7 7 7 6
R/34-8 | SGBM20 | Dec 30 2015 8:00PM | Dec 30 2015 11:00PM | Dec 31 2015 12:54AM | Dec 31 2015 2:25AM | 52.18 | 48.825 | 52.93 | 0.00 | 26.430 | 25.750 | 22.395 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 2
M/39-1 | SGBM15 | Dec 30 2015 8:00AM | Dec 30 2015 1:04PM | Dec 30 2015 11:25PM | Dec 31 2015 1:28AM | 51.93 | 51.375 | 52.87 | 0.00 | 27.168 | 24.762 | 24.207 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 26.0 | -21.0 | G45T2 | PJ3748 PJ3751 PJ3753 | 8 10 8
M/38-1 | SGBM15 | Dec 29 2015 10:20AM | Dec 30 2015 6:33PM | Dec 30 2015 9:45PM | Dec 30 2015 11:29PM | 51.824 | 51.375 | 52.79 | 0.00 | 28.292 | 23.532 | 23.083 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 24.0 | -100.0 | G45T2 | PJ3740 PJ3744 PJ3746 | 9 7 8
J/46-4 | SGBM23 | Dec 29 2015 2:35PM | Dec 30 2015 12:00PM | Dec 30 2015 7:42PM | Dec 30 2015 10:55PM | 51.58 | 49.375 | 52.51 | 0.00 | 14.206 | 37.374 | 35.169 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.5 | 38.0 | -8.1 | G45T2 | PJ3731 PJ3734 PJ3739 PJ3742 | 10 10 8 10
V/39-1a | SGBM19 | Dec 30 2015 8:00AM | Dec 30 2015 1:15PM | Dec 30 2015 7:15PM | Dec 30 2015 10:30PM | 49.94 | 47.075 | 50.72 | 0.00 | 17.017 | 32.923 | 30.058 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 34.0 | -100.0 | G35T2 | 1 2 3 4 | 11 10 8 5
M/36-1 | SGBM15 | Dec 29 2015 10:51AM | Dec 29 2015 2:28PM | Dec 30 2015 6:40PM | Dec 30 2015 8:35PM | 51.89 | 51.075 | 52.84 | 0.00 | 30.844 | 21.046 | 20.231 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.5 | 22.0 | -17.5 | G45T2 | PJ3725 3729 PJ3732 | 8 7 7
P/33-1 | SGBM20 | Dec 29 2015 7:00PM | Dec 30 2015 9:38AM | Dec 30 2015 6:07PM | Dec 30 2015 7:26PM | 52.135 | 49.725 | 52.88 | 0.00 | 29.176 | 22.959 | 20.549 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.8 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
V/55-1 | SGBM19 | Dec 29 2015 1:20PM | Dec 29 2015 6:28PM | Dec 30 2015 1:25AM | Dec 30 2015 3:24AM | 49.497 | 47.375 | 50.32 | 0.00 | 17.918 | 31.579 | 29.457 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 30.0 | -100.0 | G45T2 | PJ3714 PJ3715 PJ3716 PJ3717 | 8 8 7 7
R/34-9 | SGBM20 | Dec 29 2015 8:00AM | Dec 29 2015 4:45PM | Dec 29 2015 10:35PM | Dec 29 2015 11:53PM | 52.098 | 48.825 | 52.85 | 0.00 | 26.355 | 25.743 | 22.470 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 25.0 | -100.0 | G45T2 | 1 2 3 | 8 8 9
Ua/36-1 | SGBM16 | Dec 29 2015 1:00PM | Dec 29 2015 5:10PM | Dec 29 2015 8:24PM | Dec 29 2015 10:35PM | 52.278 | 51.325 | 52.92 | 0.00 | 25.325 | 26.953 | 26.000 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.5 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
Z/51-1 | SGBM19 | Dec 28 2015 5:45PM | Dec 29 2015 1:00PM | Dec 29 2015 6:15PM | Dec 29 2015 8:40PM | 49.501 | 46.925 | 50.40 | 0.00 | 16.399 | 33.102 | 30.526 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.4 | 30.0 | -100.0 | G45T2 | PJ3675 PJ3677 PJ3682 PJ3685 | 8 8 7 7
R/34-4 | SGBM03 | Dec 28 2015 3:00PM | Dec 29 2015 12:48PM | Dec 29 2015 4:22PM | Dec 29 2015 6:32PM | 52.145 | 48.825 | 52.84 | 0.00 | 26.638 | 25.507 | 22.187 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 25.0 | -19.2 | G45T2 | 1 2 3 | 10 8 7
Ua/37-1 | SGBM16 | Dec 28 2015 7:00PM | Dec 29 2015 12:00PM | Dec 29 2015 3:35PM | Dec 29 2015 6:10PM | 52.234 | 51.325 | 53.17 | 0.00 | 24.325 | 27.909 | 27.000 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 7 7
H/46-4 | SGBM15 | Dec 28 2015 5:30PM | Dec 29 2015 12:17PM | Dec 29 2015 2:48PM | Dec 29 2015 4:58PM | 51.379 | 49.475 | 52.31 | 0.00 | 12.013 | 39.366 | 37.462 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.4 | 40.0 | 23.3 | G45T2 | PJ3653 PJ3655 PJ3656 PJ3658 PJ3660 | 7 7 10 8 8
R/33-3 | SGBM03 | Dec 28 2015 3:47PM | Dec 29 2015 9:05AM | Dec 29 2015 1:22PM | Dec 29 2015 2:59PM | 52.215 | 49.775 | 53.01 | 0.00 | 27.708 | 77.515 | 22.067 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 24.0 | 4.9 | G45T2 | 1 2 3 | 8 8 8
Ma/58a-1 | SGBM23 | Dec 28 2015 1:00PM | Dec 28 2015 6:45PM | Dec 29 2015 11:56AM | Dec 29 2015 2:34PM | 51.807 | 51.075 | 52.48 | 0.00 | 14.977 | 36.830 | 36.098 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 36.0 | 15.2 | G45T2 | PJ3642 PJ3643 PJ3644 PJ3645 PJ3648 | 8 7 7 7 7
V/39-1b | SGBM17 | Dec 28 2015 8:40AM | Dec 28 2015 1:45PM | Dec 28 2015 11:10PM | Dec 29 2015 12:50AM | 49.652 | 47.075 | 50.43 | 0.00 | 15.827 | 33.825 | 31.248 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 33.0 | -100.0 | G35T2 | 1 2 3 4 | 8 8 8 9
X/60-1 | SGBM17 | Dec 28 2015 8:35AM | Dec 28 2015 2:46PM | Dec 28 2015 8:28PM | Dec 28 2015 10:35PM | 49.589 | 47.375 | 50.47 | 0.00 | 16.568 | 33.021 | 30.807 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.7 | 33.0 | -100.0 | G45T2 | PJ3612 PJ3615 PJ3617 PJ3621 | 9 8 8 8
S/26-1 | SGBM03 | Dec 26 2015 4:25PM | Dec 28 2015 5:15PM | Dec 28 2015 8:00PM | Dec 28 2015 9:28PM | 52.065 | 51.275 | 52.89 | 0.00 | 31.090 | 20.975 | 20.185 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.5 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
P/33-4 | SGBM01 | Dec 26 2015 6:30PM | Dec 28 2015 12:17PM | Dec 28 2015 6:48PM | Dec 28 2015 8:38PM | 51.951 | 49.725 | 52.84 | 0.00 | 29.638 | 22.313 | 20.087 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.4 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
Ma/57-1 | SGBM23 | Dec 26 2015 10:00AM | Dec 28 2015 12:15PM | Dec 28 2015 6:07PM | Dec 28 2015 8:25PM | 51.76 | 50.075 | 52.65 | 0.00 | 13.753 | 38.007 | 36.322 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.5 | 37.0 | 17.6 | G45T2 | PJ3596 PJ3598 PJ3601 PJ3603 PJ3607 | 8 7 8 7 7
Ma/56-1 | SGBM23 | Dec 28 2015 10:00AM | Dec 28 2015 4:19PM | Dec 28 2015 12:00PM | Dec 28 2015 1:51PM | 51.894 | 50.075 | 52.82 | 0.00 | 14.018 | 37.876 | 36.057 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.2 | 37.0 | 18.5 | G45T2 | PJ3573 PJ3574 PJ3576 PJ3577 PJ3578 | 10 8 7 6 6
G/42-1 | SGBM15 | Dec 23 2015 1:35PM | Dec 26 2015 8:54PM | Dec 28 2015 11:08AM | Dec 28 2015 1:28PM | 51.935 | 49.775 | 52.88 | 0.00 | 18.475 | 33.460 | 31.300 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 33.0 | 21.7 | G45T2 | PJ3568 PJ3571 PJ3572 PJ3575 | 8 9 8 8
Ma/55-1 | SGBM23 | Dec 26 2015 9:48AM | Dec 26 2015 3:25PM | Dec 26 2015 9:45PM | Dec 26 2015 11:35PM | 51.79 | 50.075 | 52.68 | 0.00 | 13.683 | 38.107 | 36.392 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.5 | 38.0 | -100.0 | G45T2 | PJ3558 PJ3561 PJ3564 PJ3565 PJ3566 | 10 7 7 7 7
G/41-2 | SGBM15 | Dec 23 2015 2:00PM | Dec 26 2015 8:02PM | Dec 26 2015 9:03PM | Dec 26 2015 11:00PM | 51.908 | 49.675 | 52.95 | 0.00 | 18.452 | 33.456 | 31.223 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.0 | 34.0 | 25.7 | G45T2 | PJ3555 PJ3557 PJ3560 PJ3563 | 8 8 8 10
Q/33a-2 | SGBM01 | Dec 26 2015 4:00PM | Dec 26 2015 6:55PM | Dec 26 2015 9:15PM | Dec 26 2015 10:45PM | 52.223 | 49.675 | 53.00 | 0.00 | 27.400 | 24.823 | 22.275 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 25.0 | -19.3 | G45T2 | 1 2 3 | 10 8 7
G/40-2 | SGBM15 | Dec 23 2015 2:00PM | Dec 26 2015 2:10PM | Dec 26 2015 6:50PM | Dec 26 2015 9:10PM | 52 | 49.675 | 52.88 | 0.00 | 19.575 | 32.425 | 30.100 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 32.0 | -100.0 | G45T2 | PJ3541 PJ3545 PJ3546 PJ3550 | 8 8 8 8
Q/26-1 | SGBM03 | Dec 26 2015 8:00AM | Dec 26 2015 12:19PM | Dec 26 2015 7:26PM | Dec 26 2015 9:05PM | 52.076 | 51.275 | 52.96 | 0.00 | 30.159 | 21.917 | 21.116 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 22.0 | -100.0 | G45T2 | 1 2 3 | 9 7 6
X/60-3 | SGBM17 | Dec 22 2015 3:55PM | Dec 26 2015 3:30PM | Dec 26 2015 4:55PM | Dec 26 2015 7:35PM | 49.754 | 47.375 | 50.50 | 0.00 | 16.500 | 33.254 | 30.875 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.7 | 40.0 | -100.0 | G45T2 | PJ3528 PJ3530 PJ3534 PJ3537 PJ3542 | 10 8 8 9 5
R/34-1 | SGBM20 | Dec 26 2015 1:00PM | Dec 26 2015 3:55PM | Dec 26 2015 5:54PM | Dec 26 2015 7:03PM | 52.123 | 48.825 | 52.72 | 0.00 | 26.323 | 25.800 | 22.502 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 24.0 | -19.5 | G45T2 | 1 2 3 | 8 8 8
Z/51-2 | SGBM17 | Dec 23 2015 9:20AM | Dec 23 2015 3:37PM | Dec 24 2015 3:44AM | Dec 24 2015 8:30PM | 49.46 | 46.925 | 50.27 | 0.00 | 16.574 | 32.886 | 30.351 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 40.0 | -100.0 | G45T2 | C520124379 C520124381 C520124384 C520124385 C520124389 | 9 9 7 10 5
S/33-2 | SGBM20 | Dec 22 2015 5:10PM | Dec 23 2015 7:48PM | Dec 24 2015 12:16PM | Dec 24 2015 1:42PM | 52.25 | 49.225 | 53.03 | 0.00 | 27.026 | 25.224 | 22.199 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 27.0 | -100.0 | G45T2 | 1 2 3 | 11 10 6
J/46-2 | SGBM23 | Dec 23 2015 1:30PM | Dec 23 2015 6:50PM | Dec 24 2015 3:12AM | Dec 24 2015 5:15AM | 51.583 | 49.375 | 52.43 | 0.00 | 14.031 | 37.552 | 35.344 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 35.0 | -30.6 | G45T2 | C520124376 C52014377 C520124380 C520124381 C520124382 | 7 6 10 3 9
G/45-2 | SGBM23 | Dec 23 2015 8:40AM | Dec 23 2015 3:37PM | Dec 23 2015 11:35PM | Dec 24 2015 1:37AM | 51.56 | 49.675 | 52.46 | 0.00 | 11.558 | 40.002 | 38.117 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.0 | 42.0 | -33.0 | G45T2 | C521024361 C520124362 C520124366 C520124368 | 10 10 10 12
Y/60-2 | SGBM05 | Dec 22 2015 5:40PM | Dec 23 2015 1:00PM | Dec 23 2015 7:20PM | Dec 23 2015 10:40PM | 49.316 | 47.375 | 50.03 | 0.00 | 14.134 | 35.182 | 33.241 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 37.0 | -100.0 | G45T2 | C480013928 C480013930 C520124351 C520124356 | 11 9 12 5
Z/52-1 | SGBM19 | Dec 22 2015 9:10AM | Dec 22 2015 4:53PM | Dec 23 2015 2:07AM | Dec 23 2015 7:10AM | 49.571 | 46.925 | 50.39 | 0.00 | 15.886 | 33.685 | 31.039 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 36.0 | -100.0 | G45T2 | C480013870 C480013875 C480013879 C480013883 | 11 10 10 5
W/58-2 | SGBM05 | Dec 22 2015 8:20AM | Dec 22 2015 2:10PM | Dec 23 2015 1:56AM | Dec 23 2015 4:40AM | 49.223 | 47.375 | 50.16 | 0.00 | 19.263 | 29.960 | 28.112 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 32.0 | -100.0 | G45T2 | C520124333 C520124336 C480013876 | 12 10 10
K/40-2 | SGBM15 | Dec 22 2015 5:35PM | Dec 22 2015 8:15PM | Dec 23 2015 2:22AM | Dec 23 2015 4:00AM | 51.89 | 49.675 | 52.83 | 0.00 | 22.528 | 29.362 | 27.147 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.5 | 27.0 | 27.6 | G45T2 | 1 2 3 | 10 10 7
G/43-2 | SGBM15 | Dec 19 2015 12:55PM | Dec 22 2015 2:05PM | Dec 22 2015 10:00PM | Dec 23 2015 1:35AM | 51.66 | 49.675 | 52.71 | 0.00 | 16.505 | 35.155 | 33.170 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.7 | 37.0 | -28.7 | G45T2 | C480013853 C520124330 C480013866 C480013867 | 3 12 11 11
W/57-1 | SGBM16 | Dec 21 2015 4:00PM | Dec 22 2015 11:48AM | Dec 22 2015 9:50PM | Dec 23 2015 1:35AM | 49.441 | 47.375 | 50.33 | 0.00 | 19.332 | 30.109 | 28.043 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 33.0 | -100.0 | G45T2 | C480013851 C480013861 C480013863 | 11 11 11
R/33-2 | SGBM20 | Dec 21 2015 4:25PM | Dec 22 2015 1:44PM | Dec 22 2015 9:52PM | Dec 23 2015 1:21AM | 51.92 | 49.775 | 49.78 | 0.00 | 26.275 | 25.645 | 23.500 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 25.0 | -100.0 | G45T2 | 1 2 3 | 11 11 3
G/42-2 | SGBM15 | Dec 19 2015 1:19PM | Dec 19 2015 10:00PM | Dec 22 2015 10:00PM | Dec 23 2015 1:20AM | 51.873 | 49.775 | 52.83 | 0.00 | 17.331 | 35.500 | 32.444 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 37.0 | 31.7 | G45T2 | 1 2 3 4 | 3 12 11 11
P/33-3 | SGBM20 | Dec 21 2015 5:25PM | Dec 22 2015 4:30PM | Dec 22 2015 6:37PM | Dec 22 2015 9:25PM | 51.868 | 49.725 | 52.62 | 0.00 | 29.323 | 22.545 | 20.402 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.7 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
W/54-1 | SGBM17 | Dec 22 2015 8:40AM | Dec 22 2015 3:45PM | Dec 22 2015 7:15PM | Dec 22 2015 9:16PM | 49.469 | 47.375 | 50.26 | 0.00 | 18.363 | 31.106 | 29.012 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.1 | 30.0 | -100.0 | G45T2 | C4800137835 C480013837 C480013843 | 10 9 11
R/34-6 | SGBM20 | Dec 21 2015 3:40PM | Dec 22 2015 10:56AM | Dec 22 2015 4:47PM | Dec 22 2015 8:22PM | 51.953 | 48.825 | 52.73 | 0.00 | 26.526 | 25.427 | 22.299 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 9 7
J/46-1 | SGBM23 | Dec 19 2015 7:05PM | Dec 21 2015 7:30PM | Dec 22 2015 2:09AM | Dec 22 2015 3:20AM | 51.595 | 49.375 | 52.52 | 0.00 | 13.523 | 38.072 | 35.852 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.0 | 41.0 | -100.0 | G45T2 | 1 2 3 4 | 10 11 10 10
H/46-1 | SGBM23 | Dec 19 2015 7:30PM | Dec 21 2015 4:15PM | Dec 22 2015 12:06AM | Dec 22 2015 1:50AM | 51.43 | 49.475 | 52.23 | 0.00 | 12.234 | 39.196 | 37.241 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.3 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 9 11 10 10
W/52-1 | SGBM19 | Dec 21 2015 2:20PM | Dec 21 2015 7:00PM | Dec 21 2015 9:36PM | Dec 22 2015 1:25AM | 49.232 | 47.025 | 49.95 | 0.00 | 18.447 | 30.785 | 28.578 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 34.0 | -100.0 | G45T2 | PJ3469 PJ3470 PJ3473 PJ3475 PJ3477 | 8 8 7 7 4
G/41-1 | SGBM15 | Dec 19 2015 1:53PM | Dec 21 2015 3:30PM | Dec 21 2015 9:09PM | Dec 21 2015 10:30PM | 51.85 | 49.675 | 52.92 | 0.00 | 18.424 | 33.426 | 31.251 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 31.0 | 14.5 | G45T2 | 1 2 3 | 10 11 10
R/34-2 | SGBM20 | Dec 21 2015 3:30PM | Dec 21 2015 7:05PM | Dec 21 2015 9:33PM | Dec 21 2015 10:30PM | 51.968 | 48.825 | 52.82 | 0.00 | 26.724 | 25.244 | 22.101 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 25.0 | -19.1 | G45T2 | 1 2 3 | 12 10 3
Y/60-3 | SGBM19 | Dec 21 2015 10:00AM | Dec 21 2015 4:00PM | Dec 21 2015 7:13PM | Dec 21 2015 9:55PM | 49.408 | 47.375 | 50.56 | 0.00 | 14.865 | 34.543 | 32.510 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.2 | 36.0 | -100.0 | G45T2 | PJ3457 PJ3460 PJ3462 PJ3465 | 10 10 8 8
Y/61-1 | SGBM17 | Dec 21 2015 9:30AM | Dec 21 2015 4:00PM | Dec 21 2015 5:20PM | Dec 21 2015 8:51PM | 49.673 | 47.475 | 50.25 | 0.00 | 15.046 | 34.627 | 32.429 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 31.0 | 2.9 | G45T2 | PJ3448 PJ3451 PJ3454 PJ3459 | 8 7 8 8
G/40-1 | SGBM15 | Dec 19 2015 2:36PM | Dec 21 2015 11:30AM | Dec 21 2015 7:35PM | Dec 21 2015 8:15PM | 52 | 49.675 | 52.96 | 0.00 | 19.561 | 32.439 | 30.114 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 34.0 | 30.4 | G45T2 | 1 2 3 | 12 10 12
P/20-4 | SGBM20 | Dec 21 2015 8:00AM | Dec 21 2015 12:15PM | Dec 21 2015 3:01PM | Dec 21 2015 4:40PM | 53.869 | 51.125 | 54.53 | 0.00 | 27.828 | 26.041 | 23.297 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.2 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
X/60-2 | SGBM17 | Dec 19 2015 10:30AM | Dec 19 2015 7:45PM | Dec 20 2015 3:29AM | Dec 20 2015 7:04AM | 49.666 | 47.375 | 50.40 | 0.00 | 14.796 | 34.870 | 32.579 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.2 | 37.5 | -28.2 | G45T2 | C480013702 C480013703 C480013706 C480013709 | 10 11 11.5 5
X/61-1 | SGBM19 | Dec 19 2015 2:14PM | Dec 19 2015 11:50PM | Dec 20 2015 3:48AM | Dec 20 2015 6:30AM | 49.756 | 47.475 | 50.56 | 0.00 | 16.557 | 33.199 | 30.918 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.8 | 31.5 | -100.0 | G45T2 | 1 2 3 | 9 11.5 11
Y/60-1 | SGBM16 | Dec 19 2015 10:30AM | Dec 19 2015 9:46PM | Dec 20 2015 12:36AM | Dec 20 2015 2:55AM | 49.487 | 47.375 | 50.36 | 0.00 | 13.460 | 36.027 | 33.915 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.4 | 33.0 | -100.0 | G45T2 | C520124244 C480013695 C520124247 | 12 11 10
P/20-2 | SGBM03 | Dec 19 2015 8:00AM | Dec 19 2015 12:20PM | Dec 19 2015 7:35PM | Dec 19 2015 9:06PM | 54.034 | 51.125 | 54.64 | 0.00 | 27.641 | 26.393 | 23.484 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 20.0 | -100.0 | G45T2 | 1 2 | 10 10
R/34-5 | SGBM01 | Dec 18 2015 7:15PM | Dec 19 2015 1:47PM | Dec 19 2015 4:48PM | Dec 19 2015 7:13PM | 52.211 | 48.825 | 53.00 | 0.00 | 26.502 | 25.709 | 22.323 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 26.0 | -100.0 | G45T2 | 1 2 3 | 11 11 4
R/34-10 | SGBM01 | Dec 18 2015 6:30PM | Dec 19 2015 11:17AM | Dec 19 2015 2:21PM | Dec 19 2015 3:52PM | 52.076 | 48.825 | 52.74 | 0.00 | 26.244 | 25.832 | 22.581 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 25.0 | -100.0 | G45T2 | Pending 2 3 4 | 8 5 5 7
Y/61-3 | SGBM05 | Dec 17 2015 8:40AM | Dec 18 2015 7:00PM | Dec 18 2015 11:18PM | Dec 19 2015 2:15AM | 49.749 | 47.475 | 50.49 | 0.00 | 14.788 | 34.961 | 32.687 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.3 | 37.0 | -100.0 | G45T2 | PJ3394 PJ3397 PJ3400 PJ3401 PJ3406 PJ3407 | 7 7 7 7 6 3
W/52-3 | SGBM19 | Dec 18 2015 8:35AM | Dec 18 2015 6:00PM | Dec 18 2015 11:02PM | Dec 19 2015 1:40AM | 49.23 | 47.025 | 50.01 | 0.00 | 18.507 | 30.723 | 28.518 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 33.0 | -100.0 | G45T2 | PJ3392 PJ3393 PJ3395 PJ3404 | 7 8 8 10
G/44-2 | SGBM23 | Dec 17 2015 1:20PM | Dec 18 2015 8:15PM | Dec 18 2015 10:15PM | Dec 18 2015 11:20PM | 51.54 | 49.675 | 52.54 | 0.00 | 14.043 | 37.497 | 35.632 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.9 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 10 10
R/33-1 | SGBM20 | Dec 17 2015 6:00PM | Dec 18 2015 10:53AM | Dec 18 2015 8:19PM | Dec 18 2015 10:44PM | 52.131 | 49.775 | 49.78 | 0.00 | 24.175 | 27.956 | 25.600 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.2 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 2
G/45-1 | SGBM23 | Dec 17 2015 12:59PM | Dec 18 2015 5:00PM | Dec 18 2015 7:40PM | Dec 18 2015 9:55PM | 51.492 | 49.675 | 52.42 | 0.00 | 11.119 | 40.373 | 38.556 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.4 | 42.0 | -100.0 | G45T2 | 1 2 3 4 | 9 11 11 11
K/40-1 | SGBM15 | Dec 18 2015 9:15AM | Dec 18 2015 4:45PM | Dec 18 2015 6:30PM | Dec 18 2015 8:20PM | 51.862 | 49.675 | 52.84 | 0.00 | 22.639 | 29.223 | 27.036 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 30.0 | 28.1 | G45T2 | 1 2 3 4 | 8 8 7 7
G/46-1 | SGBM23 | Dec 17 2015 12:38PM | Dec 18 2015 11:00AM | Dec 18 2015 6:43PM | Dec 18 2015 8:00PM | 51.59 | 49.675 | 52.45 | 0.00 | 9.250 | 42.340 | 40.425 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.0 | 43.0 | 22.8 | G45T2 | 1 2 3 4 | 11 11 11 10
S/33-1 | SGBM01 | Dec 17 2015 2:30PM | Dec 17 2015 9:57PM | Dec 18 2015 12:13PM | Dec 18 2015 1:58PM | 52.166 | 49.225 | 53.06 | 0.00 | 26.055 | 26.111 | 23.170 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 8 7 6 6
X/61-3 | SGBM05 | Dec 17 2015 8:45AM | Dec 17 2015 5:27PM | Dec 18 2015 3:08AM | Dec 18 2015 7:11AM | 49.725 | 47.475 | 50.59 | 0.00 | 17.394 | 32.331 | 30.081 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 32.0 | -100.0 | G45T2 | C520124198 C520124200 C480013751 | 10 12 10
H/46-3 | SGBM23 | Dec 17 2015 11:16AM | Dec 17 2015 7:25PM | Dec 18 2015 2:24AM | Dec 18 2015 5:30AM | 51.464 | 49.475 | 52.30 | 0.00 | 11.901 | 39.563 | 37.574 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.5 | 38.0 | 19.9 | G45T2 | 1 2 3 4 5 | 8 9 7 8 6
Z/56a-2 | SGBM16 | Dec 17 2015 11:26AM | Dec 17 2015 8:00PM | Dec 18 2015 2:40AM | Dec 18 2015 3:45AM | 49.328 | 48.425 | 50.10 | 0.00 | 16.400 | 32.928 | 32.025 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.7 | 34.0 | -100.0 | G45T2 | C480013565 C480013566 C520124196 C520124198 | 10 10 10 4
F/39-1 | SGBM23 | Dec 15 2015 12:43PM | Dec 17 2015 10:55AM | Dec 17 2015 9:54PM | Dec 18 2015 1:30AM | 51.919 | 51.375 | 52.79 | 0.00 | 22.188 | 82.519 | 29.187 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 28.0 | 10.8 | G45T2 | 1 2 3 4 | 7 7 7 7
W/55-2 | SGBM17 | Dec 16 2015 4:45PM | Dec 17 2015 4:30PM | Dec 17 2015 9:40PM | Dec 17 2015 11:45PM | 49.646 | 47.375 | 50.37 | 0.00 | 18.372 | 31.274 | 29.003 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.1 | 32.0 | -100.0 | G45T2 | PJ3307 PJ3313 PJ3314 PJ3318 | 10 9 8 5
L/49-2 | SGBM15 | Dec 16 2015 9:57AM | Dec 17 2015 11:43AM | Dec 17 2015 8:27PM | Dec 17 2015 10:51PM | 51.9 | 49.075 | 52.84 | 0.00 | 14.742 | 37.158 | 34.333 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.7 | 37.0 | 24.4 | G45T2 | 1 2 3 4 | 10 7 10 10
S/29-1 | SGBM01 | Dec 17 2015 8:00AM | Dec 17 2015 11:05AM | Dec 17 2015 8:53PM | Dec 17 2015 10:30PM | 52.022 | 51.375 | 52.83 | 0.00 | 30.227 | 21.795 | 21.148 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 8 7
P/20-1 | SGBM20 | Dec 17 2015 8:00AM | Dec 17 2015 1:41PM | Dec 17 2015 8:38PM | Dec 17 2015 10:29PM | 55.716 | 51.125 | 56.35 | 0.00 | 27.846 | 27.870 | 23.279 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.2 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
Y/59-2 | SGBM16 | Dec 16 2015 4:15PM | Dec 17 2015 2:50PM | Dec 17 2015 6:57PM | Dec 17 2015 10:10PM | 49.569 | 47.275 | 50.20 | 0.00 | 14.900 | 34.669 | 32.375 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 34.0 | -100.0 | G45T2 | PJ3287 PJ3294 PJ3297 PJ3303 | 10 10 7 7
L/48-2 | SGBM15 | Dec 16 2015 10:25AM | Dec 16 2015 9:20PM | Dec 17 2015 5:15PM | Dec 17 2015 7:29PM | 51.652 | 49.075 | 52.66 | 0.00 | 14.661 | 36.991 | 34.414 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.8 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 7
Q/33a-1 | SGBM20 | Dec 16 2015 11:25AM | Dec 16 2015 5:30PM | Dec 17 2015 3:06PM | Dec 17 2015 5:19PM | 52.165 | 49.675 | 52.97 | 0.00 | 28.574 | 23.591 | 21.101 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 7 8
Pa/32-1 | SGBM20 | Dec 16 2015 1:30PM | Dec 16 2015 8:35PM | Dec 17 2015 1:25PM | Dec 17 2015 2:47PM | 52.077 | 51.075 | 52.85 | 0.00 | 28.651 | 76.277 | 22.424 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 24.0 | -100.0 | G45T2 | 1 2 3 | 8 8 8
Y/57-2 | SGBM05 | Dec 16 2015 1:30PM | Dec 16 2015 9:29PM | Dec 17 2015 4:45AM | Dec 17 2015 7:04AM | 49.364 | 47.375 | 50.11 | 0.00 | 16.808 | 32.556 | 30.567 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.5 | 35.0 | -100.0 | G45T2 | PJ3255 PJ3256 Pending PJ3258 PJ3259 | 7 7 7 7 7
W/58-1 | SGBM16 | Dec 16 2015 9:00AM | Dec 16 2015 4:00PM | Dec 17 2015 3:00AM | Dec 17 2015 4:47AM | 49.28 | 47.375 | 50.19 | 0.00 | 18.986 | 30.294 | 28.389 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.6 | 30.0 | -100.0 | G45T2 | PJ3251 PJ3252 PJ3253 PJ3254 | 8 8 8 6
G/43-1 | SGBM23 | Dec 15 2015 4:40PM | Dec 16 2015 9:55PM | Dec 17 2015 1:27AM | Dec 17 2015 3:00AM | 51.811 | 49.675 | 52.62 | 0.00 | 16.624 | 35.187 | 33.051 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 8 7
Y/52-1 | SGBM05 | Dec 12 2015 5:30PM | Dec 16 2015 6:20PM | Dec 16 2015 11:11PM | Dec 17 2015 1:15AM | 49.666 | 47.475 | 50.63 | 0.00 | 17.035 | 32.631 | 30.440 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.4 | 32.0 | -100.0 | G45T2 | PJ3231 PJ3234 PJ3238 PJ3240 | 8 8 8 8
K/48-1 | SGBM15 | Dec 16 2015 10:49AM | Dec 16 2015 5:30PM | Dec 16 2015 10:05PM | Dec 17 2015 12:25AM | 51.34 | 49.675 | 52.35 | 0.00 | 16.655 | 34.685 | 33.020 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 35.0 | 22.4 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
R/19-3 | SGBM03 | Dec 16 2015 8:00AM | Dec 16 2015 1:12PM | Dec 16 2015 9:10PM | Dec 16 2015 11:38PM | 55.878 | 48.925 | 56.51 | 0.00 | 26.514 | 29.364 | 22.411 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 26.0 | -19.4 | G45T2 | 1 2 3 4 | 8 8 8 2
S/28-1 | SGBM20 | Dec 15 2015 7:00PM | Dec 16 2015 8:47AM | Dec 16 2015 4:45PM | Dec 16 2015 6:48PM | 52.084 | 51.375 | 52.92 | 0.00 | 30.115 | 21.969 | 21.260 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.4 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 8 7
G/44-1 | SGBM23 | Dec 15 2015 5:30PM | Dec 15 2015 9:50PM | Dec 16 2015 4:35PM | Dec 16 2015 6:19PM | 51.5 | 49.675 | 52.44 | 0.00 | 13.542 | 37.958 | 36.133 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 8 7
Y/58-1 | SGBM17 | Dec 15 2015 4:30PM | Dec 15 2015 11:45PM | Dec 16 2015 2:11AM | Dec 16 2015 5:10AM | 49.315 | 47.375 | 58.15 | 0.00 | 23.549 | 25.766 | 23.826 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 39.0 | -100.0 | G45T2 | PJ3177 PJ3179 PJ3180 PJ3182 PJ3184 PJ3185 | 7 7 7 6 7 5
L/48-1 | SGBM15 | Dec 15 2015 10:48AM | Dec 15 2015 5:00PM | Dec 15 2015 8:48PM | Dec 15 2015 11:00PM | 51.59 | 49.075 | 52.67 | 0.00 | 14.974 | 36.616 | 34.101 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.5 | 37.0 | 25.3 | G45T2 | 1 2 3 4 5 | 8 7 7 8 7
X/61-2 | SGBM17 | Dec 14 2015 6:30PM | Dec 15 2015 2:45PM | Dec 15 2015 8:22PM | Dec 15 2015 9:30PM | 49.775 | 47.475 | 50.71 | 0.00 | 17.106 | 32.669 | 30.369 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 33.0 | -100.0 | G45T2 | C480013332 C480013334 C480013335 | 11 11 11
Y/61-2 | SGBM17 | Dec 14 2015 3:40PM | Dec 15 2015 4:00PM | Dec 15 2015 5:58PM | Dec 15 2015 8:03PM | 49.766 | 47.475 | 50.51 | 0.00 | 14.513 | 35.253 | 32.962 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.5 | 33.5 | -100.0 | G45T2 | C480013318 C480013321 C480013326 | 11.5 11 11
Qb/32-1 | SGBM20 | Dec 14 2015 3:13PM | Dec 14 2015 9:05PM | Dec 15 2015 6:13PM | Dec 15 2015 7:42PM | 52.149 | 51.075 | 52.82 | 0.00 | 29.020 | 23.129 | 22.055 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 22.5 | -100.0 | G45T2 | 1 2 | 11.5 11
J/63a-1 | SGBM23 | Dec 14 2015 4:03PM | Dec 15 2015 12:50PM | Dec 15 2015 4:09PM | Dec 15 2015 7:10PM | 52.026 | 51.275 | 52.92 | 0.00 | 9.115 | 42.911 | 42.160 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 44.0 | 20.5 | G45T2 | 1 2 3 4 5 6 | 7 7 7 8 8 7
R/28-1 | SGBM01 | Dec 14 2015 3:15PM | Dec 14 2015 9:00PM | Dec 15 2015 2:52PM | Dec 15 2015 4:20PM | 52.097 | 51.375 | 52.95 | 0.00 | 30.151 | 21.946 | 21.224 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.4 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
G/46-2 | SGBM23 | Dec 14 2015 5:56PM | Dec 15 2015 9:16AM | Dec 15 2015 1:47PM | Dec 15 2015 3:50PM | 51.54 | 49.675 | 52.43 | 0.00 | 9.131 | 42.409 | 40.544 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.1 | 43.0 | 22.5 | G45T2 | 1 2 3 4 5 6 | 7 8 7 7 7 7
P/20-3 | SGBM03 | Dec 14 2015 6:05PM | Dec 15 2015 10:17AM | Dec 15 2015 2:13PM | Dec 15 2015 3:48PM | 55.73 | 51.125 | 56.43 | 0.00 | 27.631 | 28.099 | 23.494 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 6 6
W/57-2 | SGBM17 | Dec 14 2015 8:45AM | Dec 14 2015 8:16PM | Dec 15 2015 7:15AM | Dec 15 2015 10:02AM | 49.531 | 47.375 | 50.36 | 0.00 | 19.262 | 30.269 | 28.113 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 33.5 | -100.0 | G45T2 | C48001389 C480013291 C480013294 C480013295 | 7.5 10 8 8
H/47-1 | SGBM23 | Dec 12 2015 6:29PM | Dec 14 2015 5:17PM | Dec 15 2015 6:15AM | Dec 15 2015 8:45AM | 51.331 | 49.675 | 52.24 | 0.00 | 14.342 | 36.989 | 35.333 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 38.0 | 24.2 | G45T2 | 1 2 3 4 | 8 11 9 10
Z/56a-1 | SGBM19 | Dec 14 2015 10:40AM | Dec 14 2015 8:15PM | Dec 15 2015 4:35AM | Dec 15 2015 7:45AM | 49.473 | 48.425 | 50.32 | 0.00 | 16.323 | 33.150 | 32.102 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 33.0 | 18.7 | G45T2 | C480013278 C480013283 C480013287 C480013289 | 9 11.5 11 1.5
K/48-2 | SGBM15 | Dec 12 2015 6:05PM | Dec 14 2015 7:26PM | Dec 15 2015 4:40AM | Dec 15 2015 6:45AM | 51.426 | 49.675 | 52.42 | 0.00 | 16.417 | 35.009 | 33.258 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 35.5 | 6.7 | G45T2 | 1 2 3 4 | 11.5 9 11.5 3.5
K/49-1 | SGBM15 | Dec 12 2015 5:20PM | Dec 14 2015 4:30PM | Dec 15 2015 12:40AM | Dec 15 2015 4:13AM | 51.62 | 49.675 | 52.69 | 0.00 | 15.393 | 36.227 | 34.282 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.7 | 37.5 | 26.3 | G45T2 | 1 2 3 4 | 4 11.5 11 11
L/50-1 | SGBM15 | Dec 12 2015 5:00PM | Dec 12 2015 9:15PM | Dec 14 2015 10:10PM | Dec 15 2015 1:18AM | 51.98 | 51.075 | 52.91 | 0.00 | 15.508 | 89.380 | 35.567 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.8 | 37.0 | 6.2 | G45T2 | 1 2 3 4 | 10 9 11 7
R/19-5 | SGBM03 | Dec 14 2015 8:00AM | Dec 14 2015 3:05PM | Dec 14 2015 7:08PM | Dec 14 2015 8:58PM | 55.87 | 48.925 | 56.64 | 0.00 | 26.639 | 29.231 | 22.286 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 10 5
Q/19a-2 | SGBM20 | Dec 12 2015 7:05PM | Dec 14 2015 11:25AM | Dec 14 2015 4:40PM | Dec 14 2015 5:53PM | 54.404 | 49.775 | 55.21 | 0.00 | 27.708 | 26.696 | 22.067 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 10 5
X10/Y3-1 | SGBM18 | Dec 12 2015 12:00PM | Dec 14 2015 10:35AM | Dec 14 2015 1:39PM | Dec 14 2015 5:41PM | 55.376 | 55.075 | 56.07 | 0.00 | 22.873 | 32.503 | 32.202 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 37.0 | 29.1 | G35T2 | 1 2 3 4 5 6 | 7 7 7 8 7 1
W/59-1 | SGBM17 | Dec 15 2015 8:40AM | Dec 13 2015 8:30PM | Dec 13 2015 6:28AM | Dec 13 2015 9:00AM | 49.641 | 47.375 | 50.52 | 0.00 | 18.619 | 31.043 | 28.756 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.9 | 31.0 | 24.5 | G45T2 | PJ3081 PJ3082 PJ3083 PJ3084 | 8 8 8 7
W/59-2 | SGBM17 | Dec 12 2015 6:30PM | Dec 12 2015 11:59PM | Dec 13 2015 6:28AM | Dec 13 2015 8:55AM | 49.723 | 47.375 | 50.58 | 0.00 | 18.680 | 31.043 | 28.695 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.9 | 31.0 | 24.7 | G45T2 | PJ3081 PJ3082 PJ3083 PJ3084 | 8 8 8 7
Y/59-1 | SGBM17 | Dec 12 2015 8:30AM | Dec 12 2015 5:00PM | Dec 13 2015 2:23AM | Dec 13 2015 5:15AM | 49.611 | 47.275 | 50.38 | 0.00 | 14.784 | 34.827 | 32.491 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.1 | 35.0 | -100.0 | G45T2 | PJ3062 PJ3065 PJ3068 PJ3071 PJ3074 | 7 7 7 7 7
S/20-2 | SGBM20 | Dec 12 2015 1:45PM | Dec 12 2015 5:05PM | Dec 12 2015 9:11PM | Dec 13 2015 12:12AM | 54.452 | 47.375 | 55.21 | 0.00 | 23.712 | 30.334 | 23.663 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 6 6
W/54-2 | SGBM19 | Dec 11 2015 5:15PM | Dec 12 2015 12:00AM | Dec 12 2015 5:15AM | Dec 12 2015 8:00AM | 49.616 | 47.375 | 50.46 | 0.00 | 18.355 | 31.261 | 29.020 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.1 | 34.0 | -100.0 | G45T2 | PJ3008 PJ3009 PJ3010 PJ3011 PJ3012 | 8 9 8 7 2
X/59-1 | SGBM16 | Dec 11 2015 5:20PM | Dec 12 2015 12:15AM | Dec 12 2015 3:55AM | Dec 12 2015 7:00AM | 49.651 | 47.275 | 50.13 | 0.00 | 17.933 | 31.718 | 29.342 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.4 | 37.0 | -100.0 | G45T2 | C480013138 C480013139 C480013144 C480013152 | 10 10 10 7
X8/Y2-4 | SGBM01 | Dec 9 2015 7:30PM | Dec 10 2015 3:00PM | Dec 11 2015 1:54AM | Dec 12 2015 4:30AM | 55.503 | 52.875 | 46.99 35.99 | 0.00 0.00 | 16.694 | 38.809 | 36.181 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 8
R/26-1 | SGBM01 | Dec 11 2015 2:30PM | Dec 11 2015 9:00PM | Dec 12 2015 1:34AM | Dec 12 2015 3:21AM | 55.097 | 51.275 | 52.48 | 0.00 | 30.184 | 24.913 | 21.091 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 8 7
S/20-1 | SGBM20 | Dec 11 2015 4:30PM | Dec 11 2015 8:17PM | Dec 11 2015 11:02PM | Dec 12 2015 1:25AM | 5.452 | 47.375 | 55.22 | 0.00 | 5.452 | -18.268 | 41.923 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.3 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 4
Y/57-1 | SGBM17 | Dec 11 2015 9:10AM | Dec 11 2015 6:45PM | Dec 11 2015 11:00PM | Dec 12 2015 12:38AM | 49.45 | 47.375 | 50.31 | 0.00 | 17.206 | 32.244 | 30.169 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 34.0 | -100.0 | G45T2 | C480013105 C480013107 C480013113 | 11.5 11.5 11
J/44-9 | SGBM23 | Dec 10 2015 5:30PM | Dec 11 2015 6:45PM | Dec 11 2015 8:10PM | Dec 11 2015 11:30PM | 51.63 | 47.825 | 52.50 | 0.00 | 12.504 | 39.126 | 35.321 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 39.0 | 27.5 | G45T2 | 1 2 3 4 5 | 8 7 8 7 9
X5/Y2-4 | SGBM01 | Dec 2 2015 6:00PM | Dec 11 2015 12:48PM | Dec 11 2015 7:05PM | Dec 11 2015 9:12PM | 55.408 | 53.175 | 47.15 41.15 | 0.00 0.00 | 17.446 | 37.962 | 35.729 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 30.9 | 40.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 8 7 7 8
J/46-3 | SGBM23 | Dec 10 2015 4:17PM | Dec 11 2015 11:00AM | Dec 11 2015 4:30PM | Dec 11 2015 6:50PM | 51.57 | 49.375 | 52.50 | 0.00 | 14.003 | 37.567 | 35.372 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 37.0 | 20.8 | G45T2 | PJ2953 PJ2956 PJ2957 PJ2958 PJ2961 | 7 8 7 7 8
Q/19a-1 | SGBM20 | Dec 10 2015 3:20PM | Dec 11 2015 9:00AM | Dec 11 2015 4:04PM | Dec 11 2015 5:23PM | 55.908 | 49.775 | 47.72 32.72 | 0.00 0.00 | 27.621 | 28.287 | 22.154 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 29.0 | -100.0 | G45T2 | 1 2 3 | 8 9 12
Y/58-2 | SGBM17 | Dec 10 2015 8:10AM | Dec 10 2015 8:00PM | Dec 11 2015 1:29AM | Dec 11 2015 5:03AM | 49.673 | 47.375 | 50.43 | 0.00 | 15.527 | 34.146 | 31.848 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 33.0 | 8.8 | G45T2 | PJ2935 PJ2937 PJ2942 PJ2944 PJ2946 | 7 7 6 6 7
X/58-2 | SGBM17 | Dec 8 2015 4:00PM | Dec 10 2015 12:45PM | Dec 10 2015 11:41PM | Dec 11 2015 1:55AM | 49.58 | 47.375 | 49.98 | 0.00 | 18.679 | 30.901 | 28.696 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.9 | 32.0 | -100.0 | G45T2 | PJ2925 PJ2929 PJ2930 PJ2933 | 7 8 9 8
X/59-2 | SGBM17 | Dec 9 2015 6:00PM | Dec 10 2015 2:30PM | Dec 10 2015 7:41PM | Dec 10 2015 10:05PM | 49.754 | 47.275 | 50.59 | 0.00 | 17.589 | 32.165 | 29.686 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.7 | 32.0 | -100.0 | G45T2 | PJ2908 PJ2912 PJ2914 PJ2918 | 7 7 8 10
K/49-2 | SGBM23 | Dec 8 2015 8:10PM | Dec 10 2015 3:29PM | Dec 10 2015 6:05PM | Dec 10 2015 8:08PM | 51.86 | 49.675 | 43.67 | 0.00 | 15.670 | 36.190 | 34.005 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.4 | 37.0 | -100.0 | G45T2 | PJ2899 PJ2900 PJ2902 PJ2904 PJ2907 | 7 8 7 8 7
R/15-2 | SGBM20 | Dec 9 2015 3:00PM | Dec 10 2015 1:33PM | Dec 10 2015 2:57PM | Dec 10 2015 6:00PM | 55.805 | 52.775 | 47.32 | 0.00 | 26.323 | 29.482 | 26.452 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.9 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
P/15-1 | SGBM20 | Dec 9 2015 4:50PM | Dec 10 2015 9:13AM | Dec 10 2015 11:03AM | Dec 10 2015 2:32PM | 55.653 | 52.925 | 47.30 31.30 | 0.00 0.00 | 24.798 | 30.855 | 28.127 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 29.0 | 19.1 | G45T2 | 1 2 3 4 | 7 7 7 8
G/47-1 | SGBM23 | Dec 8 2015 8:40PM | Dec 9 2015 10:50PM | Dec 10 2015 12:27AM | Dec 10 2015 3:00AM | 51.493 | 49.675 | 43.35 28.35 | 0.00 0.00 | 10.250 | 41.243 | 39.425 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.1 | 45.0 | 31.8 | G45T2 | PJ2853 PJ2854 PJ2856 PJ2859 PJ2858 PJ2861 PJ2862 | 7 9 3 9 7 7 3
G/48-1 | SGBM23 | Dec 8 2015 8:55PM | Dec 9 2015 12:45PM | Dec 9 2015 8:14PM | Dec 9 2015 11:50PM | 51.216 | 49.675 | 52.10 | 0.00 | 10.303 | 40.913 | 39.372 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.1 | 40.0 | 17.3 | G45T2 | 1 2 3 4 | 10 10 10 10
X/52-2 | SGBM19 | Dec 7 2015 11:00AM | Dec 9 2015 11:30AM | Dec 9 2015 5:14PM | Dec 9 2015 7:57PM | 49.475 | 47.715 | 50.28 | 0.00 | 18.084 | 31.391 | 29.631 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.7 | 32.0 | -100.0 | G45T2 | PJ2816 PJ2817 PJ2818 PJ2822 PJ2827 | 7 7 6 6 6
Y/53-3 | SGBM17 | Dec 7 2015 5:30PM | Dec 9 2015 11:00AM | Dec 9 2015 1:30PM | Dec 9 2015 3:55PM | 49.543 | 47.475 | 50.44 | 0.00 | 17.139 | 32.404 | 30.336 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 33.0 | -100.0 | G45T2 | PJ2801 PJ2802 PJ2804 PJ2805 PJ2807 | 7 7 7 6 6
J/44-4 | SGBM23 | Dec 7 2015 10:26AM | Dec 8 2015 7:40PM | Dec 8 2015 10:31PM | Dec 8 2015 11:35PM | 51.596 | 47.825 | 42.54 32.54 | 0.00 0.00 | 32.545 | 39.551 | 15.280 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 13.2 | 37.0 | 22.6 | G45T2 | PJ2783 PJ2786 PJ2786 PJ2787 | 12 7 8 10
R/19-8 | SGBM20 | Dec 8 2015 12:00PM | Dec 8 2015 6:00PM | Dec 8 2015 7:20PM | Dec 8 2015 8:55PM | 55.728 | 48.925 | 47.50 | 0.00 | 26.904 | 28.824 | 22.021 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 24.0 | 4.9 | G45T2 | 1 2 3 | 7 9 8
J/44-19 | SGBM23 | Dec 7 2015 10:01AM | Dec 8 2015 1:00PM | Dec 8 2015 4:00PM | Dec 8 2015 6:10PM | 51.436 | 47.825 | 43.44 | 0.00 | 12.236 | 39.200 | 35.589 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.8 | 36.0 | 16.8 | G45T2 | PJ2756 PJ2757 PJ2759 PJ2761 PJ2762 | 8 7 7 7 7
J/43-6 | SGBM23 | Dec 7 2015 9:41AM | Dec 7 2015 11:10PM | Dec 8 2015 1:55AM | Dec 8 2015 3:32AM | 51.86 | 48.425 | 43.82 32.82 | 0.00 0.00 | 15.522 | 36.338 | 32.903 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.5 | 36.0 | 7.5 | G45T2 | 1 2 3 4 | 6 10 10 10
Pa/18-1 | SGBM20 | Dec 5 2015 8:00AM | Dec 7 2015 10:38AM | Dec 7 2015 11:10PM | Dec 8 2015 1:40AM | 55.813 | 55.075 | 47.60 | 0.00 | 33.997 | 21.816 | 21.078 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 21.0 | -100.0 | G35T2 | 1 2 3 | 5 7 9
W/52-2 | SGBM17 | Dec 5 2015 6:00PM | Dec 7 2015 3:36PM | Dec 7 2015 10:21PM | Dec 8 2015 12:25AM | 49.339 | 47.025 | 50.09 | 0.00 | 18.493 | 30.846 | 28.532 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 33.0 | -100.0 | G45T2 | C480012814 C480012815 C480012820 | 11 11 11
J/43-2 | SGBM23 | Dec 7 2015 9:13AM | Dec 7 2015 2:59PM | Dec 7 2015 5:50PM | Dec 7 2015 9:10PM | 51.817 | 48.425 | 43.80 | 0.00 | 16.100 | 35.717 | 32.325 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 33.0 | 5.0 | G45T2 | PJ2712 PJ2714 PJ2717 PJ2720 PJ2723 | 7 7 7 6 6
P/15-2 | SGBM20 | Dec 5 2015 5:45PM | Dec 7 2015 11:43AM | Dec 7 2015 2:22PM | Dec 7 2015 6:25PM | 55.61 | 52.925 | 47.39 | 0.00 | 24.594 | 31.016 | 28.331 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 7 5
X8/Y2-2 | SGBM01 | Dec 4 2015 2:30PM | Dec 7 2015 12:50PM | Dec 7 2015 2:55PM | Dec 7 2015 5:35PM | 55.442 | 52.875 | 47.19 | 0.00 | 16.395 | 39.047 | 36.480 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.6 | 39.0 | -100.0 | G45T2 | 1 2 3 4 4 5 | 7 7 7 6 6 6
Z/46-1 | SGBM17 | Dec 4 2015 7:00PM | Dec 5 2015 7:32PM | Dec 7 2015 1:20PM | Dec 7 2015 3:05PM | 49.455 | 48.625 | 50.29 | 0.00 | 18.590 | 30.865 | 30.035 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 30.0 | -100.0 | G45T2 | PJ2694 PJ2695 PJ2696 PJ2697 | 8 7 8 7
X/53-1 | SGBM19 | Dec 2 2015 1:20PM | Dec 5 2015 6:15PM | Dec 6 2015 12:02AM | Dec 6 2015 2:50AM | 49.18 | 47.475 | 50.00 | 0.00 | 17.000 | 32.180 | 30.475 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.4 | 35.0 | -26.4 | G45T2 | PJ2674 PJ2676 PJ2678 PJ2682 | 7 8 7 13
J/44-14 | SGBM15 | Dec 4 2015 9:22PM | Dec 5 2015 9:25PM | Dec 5 2015 10:27PM | Dec 6 2015 12:35AM | 51.666 | 47.825 | 43.64 | 0.00 | 12.537 | 39.129 | 35.288 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 39.0 | -30.6 | G45T2 | PJ2667 PJ2668 PJ2760 PJ2671 PJ2672 | 7 9 8 8 7
H/47-2 | SGBM15 | Dec 4 2015 8:08PM | Dec 5 2015 12:10PM | Dec 5 2015 6:48PM | Dec 5 2015 8:58PM | 51.321 | 49.675 | 43.38 | 0.00 | 14.478 | 36.843 | 35.197 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.5 | 36.0 | -100.0 | G45T2 | C480012727 C480012728 C480012730 C480012732 | 6 10 10 10
R/15-1 | SGBM20 | Dec 4 2015 4:05PM | Dec 5 2015 12:30PM | Dec 5 2015 4:41PM | Dec 5 2015 6:07PM | 55.79 | 52.775 | 47.64 | 0.00 | 26.542 | 29.248 | 26.233 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.7 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 6 7 7 6
R/19-6 | SGBM03 | Dec 4 2015 4:45PM | Dec 5 2015 11:30AM | Dec 5 2015 2:07PM | Dec 5 2015 4:00PM | 55.821 | 48.925 | 47.44 | 0.00 | 26.138 | 29.683 | 22.787 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.7 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 6
X7/Y2-3 | SGBM05 | Dec 4 2015 3:10PM | Dec 4 2015 9:20PM | Dec 5 2015 12:40AM | Dec 5 2015 3:20AM | 55.329 | 53.475 | 47.05 | 0.00 | 16.352 | 38.977 | 37.123 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 | 12 8 6 6 6
G/48-2 | SGBM15 | Dec 3 2015 5:35PM | Dec 4 2015 7:59PM | Dec 4 2015 10:35PM | Dec 5 2015 1:25AM | 51.303 | 49.675 | 43.31 | 0.00 | 11.308 | 39.995 | 38.367 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.2 | 42.0 | -100.0 | G45T2 | PJ2607 PJ2611 PJ2612 PJ2615 PJ2617 PJ2619 | 7 7 7 7 7 7
J/16-1 | SGBM20 | Dec 4 2015 4:30PM | Dec 4 2015 8:00PM | Dec 4 2015 9:15PM | Dec 5 2015 12:10AM | 55.64 | 51.375 | 56.64 | 0.00 | 19.738 | 35.902 | 31.637 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 41.0 | -100.0 | G35T2 | 1 2 3 4 5 6 | 7 7 9 7 7 4
G/47-2 | SGBM15 | Dec 3 2015 5:56PM | Dec 4 2015 3:51PM | Dec 4 2015 7:48PM | Dec 4 2015 8:45PM | 51.5 | 49.675 | 43.41 21.41 | 0.00 0.00 | 10.210 | 41.290 | 39.465 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.2 | 40.0 | 5.8 | G45T2 | 1 2 3 4 | 10 10 10 10
M/50-1 | SGBM02 | Dec 3 2015 7:49PM | Dec 4 2015 3:30PM | Dec 4 2015 6:41PM | Dec 4 2015 8:40PM | 51.9 | 51.175 | 43.69 32.69 22.69 | 0.00 0.00 0.00 | 14.585 | 37.315 | 36.590 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.7 | 38.0 | -100.0 | G45T2 | PJ2593 PJ2594 PJ2598 PJ2599 PJ2601 | 9 7 7 8 7
X7/Y4-2 | SGBM05 | Dec 3 2015 3:29PM | Dec 4 2015 11:00AM | Dec 4 2015 3:09PM | Dec 4 2015 5:35PM | 55.466 | 53.475 | 47.37 28.37 | 0.00 0.00 | 22.468 | 32.998 | 31.007 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 6 6 5
R/19-9 | SGBM03 | Dec 3 2015 8:00AM | Dec 3 2015 5:48PM | Dec 4 2015 2:55PM | Dec 4 2015 4:40PM | 55.737 | 48.925 | 47.43 | 0.00 | 26.827 | 85.337 | 22.098 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 24.0 | -19.1 | G45T2 | 1 2 3 | 8 8 8
R/19-2 | SGBM20 | Dec 3 2015 3:15PM | Dec 3 2015 9:18PM | Dec 4 2015 11:16AM | Dec 4 2015 12:50PM | 56.013 | 48.925 | 47.57 | 0.00 | 26.369 | 29.644 | 22.556 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 23.0 | -19.5 | G45T2 | 1 2 3 | 7 8 8
L/51-1 | SGBM02 | Dec 2 2015 3:46PM | Dec 3 2015 7:28PM | Dec 4 2015 3:39AM | Dec 4 2015 5:30AM | 51.945 | 51.075 | 43.92 | 0.00 | 14.921 | 37.024 | 36.154 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 7 7 7
W/55-1 | SGBM17 | Dec 3 2015 2:10PM | Dec 3 2015 11:41PM | Dec 4 2015 2:17AM | Dec 4 2015 4:25AM | 49.634 | 47.375 | 41.26 | 0.00 | 17.961 | 31.673 | 29.414 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 32.0 | -25.5 | G45T2 | PJ2567 PJ2568 PJ2570 PJ2571 | 8 8 8 8
P/16-2 | SGBM03 | Dec 2 2015 7:05PM | Dec 3 2015 5:49PM | Dec 3 2015 9:54PM | Dec 3 2015 11:37PM | 55.652 | 52.925 | -9.00 | 0.00 | -29.600 | 85.252 | 82.525 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 71.5 | 28.0 | -71.5 | G45T2 | 1 2 3 | 7 12 9
H/38-2 | SGBM23 | Dec 2 2015 8:16PM | Dec 3 2015 11:38AM | Dec 3 2015 9:28PM | Dec 3 2015 10:50PM | 52.014 | 49.675 | 43.01 | 0.00 | 22.605 | 29.409 | 27.070 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 31.0 | -100.0 | G45T2 | 1 2 3 | 11 10 10
Q/15-2 | SGBM21 | Dec 2 2015 6:10PM | Dec 3 2015 3:00PM | Dec 3 2015 5:55PM | Dec 3 2015 8:24PM | 55.762 | 52.925 | 47.55 43.55 | 0.00 0.00 | 25.852 | 29.910 | 27.073 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 30.0 | -23.4 | G45T2 | 1 2 3 4 | 7 8 8 7
J/43-7 | SGBM23 | Dec 1 2015 1:40PM | Dec 2 2015 8:40PM | Dec 3 2015 3:36PM | Dec 3 2015 6:15PM | 51.861 | 48.425 | 43.73 | 0.00 | 16.130 | 35.731 | 32.295 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 3 7 8 6
X8/Y4-1 | SGBM05 | Dec 1 2015 6:40PM | Dec 3 2015 10:41AM | Dec 3 2015 1:34PM | Dec 3 2015 4:56PM | 55.574 | 52.875 | -9.00 -26.00 | 0.00 0.00 | -34.400 | 89.974 | 87.275 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 75.6 | 33.0 | -75.6 | G45T2 | 1 2 3 4 5 | 8 7 7 6 5
M/51-1 | SGBM02 | Dec 2 2015 3:10PM | Dec 3 2015 1:15PM | Dec 3 2015 3:08PM | Dec 3 2015 4:45PM | 51.81 | 51.375 | 43.72 20.72 18.72 | 0.00 0.00 0.00 | 15.116 | 36.694 | 36.259 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.4 | 40.0 | 8.6 | G45T2 | 1 2 3 4 5 | 8 9 8 8 7
J/43-3 | SGBM23 | Dec 1 2015 2:14PM | Dec 2 2015 3:37PM | Dec 3 2015 2:05PM | Dec 3 2015 4:10PM | 51.79 | 48.425 | 43.75 | 0.00 | 14.946 | 36.844 | 33.479 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.0 | 33.0 | 4.0 | G45T2 | 1 2 3 4 5 6 | 6 6 6 6 4 5
R/19-4 | SGBM20 | Dec 1 2015 8:00AM | Dec 2 2015 4:13PM | Dec 3 2015 10:56AM | Dec 3 2015 11:46AM | 55.95 | 48.925 | -9.00 | 0.00 | -30.000 | 85.950 | 78.925 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 68.4 | 24.0 | -68.3 | G45T2 | 1 2 3 4 | 6 6 6 6
X9/Y3-4 | SGBM03 | Dec 1 2015 7:45PM | Dec 2 2015 4:47PM | Dec 3 2015 1:59AM | Dec 3 2015 4:19AM | 55.262 | 50.075 | 47.01 35.01 | 0.00 0.00 | 17.005 | 94.262 | 33.070 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
X8/Y2-3 | SGBM05 | Dec 1 2015 6:00PM | Dec 2 2015 4:47PM | Dec 2 2015 9:15PM | Dec 3 2015 1:50AM | 55.586 | 52.875 | 47.32 40.32 | 0.00 0.00 | 16.819 | 95.086 | 36.056 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.2 | 40.0 | -100.0 | G45T2 | 2 2 3 4 5 | 7 7 12 7 7
S/24-1 | SGBM21 | Dec 1 2015 7:30PM | Dec 2 2015 12:05PM | Dec 2 2015 8:25PM | Dec 2 2015 10:57PM | 49.9 | 48.625 | 41.46 | 0.00 | 27.264 | 73.100 | 21.361 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.5 | 24.0 | -18.5 | G45T2 | 1 2 3 | 7 7 10
G/49-2 | SGBM15 | Nov 30 2015 10:35AM | Dec 2 2015 1:55PM | Dec 2 2015 9:08PM | Dec 2 2015 10:45PM | 51.68 | 49.675 | 43.60 22.60 | 0.00 0.00 | 12.295 | 39.385 | 37.380 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.4 | 42.0 | 9.6 | G45T2 | 1 2 3 4 5 | 9 7 9 8 9
X6/Y3-8 | SGBM18 | Nov 26 2015 1:20PM | Dec 2 2015 1:43PM | Dec 2 2015 6:53PM | Dec 2 2015 10:18PM | 55.545 | 52.475 | 47.26 22.26 | 0.00 0.00 | 19.262 | 92.545 | 33.213 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 36.0 | 25.2 | G45T2 | 1 2 3 4 5 | 7 7 7 7 8
H/49-2 | SGBM15 | Nov 30 2015 11:05AM | Dec 1 2015 8:05PM | Dec 2 2015 7:46PM | Dec 2 2015 8:51PM | 51.788 | 49.675 | 43.80 | 0.00 | 14.697 | 37.091 | 34.978 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.3 | 39.0 | 28.8 | G45T2 | 1 2 3 4 5 | 7 11 7 7 7
X/52-1 | SGBM19 | Dec 1 2015 11:30AM | Dec 2 2015 11:10AM | Dec 2 2015 4:22PM | Dec 2 2015 8:25PM | 49.132 | 47.175 | 41.16 20.36 | 0.00 0.00 | 17.658 | 31.474 | 29.517 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.6 | 34.0 | -26.0 | G45T2 | PJ2456 PJ2459 PJ2461 PJ2463 PJ2469 | 8 8 7 7 4
J/38-2 | SGBM23 | Nov 30 2015 2:45PM | Dec 1 2015 11:00AM | Dec 1 2015 10:41PM | Dec 1 2015 11:30PM | 52.015 | 49.675 | 44.00 | 0.00 | 24.300 | 80.715 | 25.375 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.0 | 28.0 | 27.4 | G45T2 | 1 2 3 | 8 10 10
J/49-2 | SGBM15 | Nov 30 2015 12:40PM | Dec 1 2015 3:59PM | Dec 1 2015 8:53PM | Dec 1 2015 11:20PM | 51.78 | 49.675 | 43.73 | 0.00 | 15.433 | 36.347 | 34.242 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.7 | 37.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 4
X7/Y2-2 | SGBM05 | Nov 30 2015 8:00AM | Dec 1 2015 4:17PM | Dec 1 2015 7:23PM | Dec 1 2015 10:30PM | 55.314 | 53.475 | 46.82 | 0.00 | 16.417 | 38.897 | 37.058 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 6 4
N/16-2 | SGBM20 | Nov 30 2015 6:03PM | Dec 1 2015 5:28PM | Dec 1 2015 7:10PM | Dec 1 2015 9:05PM | 55.811 | 52.925 | 47.62 36.62 | 0.00 0.00 | 25.720 | 30.091 | 27.205 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.6 | 30.0 | -23.6 | G45T2 | 1 2 3 | 10 10 10
R/24-1 | SGBM21 | Nov 29 2015 11:00AM | Nov 30 2015 9:05PM | Dec 1 2015 2:10PM | Dec 1 2015 3:23PM | 50.387 | 49.075 | 42.37 | 0.00 | 26.868 | 23.519 | 22.207 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | -19.2 | G45T2 | 1 2 | 11 11
S/16-1 | SGBM20 | Nov 30 2015 2:15PM | Dec 1 2015 9:18AM | Dec 1 2015 12:43PM | Dec 1 2015 2:29PM | 55.883 | 53.275 | 47.62 31.32 | 0.00 0.00 | 28.923 | 26.960 | 24.352 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.1 | 27.0 | -21.1 | G45T2 | 1 2 3 | 5 11 11
H/38-1 | SGBM23 | Nov 30 2015 1:47PM | Nov 30 2015 4:55PM | Dec 1 2015 12:22AM | Dec 1 2015 3:30AM | 52.02 | 49.675 | 44.01 | 0.00 | 21.015 | 31.005 | 28.660 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.8 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 6 6 6
Y/52-2 | SGBM17 | Nov 28 2015 8:12AM | Nov 30 2015 5:24PM | Dec 1 2015 12:42AM | Dec 1 2015 3:10AM | 49.321 | 47.475 | 41.44 | 0.00 | 17.337 | 31.984 | 30.138 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 32.0 | 22.6 | G45T2 | PJ2402 PJ2405 PJ2407 PJ2411 PJ2413 | 7 7 6 6 6
X6/Y2-3 | SGBM05 | Nov 29 2015 2:00PM | Nov 30 2015 8:30PM | Nov 30 2015 10:32PM | Dec 1 2015 3:00AM | 55.48 | 53.475 | 47.10 | 0.00 | 16.297 | 39.183 | 37.178 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 43.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 7 8 8 7 5
R/19-10 | SGBM20 | Nov 29 2015 11:28AM | Nov 30 2015 1:10PM | Nov 30 2015 5:20PM | Nov 30 2015 6:43PM | 55.777 | 48.925 | 47.69 37.69 | 0.00 0.00 | 26.691 | 29.086 | 22.234 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 6 6 6
X8/Y4-3 | SGBM05 | Nov 25 2015 4:15PM | Nov 30 2015 1:17PM | Nov 30 2015 3:33PM | Nov 30 2015 5:22PM | 55.505 | 52.875 | 47.28 | 0.00 | 21.775 | 33.730 | 31.100 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 33.0 | -26.9 | G45T2 | 1 2 3 4 5 | 7 7 7 6 6
K/38-2 | SGBM23 | Nov 30 2015 1:35PM | Nov 30 2015 7:40PM | Nov 30 2015 1:48AM | Nov 30 2015 4:00AM | 51.95 | 49.675 | 43.90 | 0.00 | 20.904 | 31.046 | 28.771 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.9 | 30.0 | 5.1 | G45T2 | 1 2 3 4 | 8 8 7 7
X9/Y3-2 | SGBM05 | Nov 27 2015 2:45PM | Nov 28 2015 7:00PM | Nov 29 2015 12:04PM | Nov 29 2015 1:35PM | 55.3 | 50.075 | 46.86 | 0.00 | 16.762 | 38.538 | 33.313 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 5
Y/53-2 | SGBM17 | Nov 27 2015 2:30PM | Nov 28 2015 2:25PM | Nov 28 2015 9:32PM | Nov 29 2015 12:21AM | 49.292 | 47.475 | 41.06 35.56 28.46 | 0.00 3.70 0.00 | 17.262 | 32.030 | 30.213 |  | 3.7 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.2 | 32.0 | -100.0 | G45T2 | PJ2319 PJ2322 PJ2326 PJ2329 PJ2332 | 7 7 6 6 6
Q/16-2 | SGBM03 | Nov 27 2015 5:20PM | Nov 28 2015 4:30PM | Nov 28 2015 9:06PM | Nov 28 2015 10:43PM | 55.709 | 52.925 | 47.63 | 0.00 | 27.731 | 27.978 | 25.194 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 26.0 | -21.8 | G45T2 | 1 2 3 4 | 7 7 6 6
G/38-2 | SGBM23 | Nov 27 2015 5:05PM | Nov 28 2015 11:42AM | Nov 28 2015 8:11PM | Nov 28 2015 10:37PM | 52.01 | 49.675 | -9.00 | 0.00 | -31.000 | 83.010 | 80.675 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 69.9 | 32.0 | -69.9 | G45T2 | 1 2 3 4 5 | 7 7 6 6 6
La/56-1 | SGBM02 | Nov 27 2015 7:30PM | Nov 28 2015 12:28PM | Nov 28 2015 6:34PM | Nov 28 2015 9:36PM | 52.78 | 51.375 | 44.58 37.58 27.58 | 0.00 0.00 0.00 | 16.080 | 37.500 | 35.295 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.6 | 37.0 | 6.4 | G45T2 | 1 2 3 4 5 | 7 8 7 8 7
R/16-2 | SGBM03 | Nov 27 2015 4:40PM | Nov 28 2015 11:00AM | Nov 28 2015 5:19PM | Nov 28 2015 6:58PM | 55.768 | 53.375 | 47.57 | 0.00 | 29.169 | 26.599 | 24.206 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 25.0 | -21.0 | G45T2 | 1 2 3 4 | 7 6 6 6
X9/Y4-2 | SGBM05 | Nov 25 2015 4:55PM | Nov 28 2015 10:36AM | Nov 28 2015 1:46PM | Nov 28 2015 5:34PM | 55.529 | 53.375 | 47.37 29.37 | 0.00 0.00 | 22.069 | 33.460 | 31.306 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 34.0 | -27.1 | G45T2 | 1 2 3 | 11.5 11.5 11
R/19-1 | SGBM03 | Nov 27 2015 5:55PM | Nov 27 2015 9:38PM | Nov 28 2015 1:33PM | Nov 28 2015 4:09PM | 56.01 | 48.925 | 47.55 | 0.00 | 26.648 | 29.362 | 22.277 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 23.0 | 3.7 | G45T2 | 1 2 3 4 | 6 6 6 5
G/39-2 | SGBM23 | Nov 27 2015 12:00PM | Nov 27 2015 4:45PM | Nov 28 2015 12:57AM | Nov 28 2015 3:00AM | 52.04 | 49.675 | 52.90 | 0.00 | 20.501 | 31.539 | 29.174 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 34.0 | 34.6 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
La/57-1 | SGBM02 | Nov 26 2015 1:00PM | Nov 27 2015 3:40PM | Nov 27 2015 8:40PM | Nov 27 2015 11:55PM | 51.8 | 51.375 | 43.66 19.66 | 0.00 0.00 | 14.859 | 37.800 | 36.516 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.6 | 40.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 7 8 7 7 3
H/49-1 | SGBM15 | Nov 26 2015 10:00AM | Nov 27 2015 4:46PM | Nov 27 2015 8:10PM | Nov 27 2015 11:30PM | 51.747 | 49.675 | 43.49 | 0.00 | 14.492 | 38.000 | 35.183 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.5 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 7 7 8
J/43-4 | SGBM23 | Nov 20 2015 4:50PM | Nov 21 2015 5:07PM | Nov 27 2015 5:36PM | Nov 27 2015 7:49PM | 51.845 | 48.425 | 43.59 36.99 22.99 | 0.00 0.00 0.00 | 15.593 | 88.845 | 32.832 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.4 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
X5/Y2-3 | SGBM18 | Nov 26 2015 11:40AM | Nov 27 2015 10:00AM | Nov 27 2015 3:59PM | Nov 27 2015 6:17PM | 55.48 | 53.175 | 47.00 21.00 | 0.00 0.00 | 16.902 | 39.100 | 36.273 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.4 | 40.0 | -31.4 | G45T2 | 1 2 3 4 | 10 10 10 10
G/49-1 | SGBM15 | Nov 26 2015 9:20AM | Nov 26 2015 6:41PM | Nov 27 2015 3:07PM | Nov 27 2015 5:00PM | 51.632 | 49.675 | 43.57 | 0.00 | 11.572 | 40.060 | 38.103 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.0 | 40.0 | 21.2 | G45T2 | 1 2 3 4 5 6 | 7 7 6 6 7 7
K/38-1 | SGBM23 | Nov 25 2015 8:05PM | Nov 26 2015 3:28PM | Nov 26 2015 11:25PM | Nov 27 2015 2:10AM | 51.911 | 49.675 | 43.72 | 0.00 | 25.621 | 26.290 | 24.054 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
La/58-1 | SGBM02 | Nov 24 2015 8:00PM | Nov 25 2015 9:00PM | Nov 26 2015 8:39PM | Nov 27 2015 12:55AM | 53.066 | 51.375 | 44.96 | 0.00 | 15.959 | 37.107 | 35.416 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.7 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 2 7 7 7 7 6
S/16-2 | SGBM20 | Nov 26 2015 9:30AM | Nov 26 2015 5:45PM | Nov 26 2015 10:43PM | Nov 27 2015 12:45AM | 55.88 | 53.275 | 47.56 | 0.00 | 29.256 | 26.624 | 24.019 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 6 6 6
J/38-1 | SGBM23 | Nov 25 2015 8:25PM | Nov 26 2015 12:00PM | Nov 26 2015 9:06PM | Nov 26 2015 10:35PM | 51.97 | 49.675 | 43.62 | 0.00 | 24.620 | 27.350 | 25.055 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.7 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
J/49-1 | SGBM15 | Nov 25 2015 3:27PM | Nov 25 2015 8:17PM | Nov 26 2015 7:12PM | Nov 26 2015 9:15PM | 51.808 | 49.675 | 43.77 | 0.00 | 15.170 | 36.638 | 34.505 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.9 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 8 7 7
La/59-1 | SGBM02 | Nov 24 2015 8:40PM | Nov 26 2015 1:30PM | Nov 26 2015 6:58PM | Nov 26 2015 9:15PM | 53.104 | 51.375 | 44.78 | 0.00 | 15.777 | 37.327 | 35.598 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.8 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 8 6
X6/Y3-4 | SGBM20 | Nov 24 2015 12:14PM | Nov 25 2015 3:13PM | Nov 26 2015 5:05PM | Nov 26 2015 7:16PM | 55.53 | 52.475 | 47.28 39.98 | 0.00 0.00 | 19.583 | 35.947 | 32.892 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.5 | 37.0 | -28.5 | G35T2 | 1 2 3 4 | 11 10 10 6
X9/Y3-6 | SGBM05 | Nov 24 2015 6:15PM | Nov 25 2015 3:00PM | Nov 26 2015 12:45PM | Nov 26 2015 4:48PM | 55.365 | 50.075 | 47.11 | 0.00 | 17.009 | 38.356 | 33.066 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 35.0 | -100.0 | G35T2 | 1 2 3 4 | 10 10 10 5
X/52-3 | SGBM17 | Nov 25 2015 2:15PM | Nov 26 2015 10:40AM | Nov 26 2015 11:55AM | Nov 26 2015 2:10PM | 49.304 | 47.715 | 41.25 37.95 33.95 | 0.00 2.00 15.90 | 18.051 | 31.253 | 29.664 |  | 17.9 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.7 | 30.0 | 4.3 | G45T2 | PJ2175 PJ2176 PJ2177 PJ2178 | 8 7 8 7
X8/Y3-3 | SGBM05 | Nov 24 2015 4:10PM | Nov 25 2015 1:10PM | Nov 25 2015 11:30PM | Nov 26 2015 2:36AM | 55.464 | 53.175 | 47.10 39.81 | 0.00 0.00 | 20.105 | 35.359 | 33.070 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 7
H/24-3 | SGBM15 | Aug 24 2015 3:00PM | Aug 25 2015 11:00AM | Aug 25 2015 9:13PM | Nov 25 2015 11:05PM | 52.165 | 49.775 | 43.94 | 0.00 | 25.935 | 26.230 | 23.840 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 26.0 | -20.6 | G45T2 | 1 2 3 | 11 8 7
G/38-1 | SGBM23 | Nov 24 2015 6:24PM | Nov 25 2015 3:50PM | Nov 25 2015 9:25PM | Nov 25 2015 11:00PM | 52.082 | 49.675 | 43.94 | 0.00 | 21.945 | 30.137 | 27.730 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.0 | 30.0 | -100.0 | G35T2 | 1 2 3 4 | 7 8 8 7
N/16-1 | SGBM20 | Nov 24 2015 6:00PM | Nov 25 2015 11:47AM | Nov 25 2015 8:30PM | Nov 25 2015 10:29PM | 55.841 | 52.925 | 47.66 | 0.00 | 25.461 | 30.380 | 27.464 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.8 | 25.0 | -23.8 | G45T2 | 1 2 3 4 | 6 8 6 5
G/39-1 | SGBM23 | Nov 24 2015 6:48PM | Nov 25 2015 12:55PM | Nov 25 2015 4:58PM | Nov 25 2015 7:53PM | 51.983 | 49.675 | 43.90 | 0.00 | 19.602 | 85.283 | 30.073 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 33.0 | 7.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 6
X6/Y2-2 | SGBM18 | Nov 24 2015 2:00PM | Nov 25 2015 11:05AM | Nov 25 2015 2:53PM | Nov 25 2015 6:25PM | 55.617 | 53.475 | 47.39 22.69 17.39 | 0.00 0.00 0.00 | 16.391 | 39.226 | 37.084 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 38.0 | -32.1 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 7 3
J/41-1 | SGBM23 | Nov 24 2015 5:58PM | Nov 25 2015 10:00AM | Nov 25 2015 1:50PM | Nov 25 2015 5:00PM | 51.808 | 49.775 | 43.69 32.69 | 0.00 0.00 | 16.491 | 35.317 | 33.284 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 32.0 | -28.8 | G45T2 | 1 2 3 4 5 | 7 7 6.5 5.5 6
AA/55-1 | SGBM17 | Nov 24 2015 5:22PM | Nov 25 2015 12:14PM | Nov 25 2015 1:35PM | Nov 25 2015 4:50PM | 49.509 | 49.075 | 41.43 30.73 | 0.00 0.00 | 16.932 | 33.477 | 32.143 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.8 | 36.0 | 7.4 | G35T2 | 2098 2099 2100 2103 2106 2114 | 7 7 6 7 6 3
X6/Y3-6 | SGBM18 | Nov 23 2015 6:25PM | Nov 24 2015 7:12PM | Nov 24 2015 10:14PM | Nov 25 2015 12:51AM | 55.541 | 52.475 | 47.40 | 0.00 | 18.500 | 37.041 | 33.975 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 29.4 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
P/16-1 | SGBM20 | Nov 24 2015 10:48AM | Nov 24 2015 4:35PM | Nov 24 2015 8:49PM | Nov 24 2015 10:50PM | 55.696 | 52.925 | 47.48 | 0.00 | 26.477 | 29.219 | 26.448 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.9 | 26.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 6 6
X8/Y4-4 | SGBM20 | Nov 23 2015 3:45PM | Nov 24 2015 2:28PM | Nov 24 2015 7:40PM | Nov 24 2015 9:06PM | 55.711 | 52.875 | 47.53 | 0.00 | 21.535 | 34.176 | 31.340 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 37.0 | 9.8 | G45T2 | 1 2 3 4 5 | 7 7 8 7 8
F/44-1 | SGBM23 | Nov 23 2015 4:00PM | Nov 24 2015 11:42AM | Nov 24 2015 5:05PM | Nov 24 2015 7:00PM | 51.872 | 51.375 | 43.57 | 0.00 | 15.070 | 36.802 | 36.305 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.4 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 7 7 7
Q/16-1 | SGBM20 | Nov 19 2015 6:20PM | Nov 24 2015 9:00AM | Nov 24 2015 4:42PM | Nov 24 2015 6:32PM | 55.797 | 52.925 | 47.60 31.60 | 0.00 0.00 | 27.404 | 28.393 | 25.521 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.1 | 25.0 | -22.1 | G35T2 | 1 2 3 4 | 7 7 7 4
X7/Y4-1 | SGBM18 | Nov 23 2015 5:15PM | Nov 24 2015 10:30AM | Nov 24 2015 4:27PM | Nov 24 2015 6:27PM | 55.697 | 53.475 | 47.35 36.15 | 0.00 0.00 | 22.345 | 33.352 | 31.130 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.0 | 37.0 | -26.9 | G45T2 | 1 2 3 4 5 | 7 8 7 8 7
Y/52-3 | SGBM17 | Nov 23 2015 9:30AM | Nov 24 2015 8:13AM | Nov 24 2015 3:22PM | Nov 24 2015 6:10PM | 49.401 | 47.475 | 50.29 | 0.00 | 17.389 | 32.012 | 30.086 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 30.0 | -100.0 | G35T2 | 1 2 3 4 | 8 7 8 7
X9/Y3-5 | SGBM05 | Nov 23 2015 4:20PM | Nov 23 2015 9:40PM | Nov 24 2015 11:50AM | Nov 24 2015 1:25PM | 55.412 | 50.075 | 47.01 | 0.00 | 24.605 | 30.807 | 25.470 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 22.1 | 35.0 | -100.0 | G35T2 | 1 2 3 4 5 | 7 7 7 7 7
X7/Y2-1 | SGBM05 | Nov 21 2015 8:00PM | Nov 23 2015 5:00PM | Nov 23 2015 9:27PM | Nov 23 2015 11:20PM | 55.472 | 53.475 | 47.21 35.21 | 0.00 0.00 | 16.411 | 39.061 | 37.064 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 39.0 | -32.1 | G45T2 | 1 2 3 4 5 6 | 5 7 7 7 6 7
X6/Y3-7 | SGBM18 | Nov 22 2015 9:00AM | Nov 23 2015 3:17PM | Nov 23 2015 6:34PM | Nov 23 2015 8:57PM | 55.504 | 52.475 | 47.21 | 0.00 | 19.206 | 36.298 | 33.269 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 36.0 | -28.8 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 6 2
H/41-3 | SGBM23 | Nov 22 2015 1:30PM | Nov 23 2015 11:46AM | Nov 23 2015 5:14PM | Nov 23 2015 7:00PM | 51.9 | 49.775 | 43.65 | 0.00 | 19.550 | 32.350 | 30.225 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.2 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 6 6 6
X9/Y6a-1 | SGBM20 | Nov 22 2015 5:15PM | Nov 23 2015 3:40PM | Nov 23 2015 3:52PM | Nov 23 2015 4:41PM | 55.075 | 55.075 | 47.29 | 0.00 | 26.595 | 28.480 | 28.480 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 29.0 | 4.3 | G35T2 | 1 2 3 4 | 7 7 7 8
J/43-5 | SGBM23 | Nov 20 2015 5:45PM | Nov 22 2015 1:05PM | Nov 23 2015 2:08PM | Nov 23 2015 3:45PM | 51.312 | 48.425 | 43.69 | 0.00 | 16.191 | 35.121 | 32.234 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.9 | 34.0 | 21.8 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
Q/15-1 | SGBM20 | Nov 20 2015 6:29PM | Nov 23 2015 11:42AM | Nov 23 2015 1:35PM | Nov 23 2015 3:38PM | 55 | 52.925 | 46.77 37.77 | 0.00 0.00 | 24.668 | 31.100 | 28.257 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 26.0 | -24.5 | G45T2 | 1 2 3 4 | 7 7 6 6
J/43-1 | SGBM23 | Nov 20 2015 4:22PM | Nov 21 2015 7:44PM | Nov 23 2015 12:15PM | Nov 23 2015 1:25PM | 51.694 | 48.425 | 44.46 | 0.00 | 16.261 | 35.433 | 32.164 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - |  | - | 27.9 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
X6/Y3-3 | SGBM05 | Nov 20 2015 7:15PM | Nov 22 2015 10:10AM | Nov 22 2015 11:05AM | Nov 22 2015 1:37PM | 55.66 | 52.475 | 47.51 38.71 22.81 | 0.00 0.00 0.00 | 19.308 | 36.352 | 33.167 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.7 | 38.0 | -100.0 | G35T2 | 1 2 3 4 5 6 | 8 7 7 7 7 2
Z/41-1 | SGBM17 | Nov 20 2015 3:00PM | Nov 22 2015 8:30AM | Nov 22 2015 9:58AM | Nov 22 2015 11:40AM | 49.492 | 48.525 | 50.30 | 0.00 | 18.198 | 31.294 | 30.327 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 32.0 | -100.0 | G35T2 | 1 2 3 4 5 | 8 8 7 7 2
R/16-1 | SGBM20 | Nov 19 2015 6:20PM | Nov 21 2015 2:55PM | Nov 21 2015 10:37PM | Nov 22 2015 12:20AM | 55.797 | 53.375 | 47.45 | 0.00 | 26.848 | 28.949 | 26.527 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.0 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 6 6
X8/Y3-2 | SGBM18 | Nov 20 2015 11:15AM | Nov 21 2015 2:18PM | Nov 21 2015 8:35PM | Nov 22 2015 12:10AM | 55.61 | 53.175 | 47.25 | 0.00 | 20.053 | 35.557 | 33.122 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.7 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 9 8 8 10
J/43-8 | SGBM15 | Nov 20 2015 7:18PM | Nov 21 2015 11:10AM | Nov 21 2015 3:53PM | Nov 21 2015 5:30PM | 51.685 | 48.425 | 43.62 37.62 | 0.00 0.00 | 15.817 | 35.868 | 32.608 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.2 | 36.0 | 7.8 | G45T2 | PJ1923 PJ1924 PJ1925 PJ1926 PJ1927 | 7 7 7 7 8
X6/Y3-10 | SGBM20 | Nov 20 2015 2:30PM | Nov 20 2015 8:47PM | Nov 21 2015 10:17AM | Nov 21 2015 11:45AM | 55.584 | 52.475 | 47.41 | 0.00 | 19.411 | 36.173 | 33.064 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
X9/Y3-1 | SGBM05 | Nov 18 2015 9:00AM | Nov 20 2015 7:00PM | Nov 20 2015 9:14PM | Nov 20 2015 11:35PM | 55.497 | 50.075 | 47.40 29.40 21.40 | 0.00 0.00 0.00 | 16.996 | 38.501 | 33.079 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 34.0 | -28.6 | G45T2 | 1 2 3 | 11 11 12
X7/Y4-3 | SGBM20 | Nov 20 2015 8:00AM | Nov 20 2015 1:45PM | Nov 20 2015 6:24PM | Nov 20 2015 10:20PM | 55.74 | 53.475 | 47.60 | 0.00 | 22.400 | 33.340 | 31.075 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 6 6 7 2
H/41-2 | SGBM23 | Nov 19 2015 11:30AM | Nov 19 2015 4:56PM | Nov 20 2015 4:03PM | Nov 20 2015 6:20PM | 51.821 | 49.775 | 43.78 | 0.00 | 19.085 | 85.521 | 30.690 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.6 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 7 6 6
X6/Y3-1 | SGBM03 | Nov 19 2015 10:00AM | Nov 19 2015 3:35PM | Nov 19 2015 8:00PM | Nov 19 2015 11:50PM | 55.683 | 52.475 | 47.47 | 0.00 | 19.466 | 36.217 | 33.009 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.6 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
J/41-2 | SGBM23 | Nov 19 2015 11:00AM | Nov 19 2015 2:10PM | Nov 19 2015 7:27PM | Nov 19 2015 9:55PM | 51.875 | 49.775 | 43.64 | 0.00 | 19.840 | 32.800 | 29.935 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.9 | 32.0 | -100.0 | G45T2 | 1 2 3 | 11 10 11
N/21-1 | SGBM21 | Nov 18 2015 6:50PM | Nov 19 2015 5:10PM | Nov 19 2015 7:03PM | Nov 19 2015 9:00PM | 53.412 | 52.775 | 45.15 | 0.00 | 27.645 | 25.767 | 25.130 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 6
X9/Y3-3 | SGBM05 | Nov 23 2015 4:20PM | Nov 23 2015 9:33PM | Nov 19 2015 5:27PM | Nov 19 2015 8:05PM | 55.412 | 50.075 | 47.01 | 0.00 | 16.605 | 38.517 | 33.470 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 29.0 | 34.0 | -29.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
X/52-4 | SGBM17 | Nov 18 2015 9:40AM | Nov 18 2015 9:30PM | Nov 19 2015 6:06AM | Nov 19 2015 8:30AM | 49.279 | 47.715 | 40.94 | 0.00 | 18.397 | 30.882 | 29.318 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.4 | 38.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 8 7 8 4 4
J/42-7 | SGBM23 | Nov 17 2015 11:00AM | Nov 18 2015 6:40PM | Nov 18 2015 10:56PM | Nov 19 2015 1:55AM | 51.891 | 50.375 | 43.85 | 0.00 | 20.349 | 31.542 | 30.026 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 6
X8/Y2-1 | SGBM03 | Nov 18 2015 2:00PM | Nov 18 2015 8:40PM | Nov 18 2015 10:12PM | Nov 19 2015 1:20AM | 55.58 | 52.875 | 56.39 | 0.00 | 16.388 | 39.192 | 36.487 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.6 | 38.0 | -31.6 | G45T2 | 1 2 3 4 5 | 7 8 7 8 8
AA/54-1 | SGBM17 | Nov 17 2015 4:30PM | Nov 18 2015 12:25PM | Nov 18 2015 9:43PM | Nov 19 2015 12:18AM | 49.308 | 49.075 | 41.08 29.08 | 0.00 0.00 | 15.776 | 33.532 | 33.299 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.8 | 33.0 | -28.8 | G45T2 | PJ1778 PJ1781 PJ1784 PJ1787 PJ1790 | 7 7 7 6 6
J/42-3 | SGBM23 | Nov 17 2015 10:26AM | Nov 18 2015 3:45PM | Nov 18 2015 8:52PM | Nov 18 2015 11:20PM | 51.865 | 50.375 | 43.84 | 0.00 | 19.136 | 32.729 | 31.239 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 6 6
AA/53-1 | SGBM19 | Nov 16 2015 5:20PM | Nov 18 2015 4:44PM | Nov 18 2015 7:13PM | Nov 18 2015 9:15PM | 49.242 | 49.075 | 41.12 38.12 | 0.00 0.00 | 16.799 | 32.443 | 32.276 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 28.0 | 33.0 | 5.0 | G35T2 | 1 2 3 4 5 | 7 7 7 7 5
Qa/18-1 | SGBM20 | Nov 18 2015 1:00PM | Nov 18 2015 4:00PM | Nov 18 2015 6:07PM | Nov 18 2015 7:40PM | 55.805 | 55.075 | 56.65 | 0.00 | 32.447 | 23.358 | 22.628 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 22.0 | -100.0 | G35T2 | 1 2 3 | 7 8 7
J/42-2 | SGBM23 | Nov 17 2015 12:00PM | Nov 17 2015 7:20PM | Nov 18 2015 2:21PM | Nov 18 2015 4:55PM | 52.05 | 50.375 | 43.92 | 0.00 | 20.425 | 32.500 | 29.950 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.9 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 7 3
Q/23-1 | SGBM05 | Nov 17 2015 8:30PM | Nov 18 2015 11:50AM | Nov 18 2015 3:07PM | Nov 18 2015 4:40PM | 53.454 | 52.775 | 45.10 | 0.00 | 29.802 | 23.652 | 22.973 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.9 | 23.0 | -100.0 | G45T2 | 1 2 3 | 8 8 7
X5/Y2-1 | SGBM03 | Nov 17 2015 2:00PM | Nov 17 2015 9:47PM | Nov 17 2015 11:03PM | Nov 18 2015 1:00AM | 55.714 | 53.175 | 56.17 | 0.00 | 16.775 | 38.939 | 36.400 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.5 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 8 8 7
X/53-3 | SGBM17 | Nov 17 2015 8:30AM | Nov 17 2015 3:10PM | Nov 17 2015 7:35PM | Nov 17 2015 10:45PM | 49.461 | 47.475 | 41.18 | 0.00 | 17.980 | 31.481 | 29.495 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 36.0 | -100.0 | G45T2 | PJ1712 PJ1714 PJ1715 PJ1716 PJ1722 | 8 8 8 8 4
J/42-6 | SGBM23 | Nov 17 2015 11:18AM | Nov 17 2015 3:10PM | Nov 17 2015 6:20PM | Nov 17 2015 8:40PM | 51.98 | 50.375 | 43.83 | 0.00 | 20.325 | 31.655 | 30.050 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 7 7 6 6
X6/Y3-2 | SGBM03 | Nov 14 2015 11:41AM | Nov 16 2015 11:00AM | Nov 17 2015 11:29AM | Nov 17 2015 1:20PM | 55.695 | 52.475 | 47.82 30.52 | 0.00 0.00 | 19.116 | 36.579 | 33.359 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.9 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
Y/53-1 | SGBM17 | Nov 16 2015 8:10AM | Nov 16 2015 2:48PM | Nov 17 2015 1:39AM | Nov 17 2015 3:30AM | 49.412 | 47.475 | 50.21 | 0.00 | 17.412 | 32.000 | 30.063 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 6 8 8 8
X9/Y4-1 | SGBM21 | Nov 13 2015 7:00PM | Nov 16 2015 1:20PM | Nov 16 2015 9:59PM | Nov 16 2015 11:41PM | 55.725 | 53.375 | 47.19 39.19 | 0.00 0.00 | 22.294 | 33.431 | 31.081 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
X6/Y2-1 | SGBM03 | Nov 15 2015 10:00AM | Nov 16 2015 4:00PM | Nov 16 2015 6:16PM | Nov 16 2015 9:00PM | 55.58 | 53.475 | 56.38 | 0.00 | 15.979 | 39.601 | 37.496 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 32.5 | 39.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 7 4
N/22-1 | SGBM05 | Nov 15 2015 10:30AM | Nov 16 2015 1:20PM | Nov 16 2015 7:22PM | Nov 16 2015 8:57PM | 53.367 | 52.775 | 44.99 | 0.00 | 27.289 | 26.078 | 25.486 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.1 | 25.0 | -22.1 | G45T2 | 1 2 3 4 | 7 6 6 6
Q/25-1 | SGBM21 | Nov 16 2015 8:00AM | Nov 16 2015 11:10AM | Nov 16 2015 2:09PM | Nov 16 2015 3:50PM | 52.468 | 51.275 | 54.23 | 0.00 | 30.029 | 22.439 | 21.246 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.4 | 22.0 | -100.0 | G45T2 | 1 2 3 | 7 8 7
J/41-3 | SGBM23 | Nov 15 2015 2:00PM | Nov 16 2015 10:40AM | Nov 16 2015 12:35PM | Nov 16 2015 2:20PM | 51.885 | 49.775 | 44.81 | 0.00 | 20.109 | 31.776 | 29.666 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.7 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 6 7 7 6
J/42-4 | SGBM15 | Nov 14 2015 12:10PM | Nov 14 2015 4:00PM | Nov 14 2015 11:55PM | Nov 15 2015 4:20AM | 51.906 | 50.375 | 52.90 | 0.00 | 20.200 | 31.706 | 30.175 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 2 7 7 7 6 5
X6/Y3-5 | SGBM03 | Nov 14 2015 10:00AM | Nov 14 2015 7:13PM | Nov 14 2015 11:10PM | Nov 15 2015 2:00AM | 55.664 | 52.475 | 47.51 30.51 | 0.00 0.00 | 19.515 | -16.664 | 32.960 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.5 | 37.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 8 8 5
E/51-1 | SGBM23 | Nov 13 2015 8:00PM | Nov 14 2015 2:17PM | Nov 14 2015 8:05PM | Nov 14 2015 11:55PM | 52.05 | 51.275 | 43.46 | 0.00 | 6.960 | 45.500 | 44.315 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.4 | 45.5 | -100.0 | G45T2 | 1 2 3 4 5 | 4 11 11.5 10 9
J/42-5 | SGBM15 | Nov 13 2015 9:20AM | Nov 14 2015 12:00PM | Nov 14 2015 6:12PM | Nov 14 2015 8:35PM | 51.92 | 50.375 | 52.80 | 0.00 | 20.098 | 31.822 | 30.277 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.2 | 30.0 | -100.0 | G45T2 | 1 2 3 | 11 11 8
J/42-8 | SGBM15 | Nov 14 2015 11:00AM | Nov 14 2015 2:45PM | Nov 14 2015 6:50PM | Nov 14 2015 8:35PM | 51.811 | 50.375 | 52.83 | 0.00 | 19.932 | 31.879 | 30.443 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.4 | 30.0 | -100.0 | G45T2 | 1 2 3 4 | 3 11 9 7
R/19-7 | SGBM05 | Nov 13 2015 7:16PM | Nov 14 2015 4:00PM | Nov 14 2015 6:58PM | Nov 14 2015 8:23PM | 55.802 | 48.925 | 47.40 | 0.00 | 26.202 | 30.200 | 22.723 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.7 | 28.0 | 8.3 | G45T2 | 1 2 3 4 | 7 8 8 5
J/42-1 | SGBM15 | Nov 13 2015 8:50PM | Nov 14 2015 8:33AM | Nov 14 2015 4:43PM | Nov 14 2015 6:25PM | 51.94 | 50.375 | 52.83 | 0.00 | 19.832 | 32.108 | 30.543 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.5 | 29.0 | -100.0 | G45T2 | 1 2 3 | 11 9 9
X8/Y4-2 | SGBM03 | Nov 12 2015 5:00PM | Nov 13 2015 9:20PM | Nov 14 2015 3:10PM | Nov 14 2015 4:30PM | 55.877 | 52.875 | 47.71 | 0.00 | 21.911 | 33.966 | 30.964 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.8 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 8
G/21-1 | SGBM20 | Nov 13 2015 3:15PM | Nov 13 2015 10:00PM | Nov 14 2015 12:37PM | Nov 14 2015 2:20PM | 52.54 | 50.475 | 43.26 | 0.00 | 23.863 | 28.400 | 26.612 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.0 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 5
Pa/21-1 | SGBM05 | Nov 12 2015 3:30PM | Nov 13 2015 11:35AM | Nov 13 2015 5:45PM | Nov 13 2015 8:25PM | 53.8 | 52.375 | 45.71 | 0.00 | 28.105 | 25.695 | 24.270 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 8 8 8
K/51-1 | SGBM15 | Nov 12 2015 11:20AM | Nov 12 2015 8:04PM | Nov 13 2015 3:03PM | Nov 13 2015 5:24PM | 52.041 | 51.275 | 44.04 | 0.00 | 15.143 | 36.898 | 36.132 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 42.0 | -31.3 | G45T2 | pj1532 pj1533 pj1534 pj1535 pj1536 pj1542 | 8 8 8 7 7 4
X6/Y3-9 | SGBM03 | Nov 11 2015 6:58PM | Nov 12 2015 12:20PM | Nov 12 2015 9:10PM | Nov 13 2015 12:00AM | 55.535 | 52.475 | 47.34 | 0.00 | 19.543 | 35.992 | 32.932 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 28.5 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
G/21-2 | SGBM05 | Nov 6 2015 5:45PM | Nov 12 2015 1:40PM | Nov 12 2015 9:30PM | Nov 12 2015 11:20PM | 52.391 | 50.475 | 44.56 | 0.00 | 24.758 | 27.633 | 25.717 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.3 | 26.0 | -22.3 | G45T2 | 1 2 3 4 | 7 7 7 5
X/53-2 | SGBM17 | Nov 12 2015 9:36AM | Nov 12 2015 5:20PM | Nov 12 2015 6:46PM | Nov 12 2015 9:00PM | 31.435 | 47.475 | 41.20 | 0.00 | 18.762 | 12.673 | 28.713 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.9 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 6
P/23-1 | SGBM05 | Nov 9 2015 2:00PM | Nov 9 2015 9:05PM | Nov 11 2015 4:56PM | Nov 11 2015 6:35PM | 53.428 | 52.475 | 44.43 | 0.00 | 27.428 | 26.000 | 25.047 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.7 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 6
X6/Y6-3 | SGBM03 | Nov 7 2015 8:40PM | Nov 9 2015 3:05PM | Nov 11 2015 11:43AM | Nov 11 2015 2:10PM | 55.618 | 53.475 | 47.43 | 0.00 | 25.830 | 30.600 | 27.645 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.9 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 4 7
X9/Y6-2 | SGBM03 | Nov 6 2015 4:46PM | Nov 7 2015 1:45PM | Nov 7 2015 9:30PM | Nov 8 2015 12:45AM | 55.722 | 53.375 | 47.47 | 0.00 | 24.170 | 31.552 | 29.205 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 5 2
M/35-1 | SGBM20 | Nov 7 2015 9:45AM | Nov 7 2015 1:26PM | Nov 7 2015 4:56PM | Nov 7 2015 7:25PM | 51.982 | 51.075 | 43.64 | 0.00 | 26.440 | 25.542 | 24.635 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.3 | 27.0 | -21.3 | G45T2 | 1 2 3 4 5 | 6 6 6 6 3
X8/Y6-2 | SGBM03 | Nov 6 2015 6:00PM | Nov 7 2015 9:35AM | Nov 7 2015 11:56AM | Nov 7 2015 1:40PM | 55.766 | 52.925 | 47.63 33.63 | 0.00 0.00 | 24.928 | 30.838 | 27.997 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.2 | 30.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 2
F/63a-1 | SGBM17 | Nov 5 2015 7:35PM | Nov 6 2015 5:35PM | Nov 6 2015 7:43PM | Nov 6 2015 10:10PM | 51.858 | 51.275 | 43.70 36.70 33.70 | 0.00 0.00 0.00 | 9.098 | 42.760 | 42.177 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 50.0 | -100.0 | G45T2 | 1 2 3 4 5 6 7 | 7 7 7 9 6 7 7
D/51-1 | SGBM23 | Nov 4 2015 4:00PM | Nov 5 2015 7:47PM | Nov 6 2015 3:55PM | Nov 6 2015 5:49PM | 51.874 | 51.275 | 43.72 | 0.00 | 6.920 | 44.954 | 44.355 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.4 | 48.0 | -38.4 | G45T2 | C480011430 C480011431 C170013372 C480011434 C520123166 | 10 10 8 10 10
X6/Y6-2 | SGBM03 | Nov 5 2015 1:00PM | Nov 6 2015 10:30AM | Nov 6 2015 11:17AM | Nov 6 2015 1:00PM | 55.706 | 53.475 | 47.51 43.51 | 0.00 0.00 | 26.006 | 30.500 | 27.469 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.8 | 29.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 8
V/42-2 | SGBM02 | Nov 5 2015 3:35PM | Nov 5 2015 8:03PM | Nov 6 2015 3:20AM | Nov 6 2015 6:40AM | 49.467 | 47.275 | 50.26 | 0.00 | 15.457 | 34.010 | 31.818 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.6 | 46.0 | -100.0 | G45T2 | 1 2 3 4 5 6 7 | 7 6 7 7 7 6 6
X9/Y6-1 | SGBM03 | Nov 5 2015 3:30PM | Nov 5 2015 8:17PM | Nov 5 2015 8:57PM | Nov 5 2015 11:10PM | 55.796 | 53.375 | 47.59 | 0.00 | 24.186 | 31.610 | 29.189 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 6 6 7 6
J/27-2a | SGBM20 | Nov 5 2015 9:55AM | Nov 5 2015 2:17PM | Nov 5 2015 4:56PM | Nov 5 2015 7:05PM | 52.31 | 48.825 | 53.06 | 0.00 | 17.163 | 35.147 | 31.662 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.4 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 5
D/49-1 | SGBM23 | Nov 4 2015 3:20PM | Nov 5 2015 2:00PM | Nov 5 2015 4:54PM | Nov 5 2015 6:25PM | 51.72 | 51.275 | 43.30 | 0.00 | 6.803 | 44.917 | 44.472 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.5 | 52.0 | -38.5 | G45T2 | C480011375 C170013361 C480011377 C480011378 C170013362 | 11 9 11 11 10
H/41-1 | SGBM23 | Nov 4 2015 4:50PM | Nov 4 2015 8:45PM | Nov 5 2015 11:17AM | Nov 5 2015 1:05PM | 51.98 | 49.775 | 43.81 | 0.00 | 19.012 | 32.968 | 30.763 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.6 | 33.5 | -100.0 | G45T2 | C480011354 C480011355 C480011359 | 11 11 11.5
M/20-1 | SGBM05 | Nov 4 2015 9:15AM | Nov 5 2015 8:42AM | Nov 5 2015 10:56AM | Nov 5 2015 12:30PM | 54.747 | 52.775 | 46.57 31.67 | 0.00 0.00 | 29.567 | 25.180 | 23.208 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 24.0 | -20.1 | G45T2 | 1 2 3 4 | 6 6 6 6
V/44-2 | SGBM02 | Nov 4 2015 9:00AM | Nov 4 2015 7:35PM | Nov 5 2015 2:53AM | Nov 5 2015 5:15AM | 49.309 | 47.275 | 41.28 | 0.00 | 17.679 | 31.630 | 29.596 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.6 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 8 7 8 6
X8/Y6-1 | SGBM21 | Oct 31 2015 4:38PM | Nov 2 2015 5:32PM | Nov 3 2015 8:52PM | Nov 3 2015 11:59PM | 55.78 | 52.925 | 47.81 | 0.00 | 24.808 | 32.000 | 28.117 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 4 1
V/42-1 | SGBM02 | Nov 2 2015 2:00PM | Nov 3 2015 9:20AM | Nov 3 2015 7:26PM | Nov 3 2015 10:10PM | 49.433 | 47.275 | 41.32 19.32 | 0.00 0.00 | 19.269 | 30.164 | 28.006 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 40.0 | -100.0 | G45T2 | 2 2 3 4 5 5 | 7 7 7 7 4 8
X6/Y6-1 | SGBM03 | Oct 31 2015 3:59PM | Nov 3 2015 9:35AM | Nov 3 2015 7:47PM | Nov 3 2015 10:00PM | 55.702 | 53.475 | 47.72 33.32 | 0.00 0.00 | 25.724 | 29.978 | 27.751 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.0 | 30.0 | -100.0 | G45T2 | 1 2 3 | 9 10 11
G/63a-1 | SGBM17 | Nov 2 2015 12:50PM | Nov 3 2015 2:50PM | Nov 3 2015 5:47PM | Nov 3 2015 8:10PM | 51.96 | 51.275 | 43.69 | 0.00 | 8.787 | 43.173 | 42.488 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.8 | 44.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 9 7 7 7 7 7
V/44-1 | SGBM02 | Nov 2 2015 8:00AM | Nov 2 2015 1:17PM | Nov 3 2015 1:40AM | Nov 3 2015 5:10AM | 49.447 | 47.275 | 50.31 | 0.00 | 18.208 | 31.239 | 29.067 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 29.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 6 6 6 7 2 2
V/35-2 | SGBM19 | Nov 2 2015 9:20AM | Nov 2 2015 4:20PM | Nov 2 2015 11:32PM | Nov 3 2015 1:20AM | 49.601 | 47.075 | 41.35 | 0.00 | 22.749 | 26.852 | 24.326 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.1 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
K/20-1 | SGBM05 | Oct 31 2015 8:30AM | Oct 31 2015 9:00PM | Nov 2 2015 2:20PM | Nov 2 2015 4:23PM | 53.463 | 51.075 | 45.12 | 0.00 | 29.620 | 24.500 | 21.455 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G45T2 | 1 2 3 | 8 7 7
J/19-1 | SGBM05 | Oct 28 2015 9:00PM | Oct 30 2015 5:10PM | Oct 30 2015 11:06PM | Nov 1 2015 12:30AM | 53.477 | 52.775 | 47.02 43.02 34.02 | 0.00 0.00 0.00 | 26.322 | 27.155 | 26.453 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.9 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 6 7 4 6
V/37-1 | SGBM19 | Oct 31 2015 8:30AM | Oct 31 2015 3:27PM | Oct 31 2015 8:40PM | Nov 1 2015 12:12AM | 49.615 | 47.075 | 41.47 | 0.00 | 20.072 | 29.543 | 27.003 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 39.0 | -23.4 | G45T2 | C480011141 C48001142 C480011144 C480011147 | 11 11 11 6
L/19-1 | SGBM05 | Oct 31 2015 10:20AM | Oct 31 2015 3:22PM | Oct 31 2015 10:30PM | Nov 1 2015 12:10AM | 53.709 | 52.775 | 45.40 | 0.00 | 30.403 | 24.000 | 22.372 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 2
AB/37-1 | SGBM02 | Oct 31 2015 8:11AM | Oct 31 2015 3:50PM | Oct 31 2015 8:05PM | Oct 31 2015 10:05PM | 49.586 | 49.075 | 41.57 | 0.00 | 22.571 | 27.015 | 26.504 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.0 | 30.0 | -22.9 | G35T2 | PJ1032 PJ1034 PJ1036 PJ1038 PJ1039 | 7 7 6 5 5
V/41-2 | SGBM08 | Oct 31 2015 8:16AM | Oct 31 2015 3:45PM | Oct 31 2015 6:39PM | Oct 31 2015 8:30PM | 49.522 | 47.275 | 41.47 | 0.00 | 17.668 | 31.854 | 29.607 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.6 | 30.0 | -100.0 | G45T2 | PJ1025 PJ1027 PJ1030 PJ1031 | 7 9 7 7
X4b/Y5-1 | SGBM21 | Oct 30 2015 5:46PM | Oct 31 2015 2:07PM | Oct 31 2015 5:14PM | Oct 31 2015 6:40PM | 55.666 | 47.975 | 47.30 | 0.00 | 35.796 | 19.870 | 12.179 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 10.5 | 11.0 | -100.0 | G45T2 | 1 2 | 5.5 5.5
M/31-1 | SGBM20 | Oct 31 2015 9:30AM | Oct 31 2015 2:03PM | Oct 31 2015 4:03PM | Oct 31 2015 5:16PM | 52.024 | 51.075 | 43.95 | 0.00 | 29.753 | 23.200 | 21.322 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.5 | 17.0 | -100.0 | G45T2 | 1 2 3 | 6 6 5
V/38-2 | SGBM02 | Oct 30 2015 3:50PM | Oct 30 2015 9:10PM | Oct 31 2015 12:17AM | Oct 31 2015 3:00AM | 49.372 | 47.075 | 50.56 | 0.00 | 18.060 | 31.312 | 29.015 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.1 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 7 8 7 3
U/31-1 | SGBM03 | Oct 30 2015 4:20PM | Oct 30 2015 7:00PM | Oct 30 2015 9:47PM | Oct 31 2015 12:10AM | 51.975 | 51.375 | 52.66 | 0.00 | 29.363 | 22.612 | 22.012 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 25.0 | -19.1 | G45T2 | 1 2 3 4 | 5 6 7 7
V/43-2 | SGBM02 | Oct 30 2015 9:10AM | Oct 30 2015 3:19PM | Oct 30 2015 7:18PM | Oct 30 2015 10:40PM | 49.401 | 47.275 | 50.24 | 0.00 | 17.245 | 32.156 | 30.030 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 4 7 7 7 7 4
X4/Y5-1 | SGBM21 | Oct 29 2015 8:00AM | Oct 30 2015 5:35PM | Oct 30 2015 6:26PM | Oct 30 2015 8:50PM | 55.814 | 54.725 | 47.48 30.48 | 0.00 0.00 | 25.477 | 30.337 | 29.248 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 31.0 | -25.3 | G45T2 | 1 2 3 4 | 10 9 9 3
M/29-1 | SGBM20 | Oct 30 2015 9:58AM | Oct 30 2015 1:33PM | Oct 30 2015 5:16PM | Oct 30 2015 7:10PM | 52.658 | 51.075 | 44.55 | 0.00 | 26.251 | 26.407 | 24.824 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.5 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 6 6
V/40-1 | SGBM19 | Oct 29 2015 2:20PM | Oct 29 2015 8:11PM | Oct 30 2015 12:40AM | Oct 30 2015 4:10AM | 49.438 | 49.075 | 50.39 | 0.00 | 17.789 | 31.649 | 31.286 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
U/32-1 | SGBM03 | Oct 29 2015 5:30PM | Oct 29 2015 10:00PM | Oct 30 2015 1:57AM | Oct 30 2015 3:50AM | 52.091 | 51.375 | 52.89 | 0.00 | 29.187 | 22.904 | 22.188 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 25.0 | -19.2 | G45T2 | 1 2 3 4 | 6 7 6 6
G/62-1 | SGBM15 | Oct 29 2015 2:00PM | Oct 29 2015 7:15PM | Oct 29 2015 11:09PM | Oct 30 2015 1:20AM | 51.733 | 51.275 | 52.66 | 0.00 | 6.259 | 45.474 | 45.016 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 10 11.5 11.5
V/37-2 | SGBM02 | Oct 29 2015 10:20AM | Oct 29 2015 3:15PM | Oct 29 2015 6:15PM | Oct 29 2015 9:40PM | 49.619 | 47.075 | 50.47 | 0.00 | 20.072 | 29.547 | 27.003 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 4
J/62-1 | SGBM15 | Oct 29 2015 10:20AM | Oct 29 2015 3:20PM | Oct 29 2015 5:19PM | Oct 29 2015 8:20PM | 51.99 | 51.375 | 52.85 | 0.00 | 8.250 | 43.740 | 43.125 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 41.5 | -100.0 | G45T2 | 1 2 3 4 | 11.5 10 10 10
Z/43-2 | SGBM19 | Oct 29 2015 9:05AM | Oct 29 2015 2:35PM | Oct 29 2015 4:55PM | Oct 29 2015 7:45PM | 49.578 | 46.925 | 50.49 | 0.00 | 18.895 | 30.683 | 28.030 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 31.5 | -100.0 | G45T2 | 1 2 3 4 | 9.5 9 8 5
M/34-1 | SGBM21 | Oct 29 2015 9:00AM | Oct 29 2015 1:00PM | Oct 29 2015 4:55PM | Oct 29 2015 6:25PM | 51.954 | 51.075 | 43.69 | 0.00 | 26.685 | 26.000 | 24.390 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.1 | 25.0 | -21.1 | G45T2 | 1 2 3 4 | 6 7 6 6
H/20-1 | SGBM20 | Oct 28 2015 6:13PM | Oct 29 2015 1:54PM | Oct 29 2015 3:14PM | Oct 29 2015 5:15PM | 53.085 | 50.975 | 44.47 | 0.00 | 24.875 | 28.600 | 26.100 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.6 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 6 6 7
M/25-1 | SGBM20 | Oct 28 2015 5:05PM | Oct 29 2015 9:30AM | Oct 29 2015 9:58AM | Oct 29 2015 11:45AM | 53.384 | 52.475 | 45.09 34.09 | 0.00 0.00 | 29.786 | 23.598 | 22.689 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 6 6 6
V/39-2 | SGBM02 | Oct 28 2015 10:50AM | Oct 28 2015 5:20PM | Oct 29 2015 2:00AM | Oct 29 2015 5:15AM | 49.497 | 47.075 | 50.27 | 0.00 | 17.074 | 32.423 | 30.001 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 5 5 3
H/30-1 | SGBM20 | Oct 28 2015 9:30AM | Oct 28 2015 4:45PM | Oct 28 2015 9:34PM | Oct 28 2015 11:54PM | 52.239 | 49.675 | 43.91 | 0.00 | 25.813 | 26.426 | 23.862 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 25.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 6 6 5 1
E/52-1 | SGBM23 | Oct 28 2015 9:10AM | Oct 28 2015 4:11PM | Oct 28 2015 7:40PM | Oct 28 2015 10:30PM | 51.95 | 51.275 | 52.72 | 0.00 | 6.922 | 45.028 | 44.353 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.4 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 7 10 10 11
V/35-1 | SGBM03 | Oct 28 2015 10:20AM | Oct 28 2015 3:40PM | Oct 28 2015 6:40PM | Oct 28 2015 9:00PM | 49.62 | 47.075 | 50.41 | 0.00 | 23.013 | 26.607 | 24.062 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 26.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 6 6 6 2
M/22-1 | SGBM05 | Oct 27 2015 4:20PM | Oct 28 2015 11:40AM | Oct 28 2015 3:01PM | Oct 28 2015 4:10PM | 53.786 | 52.775 | 45.63 | 0.00 | 27.429 | 26.357 | 25.346 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.9 | 26.0 | -21.9 | G45T2 | 1 2 3 4 | 7 7 6 6
V/36-2 | SGBM02 | Oct 27 2015 7:00PM | Oct 28 2015 8:10AM | Oct 28 2015 1:14PM | Oct 28 2015 4:00PM | 49.648 | 47.075 | 50.56 | 0.00 | 21.060 | 28.588 | 26.015 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.5 | 30.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 6 6 6 5
X4/Y4-1 | SGBM21 | Oct 26 2015 8:40AM | Oct 28 2015 12:00PM | Oct 28 2015 12:29PM | Oct 28 2015 2:20PM | 55.805 | 54.725 | 47.56 | 0.00 | 23.565 | 33.000 | 31.160 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.0 | 35.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 7
M/32-1 | SGBM19 | Oct 24 2015 6:20PM | Oct 26 2015 10:00PM | Oct 27 2015 10:39PM | Oct 28 2015 12:25AM | 52.021 | 51.075 | 43.70 | 0.00 | 27.000 | 25.700 | 24.075 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 6
M/33-1 | SGBM20 | Oct 26 2015 9:30PM | Oct 27 2015 9:03AM | Oct 27 2015 7:09PM | Oct 27 2015 9:20PM | 51.965 | 51.075 | 52.66 | 0.00 | 26.464 | 25.501 | 24.611 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.3 | 26.0 | -21.3 | G45T2 | 1 2 3 4 | 7 7 6 6
X/28-1a | SGBM03 | Oct 27 2015 8:00AM | Oct 27 2015 3:00PM | Oct 27 2015 6:23PM | Oct 27 2015 9:00PM | 48.73 | 47.375 | 49.55 | 0.00 | 23.650 | 25.080 | 23.725 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 4
V/43-1 | SGBM19 | Oct 27 2015 8:00AM | Oct 27 2015 1:05PM | Oct 27 2015 2:14PM | Oct 27 2015 5:12PM | 49.459 | 47.275 | 50.32 | 0.00 | 17.217 | 32.242 | 30.058 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 34.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 4 2
H/62-1 | SGBM15 | Oct 26 2015 6:20PM | Oct 27 2015 8:17AM | Oct 27 2015 11:50AM | Oct 27 2015 2:30PM | 51.89 | 51.375 | 52.81 | 0.00 | 7.212 | 44.678 | 44.163 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.2 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 10 10 5
W/30-1a | SGBM03 | Oct 26 2015 10:00AM | Oct 26 2015 6:15PM | Oct 26 2015 10:49PM | Oct 27 2015 1:50AM | 48.426 | 47.375 | 49.37 | 0.00 | 23.865 | 24.561 | 23.510 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 25.0 | 8.1 | G45T2 | 1 2 3 4 | 7 7 7 4
X4a/Y4a-1 | SGBM21 | Oct 26 2015 11:30AM | Oct 26 2015 5:36PM | Oct 26 2015 7:57PM | Oct 26 2015 10:00PM | 55.722 | 47.975 | 56.51 | 0.00 | 24.906 | 30.816 | 23.069 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
H/54-3 | SGBM17 | Oct 25 2015 6:50PM | Oct 26 2015 8:23AM | Oct 26 2015 4:44PM | Oct 26 2015 7:10PM | 51.85 | 49.775 | 52.78 | 0.00 | 9.282 | 42.568 | 40.493 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.1 | 43.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 10 10 10 7
H/20-2 | SGBM19 | Oct 26 2015 8:45AM | Oct 26 2015 3:15PM | Oct 26 2015 4:25PM | Oct 26 2015 6:10PM | 53.505 | 50.975 | 45.36 42.36 | 0.00 0.00 | 25.163 | 29.200 | 25.812 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.4 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
X/28-1b | SGBM03 | Oct 25 2015 7:20PM | Oct 26 2015 10:00AM | Oct 26 2015 12:45PM | Oct 26 2015 3:10PM | 48.612 | 47.375 | 49.51 | 0.00 | 23.907 | 24.705 | 23.468 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 4
D/57-3 | SGBM15 | Oct 25 2015 5:10PM | Oct 26 2015 8:23AM | Oct 26 2015 12:24PM | Oct 26 2015 3:00PM | 51.875 | 49.775 | 52.81 | 0.00 | 7.508 | 44.367 | 42.267 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.6 | 45.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11.5 11 11.5 6 5
M/24-1 | SGBM19 | Oct 24 2015 11:18AM | Oct 25 2015 11:50AM | Oct 26 2015 10:24AM | Oct 26 2015 12:50PM | 53.411 | 52.475 | 45.37 | 0.00 | 29.874 | 24.500 | 22.601 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 3
J/57-4 | SGBM17 | Oct 24 2015 11:00AM | Oct 24 2015 4:31PM | Oct 24 2015 8:34PM | Oct 24 2015 11:30PM | 51.966 | 48.775 | 52.87 | 0.00 | 8.174 | 43.792 | 40.601 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.2 | 45.0 | -100.0 | G45T2 | 1 2 3 4 5 | 5 10 11 11 8
M/21-1 | SGBM19 | Oct 24 2015 10:30AM | Oct 24 2015 6:00PM | Oct 24 2015 7:24PM | Oct 24 2015 9:05PM | 54.191 | 52.775 | 45.97 38.97 | 0.00 0.00 | 28.374 | 80.791 | 24.401 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.1 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 6 6
AA/33-1 | SGBM03 | Oct 24 2015 10:00AM | Oct 24 2015 2:20PM | Oct 24 2015 6:16PM | Oct 24 2015 8:29PM | 48.751 | 48.775 | 50.82 | 0.00 | 23.422 | 25.329 | 25.353 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.0 | 26.0 | -100.0 | G35T2 | 1 2 3 4 5 | 6 6 6 6 2
E/56-3 | SGBM17 | Oct 23 2015 10:00AM | Oct 24 2015 12:40PM | Oct 24 2015 5:28PM | Oct 24 2015 8:18PM | 51.927 | 49.775 | 44.62 26.62 | 0.00 0.00 | 7.615 | 44.312 | 42.160 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 46.0 | -36.5 | G45T2 | 1 2 3 4 5 | 2 11 11 11 11
L/52-1 | SGBM23 | Oct 24 2015 8:00AM | Oct 24 2015 12:55PM | Oct 24 2015 3:36PM | Oct 24 2015 6:20PM | 52.01 | 51.075 | 52.89 | 0.00 | 14.089 | 37.921 | 36.986 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.0 | 38.0 | -100.0 | G45T2 | 1 2 3 4 | 7 11 11 9
G/55-1 | SGBM17 | Oct 23 2015 6:45PM | Oct 24 2015 9:22AM | Oct 24 2015 1:10PM | Oct 24 2015 4:25PM | 51.782 | 49.675 | 52.60 | 0.00 | 7.605 | 44.177 | 42.070 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.4 | 44.0 | 20.8 | G45T2 | 1 2 3 4 5 6 | 3 9 9 9 10 4
J/29-2 | SGBM20 | Oct 23 2015 3:10PM | Oct 24 2015 9:00AM | Oct 24 2015 1:08PM | Oct 24 2015 4:10PM | 52.204 | 49.775 | 43.95 31.95 | 0.00 0.00 | 26.350 | 25.854 | 23.425 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 27.0 | -100.0 | G45T2 | 1 2 3 4 5 | 6 6 6 6 3
X5/Y5-1 | SGBM21 | Oct 23 2015 9:15PM | Oct 24 2015 11:02AM | Oct 24 2015 12:55PM | Oct 24 2015 2:30PM | 55.688 | 53.175 | 56.62 | 0.00 | 24.017 | 31.671 | 29.158 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 30.0 | -100.0 | G45T2 | 1 2 3 | 11 11 8
X8/Y5-1 | SGBM21 | Oct 23 2015 7:00PM | Oct 24 2015 9:04AM | Oct 24 2015 10:14AM | Oct 24 2015 12:15PM | 55.841 | 53.175 | 56.74 | 0.00 | 23.043 | 32.798 | 30.132 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
AB/30-1 | SGBM22 | Oct 23 2015 3:30PM | Oct 23 2015 7:41PM | Oct 23 2015 11:19PM | Oct 24 2015 2:00AM | 50.15 | 48.475 | 50.81 | 0.00 | 23.305 | 26.845 | 25.170 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 30.0 | -100.0 | G35T2 | 1 2 3 4 5 | 5 7 7 6 5
H/19-1 | SGBM19 | Oct 23 2015 9:05AM | Oct 23 2015 6:08PM | Oct 23 2015 10:37PM | Oct 24 2015 1:15AM | 53.49 | 52.675 | 45.24 | 0.00 | 26.240 | 28.000 | 26.435 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.9 | 31.0 | -22.9 | G45T2 | 1 2 3 4 5 | 7 7 7 4 6
AB/29-1 | SGBM03 | Oct 23 2015 8:30AM | Oct 23 2015 1:15PM | Oct 23 2015 6:53PM | Oct 23 2015 11:20PM | 50.189 | 48.475 | 51.18 | 0.00 | 22.878 | 27.311 | 25.597 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.2 | 33.0 | -100.0 | G35T2 | 1 2 3 4 5 6 | 3 5 6 6 6 7
H/55-2 | SGBM17 | Oct 23 2015 10:00AM | Oct 23 2015 5:04PM | Oct 23 2015 7:45PM | Oct 23 2015 10:20PM | 51.85 | 49.675 | 52.72 | 0.00 | 8.417 | 43.433 | 41.258 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.7 | 46.0 | 28.7 | G45T2 | 1 2 3 4 5 | 11 11 10 12 2
W/30-1b | SGBM03 | Oct 23 2015 8:10AM | Oct 23 2015 3:30PM | Oct 23 2015 7:05PM | Oct 23 2015 9:00PM | 48.519 | 47.375 | 49.28 | 0.00 | 23.882 | 24.637 | 23.493 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 22.0 | -100.0 | G45T2 | 1 2 3 4 | 5 6 7 4
D/57-2 | SGBM15 | Oct 23 2015 9:12AM | Oct 23 2015 2:32PM | Oct 23 2015 5:13PM | Oct 23 2015 7:35PM | 51.88 | 49.775 | 52.79 | 0.00 | 7.695 | 44.185 | 42.080 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.4 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 9 9 9
K/20-2 | SGBM19 | Oct 23 2015 8:30AM | Oct 23 2015 2:05PM | Oct 23 2015 5:50PM | Oct 23 2015 7:30PM | 53.484 | 51.075 | 45.33 | 0.00 | 29.325 | 24.159 | 21.750 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.8 | 23.0 | -100.0 | G45T2 | 1 2 3 4 | 6 6 5 6
J/57-2 | SGBM17 | Oct 23 2015 8:00AM | Oct 23 2015 1:55PM | Oct 23 2015 4:36PM | Oct 23 2015 6:15PM | 52.101 | 48.775 | 52.90 | 0.00 | 8.601 | 43.500 | 40.174 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.8 | 42.0 | -100.0 | G45T2 | 1 2 3 4 | 11 9 10 12
D/58-2 | SGBM15 | Oct 22 2015 8:00PM | Oct 23 2015 9:50AM | Oct 23 2015 11:05AM | Oct 23 2015 2:10PM | 51.92 | 49.775 | 52.80 | 0.00 | 7.700 | 44.220 | 42.075 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.4 | 45.0 | -36.4 | G45T2 | 1 2 3 4 5 6 7 | 7 7 7 6 6 5 7
X4a/Y4-1 | SGBM21 | Oct 22 2015 6:00PM | Oct 23 2015 9:20AM | Oct 23 2015 12:04PM | Oct 23 2015 2:00PM | 55.815 | 47.375 | 47.47 30.87 | 0.00 0.00 | 23.874 | 31.941 | 23.501 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
AB/27-1 | SGBM03 | Oct 21 2015 3:30PM | Oct 22 2015 7:50PM | Oct 23 2015 12:17AM | Oct 23 2015 2:00AM | 49.792 | 48.475 | 50.48 | 0.00 | 22.684 | 27.108 | 25.791 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.3 | 26.3 | -100.0 | G35T2 | 1 2 3 4 | 7 7 7 5.3
H/54-1 | SGBM17 | Oct 22 2015 8:30AM | Oct 22 2015 4:15PM | Oct 22 2015 7:17PM | Oct 22 2015 9:30PM | 51.91 | 49.775 | 52.78 | 0.00 | 8.978 | 42.932 | 40.797 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.3 | 41.0 | -100.0 | G45T2 | 1 2 3 4 | 9 11 11 10
H/56-5 | SGBM17 | Oct 21 2015 9:00AM | Oct 21 2015 8:20PM | Oct 22 2015 1:53PM | Oct 22 2015 4:40PM | 51.81 | 46.875 | 44.61 | 0.00 | 3.607 | 48.203 | 43.268 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.5 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 10 11 7
J/29-3 | SGBM20 | Oct 21 2015 11:30AM | Oct 22 2015 11:00AM | Oct 22 2015 2:45PM | Oct 22 2015 4:10PM | 52.169 | 49.775 | -9.00 | 0.00 | -26.500 | 78.669 | 76.275 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 66.1 | 26.0 | -40.0 | G45T2 | 1 2 3 4 | 7 7 7 5
J/59-3 | SGBM23 | Oct 21 2015 6:50PM | Oct 22 2015 9:20AM | Oct 22 2015 11:31AM | Oct 22 2015 2:40PM | 51.906 | 49.775 | 52.80 | 0.00 | 7.601 | 44.305 | 42.174 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 45.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 12 11
X5/Y5-3 | SGBM21 | Oct 21 2015 5:00PM | Oct 21 2015 10:00PM | Oct 22 2015 12:09PM | Oct 22 2015 2:20PM | 56.551 | 53.175 | 46.76 | 0.00 | 23.359 | 33.192 | 29.816 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 30.0 | -25.8 | G45T2 | 1 2 3 4 | 8 8 7 7
V/38-1 | SGBM19 | Oct 21 2015 11:00AM | Oct 21 2015 4:04PM | Oct 21 2015 8:48PM | Oct 21 2015 11:30PM | 49.552 | 47.075 | 50.38 | 0.00 | 17.979 | 31.573 | 29.096 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 33.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 7 7 7 7 2 3
J/57-3 | SGBM23 | Oct 21 2015 8:40AM | Oct 21 2015 6:00PM | Oct 21 2015 8:18PM | Oct 21 2015 10:55PM | 52.03 | 48.775 | 52.93 | 0.00 | 8.427 | 43.603 | 40.348 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.9 | 42.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 9
AB/26-1 | SGBM03 | Oct 20 2015 1:20PM | Oct 21 2015 2:20PM | Oct 21 2015 9:08PM | Oct 21 2015 10:40PM | 49.581 | 48.475 | 50.43 | 0.00 | 23.430 | 26.151 | 25.045 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.7 | 25.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 7 4
D/58-3 | SGBM15 | Oct 21 2015 8:00AM | Oct 21 2015 3:35PM | Oct 21 2015 6:30PM | Oct 21 2015 9:30PM | 51.77 | 49.775 | 52.60 | 0.00 | 7.300 | 44.470 | 42.475 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.8 | 46.0 | -100.0 | G45T2 | 1 2 3 4 | 11 12 11.5 11.5
X8/Y5-2 | SGBM21 | Oct 21 2015 9:35AM | Oct 21 2015 3:44PM | Oct 21 2015 6:59PM | Oct 21 2015 9:20PM | 55.844 | 53.175 | 56.62 | 0.00 | 22.819 | 33.025 | 30.356 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.3 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
J/58-4 | SGBM23 | Oct 20 2015 6:30PM | Oct 21 2015 1:00PM | Oct 21 2015 4:18PM | Oct 21 2015 7:00PM | 51.97 | 49.475 | 52.85 | 0.00 | 8.050 | 43.920 | 41.425 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.9 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
X5/Y4-2 | SGBM21 | Oct 19 2015 2:04PM | Oct 21 2015 10:30AM | Oct 21 2015 1:30PM | Oct 21 2015 4:00PM | 55.821 | 53.375 | 47.66 27.96 | 0.00 0.00 | 22.262 | 33.559 | 31.113 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.9 | 31.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
D/57-1 | SGBM15 | Oct 20 2015 6:00PM | Oct 21 2015 9:30AM | Oct 21 2015 11:30AM | Oct 21 2015 3:00PM | 51.857 | 49.775 | 52.67 | 0.00 | 7.670 | 44.187 | 42.105 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 6 7 | 7 7 7 7 7 7 5
Z/42-2 | SGBM19 | Oct 20 2015 3:00PM | Oct 20 2015 9:09PM | Oct 21 2015 1:09AM | Oct 21 2015 2:30AM | 49.7 | 47.025 | 50.61 | 0.00 | 20.010 | 29.690 | 27.015 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 32.0 | 36.8 | G45T2 | 1 2 3 4 5 | 7 6 7 6 6
H/55-1 | SGBM23 | Oct 20 2015 11:25AM | Oct 20 2015 7:05PM | Oct 20 2015 10:00PM | Oct 21 2015 12:20AM | 51.765 | 49.675 | 52.72 | 0.00 | 8.215 | 43.550 | 41.460 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.9 | 43.0 | 19.8 | G45T2 | 1 2 3 4 5 | 9 8 9 9 8
H/54-2 | SGBM23 | Oct 20 2015 8:20AM | Oct 20 2015 4:50PM | Oct 20 2015 7:55PM | Oct 20 2015 10:40PM | 51.91 | 49.775 | 52.75 | 0.00 | 9.754 | 42.156 | 40.021 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 45.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 12
K/30-1 | SGBM20 | Oct 19 2015 4:29PM | Oct 20 2015 1:50PM | Oct 20 2015 7:55PM | Oct 20 2015 9:30PM | 52.043 | 49.375 | 43.86 | 0.00 | 26.262 | 25.781 | 23.113 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 25.0 | -100.0 | G35T2 | 1 2 3 4 | 6 6 6 7
H/30-2 | SGBM20 | Oct 20 2015 8:00AM | Oct 20 2015 11:30AM | Oct 20 2015 2:23PM | Oct 20 2015 5:00PM | 52.082 | 49.675 | 43.83 | 0.00 | 26.630 | 25.452 | 23.045 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 25.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 6 6 5 1
V/36-1 | SGBM02 | Oct 19 2015 7:00PM | Oct 20 2015 8:13AM | Oct 20 2015 11:11AM | Oct 20 2015 4:00PM | 49.635 | 47.075 | 50.62 | 0.00 | 21.019 | 28.616 | 26.056 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.6 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 4
J/59-1 | SGBM17 | Oct 19 2015 9:00PM | Oct 20 2015 10:03AM | Oct 20 2015 1:30PM | Oct 20 2015 3:50PM | 51.909 | 49.775 | 52.77 | 0.00 | 7.468 | 44.441 | 42.307 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.6 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
G/55-2 | SGBM15 | Oct 19 2015 7:00PM | Oct 20 2015 8:17AM | Oct 20 2015 12:23PM | Oct 20 2015 2:50PM | 51.765 | 49.675 | 52.55 | 0.00 | 7.552 | 44.213 | 42.123 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
V/39-1 | SGBM19 | Oct 19 2015 9:10AM | Oct 19 2015 5:17PM | Oct 20 2015 12:18AM | Oct 20 2015 2:30AM | 49.478 | 47.075 | 50.39 | 0.00 | 16.992 | 32.486 | 30.083 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.1 | 34.0 | 30.5 | G45T2 | 1 2 3 | 11 11 12
J/56-3 | SGBM23 | Oct 19 2015 8:30AM | Oct 19 2015 1:23PM | Oct 19 2015 9:41PM | Oct 20 2015 12:30AM | 51.976 | 49.075 | 52.91 | 0.00 | 8.211 | 43.765 | 40.864 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.4 | 43.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 10 11
J/29-1 | SGBM23 | Oct 19 2015 10:00AM | Oct 19 2015 1:40PM | Oct 19 2015 7:00PM | Oct 19 2015 9:45PM | 52.121 | 49.775 | 52.98 | 0.00 | 26.679 | 25.442 | 23.096 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 27.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 3 3
D/58-1 | SGBM15 | Oct 17 2015 7:00PM | Oct 19 2015 4:10PM | Oct 19 2015 6:15PM | Oct 19 2015 9:00PM | 51.79 | 49.775 | 52.67 | 0.00 | 7.672 | 44.118 | 42.103 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 43.0 | -100.0 | G45T2 | 1 2 3 4 | 10 11 11 11
X8/Y5-3 | SGBM21 | Oct 19 2015 8:00AM | Oct 19 2015 1:00PM | Oct 19 2015 3:13PM | Oct 19 2015 6:00PM | 55.841 | 53.175 | 47.75 | 0.00 | 23.152 | 32.689 | 30.023 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 32.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 4
J/60-3 | SGBM17 | Oct 17 2015 7:50PM | Oct 18 2015 9:10AM | Oct 19 2015 10:40AM | Oct 19 2015 1:30PM | 51.928 | 49.775 | 52.86 | 0.00 | 6.157 | 45.771 | 43.618 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.8 | 46.0 | -100.0 | G45T2 | 1 2 3 4 5 6 7 | 7 7 7 7 7 7 4
J/58-2 | SGBM23 | Oct 17 2015 6:20PM | Oct 18 2015 10:15AM | Oct 18 2015 12:35PM | Oct 18 2015 4:00PM | 51.986 | 49.475 | 52.79 | 0.00 | 8.287 | 43.699 | 41.188 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.7 | 42.0 | 17.7 | G45T2 | 1 2 3 4 5 6 7 | 3 7 7 4 7 7 7
F/61-1 | SGBM15 | Oct 16 2015 7:00PM | Oct 17 2015 4:32PM | Oct 17 2015 7:03PM | Oct 17 2015 10:30PM | 51.895 | 50.775 | 52.70 | 0.00 | 6.603 | 45.292 | 44.172 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.3 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 5 | 4 11 11 10 10 3
X5/Y5-4 | SGBM21 | Oct 17 2015 2:30PM | Oct 17 2015 7:10PM | Oct 17 2015 8:01PM | Oct 17 2015 10:00PM | 55.7 | 53.175 | 56.52 | 0.00 | 24.118 | 31.582 | 29.057 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 32.0 | 27.2 | G45T2 | 1 2 3 4 5 | 7 7 7 4 7
X/20-1 | SGBM19 | Oct 16 2015 10:00AM | Oct 17 2015 4:20PM | Oct 17 2015 6:19PM | Oct 17 2015 8:15PM | 49.812 | 48.475 | 50.51 | 0.00 | 24.210 | 25.602 | 24.265 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 4
J/57-1 | SGBM17 | Oct 16 2015 9:00PM | Oct 17 2015 10:05AM | Oct 17 2015 3:24PM | Oct 17 2015 6:55PM | 52.017 | 48.775 | 52.90 | 0.00 | 8.404 | 43.613 | 40.371 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.0 | 44.0 | 25.9 | G45T2 | 1 2 3 4 | 11 11 11 11
G/54-3 | SGBM23 | Oct 17 2015 8:35AM | Oct 17 2015 2:00PM | Oct 17 2015 2:06PM | Oct 17 2015 4:20PM | 51.683 | 49.775 | 52.60 | 0.00 | 8.595 | 43.088 | 41.180 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.7 | 44.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 10 1
Z/42-1 | SGBM19 | Oct 16 2015 3:00PM | Oct 16 2015 8:20PM | Oct 16 2015 11:47PM | Oct 17 2015 2:10AM | 49.969 | 47.025 | 50.79 | 0.00 | 19.994 | 29.975 | 27.031 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 30.0 | -100.0 | G45T2 | 1 2 3 | 9 10 11
J/31-5 | SGBM20 | Oct 16 2015 4:15PM | Oct 16 2015 6:08PM | Oct 16 2015 9:27PM | Oct 17 2015 12:30AM | 52.039 | 49.675 | 43.95 | 0.00 | 27.350 | 24.689 | 22.325 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 3
J/58-1 | SGBM17 | Oct 15 2015 8:20PM | Oct 16 2015 4:00PM | Oct 16 2015 8:35PM | Oct 16 2015 11:50PM | 52 | 49.475 | 52.76 | 0.00 | 8.264 | 43.736 | 41.211 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.7 | 50.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 10 10 10
J/60-1 | SGBM15 | Oct 16 2015 8:00AM | Oct 16 2015 3:10PM | Oct 16 2015 6:45PM | Oct 16 2015 9:20PM | 51.904 | 49.775 | 52.63 | 0.00 | 6.632 | 45.272 | 43.143 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.4 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
Y/20-1 | SGBM19 | Oct 16 2015 9:20AM | Oct 16 2015 3:30PM | Oct 16 2015 5:10PM | Oct 16 2015 6:50PM | 49.756 | 48.475 | 50.63 | 0.00 | 23.932 | 25.824 | 24.543 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.3 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 4
J/56-1 | SGBM15 | Oct 16 2015 8:10AM | Oct 16 2015 3:10PM | Oct 16 2015 4:50PM | Oct 16 2015 6:30PM | 51.98 | 49.075 | 52.87 | 0.00 | 8.872 | 43.108 | 40.203 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.8 | 40.5 | -100.0 | G45T2 | 1 2 3 4 5 | 9 8 11.5 11 1
K/29-2 | SGBM20 | Oct 16 2015 10:30AM | Oct 16 2015 3:35PM | Oct 16 2015 4:27PM | Oct 16 2015 6:00PM | 52.121 | 49.375 | 43.90 | 0.00 | 26.199 | 25.922 | 23.176 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 25.0 | -20.1 | G35T2 | 1 2 3 4 | 7 7 7 4
H/58-4 | SGBM17 | Oct 15 2015 6:00PM | Oct 16 2015 9:13AM | Oct 16 2015 11:00AM | Oct 16 2015 2:00PM | 51.956 | 46.375 | 52.77 | 0.00 | 0.073 | 51.883 | 46.302 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.1 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 6 7 8 | 7 7 7 7 7 7 4 3
X5/Y4-1 | SGBM21 | Oct 15 2015 9:00AM | Oct 15 2015 3:30PM | Oct 15 2015 9:28PM | Oct 15 2015 11:50PM | 55.82 | 53.375 | 56.65 | 0.00 | 22.249 | 33.571 | 31.126 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.0 | 31.0 | 15.0 | G45T2 | 1 2 3 4 5 | 7 7 7 7 3
H/55-3 | SGBM15 | Oct 15 2015 8:00AM | Oct 15 2015 4:10PM | Oct 15 2015 6:34PM | Oct 15 2015 9:10PM | 51.815 | 49.675 | 52.64 | 0.00 | 8.638 | 43.177 | 41.037 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.5 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 10 10 10 4
H/58-8 | SGBM17 | Oct 14 2015 7:20PM | Oct 15 2015 12:40PM | Oct 15 2015 2:27PM | Oct 15 2015 7:30PM | 51.91 | 46.375 | 52.87 | 0.00 | 0.073 | 51.837 | 46.302 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.1 | 46.0 | 14.7 | G45T2 | 1 2 3 4 5 6 | 7 10 9 9 9 2
X5/Y5-2 | SGBM21 | Oct 15 2015 9:00AM | Oct 15 2015 3:10PM | Oct 15 2015 4:18PM | Oct 15 2015 5:55PM | 55.695 | 53.175 | 56.53 | 0.00 | 24.125 | 31.570 | 29.050 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 28.0 | -100.0 | G45T2 | 1 2 3 4 5 | 4 7 7 3 7
J/30-1 | SGBM20 | Oct 13 2015 2:34PM | Oct 15 2015 10:38AM | Oct 15 2015 3:40PM | Oct 15 2015 5:20PM | 51.968 | 49.675 | 43.63 | 0.00 | 26.429 | 26.200 | 23.246 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 24.0 | -20.1 | G45T2 | 1 2 3 4 | 7 7 7 3
J/59-2 | SGBM15 | Oct 14 2015 6:00PM | Oct 15 2015 10:30AM | Oct 15 2015 12:33PM | Oct 15 2015 3:30PM | 51.89 | 49.775 | 52.79 | 0.00 | 7.590 | 44.300 | 42.185 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 42.0 | -36.5 | G45T2 | 1 2 3 4 5 6 7 | 4 9 8 4 6 9 2
H/57-6 | SGBM17 | Oct 13 2015 2:00PM | Oct 15 2015 9:30AM | Oct 15 2015 10:50AM | Oct 15 2015 1:30PM | 51.86 | 46.375 | 52.70 | 0.00 | -0.100 | 51.960 | 46.475 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.2 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 6 7 | 6 4 9 9 8 7 6
J/32-2 | SGBM20 | Oct 13 2015 9:00AM | Oct 13 2015 12:48PM | Oct 13 2015 10:59PM | Oct 14 2015 12:40AM | 52.126 | 49.675 | 52.84 | 0.00 | 26.544 | 25.582 | 23.131 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 24.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 3
G/54-1 | SGBM23 | Oct 12 2015 6:00PM | Oct 13 2015 4:30PM | Oct 13 2015 7:12PM | Oct 13 2015 10:00PM | 51.883 | 49.775 | 52.74 | 0.00 | 8.738 | 43.145 | 41.037 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.5 | 48.0 | 35.1 | G45T2 | 1 2 3 4 5 6 | 9 9 9 9 8 4
J/58-3 | SGBM17 | Oct 13 2015 8:00AM | Oct 13 2015 1:45PM | Oct 13 2015 2:59PM | Oct 13 2015 7:00PM | 51.942 | 49.475 | 52.90 | 0.00 | 8.395 | 43.547 | 41.080 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.6 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 9 9 9 9 6 6
K/55-1 | SGBM15 | Oct 12 2015 9:00PM | Oct 13 2015 11:00AM | Oct 13 2015 1:27PM | Oct 13 2015 4:00PM | 52.198 | 49.775 | 52.92 | 0.00 | 12.720 | 39.478 | 37.055 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 38.0 | -100.0 | G45T2 | 1 2 3 4 | 10 9 9 10
J/56-2 | SGBM17 | Oct 11 2015 6:30PM | Oct 12 2015 10:00AM | Oct 13 2015 11:09AM | Oct 13 2015 2:00PM | 51.892 | 49.075 | 52.81 | 0.00 | 9.012 | 42.880 | 40.063 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 42.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 9
V/22-2 | SGBM19 | Oct 12 2015 11:00AM | Oct 12 2015 5:45PM | Oct 13 2015 1:40AM | Oct 13 2015 3:35AM | 49.716 | 47.025 | 50.50 | 0.00 | 24.696 | 25.020 | 22.329 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
X/21-1 | SGBM19 | Oct 12 2015 8:10AM | Oct 12 2015 3:15PM | Oct 12 2015 11:00PM | Oct 13 2015 12:00AM | 49.742 | 48.775 | 50.61 | 0.00 | 25.512 | 24.230 | 23.263 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 25.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 4
F/57-1 | SGBM22 | Oct 11 2015 7:00PM | Oct 12 2015 3:00PM | Oct 12 2015 5:01PM | Oct 12 2015 8:00PM | 51.879 | 49.775 | 52.70 | 0.00 | 4.200 | 47.679 | 45.575 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.5 | 45.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 2 9 9 10 10 5
Y/21-1 | SGBM19 | Oct 12 2015 8:00AM | Oct 12 2015 3:30PM | Oct 12 2015 5:50PM | Oct 12 2015 7:39PM | 49.809 | 48.775 | 50.56 | 0.00 | 24.257 | 25.552 | 24.518 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.2 | 26.0 | -100.0 | G45T2 | 1 2 3 4 | 7 5 7 7
H/58-5 | SGBM17 | Oct 10 2015 5:00PM | Oct 12 2015 11:00AM | Oct 12 2015 2:58PM | Oct 12 2015 6:00PM | 51.909 | 46.375 | 52.73 | 0.00 | 0.231 | 51.678 | 46.144 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.0 | 53.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 11 9
J/31-6 | SGBM20 | Oct 12 2015 8:00AM | Oct 12 2015 2:00PM | Oct 12 2015 3:42PM | Oct 12 2015 6:00PM | 52.014 | 50.875 | 43.76 | 0.00 | 27.875 | 24.139 | 23.000 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.9 | 25.0 | -19.9 | G45T2 | 1 2 3 4 | 7 7 7 4
J/60-2 | SGBM15 | Oct 11 2015 7:00PM | Oct 12 2015 10:00AM | Oct 12 2015 12:11PM | Oct 12 2015 3:45PM | 51.93 | 49.775 | 52.79 | 0.00 | 6.687 | 45.243 | 43.088 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 2 11 11 11.5 11.5
H/58-9 | SGBM23 | Oct 9 2015 3:45PM | Oct 10 2015 10:37PM | Oct 12 2015 10:40AM | Oct 12 2015 1:30PM | 51.9 | 46.375 | 43.76 | 0.00 | -0.239 | 52.139 | 46.614 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.4 | 53.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 11 9
U/21-1 | SGBM19 | Oct 12 2015 12:00PM | Oct 12 2015 10:00PM | Oct 13 2015 3:51AM | Oct 12 2015 4:55AM | 49.786 | 49.075 | 50.56 | 0.00 | 25.764 | 24.022 | 23.311 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.2 | 27.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 6
Z/21-1 | SGBM20 | Oct 10 2015 8:50AM | Oct 10 2015 6:00PM | Oct 10 2015 11:55PM | Oct 11 2015 2:30AM | 49.792 | 48.775 | 50.83 | 0.00 | 24.532 | 25.260 | 24.243 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 27.0 | -21.0 | G45T2 | 1 2 3 4 | 7 7 7 6
J/28-8 | SGBM20 | Oct 10 2015 1:30PM | Oct 10 2015 5:40PM | Oct 10 2015 6:32PM | Oct 10 2015 8:30PM | 52.145 | 51.375 | 43.94 | 0.00 | 27.737 | 24.408 | 23.638 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 28.0 | -20.5 | G45T2 | 1 2 3 4 | 7 7 7 7
G/54-2 | SGBM15 | Oct 9 2015 7:20PM | Oct 10 2015 11:40AM | Oct 10 2015 4:47PM | Oct 10 2015 8:15PM | 51.82 | 49.775 | 52.63 | 0.00 | 8.327 | 43.493 | 41.448 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 35.9 | 52.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 10 11 11 11
AA/25-1 | SGBM19 | Oct 9 2015 6:00PM | Oct 10 2015 3:00PM | Oct 10 2015 4:39PM | Oct 10 2015 7:20PM | 49.913 | 49.075 | 50.64 | 0.00 | 23.638 | 26.275 | 25.437 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.0 | 25.0 | -100.0 | G35T2 | 1 2 3 4 | 7 7 7 4
F/57-3 | SGBM23 | Oct 9 2015 4:50PM | Oct 10 2015 11:40AM | Oct 10 2015 2:00PM | Oct 10 2015 4:00PM | 51.91 | 49.775 | 52.76 | 0.00 | 4.462 | 47.448 | 45.313 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.2 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 9 11 9 9
E/55-3 | SGBM17 | Oct 9 2015 7:00PM | Oct 10 2015 4:30AM | Oct 10 2015 11:10AM | Oct 10 2015 2:40PM | 51.897 | 49.475 | 52.70 | 0.00 | 6.398 | 45.499 | 43.077 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 10 10 9 9 3
J/55-4 | SGBM15 | Oct 9 2015 8:00AM | Oct 9 2015 6:00PM | Oct 9 2015 9:45PM | Oct 10 2015 12:50AM | 51.9 | 49.375 | 52.69 | 0.00 | 10.087 | 41.813 | 39.288 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.0 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 4 10 11 12 5
J/25-7 | SGBM20 | Oct 9 2015 11:00AM | Oct 9 2015 5:00PM | Oct 9 2015 6:53PM | Oct 9 2015 10:30PM | 52.495 | 47.325 | 44.21 | 0.00 | 23.711 | 28.784 | 23.614 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 28.0 | -20.4 | G45T2 | 1 2 3 4 | 7 7 7 7
H/58-1 | SGBM23 | Oct 8 2015 3:45PM | Oct 9 2015 1:20PM | Oct 9 2015 6:51PM | Oct 9 2015 10:20PM | 51.96 | 46.375 | 44.77 18.77 | 0.00 0.00 | -0.030 | 51.990 | 46.405 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.2 | 60.0 | 49.3 | G45T2 | 1 2 3 4 5 6 7 | 9 10 10 10 8 8 5
V/22-1 | SGBM03 | Oct 8 2015 11:00AM | Oct 9 2015 5:00PM | Oct 9 2015 7:22PM | Oct 9 2015 10:00PM | 49.703 | 47.025 | 50.50 | 0.00 | 24.900 | 24.803 | 22.125 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 21.0 | -100.0 | G45T2 | 1 2 3 | 7 7 7
F/56-3 | SGBM19 | Oct 8 2015 9:00PM | Oct 9 2015 4:00PM | Oct 9 2015 5:48PM | Oct 9 2015 8:20PM | 51.911 | 49.775 | 52.73 | 0.00 | 5.729 | 46.182 | 44.046 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.1 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 12 11 10 12 2
Z/27-2 | SGBM20 | Oct 7 2015 2:10PM | Oct 9 2015 3:30PM | Oct 9 2015 4:22PM | Oct 9 2015 6:45PM | 49.953 | 47.425 | 51.06 | 0.00 | 23.261 | 26.692 | 24.164 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.9 | 28.0 | -100.0 | G45T2 | PJ192 PJ193 PJ195 PJ196 | 7 7 7 7
K/60-2 | SGBM15 | Oct 8 2015 9:00AM | Oct 8 2015 6:24PM | Oct 9 2015 4:39PM | Oct 9 2015 6:10PM | 52.049 | 49.475 | 52.78 | 0.00 | 9.376 | 42.673 | 40.099 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 43.0 | -100.0 | G45T2 | 1 2 3 4 | 11 12 10 10
J/27-1 | SGBM20 | Oct 9 2015 9:00AM | Oct 9 2015 2:38PM | Oct 9 2015 3:00PM | Oct 9 2015 5:10PM | 52.311 | 48.825 | 44.29 | 0.00 | 24.992 | 27.319 | 23.833 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 24.0 | -20.6 | G45T2 | 1 2 3 4 | 7 7 7 3
E/60-2 | SGBM18 | Oct 8 2015 4:45PM | Oct 9 2015 9:30AM | Oct 9 2015 11:39AM | Oct 9 2015 2:00PM | 51.939 | 49.475 | 52.78 | 0.00 | 7.277 | 44.662 | 42.198 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.5 | 44.0 | 20.4 | G45T2 | 1 2 3 4 5 | 11 11 3 10 9
W/22-2 | SGBM03 | Oct 7 2015 3:00PM | Oct 8 2015 5:00PM | Oct 8 2015 11:30PM | Oct 9 2015 2:00AM | 49.872 | 47.025 | 50.66 | 0.00 | 24.863 | 25.009 | 22.162 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 25.0 | -100.0 | G45T2 | 1 2 3 | 9 10 6
H/57-8 | SGBM23 | Oct 7 2015 1:10PM | Oct 7 2015 4:20PM | Oct 8 2015 9:00PM | Oct 9 2015 1:45AM | 51.843 | 46.375 | 43.69 | 0.00 | -0.115 | 51.958 | 46.490 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.3 | 51.0 | -40.3 | G45T2 | 1 2 3 4 5 6 7 8 | 7 2 7 7 7 7 7 7
Z/27-3 | SGBM19 | Oct 7 2015 5:00PM | Oct 8 2015 2:15PM | Oct 8 2015 7:12PM | Oct 8 2015 9:00PM | 50 | 47.425 | 50.99 | 0.00 | 23.192 | 26.808 | 24.233 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 28.0 | -100.0 | G45T2 | 1 2 3 | 10 7 11
Z/30-2 | SGBM19 | Oct 7 2015 9:00PM | Oct 8 2015 2:00PM | Oct 8 2015 3:59PM | Oct 8 2015 8:20PM | 49.887 | 47.025 | 50.82 | 0.00 | 22.918 | 26.969 | 24.107 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.9 | 27.0 | 29.3 | G45T2 | 1 2 3 4 | 3 11 10 3
J/32-1 | SGBM20 | Oct 8 2015 1:30PM | Oct 8 2015 4:40PM | Oct 8 2015 5:45PM | Oct 8 2015 8:00PM | 52.145 | 49.675 | 43.90 | 0.00 | 26.500 | 25.645 | 23.175 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 23.0 | 2.9 | G45T2 | 1 2 3 4 | 7 5 7 4
E/55-2 | SGBM17 | Oct 7 2015 8:10AM | Oct 8 2015 10:00AM | Oct 8 2015 11:43AM | Oct 8 2015 2:50PM | 51.873 | 49.475 | 52.67 | 0.00 | 6.371 | 45.502 | 43.104 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 50.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 10 10 10
F/58-2 | SGBM17 | Oct 7 2015 8:00AM | Oct 7 2015 6:00PM | Oct 7 2015 11:49PM | Oct 8 2015 3:00AM | 51.93 | 49.775 | 52.72 | 0.00 | 4.721 | 47.209 | 45.054 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 45.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 9 10 6
V/21-1 | SGBM22 | Oct 7 2015 3:00PM | Oct 7 2015 10:10PM | Oct 8 2015 12:50AM | Oct 8 2015 3:00AM | 49.773 | 48.725 | 50.49 | 0.00 | 24.392 | 25.381 | 24.333 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.1 | 25.0 | -100.0 | G45T2 | 1 2 3 | 10 9 6
Z/27a-2 | SGBM19 | Oct 7 2015 10:00AM | Oct 7 2015 4:40PM | Oct 7 2015 11:40PM | Oct 8 2015 2:10AM | 49.819 | 49.075 | 50.93 | 0.00 | 27.627 | 22.192 | 21.448 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.6 | 16.0 | -100.0 | G45T2 | 1 2 3 | 7 7 2
J/27-3 | SGBM20 | Oct 7 2015 9:00AM | Oct 7 2015 2:00PM | Oct 7 2015 10:48PM | Oct 8 2015 1:00AM | 52.242 | 48.825 | 43.92 | 0.00 | 24.918 | 27.324 | 23.907 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 26.0 | -20.7 | G45T2 | 1 2 3 | 4 11 11
J/25-3 | SGBM20 | Oct 7 2015 9:30AM | Oct 7 2015 5:00PM | Oct 7 2015 9:46PM | Oct 7 2015 11:56PM | 52.46 | 47.325 | 44.10 | 0.00 | 23.300 | 29.160 | 24.025 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 25.0 | -20.8 | G45T2 | 1 2 3 | 9 11 5
J/55-2 | SGBM15 | Oct 7 2015 8:10AM | Oct 7 2015 6:27PM | Oct 7 2015 9:00PM | Oct 7 2015 11:55PM | 51.957 | 49.375 | 52.76 | 0.00 | 10.365 | 41.592 | 39.010 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.8 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 11 9 10 2
G/60-2 | SGBM23 | Oct 7 2015 8:00AM | Oct 7 2015 6:00PM | Oct 7 2015 8:02PM | Oct 7 2015 11:10PM | 51.891 | 49.675 | 52.67 | 0.00 | 4.672 | 47.219 | 45.003 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 11 8 9 11
E/60-3 | SGBM18 | Oct 6 2015 10:10AM | Oct 7 2015 1:00PM | Oct 7 2015 4:21PM | Oct 7 2015 9:00PM | 51.919 | 49.475 | 52.77 | 0.00 | 7.473 | 44.446 | 42.002 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.4 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 11 3
K/60-3 | SGBM15 | Oct 6 2015 1:00PM | Oct 6 2015 10:00PM | Oct 7 2015 11:25AM | Oct 7 2015 2:00PM | 51.837 | 49.475 | 52.70 | 0.00 | 9.401 | 42.436 | 40.074 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 10 9 11 10
W/21-1 | SGBM03 | Oct 6 2015 3:00PM | Oct 6 2015 9:00PM | Oct 7 2015 2:37AM | Oct 7 2015 4:20AM | 49.742 | 48.725 | 50.72 | 0.00 | 25.419 | 24.323 | 23.306 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.2 | 29.0 | -100.0 | G45T2 | 1 2 3 | 9 10 10
W/22-1 | SGBM03 | Oct 6 2015 3:00PM | Oct 6 2015 9:00PM | Oct 7 2015 1:07AM | Oct 7 2015 3:00AM | 49.967 | 47.025 | 50.66 | 0.00 | 25.063 | 24.904 | 21.962 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.0 | 27.0 | -100.0 | G45T2 | 1 2 3 | 6 10 11
H/56-7 | SGBM23 | Oct 5 2015 11:00AM | Oct 6 2015 7:50PM | Oct 6 2015 10:40PM | Oct 7 2015 2:00AM | 51.949 | 46.875 | 46.67 27.57 | 0.00 0.00 | 3.875 | 48.074 | 43.000 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.2 | 51.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 5 9 10 11 11 5
J/28-2 | SGBM20 | Oct 6 2015 6:00PM | Oct 6 2015 10:15PM | Oct 6 2015 11:05PM | Oct 7 2015 12:13AM | 52.29 | 51.375 | 44.10 | 0.00 | 27.505 | 24.785 | 23.870 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 25.0 | -100.0 | G45T2 | 1 2 3 | 11 11 3
H/57-4 | SGBM15 | Oct 5 2015 8:00AM | Oct 6 2015 5:00PM | Oct 6 2015 8:57PM | Oct 6 2015 11:15PM | 51.938 | 46.375 | 46.73 25.63 | 0.00 0.00 | 0.332 | 51.606 | 46.043 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 42.0 | -100.0 | G45T2 | 1 2 3 4 | 10 10 11 11
Z/40a-1 | SGBM03 | Oct 3 2015 8:45PM | Oct 5 2015 8:18AM | Oct 6 2015 6:20PM | Oct 6 2015 10:30PM | 49.861 | 48.525 | 50.41 | 0.00 | 20.312 | 29.549 | 28.213 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 36.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 5 7 7 7 7 3
N/37-1 | SGBM08 | Oct 6 2015 12:00PM | Oct 6 2015 4:00PM | Oct 6 2015 6:35PM | Oct 6 2015 8:10PM | 51.911 | 49.575 | 52.70 | 0.00 | 28.575 | 23.336 | 21.000 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.2 | 21.0 | -100.0 | G45T2 | 1 2 | 11 10
H/58-10 | SGBM17 | Oct 5 2015 11:40AM | Oct 5 2015 2:25PM | Oct 6 2015 3:22PM | Oct 6 2015 7:00PM | 51.938 | 46.375 | 43.67 | 0.00 | 0.373 | 51.565 | 46.002 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.8 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 11 11 11 7
Z/30-1 | SGBM19 | Oct 5 2015 8:30AM | Oct 6 2015 2:00PM | Oct 6 2015 5:03PM | Oct 6 2015 6:30PM | 49.988 | 47.025 | 50.85 | 0.00 | 22.849 | 27.139 | 24.176 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.9 | 26.0 | -100.0 | G45T2 | 1 2 3 | 11 4 11
X/43-1 | SGBM21 | Oct 5 2015 6:15PM | Oct 6 2015 8:18AM | Oct 6 2015 1:47PM | Oct 6 2015 3:30PM | 49.597 | 47.375 | 50.47 | 0.00 | 17.974 | 31.623 | 29.401 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 28.0 | -100.0 | G45T2 | 1 2 3 4 | 7 7 7 7
Z/27-1 | SGBM19 | Oct 3 2015 5:00PM | Oct 6 2015 10:00AM | Oct 6 2015 12:22PM | Oct 6 2015 3:00PM | 50.043 | 47.425 | 50.85 | 0.00 | 22.952 | 27.091 | 24.473 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 21.2 | 26.0 | -100.0 | G45T2 | 1 2 3 | 8 11 7
J/55-3 | SGBM23 | Oct 5 2015 12:30PM | Oct 5 2015 8:00PM | Oct 6 2015 12:17AM | Oct 6 2015 3:20AM | 51.948 | 49.375 | 52.77 | 0.00 | 10.368 | 41.580 | 39.007 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.8 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 9 10 10 11
E/55-4 | SGBM23 | Oct 4 2015 9:00PM | Oct 5 2015 5:00PM | Oct 5 2015 11:16PM | Oct 6 2015 1:40AM | 51.937 | 49.475 | 52.71 | 0.00 | 9.414 | 42.523 | 40.061 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 45.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 11 11 8 5
X8/Y3-1 | SGBM09 | Oct 3 2015 1:00PM | Oct 5 2015 8:30PM | Oct 5 2015 10:17PM | Oct 6 2015 1:00AM | 55.64 | 53.175 | 47.45 | 0.00 | 16.850 | 38.790 | 36.325 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.5 | 35.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 9 4
J/25-15 | SGBM20 | Oct 5 2015 1:30PM | Oct 5 2015 9:00PM | Oct 5 2015 9:54PM | Oct 5 2015 11:57PM | 52.319 | 47.325 | 44.12 | 0.00 | 23.617 | 28.702 | 23.708 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 25.0 | -20.5 | G45T2 | 1 2 3 | 8 9 8
E/60-4 | SGBM18 | Oct 4 2015 9:00PM | Oct 5 2015 4:00PM | Oct 5 2015 6:15PM | Oct 5 2015 10:00PM | 51.929 | 49.475 | 52.76 | 0.00 | 7.463 | 44.466 | 42.012 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.4 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 8 6 10 10
Z/27-4 | SGBM19 | Oct 5 2015 8:00AM | Oct 5 2015 2:40PM | Oct 5 2015 5:58PM | Oct 5 2015 8:00PM | 50.012 | 47.425 | 51.24 | 0.00 | 23.143 | 26.869 | 24.282 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 27.0 | -100.0 | G45T2 | 1 2 3 | 9 10 8
J/25-4 | SGBM20 | Oct 3 2015 12:00PM | Oct 5 2015 5:30PM | Oct 5 2015 5:38PM | Oct 5 2015 7:31PM | 52.249 | 47.325 | 44.08 | 0.00 | 23.685 | 28.564 | 23.640 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 26.0 | -20.5 | G45T2 | 1 2 3 | 11 11 4
K/60-4 | SGBM17 | Oct 4 2015 9:00PM | Oct 5 2015 1:00PM | Oct 5 2015 2:07PM | Oct 5 2015 5:50PM | 51.837 | 49.475 | 52.70 | 0.00 | 9.401 | 42.436 | 40.074 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 43.0 | 23.9 | G45T2 | 1 2 3 4 5 | 8 11 6 10 8
J/30-2 | SGBM20 | Oct 5 2015 10:30AM | Oct 5 2015 2:40PM | Oct 5 2015 1:40PM | Oct 5 2015 3:30PM | 52.103 | 49.675 | 43.86 | 0.00 | 26.557 | 25.546 | 23.118 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 25.0 | -20.0 | G45T2 | 1 2 3 | 10 11 4
Z/43-1 | SGBM03 | Oct 3 2015 10:30AM | Oct 5 2015 8:12AM | Oct 5 2015 11:11AM | Oct 5 2015 1:00PM | 49.688 | 46.925 | 50.56 | 0.00 | 19.257 | 30.431 | 27.668 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.0 | 31.5 | -24.0 | G45T2 | 1 2 3 4 | 11 5.5 11 4
K/55-3 | SGBM15 | Oct 2 2015 7:40PM | Oct 3 2015 7:50PM | Oct 3 2015 9:09PM | Oct 4 2015 1:15AM | 51.954 | 49.775 | 52.83 | 0.00 | 12.734 | 39.220 | 37.041 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 43.0 | -100.0 | G45T2 | 1 2 3 4 5 | 4 10 10 12 7
J/25-1 | SGBM20 | Oct 3 2015 12:00PM | Oct 3 2015 6:05PM | Oct 3 2015 8:37PM | Oct 3 2015 10:01PM | 52.597 | 47.325 | 44.41 | 0.00 | 23.607 | 28.990 | 23.718 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 25.0 | -20.5 | G45T2 | 1 2 3 | 7 12 6
H/58-13 | SGBM17 | Oct 2 2015 4:00PM | Oct 3 2015 3:00PM | Oct 3 2015 6:10PM | Oct 3 2015 9:00PM | 51.949 | 46.375 | 46.71 29.91 | 0.00 0.00 | 0.311 | 51.638 | 46.064 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 10 12 12 5
J/28-1 | SGBM20 | Oct 2 2015 6:40PM | Oct 3 2015 3:15PM | Oct 3 2015 5:18PM | Oct 3 2015 7:20PM | 52.199 | 51.375 | 43.99 | 0.00 | 27.495 | 24.704 | 23.880 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 24.0 | -100.0 | G45T2 | 1 2 3 | 4 10 10
H/57-7 | SGBM23 | Oct 2 2015 3:10PM | Oct 3 2015 2:05PM | Oct 3 2015 4:00PM | Oct 3 2015 6:20PM | 51.88 | 46.375 | 46.67 29.67 | 0.00 0.00 | 0.365 | 51.515 | 46.010 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.8 | 47.0 | -100.0 | G45T2 | 1 2 3 4 | 12 12 11 12
P/39-1 | SGBM16 | Oct 2 2015 9:00PM | Oct 3 2015 8:14AM | Oct 3 2015 11:01AM | Oct 3 2015 1:30PM | 51.905 | 51.375 | 52.60 | 0.00 | 27.375 | 24.530 | 24.000 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 24.0 | -100.0 | G45T2 | 1 2 3 | 11 9 4
X/43-2 | SGBM03 | Oct 2 2015 6:15PM | Oct 3 2015 8:12AM | Oct 3 2015 11:57AM | Oct 3 2015 1:20PM | 49.611 | 47.375 | 50.51 | 0.00 | 18.305 | 31.306 | 29.070 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 29.0 | -100.0 | G45T2 | 1 2 3 | 8 10 11
J/55-1 | SGBM17 | Oct 2 2015 8:10AM | Oct 2 2015 5:20PM | Oct 3 2015 12:02AM | Oct 3 2015 3:20AM | 52.056 | 49.375 | 52.90 | 0.00 | 10.300 | 41.756 | 39.075 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.8 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 11 11 11 7
G/60-1 | SGBM23 | Oct 2 2015 11:00AM | Oct 2 2015 5:00PM | Oct 2 2015 11:00PM | Oct 3 2015 1:50AM | 51.895 | 49.675 | 52.73 | 0.00 | 4.630 | 47.265 | 45.045 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 45.0 | -39.0 | G45T2 | 1 2 3 4 5 | 11 9 11 11 3
Q/39-1 | SGBM16 | Oct 2 2015 9:00AM | Oct 2 2015 1:00PM | Oct 2 2015 9:48PM | Oct 3 2015 12:30AM | 52.78 | 51.375 | 53.46 | 0.00 | 26.375 | 26.405 | 25.000 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.7 | 25.0 | -21.6 | G45T2 | 1 2 3 | 11 11 3
X5/Y2-2 | SGBM09 | Oct 1 2015 6:00PM | Oct 2 2015 4:00PM | Oct 2 2015 9:00PM | Oct 2 2015 11:40PM | 55.69 | 53.175 | 47.45 38.45 | 0.00 0.00 | 17.046 | 38.644 | 36.129 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 31.3 | 41.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 9 11 4 6
E/60-1 | SGBM18 | Oct 1 2015 10:10AM | Oct 2 2015 1:00PM | Oct 2 2015 5:33PM | Oct 2 2015 8:10PM | 51.918 | 49.475 | 52.81 | 0.00 | 7.409 | 44.509 | 42.066 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 36.4 | 44.0 | -100.0 | G45T2 | 1 2 3 4 5 | 4 11 9 11 9
Z/44-1 | SGBM03 | Oct 1 2015 9:50AM | Oct 1 2015 5:05PM | Oct 2 2015 3:45PM | Oct 2 2015 6:10PM | 49.592 | 46.925 | 42.46 | 0.00 | 17.158 | 32.434 | 29.767 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.8 | 37.0 | -25.8 | G45T2 | 1 2 3 4 5 6 | 9 1 8 9 9 1
J/27-7 | SGBM20 | Oct 1 2015 6:08PM | Oct 2 2015 12:30PM | Oct 2 2015 4:21PM | Oct 2 2015 6:10PM | 52.118 | 48.825 | 43.93 | 0.00 | 25.134 | 26.984 | 23.691 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 24.0 | -20.5 | G45T2 | 1 2 3 | 11 8 5
E/55-1 | SGBM17 | Oct 1 2015 9:00AM | Oct 2 2015 9:10AM | Oct 2 2015 2:45PM | Oct 2 2015 5:00PM | 51.888 | 49.475 | 52.75 | 0.00 | 6.448 | 45.440 | 43.027 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 42.0 | 4.7 | G45T2 | 1 2 3 4 | 11 11 11 9
K/55-2 | SGBM23 | Oct 1 2015 8:30AM | Oct 1 2015 6:00PM | Oct 2 2015 12:42AM | Oct 2 2015 3:30AM | 51.973 | 49.775 | 52.84 | 0.00 | 12.743 | 39.230 | 37.032 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 39.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 8 8 8 5
F/57-2 | SGBM18 | Oct 1 2015 1:20PM | Oct 1 2015 8:30PM | Oct 1 2015 10:49PM | Oct 2 2015 1:40AM | 52.01 | 49.775 | 52.75 | 0.00 | 4.751 | 47.259 | 45.024 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 5 11 10 10 11
P/38-1 | SGBM16 | Oct 1 2015 8:00AM | Oct 1 2015 1:12PM | Oct 1 2015 10:39PM | Oct 2 2015 12:20AM | 52.013 | 49.475 | 52.82 | 0.00 | 26.319 | 25.694 | 23.156 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 24.0 | -100.0 | G45T2 | 1 2 3 | 10 9 5
J/25-2 | SGBM20 | Sep 30 2015 9:00PM | Oct 1 2015 8:15PM | Oct 1 2015 8:15PM | Oct 1 2015 10:05PM | 52.267 | 47.325 | 44.04 | 0.00 | 23.542 | 28.725 | 23.783 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 26.0 | -20.6 | G45T2 | 1 2 3 | 8 10 8
J/25-11 | SGBM20 | Sep 30 2015 9:00PM | Oct 1 2015 8:00PM | Oct 1 2015 6:13PM | Oct 1 2015 7:45PM | 52.201 | 47.325 | 44.01 | 0.00 | 23.511 | 28.690 | 23.814 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 26.0 | -100.0 | G45T2 | 1 2 3 | 11 11 4
Y/43-1 | SGBM03 | Sep 30 2015 3:05PM | Sep 30 2015 10:25PM | Oct 1 2015 3:45PM | Oct 1 2015 6:40PM | 46.681 | 47.375 | 42.59 | 0.00 | 19.090 | 27.591 | 28.285 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 3
H/58-6 | SGBM15 | Sep 30 2015 4:00PM | Sep 30 2015 9:00PM | Oct 1 2015 12:58PM | Oct 1 2015 4:10PM | 51.898 | 46.375 | 46.87 | 0.00 | 0.370 | 47.128 | 46.005 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.8 | 57.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 11 11 11 8 8
Z/37-1 | SGBM03 | Sep 30 2015 10:35AM | Sep 30 2015 4:45PM | Oct 1 2015 12:48PM | Oct 1 2015 3:25PM | 49.746 | 46.925 | 42.70 | 0.00 | 18.400 | 31.346 | 28.525 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 32.0 | -24.7 | G45T2 | 1 2 3 4 | 11 8 11 2
S/36-2 | SGBM16 | Sep 30 2015 10:00AM | Oct 1 2015 8:17AM | Oct 1 2015 12:10PM | Oct 1 2015 2:10PM | 51.54 | 49.225 | 53.19 | 0.00 | 25.190 | 26.350 | 24.035 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 25.0 | -100.0 | G45T2 | 1 2 3 | 11 11 3
G/60-3 | SGBM23 | Sep 30 2015 6:00PM | Oct 1 2015 8:20AM | Oct 1 2015 11:35AM | Oct 1 2015 1:20PM | 51.862 | 49.675 | 52.73 | 0.00 | 4.629 | 47.233 | 45.046 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 11 6 11 10
H/58-12 | SGBM15 | Sep 30 2015 9:00AM | Sep 30 2015 8:40PM | Oct 1 2015 5:38AM | Oct 1 2015 8:00AM | 52 | 46.375 | 46.87 | 0.00 | 0.372 | 51.628 | 46.003 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.8 | 53.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 10 10
J/27-2 | SGBM20 | Sep 30 2015 1:00PM | Sep 30 2015 10:00PM | Oct 1 2015 12:51AM | Oct 1 2015 6:00AM | 52.166 | 48.825 | 43.92 | 0.00 | 25.316 | 26.850 | 23.509 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 26.0 | -100.0 | G45T2 | 1 2 3 | 9 12 5
F/56-2 | SGBM23 | Sep 30 2015 8:10AM | Sep 30 2015 8:00PM | Oct 1 2015 3:01AM | Oct 1 2015 5:20AM | 51.868 | 49.775 | 52.80 | 0.00 | 5.702 | 46.166 | 44.073 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.2 | 45.0 | -100.0 | G45T2 | 1 2 3 4 | 12 11 11 11
J/31-2 | SGBM20 | Sep 29 2015 7:00PM | Sep 30 2015 6:15PM | Sep 30 2015 10:26PM | Oct 1 2015 12:00AM | 52.113 | 49.675 | 43.82 | 0.00 | 27.523 | 24.590 | 22.152 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 24.0 | -100.0 | G45T2 | 1 2 3 | 10 10 4
F/58-3 | SGBM18 | Sep 30 2015 8:00AM | Sep 30 2015 3:00PM | Sep 30 2015 7:25PM | Sep 30 2015 9:40PM | 51.906 | 49.775 | 52.79 | 0.00 | 4.692 | 47.214 | 45.083 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 40.0 | -39.0 | G45T2 | 1 2 3 4 | 10 10 10 10
J/28-3 | SGBM20 | Sep 29 2015 7:00PM | Sep 30 2015 1:15PM | Sep 30 2015 6:55PM | Sep 30 2015 8:40PM | 52.222 | 51.375 | 44.03 | 0.00 | 27.635 | 24.587 | 23.740 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 24.0 | -100.0 | G45T2 | 1 2 3 | 6 11 7
S/39-1 | SGBM16 | Sep 29 2015 1:00PM | Sep 30 2015 4:30PM | Sep 30 2015 6:27PM | Sep 30 2015 8:10PM | 52.638 | 51.375 | 53.41 | 0.00 | 24.311 | 28.327 | 27.064 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.4 | 27.0 | -100.0 | G45T2 | 1 2 3 | 11 11 5
H/57-5 | SGBM15 | Sep 26 2015 6:00PM | Sep 30 2015 2:00PM | Sep 30 2015 3:12PM | Sep 30 2015 6:23PM | 52.026 | 46.375 | 46.75 28.35 | 0.00 0.00 | 0.349 | 51.677 | 46.026 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 10 10 10 7
H/24-1 | SGBM20 | Sep 29 2015 6:00PM | Sep 30 2015 12:15PM | Sep 30 2015 1:57PM | Sep 30 2015 3:50PM | 52.139 | 49.775 | 43.92 | 0.00 | 26.219 | 25.920 | 23.556 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 24.0 | -20.4 | G45T2 | 1 2 3 | 2 11 11
H/56-9 | SGBM17 | Sep 28 2015 3:00PM | Sep 29 2015 3:20PM | Sep 30 2015 11:30AM | Sep 30 2015 2:30PM | 51.982 | 46.875 | 46.75 | 0.00 | 3.852 | 48.130 | 43.023 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 11 3
X/32-3 | SGBM22 | Sep 29 2015 3:00PM | Sep 30 2015 8:45AM | Sep 30 2015 1:00PM | Sep 30 2015 2:20PM | 49.709 | 47.475 | 50.45 | 0.00 | 23.847 | 25.862 | 23.628 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 21.0 | -100.0 | G45T2 | 1 2 | 11 10
J/27-8 | SGBM20 | Sep 28 2015 8:00PM | Sep 29 2015 11:15AM | Sep 30 2015 1:57AM | Sep 30 2015 4:00AM | 51.375 | 48.825 | 43.11 | 0.00 | 27.008 | 24.367 | 21.817 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.9 | 28.0 | -100.0 | G45T2 | 1 2 3 | 11 9 8
H/58-11 | SGBM15 | Sep 26 2015 12:40PM | Sep 28 2015 10:10PM | Sep 29 2015 10:31PM | Sep 30 2015 2:58AM | 51.987 | 46.375 | 46.83 | 0.00 | 0.334 | 51.653 | 46.041 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 4 3 11 11 9 11
J/25-5 | SGBM20 | Sep 29 2015 1:00PM | Sep 29 2015 5:25PM | Sep 29 2015 9:36PM | Sep 29 2015 11:50PM | 52.262 | 47.325 | 53.05 | 0.00 | 23.554 | 23.708 | 23.771 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 25.0 | 21.4 | G45T2 | 1 2 3 4 | 3 9 9 4
Z/44-2 | SGBM03 | Sep 28 2015 4:45PM | Sep 29 2015 12:40PM | Sep 29 2015 7:45PM | Sep 29 2015 10:00PM | 49.698 | 46.925 | 42.50 22.50 | 0.00 0.00 | 17.698 | 32.000 | 29.227 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 34.0 | -25.3 | G45T2 | 1 2 3 4 | 6 9 11 8
K/30-2 | SGBM09 | Sep 29 2015 10:00AM | Sep 29 2015 2:45PM | Sep 29 2015 6:50PM | Sep 29 2015 9:30PM | 52.02 | 49.375 | 52.83 | 0.00 | 26.330 | 25.690 | 23.045 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 24.0 | -100.0 | G35T2 | 1 2 3 4 | 2 10 10 2
F/56-1 | SGBM15 | Sep 28 2015 8:00AM | Sep 28 2015 3:00PM | Sep 29 2015 1:24PM | Sep 29 2015 4:00PM | 52.941 | 49.775 | 52.74 | 0.00 | 5.739 | 47.202 | 44.036 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.1 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
J/25-16 | SGBM20 | Sep 28 2015 5:30PM | Sep 29 2015 11:45AM | Sep 29 2015 1:15AM | Sep 29 2015 3:00PM | 52.12 | 47.325 | 43.92 | 0.00 | 23.724 | 28.396 | 23.601 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 24.0 | -100.0 | G45T2 | c480009264 c170012756 c480009272 | 8 8 8
E/56-1 | SGBM23 | Sep 28 2015 8:00PM | Sep 29 2015 9:00AM | Sep 29 2015 11:53AM | Sep 29 2015 2:30PM | 51.955 | 49.775 | 52.80 | 0.00 | 6.702 | 45.253 | 43.073 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 43.0 | 15.3 | G45T2 | 1 2 3 4 5 | 5 9 9 9 11
Z/37-2 | SGBM21 | Sep 28 2015 1:00PM | Sep 29 2015 8:16AM | Sep 29 2015 11:25AM | Sep 29 2015 1:30PM | 49.7 | 46.925 | 50.55 | 0.00 | 18.448 | 31.252 | 28.477 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 7 11 11 3
S/36-1 | SGBM16 | Sep 28 2015 7:30PM | Sep 28 2015 10:55PM | Sep 29 2015 10:40AM | Sep 29 2015 12:45PM | 52.39 | 49.225 | 53.21 | 0.00 | 25.210 | 27.180 | 24.015 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 24.0 | -20.8 | G45T2 | 1 2 3 | 11 11 2
H/58-2 | SGBM15 | Sep 22 2015 1:50PM | Sep 28 2015 5:30PM | Sep 28 2015 9:53PM | Sep 29 2015 12:45AM | 52 | 46.375 | 46.84 20.84 | 0.00 0.00 | 0.337 | 51.663 | 46.038 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 11 6 12 11
J/31-1 | SGBM09 | Sep 26 2015 5:00PM | Sep 28 2015 6:00PM | Sep 28 2015 9:35PM | Sep 28 2015 10:50PM | 52.034 | 49.675 | 43.81 | 0.00 | 27.608 | 24.426 | 22.067 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 22.0 | -100.0 | G45T2 | c480009221 c480009222 | 11 11
J/28-4 | SGBM20 | Sep 26 2015 6:50PM | Sep 28 2015 5:15PM | Sep 28 2015 7:45PM | Sep 28 2015 9:30PM | 52.204 | 51.375 | 43.98 | 0.00 | 27.684 | 24.520 | 23.691 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 27.0 | -100.0 | G45T2 | c520121949 c480009217 c480009220 | 11 11 5
Y/42-1 | SGBM03 | Sep 26 2015 12:00PM | Sep 28 2015 8:17AM | Sep 28 2015 5:17PM | Sep 28 2015 7:00PM | 49.679 | 47.375 | 50.60 | 0.00 | 18.797 | 30.882 | 28.578 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.7 | 32.0 | -100.0 | G45T2 | 1 2 3 | 11 10 11
X/32-1 | SGBM19 | Sep 26 2015 4:00PM | Sep 28 2015 2:30PM | Sep 28 2015 4:48PM | Sep 28 2015 7:00PM | 49.659 | 47.475 | 50.61 | 0.00 | 24.312 | 25.347 | 23.163 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 22.0 | -100.0 | G45T2 | 1 2 3 | 2 9 11
Q/38-2 | SGBM16 | Sep 28 2015 9:00AM | Sep 28 2015 12:40PM | Sep 28 2015 3:32PM | Sep 28 2015 5:10PM | 52.573 | 49.575 | 53.17 | 0.00 | 25.668 | 26.905 | 23.907 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 24.0 | -20.7 | G45T2 | 1 2 3 | 4 11 9
J/25-14 |  | Sep 25 2015 5:00PM | Sep 26 2015 8:05PM | Sep 28 2015 1:50PM | Sep 28 2015 4:00PM | 52.171 | 47.325 | 43.95 23.45 | 0.00 0.00 | 23.451 | 28.720 | 23.874 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 27.0 | -100.0 | G45T2 | c480009189 c480009192 c480009195 | 11 9 7
D/52-1 | SGBM23 | Sep 26 2015 9:00PM | Sep 27 2015 12:58PM | Sep 27 2015 4:33PM | Sep 27 2015 6:10PM | 51.8 | 51.275 | 52.64 | 0.00 | 6.737 | 45.063 | 44.538 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.6 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
J/25-6 | SGBM20 | Sep 23 2015 1:00PM | Sep 26 2015 3:30PM | Sep 26 2015 7:25PM | Sep 26 2015 11:30PM | 52.344 | 47.325 | 44.12 | 0.00 | 23.724 | 28.620 | 23.601 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 25.0 | -100.0 | G45T2 | c170012739 c520121916 c520121920 | 10 10 5
K/31-2 | SGBM09 | Sep 26 2015 8:00AM | Sep 26 2015 6:30PM | Sep 26 2015 9:30PM | Sep 26 2015 11:15PM | 52.051 | 49.675 | 43.84 | 0.00 | 26.239 | 25.812 | 23.436 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 26.0 | -100.0 | G35T2 | c52012198 c520121919 c520121920 | 12 12 2
K/54-1 | SGBM17 | Sep 26 2015 8:00AM | Sep 26 2015 2:00PM | Sep 26 2015 7:00PM | Sep 26 2015 9:50PM | 52.116 | 51.025 | 53.03 | 0.00 | 13.926 | 38.190 | 37.099 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 41.0 | -100.0 | G45T2 | 1 2 3 4 | 12 12 10 7
J/53-1 | SGBM18 | Sep 26 2015 8:00AM | Sep 26 2015 3:00PM | Sep 26 2015 6:46PM | Sep 26 2015 9:00PM | 52.08 | 51.025 | 52.90 | 0.00 | 12.996 | 39.084 | 38.029 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.9 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 10 8
H/57-2 | SGBM17 | Sep 26 2015 8:00AM | Sep 26 2015 12:40PM | Sep 26 2015 4:14PM | Sep 26 2015 7:03PM | 51.96 | 46.375 | 52.80 | 0.00 | 0.298 | 51.662 | 46.077 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 53.0 | -100.0 | G45T2 | 1 2 3 4 5 6 | 8 11 9 10 8 7
J/27-4 | SGBM20 | Sep 25 2015 1:00PM | Sep 26 2015 11:55AM | Sep 26 2015 4:40PM | Sep 26 2015 6:35PM | 52.446 | 48.825 | 44.34 | 0.00 | 24.936 | 27.510 | 23.889 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 27.0 | -100.0 | G45T2 | c520121902 c520121995 c520121907 | 10 12 5
R/38-2 | SGBM16 | Sep 25 2015 5:35PM | Sep 26 2015 8:15AM | Sep 26 2015 3:30PM | Sep 26 2015 5:35PM | 52.822 | 49.575 | 45.74 24.74 | 0.00 0.00 | 24.443 | 28.379 | 25.132 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 25.0 | -100.0 | G45T2 | a1 a2 a3 | 11 11 3
W/45-2 | SGBM03 | Sep 22 2015 6:00PM | Sep 25 2015 12:00PM | Sep 26 2015 2:45PM | Sep 26 2015 5:00PM | 49.802 | 47.625 | 42.66 22.66 | 0.00 0.00 | 19.457 | 30.345 | 28.168 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 33.0 | 35.3 | G35T2 | c520121896 c520121892 c520121897 c520121902 | 11 10 10 2
Z/28-2 | SGBM19 | Sep 25 2015 1:00PM | Sep 26 2015 9:30AM | Sep 26 2015 2:27PM | Sep 26 2015 4:25PM | 49.996 | 48.575 | 50.84 | 0.00 | 24.541 | 25.455 | 24.034 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 33.0 | -100.0 | G45T2 | 1 2 3 | 11 11 11
F/58-1 | SGBM15 | Sep 25 2015 11:00AM | Sep 25 2015 6:00PM | Sep 25 2015 9:22PM | Sep 26 2015 12:20AM | 51.947 | 49.775 | 52.78 | 0.00 | 4.677 | 47.270 | 45.098 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.1 | 49.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 9 11 7 11
K/32-2 | SGBM09 | Sep 23 2015 1:00PM | Sep 25 2015 5:30PM | Sep 25 2015 9:00PM | Sep 25 2015 10:30PM | 52.309 | 49.325 | 43.90 | 0.00 | 29.604 | 22.705 | 19.721 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.1 | 16.0 | 1.7 | G45T2 | c520121871 c520121872 | 10 6
G/59-7 | SGBM18 | Sep 23 2015 4:00PM | Sep 25 2015 3:20PM | Sep 25 2015 7:30PM | Sep 25 2015 10:20PM | 52.01 | 49.875 | 46.83 30.83 10.03 | 0.00 0.00 0.00 | 4.826 | 47.184 | 45.049 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 45.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 12 8 8 7
J/28-7 | SGBM20 | Sep 23 2015 6:00PM | Sep 25 2015 1:10PM | Sep 25 2015 5:30PM | Sep 25 2015 8:00PM | 52.056 | 51.375 | 43.93 | 0.00 | 27.626 | 24.430 | 23.749 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 24.0 | -100.0 | G45T2 | c520121861 c520121860 c170012731 | 12 10 2
Y/44-3 | SGBM03 | Sep 22 2015 8:25PM | Sep 23 2015 2:20PM | Sep 25 2015 5:40PM | Sep 25 2015 7:40PM | 49.624 | 47.475 | 42.48 | 0.00 | 19.181 | 30.443 | 28.294 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 32.0 | -100.0 | G45T2 | 520121862 c520121865 c520121864 | 12 10 10
H/57-9 | SGBM15 | Sep 21 2015 5:50PM | Sep 25 2015 9:00AM | Sep 25 2015 3:20PM | Sep 25 2015 6:25PM | 51.975 | 46.375 | 46.79 29.59 3.79 | 0.00 0.00 0.00 | 0.286 | 51.689 | 46.089 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 12 10 10 6
X/58-1 | SGBM19 | Sep 23 2015 10:20AM | Sep 23 2015 5:23PM | Sep 23 2015 9:47PM | Sep 24 2015 12:00AM | 49.664 | 47.375 | 50.56 | 0.00 | 19.356 | 30.308 | 28.019 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 6 11 11 8
K/31-1 | SGBM09 | Sep 22 2015 6:00PM | Sep 23 2015 3:45PM | Sep 23 2015 7:10PM | Sep 23 2015 9:00PM | 52.02 | 49.675 | 43.83 | 0.00 | 26.230 | 25.790 | 23.445 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.3 | 26.0 | -100.0 | G35T2 | c480009129 c480009130 c480009136 | 9 11 6
J/25-13 | SGBM20 | Sep 22 2015 6:00PM | Sep 23 2015 8:30PM | Sep 23 2015 5:55PM | Sep 23 2015 7:30PM | 52.193 | 47.325 | 43.91 | 0.00 | 23.613 | 28.580 | 23.712 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 27.0 | 4.8 | G45T2 | c480009210 c480009121 c480009124 | 11 5 11
K/53-1 | SGBM18 | Sep 22 2015 5:00PM | Sep 23 2015 1:10PM | Sep 23 2015 4:30PM | Sep 23 2015 6:50PM | 52.148 | 51.025 | 52.97 | 0.00 | 13.973 | 38.175 | 37.052 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 3 11 11 11
Y/43-2 | SGBM21 | Sep 21 2015 7:00PM | Sep 22 2015 2:10PM | Sep 23 2015 5:35PM | Sep 23 2015 6:45PM | 49.667 | 47.375 | 42.27 34.27 | 0.00 0.00 | 19.167 | 30.500 | 28.208 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 28.0 | -100.0 | G45T2 | c480009116 c480009117 c480009121 | 11 11 6
Q/38-1 | SGBM16 | Sep 22 2015 6:00PM | Sep 23 2015 12:00PM | Sep 23 2015 2:30PM | Sep 23 2015 4:30PM | 52.573 | 49.575 | 45.17 | 0.00 | 25.668 | 26.905 | 23.907 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 24.0 | -100.0 | G45T2 | a1 a2 a3 | 2 11 11
Y/42-2 | SGBM03 | Sep 22 2015 1:50PM | Sep 22 2015 9:30PM | Sep 23 2015 2:05PM | Sep 23 2015 4:15PM | 49.657 | 47.375 | 42.53 | 0.00 | 19.331 | 30.326 | 28.044 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 33.0 | -100.0 | G45T2 | c480009101 c520121838 c520121839 | 11 10 12
J/25-8 | SGBM20 | Sep 22 2015 3:30PM | Sep 23 2015 10:05AM | Sep 23 2015 1:20PM | Sep 23 2015 3:05PM | 52.074 | 47.325 | 43.90 32.90 | 0.00 0.00 | 23.602 | 28.472 | 23.723 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 25.0 | -100.0 | G45T2 | c480009095 c480009099 c480009100 | 5 11 9
H/56-3 | SGBM15 | Sep 21 2015 5:10PM | Sep 22 2015 10:40PM | Sep 23 2015 11:12AM | Sep 23 2015 2:30PM | 52.02 | 46.875 | 46.67 33.57 | 0.00 0.00 | 3.865 | 48.155 | 43.010 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.2 | 44.0 | -100.0 | G45T2 | 1 2 3 4 5 | 5 11 11 11 6
R/38-1 | SGBM16 | Sep 22 2015 5:30PM | Sep 23 2015 8:45AM | Sep 23 2015 11:00AM | Sep 23 2015 12:45PM | 52.79 | 49.575 | 45.66 25.16 | 0.00 0.00 | 24.561 | 28.229 | 25.014 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.7 | 26.0 | -100.0 | G45T2 | a1 a2 a3 | 11 11 4
J/27-6 | SGBM20 | Sep 21 2015 7:30PM | Sep 22 2015 7:15PM | Sep 23 2015 12:30AM | Sep 23 2015 3:55AM | 52.074 | 48.825 | 43.80 | 0.00 | 25.002 | 27.072 | 23.823 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 26.5 | -100.0 | G45T2 | c480009072 c480009075 c480009082 | 10 11.5 5
H/58-14 | SGBM17 | Sep 22 2015 8:00AM | Sep 22 2015 2:00PM | Sep 22 2015 7:25PM | Sep 23 2015 12:15AM | 52 | 46.375 | 52.81 | 0.00 | 0.305 | 51.695 | 46.070 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 50.0 | -100.0 | G45T2 | 1 2 3 4 5 | 8 11 11 10 10
J/31-4 | SGBM20 | Sep 21 2015 5:00PM | Sep 22 2015 7:30PM | Sep 22 2015 11:30PM | Sep 23 2015 12:05AM | 52.02 | 49.675 | 43.76 | 0.00 | 27.664 | 24.356 | 22.011 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 23.0 | -100.0 | G45T2 | c480009069 c480009071 | 11.5 11.5
Z/28-1 | SGBM19 | Sep 22 2015 10:30AM | Sep 22 2015 3:05PM | Sep 22 2015 6:36PM | Sep 22 2015 8:30PM | 50.066 | 48.575 | 51.10 | 0.00 | 24.296 | 25.770 | 24.279 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 25.0 | -100.0 | G45T2 | 1 2 3 | 11 11 3
J/25-10 | SGBM20 | Sep 21 2015 12:00PM | Sep 22 2015 3:15PM | Sep 22 2015 3:20PM | Sep 22 2015 5:30PM | 52.105 | 47.325 | 43.82 | 0.00 | 23.616 | 28.489 | 23.709 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 27.0 | 4.8 | G45T2 | c480009035 c480009036 c480009038 | 4 11.5 11.5
Pb/35-1 | SGBM16 | Sep 21 2015 3:00PM | Sep 22 2015 1:00PM | Sep 22 2015 3:00PM | Sep 22 2015 5:00PM | 52.262 | 51.375 | 44.81 33.81 | 0.00 0.00 | 33.313 | 18.949 | 18.062 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 15.6 | 18.0 | 15.1 | G45T2 | a1 a2 | 11 7
K/57-3 | SGBM18 | Sep 21 2015 11:20AM | Sep 22 2015 11:20AM | Sep 22 2015 12:51PM | Sep 22 2015 3:50PM | 52.08 | 49.775 | 46.95 19.95 | 0.00 0.00 | 13.753 | 38.327 | 36.022 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.2 | 37.0 | -100.0 | G45T2 | 1 2 3 4 | 5 11 10 11
X/44-1 | SGBM03 | Sep 21 2015 10:45AM | Sep 21 2015 7:30PM | Sep 22 2015 1:00PM | Sep 22 2015 2:15PM | 49.626 | 47.475 | 42.33 | 0.00 | 18.226 | 31.400 | 29.249 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 33.0 | -100.0 | G45T2 | c480009020 c480009022 c480009024 | 11 11 11
Pb/36-1 | SGBM16 | Sep 19 2015 5:30PM | Sep 22 2015 8:30AM | Sep 22 2015 11:50AM | Sep 22 2015 2:00PM | 52.45 | 50.925 | 45.09 32.09 | 0.00 0.00 | 31.786 | 20.664 | 19.139 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 16.6 | 20.0 | 20.7 | G45T2 | a1 a2 | 11 9
H/57-3 | SGBM17 | Sep 19 2015 5:00PM | Sep 22 2015 8:30AM | Sep 22 2015 9:35AM | Sep 22 2015 12:30PM | 51.972 | 46.375 | 46.80 34.80 1.30 | 0.00 0.00 0.00 | 0.300 | 51.672 | 46.075 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 11 4
Z/27a-3 | SGBM19 | Sep 21 2015 1:00PM | Sep 21 2015 4:30PM | Sep 21 2015 10:35PM | Sep 22 2015 1:00AM | 50.091 | 49.075 | 50.82 | 0.00 | 27.319 | 22.772 | 21.756 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.8 | 19.0 | -100.0 | G45T2 | 1 2 | 9 10
J/54-1 | SGBM18 | Sep 21 2015 8:30AM | Sep 21 2015 3:00PM | Sep 21 2015 7:20PM | Sep 21 2015 10:50PM | 51.82 | 51.025 | 52.78 | 0.00 | 10.681 | 41.139 | 40.344 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.9 | 39.0 | -100.0 | G45T2 | 1 2 3 4 5 | 7 11 9 8 4
K/32-1 | SGBM09 | Sep 19 2015 6:20PM | Sep 21 2015 11:30AM | Sep 21 2015 9:45PM | Sep 21 2015 10:30PM | 52.005 | 49.325 | 43.74 | 0.00 | 29.944 | 22.061 | 19.381 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 16.8 | 15.0 | -100.0 | G45T2 | c520121802 c520121801 | 6 9
J/23-3 | SGBM20 | Sep 21 2015 1:00PM | Sep 21 2015 5:06PM | Sep 21 2015 6:11PM | Sep 21 2015 8:30PM | 52.426 | 49.775 | 44.31 | 0.00 | 26.786 | 25.640 | 22.989 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.9 | 25.0 | -19.9 | G45T2 | 1 2 3 | 10 11 4
Z/39-2 | SGBM03 | Sep 19 2015 3:00PM | Sep 21 2015 10:20AM | Sep 21 2015 5:00PM | Sep 21 2015 8:10PM | 49.741 | 47.025 | 42.38 21.77 | 0.00 0.00 | 17.875 | 31.866 | 29.150 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 33.0 | -100.0 | G45T2 | c480008970 c480008972 c480008975 c480008974 | 9 11 10 3
Qa/36-1 | SGBM16 | Sep 18 2015 4:00PM | Sep 21 2015 8:30AM | Sep 21 2015 2:00PM | Sep 21 2015 4:45PM | 52.525 | 50.925 | 45.05 30.05 | 0.00 0.00 | 29.746 | 22.779 | 21.179 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 22.8 | -100.0 | G45T2 | a1 a2 a3 | 11.8 10 1
J/28-6 | SGBM20 | Sep 18 2015 4:29PM | Sep 21 2015 11:35AM | Sep 21 2015 11:50AM | Sep 21 2015 2:00PM | 52.142 | 51.375 | 43.92 | 0.00 | 27.615 | 24.527 | 23.760 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 23.0 | 2.4 | G45T2 | c480008953 c480008949 c520121791 | 8 4 11
Z/27a-1 | SGBM22 | Sep 18 2015 7:00PM | Sep 21 2015 9:30AM | Sep 21 2015 11:43AM | Sep 21 2015 1:10PM | 50.079 | 49.075 | 42.93 | 0.00 | 27.434 | 22.645 | 21.641 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 18.0 | -100.0 | G45T2 | 1 2 | 11 7
G/59-8 | SGBM18 | Sep 19 2015 3:00PM | Sep 21 2015 8:20AM | Sep 21 2015 10:39AM | Sep 21 2015 1:00PM | 51.976 | 49.875 | 46.78 32.78 5.28 | 0.00 0.00 0.00 | 4.780 | 47.196 | 45.095 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.1 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 11 8 10 4
Z/28-3 | SGBM19 | Sep 19 2015 8:00AM | Sep 19 2015 12:17PM | Sep 19 2015 7:50PM | Sep 19 2015 10:00PM | 44.956 | 48.575 | 50.85 | 0.00 | 24.252 | 20.704 | 24.323 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 21.1 | 27.0 | -100.0 | G45T2 | 1 2 3 | 5 11 11
J/31-3 | SGBM20 | Sep 18 2015 5:30PM | Sep 19 2015 10:00AM | Sep 19 2015 4:20PM | Sep 19 2015 6:00PM | 51.985 | 49.675 | 43.74 29.74 | 0.00 0.00 | 27.537 | 24.448 | 22.138 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | -100.0 | G45T2 | c480008893 c480008889 | 11.5 10.5
Y/45-2 | SGBM03 | Sep 18 2015 10:29AM | Sep 19 2015 10:20AM | Sep 19 2015 3:25PM | Sep 19 2015 5:45PM | 49.836 | 47.075 | 42.71 28.71 21.71 | 0.00 0.00 0.00 | 17.805 | 32.031 | 29.270 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 35.0 | -100.0 | G45T2 | c480008881 c480008887 c480008890 c480008893 | 11 11.5 11.5 1
Qa/35-1 | SGBM16 | Sep 18 2015 5:00PM | Sep 19 2015 1:55PM | Sep 19 2015 2:00PM | Sep 19 2015 4:30PM | 52.324 | 51.375 | 45.35 | 0.00 | 31.352 | 20.972 | 20.023 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.3 | 22.0 | 26.9 | G45T2 | a1 a2 a3 | 11 3 8
J/27-5 | SGBM15 | Sep 18 2015 3:00PM | Sep 19 2015 9:50AM | Sep 19 2015 12:45PM | Sep 19 2015 2:30PM | 52.052 | 48.825 | 43.77 27.07 | 0.00 0.00 | 25.072 | 26.980 | 23.753 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 25.0 | -100.0 | G45T2 | c480008867 c480008871 c480008872 | 7 10 8
Z/38-2 | SGBM21 | Sep 18 2015 11:44AM | Sep 18 2015 9:15PM | Sep 19 2015 11:15AM | Sep 19 2015 1:45PM | 49.762 | 46.925 | 42.50 | 0.00 | 18.502 | 31.260 | 28.423 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.6 | 28.0 | -100.0 | G45T2 | c480008862 c480008860 c480008868 c480008867 | 10 6 9 3
H/57-10 | SGBM23 | Sep 15 2015 4:10PM | Sep 18 2015 9:50PM | Sep 19 2015 10:07AM | Sep 19 2015 1:00PM | 52.036 | 46.375 | 46.80 28.80 | 0.00 0.00 | 0.296 | 51.740 | 46.079 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 49.0 | -39.9 | G45T2 | 1 2 3 4 5 | 11 11 11 11 5
K/28-2 | SGBM20 | Sep 17 2015 5:57PM | Sep 18 2015 4:00PM | Sep 18 2015 10:10PM | Sep 19 2015 12:20AM | 53.528 | 50.775 | 45.33 | 0.00 | 28.335 | 25.193 | 22.440 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 28.0 | -19.4 | G35T2 | 1 2 3 | 9 10 9
Z/40a-2 | SGBM19 | Sep 17 2015 5:15PM | Sep 18 2015 10:55AM | Sep 18 2015 7:45PM | Sep 18 2015 11:00PM | 49.664 | 48.525 | 42.40 26.40 | 0.00 0.00 | 19.505 | -0.741 | 29.020 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.1 | 31.0 | 22.9 | G45T2 | c520121729 c520121731 c480008843 c520121736 | 10 10 8 3
H/58-3 | SGBM17 | Sep 15 2015 5:15PM | Sep 18 2015 4:30PM | Sep 18 2015 5:12PM | Sep 18 2015 8:30PM | 52.033 | 46.375 | 46.81 22.81 | 0.00 0.00 | 0.309 | 51.724 | 46.066 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.9 | 56.0 | -39.9 | G45T2 | 1 2 3 4 5 6 | 7 11 9 12 11 6
J/25-9 | SGBM20 | Sep 15 2015 2:20PM | Sep 18 2015 11:20AM | Sep 18 2015 12:20PM | Sep 18 2015 1:51PM | 52.106 | 47.325 | 43.81 | 0.00 | 23.708 | 28.398 | 23.617 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 28.0 | -20.4 | G45T2 | 1 2 3 | 9 10 9
H/56-1 | SGBM18 | Sep 15 2015 11:20AM | Sep 18 2015 9:00AM | Sep 18 2015 10:31AM | Sep 18 2015 1:10PM | 52.007 | 46.875 | 46.85 5.85 | 0.00 0.00 | 3.847 | 48.160 | 43.028 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 44.0 | -37.3 | G45T2 | 1 2 3 4 | 11 11 11 11
X/44-3 | SGBM21 | Sep 15 2015 6:30PM | Sep 17 2015 4:55PM | Sep 18 2015 9:25AM | Sep 18 2015 10:50AM | 49.627 | 47.475 | 42.53 34.53 32.53 | 0.00 0.00 0.00 | 18.229 | 31.398 | 29.246 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 33.0 | -100.0 | G45T2 | c480008797 c480008798 c480008799 | 11 11 11
W/45-1 | SGBM21 | Sep 14 2015 6:30PM | Sep 17 2015 10:30AM | Sep 17 2015 8:10PM | Sep 17 2015 10:30PM | 49.726 | 47.625 | 42.57 34.57 26.57 | 0.00 0.00 4.00 | 19.570 | 30.156 | 28.055 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 42.0 | -24.3 | G35T2 | c170012622 c480008781 c480008783 c480008788 | 12 12 12 6
J/25-12 | SGBM20 | Sep 17 2015 8:00AM | Sep 17 2015 4:00PM | Sep 17 2015 7:38PM | Sep 17 2015 9:30PM | 52.03 | 47.325 | 43.75 | 0.00 | 24.268 | 27.762 | 23.057 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 27.0 | -20.0 | G45T2 | 1 2 3 | 12 10 5
K/58-3 | SGBM23 | Sep 14 2015 9:30AM | Sep 17 2015 10:40AM | Sep 17 2015 6:17PM | Sep 17 2015 8:45PM | 52.042 | 49.775 | 46.90 22.90 | 0.00 0.00 | 12.697 | 39.345 | 37.078 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 41.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 8
V/24-2 | SGBM16 | Sep 16 2015 1:30PM | Sep 17 2015 10:42AM | Sep 17 2015 3:37PM | Sep 17 2015 5:10PM | 49.725 | 47.375 | 50.39 | 0.00 | 27.294 | 22.431 | 20.081 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 17.4 | 22.0 | -100.0 | G35T2 | 1 2 3 | 9 11 2
Z/39-1 | SGBM03 | Sep 15 2015 11:30AM | Sep 17 2015 10:05AM | Sep 17 2015 2:15PM | Sep 17 2015 4:40PM | 49.716 | 47.025 | 42.45 21.45 | 0.00 0.00 | 17.952 | 31.764 | 29.073 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 32.0 | -100.0 | G45T2 | c170012605 c480008762 c480008763 c480008767 | 10 9 11 2
J/28-5 | SGBM20 | Sep 15 2015 2:00PM | Sep 17 2015 11:00AM | Sep 17 2015 12:48PM | Sep 17 2015 2:30PM | 52.116 | 51.375 | 43.85 | 0.00 | 27.746 | 24.370 | 23.629 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 26.0 | -20.5 | G45T2 | 1 2 3 | 5 11 10
K/56-3 | SGBM18 | Sep 14 2015 6:00PM | Sep 17 2015 9:20AM | Sep 17 2015 11:14AM | Sep 17 2015 1:50PM | 52.107 | 49.175 | 46.93 16.93 | 0.00 0.00 | 12.133 | 39.974 | 37.042 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 39.0 | -32.1 | G45T2 | 1 2 3 4 | 11 11 11 6
H/56-11 | SGBM23 | Sep 14 2015 11:20AM | Sep 15 2015 7:00PM | Sep 15 2015 9:50PM | Sep 16 2015 1:50AM | 51.894 | 46.875 | 46.67 | 0.00 | 3.874 | 48.020 | 43.001 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.2 | 47.5 | 27.6 | G45T2 | 1 2 3 4 5 | 8.5 12 9 10 8
K/60-1 | SGBM15 | Sep 15 2015 8:00AM | Sep 15 2015 1:00PM | Sep 15 2015 8:22PM | Sep 15 2015 11:30PM | 52.028 | 49.475 | 52.79 | 0.00 | 9.389 | 42.639 | 40.086 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 34.7 | 42.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 4 11 5
K/29-1 | SGBM20 | Sep 15 2015 11:00AM | Sep 15 2015 3:30PM | Sep 15 2015 8:00PM | Sep 15 2015 11:00PM | 53.501 | 49.375 | 45.23 | 0.00 | 26.967 | 26.534 | 22.408 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 25.5 | -19.4 | G35T2 | 1 2 3 | 10 12 3.5
Y/45-1 | SGBM19 | Sep 14 2015 5:05PM | Sep 15 2015 2:05PM | Sep 15 2015 4:30PM | Sep 15 2015 6:30PM | 49.674 | 47.075 | 42.63 29.63 | 0.00 0.00 | 17.831 | 31.843 | 29.244 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 31.0 | -25.3 | G45T2 | c480008662 c480008665 c480008668 | 11 11 9
H/57-1 | SGBM17 | Sep 14 2015 10:30AM | Sep 15 2015 12:40PM | Sep 15 2015 2:54PM | Sep 15 2015 6:00PM | 51.978 | 46.375 | 46.76 12.76 | 0.00 0.00 | 0.363 | 51.615 | 46.012 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.8 | 55.0 | -100.0 | G45T2 | 1 2 3 4 5 | 11 11 11 11 11
J/24-1 | SGBM15 | Sep 14 2015 3:00PM | Sep 15 2015 1:00PM | Sep 15 2015 1:45PM | Sep 15 2015 4:30PM | 52.304 | 49.775 | 44.08 | 0.00 | 26.085 | 26.219 | 23.690 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 25.0 | -100.0 | G45T2 | c480008651 c480008653 c480008654 | 11 3 11
K/59-3 | SGBM23 | Sep 14 2015 8:40AM | Sep 15 2015 9:20AM | Sep 15 2015 1:00PM | Sep 15 2015 3:45PM | 51.82 | 49.775 | 46.78 11.28 | 0.00 0.00 | 10.681 | 41.139 | 39.094 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.9 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 8 10
Z/36-1 | SGBM03 | Sep 14 2015 4:15PM | Sep 15 2015 10:15AM | Sep 15 2015 11:45AM | Sep 15 2015 3:00PM | 49.782 | 46.925 | 42.62 25.62 | 0.00 0.00 | 20.120 | 29.662 | 26.805 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 23.2 | 33.0 | 13.8 | G45T2 | c520121613 c520121614 c480008648 c480008653 | 4 10 11 8
G/59-6 | SGBM18 | Sep 12 2015 8:50AM | Sep 15 2015 8:15AM | Sep 15 2015 10:30AM | Sep 15 2015 1:00PM | 51.967 | 49.875 | 46.80 5.20 | 0.00 0.00 | 4.801 | 47.166 | 45.074 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 45.0 | -100.0 | G35T2 | 1 2 3 4 5 | 8 11 9 11 6
F/60-2 | SGBM17 | Sep 10 2015 10:50AM | Sep 14 2015 10:40AM | Sep 14 2015 3:35PM | Sep 14 2015 6:35PM | 51.985 | 49.675 | 46.83 32.83 10.83 | 0.00 0.00 0.00 | 5.625 | 46.360 | 44.050 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.1 | 51.0 | -100.0 | G45T2 | 1 2 3 4 5 | 10 12 11 9 9
J/23-2 | SGBM15 | Sep 12 2015 3:35PM | Sep 14 2015 12:00PM | Sep 14 2015 3:25PM | Sep 14 2015 6:10PM | 52.193 | 49.775 | 43.91 | 0.00 | 25.911 | 26.282 | 23.864 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 27.0 | 32.3 | G45T2 | c480008603 c5290121597 c480008611 c520121603 | 3 10 11 3
Y/44-2 | SGBM03 | Sep 12 2015 6:00PM | Sep 14 2015 8:19AM | Sep 14 2015 2:40PM | Sep 14 2015 5:00PM | 49.654 | 47.475 | 50.62 | 0.00 | 19.219 | 30.435 | 28.256 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 34.0 | -100.0 | G45T2 | 1 2 3 4 | 8 10 10 6
H/21-3 | SGBM20 | Sep 12 2015 4:30PM | Sep 14 2015 10:30AM | Sep 14 2015 12:50PM | Sep 14 2015 4:00PM | 53.582 | 49.775 | 45.38 32.38 | 0.00 0.00 | 24.177 | 29.405 | 25.598 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.2 | 26.0 | -100.0 | G45T2 | c480008594 c520121591 c480008602 | 11 12 3
E/56-2 | SGBM23 | Sep 10 2015 1:20PM | Sep 14 2015 9:10AM | Sep 14 2015 11:53AM | Sep 14 2015 2:20PM | 52.01 | 49.775 | 43.80 14.80 | 0.00 0.00 | 6.701 | 45.309 | 43.074 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 48.0 | -100.0 | G45T2 | 1 2 3 4 5 | 9 11 9 8 11
Y/41-2 | SGBM03 | Sep 13 2015 2:30PM | Sep 14 2015 8:18AM | Sep 14 2015 10:40AM | Sep 14 2015 12:00PM | 49.625 | 47.375 | 50.51 | 0.00 | 19.211 | 30.414 | 28.164 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 31.0 | -100.0 | G45T2 | 1 2 3 | 11 9 11
K/28-1 | SGBM20 | Sep 11 2015 3:00PM | Sep 12 2015 3:20PM | Sep 12 2015 6:00PM | Sep 12 2015 8:00PM | 53.492 | 50.775 | 45.20 | 0.00 | 28.504 | 24.988 | 22.271 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 24.0 | -100.0 | G35T2 | c520121566 c520121567 c520121568 | 7 11 6
K/57-2 | SGBM23 | Sep 11 2015 9:50AM | Sep 12 2015 10:20AM | Sep 12 2015 4:05PM | Sep 12 2015 6:30PM | 52.163 | 49.775 | 46.95 18.95 | 0.00 0.00 | 13.753 | 38.410 | 36.022 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 31.2 | 33.0 | -100.0 | G45T2 | 1 2 3 4 | 11 9 11 2
Z/36-2 | SGBM21 | Sep 11 2015 12:05PM | Sep 12 2015 11:45AM | Sep 12 2015 2:20PM | Sep 12 2015 4:05PM | 49.798 | 46.925 | 42.62 25.62 | 0.00 0.00 | 20.520 | 29.278 | 26.405 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.9 | 29.0 | -100.0 | G45T2 | c520121549 c520121550 c480008512 | 9 9 11
J/24-2 | SGBM15 | Sep 11 2015 10:30AM | Sep 12 2015 11:35AM | Sep 12 2015 1:25PM | Sep 12 2015 3:00PM | 52.115 | 49.775 | 44.01 | 0.00 | 26.215 | 26.046 | 23.560 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 24.0 | 17.6 | G45T2 | c520121544 c5201211546 c520121545 | 9 10 5
X/44-2 | SGBM19 | Sep 11 2015 2:15PM | Sep 12 2015 10:50AM | Sep 12 2015 11:50AM | Sep 12 2015 1:20PM | 49.671 | 47.475 | 42.47 23.47 | 0.00 0.00 | 18.372 | 31.299 | 29.103 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 33.0 | -100.0 | G45T2 | c480008497 c480008498 c480008499 | 11 11 11
K/59-2 | SGBM18 | Sep 10 2015 2:10PM | Sep 12 2015 9:00AM | Sep 12 2015 10:42AM | Sep 12 2015 12:31PM | 51.713 | 49.775 | 46.82 28.82 12.82 | 0.00 0.00 0.00 | 10.722 | 40.991 | 39.053 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.8 | 40.0 | -100.0 | G45T2 | 1 2 3 4 | 10 8 11 11
V/25-2 | SGBM16 | Sep 10 2015 4:00PM | Sep 11 2015 10:15AM | Sep 11 2015 8:50PM | Sep 11 2015 10:25PM | 49.909 | 47.075 | 41.71 29.71 | 0.00 0.00 | 26.514 | 23.395 | 20.561 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 17.8 | 21.0 | -100.0 | G35T2 | 1 2 3 | 3 11 7
K/21-2 | SGBM20 | Sep 10 2015 6:00PM | Sep 11 2015 5:00PM | Sep 11 2015 8:00PM | Sep 11 2015 9:30PM | 53.512 | 51.075 | 45.21 | 0.00 | 29.109 | 24.403 | 21.966 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.0 | 23.0 | -100.0 | G35T2 | c170012577 c480008473 c480008475 | 8 11 4
E/57-3 | SGBM17 | Sep 10 2015 11:20AM | Sep 11 2015 3:30PM | Sep 11 2015 6:40PM | Sep 11 2015 9:11PM | 51.996 | 49.775 | 46.78 18.78 | 0.00 0.00 | 6.677 | 45.319 | 43.098 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 44.0 | -100.0 | G35T2 | 1 2 3 4 | 11 11 11 11
X/42-2 | SGBM19 | Sep 10 2015 3:05PM | Sep 11 2015 1:55PM | Sep 11 2015 3:50PM | Sep 11 2015 6:00PM | 49.682 | 47.375 | 42.65 30.65 | 0.00 0.00 | 18.154 | 31.528 | 29.221 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.3 | 34.0 | -100.0 | G45T2 | c170012573 c170012574 c480008455 c520121524 | 10 3 11 10
H/21-1 | SGBM20 | Sep 10 2015 3:35PM | Sep 11 2015 3:15PM | Sep 11 2015 3:25PM | Sep 11 2015 5:00PM | 53.73 | 49.775 | 45.27 | 0.00 | 23.968 | 29.762 | 25.807 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.3 | 28.0 | -100.0 | G45T2 | c480008448 hx043 c170012574 | 11 11 6
W/41-1 | SGBM03 | Sep 10 2015 2:10PM | Sep 11 2015 11:05AM | Sep 11 2015 12:30PM | Sep 11 2015 2:05PM | 49.432 | 46.925 | 42.40 23.40 | 0.00 0.00 | 15.798 | 33.634 | 31.127 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.0 | 30.0 | -100.0 | G35T2 | c170012572 c480008441 c480008442 | 8 11 11
J/23-1 | SGBM20 | Sep 10 2015 8:30AM | Sep 11 2015 11:00AM | Sep 11 2015 11:50AM | Sep 11 2015 1:05PM | 53.481 | 49.775 | 45.21 | 0.00 | 26.214 | 27.267 | 23.561 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 27.0 | -20.4 | G45T2 | 1 2 3 | 11 10 6
U/24-1 | SGBM16 | Sep 10 2015 3:30PM | Sep 11 2015 9:30AM | Sep 11 2015 10:40AM | Sep 11 2015 12:10PM | 49.615 | 49.075 | 50.61 | 0.00 | 27.212 | 22.403 | 21.863 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.9 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
Y/36-1 | SGBM21 | Sep 9 2015 10:55AM | Sep 10 2015 11:30AM | Sep 10 2015 7:50PM | Sep 10 2015 10:10PM | 49.079 | 47.475 | 41.56 25.56 | 0.00 0.00 | 21.160 | 27.919 | 26.315 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.8 | 32.0 | -100.0 | G45T2 | c520121497 c480008387 c520121500 | 10 11 11
J/21-1 | SGBM20 | Sep 9 2015 1:00PM | Sep 10 2015 4:30PM | Sep 10 2015 6:50PM | Sep 10 2015 9:59PM | 53.505 | 51.075 | 45.26 | 0.00 | 25.358 | 28.147 | 25.717 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.3 | 29.0 | -100.0 | G45T2 | c480008377 c520121495 c480008380 c480008382 | 7 9 9 4
K/56-2 | SGBM17 | Sep 9 2015 9:40AM | Sep 10 2015 4:05PM | Sep 10 2015 5:40PM | Sep 10 2015 8:00PM | 52.086 | 49.175 | 46.87 24.87 | 0.00 0.00 | 12.171 | 39.915 | 37.004 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.0 | 37.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 4
H/24-2 | SGBM15 | Sep 10 2015 8:00AM | Sep 10 2015 4:30PM | Sep 10 2015 4:30PM | Sep 10 2015 7:00PM | 52.174 | 49.775 | 43.93 | 0.00 | 25.934 | 26.240 | 23.841 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 25.0 | -100.0 | G45T2 | c480008363 c480008363 c480008369 | 6 11 8
W/25-2 | SGBM18 | Sep 9 2015 10:30AM | Sep 10 2015 10:30AM | Sep 10 2015 3:40PM | Sep 10 2015 5:39PM | 49.743 | 47.375 | 41.79 34.39 | 0.00 0.00 | 26.847 | 22.896 | 20.528 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 17.8 | 22.0 | -100.0 | G35T2 | 1 2 3 | 6 11 5
L/21-2 | SGBM20 | Sep 9 2015 8:00AM | Sep 10 2015 11:00AM | Sep 10 2015 1:40PM | Sep 10 2015 4:00PM | 53.482 | 50.775 | 45.30 | 0.00 | 29.003 | 24.479 | 21.772 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.9 | 22.0 | -18.9 | G35T2 | 1 2 | 11 11
K/58-2 | SGBM23 | Sep 9 2015 10:40AM | Sep 10 2015 10:30AM | Sep 10 2015 11:45AM | Sep 10 2015 2:20PM | 51.838 | 49.775 | 46.86 17.86 | 0.00 0.00 | 12.758 | 39.080 | 37.017 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 43.0 | -100.0 | G45T2 | 1 2 3 4 5 | 3 11 11 11 7
Y/44-1 | SGBM03 | Sep 9 2015 11:50AM | Sep 9 2015 8:15PM | Sep 10 2015 11:00AM | Sep 10 2015 12:30PM | 49.72 | 47.475 | 42.61 | 0.00 | 19.408 | 30.312 | 28.067 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.3 | 30.0 | -100.0 | G45T2 | c480008331 c480008332 c480008335 | 11 11 8
J/24-3 | SGBM15 | Sep 9 2015 9:00AM | Sep 9 2015 4:45PM | Sep 9 2015 6:30PM | Sep 9 2015 8:55PM | 51.093 | 49.775 | 42.85 | 0.00 | 26.252 | 24.841 | 23.523 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 29.0 | -100.0 | G45T2 | c480008302 c480008306 c480008309 | 9 10 10
K/21-1 | SGBM20 | Sep 9 2015 8:00AM | Sep 9 2015 3:30PM | Sep 9 2015 5:40PM | Sep 9 2015 7:17PM | 53.43 | 51.075 | 45.23 | 0.00 | 30.322 | 23.108 | 20.753 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.0 | 24.0 | -100.0 | G35T2 | 1 2 3 | 11 11 2
F/60-3 | SGBM17 | Aug 24 2015 4:10PM | Sep 9 2015 11:15AM | Sep 9 2015 2:40PM | Sep 9 2015 6:30PM | 51.973 | 49.675 | 47.87 23.87 | 0.00 0.00 | 5.673 | 46.300 | 44.002 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.1 | 47.0 | -100.0 | G45T2 | 1 2 3 4 5 | 4 12 12 11 8
Y/41-1 | SGBM03 | Sep 8 2015 4:10PM | Sep 9 2015 1:15PM | Sep 9 2015 1:30PM | Sep 9 2015 3:35PM | 49.62 | 47.375 | 42.66 34.66 | 0.00 0.00 | 19.160 | 30.460 | 28.215 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.4 | 30.0 | 22.8 | G45T2 | c480008274 c480008275 c480008277 | 10 12 8
V/30-2 | SGBM16 | Aug 20 2015 1:30PM | Sep 9 2015 10:30AM | Sep 9 2015 1:16PM | Sep 9 2015 2:55PM | 49.74 | 47.075 | 41.52 33.72 | 0.00 0.00 | 25.708 | 24.032 | 21.367 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.5 | 25.0 | -100.0 | G35T2 | 1 2 3 | 11 12 2
G/59-5 | SGBM23 | Aug 25 2015 8:50AM | Sep 8 2015 5:40PM | Sep 8 2015 7:30PM | Sep 8 2015 11:00PM | 52.009 | 49.875 | 46.80 22.80 | 0.00 0.00 | 4.797 | 47.212 | 45.078 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 51.0 | -100.0 | G35T2 | 1 2 3 4 5 | 6 12 12 12 9
H/21-2 | SGBM20 | Aug 25 2015 5:00PM | Sep 8 2015 3:00PM | Sep 8 2015 4:20PM | Sep 8 2015 7:00PM | 53.607 | 49.775 | 45.43 | 0.00 | 24.427 | 29.180 | 25.348 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.0 | 30.0 | -21.9 | G45T2 | 1 2 3 4 | 4 11 10 5
W/24-2 | SGBM16 | Sep 5 2015 9:30AM | Sep 7 2015 1:00PM | Sep 7 2015 4:40PM | Sep 7 2015 7:30PM | 49.676 | 47.375 | 41.53 | 0.00 | 26.576 | 23.100 | 20.799 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.0 | 25.0 | -100.0 | G35T2 | 1 2 3 | 10 10 5
E/59-2 | SGBM17 | Aug 22 2015 3:00PM | Aug 24 2015 6:55PM | Aug 25 2015 10:45PM | Aug 26 2015 1:40AM | 51.894 | 49.775 | 46.62 34.62 | 0.00 0.00 | 6.724 | 45.170 | 43.051 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 44.0 | -100.0 | G35T2 | 7605 7606 7610 7617 | 11 11 11 11
U/23-1 | SGBM18 | Aug 24 2015 2:00PM | Aug 25 2015 12:30PM | Aug 25 2015 11:00PM | Aug 26 2015 1:20AM | 49.821 | 49.075 | 50.64 | 0.00 | 27.643 | 22.178 | 21.432 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.6 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
E/57-2 | SGBM23 | Aug 24 2015 2:30PM | Aug 25 2015 2:00PM | Aug 25 2015 10:23PM | Aug 26 2015 1:00AM | 51.978 | 49.775 | 43.77 29.77 | 0.00 0.00 | 6.773 | 45.205 | 43.002 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.2 | 50.0 | -100.0 | G35T2 | 1 2 3 4 5 | 8 11 11 10 10
W/41-2 | SGBM19 | Aug 24 2015 5:15PM | Aug 25 2015 3:30PM | Aug 25 2015 6:55PM | Aug 25 2015 10:05PM | 49.387 | 46.925 | 42.31 38.31 | 0.00 0.00 | 15.606 | 33.781 | 31.319 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 27.1 | 36.0 | 32.7 | G35T2 | c480007587 c480007589 c480007594 c480007599 | 11 11 11 3
J/21-2 | SGBM20 | Aug 24 2015 8:00PM | Aug 25 2015 12:20PM | Aug 25 2015 1:43PM | Aug 25 2015 3:30PM | 53.489 | 51.075 | 45.26 41.76 | 0.00 0.00 | 25.056 | 28.433 | 26.019 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.5 | 25.0 | -22.5 | G45T2 | 1 2 3 | 10 8 7
X/42-1 | SGBM03 | Aug 24 2015 5:15PM | Aug 25 2015 8:20AM | Aug 25 2015 11:40AM | Aug 25 2015 1:56PM | 49.689 | 47.375 | 50.55 | 0.00 | 18.049 | 31.640 | 29.326 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.4 | 32.0 | -100.0 | G45T2 | 1 2 3 4 | 8 9 10 5
L/21-1 | SGBM20 | Aug 24 2015 3:00PM | Aug 24 2015 8:00PM | Aug 25 2015 10:09AM | Aug 25 2015 11:30AM | 53.511 | 50.775 | 45.25 | 0.00 | 29.895 | 23.616 | 20.880 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.1 | 23.0 | -100.0 | G35T2 | 1 2 3 | 10 9 4
Z/39-3 | SGBM03 | Aug 24 2015 9:55AM | Aug 24 2015 8:00PM | Aug 25 2015 9:15AM | Aug 25 2015 11:05AM | 49.689 | 47.025 | 42.55 | 0.00 | 17.949 | 31.740 | 29.076 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.2 | 31.0 | 23.1 | G45T2 | c480007553 c480007554 c520121165 | 11 11 9
K/57-1 | SGBM23 | Aug 21 2015 3:40PM | Aug 24 2015 8:15AM | Aug 24 2015 7:07PM | Aug 24 2015 10:45PM | 52.214 | 49.775 | 46.92 24.92 13.72 | 0.00 0.00 0.00 | 13.615 | 38.599 | 36.160 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12+12+12+7.4 | - | 31.3 | 41.0 | -100.0 | G45T2 | 1161 1162 1163 1164 | 10 11 10 10
L/26-2 | SGBM15 | Aug 24 2015 8:00AM | Aug 24 2015 4:00PM | Aug 24 2015 6:10PM | Aug 24 2015 7:15PM | 53.45 | 50.475 | 45.28 | 0.00 | 31.180 | 22.270 | 19.295 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 16.7 | 17.0 | -100.0 | G45T2 | c520121157 c520121159 | 11 6
V/23-2 | SGBM18 | Aug 22 2015 5:30PM | Aug 24 2015 10:30AM | Aug 24 2015 3:25PM | Aug 24 2015 4:40PM | 49.745 | 47.375 | 50.46 | 0.00 | 26.156 | 23.589 | 21.219 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.4 | 21.0 | -100.0 | G35T2 | 1 2 | 11 10
K/24-1 | SGBM20 | Aug 22 2015 7:10PM | Aug 23 2015 2:15PM | Aug 24 2015 2:42PM | Aug 24 2015 3:40PM | 53.469 | 51.075 | 45.29 | 0.00 | 28.789 | 24.680 | 22.286 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 23.0 | -19.3 | G35T2 | 1 2 3 | 11 10 2
Y/36-3 | SGBM03 | Aug 22 2015 9:42AM | Aug 24 2015 8:52AM | Aug 24 2015 10:20AM | Aug 24 2015 11:25AM | 49.67 | 47.475 | 42.57 40.07 21.47 | 0.00 0.00 0.00 | 21.374 | 28.296 | 26.101 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.6 | 29.0 | -100.0 | G45T2 | c520121135 c520121136 c170012423 | 11 11 7
W/26-2 | SGBM16 | Aug 22 2015 8:00AM | Aug 22 2015 1:00PM | Aug 22 2015 4:45PM | Aug 22 2015 6:30PM | 49.643 | 47.375 | 50.63 | 0.00 | 25.125 | 24.518 | 22.250 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 22.0 | -100.0 | G35T2 | 1 2 3 | 4 11 7
Z/35-1 | SGBM03 | Aug 21 2015 4:48PM | Aug 22 2015 2:00PM | Aug 22 2015 2:55PM | Aug 22 2015 4:40PM | 49.824 | 48.625 | 42.74 35.74 | 0.00 0.00 | 22.845 | 26.979 | 25.780 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.3 | 27.0 | 4.7 | G45T2 | c480007435 c520121124 c520121123 | 12 10 5
E/58-2 | SGBM17 | Aug 20 2015 2:00PM | Aug 22 2015 8:45AM | Aug 22 2015 11:30AM | Aug 22 2015 1:40PM | 51.491 | 49.775 | 40.00 31.00 2.00 | 0.00 0.00 0.00 | 0.000 | 51.491 | 49.775 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 43.1 | 44.0 | 2.1 | G35T2 | 1116 1117 0039 7426 | 11 11 10 12
U/26-1 | SGBM18 | Aug 21 2015 6:00PM | Aug 22 2015 9:30AM | Aug 22 2015 11:00AM | Aug 22 2015 12:15PM | 52.197 | 51.375 | 53.09 | 0.00 | 30.687 | 21.510 | 20.688 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 17.9 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
Y/39-1 | SGBM03 | Aug 21 2015 8:05AM | Aug 21 2015 5:55PM | Aug 22 2015 9:15AM | Aug 22 2015 10:50AM | 49.696 | 47.375 | 42.53 | 0.00 | 17.330 | 32.366 | 30.045 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 26.0 | 33.0 | 26.8 | G45T2 | c480007417 c480007418 c480007420 | 11 11 11
U/29-1 | SGBM18 | Aug 20 2015 2:30PM | Aug 21 2015 11:00AM | Aug 21 2015 9:00PM | Aug 21 2015 11:00PM | 51.851 | 51.375 | 52.76 | 0.00 | 30.159 | 21.692 | 21.216 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.4 | 21.0 | -100.0 | G45T2 | 1 2 | 11 10
V/31-2 | SGBM16 | Aug 20 2015 3:00PM | Aug 21 2015 9:00AM | Aug 21 2015 9:18PM | Aug 21 2015 11:00PM | 49.751 | 47.075 | 50.71 | 0.00 | 24.713 | 25.038 | 22.362 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 9 | - | 19.4 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
Z/38-1 | SGBM19 | Aug 20 2015 3:45PM | Aug 21 2015 4:25PM | Aug 21 2015 6:30PM | Aug 21 2015 9:00PM | 49.724 | 46.925 | 42.73 | 0.00 | 18.534 | 31.190 | 28.391 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 24.6 | 33.0 | -100.0 | G45T2 | c480007392 c480007395 c480007398 | 11 11 11
G/59-4 | SGBM23 | Aug 18 2015 8:10AM | Aug 21 2015 8:50AM | Aug 21 2015 10:40AM | Aug 21 2015 1:10PM | 51.976 | 49.875 | 46.82 6.82 | 0.00 0.00 | 4.824 | 47.152 | 45.051 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 43.0 | -39.0 | G35T2 | 1 2 3 4 | 10 11 11 11
Y/36-2 | SGBM03 | Aug 20 2015 10:40AM | Aug 20 2015 7:20PM | Aug 21 2015 9:30AM | Aug 21 2015 11:15AM | 49.602 | 47.475 | 50.71 | 8.00 | 21.208 | 28.394 | 26.267 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.7 | 27.0 | -100.0 | G45T2 | c170012413 c170012414 c170012415 | 10 8 9
K/59-1 | SGBM17 | Aug 18 2015 5:18PM | Aug 19 2015 6:30PM | Aug 20 2015 4:00PM | Aug 20 2015 6:30PM | 52.193 | 49.775 | 45.94 | 0.00 | 10.741 | 41.452 | 39.034 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 33.8 | 44.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 11
L/27-2 | SGBM20 | Aug 19 2015 5:30PM | Aug 20 2015 11:33AM | Aug 20 2015 4:51PM | Aug 20 2015 6:00PM | 53.443 | 50.475 | 45.17 | 0.00 | 31.166 | 22.277 | 19.309 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 16.7 | 16.0 | -0.7 | G45T2 | C480007356 C480007357 | 10 6
U/28-1 | SGBM16 | Aug 19 2015 4:00PM | Aug 20 2015 11:30AM | Aug 20 2015 2:20PM | Aug 20 2015 4:20PM | 51.942 | 51.375 | 52.79 | 0.00 | 29.794 | 22.148 | 21.581 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 22.0 | -100.0 | G45T2 | 1 2 | 11 11
K/23-2 | SGBM20 | Aug 19 2015 4:30PM | Aug 20 2015 1:00PM | Aug 20 2015 3:07PM | Aug 20 2015 4:09PM | 53.481 | 51.075 | 45.20 | 0.00 | 28.801 | 24.680 | 22.274 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 22.0 | 14.0 | G35T2 | C480007348 C480007350 | 11 11
U/30-1 | SGBM18 | Aug 20 2015 8:00AM | Aug 20 2015 11:14AM | Aug 20 2015 12:10PM | Aug 20 2015 2:00PM | 51.892 | 51.375 | 52.96 | 0.00 | 29.358 | 22.534 | 22.017 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 21.0 | -100.0 | G45T2 | 1 2 | 11 10
X/37-1 | SGBM19 | Aug 18 2015 5:15PM | Aug 19 2015 3:00PM | Aug 20 2015 11:20AM | Aug 20 2015 12:45PM | 49.535 | 47.475 | 42.43 | 0.00 | 20.327 | 30.100 | 27.148 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.5 | 30.0 | -100.0 | G35T2 | c480007331 c480007332 c480007333 | 11 11 8
V/29-2 | SGBM16 | Aug 19 2015 10:30AM | Aug 19 2015 4:00PM | Aug 19 2015 5:25PM | Aug 19 2015 7:30PM | 49.791 | 47.075 | 41.74 | 0.00 | 25.483 | 24.308 | 21.592 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 25.0 | -100.0 | G35T2 | 1 2 3 | 8 10 7
Y/35-2 | SGBM03 | Aug 18 2015 3:05PM | Aug 19 2015 12:15PM | Aug 19 2015 1:50PM | Aug 19 2015 4:20PM | 49.711 | 47.275 | 42.58 33.08 | 0.00 0.00 | 22.080 | 27.631 | 25.195 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 21.8 | 27.0 | -100.0 | G45T2 | c480007291 c480007293 c480007294 c520121074 | 7 7 5 8
E/59-3 | SGBM23 | Aug 17 2015 4:00PM | Aug 19 2015 9:10AM | Aug 19 2015 11:30AM | Aug 19 2015 1:20PM | 51.933 | 49.775 | 45.65 8.65 | 0.00 0.00 | 6.654 | 45.279 | 43.121 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 47.0 | 9.7 | G35T2 | 1 2 3 4 5 | 11 9 7 10 10
Y/39-2 | SGBM03 | Aug 18 2015 10:30AM | Aug 18 2015 7:40PM | Aug 19 2015 9:25AM | Aug 19 2015 10:35AM | 49.655 | 47.375 | 42.58 | 0.00 | 18.085 | 31.570 | 29.290 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 25.4 | 33.0 | -100.0 | G45T2 | c480007275 c480007276 c480007278 | 11 11 11
K/25-1 | SGBM20 | Aug 17 2015 4:50PM | Aug 17 2015 9:50PM | Aug 18 2015 5:58PM | Aug 18 2015 8:06PM | 53.439 | 51.075 | 45.22 | 0.00 | 28.919 | 23.740 | 22.156 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 23.0 | 19.9 | G35T2 | 1 2 3 | 6 10 7
V/30-1 | SGBM18 | Aug 17 2015 3:10PM | Aug 18 2015 10:00AM | Aug 18 2015 4:30PM | Aug 18 2015 6:35PM | 49.778 | 47.075 | 41.61 32.71 | 0.00 0.00 | 25.634 | 24.144 | 21.441 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.6 | 23.0 | -100.0 | G35T2 | 1 2 3 | 7.5 11.5 4
X/39-1 | SGBM03 | Aug 17 2015 3:10PM | Aug 18 2015 1:40PM | Aug 18 2015 1:40PM | Aug 18 2015 3:55PM | 49.539 | 47.375 | 42.48 32.98 | 0.00 0.00 | 17.982 | 31.557 | 29.393 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.5 | 33.0 | -100.0 | G35T2 | 1 2 3 4 | 6 11.5 11.5 4
K/56-1 | SGBM17 | Aug 15 2015 3:00PM | Sep 18 2015 9:00AM | Aug 18 2015 11:05AM | Aug 18 2015 1:30PM | 52.15 | 49.175 | 45.94 14.85 | 0.00 0.00 | 11.945 | 40.205 | 37.230 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.2 | 41.5 | -100.0 | G45T2 | 1 2 3 4 | 11.5 7 11.5 11.5
L/27-1 | SGBM20 | Aug 16 2015 5:07PM | Aug 17 2015 11:00AM | Aug 17 2015 5:05PM | Aug 17 2015 7:10PM | 53.421 | 50.475 | 46.19 36.29 | 0.00 0.00 | 31.388 | 22.033 | 19.087 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 16.5 | 18.0 | -100.0 | G45T2 | c520121054 c480007178 | 7 11
Y/35-1 | SGBM03 | Aug 17 2015 8:00AM | Aug 17 2015 3:30PM | Aug 17 2015 4:45PM | Aug 17 2015 6:55PM | 0 | 47.275 | 42.35 | 0.00 | 0.000 | -21.951 | 47.275 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 40.9 | 24.0 | -100.0 | G45T2 | c480007171 c480007173 c520121054 | 11 10 3
V/29-1 | SGBM20 | Aug 15 2015 10:30AM | Aug 17 2015 11:00AM | Aug 17 2015 2:15PM | Aug 17 2015 3:25PM | 49.775 | 47.075 | 50.65 | 0.00 | 24.950 | 24.825 | 22.125 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | -19.2 | G35T2 | 1 2 | 11 11
E/57-1 | SGBM23 | Aug 14 2015 10:10AM | Aug 17 2015 9:30AM | Aug 17 2015 11:06AM | Aug 17 2015 2:00PM | 51.966 | 49.775 | 46.76 9.76 | 0.00 0.00 | 6.761 | 45.205 | 43.014 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 46.0 | 8.7 | G35T2 | 1 2 3 4 5 6 | 6.5 6.5 10 10 6.5 6.5
K/22-2 | SGBM20 | Aug 16 2015 12:00PM | Aug 16 2015 7:15PM | Aug 17 2015 12:37PM | Aug 17 2015 1:40PM | 53.466 | 51.075 | 45.26 | 0.00 | 29.465 | 24.001 | 21.610 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 22.0 | 17.6 | G35T2 | pj25684704 pj25684706 pj25684705 | 5.5 10 6.5
V/23-1 | SGBM16 | Aug 13 2015 6:00PM | Aug 15 2015 9:00AM | Aug 15 2015 2:00PM | Aug 15 2015 4:15PM | 49.725 | 47.375 | 41.55 30.75 | 0.00 0.00 | 27.037 | 22.688 | 20.338 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 17.6 | 22.0 | -17.6 | G35T2 | 1 2 | 11 11
E/58-3 | SGBM17 | Aug 14 2015 8:00AM | Aug 15 2015 9:40AM | Aug 15 2015 12:23PM | Aug 15 2015 3:15PM | 51.9 | 49.775 | 45.77 12.77 | 0.00 0.00 | 6.766 | 45.134 | 43.009 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.2 | 44.0 | -100.0 | G35T2 | 1 2 3 4 | 11 11 11 11
X/37-3 | SGBM19 | Aug 14 2015 2:15PM | Aug 15 2015 10:05AM | Aug 15 2015 11:25AM | Aug 15 2015 1:05PM | 49.526 | 47.475 | 42.23 24.23 | 0.00 0.00 | 20.326 | 29.200 | 27.149 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.5 | 29.0 | -100.0 | G35T2 | c480007080 c480007082 c480007085 | 11 11 7
K/23-1 | SGBM15 | Aug 13 2015 5:40PM | Aug 14 2015 12:00PM | Aug 14 2015 9:35PM | Aug 14 2015 9:30PM | 53.482 | 51.075 | 45.23 | 0.00 | 28.929 | 24.553 | 22.146 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | 14.7 | G35T2 | c480007039 c480007307 | 11 11
V/24-1 | SGBM18 | Aug 13 2015 4:00PM | Aug 14 2015 11:30AM | Aug 14 2015 6:30PM | Aug 14 2015 9:30PM | 49.691 | 47.375 | 41.48 38.08 | 0.00 0.00 | 27.869 | 21.822 | 19.506 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 16.9 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
W/24-1 | SGBM18 | Aug 12 2015 10:10AM | Aug 14 2015 9:30AM | Aug 14 2015 6:30PM | Aug 14 2015 8:30PM | 49.717 | 47.375 | 41.60 30.50 | 0.00 0.00 | 26.893 | 22.824 | 20.482 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 17.7 | 22.0 | 24.0 | G35T2 | 1 2 | 11 11
X/36-3 | SGBM03 | Aug 14 2015 9:30AM | Aug 14 2015 1:50PM | Aug 14 2015 5:15PM | Aug 14 2015 7:05PM | 49.557 | 47.475 | 50.01 | 0.00 | 21.209 | 28.348 | 26.266 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.7 | 28.0 | -100.0 | G45T2 | 1 2 3 | 11 11 6
K/58-1 | SGBM23 | Aug 13 2015 11:20AM | Aug 14 2015 8:15AM | Aug 14 2015 3:18PM | Aug 14 2015 6:20PM | 52.215 | 49.775 | 44.92 13.12 | 0.00 0.00 | 12.722 | 39.493 | 37.053 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 32.1 | 39.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 6 11
E/59-1 | SGBM17 | Aug 12 2015 12:00PM | Aug 13 2015 3:20PM | Aug 13 2015 8:45PM | Aug 13 2015 11:30PM | 51.919 | 49.775 | 45.63 17.63 | 0.00 0.00 | 6.625 | 45.294 | 43.150 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.4 | 51.0 | -100.0 | G35T2 | 1 2 3 4 5 | 9 11 11 10 10
K/25-2 | SGBM20 | Aug 12 2015 1:35PM | Aug 12 2015 7:30PM | Aug 13 2015 5:05PM | Aug 13 2015 7:20PM | 53.463 | 51.075 | 45.16 | 0.00 | 28.858 | 24.605 | 22.217 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | -100.0 | G35T2 | c480006978 c480006977 c480006987 | 10 10 2
W/32-2 | SGBM16 | Aug 12 2015 3:45PM | Aug 13 2015 10:00AM | Aug 13 2015 3:30PM | Aug 13 2015 5:57PM | 49.586 | 47.375 | 41.51 35.61 | 0.00 0.00 | 25.534 | 24.052 | 21.841 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.9 | 24.0 | -18.9 | G35T2 | 1 2 3 | 11 11 2
X/39-2 | SGBM03 | Aug 13 2015 9:15AM | Aug 13 2015 1:40PM | Aug 13 2015 2:40PM | Aug 13 2015 5:00PM | 49.542 | 47.375 | 50.14 | 0.00 | 18.042 | 31.500 | 29.333 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 25.4 | 33.0 | -100.0 | G35T2 | 1 2 3 | 11 11 11
L/26-1 | SGBM20 | Aug 12 2015 8:00AM | Aug 12 2015 12:10PM | Aug 12 2015 5:44PM | Aug 12 2015 9:00PM | 53.375 | 50.475 | 45.16 | 0.00 | 31.364 | 22.011 | 19.111 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 16.6 | 15.0 | -9.4 | G45T2 | 1 2 3 | 10 2 3
W/25-1 | SGBM16 | Aug 12 2015 8:20AM | Aug 12 2015 2:30PM | Aug 12 2015 3:45PM | Aug 12 2015 5:30PM | 49.717 | 47.375 | 41.80 30.50 | 0.00 0.00 | 26.779 | 22.938 | 20.596 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 17.8 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
W/26-1 | SGBM16 | Aug 11 2015 1:01PM | Aug 11 2015 7:10PM | Aug 12 2015 2:10PM | Aug 12 2015 4:47PM | 49.689 | 47.375 | 42.55 | 0.00 | 25.048 | 24.641 | 22.327 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 22.0 | -19.3 | G35T2 | 1 2 | 11 11
E/58-1 | SGBM23 | Aug 11 2015 8:15AM | Aug 11 2015 4:30PM | Aug 11 2015 9:07PM | Aug 12 2015 12:15AM | 51.941 | 49.775 | 44.75 | 0.00 | 6.754 | 45.187 | 43.021 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.3 | 46.0 | -100.0 | G35T2 | 1 2 3 4 5 | 12 3 11 11 9
X/37-2 | SGBM03 | Aug 11 2015 1:00PM | Aug 11 2015 6:43PM | Aug 11 2015 9:00PM | Aug 11 2015 10:15PM | 49.538 | 47.475 | 50.24 | 0.00 | 20.238 | 29.300 | 27.237 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.6 | 30.0 | -100.0 | G35T2 | 1 2 3 | 11 11 8
K/24-2 | SGBM20 | Aug 10 2015 6:00PM | Aug 11 2015 1:40PM | Aug 11 2015 3:50PM | Aug 11 2015 6:00PM | 53.418 | 51.075 | 54.20 | 0.00 | 28.798 | 24.620 | 22.277 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 22.0 | 14.0 | G35T2 | c480006843 c480006845 | 11 11
W/32-1 | SGBM16 | Aug 10 2015 2:30PM | Aug 11 2015 1:13PM | Aug 11 2015 3:35PM | Aug 11 2015 5:30PM | 49.535 | 47.375 | 41.46 37.96 | 0.00 0.00 | 24.859 | 24.676 | 22.516 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 22.0 | -19.5 | G35T2 | 1 2 | 11 11
X/36-2 | SGBM03 | Aug 10 2015 6:00PM | Aug 11 2015 11:39AM | Aug 11 2015 2:00PM | Aug 11 2015 4:45PM | 49.538 | 47.475 | 50.53 | 0.00 | 21.227 | 28.311 | 26.248 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.7 | 30.0 | -100.0 | G45T2 | 1 2 3 | 11 11 8
G/61-3 | SGBM17 | Aug 10 2015 8:05AM | Sep 11 2015 10:00AM | Aug 11 2015 12:40PM | Aug 11 2015 2:09PM | 51.888 | 49.675 | 45.65 16.65 | 0.00 0.00 | 4.648 | 47.240 | 45.027 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 50.0 | -100.0 | G35T2 | 1 2 3 4 5 | 12 12 11 11 4
K/22-1 | SGBM20 | Aug 10 2015 6:40PM | Aug 11 2015 3:20PM | Aug 11 2015 12:05PM | Aug 11 2015 1:10PM | 53.445 | 51.075 | 45.15 | 0.00 | 28.745 | 24.700 | 22.330 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 22.0 | 13.8 | G35T2 | c480006857 c480006858 | 11 11
Z/29-2 | SGBM16 | Aug 8 2015 7:40AM | Aug 10 2015 5:00PM | Aug 10 2015 10:54PM | Aug 11 2015 12:30AM | 50.068 | 47.375 | 41.89 41.89 | 0.00 0.00 | 24.218 | 26.675 | 23.157 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 23.5 | -20.1 | G35T2 | 1 2 | 11.5 12
W/36-2 | SGBM03 | Aug 10 2015 1:50PM | Aug 10 2015 6:16PM | Aug 10 2015 8:55PM | Aug 10 2015 11:10PM | 49.577 | 47.375 | 50.28 | 0.00 | 21.077 | 28.500 | 26.298 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 22.8 | 30.0 | -100.0 | G35T2 | 1 2 3 | 11 11 8
F/60-1 | SGBM23 | Aug 8 2015 2:30PM | Aug 10 2015 3:55PM | Aug 10 2015 3:18PM | Aug 10 2015 6:00PM | 51.923 | 49.675 | 46.70 25.70 | 0.00 0.00 | 5.604 | 46.319 | 44.071 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 2+12+12+12+12 | - | 38.2 | 48.0 | -100.0 | G45T2 | 1 2 3 4 | 12 12 12 12
W/37-1 | SGBM03 | Aug 10 2015 8:50AM | Aug 10 2015 1:05PM | Aug 10 2015 1:45PM | Aug 10 2015 3:30PM | 43.458 | 47.375 | 50.16 | 0.00 | 19.958 | 23.500 | 27.417 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.7 | 31.0 | -100.0 | G35T2 | 1 2 3 | 11 10 10
Y/31-2 | SGBM16 | Aug 8 2015 8:30AM | Aug 10 2015 10:30AM | Aug 10 2015 1:00PM | Aug 10 2015 2:20PM | 49.833 | 47.475 | 41.63 36.13 | 0.00 0.00 | 25.037 | 24.796 | 22.438 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 22.0 | -19.4 | G35T2 | 1 2 | 11 11
H/61-3 | SGBM17 | Aug 7 2015 10:00PM | Aug 8 2015 6:40PM | Aug 8 2015 7:58PM | Aug 9 2015 12:35AM | 51.904 | 49.775 | 46.70 | 0.00 | 4.197 | 47.707 | 45.578 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.5 | 51.0 | -100.0 | G35T2 | 1 2 3 4 5 6 7 | 6.5 6.5 10 8 6.5 6.5 7
W/39-1 | SGBM03 | Aug 8 2015 9:45AM | Aug 8 2015 2:05PM | Aug 8 2015 4:05PM | Aug 8 2015 6:55PM | 49.518 | 47.375 | 50.22 | 0.00 | 16.018 | 33.500 | 31.357 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.2 | 36.0 | -100.0 | G45T2 | 1 2 3 4 | 11 11 11 3
G/59-3 | SGBM23 | Aug 6 2015 8:10PM | Aug 7 2015 8:00PM | Aug 7 2015 11:35PM | Aug 8 2015 1:47AM | 52 | 49.875 | 44.80 | 0.00 | 4.800 | 47.200 | 45.075 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 46.0 | 7.0 | G35T2 | C410000014 C410000015 C410000016 C410000017 C410000018 | 9 10 9 9 9
W/35-2 | SGBM03 | Aug 7 2015 1:00PM | Aug 7 2015 5:55PM | Aug 7 2015 10:35PM | Aug 8 2015 1:30AM | 49.446 | 47.375 | 50.46 | 0.00 | 23.160 | 26.286 | 24.215 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 21.0 | 27.0 | -100.0 | G35T2 | 1 2 3 | 8 12 7
H/60-3 | SGBM17 | Aug 6 2015 4:50PM | Aug 7 2015 10:30AM | Aug 7 2015 7:25PM | Aug 7 2015 10:35PM | 51.994 | 49.775 | 44.82 19.32 | 0.00 0.00 | 5.723 | 46.271 | 44.052 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.1 | 47.0 | 23.2 | G45T2 | c480006607 c480006609 c480006615 c480006618 c480006624 | 11 11 11 11 3
X/31-2 | SGBM20 | Aug 6 2015 3:30PM | Aug 7 2015 2:10PM | Aug 7 2015 7:15PM | Aug 7 2015 8:40PM | 49.814 | 47.475 | 41.63 29.03 | 0.00 0.00 | 24.856 | 24.958 | 22.619 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 22.0 | -100.0 | G35T2 | 11 2 | 11 11
Y/31-1 | SGBM20 | Aug 6 2015 6:00PM | Aug 7 2015 2:30PM | Aug 7 2015 5:50PM | Aug 7 2015 7:40PM | 49.844 | 47.475 | 41.87 31.97 | 0.00 0.00 | 25.396 | 24.448 | 22.079 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
W/38-2 | SGBM03 | Aug 6 2015 6:30PM | Aug 7 2015 11:00AM | Aug 7 2015 4:00PM | Aug 7 2015 5:50PM | 49.508 | 47.375 | 50.21 | 0.00 | 19.014 | 30.494 | 28.361 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.6 | 32.0 | -24.6 | G35T2 | 1 2 3 | 11 11 10
Y/30-2 | SGBM16 | Aug 6 2015 4:00PM | Aug 7 2015 2:30PM | Aug 7 2015 3:00PM | Aug 7 2015 5:00PM | 49.901 | 47.375 | 41.78 25.25 | 0.00 0.00 | 24.951 | 24.950 | 22.424 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 24.0 | -100.0 | G35T2 | 1 2 3 | 4 10 10
X/29-1 | SGBM16 | Aug 6 2015 2:30PM | Aug 7 2015 10:30AM | Aug 7 2015 2:20PM | Aug 7 2015 3:47PM | 49.921 | 47.375 | 41.65 34.85 | 0.00 0.00 | 24.779 | 25.142 | 22.596 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 25.0 | -19.6 | G35T2 | 1 2 3 | 9 10 6
G/61-2 | SGBM23 | Aug 5 2015 8:00AM | Aug 6 2015 3:00PM | Aug 6 2015 7:44PM | Aug 6 2015 10:20PM | 51.896 | 49.675 | 44.64 | 0.00 | 4.637 | 47.259 | 45.038 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 46.0 | 17.9 | G35T2 | c480006527 c480006529 c480006532 c520120881 | 11 11.5 11.5 12
W/37-2 | SGBM03 | Aug 6 2015 12:00PM | Aug 6 2015 4:17PM | Aug 6 2015 7:10PM | Aug 6 2015 9:30PM | 49.55 | 47.375 | 50.25 | 0.00 | 19.950 | 29.600 | 27.425 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 23.8 | 28.0 | 17.9 | G35T2 | 1 2 3 | 11 11 6
Z/29-1 | SGBM16 | Aug 5 2015 7:00PM | Aug 6 2015 2:00PM | Aug 6 2015 4:30PM | Aug 6 2015 6:20PM | 49.817 | 47.375 | 41.92 | 0.00 | 24.321 | 25.496 | 23.054 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.0 | 24.0 | -20.0 | G35T2 | 1 2 3 | 11 11 2
X/29-2 | SGBM16 | Aug 5 2015 9:00AM | Aug 5 2015 5:00PM | Aug 6 2015 12:24AM | Aug 6 2015 1:50AM | 49.768 | 47.375 | 41.68 | 0.00 | 25.290 | 24.478 | 22.085 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 22.0 | -19.1 | G35T2 | 1 2 | 11 11
Y/30-1 | SGBM20 | Aug 5 2015 7:30AM | Aug 5 2015 5:00PM | Aug 5 2015 10:25PM | Aug 6 2015 1:30AM | 49.821 | 47.375 | 41.79 31.89 | 0.00 0.00 | 25.153 | 24.668 | 22.222 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | -19.2 | G35T2 | 1 2 | 11 11
W/36-1 | SGBM03 | Aug 5 2015 3:00PM | Aug 5 2015 7:14PM | Aug 5 2015 8:16PM | Aug 5 2015 10:15PM | 49.574 | 47.375 | 50.27 | 0.00 | 21.074 | 28.500 | 26.301 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 22.8 | 28.0 | 22.9 | G35T2 | 1 2 3 | 11 11 6
Y/31-3 | SGBM20 | Aug 5 2015 9:30AM | Aug 5 2015 2:00PM | Aug 5 2015 5:30PM | Aug 5 2015 7:20PM | 49.801 | 47.475 | 41.66 | 0.00 | 25.217 | 24.584 | 22.258 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 24.0 | -19.3 | G35T2 | 1 2 3 | 6 10 8
X/31-3 | SGBM16 | Aug 4 2015 4:20PM | Aug 5 2015 9:20AM | Aug 5 2015 4:50PM | Aug 5 2015 6:25PM | 49.761 | 47.475 | 41.55 38.23 | 0.00 0.00 | 24.939 | 24.822 | 22.536 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 24.0 | -19.5 | G35T2 | 1 2 3 | 10 10 4
W/39-2 | SGBM03 | Aug 5 2015 9:00AM | Aug 5 2015 1:13PM | Aug 5 2015 3:10PM | Aug 5 2015 5:45PM | 49.415 | 47.375 | 50.12 | 0.00 | 15.915 | 33.500 | 31.460 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 27.2 | 32.5 | 19.3 | G45T2 | 1 2 3 4 | 10 10 11 1.5
H/61-2 | SGBM23 | Aug 4 2015 11:10AM | Aug 5 2015 10:10AM | Aug 5 2015 11:33AM | Aug 5 2015 2:55PM | 52.01 | 49.775 | 44.82 15.32 | 0.00 0.00 | 5.524 | 46.486 | 44.251 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 38.3 | 50.0 | 30.5 | G35T2 | c480006423 c480006424 c480006425 c480006426 c480006434 | 11.5 11.5 11 11 5
H/60-2 | SGBM23 | Aug 3 2015 5:40PM | Aug 4 2015 6:40PM | Aug 4 2015 11:07PM | Aug 5 2015 3:00AM | 52.028 | 49.775 | 44.77 | 0.00 | 5.573 | 46.455 | 44.202 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.3 | 56.0 | 46.3 | G45T2 | c480006418 c480006419 c480006420 c480006421 c480006422 c480006422 | 10 10 10 8 10 8
W/29-2 | SGBM20 | Aug 4 2015 8:30AM | Aug 4 2015 5:00PM | Aug 4 2015 10:15PM | Aug 5 2015 1:00AM | 49.622 | 47.375 | 41.47 33.67 | 0.00 0.00 | 25.624 | 23.998 | 21.751 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.8 | 23.0 | -100.0 | G35T2 | 1 2 3 | 9.5 11.5 2
W/38-1 | SGBM03 | Aug 4 2015 10:20AM | Aug 4 2015 3:30PM | Aug 4 2015 8:45PM | Aug 4 2015 10:55PM | 49.46 | 47.375 | 50.16 | 0.00 | 19.060 | 30.400 | 28.315 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 24.5 | 29.0 | -24.5 | G35T2 | 1 2 3 | 11 11 7
X/30-2 | SGBM20 | Aug 4 2015 8:00AM | Aug 4 2015 1:30PM | Aug 4 2015 5:20PM | Aug 4 2015 6:30PM | 49.715 | 47.375 | 41.59 | 0.00 | 25.771 | 23.944 | 21.604 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 23.0 | -100.0 | G35T2 | 1 2 | 11.5 11.5
W/35-1 | SGBM21 | Aug 3 2015 5:00PM | Aug 4 2015 11:00AM | Aug 4 2015 1:15PM | Aug 4 2015 2:25PM | 49.431 | 47.375 | 42.13 | 0.00 | 23.231 | 26.200 | 24.144 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.9 | 26.0 | -100.0 | G35T2 | c480006372 c480006373 c480006376 | 10 10 6
W/31-2 | SGBM16 | Aug 3 2015 8:00AM | Aug 3 2015 5:50PM | Aug 3 2015 11:49PM | Aug 4 2015 3:30AM | 49.742 | 47.375 | 41.68 | 0.00 | 26.210 | 23.532 | 21.165 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.3 | 26.5 | -18.3 | G35T2 | 1 2 3 | 10 10 6.5
W/30-2 | SGBM20 | Aug 3 2015 11:29AM | Aug 3 2015 4:00PM | Aug 4 2015 12:28AM | Aug 4 2015 3:20AM | 49.766 | 47.375 | 41.48 | 0.00 | 25.902 | 23.864 | 21.473 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.6 | 26.5 | -100.0 | G35T2 | 1 2 3 | 11.5 11.5 3.5
G/59-2 | SGBM23 | Aug 3 2015 10:20AM | Aug 3 2015 7:20PM | Aug 3 2015 9:15PM | Aug 3 2015 11:35PM | 52.015 | 49.875 | 44.81 | 0.00 | 4.807 | 47.208 | 45.068 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 47.0 | 20.4 | G35T2 | c480006345 c480006347 c480006353 c480006354 c480006355 | 11.5 11.5 11 10 3
X/31-1 | SGBM16 | Aug 3 2015 10:10AM | Aug 3 2015 4:30PM | Aug 3 2015 6:40PM | Aug 3 2015 8:30PM | 49.876 | 47.475 | 41.56 34.86 | 0.00 0.00 | 24.734 | 25.142 | 22.741 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.7 | 23.0 | -19.7 | G35T2 | 1 2 | 11.5 11.5
W/28-2 | SGBM20 | Aug 3 2015 1:44PM | Aug 3 2015 4:30PM | Aug 3 2015 5:50PM | Aug 3 2015 7:43PM | 49.715 | 47.375 | 41.59 | 0.00 | 25.771 | 23.944 | 21.604 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 18.7 | 23.0 | -18.7 | G35T2 | 1 2 | 11.5 11.5
X/36-1 | SGBM21 | Aug 3 2015 8:15AM | Aug 3 2015 2:30PM | Aug 3 2015 5:05PM | Aug 3 2015 6:20PM | 49.552 | 47.475 | 42.25 | 0.00 | 21.152 | 28.400 | 26.323 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 22.8 | 28.0 | -100.0 | G45T2 | pj25683851 pj2568852 pj25683853 pj25683855 | 6.5 6.5 10 5
G/61-1 | SGBM15 | Aug 1 2015 2:00PM | Aug 3 2015 12:30PM | Aug 3 2015 12:12PM | Aug 3 2015 2:35PM | 51.93 | 49.675 | 44.73 32.23 | 0.00 0.00 | 4.630 | 47.300 | 45.045 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 44.9 | 15.1 | G35T2 | c480006297 c480006298 c480006302 c480006306 | 11.5 11.4 11 11
X/28-2 | SGBM17 | Aug 1 2015 1:00PM | Aug 1 2015 5:20PM | Aug 1 2015 7:50PM | Aug 1 2015 10:15PM | 49.791 | 47.375 | 41.69 | 0.00 | 25.083 | 24.708 | 22.292 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.3 | 23.5 | -100.0 | G35T2 | 1 2 | 11.5 12
W/29-1 | SGBM16 | Aug 1 2015 1:20PM | Aug 1 2015 5:30PM | Aug 1 2015 7:20PM | Aug 1 2015 8:50PM | 49.614 | 47.375 | 41.52 | 0.00 | 25.324 | 24.290 | 22.051 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 22.5 | -100.0 | G35T2 | 1 2 | 11 11.5
G/59-1 | SGBM23 | Jul 31 2015 12:01PM | Aug 1 2015 2:33PM | Aug 1 2015 3:59PM | Aug 1 2015 5:56PM | 51.995 | 49.875 | 44.80 | 0.00 | 4.299 | 47.696 | 45.576 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 39.5 | 47.0 | -39.5 | G35T2 | c480006184 C480006186 C480006189 C480006194 | 12 12 11.5 11.5
W/31-1 | SGBM17 | Jul 31 2015 8:30AM | Jul 31 2015 7:30PM | Aug 1 2015 2:10PM | Aug 1 2015 5:00PM | 49.482 | 47.375 | 41.29 31.39 | 0.00 0.00 | 24.702 | 25.590 | 22.673 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 22.0 | -19.6 | G35T2 | 1 2 | 11 11
X/30-1 | SGBM17 | Jul 31 2015 2:00PM | Jul 31 2015 5:20PM | Aug 1 2015 12:00AM | Aug 1 2015 3:30AM | 49.746 | 47.375 | 41.63 | 0.00 | 25.020 | 24.726 | 22.355 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.4 | 25.0 | -100.0 | G35T2 | 1 2 3 | 9 12 4
Y/28-2 | SGBM16 | Jul 31 2015 8:30AM | Jul 31 2015 6:45PM | Jul 31 2015 10:10PM | Aug 1 2015 12:45AM | 49.816 | 47.375 | 41.75 38.45 | 0.00 0.00 | 25.184 | 24.632 | 22.191 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 25.0 | -19.2 | G35T2 | 1 2 3 | 11 11 3
H/61-1 | SGBM23 | Jul 31 2015 8:00AM | Jul 31 2015 2:00PM | Jul 31 2015 7:52PM | Jul 31 2015 10:25PM | 51.993 | 49.775 | 44.86 | 0.00 | 4.759 | 47.234 | 45.016 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 39.0 | 46.0 | 18.0 | G45T2 | c480006139 c480006140 c480006141 c480006144 | 11.5 11.5 11.5 11.5
X/23-3 | SGBM16 | Jul 31 2015 8:30AM | Jul 31 2015 5:00PM | Jul 31 2015 7:25PM | Jul 31 2015 9:57PM | 49.812 | 47.975 | 41.63 32.03 | 0.00 0.00 | 25.836 | 23.976 | 22.139 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.2 | 22.0 | -19.2 | G35T2 | 1 2 3 | 8 7.5 6.5
W/28-1 | SGBM17 | Jul 30 2015 8:10AM | Jul 30 2015 2:38PM | Jul 30 2015 11:15PM | Jul 31 2015 1:47AM | 49.621 | 47.375 | 41.40 | 0.00 | 24.597 | 25.024 | 22.778 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.7 | 23.5 | -100.0 | G35T2 | 1 2 3 4 | 6.5 6.5 7.5 3
H/60-1 | SGBM23 | Jul 29 2015 3:10PM | Jul 30 2015 5:40PM | Jul 30 2015 10:20PM | Jul 31 2015 12:40AM | 51.972 | 49.775 | 43.84 | 0.00 | 5.742 | 46.230 | 44.033 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 38.1 | 45.0 | 18.0 | G45T2 | c480006090 c480006092 c480006094 c480006096 | 11.5 11.5 11 11
W/30-1 | SGBM17 | Jul 29 2015 5:00PM | Jul 30 2015 8:55AM | Jul 30 2015 9:24PM | Jul 30 2015 10:40PM | 49.621 | 47.375 | 42.42 31.52 | 0.00 0.00 | 24.824 | 24.797 | 22.551 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 22.5 | 15.2 | G35T2 | pj25683684 pj25693686 pj25683687 | 6 6.5 10
X/28-1 | SGBM17 | Jul 30 2015 1:30PM | Jul 30 2015 4:45PM | Jul 30 2015 6:40PM | Jul 30 2015 10:25PM | 49.748 | 47.375 | 41.59 | 0.00 | 24.734 | 25.014 | 22.641 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 23.5 | -19.6 | G35T2 | 1 2 3 4 | 2.5 6.5 6.5 8
Y/25-3 | SGBM16 | Jul 30 2015 8:30AM | Jul 30 2015 12:25PM | Jul 30 2015 6:00PM | Jul 30 2015 8:52PM | 49.846 | 47.975 | 41.68 | 0.00 | 25.022 | 24.824 | 22.953 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.9 | 25.0 | -19.9 | G35T2 | 1 2 3 4 | 6.5 6.5 6.5 5.5
L/58-3 | SGBM18 | Jul 28 2015 8:00AM | Jul 29 2015 3:40PM | Jul 30 2015 12:35PM | Jul 30 2015 2:15PM | 52.123 | 49.175 | 44.97 | 0.00 | 14.174 | 37.949 | 35.001 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.3 | 40.0 | 29.4 | G45T2 | c480006055 c480006056 c480006057 c480006059 | 10 10 10 10
X/23-2 | SGBM16 | Jul 29 2015 9:20AM | Jul 29 2015 12:15PM | Jul 29 2015 9:30PM | Jul 29 2015 11:58PM | 49.763 | 47.975 | 41.60 | 0.00 | 24.795 | 24.836 | 23.180 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.1 | 24.0 | -20.1 | G35T2 | 1 2 3 | 7 10 7
Y/28-1 | SGBM16 | Jul 29 2015 8:30AM | Jul 29 2015 1:25PM | Jul 29 2015 8:30PM | Jul 29 2015 10:50PM | 49.907 | 47.375 | 50.74 | 0.00 | 24.737 | 25.170 | 22.638 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.6 | 23.0 | -100.0 | G35T2 | 1 2 3 | 3 10 10
Y/23-3 | SGBM16 | Jul 28 2015 11:00AM | Jul 28 2015 3:15PM | Jul 28 2015 5:40PM | Jul 28 2015 7:40PM | 49.819 | 47.975 | 50.69 | 0.00 | 24.191 | 25.628 | 23.784 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.6 | 23.5 | -100.0 | G35T2 | 1 2 3 | 7 11.5 5
Y/25-2 | SGBM17 | Jul 28 2015 9:20AM | Jul 28 2015 1:30PM | Jul 28 2015 4:45PM | Jul 28 2015 6:50PM | 49.858 | 47.975 | 50.62 | 0.00 | 24.121 | 25.737 | 23.854 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.7 | 23.0 | -100.0 | G35T2 | 1 2 3 | 9 9 5
F/55-2 | SGBM23 | Jul 25 2015 8:03AM | Jul 27 2015 2:01PM | Jul 28 2015 2:05PM | Jul 28 2015 5:01PM | 51.974 | 50.275 | 44.80 | 0.00 | 6.499 | 45.475 | 43.776 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.9 | 52.5 | -100.0 | G35T2 | C480005925 c480005928 c480005930 c480005932 c480005936 c480005939 | 10 10 10 10 10.5 2
X/25-2 | SGBM18 | Jul 27 2015 7:50AM | Jul 27 2015 12:05PM | Jul 28 2015 1:36AM | Jul 28 2015 3:20AM | 49.814 | 47.375 | 50.66 | 0.00 | 24.364 | 25.450 | 23.011 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.9 | 20.0 | -100.0 | G35T2 | 1 2 | 10 10
X/26-1 | SGBM17 | Jul 27 2015 11:15AM | Jul 27 2015 3:33PM | Jul 28 2015 12:35AM | Jul 28 2015 2:20AM | 49.87 | 47.375 | 50.81 | 0.00 | 24.805 | 25.065 | 22.570 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.5 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
X/23-1 | SGBM16 | Jul 27 2015 1:30PM | Jul 27 2015 7:42PM | Jul 27 2015 10:40PM | Jul 28 2015 1:00AM | 49.79 | 47.975 | 50.65 | 0.00 | 24.345 | 25.445 | 23.630 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
X/22-3 | SGBM16 | Jul 27 2015 8:00AM | Jul 27 2015 1:55PM | Jul 27 2015 6:58PM | Jul 27 2015 9:45PM | 49.74 | 47.975 | 50.51 | 0.00 | 24.305 | 25.435 | 23.670 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.5 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
L/57-3 | SGBM23 | Jul 25 2015 1:00PM | Jul 27 2015 1:00PM | Jul 27 2015 4:06PM | Jul 27 2015 7:25PM | 52.09 | 49.175 | 44.97 37.87 | 0.00 0.00 | 14.170 | 37.920 | 35.005 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.3 | 36.0 | 17.1 | G45T2 | c480005859 c480005860 c480005865 c480005868 | 11 11 11 3
Y/23-2 | SGBM16 | Jul 23 2015 8:30AM | Jul 23 2015 3:21PM | Jul 24 2015 12:20AM | Jul 24 2015 1:45AM | 49.85 | 47.975 | 50.44 | 0.00 | 24.442 | 25.408 | 23.533 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 22.0 | -100.0 | G35T2 | 1 2 | 11 11
F/55-3 | SGBM23 | Jul 23 2015 8:20AM | Jul 23 2015 3:00PM | Jul 23 2015 9:01PM | Jul 23 2015 11:31PM | 51.952 | 50.275 | 44.95 | 0.00 | 6.750 | 45.202 | 43.525 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 37.7 | 45.0 | -100.0 | G35T2 | c480005746 c480005747 c480005749 c480005753 | 12 10 12 11
Y/25-1 | SGBM16 | Jul 21 2015 8:45AM | Jul 22 2015 7:45PM | Jul 22 2015 8:30PM | Jul 22 2015 9:30PM | 49.877 | 47.975 | 42.60 | 0.00 | 23.900 | 25.977 | 24.075 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.8 | 25.0 | -100.0 | G35T2 | C480005694 C480005696 C480005699 | 10 10 5
L/58-2 | SGBM23 | Jul 22 2015 8:30AM | Jul 22 2015 1:40PM | Jul 22 2015 3:59PM | Jul 22 2015 6:15PM | 52.127 | 49.175 | 44.98 | 0.00 | 14.476 | 37.651 | 34.699 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.0 | 35.0 | 14.2 | G45T2 | c480005679 c480005680 c480005683 | 11.5 11.5 12
L/57-2 | SGBM23 | Jul 21 2015 8:40AM | Jul 21 2015 2:00PM | Jul 21 2015 6:24PM | Jul 21 2015 8:56PM | 55.121 | 49.175 | 45.03 | 0.00 | 14.428 | 40.693 | 34.747 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.1 | 39.0 | -100.0 | G45T2 | c480005646 c480005647 c480005648 c480005650 | 11 11 10 7
F/55-1 | SGBM17 | Jul 16 2015 8:30AM | Jul 20 2015 2:00PM | Jul 20 2015 6:58PM | Jul 20 2015 10:41PM | 45.672 | 50.275 | 42.28 | 0.00 | 3.775 | 41.897 | 46.500 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 40.3 | 51.5 | -100.0 | G35T2 | c480005626 c480005627 c480005626 c480005629 c480005630 | 11 11 11.5 11 7
X/26-2 | SGBM16 | Jul 15 2015 9:00AM | Jul 20 2015 11:30AM | Jul 20 2015 6:00PM | Jul 20 2015 7:00PM | 49.796 | 47.375 | 42.60 33.60 | 0.00 0.00 | 23.796 | 26.000 | 23.579 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 25.0 | -100.0 | G35T2 | C480005621 C480005621 C480005622 | 11 11 3
X/22-2 | SGBM16 | Jul 14 2015 11:15AM | Jul 14 2015 3:50PM | Jul 14 2015 4:15PM | Jul 14 2015 5:15PM | 49.738 | 47.975 | 42.38 | 0.00 | 25.180 | 24.558 | 22.795 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.7 | 22.0 | -100.0 | G35T2 | C480005583 C480005584 C480005586 | 4 10 8
Y/23-1 | SGBM16 | Jul 13 2015 9:50AM | Jul 13 2015 4:25PM | Jul 13 2015 8:33PM | Jul 13 2015 10:55PM | 49.83 | 47.975 | 42.58 | 0.00 | 24.678 | 25.152 | 23.297 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.2 | 25.0 | -100.0 | G35T2 | c480005542 c480005541 c480007890 | 11 11 3
L/58-1 | SGBM23 | Jul 13 2015 10:00AM | Jul 13 2015 1:50PM | Jul 13 2015 4:20PM | Jul 13 2015 7:52PM | 52.049 | 49.175 | 44.87 | 0.00 | 14.973 | 37.076 | 34.202 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 29.6 | 36.0 | 19.1 | G45T2 | c480005523 c480005524 c480005532 c480005535 | 11 11 10 4
X/25-1 |  | Jul 11 2015 1:00PM | Jul 11 2015 6:10PM | Jul 11 2015 8:50PM | Jul 11 2015 9:20PM | 49.818 | 47.375 | 42.47 25.37 | 0.00 0.00 | 25.371 | 24.447 | 22.004 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 19.1 | 22.0 | 15.4 | G35T2 | C480005418 C480005420 | 11 11
L/57-1 | SGBM19 | Jul 11 2015 11:50AM | Jul 11 2015 7:40PM | Jul 11 2015 9:17PM | Jul 11 2015 4:17AM | 52.062 | 49.175 | 44.90 | 0.00 | 14.401 | 37.661 | 34.774 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - | 12 | - | 30.1 | 35.0 | 14.6 | G45T2 | c480005421 c480005423 c480005429 c480005443 | 11 10 10 4
X/22-1 | SGBM16 | Jul 10 2015 8:30AM | Jul 10 2015 11:45AM | Jul 10 2015 3:29PM | Jul 10 2015 4:20PM | 49.784 | 47.975 | 42.52 | 0.00 | 24.417 | 25.367 | 23.558 |  | 0.0 | 0.0 | 0.0 | 12T20 + 9T20 | - | T12-225 | - | - | 12 | - | 20.4 | 25.0 | 2.2 | G35T2 | c520120540 c480005344 c480005346 | 10 10 5
Pa/11-1 | [5 empty] | 0 | 51.075 |  |  | 0.000 | 0.000 | 51.075 |  | 0.0 | 0.0 | 0.0 | 12T20+9T20 | - | T12-225 | - | - |  | - | 44.2 | 0.0 | 0.0 | G35T2
Total | [10 empty] | 33525.099 | 30302.047 | 0.0 | 21.6 | 0.0 | 0.0 |  | 0.0 |  | 0.0 | 0.0 |  |  | 26242.0 | 31879.0