## 1200
Summary List for 18916521-MRT-V1 Spur Line
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T40 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T16 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
ABUT FDA-2 | SGBM32 | Mar 3 2016 9:20AM | Mar 5 2016 2:30PM | Mar 5 2016 6:50PM | Mar 5 2016 10:00PM | 40.343 | 41.304 | -6.39 | 1.70 | -8.087 | 48.430 | 49.391 |  | 1.7 | 1.7 | 1.7 | 23T40 | - | - | T16-150 | - | - | 12+12+12+12+8 | - | 55.9 | 72.0 | -67.8 | G40T2 | 1 2 3 4 5 6 7 8 | 9 9 9 9 9 9 9 9
ABUT FDA-1 | SGBM32 | Feb 25 2016 7:50PM | Feb 28 2016 10:00AM | Mar 1 2016 8:10PM | Mar 2 2016 12:30AM | 40.408 | 41.304 | 0.40 | 3.60 | -3.200 | 43.608 | 44.504 |  | 3.6 | 0.0 | 3.6 | 23T40 | - | - | T16-150 | - | - | 12+12+12+12+6 | - | 50.3 | 63.0 | -16.6 | G40T2 | 1 2 3 4 5 6 7 | 9 9 9 9 9 9 9
ABUT FDD-2 |  | Feb 27 2016 8:30AM | Feb 29 2016 11:15AM | Feb 29 2016 6:00PM | Feb 29 2016 9:00PM | 40.733 | 40.547 | 41.98 | 0.00 | 1.226 | 39.507 | 39.321 |  | 0.0 | 0.0 | 0.0 | 23T40 | - | - | T16-150 | - | - | 12+12+12+12 | - | 44.5 | 60.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 | 9 9 9 9 9 9 6
ABUT FDD-1 |  | Feb 23 2016 9:30AM | Feb 25 2016 9:15AM | Feb 25 2016 2:30PM | Feb 25 2016 6:00PM | 40.714 | 40.547 | 41.64 | 0.00 | 0.543 | 40.171 | 40.004 |  | 0.0 | 0.0 | 0.0 | 23T40 | - | - | T16-150 | - | - | 12+12+12+12 | - | 45.2 | 60.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 | 9 9 9 9 9 9 6
Total | [10 empty] | 171.716 | 173.220 | 0.0 | 5.3 | 1.7 | 5.3 |  | 0.0 |  |  | 0.0 | 0.0 |  |  | 195.9 | 255.0

## 1500
Summary List for 18916521-MRT-V1 Spur Line
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
FDA 13-4 | SGBM13 | Apr 10 2016 11:00AM | Apr 17 2016 6:00PM | Apr 18 2016 8:00PM | Apr 18 2016 11:50PM | 38.772 | 35.049 | -16.75 | 2.20 | -16.747 | 57.719 | 51.796 |  | 2.2 | 2.2 | 2.2 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 91.5 | 114.0 | 19.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 13-2 | SGBM13 | Apr 6 2016 5:20PM | Apr 8 2016 12:30AM | Apr 8 2016 8:40PM | Apr 9 2016 1:00AM | 38.203 | 35.049 | -18.38 | 1.70 | -20.084 | 58.287 | 55.133 |  | 1.7 | 1.7 | 1.7 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+2 | - | 97.4 | 114.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 13-7 | SGBM26 | Apr 3 2016 11:40AM | Apr 4 2016 5:30PM | Apr 4 2016 11:20PM | Apr 5 2016 4:05AM | 38.733 | 35.049 | -16.80 | 2.00 | -18.801 | 57.534 | 53.850 |  | 2.0 | 2.0 | 2.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 95.2 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-8 | SGBM26 | Mar 21 2016 2:20PM | Mar 25 2016 4:10PM | Apr 1 2016 7:40PM | Apr 2 2016 2:10AM | 38.545 | 35.049 | -12.91 | 1.90 | -14.809 | 53.354 | 49.858 |  | 1.9 | 1.9 | 1.9 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+11 | - | 88.1 | 112.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 4
FDA 13-1 | SGBM26 | Mar 24 2016 1:00PM | Mar 26 2016 2:30AM | Apr 1 2016 8:50PM | Apr 2 2016 1:45AM | 38.247 | 35.049 | -19.82 | 1.80 | -21.619 | 59.866 | 56.668 |  | 1.8 | 0.0 | 1.8 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+5 | - | 100.2 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-3 | SGBM26 | Mar 17 2016 8:00PM | Mar 21 2016 2:00PM | Mar 22 2016 6:39PM | Mar 22 2016 11:30PM | 38.574 | 35.049 | -18.30 | 1.80 | -20.102 | 58.676 | 55.151 |  | 1.8 | 1.8 | 1.8 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+2 | - | 97.5 | 105.0 | 7.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 6
FDD 11-4 | SGBM13 | Mar 17 2016 10:00AM | Mar 18 2016 2:15AM | Mar 18 2016 6:45PM | Mar 18 2016 9:30PM | 39.617 | 35.092 | -4.03 | 2.00 | 30.467 | 45.650 | 4.625 |  | 2.0 | 2.0 | 2.0 | 28T20 | - | - | T12-150 | - | - | 12+12+129 | 5.425 | 8.2 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 11-4 | SGBM13 | Mar 17 2016 10:00AM | Mar 18 2016 3:15PM | Mar 18 2016 6:30PM | Mar 18 2016 9:00PM | 39.617 | 34.635 | -4.03 | 2.00 | -6.033 | 45.650 | 40.668 |  | 2.0 | 2.0 | 2.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+9 | - | 71.9 | 81.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 10 | 9 9 9 9 9 9 9 9 9
FDA 12-5 | SGBM26 | Mar 16 2016 1:30PM | Mar 17 2016 5:00AM | Mar 17 2016 4:30PM | Mar 17 2016 7:45PM | 38.977 | 35.025 | -10.04 | 1.90 | -11.939 | 50.916 | 46.964 |  | 1.9 | 1.9 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+4.5 | - | 83.0 | 90.0 | 8.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 13-9 | SGBM32 | Mar 12 2016 8:30AM | Mar 15 2016 11:50PM | Mar 16 2016 4:16PM | Mar 17 2016 12:45AM | 38.441 | 35.049 | -10.34 | 1.95 | -12.289 | 50.730 | 47.338 |  | 1.9 | 1.9 | 1.9 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+4.8 | - | 83.7 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 10-3 | SGBM32 | Mar 12 2016 1:00PM | Mar 13 2016 4:30PM | Mar 14 2016 9:54PM | Mar 15 2016 1:30AM | 40.014 | 35.351 | 40.93 | 0.00 | -21.171 | 61.185 | 56.522 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+4 | - | 99.9 | 104.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 5
FDA 12-1 | SGBM26 | Mar 11 2016 5:00PM | Mar 12 2016 11:00PM | Mar 14 2016 6:50PM | Mar 14 2016 10:30PM | 38.58 | 35.025 | -8.44 | 1.74 | -10.182 | 48.762 | 45.207 |  | 1.7 | 1.6 | 1.7 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3.5 | - | 79.9 | 84.0 | 5.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 3
FDA 11-1 | SGBM32 | Mar 11 2016 8:30AM | Mar 12 2016 10:00AM | Mar 12 2016 5:30PM | Mar 12 2016 10:00PM | 39.688 | 34.635 | 40.55 | 0.00 | -6.547 | 46.235 | 41.182 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 72.8 | 81.0 | 11.3 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDA 12-6 | SGBM26 | Mar 8 2016 6:40PM | Mar 10 2016 4:00PM | Mar 12 2016 5:17PM | Mar 12 2016 10:00PM | 38.72 | 35.025 | -9.17 | 1.70 | -10.866 | 49.586 | 45.891 |  | 1.7 | 1.7 | 1.7 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+6 | - | 81.1 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 11-1 | SGBM32 | Mar 11 2016 8:30AM | Mar 12 2016 10:00AM | Mar 12 2016 5:30PM | Mar 12 2016 10:00PM | 39.688 | 34.635 | 40.55 | 0.00 | -6.547 | 46.235 | 41.182 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12 | - | 72.8 | 81.0 | 8.2 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDA 10-4 | SGBM32 | Mar 8 2016 3:15PM | Mar 9 2016 10:30PM | Mar 10 2016 9:00PM | Mar 11 2016 2:30AM | 40.043 | 35.351 | -13.94 | 2.70 | -9.143 | 56.686 | 44.494 |  | 2.7 | 2.5 | 2.7 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+10 | - | 78.6 | 122.0 | 37.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 12-4 | SGBM26 | Mar 7 2016 8:30AM | Mar 8 2016 12:00PM | Mar 9 2016 1:31AM | Mar 9 2016 6:00AM | 39.025 | 35.025 | -13.70 | 1.70 | -15.401 | 54.426 | 50.426 |  | 1.7 | 1.7 | 1.7 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+9 | - | 89.1 | 108.0 | 21.2 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 11-5 | SGBM32 | Mar 7 2016 4:45PM | Mar 7 2016 11:50PM | Mar 8 2016 6:10PM | Mar 8 2016 9:30PM | 39.555 | 34.635 | 40.26 | 0.00 | -7.094 | 46.649 | 41.729 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3.1 | - | 73.8 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDA 10-2 | SGBM26 | Mar 5 2016 8:30AM | Mar 7 2016 4:00PM | Mar 7 2016 9:30PM | Mar 8 2016 1:10AM | 39.981 | 35.351 | 40.93 | 0.00 | -20.669 | 60.650 | 56.020 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+4 | - | 99.0 | 123.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 11-2 | SGBM32 | Mar 4 2016 8:30PM | Mar 5 2016 4:00PM | Mar 5 2016 10:45PM | Mar 6 2016 3:48AM | 39.813 | 34.635 | 40.56 | 0.00 | -6.437 | 46.250 | 41.072 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12 | - | 72.6 | 90.0 | 24.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 10-3 | SGBM26 | Mar 4 2016 8:30AM | Mar 4 2016 8:00PM | Mar 5 2016 3:20PM | Mar 5 2016 7:30PM | 40.535 | 36.102 | 41.45 | 0.00 | -22.152 | 62.687 | 58.254 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+5.8 | - | 103.0 | 135.0 | 31.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 12 14 15 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 10-5 | SGBM32 | Mar 1 2016 4:00PM | Mar 3 2016 12:30PM | Mar 3 2016 6:50PM | Mar 3 2016 11:30PM | 39.818 | 35.351 | -14.53 | 2.30 | -16.826 | 56.644 | 52.177 |  | 2.3 | 0.0 | 2.3 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+3 | - | 92.2 | 126.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 12-3 | SGBM13 | Feb 28 2016 1:00PM | Mar 3 2016 9:00AM | Mar 3 2016 1:45PM | Mar 3 2016 6:30PM | 38.745 | 35.025 | -8.04 | 2.20 | -10.239 | 48.984 | 45.264 |  | 2.2 | 0.0 | 2.2 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3 | - | 80.0 | 108.0 | 35.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-1 | SGBM26 | Mar 1 2016 11:00AM | Mar 2 2016 11:00AM | Mar 2 2016 8:00PM | Mar 2 2016 11:45PM | 40.57 | 36.102 | 41.42 | 0.00 | -22.278 | 62.848 | 58.380 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+5 | - | 103.2 | 108.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDD 11-3 | SGBM26 | Feb 29 2016 1:00PM | Feb 29 2016 10:15PM | Mar 1 2016 8:30PM | Mar 2 2016 2:00AM | 40.097 | 35.092 | 41.19 | 0.00 | -22.309 | 62.406 | 57.401 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+4 | - | 101.4 | 115.0 | 13.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 7
FDA 13-6 |  | Feb 26 2016 3:50PM | Feb 28 2016 2:30PM | Mar 1 2016 1:10PM | Mar 1 2016 5:00PM | 38.591 | 35.049 | -15.58 | 1.90 | -17.482 | 56.073 | 52.531 |  | 1.9 | 1.6 | 1.9 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+10 | - | 92.8 | 99.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 9 9
FDD 10-5 |  | Feb 27 2016 11:00AM | Feb 29 2016 10:30AM | Feb 29 2016 8:50PM | Feb 29 2016 11:55PM | 40.508 | 36.102 | 41.49 | 0.00 | -22.511 | 63.019 | 58.613 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+7 | - | 103.6 | 129.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | 3 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 11-1 |  | Feb 26 2016 9:00AM | Feb 27 2016 5:00PM | Feb 27 2016 8:10PM | Feb 28 2016 1:00AM | 40.102 | 35.092 | 41.03 | 0.00 | -21.225 | 61.327 | 56.317 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+4 | - | 99.5 | 122.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 7 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 12-7 | SGBM13 | Feb 23 2016 4:15PM | Feb 26 2016 11:30AM | Feb 27 2016 1:00AM | Feb 27 2016 7:45AM | 39.043 | 35.025 | 40.16 | 0.00 | -25.039 | 64.082 | 60.064 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+9 | - | 106.2 | 149.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDD 12-3 |  | Feb 24 2016 12:30PM | Feb 26 2016 3:00PM | Feb 26 2016 9:10PM | Feb 27 2016 1:25AM | 40.339 | 34.503 | 41.42 | 0.00 | -19.582 | 59.921 | 54.085 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 95.6 | 117.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 10-1 | SGBM32 | Feb 23 2016 1:45PM | Feb 26 2016 10:00AM | Feb 26 2016 4:30PM | Feb 26 2016 8:30PM | 40.184 | 35.351 | 2.58 | 2.75 | -0.169 | 40.353 | 35.520 |  | 2.8 | 2.5 | 2.8 | 28T20 | - | - | T12-150 | - | - | 12+12+12+5 | - | 62.8 | 78.0 | -62.8 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 6 9 9
FDD 10-2 | SGBM26 | Feb 22 2016 10:45AM | Feb 25 2016 1:30PM | Feb 25 2016 7:10PM | Feb 25 2016 11:50PM | 40.487 | 36.102 | 41.24 | 0.00 | -22.606 | 63.093 | 58.708 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+5 | - | 103.8 | 108.0 | 4.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDA 13-5 | SGBM13 | Feb 20 2016 10:00AM | Feb 24 2016 11:00AM | Feb 24 2016 9:50PM | Feb 25 2016 1:30AM | 38.604 | 35.049 | -12.99 | 2.00 | -14.987 | 53.591 | 50.036 |  | 2.0 | 2.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+8 | - | 88.4 | 117.0 | 32.3 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 11-5 | SGBM26 | Feb 22 2016 4:30PM | Feb 24 2016 9:30AM | Feb 24 2016 7:00PM | Feb 24 2016 11:50PM | 39.912 | 35.092 | 40.92 | 0.00 | -22.984 | 62.896 | 58.076 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+4 | - | 102.6 | 117.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 10-4 | SGBM32 | Feb 22 2016 2:00PM | Feb 23 2016 5:00PM | Feb 23 2016 10:55PM | Feb 24 2016 5:15AM | 40.388 | 36.102 | 36.10 | 0.00 | -28.098 | 68.486 | 64.200 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 113.5 | 135.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 12-1 | SGBM26 | Feb 22 2016 8:30AM | Feb 22 2016 6:30PM | Feb 23 2016 1:45AM | Feb 23 2016 5:30AM | 40.357 | 34.503 | 41.33 | 0.00 | -19.075 | 59.432 | 53.578 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+11 | - | 94.7 | 104.0 | 9.3 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 5
FDD 12-5 | SGBM26 | Feb 20 2016 12:00PM | Feb 20 2016 8:00PM | Feb 21 2016 12:30AM | Feb 21 2016 5:30AM | 40.36 | 34.503 | 41.40 | 0.00 | -18.800 | 59.160 | 53.303 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12+6 | - | 94.2 | 122.0 | 27.8 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 12-2 | SGBM13 | Feb 5 2016 11:00AM | Feb 19 2016 6:00PM | Feb 19 2016 11:35PM | Feb 20 2016 3:30AM | 38.984 | 35.025 | -9.96 | 2.65 | -12.610 | 51.594 | 47.635 |  | 2.1 | 2.0 | 2.6 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+5 | - | 84.2 | 104.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 5 9 9 9 9 9 9 9 9 9 9 9
FDD 16-5 | SGBM32 | Feb 19 2016 8:30AM | Feb 19 2016 4:00PM | Feb 19 2016 9:10PM | Feb 20 2016 12:30AM | 42.23 | 35.976 | 43.00 | 0.00 | -5.197 | 47.427 | 41.173 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 72.8 | 81.0 | 11.3 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 11-2 |  | Feb 16 2016 5:00PM | Feb 19 2016 12:00PM | Feb 19 2016 7:00PM | Feb 19 2016 11:55PM | 40.04 | 35.092 | 41.17 | 0.00 | -21.833 | 61.873 | 56.925 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 100.6 | 130.0 | 29.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 4
FDD 12-4 | SGBM26 | Feb 17 2016 8:30AM | Feb 18 2016 9:05AM | Feb 18 2016 8:00PM | Feb 19 2016 12:05PM | 40.356 | 34.503 | 41.28 | 0.00 | -13.715 | 59.271 | 48.218 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+11 | - | 85.2 | 108.0 | 14.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 | 9 9 9 9 9 9 9 9 9 9 9 9
FDD 16-2 | SGBM32 | Feb 17 2016 8:45AM | Feb 17 2016 5:00PM | Feb 17 2016 8:45PM | Feb 18 2016 12:45AM | 41.462 | 35.976 | 42.26 | 0.00 | -5.735 | 47.197 | 41.711 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+11 | - | 73.7 | 81.0 | 9.9 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 16-7 | SGBM32 | Feb 13 2016 2:30PM | Feb 16 2016 3:00PM | Feb 16 2016 7:40PM | Feb 16 2016 10:45PM | 41.869 | 35.976 | 42.75 | 0.00 | -5.651 | 47.520 | 41.627 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 73.6 | 86.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 5 9 9
FDA 12-8 | SGBM13 | Feb 6 2016 11:00AM | Feb 16 2016 10:20AM | Feb 16 2016 1:50PM | Feb 16 2016 8:15PM | 39.193 | 35.025 | -10.95 | 2.25 | -13.204 | 52.397 | 48.229 |  | 2.3 | 2.3 | 2.3 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+6.5 | - | 85.2 | 117.0 | -85.2 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 12-2 | SGBM13 | Feb 13 2016 3:40PM | Feb 15 2016 11:00AM | Feb 15 2016 8:24PM | Feb 16 2016 1:00AM | 40.389 | 34.503 | 41.16 | 0.00 | -18.737 | 59.126 | 53.240 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+11 | - | 94.1 | 117.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 11 13 | 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 16-6 | SGBM32 | Feb 13 2016 10:30AM | Feb 15 2016 11:00AM | Feb 15 2016 6:10PM | Feb 15 2016 10:00PM | 41.94 | 35.976 | 43.07 | 0.00 | -5.434 | 47.374 | 41.410 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 73.2 | 84.0 | 2.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 3 9 9 9 9 9 9 9 9 9
FDD 15-5 | SGBM13 | Feb 14 2016 8:30AM | Feb 15 2016 10:00AM | Feb 15 2016 4:00PM | Feb 15 2016 8:45PM | 39.402 | 37.075 | 40.22 | 0.00 | -7.781 | 47.683 | 44.856 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3 | - | 79.3 | 88.0 | -32.6 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 7 9 9 9
FDD 15-9 | SGBM26 | Feb 11 2016 2:55PM | Feb 12 2016 10:00AM | Feb 12 2016 7:00PM | Feb 12 2016 10:00PM | 39.113 | 37.075 | 39.97 | 0.00 | -8.331 | 47.444 | 45.406 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3 | - | 80.2 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 16-8 | SGBM32 | Feb 5 2016 9:00AM | Feb 12 2016 11:00AM | Feb 12 2016 6:18PM | Feb 12 2016 9:30PM | 42.004 | 35.976 | 43.04 | 0.00 | -5.560 | 47.564 | 41.536 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 73.4 | 90.0 | 22.6 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 16-1 | SGBM32 | Feb 6 2016 8:30AM | Feb 11 2016 11:00AM | Feb 11 2016 3:44PM | Feb 11 2016 7:15PM | 42.139 | 35.976 | 42.77 | 0.00 | -5.630 | 47.769 | 41.606 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 73.5 | 81.0 | 10.2 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 15-2 | SGBM26 | Feb 6 2016 3:00PM | Feb 10 2016 4:30PM | Feb 10 2016 8:10PM | Feb 11 2016 12:00AM | 39.481 | 37.075 | 40.79 | 0.00 | -8.812 | 48.293 | 45.887 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+4 | - | 81.1 | 95.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 9 5
FDD 15-7 | SGBM26 | Feb 4 2016 10:40AM | Feb 5 2016 12:00PM | Feb 5 2016 8:10PM | Feb 5 2016 11:00PM | 39.105 | 37.075 | 40.03 | 0.00 | -8.216 | 47.321 | 45.291 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3 | - | 80.0 | 90.0 | -55.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 16-3 | SGBM32 | Feb 3 2016 4:10PM | Feb 4 2016 5:10PM | Feb 5 2016 3:20PM | Feb 5 2016 7:00PM | 42.123 | 35.976 | 43.10 | 0.00 | -5.101 | 47.224 | 41.077 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 72.6 | 81.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDA 12-9 | SGBM13 | Jan 31 2016 2:20PM | Feb 4 2016 12:00PM | Feb 4 2016 10:10PM | Feb 5 2016 4:00AM | 39.082 | 35.025 | -9.55 -13.65 | 2.00 1.60 | -15.252 | 54.334 | 50.277 |  | 3.6 | 3.6 | 3.5 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+12 | - | 88.9 | 126.0 | 41.8 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDD 15-6 | SGBM26 | Feb 3 2016 9:40AM | Feb 3 2016 8:30PM | Feb 4 2016 3:40AM | Feb 4 2016 6:55AM | 39.355 | 37.075 | 40.24 | 0.00 | -8.463 | 47.818 | 45.538 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3 | - | 80.5 | 93.0 | 23.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 7 5
FDD 16-9 | SGBM32 | Feb 2 2016 10:00AM | Feb 3 2016 6:00PM | Feb 3 2016 10:50PM | Feb 4 2016 2:00AM | 41.899 | 35.976 | 42.91 | 0.00 | -5.393 | 47.292 | 41.369 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 73.1 | 81.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 15-1 | SGBM26 | Feb 2 2016 11:00AM | Feb 2 2016 10:20PM | Feb 3 2016 2:10AM | Feb 3 2016 6:30AM | 39.476 | 37.075 | 40.29 | 0.00 | -8.757 | 48.233 | 45.832 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+3 | - | 81.0 | 90.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 9
FDD 16-4 | SGBM32 | Feb 2 2016 8:00AM | Feb 2 2016 7:00PM | Feb 3 2016 12:30AM | Feb 3 2016 2:45AM | 41.912 | 35.976 | 42.69 | 0.00 | -5.506 | 47.418 | 41.482 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+10 | - | 73.3 | 81.0 | -14.1 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 9
FDD 15-8 | SGBM26 | Jan 31 2016 2:10PM | Feb 1 2016 6:00PM | Feb 2 2016 1:38AM | Feb 2 2016 7:30AM | 39.146 | 37.075 | 40.18 | 0.00 | -8.520 | 47.666 | 45.595 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+4 | - | 80.6 | 83.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 7 4
FDD 17-5 | SGBM32 | Jan 31 2016 8:30AM | Feb 1 2016 10:30AM | Feb 1 2016 5:40PM | Feb 1 2016 8:30PM | 39.598 | 35.856 | 40.56 | 0.00 | -3.735 | 43.333 | 39.591 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 70.0 | 78.0 | -35.7 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 15-3 | SGBM26 | Jan 28 2016 8:15AM | Jan 30 2016 2:20PM | Jan 30 2016 9:45PM | Jan 31 2016 3:00AM | 39.59 | 37.075 | 40.32 | 0.00 | -8.282 | 47.872 | 45.357 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+4 | - | 80.2 | 95.0 | 18.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 | 9 9 9 9 9 9 9 9 9 9 5
FDD 17-2 | SGBM32 | Jan 28 2016 9:30AM | Jan 29 2016 8:00PM | Jan 30 2016 12:00AM | Jan 30 2016 4:00AM | 39.65 | 35.856 | 40.60 | 0.00 | -3.252 | 42.902 | 39.108 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 69.1 | 82.0 | 24.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 6 4
FDD 17-7 | SGBM32 | Jan 27 2016 10:00AM | Jan 28 2016 11:00AM | Jan 28 2016 4:37PM | Jan 28 2016 9:00PM | 39.725 | 35.856 | 40.45 | 0.00 | -3.448 | 43.173 | 39.304 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 69.5 | 82.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 6 4
FDD 17-6 | SGBM32 | Jan 26 2016 10:00AM | Jan 27 2016 2:00PM | Jan 27 2016 7:10PM | Jan 27 2016 10:15PM | 39.72 | 35.856 | 40.81 | 0.00 | -3.487 | 43.207 | 39.343 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 69.5 | 78.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 15-4 | SGBM26 | Jan 25 2016 10:10AM | Jan 26 2016 6:50PM | Jan 27 2016 1:40AM | Jan 27 2016 5:00AM | 39.454 | 37.075 | 40.34 | 0.00 | -8.363 | 47.817 | 45.438 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+12+4 | - | 80.3 | 85.0 | 5.8 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 4
FDD 17-1 | SGBM32 | Jan 25 2016 10:30AM | Jan 26 2016 2:00PM | Jan 26 2016 5:30PM | Jan 26 2016 9:15PM | 39.37 | 35.856 | 40.23 | 0.00 | -3.973 | 43.343 | 39.829 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 70.4 | 78.0 | -70.4 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 17-8 | SGBM32 | Jan 23 2016 8:40AM | Jan 25 2016 11:00AM | Jan 25 2016 5:20PM | Jan 25 2016 8:45PM | 39.816 | 35.856 | 40.81 | 0.00 | -3.786 | 43.602 | 39.642 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 70.1 | 75.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 3
FDD 17-3 | SGBM32 | Jan 21 2016 8:30AM | Jan 23 2016 11:30AM | Jan 23 2016 5:59PM | Jan 23 2016 11:00PM | 39.869 | 35.856 | 40.58 | 0.00 | -3.722 | 43.591 | 39.578 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 69.9 | 78.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
FDD 17-4 | SGBM32 | Jan 19 2016 1:30PM | Jan 22 2016 10:30AM | Jan 22 2016 3:45PM | Jan 22 2016 8:00PM | 39.484 | 35.856 | 40.51 | 0.00 | -3.385 | 42.869 | 39.241 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+11 | - | 69.4 | 85.0 | 22.6 | G40T2 | 1 2 3 4 5 6 7 8 9 10 | 9 9 9 9 9 9 9 9 9 4
FDD 17-9 | SGBM32 | Jan 19 2016 3:30PM | Jan 20 2016 7:30PM | Jan 21 2016 4:45AM | Jan 21 2016 9:00AM | 39.878 | 35.856 | 40.76 | 0.00 | -3.635 | 43.513 | 39.491 |  | 0.0 | 0.0 | 0.0 | 28T20 | - | - | T12-150 | - | - | 12+12+12+8 | - | 69.8 | 78.0 | 11.8 | G40T2 | 1 2 3 4 5 6 7 8 9 | 9 9 9 9 9 9 9 9 6
Total | [10 empty] | 3645.108 | 3294.125 | 0.0 | 46.2 | 38.9 | 42.8 |  | 0.0 |  |  | 0.0 | 0.0 |  |  | 5822.0 | 6963.0

## 2200
Summary List for 18916521-MRT-V1 Spur Line
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T40 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T16 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
FDA 14-4 | SGBM13 | Mar 29 2016 9:00AM | Apr 30 2016 4:40AM | May 2 2016 10:10AM | May 2 2016 5:20PM | 38.638 | 35.475 | -13.17 | 7.35 | -19.765 | 59.153 | 55.240 |  | 7.3 | 7.3 | 7.4 | 44T40 + 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+10 | - | 210.0 | 249.0 | 17.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 8 19 20 21 22 23 24 25 26 27 28 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 6
FDA 15-3 | SGBM26 | Apr 11 2016 11:00AM | Apr 12 2016 2:30PM | Apr 12 2016 11:42PM | Apr 13 2016 4:30AM | 41.898 | 36.975 | 42.75 | 0.00 | 2.746 | 56.152 | 34.229 |  | 0.0 | 0.0 | 0.0 | 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+4 | - | 130.1 | 207.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 15-4 | SGBM26 | Apr 8 2016 11:00AM | Apr 9 2016 2:30AM | Apr 9 2016 8:35PM | Apr 10 2016 1:30AM | 41.894 | 36.975 | 43.06 | 0.00 | 38.060 | 55.934 | -1.085 |  | 0.0 | 0.0 | 0.0 | 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+4 | 0.515 | -4.1 | 189.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 15-1 | SGBM26 | Apr 5 2016 12:00PM | Apr 6 2016 5:35PM | Apr 7 2016 4:20AM | Apr 7 2016 9:10AM | 42.067 | 36.975 | 42.85 | 0.00 | -14.252 | 56.319 | 51.227 |  | 0.0 | 0.0 | 0.0 | 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+4 | - | 194.8 | 194.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 5
FDA 15-2 | SGBM26 | Mar 29 2016 4:30PM | Apr 2 2016 11:00PM | Apr 3 2016 6:00PM | Apr 4 2016 1:00AM | 41.892 | 36.975 | 42.78 | 0.00 | 28.782 | 56.210 | 8.193 |  | 0.0 | 0.0 | 0.0 | 44T40 | - | - | T16-150 | - | - | 12+12+12+12+8 | 9.793 | 31.1 | 198.0 | -3.1 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-3 |  | Mar 21 2016 3:15PM | Mar 26 2016 5:00AM | Mar 3 2016 11:00AM | Mar 27 2016 6:30PM | 38.672 | 35.475 | -12.13 | 6.50 | -18.635 | 57.307 | 54.110 |  | 6.5 | 6.5 | 6.5 | 44T40 + 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+8.8 | - | 205.7 | 234.0 | -100.0 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 6 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-1 | SGBM13 | Mar 13 2016 10:00AM | Mar 18 2016 4:30PM | Mar 20 2016 5:10AM | Mar 20 2016 10:50AM | 38.731 | 35.475 | -12.99 | 6.50 | -19.489 | 58.220 | 54.964 |  | 6.5 | 6.5 | 6.5 | 44T40 + 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+7.3 | - | 209.0 | 225.0 | 3.4 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
FDA 14-2 | SGBM13 | Feb 29 2016 2:00PM | Mar 9 2016 10:00PM | Mar 11 2016 5:30PM | Mar 12 2016 12:55AM | 38.616 | 35.475 | -11.26 | 6.60 | -17.864 | 56.480 | 53.339 |  | 6.4 | 6.4 | 6.6 | 44T40 + 44T40 | - | - | T16-150 | - | - | 12+12+12+12+12+6 | - | 202.8 | 216.0 | 6.5 | G40T2 | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 | 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9 9
Total | [10 empty] | 455.775 | 310.217 | 0.0 | 26.8 | 26.8 | 27.0 |  | 0.0 |  |  | 0.0 | 0.0 |  |  | 1179.4 | 1712.0