## 1200
Summary List for 18916523-MRT-v201
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
DD14-3 | SGBM31 | Nov 24 2016 8:00PM | Nov 26 2016 11:40AM | Nov 26 2016 2:30PM | Nov 26 2016 3:35PM | 38.724 | 32.575 | 27.63 | 2.80 | 24.829 | 13.895 | 7.746 |  | 2.8 | 2.8 | 2.8 | 18T20 | 399.492 | 399.492 | T12-200 | 145.3843 | 145.3843 | 9 | 8.546 | 8.8 | 12.0 | 37.0 | G40T2(ice) | HX026-1 | 12
DD13-2 | SGBM31 | Nov 19 2016 2:40PM | Nov 24 2016 8:10PM | Nov 25 2016 4:15PM | Nov 25 2016 4:55PM | 38.29 | 32.575 | 26.67 | 2.74 | 25.173 | 14.417 | 7.402 |  | 2.7 | 2.7 | 2.8 | 18T20 | 443.880 | 443.880 | T12-200 | 162.6920 | 162.6920 | 10 | 8.202 | 8.4 | 12.0 | 21.9 | G40T2(ice) | HX026-1 | 12
SBS14-4 | SGBM12 | Nov 21 2016 9:40AM | Nov 22 2016 7:30PM | Nov 22 2016 8:10PM | Nov 22 2016 8:50PM | 40.524 | 34.475 | 34.60 | 3.30 | 33.098 | 9.226 | 1.377 |  | 3.3 | 0.0 | 3.3 | 18T20 | 186.430 | 186.430 | T12-200 | 62.3076 | 62.3076 | 4.2 | 2.177 | 1.6 | 7.0 | 15.1 | G40T2(ice) | c570009307 | 7
SBN14-4 | SGBM31 | Nov 21 2016 11:00AM | Nov 22 2016 3:50PM | Nov 22 2016 6:10PM | Nov 22 2016 6:50PM | 40.683 | 34.475 | 31.27 | 2.20 | 29.065 | 11.618 | 5.410 |  | 2.2 | 0.0 | 2.2 | 18T20 | 288.522 | 288.522 | T12-200 | 102.1152 | 102.1152 | 6.5 | 6.210 | 6.1 | 9.0 | 17.1 | G40T2(ice) | c570009304 | 9
DD12-4 | SGBM13 | Nov 19 2016 4:00PM | Nov 21 2016 4:45PM | Nov 21 2016 8:20PM | Nov 21 2016 9:30PM | 38.662 | 35.911 | 28.32 | 3.00 | 26.815 | 13.347 | 9.096 |  | 3.0 | 3.0 | 3.0 | 18T20 | 532.656 | 532.656 | T12-200 | 197.3073 | 197.3073 | 12 | 9.896 | 10.3 | 16.0 | -481.9 | G40T2(ice) | 9298 9299 | 8 8
SBN14-3 | SGBM31 | Nov 17 2016 9:00PM | Nov 19 2016 3:45PM | Nov 19 2016 5:05PM | Nov 19 2016 6:00PM | 40.755 | 34.475 | 31.70 | 2.25 | 29.451 | 11.304 | 5.024 |  | 2.3 | 0.0 | 2.3 | 18T20 | 270.767 | 270.767 | T12-200 | 95.1921 | 95.1921 | 6.1 | 5.824 | 5.7 | 8.0 | -194.6 | G40T2(ice) | c570009284 | 8
SBS14-3 | SGBM31 | Nov 16 2016 11:00AM | Nov 18 2016 5:10PM | Nov 18 2016 9:45PM | Nov 18 2016 10:45PM | 40.541 | 34.475 | 34.58 | 3.10 | 31.481 | 9.060 | 2.994 |  | 3.1 | 0.0 | 3.1 | 18T20 | 186.430 | 186.430 | T12-200 | 62.3076 | 62.3076 | 4.2 | 3.794 | 3.4 | 6.0 | 2.6 | G40T2(ice) | c570009282 | 6
DD12-3 | SGBM13 | Nov 17 2016 9:00AM | Nov 18 2016 9:15AM | Nov 18 2016 2:20PM | Nov 18 2016 4:05PM | 38.612 | 35.911 | 27.90 | 3.00 | 24.897 | 13.715 | 11.014 |  | 3.0 | 3.0 | 3.0 | 18T20 | - | - | T12-200 | - | - | 1.2+12 | 11.814 | 12.5 | 16.0 | -473.7 | G40T2(ice) | 9276 9177 | 8 8
SBS15-4 | SGBM12 | Nov 15 2016 11:00AM | Nov 16 2016 4:30PM | Nov 16 2016 6:20PM | Nov 16 2016 7:30PM | 38.215 | 34.475 | 31.35 | 2.30 | 29.749 | 9.166 | 4.726 |  | 2.3 | 0.0 | 2.3 | 18T20 | 292.961 | 292.961 | T12-200 | 103.8459 | 103.8459 | 6.6 | 5.526 | 5.3 | 9.0 | -266.7 | G40T2(ice) | c570009257 | 9
SBN15-4 | SGBM12 | Nov 14 2016 9:00AM | Nov 15 2016 11:00AM | Nov 15 2016 9:45PM | Nov 15 2016 10:30PM | 38.336 | 34.475 | 33.43 | 2.30 | 31.131 | 7.205 | 3.344 |  | 2.3 | 0.0 | 2.3 | 18T20 | 199.746 | 199.746 | T12-200 | 67.4999 | 67.4999 | 4.5 | 4.144 | 3.8 | 6.0 | 58.6 | G40T2(ice) | c570009246 | 6
SBN14-2 | SGBM31 | Nov 14 2016 7:10PM | Nov 15 2016 5:30PM | Nov 15 2016 8:55PM | Nov 15 2016 10:05PM | 40.826 | 34.475 | 32.90 | 2.50 | 32.305 | 10.421 | 2.170 |  | 2.5 | 0.0 | 2.5 | 18T20 | 230.818 | 230.818 | T12-200 | 79.6152 | 79.6152 | 5.2 | 2.970 | 2.5 | 7.0 | -183.3 | G40T2(ice) | c570009243 | 7
DD12-2 | SGBM13 | Nov 14 2016 9:00AM | Nov 15 2016 3:40PM | Nov 15 2016 8:10PM | Nov 15 2016 10:00PM | 38.741 | 35.911 | 28.29 | 3.00 | 26.795 | 13.456 | 9.116 |  | 3.0 | 3.0 | 0.0 | 18T20 | 532.656 | 532.656 | T12-200 | 197.3073 | 197.3073 | 12 | 9.916 | 10.3 | 15.0 | -441.5 | G40T2(ice) | 9240 9242 | 8 7
SBS14-2 | SGBM31 | Nov 11 2016 2:10PM | Nov 14 2016 6:00PM | Nov 14 2016 9:10PM | Nov 14 2016 10:00PM | 40.728 | 34.475 | 34.69 | 3.20 | 34.088 | 9.240 | 0.387 |  | 3.2 | 0.0 | 3.2 | 18T20 | 181.991 | 181.991 | T12-200 | 60.5768 | 60.5768 | 4.1 | 1.187 | 0.4 | 6.0 | -172.5 | G40T2(ice) | c570009220 | 6
DD12-1 | SGBM13 | Nov 10 2016 4:30PM | Nov 12 2016 11:45AM | Nov 12 2016 5:30PM | Nov 12 2016 9:30PM | 38.8 | 35.911 | 28.99 | 3.00 | 26.492 | 12.818 | 9.419 |  | 3.0 | 3.0 | 3.0 | 18T20 | 488.268 | 488.268 | T12-200 | 179.9996 | 179.9996 | 11 | 10.219 | 10.7 | 17.0 | -487.2 | G40T2(ice) | 9207 9208 9212 | 7 6 4
SBS15-2 | SGBM12 | Nov 9 2016 9:30PM | Nov 12 2016 12:10PM | Nov 12 2016 4:20PM | Nov 12 2016 5:15PM | 38.214 | 34.475 | 31.57 | 2.30 | 29.267 | 8.947 | 5.208 |  | 2.3 | 0.0 | 2.3 | 18T20 | 363.982 | 363.982 | T12-200 | 131.5382 | 131.5382 | 8.2 | 6.008 | 5.9 | 12.0 | 6.1 | G40T2(ice) | C570009206 | 12
SBN14-1 | SGBM31 | Nov 11 2016 4:40PM | Nov 12 2016 1:00PM | Nov 12 2016 3:45PM | Nov 12 2016 4:50PM | 40.894 | 34.475 | 31.87 | 2.45 | 30.771 | 11.473 | 3.704 |  | 2.5 | 0.0 | 2.5 | 18T20 | 275.206 | 275.206 | T12-200 | 96.9229 | 96.9229 | 6.2 | 4.504 | 4.2 | 9.0 | -209.8 | G40T2(ice) | c570009204 | 9
SBN15-2 | SGBM12 | Nov 9 2016 8:50AM | Nov 11 2016 4:05PM | Nov 11 2016 6:30PM | Nov 11 2016 7:15PM | 38.309 | 34.475 | 31.79 | 3.28 | 29.409 | 9.800 | 5.066 |  | 3.3 | 0.0 | 2.6 | 18T20 | 301.838 | 301.838 | T12-200 | 107.3075 | 107.3075 | 6.8 | 5.866 | 5.7 | 9.0 | -271.7 | G40T2(ice) | c570009202 | 9
SBS14-1 | SGBM31 | Nov 8 2016 5:40PM | Nov 9 2016 9:10PM | Nov 9 2016 10:20PM | Nov 9 2016 11:10PM | 40.669 | 34.475 | 34.39 | 3.00 | 31.386 | 9.283 | 3.089 |  | 3.0 | 0.0 | 3.0 | 18T20 | 181.991 | 181.991 | T12-200 | 60.5768 | 60.5768 | 4.1 | 3.889 | 3.5 | 6.0 | -175.7 | G40T2(ice) | c570009185 | 6
SBS15-3 | SGBM31 | Nov 7 2016 2:50PM | Nov 9 2016 9:45AM | Nov 9 2016 5:50PM | Nov 9 2016 6:30PM | 38.266 | 34.475 | 32.27 | 2.30 | 29.969 | 8.297 | 4.506 |  | 2.3 | 0.0 | 2.3 | 18T20 | 253.012 | 253.012 | T12-200 | 88.2691 | 88.2691 | 5.7 | 5.306 | 5.1 | 8.0 | -247.5 | G40T2(ice) | c570009173 | 8
SBN15-3 | SGBM12 | Nov 5 2016 10:30PM | Nov 7 2016 9:00PM | Nov 7 2016 10:30PM | Nov 7 2016 11:15PM | 38.29 | 34.475 | 33.01 | 2.30 | 33.007 | 7.583 | 1.468 |  | 2.3 | 0.0 | 2.3 | 18T20 | 213.062 | 213.062 | T12-200 | 72.6922 | 72.6922 | 4.8 | 2.268 | 1.7 | 7.0 | -223.0 | G40T2(ice) | c570009162 | 7
DD23-4 | SGBM13 | Nov 3 2016 1:30PM | Nov 5 2016 9:40AM | Nov 5 2016 7:30PM | Nov 5 2016 10:45PM | 41.092 | 37.775 | 21.45 | 6.60 | 14.847 | 26.245 | 22.928 |  | 6.6 | 6.6 | 0.0 | 22T20 | - | - | T12-200 | - | - | 2+12+12 | - | 25.9 | 35.0 | -792.0 | G40T2(ice) | 9140 9141 9143 9144 | 9 9 9 8
SBS15-1 | SGBM12 | Nov 4 2016 4:00PM | Nov 5 2016 5:30PM | Nov 5 2016 8:20PM | Nov 5 2016 9:15PM | 38.352 | 34.475 | 31.80 | 2.50 | 31.801 | 9.051 | 2.674 |  | 2.5 | 0.0 | 2.5 | 18T20 | 230.818 | 230.818 | T12-200 | 79.6152 | 79.6152 | 5.2 | 3.474 | 3.0 | 8.0 | 2.1 | G40T2(ice) | c570009142 | 8
SBN15-1 | SGBM12 | Nov 3 2016 11:00AM | Nov 4 2016 9:30PM | Nov 4 2016 11:00PM | Nov 4 2016 11:40PM | 38.097 | 34.475 | 33.21 | 2.30 | 30.909 | 7.188 | 3.566 |  | 2.3 | 0.0 | 2.3 | 18T20 | 199.746 | 199.746 | T12-200 | 67.4999 | 67.4999 | 4.5 | 4.366 | 4.0 | 8.0 | 6.6 | G40T2(ice) | c570009134 | 8
DD13-4 | SGBM13 | Nov 3 2016 9:00AM | Nov 4 2016 12:51PM | Nov 4 2016 5:30PM | Nov 4 2016 6:30PM | 38.157 | 32.575 | 26.15 | 2.80 | 24.151 | 14.806 | 8.424 |  | 2.8 | 2.8 | 2.8 | 18T20 | 488.268 | 488.268 | T12-200 | 179.9996 | 179.9996 | 11 | 9.224 | 9.5 | 14.0 | 3.6 | G40T2(ice) | 9127 9128 | 7 7
SBN16-1 | SGBM12 | Oct 31 2016 3:00PM | Nov 2 2016 11:00PM | Nov 3 2016 2:45PM | Nov 3 2016 3:55PM | 38.116 | 34.275 | 28.66 | 2.20 | 26.462 | 11.654 | 7.813 |  | 2.2 | 0.0 | 2.2 | 18T20 | 399.492 | 399.492 | T12-200 | 145.3843 | 145.3843 | 9 | 8.613 | 8.8 | 13.0 | -100.0 | G40T2(ice) | c570009108 Pending | 7 6
DD14-4 | SGBM31 | Oct 28 2016 4:30PM | Nov 1 2016 9:45PM | Nov 2 2016 3:45PM | Nov 2 2016 5:50PM | 38.695 | 32.575 | 29.69 | 4.46 | 27.690 | 13.505 | 4.885 |  | 4.5 | 4.5 | 4.5 | 18T20 | 399.492 | 399.492 | T12-200 | 145.3843 | 145.3843 | 9 | 5.685 | 5.5 | 13.0 | 55.6 | G40T2(ice) | 9098 9100 | 7 6
DD23-3 | SGBM13 | Oct 28 2016 4:00PM | Nov 1 2016 2:10PM | Nov 1 2016 10:30PM | Nov 2 2016 1:30AM | 41.273 | 37.775 | 20.80 | 6.60 | 14.204 | 27.069 | 23.571 |  | 6.6 | 6.6 | 6.6 | 22T20 | - | - | T12-200 | - | - | 2.7+12+12 | - | 26.7 | 36.0 | 41.1 | G40T2(ice) | 9091 9092 Pending 9094 | 9 9 9 9
SBS16-2 | SGBM12 | Oct 28 2016 11:30AM | Nov 1 2016 5:15PM | Nov 1 2016 8:50PM | Nov 1 2016 9:45PM | 38.068 | 34.475 | 28.70 | 2.20 | 26.504 | 11.564 | 7.971 |  | 2.2 | 0.0 | 2.2 | 18T20 | 399.492 | 399.492 | T12-200 | 145.3843 | 145.3843 | 9 | 8.771 | 9.0 | 13.0 | -100.0 | G40T2(ice) | c570009089 Pending | 7 6
SBN16-2 | SGBM12 | Oct 27 2016 9:09AM | Oct 28 2016 12:45PM | Oct 28 2016 6:15PM | Oct 28 2016 8:00PM | 38.188 | 34.275 | 29.69 | 2.20 | 27.490 | 10.698 | 6.785 |  | 2.2 | 0.0 | 2.2 | 18T20 | 355.104 | 355.104 | T12-200 | 128.0767 | 128.0767 | 8 | 7.585 | 7.7 | 15.0 | 95.4 | G40T2(ice) | c570009061 c570009062 | 8 7
DD13-3 | SGBM31 | Oct 26 2016 11:30AM | Oct 28 2016 10:15AM | Oct 28 2016 12:00PM | Oct 28 2016 1:00PM | 38.114 | 32.575 | 26.75 | 2.80 | 24.250 | 14.174 | 8.325 |  | 2.8 | 2.8 | 2.8 | 18T20 | 443.880 | 443.880 | T12-200 | 162.6920 | 162.6920 | 10 | 9.125 | 9.4 | 12.0 | 22.9 | G40T2(ice) | HX024-1 | 12
SBS16-4 | SGBM12 | Oct 25 2016 7:00PM | Oct 27 2016 12:00AM | Oct 27 2016 8:35PM | Oct 27 2016 10:00PM | 38.155 | 34.475 | 27.59 | 2.25 | 31.038 | 12.817 | 3.437 |  | 2.3 | 0.0 | 2.3 | 18T20 | 443.880 | 443.880 | T12-200 | 162.6920 | 162.6920 | 10 | 4.237 | 3.9 | 15.0 | 45.1 | G40T2(ice) | c570009057 c570009058 | 8 7
DD23-1 | SGBM13 | Oct 25 2016 9:00AM | Oct 26 2016 5:15PM | Oct 27 2016 2:30PM | Oct 27 2016 7:45PM | 41.301 | 37.775 | 17.03 | 6.59 | 10.431 | 30.870 | 27.344 |  | 6.6 | 6.6 | 6.6 | 22T20 | - | - | T12-200 | - | - | 6.5+12+12 | - | 30.9 | 41.0 | -100.0 | G40T2(ice) | HX024-1 HX026-1 HX024-2 H9220-1 | 12 12 11 6
SBN16-4 | SGBM12 | Oct 24 2016 9:00AM | Oct 25 2016 6:30PM | Oct 25 2016 9:55PM | Oct 26 2016 12:30AM | 38.318 | 34.275 | 27.66 | 2.25 | 25.410 | 12.908 | 8.865 |  | 2.3 | 0.0 | 2.3 | 18T20 | 443.880 | 443.880 | T12-200 | 162.6920 | 162.6920 | 10 | 9.665 | 10.0 | 16.0 | 59.6 | G40T2(ice) | c570009035 c57009036 c57009037 | 7 6 3
SBS16-1 | SGBM12 | Oct 22 2016 3:40PM | Oct 24 2016 4:00PM | Oct 24 2016 8:15PM | Oct 24 2016 9:00PM | 38.039 | 34.475 | 29.64 | 2.30 | 27.345 | 10.694 | 7.130 |  | 2.3 | 0.0 | 2.3 | 18T20 | 377.298 | 377.298 | T12-200 | 136.7305 | 136.7305 | 8.5 | 7.930 | 8.1 | 11.0 | -100.0 | G40T2(ice) | c570009015 | 11
DD23-2 | SGBM13 | Oct 19 2016 6:00PM | Oct 22 2016 7:30PM | Oct 23 2016 12:19AM | Oct 23 2016 3:30AM | 41.33 | 37.775 | 18.21 | 6.60 | 11.610 | 29.720 | 26.165 |  | 6.6 | 6.3 | 1.5 | 22T20(3) | 1627.5600 | 1627.6 | T12-200(3) | 456.0903 | 456.1 | 6+12+12 | - | 29.6 | 40.0 | -100.0 | G40T2(ice) | C570008997 C570008998 C570008999 C570009000 | 12 10 9 9
DD15-3 | SGBM31 | Oct 19 2016 4:00PM | Oct 22 2016 4:30PM | Oct 22 2016 7:30PM | Oct 22 2016 9:00PM | 38.584 | 32.575 | 25.33 | 2.80 | 23.184 | 16.055 | 9.391 |  | 2.8 | 2.8 | 2.8 | 18T20 | 532.656 | 532.656 | T12-200 | 197.3073 | 197.3073 | 12 | 10.191 | 10.6 | 16.0 | -11.4 | G40T2(ice) | C570008994 C570008995 | 8 8
SBN16-3 | SGBM12 | Oct 10 2016 3:20PM | Oct 21 2016 4:40PM | Oct 21 2016 6:50PM | Oct 21 2016 7:50PM | 38.123 | 34.275 | 28.35 | 2.25 | 26.106 | 12.027 | 8.169 |  | 2.3 | 2.3 | 0.0 | 18T20 | - | - | T12-200 | - | - |  | 8.969 | 9.2 | 13.0 | 40.5 | G40T2(ice) | C570008965 C570008968 | 7 6
DD14-2 | SGBM31 | Oct 12 2016 5:10PM | Oct 19 2016 2:00PM | Oct 21 2016 12:30AM | Oct 21 2016 1:40AM | 38.556 | 32.575 | 25.06 | 2.80 | 22.262 | 16.294 | 10.313 |  | 2.8 | 2.8 | 2.8 | 18T20(2) | 843.3720 | 843.4 | T12-200(2) | 288.6959 | 288.7 | 7+12 | - | 11.7 | 26.0 | 122.9 | G40T2(ice) | C570008950 C570008951 C570008952 | 10 10 6
DD15-2 | SGBM31 | Oct 13 2016 10:20AM | Oct 15 2016 6:50PM | Oct 15 2016 9:45PM | Oct 15 2016 11:20PM | 38.38 | 32.575 | 25.98 | 2.80 | 23.182 | 15.198 | 9.393 |  | 2.8 | 2.8 | 2.8 | 18T20 | 532.656 | 532.656 | T12-200 | 197.3073 | 197.3073 | 12 | 10.193 | 10.6 | 14.0 | -100.0 | G40T2(ice) | C570008900 Pending | 7 7
DD13-1 | SGBM31 | Oct 8 2016 10:30AM | Oct 13 2016 11:50AM | Oct 13 2016 2:25PM | Oct 13 2016 3:40PM | 38.017 | 32.575 | 26.07 | 2.80 | 23.284 | 14.743 | 9.291 |  | 2.8 | 2.8 | 2.8 | 18T20 | 488.268 | 488.268 | T12-200 | 179.9996 | 179.9996 | 11 | 10.091 | 10.5 | 14.0 | -100.0 | G40T2(ice) | C570008852 C570008853 | 7 7
DD15-4 | SGBM31 | Oct 8 2016 1:30PM | Oct 11 2016 12:45PM | Oct 11 2016 5:30PM | Oct 11 2016 6:20PM | 38.346 | 32.575 | 25.13 | 2.80 | 22.328 | 16.018 | 10.247 |  | 2.8 | 2.8 | 2.8 | 18T20 | 510.462 | 510.462 | T12-200 | 188.6535 | 188.6535 | 11.5 | 11.047 | 11.6 | 14.0 | -100.0 | G40T2(ice) | C570008832 C570008833 | 7 7
SBS16-3 | SGBM12 | Oct 7 2016 6:00PM | Oct 10 2016 5:10PM | Oct 10 2016 6:20PM | Oct 10 2016 8:10PM | 38.1 | 34.475 | 28.66 | 2.20 | 26.468 | 11.642 | 8.007 |  | 2.2 | 2.2 | 2.2 | 18T20 | 399.492 | 399.492 | T12-200 | 145.3843 | 145.3843 | 9 | 8.807 | 9.1 | 15.0 | -100.0 | G40T2(ice) | C570008809 C570008818 | 12 3
DD14-1 | SGBM31 | Oct 6 2016 8:20AM | Oct 8 2016 4:10PM | Oct 8 2016 5:15PM | Oct 8 2016 5:35PM | 38.534 | 32.575 | 28.78 | 2.92 | 25.866 | 12.678 | 6.709 |  | 2.9 | 2.9 | 2.9 | 18T20 | 355.104 | 355.104 | T12-200 | 128.0767 | 128.0767 | 8 | 7.509 | 7.6 | 11.0 | -100.0 | G40T2(ice) | C570008791 | 11
DD15-1 | SGBM31 | Oct 1 2016 11:10AM | Oct 5 2016 6:45PM | Oct 5 2016 11:40PM | Oct 6 2016 2:35AM | 38.339 | 32.575 | 25.84 | 2.81 | 23.031 | 15.308 | 9.544 |  | 2.8 | 2.8 | 2.8 | 18T20 | 488.268 | 488.268 | T12-200 | 179.9996 | 179.9996 | 11 | 10.344 | 10.8 | 15.0 | -100.0 | G40T2(ice) | C570008755 C570008756 | 12 3
DD18-4 | SGBM13 | Sep 24 2016 9:30AM | Oct 1 2016 4:30PM | Oct 2 2016 12:45AM | Oct 2 2016 1:05AM | 38.875 | 32.575 | 35.73 | 6.20 | 30.735 | 9.340 | 1.840 |  | 6.2 | 0.0 | 3.0 | 18T20 | 199.746 | 199.746 | T12-200 | 67.4999 | 67.4999 | 4.5 | 2.640 | 2.1 | 6.0 | -100.0 | G40T2 | C570008706 | 6
DD16-4 | SGBM31 | Sep 24 2016 1:45PM | Sep 27 2016 8:20PM | Oct 1 2016 9:30PM | Oct 1 2016 9:50PM | 38.491 | 32.575 | 27.83 | 3.10 | 24.726 | 13.765 | 7.849 |  | 3.1 | 0.0 | 3.1 | 18T20 | 399.492 | 399.492 | T12-200 | 145.3843 | 145.3843 | 9 | 8.649 | 8.9 | 11.0 | -100.0 | G40T2 | C570008688 | 11
DD16-3 | SGBM31 | Sep 19 2016 1:00PM | Sep 22 2016 6:15PM | Sep 22 2016 9:00PM | Sep 22 2016 10:10PM | 38.426 | 32.575 | 28.19 | 3.00 | 25.203 | 13.233 | 7.372 |  | 3.0 | 0.0 | 3.0 | 18T20 | 355.104 | 355.104 | T12-200 | 128.0767 | 128.0767 | 8 | 8.172 | 8.3 | 10.0 | 19.8 | G40T2 | C570008588 | 10
DD18-1 | SGBM13 | Sep 19 2016 6:00PM | Sep 22 2016 10:00AM | Sep 22 2016 7:35PM | Sep 22 2016 7:50PM | 38.855 | 32.575 | 32.45 | 3.00 | 29.751 | 9.404 | 2.824 |  | 3.0 | 0.0 | 3.1 | 18T20 | 199.746 | 199.746 | T12-200 | 67.4999 | 67.4999 | 4.5 | 3.624 | 3.2 | 6.0 | 69.8 | G40T2 | C570008586 | 6
DD17-4 | SGBM12 | Sep 19 2016 10:30AM | Sep 21 2016 12:30PM | Sep 21 2016 10:20PM | Sep 21 2016 11:30PM | 38.648 | 32.575 | 31.03 | 3.20 | 28.015 | 10.823 | 4.560 |  | 3.2 | 0.0 | 3.2 | 18T20 | 266.328 | 266.328 | T12-200 | 93.4614 | 93.4614 | 6 | 5.360 | 5.2 | 8.0 | 48.9 | G40T2 | c570008577 | 8
DD17-3 | SGBM12 | Sep 9 2016 11:40AM | Sep 17 2016 8:15PM | Sep 17 2016 10:50PM | Sep 17 2016 11:15PM | 38.76 | 32.575 | 33.00 | 3.60 | 29.411 | 9.359 | 3.164 |  | 3.6 | 0.0 | 3.6 | 18T20 | 199.746 | 199.746 | T12-200 | 67.4999 | 67.4999 | 4.5 | 3.964 | 3.6 | 5.0 | 39.3 | G40T2 | C570008490 | 5
DD16-1 | SGBM31 | Sep 15 2016 4:20PM | Sep 17 2016 6:00PM | Sep 17 2016 9:50PM | Sep 17 2016 11:10PM | 38.55 | 32.575 | 29.53 | 3.00 | 26.540 | 12.020 | 6.035 |  | 3.0 | 0.0 | 3.0 | 18T20 | - | - | T12-200 | - | - | 6.045+1 | 6.835 | 6.8 | 9.0 | -100.0 | G40T2 | C570008485 | 9
DD18-3 | SGBM12 | Sep 6 2016 1:30PM | Sep 15 2016 11:30AM | Sep 15 2016 6:20PM | Sep 15 2016 7:00PM | 38.881 | 32.575 | 35.39 | 5.90 | 29.505 | 9.386 | 3.070 |  | 5.9 | 0.0 | 3.0 | 18T20 | 221.940 | 221.940 | T12-200 | 76.1537 | 76.1537 | 5 | 3.870 | 3.5 | 7.0 | 100.9 | G40T2 | C570008460 | 7
DD16-2 | SGBM12 | Sep 9 2016 2:45PM | Sep 13 2016 6:15PM | Sep 13 2016 8:30PM | Sep 13 2016 8:50PM | 38.52 | 32.575 | 30.15 | 3.00 | 28.046 | 11.374 | 4.529 |  | 3.0 | 0.0 | 3.0 | 18T20 | - | - | T12-200 | - | - | 5.5+1 | 5.329 | 5.1 | 8.0 | 1.9 | G40T2 | C570008437 | 8
DD17-1 | SGBM12 | Sep 4 2016 10:30AM | Sep 6 2016 8:15PM | Sep 7 2016 11:30AM | Sep 7 2016 12:15PM | 38.825 | 32.575 | 32.20 | 3.11 | 30.085 | 9.740 | 2.490 |  | 3.1 | 0.0 | 3.1 | 18T20 | 199.746 | 199.746 | T12-200 | 67.4999 | 67.4999 | 4.5 | 3.290 | 2.8 | 6.0 | 52.0 | G40T2 | c570008371 | 6
DD17-2 | SGBM12 | Aug 27 2016 6:45PM | Aug 29 2016 5:40PM | Aug 29 2016 10:55PM | Aug 29 2016 12:15AM | 39.005 | 32.575 | 32.77 | 3.12 | 29.650 | 9.355 | 2.925 |  | 3.1 | 0.0 | 3.1 | 18T20 | 213.062 | 213.062 | T12-200 | 72.6922 | 72.6922 | 4.8 | 3.725 | 3.3 | 5.0 | 51.1 | G40T2 | C500065060 | 5
DD18-2 | SGBM12 | Aug 22 2016 1:30PM | Aug 27 2016 11:30AM | Aug 27 2016 6:40PM | Aug 27 2016 8:10PM | 38.962 | 32.575 | 35.38 | 5.82 | 30.580 | 9.402 | 1.995 |  | 5.8 | 0.0 | 5.8 | 18T20 | 177.552 | 177.552 | T12-200 | 58.8460 | 58.8460 | 4 | 2.795 | 2.3 | 6.0 | -100.0 | G40T2 | C570008217 | 6
DD11-1 | [5 empty] | 0 | 35.799 |  |  | 0.000 | 0.000 | 35.799 |  | 0.0 | 0.0 | 0.0 | 20T20 | - | - | T12-200 | - | - |  | - | 40.5 | 0.0 | 0.0 | G40T2(ice)
DD11-2 | [5 empty] | 0 | 35.799 |  |  | 0.000 | 0.000 | 35.799 |  | 0.0 | 0.0 | 0.0 | 20T20 | - | - | T12-200 | - | - |  | - | 40.5 | 0.0 | 0.0 | G40T2(ice)
DD11-3 | [5 empty] | 0 | 35.799 |  |  | 0.000 | 0.000 | 35.799 |  | 0.0 | 0.0 | 0.0 | 20T20 | - | - | T12-200 | - | - |  | - | 40.5 | 0.0 | 0.0 | G40T2(ice)
DD11-4 | [5 empty] | 0 | 35.799 |  |  | 0.000 | 0.000 | 35.799 |  | 0.0 | 0.0 | 0.0 | 20T20 | - | - | T12-200 | - | - |  | - | 40.5 | 0.0 | 0.0 | G40T2(ice)
Total | [10 empty] | 714.398 | 545.062 | 0.0 | 179.2 | 77.9 | 155.5 |  | 18215.4 | 18215.4 |  | 6395.7 | 6395.7 |  |  | 616.5 | 712.0

## 1350
Summary List for 18916523-MRT-v201
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [9 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T25 Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T10 Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
CBP103 | SGBM10 | Nov 30 2016 11:30AM | Dec 3 2016 9:30PM | Dec 3 2016 11:40PM | Dec 4 2016 1:15AM | 43.533 | 42.075 | 31.28 | 3.00 | 28.283 | 15.250 | 13.792 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+4.1 | - | 19.7 | 26.0 | 29.7 | G40T2 | c570009429 c570009429 Pending | 9 9 8
CBP91 | SGBM10 | Dec 1 2016 6:30PM | Dec 2 2016 9:30PM | Dec 2 2016 10:20PM | Dec 3 2016 1:00AM | 43.488 | 42.075 | 31.67 | 3.00 | 28.673 | 14.815 | 13.402 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+3.7 | - | 19.2 | 27.0 | -886.5 | G40T2 | c570009415 c57009417 c570009418 | 11 8 8
CBP68 | SGBM02 | Nov 30 2016 10:00AM | Nov 30 2016 10:30PM | Nov 30 2016 11:00PM | Dec 1 2016 1:45AM | 43.545 | 42.075 | 33.27 | 3.05 | 36.518 | 13.327 | 5.557 |  | 3.0 | 0.1 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+2.1 | 6.557 | 8.0 | 25.0 | 28.5 | G40T2 | c570009394 c570009396 c570009395 | 9 8 8
CBP62 | SGBM02 | Nov 28 2016 6:45PM | Nov 29 2016 7:25PM | Nov 30 2016 12:05AM | Nov 30 2016 2:40AM | 43.357 | 42.075 | 31.15 | 3.00 | 28.150 | 15.207 | 13.925 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+4.2 | - | 19.9 | 28.0 | 31.4 | G40T2 | c570009370 c570009371 c570009372 | 10 9 9
CBP84 | SGBM10 | Nov 28 2016 11:00AM | Nov 29 2016 4:30PM | Nov 29 2016 8:15PM | Nov 29 2016 10:05PM | 43.548 | 42.075 | 33.45 | 3.00 | 31.547 | 13.101 | 10.528 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+2.5 | 11.528 | 15.1 | 25.0 | 28.7 | G40T2 | c570009362 c570009364 c570009365 | 9 8 8
CBP52 | SGBM02 | Nov 26 2016 10:50AM | Nov 28 2016 6:45PM | Nov 28 2016 8:05PM | Nov 28 2016 10:00PM | 43.364 | 42.075 | 28.43 | 3.05 | 28.429 | 17.985 | 13.646 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7 | - | 19.5 | 31.0 | 34.4 | G40T2 | c5790009352 c570009353 c570009354 | 10 11 10
CBP109 | SGBM10 | Nov 24 2016 9:45PM | Nov 26 2016 5:30PM | Nov 26 2016 9:00PM | Nov 27 2016 12:00AM | 43.931 | 42.075 | 30.33 | 3.00 | 27.325 | 16.606 | 14.750 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5.1 | - | 21.1 | 30.0 | 42.1 | G40T2 | c570009344 c570009345 c570009346 | 10 11 9
CBP70 | SGBM02 | Nov 24 2016 9:10PM | Nov 25 2016 9:30PM | Nov 25 2016 10:20PM | Nov 25 2016 11:55PM | 43.61 | 42.075 | 34.36 | 3.00 | 31.357 | 12.253 | 10.718 |  | 3.0 | 0.0 | 3.0 | 25T25 | 1156.200 | 1156.200 | - | T10-125 | 363.6522 | 363.6522 | - | 12 | 11.718 | 15.3 | 22.0 | 25.6 | G40T2 | c570009338 c570009339 | 12 10
DD22-4 | SGBM13 | Nov 21 2016 3:30PM | Nov 24 2016 4:30PM | Nov 25 2016 12:10AM | Nov 25 2016 3:00AM | 39.536 | 32.275 | 15.59 | 2.40 | 13.593 | 26.343 | 18.682 |  | 2.4 | 2.4 | 2.4 | 22T20 | - | - | - | T12-200 | - | - | - | 9.5+12 | - | 26.7 | 39.0 | 42.8 | G40T2(ice) | H9220-1 HX021-1 HX022-1 H9138-1 | 10 12 12 5
CBP60 | SGBM02 | Nov 22 2016 9:30PM | Nov 24 2016 3:45PM | Nov 24 2016 11:05PM | Nov 25 2016 1:50AM | 43.404 | 42.075 | 31.16 | 3.05 | 28.110 | 15.294 | 13.965 |  | 9.1 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5.5 | - | 20.0 | 27.0 | 21.5 | G40T2 | c570009327 c570009328 c570009329 | 9 9 9
CBP89 | SGBM10 | Nov 23 2016 10:50AM | Nov 24 2016 2:50PM | Nov 24 2016 4:20PM | Nov 24 2016 6:05PM | 43.602 | 42.075 | 32.07 | 3.00 | 29.070 | 14.532 | 13.005 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+3.3 | - | 18.6 | 27.0 | 30.9 | G40T2 | c570009324 c570009325 c570009326 | 9 9 9
CBP110 | SGBM10 | Nov 21 2016 3:40PM | Nov 22 2016 9:35PM | Nov 22 2016 11:50PM | Nov 23 2016 2:40AM | 43.817 | 42.075 | 30.36 | 3.00 | 30.358 | 16.459 | 11.717 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+3.8 | - | 16.8 | 30.0 | 42.4 | G40T2 | c570009312 c570009313 c570009314 | 10 10 10
CBP49 | SGBM02 | Nov 21 2016 10:55AM | Nov 22 2016 6:15PM | Nov 22 2016 8:45PM | Nov 22 2016 11:15PM | 43.492 | 42.075 | 29.03 | 3.05 | 27.428 | 17.514 | 14.647 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5.1 | - | 21.0 | 30.0 | 33.4 | G40T2 | c570009308 c570009309 c570009310 | 10 10 10
CBP59 | SGBM02 | Nov 18 2016 1:00PM | Nov 19 2016 11:20PM | Nov 20 2016 1:10AM | Nov 20 2016 3:00AM | 43.487 | 42.075 | 30.77 | 3.00 | 27.774 | 15.713 | 14.301 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+4.6 | - | 20.5 | 30.0 | 46.5 | G40T2 | c570009293 c570009294 c570009295 | 10 10 10
CBP101 | SGBM10 | Nov 18 2016 10:25AM | Nov 19 2016 8:45PM | Nov 19 2016 9:50PM | Nov 20 2016 12:45AM | 43.59 | 42.075 | 30.79 | 3.05 | 29.345 | 15.845 | 12.730 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+3.3 | - | 18.2 | 30.0 | -884.9 | G40T2 | c570009289 c570009290 Pending | 10 10 10
CBP51 | SGBM02 | Nov 12 2016 3:25PM | Nov 14 2016 11:00PM | Nov 18 2016 12:00AM | Nov 18 2016 2:15AM | 43.474 | 42.075 | 28.91 | 3.00 | 25.915 | 17.559 | 16.160 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5.2 | - | 23.1 | 31.0 | 34.0 | G40T2 | c570009271 c570009273 c570009274 | 10 11 10
CBP112 | SGBM10 | Nov 9 2016 9:50AM | Nov 17 2016 5:00PM | Nov 17 2016 9:05PM | Nov 17 2016 11:30PM | 43.724 | 42.075 | 29.42 | 3.00 | 26.722 | 17.302 | 15.353 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+4.6 | - | 22.0 | 31.0 | 34.8 | G40T2 | c570009267 c570009268 c570009270 | 10 11 10
CBP44 | SGBM02 | Nov 8 2016 11:00AM | Nov 9 2016 7:15PM | Nov 9 2016 8:15PM | Nov 9 2016 10:40PM | 43.596 | 42.075 | 38.53 | 14.10 | 24.427 | 19.169 | 17.648 |  | 14.1 | 0.0 | 3.1 | 25T25 | - | - | - | T10-125 | - | - | - | 12+8 | - | 25.3 | 32.0 | 6.7 | G40T2 | c570009178 c57000179 c570009184 | 10 12 10
CBP100 | SGBM02 | Nov 7 2016 9:45AM | Nov 8 2016 11:40AM | Nov 8 2016 2:55PM | Nov 8 2016 5:10PM | 43.128 | 42.075 | 31.38 | 3.10 | 28.283 | 14.845 | 13.792 |  | 3.1 | 0.0 | 3.1 | 25T25 | - | - | - | T10-125 | - | - | - | 12+4.1 | - | 19.7 | 27.0 | 30.7 | G40T2 | c570009170 c570009171 c570009172 | 9 9 9
CBP50 | SGBM02 | Nov 5 2016 9:10PM | Nov 7 2016 9:10PM | Nov 7 2016 11:40PM | Nov 8 2016 1:00AM | 43.546 | 42.075 | 28.91 | 3.05 | 28.911 | 17.685 | 13.164 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 6.5+12 | - | 18.8 | 31.0 | 33.6 | G40T2 | c570009165 c570009166 c570009168 | 10 10 11
CBP111 | SGBM10 | Nov 4 2016 4:30PM | Nov 5 2016 9:25PM | Nov 5 2016 11:55PM | Nov 6 2016 2:15AM | 43.765 | 42.075 | 29.62 | 3.00 | 28.815 | 17.150 | 13.260 |  | 3.0 | 0.0 | 3.0 | 25T25 | 867.150 | 867.150 | - | T10-125 | 265.5887 | 265.5887 | - | 9 | - | 19.0 | 31.0 | -952.6 | G40T2 | c570009145 c570009146 c570009147 | 10 10 11
CBP42 | SGBM02 | Nov 4 2016 11:25AM | Nov 5 2016 3:15PM | Nov 5 2016 5:15PM | Nov 5 2016 8:45PM | 43.55 | 42.075 | 27.26 | 3.00 | 24.263 | 19.287 | 17.812 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7 | - | 25.5 | 32.0 | 25.5 | G40T2 | c570009137 c570009138 Pending | 12 10 10
CBP58 | SGBM02 | Nov 2 2016 10:10AM | Nov 3 2016 4:00PM | Nov 3 2016 10:55PM | Nov 4 2016 2:00AM | 43.427 | 42.075 | 30.13 | 3.00 | 28.629 | 16.298 | 13.446 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5.5 | - | 19.2 | 30.0 | -954.0 | G40T2 | c570009116 c570009117 c570009118 | 10 10 10
CBP105 | SGBM10 | Oct 31 2016 9:00PM | Nov 2 2016 9:50PM | Nov 3 2016 6:15PM | Nov 3 2016 8:30PM | 43.6 | 42.075 | 30.33 | 3.00 | 27.828 | 16.272 | 14.247 |  | 3.0 | 0.1 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5 | - | 20.4 | 30.0 | -889.9 | G40T2 | c570009110 c570009112 c570009113 | 10 10 10
CBP43 | SGBM02 | Oct 31 2016 12:45PM | Nov 1 2016 4:00PM | Nov 1 2016 7:20PM | Nov 1 2016 8:40PM | 43.478 | 42.075 | 27.31 | 3.00 | 24.315 | 19.163 | 17.760 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+8.1 | - | 25.4 | 31.0 | -100.0 | G40T2 | c570009086 c570009087 c570009088 | 10 10 11
CBP113 | SGBM10 | Oct 27 2016 2:10PM | Oct 31 2016 1:20PM | Oct 31 2016 4:25PM | Oct 31 2016 6:30PM | 43.852 | 42.075 | 29.16 | 3.00 | 26.165 | 17.688 | 15.910 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.5 | - | 22.8 | 31.0 | -100.0 | G40T2 | c570009072 c570009073 c570009074 | 11 10 10
DD21-1 | SGBM13 | Oct 21 2016 3:00PM | Oct 27 2016 9:45PM | Oct 28 2016 9:20PM | Oct 28 2016 11:58PM | 39.197 | 32.275 | 23.33 | 2.69 | 23.328 | 18.569 | 8.947 |  | 2.7 | 2.7 | 2.7 | 22T20 | - | - | - | T12-200 | - | - | - | 8.5+12 | 9.747 | 12.8 | 36.0 | 115.9 | G40T2(ice) | H9193-1 HX024-1 H9220-1 H9138-1 | 9 9 9 9
CBP41 | SGBM02 | Oct 27 2016 11:00AM | Oct 28 2016 4:15PM | Oct 28 2016 8:05PM | Oct 28 2016 10:10PM | 43.505 | 42.075 | 27.35 | 3.20 | 26.900 | 19.365 | 15.175 |  | 3.2 | 0.0 | 3.2 | 25T25 | - | - | - | T10-125 | - | - | - | 12+8.5 | - | 21.7 | 31.0 | 20.8 | G40T2 | c570009063 c57009064 c57009065 | 10 11 10
CBP106 | SGBM10 | Oct 25 2016 12:30PM | Oct 26 2016 10:50PM | Oct 27 2016 1:20AM | Oct 27 2016 3:30AM | 43.63 | 42.075 | 29.87 | 3.15 | 26.723 | 16.907 | 15.352 |  | 3.1 | 0.0 | 3.1 | 25T25 | - | - | - | T10-125 | - | - | - | 12+5.8 | - | 22.0 | 30.0 | 36.5 | G40T2 | c570009043 c570009044 c570009045 | 10 10 10
CBP57 | SGBM02 | Oct 25 2016 1:45PM | Oct 26 2016 6:20PM | Oct 26 2016 8:55PM | Oct 26 2016 10:45PM | 43.462 | 42.075 | 29.09 | 3.00 | 26.088 | 17.374 | 15.987 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.5 | - | 22.9 | 30.0 | 31.1 | G40T2 | 570009040 c570009041 c570009042 | 10 10 10
CBP48 | SGBM02 | Oct 21 2016 5:30PM | Oct 25 2016 10:00AM | Oct 25 2016 1:15PM | Oct 25 2016 3:15PM | 43.632 | 42.075 | 29.02 | 3.10 | 25.922 | 17.710 | 16.153 |  | 3.1 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.5 | - | 23.1 | 31.0 | -100.0 | G40T2 | c570009030 c570009031 c570009032 | 11 10 10
CBP114 | SGBM10 | Oct 21 2016 3:50PM | Oct 24 2016 9:00PM | Oct 24 2016 11:05PM | Oct 25 2016 2:30AM | 43.781 | 42.075 | 28.72 | 3.00 | 27.319 | 18.062 | 14.756 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.5 | - | 21.1 | 31.0 | -100.0 | G40T2 | c570009021 c570009022 c570009023 | 10 11 10
CBP108 | SGBM10 | Oct 19 2016 3:15PM | Oct 20 2016 10:35PM | Oct 21 2016 1:10AM | Oct 21 2016 3:15AM | 43.672 | 42.075 | 28.93 | 3.00 | 25.928 | 17.744 | 16.147 |  | 3.0 | 2.5 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.5 | - | 23.1 | 30.0 | -100.0 | G40T2 | c570008953 Pending c570008955 | 11 10 9
CBP40 |  | Oct 19 2016 3:00PM | Oct 20 2016 9:10PM | Oct 20 2016 8:50PM | Oct 20 2016 11:00PM | 43.355 | 42.075 | 27.27 | 3.00 | 24.266 | 19.089 | 17.809 |  | 3.0 | 3.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+8.1 | - | 25.5 | 31.0 | -100.0 | G40T2 | Pending c570008948 c570008948 | 10 11 10
DD22-3 | SGBM13 | Oct 17 2016 6:30PM | Oct 19 2016 7:40PM | Oct 19 2016 11:20PM | Oct 20 2016 2:00AM | 39.578 | 32.275 | 16.10 | 2.40 | 13.697 | 25.882 | 18.578 |  | 2.4 | 2.4 | 2.4 | 22T20(2) | 1085.0400 | - | 1085.0 | T12-200(2) | 370.0146 | 370.0 | - | 8.6+12 | - | 26.6 | 35.0 | -100.0 | G40T2(ice) | C570008942 C570008943 C570008944 C570008945 | 9 9 9 8
CBP115 | SGBM10 | Oct 17 2016 10:50AM | Oct 18 2016 10:30PM | Oct 18 2016 11:30PM | Oct 19 2016 1:05AM | 43.898 | 42.075 | 27.83 | 3.00 | 27.324 | 19.065 | 14.751 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7.5 | - | 21.1 | 31.0 | 25.6 | G40T2 | c570008936 c570008937 c57008938 | 11 10 10
CBP87 | SGBM02 | Oct 17 2016 4:00PM | Oct 18 2016 6:20PM | Oct 18 2016 7:46PM | Oct 18 2016 9:00PM | 43.504 | 42.075 | 32.53 | 3.00 | 31.830 | 13.974 | 10.245 |  | 3.0 | 0.2 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+2.9 | 11.245 | 14.7 | 24.0 | 33.6 | G40T2 | C57008924 c570008925 | 12 12
DD21-2 | SGBM13 | Oct 15 2016 1:40PM | Oct 18 2016 10:40AM | Oct 18 2016 2:00PM | Oct 18 2016 2:40PM | 39.286 | 32.275 | 22.85 | 2.47 | 20.136 | 19.150 | 12.139 |  | 2.5 | 2.5 | 2.7 | 22T20 | - | - | - | T12-200 | - | - | - | 2.5+12 | - | 17.4 | 24.0 | 38.1 | G40T2(ice) | C570008918 C570008919 | 12 12
CBP56 | SGBM02 | Oct 14 2016 8:00AM | Oct 20 2016 8:15PM | Oct 17 2016 6:45PM | Oct 17 2016 8:30PM | 43.464 | 42.075 | 29.24 | 3.00 | 26.243 | 17.221 | 15.832 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.3 | - | 22.7 | 31.0 | -100.0 | G40T2 | c570008913 c570008914 c570008915 | 10 10 11
DD22-2 | SGBM13 | Oct 13 2016 5:40PM | Oct 15 2016 8:25PM | Oct 16 2016 1:10AM | Oct 16 2016 2:35AM | 39.655 | 32.275 | 16.84 | 2.50 | 14.349 | 25.316 | 17.926 |  | 2.5 | 2.5 | 2.4 | 22T20 | - | - | - | T12-200 | - | - | - | 8.5+12 | - | 25.7 | 35.0 | 36.3 | G40T2(ice) | C570008907 C570008908 C570008909 c570008910 | 9 9 9 8
CBP107 | SGBM10 | Oct 10 2016 3:40PM | Oct 15 2016 7:10PM | Oct 15 2016 8:45PM | Oct 15 2016 10:00PM | 43.664 | 42.075 | 29.06 | 3.00 | 26.074 | 17.600 | 16.001 |  | 3.0 | 3.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 6.5+12 | - | 22.9 | 31.0 | 35.2 | G40T2 | C570008895 C570008896 C570008897 | 11 10 10
DD21-4 | SGBM13 | Oct 11 2016 6:00PM | Oct 14 2016 10:45AM | Oct 14 2016 3:15PM | Oct 14 2016 5:20PM | 39.21 | 32.275 | 23.28 | 2.70 | 20.582 | 18.628 | 11.693 |  | 2.7 | 2.7 | 2.7 | 22T20 | - | - | - | T12-200 | - | - | - | 2.5+12 | - | 16.7 | 25.0 | -100.0 | G40T2(ice) | C570008883 C570008884 C570008888 | 9 9 7
CBP47 | SGBM02 | Oct 12 2016 9:40AM | Oct 13 2016 9:50PM | Oct 13 2016 10:45PM | Oct 14 2016 1:00AM | 43.466 | 42.075 | 28.04 | 3.00 | 25.041 | 18.425 | 17.034 |  | 3.0 | 3.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 7.5+12 | - | 24.4 | 32.0 | 31.2 | G40T2 | C570008875 C570008876 C570008877 | 12 10 10
DD22-1 | SGBM13 | Oct 10 2016 1:30PM | Oct 12 2016 1:45PM | Oct 12 2016 5:37PM | Oct 12 2016 8:30PM | 39.821 | 32.275 | 16.42 | 2.40 | 14.031 | 25.800 | 18.244 |  | 2.4 | 2.4 | 2.4 | 22T20 | - | - | - | T12-200 | - | - | - | 8.5+12 | - | 26.1 | 35.0 | -100.0 | G40T2(ice) | C570008845 C570008846 C570008847 C570008849 | 10 10 10 5
CBP39 | SGBM02 | Oct 8 2016 9:30AM | Oct 11 2016 7:10PM | Oct 11 2016 7:50PM | Oct 11 2016 10:00PM | 43.459 | 42.075 | 27.33 | 3.01 | 24.330 | 19.139 | 17.745 |  | 3.0 | 3.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 8.1+12 | - | 25.4 | 32.0 | 25.9 | G40T2 | C570008835 C570008838 C570008840 | 12 10 10
CBP116 | SGBM10 | Oct 6 2016 5:45PM | Oct 8 2016 9:50PM | Oct 8 2016 10:40PM | Oct 9 2016 12:40AM | 44.003 | 42.075 | 27.50 | 2.50 | 25.003 | 19.000 | 17.072 |  | 2.5 | 2.5 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 8+12 | - | 24.4 | 32.0 | -100.0 | G40T2 | C570008792 C570008793 C570008795 | 12 10 10
CBP88 | SGBM02 | Oct 5 2016 6:00PM | Oct 7 2016 5:00PM | Oct 7 2016 7:25PM | Oct 7 2016 8:50PM | 43.544 | 42.075 | 31.94 | 3.00 | 29.936 | 14.608 | 12.139 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+4 | - | 17.4 | 24.0 | 27.6 | G40T2 | C570008787 C570008788 C570008789 | 8 8 8
DD21-3 | SGBM13 | Oct 4 2016 5:00PM | Oct 7 2016 4:15PM | Oct 7 2016 6:30PM | Oct 7 2016 8:25PM | 39.362 | 32.275 | 22.77 | 2.70 | 20.067 | 19.295 | 12.208 |  | 2.7 | 2.7 | 2.7 | 22T20 | - | - | - | T12-200 | - | - | - | 2.5+12 | - | 17.5 | 21.0 | -100.0 | G40T2(ice) | C570008785 C570008786 | 10 11
CBP53 | SGBM02 | Oct 1 2016 8:00PM | Oct 4 2016 10:30PM | Oct 5 2016 1:30PM | Oct 5 2016 4:40PM | 43.754 | 42.075 | 28.89 | 3.16 | 27.445 | 18.019 | 14.630 |  | 3.2 | 0.0 | 3.1 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.7 | - | 20.9 | 31.0 | 32.5 | G40T2 | C570008741 C570008745 C570008749 | 10 10 11
CBP117 | SGBM10 | Sep 28 2016 6:50PM | Oct 1 2016 7:00PM | Oct 2 2016 2:45AM | Oct 2 2016 4:30AM | 44.213 | 42.075 | 27.58 | 3.00 | 25.980 | 19.633 | 16.095 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+8.5 | - | 23.0 | 32.0 | 27.8 | G40T2 | C570008714 C570008716 C570008720 | 10 10 12
CBP45 | SGBM02 | Sep 27 2016 9:45AM | Oct 1 2016 8:10PM | Sep 1 2016 10:30PM | Oct 2 2016 12:20AM | 43.387 | 42.075 | 27.15 | 3.00 | 24.149 | 19.238 | 17.926 |  | 3.0 | 3.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 8.5+12 | - | 25.7 | 31.0 | 20.8 | G40T2 | C570008692 C570008694 C570008700 | 10 10 11
CBP38 | SGBM02 | Sep 24 2016 2:00PM | Sep 26 2016 7:10PM | Sep 26 2016 8:30PM | Sep 26 2016 10:40PM | 43.409 | 42.075 | 27.95 | 2.99 | 24.963 | 18.446 | 17.112 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7.4 | - | 24.5 | 31.0 | 26.5 | G40T2 | C570008621 C570008622 C570008623 | 10 10 11
CBP46 | SGBM02 | Sep 22 2016 5:30PM | Sep 24 2016 7:00PM | Sep 24 2016 9:45PM | Sep 24 2016 11:05PM | 43.387 | 42.075 | 28.18 | 3.31 | 24.877 | 18.520 | 17.198 |  | 3.3 | 0.0 | 3.3 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7 | - | 24.6 | 31.0 | -100.0 | G40T2 | C570008613 C570008614 C570008615 | 10 11 10
CBP37 | SGBM02 | Sep 21 2016 9:30AM | Sep 22 2016 4:45PM | Sep 22 2016 9:50PM | Sep 22 2016 11:30PM | 43.626 | 42.075 | 28.66 | 3.00 | 26.462 | 17.964 | 15.613 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.7 | - | 22.4 | 31.0 | -100.0 | G40T2 | C570008589 C570008590 C570008591 | 10 10 11
CBP54 | SGBM02 | Sep 17 2016 4:00PM | Sep 21 2016 6:45PM | Sep 21 2016 8:15PM | Sep 21 2016 11:30PM | 43.487 | 42.075 | 29.17 | 3.00 | 26.165 | 17.322 | 15.910 |  | 3.0 | 0.0 | 3.0 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.6 | - | 22.8 | 31.0 | -100.0 | G40T2 | C570008572 C570008575 C570008578 | 10 10 11
CBP36 | SGBM02 | Sep 15 2016 8:00PM | Sep 19 2016 9:45AM | Sep 19 2016 9:45PM | Sep 19 2016 11:10PM | 43.425 | 42.075 | 28.23 | 3.10 | 25.128 | 18.297 | 16.947 |  | 3.1 | 0.0 | 3.1 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7.5 | - | 24.3 | 30.0 | -100.0 | G40T2 | C570008511 C570008512 C570008515 | 10 10 10
CBP55 | SGBM02 | Sep 9 2016 12:00PM | Sep 15 2016 11:30AM | Sep 15 2016 4:00PM | Sep 15 2016 7:00PM | 43.479 | 42.075 | 29.29 | 3.20 | 26.097 | 17.392 | 15.978 |  | 3.2 | 0.0 | 3.2 | 25T25 | - | - | - | T10-125 | - | - | - | 12+6.5 | - | 22.9 | 30.0 | 31.1 | G40T2 | C570008455 C570008456 C570008458 | 10 12 8
DD19-4 | SGBM31 | Sep 6 2016 12:12PM | Sep 9 2016 11:15AM | Sep 10 2016 7:20PM | Sep 10 2016 8:55PM | 39.05 | 32.275 | 29.77 | 3.81 | 27.070 | 13.090 | 5.205 |  | 3.8 | 0.0 | 3.8 | 22T20 | 396.040 | - | 396.040 | T12-200 | 136.9802 | - | 136.9802 | 7.3 | 6.005 | 7.5 | 12.0 | -100.0 | G40T2 | c570008430 c570008431 | 7 5
CBP35 | SGBM02 | Sep 5 2016 4:00PM | Sep 8 2016 9:40PM | Sep 9 2016 7:15PM | Sep 9 2016 10:10PM | 43.546 | 42.075 | 28.31 | 3.20 | 25.114 | 18.432 | 16.961 |  | 3.2 | 0.0 | 3.2 | 25T25 | - | - | - | T10-125 | - | - | - | 12+7 | - | 24.3 | 30.0 | 23.6 | G40T2 | C570008413 C570008414 C570008417 | 12 9 9
DD20-2 | SGBM31 | Sep 4 2016 9:45AM | Sep 6 2016 1:00PM | Sep 6 2016 3:50PM | Sep 6 2016 6:10PM | 39.24 | 32.275 | 24.48 | 2.71 | 21.765 | 17.475 | 10.510 |  | 2.7 | 0.0 | 2.7 | 22T20 | 623.898 | - | 623.898 | T12-200 | 222.8484 | - | 222.8484 | 11.5 | 11.310 | 15.0 | 19.0 | -100.0 | G40T2 | C570008362 C570008364 | 12 7
DD19-1 | SGBM31 | Sep 1 2016 5:30PM | Sep 3 2016 4:40PM | Sep 3 2016 8:30PM | Sep 3 2016 10:10PM | 39.152 | 32.275 | 26.79 | 3.82 | 22.973 | 16.179 | 9.302 |  | 3.8 | 0.0 | 3.8 | 22T20 | 558.796 | - | 558.796 | T12-200 | 198.3146 | - | 198.3146 | 10.3 | 10.102 | 13.3 | 18.0 | -100.0 | G40T2 | C570008337 C570008338 | 9 9
DD20-1 | SGBM31 | Aug 29 2016 6:20PM | Sep 1 2016 7:00PM | Sep 1 2016 8:40PM | Sep 1 2016 10:30PM | 39.172 | 32.275 | 24.76 | 2.72 | 23.261 | 17.131 | 9.014 |  | 2.7 | 0.0 | 2.7 | 22T20 | 613.048 | - | 613.048 | T12-200 | 218.7594 | - | 218.7594 | 11.3 | 9.814 | 12.9 | 21.0 | -18.1 | G40T2 | C570008310 C570008310 | 12 9
DD19-3 | SGBM31 | Aug 27 2016 12:00PM | Aug 29 2016 8:00PM | Aug 29 2016 11:00PM | Aug 30 2016 1:10AM | 39.146 | 32.275 | 26.71 | 2.60 | 24.122 | 15.034 | 8.153 |  | 2.6 | 0.0 | 2.6 | 22T20 | 504.544 | - | 504.544 | T12-200 | 177.8698 | - | 177.8698 | 9.3 | 8.953 | 11.7 | 15.0 | 28.4 | G40T2 | C590065060 C590065970 C590065972 | 2 7 6
DD20-3 | SGBM31 | Aug 24 2016 4:00PM | Aug 27 2016 10:15PM | Aug 27 2016 11:10PM | Aug 28 2016 12:40AM | 39.168 | 32.275 | 24.36 | 2.72 | 22.165 | 17.523 | 10.110 |  | 2.7 | 0.0 | 2.7 | 22T20 | 629.323 | - | 629.323 | T12-200 | 224.8929 | - | 224.8929 | 11.6 | 10.910 | 14.5 | 20.0 | -100.0 | G40T2 | C570008229 C570008230 | 12 8
DD19-2 | SGBM31 | Aug 22 2016 4:30AM | Aug 24 2016 4:30PM | Aug 24 2016 8:10PM | Aug 24 2016 10:35PM | 39.214 | 32.275 | 26.57 | 3.80 | 22.773 | 16.441 | 9.502 |  | 3.8 | 0.0 | 3.8 | 22T20 | 651.024 | - | 651.024 | T12-200 | 233.0708 | - | 233.0708 | 12 | 10.302 | 13.6 | 17.0 | 25.0 | G40T2 | c570008148 c570008149 | 10 7
DD20-4 | SGBM31 | Aug 19 2016 3:20PM | Aug 22 2016 2:00PM | Aug 22 2016 10:50PM | Aug 23 2016 1:10AM | 39.003 | 32.275 | 24.54 | 2.90 | 21.839 | 17.264 | 10.436 |  | 2.9 | 0.0 | 2.7 | 22T20 | 651.024 | - | 651.024 | T12-200 | 233.0708 | - | 233.0708 | 12 | 11.236 | 14.9 | 19.0 | -100.0 | G40T2 | c570008122 c570008123 c570008124 | 8 8 3
CBP61 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP63 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP64 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP65 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP66 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP1 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP2 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP3 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP4 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP5 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP6 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP7 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP8 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP9 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP10 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP11 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP12 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP13 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP14 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP15 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP16 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP17 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP18 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP19 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP20 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP21 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP22 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP23 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP24 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP25 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP26 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP27 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP28 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP29 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP30 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP31 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP32 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP33 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP34 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP124 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP125 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP126 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP127 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP128 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP118 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP119 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP120 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP121 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP122 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP123 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP90 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP102 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP104 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP92 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP93 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP94 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP95 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP96 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP97 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP98 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP99 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP67 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP69 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP71 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP72 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP73 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP85 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP86 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP74 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP75 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP76 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP77 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP78 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP79 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP80 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP81 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP82 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
CBP83 | [5 empty] | 0 | 42.075 |  |  | 0.000 | 0.000 | 42.075 |  | 0.0 | 0.0 | 0.0 | 25T25 | - | - | - | T10-125 | - | - | - |  | - | 60.2 | 0.0 | 0.0 | G40T2
Total | [10 empty] | 1163.985 | 4214.302 | 0.0 | 213.8 | 40.7 | 196.9 |  | 7736.1 | 2023.3 | 5712.7 |  | 2645.1 | 629.2 | 2015.8 |  |  | 6033.0 | 1875.0

## 1500
Summary List for 18916523-MRT-v201
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
SB13-1 | SGBM31 | Dec 1 2016 10:30AM | Dec 2 2016 6:30PM | Dec 2 2016 7:30PM | Dec 2 2016 8:20PM | 39.642 | 34.175 | 34.02 | 3.30 | 32.315 | 8.927 | 1.860 |  | 3.3 | 0.0 | 3.3 | 26T20 | 288.522 | 288.522 | T12-175 | 97.4664 | 97.4664 | 4.5 | 2.660 | 3.3 | 9.0 | 10.2 | G40T2(ice) | c570009412 | 9
SB13-2 | SGBM31 | Nov 28 2016 10:30AM | Nov 29 2016 4:50PM | Nov 29 2016 8:25PM | Nov 29 2016 9:15PM | 39.751 | 34.175 | 34.38 | 3.50 | 30.881 | 8.870 | 3.294 |  | 3.5 | 0.0 | 3.5 | 26T20 | 288.522 | 288.522 | T12-175 | 97.4664 | 97.4664 | 4.5 | 4.094 | 5.8 | 9.0 | 54.6 | G40T2(ice) | c570009363 | 9
SB13-3 |  | Nov 22 2016 4:30PM | Nov 24 2016 10:00PM | Nov 25 2016 12:00PM | Nov 25 2016 1:00PM | 39.825 | 34.175 | 34.02 | 3.30 | 30.720 | 9.105 | 3.455 |  | 3.3 | 0.0 | 3.3 | 26T20 | 288.522 | 288.522 | T12-175 | 97.4664 | 97.4664 | 4.5 | 4.255 | 6.1 | 9.0 | 47.4 | G40T2(ice) | c570009332 | 9
SB13-4 | SGBM31 | Nov 16 2016 10:05PM | Nov 19 2016 5:50PM | Nov 19 2016 6:50PM | Nov 19 2016 7:50PM | 40.073 | 34.175 | 34.00 | 3.35 | 33.045 | 9.378 | 1.130 |  | 3.4 | 0.0 | 3.3 | 26T20 | 288.522 | 288.522 | T12-175 | 97.4664 | 97.4664 | 4.5 | 1.930 | 2.0 | 10.0 | 22.3 | G40T2(ice) | c570009285 | 10
Total | [10 empty] | 36.280 | 9.739 | 0.0 | 13.4 | 0.0 | 13.4 |  | 1154.1 | 1154.1 |  | 389.9 | 389.9 |  |  | 17.2 | 37.0