## 750
Summary List for 1891652500-CK3
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T16 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T10 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
17/AO |  | Nov 16 2016 1:00PM | Nov 19 2016 4:20PM | Nov 22 2016 10:52AM | Dec 23 2016 11:25AM | 67.988 | 66.475 | 47.99 45.09 | 2.50 2.90 | 43.588 | 24.400 | 22.887 |  | 5.4 | 0.0 | 1.5 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 11.527+12 | 10.1 | 16.0 | 5.9 | G40T2 | C150027731 C150027734 | 8 8
22/AO |  | Nov 28 2016 1:10PM | Dec 1 2016 4:15PM | Dec 3 2016 1:10PM | Dec 3 2016 1:20PM | 68.266 | 66.475 | 44.94 44.84 44.44 43.84 43.64 | 0.10 0.90 1.20 0.20 2.70 | 43.339 | 24.927 | 23.136 |  | 5.1 | 0.0 | 1.5 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 11.776+12 | 10.2 | 20.0 | 21.3 | G40T2 | C150028222 C150028224 | 10 10
4/A-CP-2 |  | Nov 23 2016 1:00PM | Nov 28 2016 11:14AM | Dec 2 2016 11:20AM | Dec 2 2016 12:10PM | 66.434 | 64.35 | 60.32 49.52 | 4.40 2.80 | 48.115 | 19.200 | 16.235 |  | 7.2 | 0.0 | 1.4 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 4.875+12 | 7.2 | 12.0 | 573.0 | G40T2 | C150028194 | 12
6/A-CP-1 |  | Nov 28 2016 1:15PM | Dec 1 2016 4:26PM | Dec 2 2016 11:20AM | Dec 2 2016 12:10PM | 66.24 | 64.35 | 48.71 | 3.20 | 47.112 | 20.100 | 17.238 |  | 3.2 | 0.0 | 1.4 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 5.878+12 | 7.6 | 12.0 | 57.5 | G40T2 | C150028188 | 12
8/A-CP-2 |  | Nov 25 2016 3:00PM | Nov 28 2016 11:25AM | Dec 1 2016 2:00PM | Dec 1 2016 3:35PM | 66.555 | 64.55 | 50.08 | 2.80 | 48.680 | 17.875 | 15.870 |  | 2.8 | 0.0 | 1.4 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 4.510+12 | 7.0 | 10.0 | -929.2 | G40T2 | C150028162 | 10
14/A-CP-2 |  | Nov 23 2016 11:30AM | Nov 24 2016 6:20PM | Nov 29 2016 3:30PM | Nov 29 2016 4:30PM | 66.843 | 63.75 | 44.13 | 3.00 | 42.627 | 25.000 | 21.123 |  | 3.0 | 0.0 | 1.4 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 9.763+12 | 9.3 | 12.0 | 2.7 | G40T2 | C150028079 | 12
6/A-CP-2 |  | Nov 23 2016 2:10PM | Nov 25 2016 10:15AM | Nov 26 2016 3:35PM | Nov 26 2016 4:50PM | 66.32 | 64.35 | 56.14 55.94 48.54 | 0.20 2.40 3.20 | 46.940 | 20.700 | 17.410 |  | 5.8 | 0.0 | 1.4 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 6.050+12 | 7.7 | 12.0 | 56.0 | G40T2 | C150027972 | 12
14/A-CP-1 |  | Nov 22 2016 9:45AM | Nov 23 2016 10:30AM | Nov 24 2016 2:05PM | Nov 24 2016 2:52PM | 66.99 | 63.75 | 52.39 51.99 | 0.80 1.40 | 51.285 | 16.500 | 12.465 |  | 2.2 | 0.0 | 0.7 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 1.105+12 | 5.5 | 13.0 | 136.0 | G40T2 | C150027869 C150027870 | 6.5 6.5
20/AO |  | Nov 19 2016 5:20PM | Nov 23 2016 6:40PM | Nov 24 2016 11:35AM | Nov 24 2016 1:00PM | 68.065 | 66.475 | 53.99 44.29 | 6.00 1.50 | 42.790 | 26.200 | 23.685 |  | 7.5 | 0.0 | 1.4 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 0.325+12+12 | 10.5 | 17.0 | 62.4 | G40T2 | C150027860 C150027861 | 9 8
11/AO |  | Nov 11 2016 11:30AM | Nov 15 2016 8:50AM | Nov 17 2016 11:50AM | Nov 17 2016 3:05PM | 66.932 | 64.65 | 42.62 | 3.20 | 41.021 | 25.911 | 23.629 |  | 3.2 | 0.0 | 1.6 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 0.269+12+12 | 10.4 | 16.0 | 53.3 | G40T2 | C150027466 C150027467 | 8 8
14-15/AO | SGBM01 | Nov 11 2016 2:30PM | Nov 14 2016 11:25AM | Nov 15 2016 11:58AM | Nov 15 2016 2:50PM | 67.207 | 64.65 | 42.87 42.57 | 0.30 3.60 | 40.769 | 26.438 | 23.881 |  | 3.9 | 0.0 | 1.8 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 0.521+12+12 | 10.6 | 20.0 | 105.0 | G40T2 | C150027354 C150027352 C150027362 | 8 8 4
8/AO |  | Nov 5 2016 8:00AM | Nov 11 2016 10:30AM | Nov 12 2016 12:00PM | Nov 12 2016 2:45PM | 66.609 | 65.85 | 55.44 55.14 54.64 54.04 43.54 42.94 | 0.50 1.20 1.10 0.90 1.20 2.20 | 41.840 | 24.769 | 24.010 |  | 7.1 | 0.0 | 1.6 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 0.650+12+12 | 10.6 | 16.0 | 50.8 | G40T2 | C150027278 C150027280 C150027292 | 7 7 2
4/AO |  | Oct 11 2016 8:30AM | Oct 18 2016 9:50AM | Oct 26 2016 5:15PM | Oct 26 2016 5:55PM | 66.54 | 65.85 | 58.63 58.43 56.23 55.13 47.73 | 0.20 3.40 1.00 1.70 6.80 | 45.326 | 88.540 | 20.524 |  | 7.7 | 0.0 | 2.3 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 9.164+12 | 9.1 | 12.5 | 3.4 | G40T2 | C150026623 C150026633 | 7.5 5
2/AO |  | Oct 8 2016 6:31PM | Oct 22 2016 9:55AM | Oct 26 2016 1:45PM | Oct 26 2016 2:55PM | 66.56 | 65.85 | 57.60 57.40 51.10 51.00 48.50 47.50 | 1.50 0.50 0.90 1.40 1.90 0.40 | 47.296 | 19.264 | 18.554 |  | 5.6 | 0.0 | 1.2 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 7.194+12 | 8.2 | 12.5 | 52.5 | G40T2 | C150026622 C150026623 | 10 2.5
6/AO | [5 empty] | 0 | 65.85 |  |  | 0.000 | 0.000 | 65.850 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 6.490+12+12+12+12+12 | 29.1 | 0.0 | 0.0 | G40T2
BP P9 | [5 empty] | 0 | 68.35 |  |  | 0.000 | 0.000 | 68.350 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 8.990+12+12+12+12+12 | 30.2 | 0.0 | 0.0 | G35T2
BP P12 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P16 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P18 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P21 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P22 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P24 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P27 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P28 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P29 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P30 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
BP P32 | [5 empty] | 0 | 63.625 |  |  | 0.000 | 0.000 | 63.625 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.265+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G35T2
6/E-CP-2 | [5 empty] | 0 | 63.65 |  |  | 0.000 | 0.000 | 63.650 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.290+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G40T2
6/E-CP-3 | [5 empty] | 0 | 63.65 |  |  | 0.000 | 0.000 | 63.650 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.290+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G40T2
7/H-CP-1 | [5 empty] | 0 | 64.45 |  |  | 0.000 | 0.000 | 64.450 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 5.090+12+12+12+12+12 | 28.5 | 0.0 | 0.0 | G40T2
7/H-CP-2 | [5 empty] | 0 | 64.45 |  |  | 0.000 | 0.000 | 64.450 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 5.090+12+12+12+12+12 | 28.5 | 0.0 | 0.0 | G40T2
7/H-CP-3 | [5 empty] | 0 | 64.45 |  |  | 0.000 | 0.000 | 64.450 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 5.090+12+12+12+12+12 | 28.5 | 0.0 | 0.0 | G40T2
7/H-CP-4 | [5 empty] | 0 | 64.45 |  |  | 0.000 | 0.000 | 64.450 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 5.090+12+12+12+12+12 | 28.5 | 0.0 | 0.0 | G40T2
7/H-CP-5 | [5 empty] | 0 | 64.45 |  |  | 0.000 | 0.000 | 64.450 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 5.090+12+12+12+12+12 | 28.5 | 0.0 | 0.0 | G40T2
8/A-CP-1 | [5 empty] | 0 | 64.55 |  |  | 0.000 | 0.000 | 64.550 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 5.190+12+12+12+12+12 | 28.5 | 0.0 | 0.0 | G40T2
25/AO | [5 empty] | 0 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 7.115+12+12+12+12+12 | 29.4 | 0.0 | 0.0 | G40T2
26-27/AO | [5 empty] | 0 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 7.115+12+12+12+12+12 | 29.4 | 0.0 | 0.0 | G40T2
28/AO | [5 empty] | 0 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 7.115+12+12+12+12+12 | 29.4 | 0.0 | 0.0 | G40T2
29/AO | [5 empty] | 0 | 66.475 |  |  | 0.000 | 0.000 | 66.475 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 7.115+12+12+12+12+12 | 29.4 | 0.0 | 0.0 | G40T2
7/P1 | [5 empty] | 0 | 68 |  |  | 0.000 | 0.000 | 68.000 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 8.640+12+12+12+12+12 | 30.0 | 0.0 | 0.0 | G40T2
2/A-CP-1 | [5 empty] | 0 | 65.375 |  |  | 0.000 | 0.000 | 65.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 6.015+12+12+12+12+12 | 28.9 | 0.0 | 0.0 | G40T2
2/A-CP-2 | [5 empty] | 0 | 65.375 |  |  | 0.000 | 0.000 | 65.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 6.015+12+12+12+12+12 | 28.9 | 0.0 | 0.0 | G40T2
2/A-CP-3 | [5 empty] | 0 | 65.375 |  |  | 0.000 | 0.000 | 65.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 6.015+12+12+12+12+12 | 28.9 | 0.0 | 0.0 | G40T2
2/A-CP-4 | [5 empty] | 0 | 65.375 |  |  | 0.000 | 0.000 | 65.375 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 6.015+12+12+12+12+12 | 28.9 | 0.0 | 0.0 | G40T2
4/A-CP-1 | [5 empty] | 0 | 64.35 |  |  | 0.000 | 0.000 | 64.350 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.990+12+12+12+12+12 | 28.4 | 0.0 | 0.0 | G40T2
14/D-CP-1 | [5 empty] | 0 | 63.65 |  |  | 0.000 | 0.000 | 63.650 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 4.290+12+12+12+12+12 | 28.1 | 0.0 | 0.0 | G40T2
19/F-M-CP-1 | [5 empty] | 0 | 62.65 |  |  | 0.000 | 0.000 | 62.650 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.290+12+12+12+12+12 | 27.7 | 0.0 | 0.0 | G40T2
19/F-M-CP-2 | [5 empty] | 0 | 62.65 |  |  | 0.000 | 0.000 | 62.650 |  | 0.0 | 0.0 | 2.9 | 12T16 | 227.376 | 227.376 | T10-150 | 145.0960 | 145.0960 | 12 | 3.290+12+12+12+12+12 | 27.7 | 0.0 | -100.0 | G40T2
21/F-M-CP-1 | [5 empty] | 0 | 62.55 |  |  | 0.000 | 0.000 | 62.550 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.190+12+12+12+12+12 | 27.6 | 0.0 | 0.0 | G40T2
8/A-CP-3 |  | Dec 2 2016 9:30AM | Dec 5 2016 7:00PM |  |  | 0 | 64.55 | -9.00 | 1.80 | -9.000 | 0.000 | 73.550 |  | 1.8 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 2.190+12+12+12+12+12+12 | 32.5 | 0.0 | -100.0 | G40T2
8/E-CP-1 | [5 empty] | 0 | 62.95 |  |  | 0.000 | 0.000 | 62.950 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.590+12+12+12+12+12 | 27.8 | 0.0 | 0.0 | G40T2
8/E-CP-2 | [5 empty] | 0 | 62.95 |  |  | 0.000 | 0.000 | 62.950 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.590+12+12+12+12+12 | 27.8 | 0.0 | 0.0 | G40T2
8/E-CP-3 | [5 empty] | 0 | 62.95 |  |  | 0.000 | 0.000 | 62.950 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.590+12+12+12+12+12 | 27.8 | 0.0 | 0.0 | G40T2
8/E-CP-4 | [5 empty] | 0 | 62.95 |  |  | 0.000 | 0.000 | 62.950 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.590+12+12+12+12+12 | 27.8 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-8 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 11.590+12+12+12+12 | 26.0 | 0.0 | 0.0 | G40T2
11/D-CP-1 | [5 empty] | 0 | 63.05 |  |  | 0.000 | 0.000 | 63.050 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.690+12+12+12+12+12 | 27.9 | 0.0 | 0.0 | G40T2
11/D-CP-2 | [5 empty] | 0 | 63.05 |  |  | 0.000 | 0.000 | 63.050 |  | 0.0 | 0.0 | 0.0 | 12T16 | - | - | T10-150 | - | - |  | 3.690+12+12+12+12+12 | 27.9 | 0.0 | 0.0 | G40T2
Total | [10 empty] | 379.824 | 3050.472 | 0.0 | 71.5 | 0.0 | 23.5 |  | 3410.6 | 3410.6 |  | 2176.4 | 2176.4 |  |  | 1347.8 | 201.0

## 1200
Summary List for 1891652500-CK3
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [10 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | T32 Weight (kg) | T40 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | T16 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
9-17/F-M-CP-7 |  | Nov 23 2016 1:00PM | Nov 28 2016 10:55AM | Dec 1 2016 3:56PM | Dec 1 2016 7:00PM | 66.409 | 58.95 | 45.17 | 7.10 | 42.466 | 23.943 | 16.484 |  | 4.4 | 0.0 | 2.4 | 15T20 | 443.880 | 443.880 | - | - | T12-250 | 158.6869 | 158.6869 | - | 12 | 5.284+12 | 18.6 | 27.0 | 44.8 | G40T2 | C150028167 C150028168 C150028169 | 9 8 10
3/P-1 | SGBM17 | Nov 18 2016 9:45AM | Nov 25 2016 9:55AM | Nov 26 2016 12:50PM | Nov 26 2016 2:15PM | 66.834 | 67.4 | 60.61 60.11 57.61 55.51 54.51 | 1.00 6.30 5.30 2.90 3.90 | 53.113 | 13.721 | 14.287 |  | 13.7 | 0.0 | 2.4 | 15T20 | 443.880 | 443.880 | - | - | T12-250 | 158.6869 | 158.6869 | - | 12 | 3.087+12 | 16.2 | 22.0 | 5.8 | G40T2 | C150027961 C150027962 | 11 11
9-17/F-M-CP-3 |  | Nov 17 2016 1:00PM | Nov 23 2016 10:15AM | Nov 25 2016 11:45AM | Nov 25 2016 1:30PM | 66.635 | 58.95 | 54.92 42.72 42.52 | 1.00 0.20 6.40 | 40.117 | 27.600 | 18.833 |  | 4.7 | 0.0 | 2.4 | 15T20 | 443.880 | 443.880 | - | - | T12-250 | 158.6869 | 158.6869 | - | 12 | 7.633+12 | 21.3 | 27.0 | 5.7 | G40T2 | C150027887 C150027889 C150027890 | 9 9 9
C24 | SGBM05 | Nov 5 2016 8:00AM | Nov 22 2016 8:45AM | Nov 23 2016 12:25PM | Nov 23 2016 2:15PM | 71.381 | 73.175 | 69.28 63.28 60.88 | 5.30 2.40 5.10 | 59.183 | 13.100 | 13.992 |  | 11.1 | 0.0 | 1.5 | 30T32 (1) , 15T32 (1) | 2462.0700 | - | 2462.1 | - | 2T16-150(1),T12-175(1) | 45.7765 | 23.4 | 22.4 | 12+2.6 | 4.552+12 | 15.8 | 19.0 | 20.0 | G35T2 | C150027801 C150027804 | 10 9
C20 |  | Nov 15 2016 9:05AM | Nov 21 2016 8:40AM | Nov 22 2016 3:20PM | Nov 22 2016 4:40PM | 71.558 | 73.675 | 68.48 60.28 59.88 | 6.50 0.40 5.40 | 58.378 | 14.100 | 15.297 |  | 9.9 | 0.0 | 1.5 | 30T32 (1) , 15T32 (1) | 2556.7650 | - | 2556.8 | - | 2T16-150(1),T12-175(1) | 44.6466 | 23.4 | 21.3 | 12+3.6 | 5.857+12 | 17.3 | 20.0 | 2.7 | G35T2 | C150027751 C150027752 | 10 10
C19 |  | Oct 25 2016 10:40AM | Nov 10 2016 3:00PM | Nov 12 2016 2:20PM | Nov 12 2016 4:05PM | 71.64 | 73.675 | 62.57 59.57 | 3.00 4.00 | 58.068 | 13.572 | 15.607 |  | 5.7 | 0.0 | 1.5 | 30T32 (1) , 15T32 (1) | 2651.4600 | - | 2651.5 | - | 2T16-150(1),T12-175(1) | 44.4273 | 23.4 | 21.0 | 12+4 | 6.167+12 | 17.7 | 20.0 | 2.3 | G35T2 | C150027292 C150027296 | 10 10
C21 |  | Oct 25 2016 9:10AM | Nov 4 2016 4:50PM | Nov 5 2016 1:10PM | Nov 5 2016 1:30PM | 71.433 | 73.175 | 60.37 59.37 | 3.00 1.50 | 58.871 | 12.562 | 14.304 |  | 3.0 | 0.0 | 1.5 | 30T32 (1) , 15T32 (1) | 2556.7650 | - | 2556.8 | - | T16-150(1),T12-175(1) | 45.0563 | 23.4 | 21.7 | 12+3.1 | 4.864+12 | 16.2 | 18.0 | -100.0 | G35T2 | C150026973 C150026974 | 9 9
C16 |  | Oct 18 2016 2:50PM | Nov 1 2016 2:15PM | Nov 2 2016 12:05PM | Nov 2 2016 2:25PM | 71.6 | 74.175 | 64.40 63.90 61.40 59.10 | 0.50 4.00 3.80 4.50 | 57.603 | 13.997 | 16.572 |  | 8.9 | 0.0 | 1.5 | 15T40(1), 36T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-125(1) | 56.6777 | 28.7 | 28.0 | 5+12 | 7.772+12 | 18.7 | 19.0 | 1.4 | G35T2 | C150026852 C150026853 | 10 9
C23 |  | Oct 21 2016 8:50AM | Oct 26 2016 8:50AM | Oct 27 2016 3:13PM | Oct 27 2016 4:11PM | 71.435 | 73.175 | 68.21 67.61 62.31 | 0.60 2.60 4.60 | 60.710 | 11.500 | 12.465 |  | 5.5 | 0.0 | 1.5 | 30T32 (1) | - | - | - | - | 2T16-100(1) | - | - | - | 12 | 0 | 14.1 | 15.0 | -14.1 | G35T2 | C150026678 C150026679 | 8 7
C18 |  | Oct 6 2016 9:25AM | Oct 18 2016 2:15PM | Oct 22 2016 1:35PM | Oct 22 2016 2:35PM | 71.565 | 73.675 | 59.10 | 5.00 | 57.600 | 15.000 | 16.075 |  | 3.0 | 0.0 | 1.5 | 15T40(1), 36T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-175(1) | 48.7863 | 28.7 | 20.1 | 5+12 | 7.275+12 | 18.2 | 19.0 | 0.8 | G35T2 | C150026489 C150026491 | 10 9
C15 |  | Oct 18 2016 3:40PM | Oct 20 2016 5:33PM | Oct 21 2016 11:25AM | Oct 21 2016 1:00PM | 71.616 | 74.175 | 64.43 64.13 | 0.30 4.50 | 62.626 | 8.990 | 11.549 |  | 1.8 | 0.0 | 1.5 | 30T32 (1) | - | - | - | - | 2T16-100(1),T12-175(1) | - | - | - | 10.5 | 0 | 13.1 | 14.0 | 7.2 | G35T2 | C150026414 C150026415 | 7 7
C22 |  | Sep 23 2016 4:00PM | Oct 8 2016 3:10PM | Oct 13 2016 3:30PM | Oct 13 2016 4:50PM | 71.5 | 73.175 | 67.24 60.24 | 1.00 4.40 | 58.740 | 12.760 | 14.435 |  | 4.0 | 0.0 | 1.5 | 24T32 | - | - | - | - | 2T16-100,T12-175 | - | - | - | 12+3.5 | 3.715+12 | 16.3 | 17.0 | 0.7 | G35T2 | Pending Pending | 9 8
C14 |  | Oct 6 2016 8:15AM | Oct 12 2016 1:45PM | Oct 13 2016 1:00PM | Oct 13 2016 2:45PM | 71.525 | 74.175 | 61.28 58.98 58.48 | 0.80 0.50 3.00 | 56.980 | 14.545 | 17.195 |  | 2.8 | 0.0 | 1.5 | 15T40(1), 36T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-125(1) | 56.6777 | 28.7 | 28.0 | 5+12 | 8.395+12 | 19.4 | 20.0 | -100.0 | G35T2 | Pending Pending | 10 10
C9 |  | Sep 21 2016 8:00AM | Oct 5 2016 1:20PM | Oct 5 2016 4:35PM | Oct 5 2016 6:25PM | 71.67 | 73.647 | 59.86 55.76 | 1.30 1.50 | 54.260 | 17.410 | 19.387 |  | 2.8 | 0.0 | 1.5 | 15T40(1), 36T40(1), 15T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-175(1),T12-125(1) | 77.6428 | 28.7 | 49.0 | 5+12+4.5 | 10.587+12 | 21.9 | 23.0 | 4.9 | G35T2 | C150025689 C150025689 | 12 11
C13 |  | Sep 27 2016 7:00AM | Sep 30 2016 3:25PM | Oct 1 2016 2:14PM | Oct 1 2016 3:55PM | 71.57 | 74.175 | 59.61 57.61 | 1.00 1.50 | 56.110 | 15.460 | 18.065 |  | 2.5 | 0.0 | 1.5 | 15T40(1), 36T40(1), 15T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-175(1),T12-125(1) | 80.2926 | 28.7 | 51.6 | 5+12+2.5 | 9.265+12 | 20.4 | 21.0 | -20.4 | G35T2 | Pending Pending | 12 9
C10 |  | Sep 20 2016 3:30PM | Sep 23 2016 3:30PM | Sep 26 2016 3:40PM | Sep 26 2016 5:40PM | 71.65 | 74.004 | 55.89 | 1.70 | 54.190 | 17.460 | 19.814 |  | 1.7 | 0.0 | 1.5 | 15T40(1), 36T40(1), 15T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-175(1),T12-125(1) | 77.6428 | 28.7 | 49.0 | 5+12+4.5 | 11.014+12 | 22.4 | 24.0 | 1.6 | G35T2 | C150025351 C150025352 | 12 12
C17 |  | Sep 15 2016 3:30PM | Sep 20 2016 2:40PM | Sep 26 2016 3:00PM | Sep 26 2016 3:00PM | 71.43 | 73.675 | 62.50 58.80 | 0.00 1.70 | 57.100 | 14.330 | 16.575 |  | 1.7 | 0.0 | 1.5 | 15T40(1), 36T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-175(1) | 48.7863 | 28.7 | 20.1 | 5+12 | 7.775+12 | 18.7 | 19.0 | 0.3 | G35T2 | C150025345 C150025346 | 10 9
C12 |  | Sep 8 2016 9:00AM | Sep 15 2016 2:55PM | Sep 17 2016 6:10PM | Sep 17 2016 8:03PM | 71.57 | 74.175 | 59.35 57.55 56.45 | 0.60 0.80 1.65 | 54.850 | 16.720 | 19.325 |  | 3.0 | 0.0 | 1.5 | 15T40(1), 36T40(1), 15T40(1) | 5004.0900 | - | - | 5004.1 | T16-125(1),T12-175(1),T12-175(1) | 70.4810 | 28.7 | 41.8 | 5+12+3.4 | 10.525+12 | 21.9 | 25.0 | 3.1 | G35T2 | C150025011 C150025013 C150025014 | 9 8 8
C8 |  | Sep 5 2016 4:30PM | Sep 8 2016 10:05AM | Sep 14 2016 10:56AM | Sep 14 2016 2:05PM | 71.58 | 73.29 | 59.75 | 2.40 | 57.346 | 14.234 | 15.944 |  | 2.4 | 0.0 | 2.4 | 30T32 (1) , 15T32 (1) | 2651.4600 | - | 2651.5 | - | T16-100(1),T12-175(1) | 55.7091 | 34.9 | 20.8 | 12+4.6 | 6.504+12 | 18.0 | 21.0 | 3.0 | G35T2 | C150024864 C150024865 | 12 9
C4 |  | Sep 1 2016 11:30AM | Sep 3 2016 10:26AM | Sep 7 2016 1:20PM | Sep 7 2016 3:24PM | 71.93 | 71.863 | 58.87 | 2.20 | 56.670 | 16.200 | 15.193 |  | 2.2 | 0.0 | 2.2 | 24T32 | - | - | - | - | 2T16-100,T12-175 | - | - | - | 5.6+12 | 4.473+12 | 17.2 | 22.0 | 4.8 | G35T2 | C150024629 C150024634 | 12 10
C11 | SGBM05 | Aug 9 2016 7:30AM | Aug 15 2016 5:04PM | Sep 5 2016 1:35PM | Sep 5 2016 3:05PM | 71.86 | 74.175 | 55.96 | 2.00 | 53.860 | 18.000 | 20.315 |  | 1.4 | 0.0 | 2.0 | 15X2T32 , 15T20 | - | - | - | - | 2T16-100,T12-175 | - | - | - | 4.6+12+5.1 | NaN | 23.0 | 26.0 | 13.1 | G35T2 | C150024519 C150024521 C150024522 | 9 9 8
C7 |  | Aug 27 2016 4:45PM | Sep 1 2016 10:55AM | Sep 3 2016 12:30PM | Sep 3 2016 2:10PM | 71.62 | 72.934 | 57.23 | 2.20 | 55.134 | 17.800 | 17.800 |  | 2.2 | 0.0 | 2.0 | 30T32 (1) , 15T20 (1) | 2531.6100 | 258.9 | 2272.7 | - | 2T16-100(1),T12-175(1) | 55.1542 | 34.9 | 20.3 | 12+7.9 | 8.360+12 | 20.1 | 26.0 | -15.6 | G35T2 | C150024476 C150024477 C150024480 | 9 8 9
C3 | SGBM05 | Aug 24 2016 7:45AM | Aug 27 2016 8:40AM | Aug 27 2016 11:35AM | Aug 27 2016 1:30PM | 71.78 | 71.507 | 58.85 56.05 | 1.80 2.10 | 53.950 | 17.830 | 17.557 |  | 3.9 | 0.0 | 2.1 | 24T32 | - | - | - | - | 2T16-100,T12-175 | - | - | - | 7+12 | 6.837+12 | 19.9 | 26.0 | 6.1 | G35T2 | C150024163 C150024164 C150024165 | 9 9 8
C5 |  | Aug 18 2016 10:53AM | Aug 23 2016 2:30PM | Aug 23 2016 5:05PM | Aug 23 2016 7:40PM | 71.584 | 72.22 | 58.45 55.05 | 1.50 2.10 | 52.952 | 18.632 | 19.268 |  | 3.6 | 0.0 | 2.0 | 24T32 (1) , 24T32 (1) | 3181.7520 | - | 3181.8 | - | 2T16-100(1),T12-175(1) | 55.0983 | 34.9 | 20.2 | 12+9.3 | 9.828+12 | 21.8 | 24.0 | 10.1 | G35T2 | C150023956 C150023962 C150023965 | 8 8 8
C2 | SGBM05 | Aug 11 2016 2:10PM | Aug 17 2016 11:05AM | Aug 17 2016 5:05PM | Aug 17 2016 6:58PM | 71.641 | 71.15 | 58.17 | 2.20 | 55.970 | 15.671 | 15.180 |  | 2.2 | 0.0 | 2.2 | 24T32 (1) , 24T32 (1) | 2727.2160 | - | 2727.2 | - | 2T16-100(1),T12-175(1) | 55.3427 | 34.9 | 20.4 | 12+6.4 | 5.740+12 | 17.2 | 21.0 | 22.3 | G35T2 | C150023655 C150023663 | 12 9
C6 |  | Jul 26 2016 7:30AM | Jul 29 2016 9:45AM | Aug 11 2016 11:20AM | Aug 11 2016 11:54AM | 71.83 | 72.577 | 60.27 60.07 56.27 | 0.20 1.90 2.00 | 54.270 | 17.560 | 18.307 |  | 3.9 | 0.0 | 2.0 | 15X2T32 , 15T20 | - | - | - | - | 2T16-100,T12-175 | - | - | - | 12+6 | NaN | 20.7 | 24.0 | 3.3 | G35T2 | 1 2 3 | 9 8 7
C1 |  | Jul 30 2016 11:00AM | Aug 8 2016 1:25PM | Aug 8 2016 6:50PM | Aug 8 2016 7:12PM | 71.78 | 70.793 | 60.56 57.66 | 1.80 2.20 | 55.461 | 16.319 | 15.332 |  | 3.8 | 0.0 | 3.8 | 24T32 | - | - | - | - | 2T16-100,T12-175 | - | - | - | 5.5+12 | 4.612+12 | 17.3 | 20.0 | 15.3 | G35T2 | c15002317 c150023179 | 10 10
3/P-2 | [5 empty] | 0 | 67.4 |  |  | 0.000 | 0.000 | 67.400 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 8.200+12+12+12+12+12 | 76.2 | 0.0 | 0.0 | G40T2
29/P | [5 empty] | 0 | 64.55 |  |  | 0.000 | 0.000 | 64.550 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 5.350+12+12+12+12+12 | 73.0 | 0.0 | 0.0 | G40T2
30/P | [5 empty] | 0 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 6.550+12+12+12+12+12 | 74.4 | 0.0 | 0.0 | G40T2
32/P | [5 empty] | 0 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 6.550+12+12+12+12+12 | 74.4 | 0.0 | 0.0 | G40T2
29/N | [5 empty] | 0 | 64.55 |  |  | 0.000 | 0.000 | 64.550 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 5.350+12+12+12+12+12 | 73.0 | 0.0 | 0.0 | G40T2
30/N | [5 empty] | 0 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 6.550+12+12+12+12+12 | 74.4 | 0.0 | 0.0 | G40T2
32/N | [5 empty] | 0 | 65.75 |  |  | 0.000 | 0.000 | 65.750 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 6.550+12+12+12+12+12 | 74.4 | 0.0 | 0.0 | G40T2
6/E-CP-1 | [5 empty] | 0 | 63.65 |  |  | 0.000 | 0.000 | 63.650 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 4.450+12+12+12+12+12 | 72.0 | 0.0 | 0.0 | G40T2
6/E-CP-4 | [5 empty] | 0 | 63.65 |  |  | 0.000 | 0.000 | 63.650 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 4.450+12+12+12+12+12 | 72.0 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-1 |  | Nov 28 2016 1:10PM | Nov 28 2016 1:10PM |  |  | 0 | 58.95 | 0.00 | 0.00 | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 11.750+12+12+12+12 | 66.7 | 0.0 | -100.0 | G40T2
9-17/F-M-CP-9 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 11.750+12+12+12+12 | 66.7 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-10 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 11.750+12+12+12+12 | 66.7 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-11 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 11.750+12+12+12+12 | 66.7 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-4 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 11.750+12+12+12+12 | 66.7 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-5 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 15T20 | - | - | - | - | T12-250 | - | - | - |  | 11.750+12+12+12+12 | 66.7 | 0.0 | 0.0 | G40T2
Total | [10 empty] | 429.016 | 1385.657 | 0.0 | 115.9 | 0.0 | 50.4 |  | 62683.5 | 1590.6 | 21060.2 | 40032.7 |  | 1394.3 | 931.7 | 287.7 |  |  | 1567.3 | 579.0

## 1350
Summary List for 1891652500-CK3
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
1/H |  | Nov 8 2016 6:00PM | Nov 17 2016 8:35AM | Nov 17 2016 2:25PM | Nov 17 2016 6:14PM | 66.78 | 63.175 | 49.94 46.34 | 14.20 0.50 | 46.140 | 20.640 | 17.035 |  | 3.5 | 0.0 | 2.8 | 18T20 | 532.656 | 532.656 | T12-250 | 187.4004 | 187.4004 | 12 | 5.835+12 | 24.4 | 36.0 | 47.6 | G40T2 | C150027488 C150027489 C150027495 C150027497 | 11 9 8 8
5/N | [5 empty] | 0 | 67.9 |  |  | 0.000 | 0.000 | 67.900 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 8.700+12+12+12+12+12 | 97.2 | 0.0 | 0.0 | G40T2
7/N | [5 empty] | 0 | 67.9 |  |  | 0.000 | 0.000 | 67.900 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 8.700+12+12+12+12+12 | 97.2 | 0.0 | 0.0 | G40T2
9/O-1 | [5 empty] | 0 | 64.05 |  |  | 0.000 | 0.000 | 64.050 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 4.850+12+12+12+12+12 | 91.7 | 0.0 | 0.0 | G40T2
9/O-2 | [5 empty] | 0 | 64.05 |  |  | 0.000 | 0.000 | 64.050 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 4.850+12+12+12+12+12 | 91.7 | 0.0 | 0.0 | G40T2
12/O-1 | [5 empty] | 0 | 62.45 |  |  | 0.000 | 0.000 | 62.450 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 3.250+12+12+12+12+12 | 89.4 | 0.0 | 0.0 | G40T2
12/O-2 | [5 empty] | 0 | 62.45 |  |  | 0.000 | 0.000 | 62.450 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 3.250+12+12+12+12+12 | 89.4 | 0.0 | 0.0 | G40T2
12/O-3 | [5 empty] | 0 | 62.45 |  |  | 0.000 | 0.000 | 62.450 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 3.250+12+12+12+12+12 | 89.4 | 0.0 | 0.0 | G40T2
12/O-4 | [5 empty] | 0 | 62.45 |  |  | 0.000 | 0.000 | 62.450 |  | 0.0 | 0.0 | 0.0 | 18T20 | - | - | T12-250 | - | - |  | 3.250+12+12+12+12+12 | 89.4 | 0.0 | 0.0 | G40T2
7/P-1 | [5 empty] | 0 | 65.8 |  |  | 0.000 | 0.000 | 65.800 |  | 0.0 | 0.0 | 0.0 | 23T20 | - | - | T12-250 | - | - |  | 6.600+12+12+12+12+12 | 94.2 | 0.0 | 0.0 | G40T2
7/P-2 | [5 empty] | 0 | 65.8 |  |  | 0.000 | 0.000 | 65.800 |  | 0.0 | 0.0 | 0.0 | 23T20 | - | - | T12-250 | - | - |  | 6.600+12+12+12+12+12 | 94.2 | 0.0 | 0.0 | G40T2
7/P-3 | [5 empty] | 0 | 65.8 |  |  | 0.000 | 0.000 | 65.800 |  | 0.0 | 0.0 | 0.0 | 23T20 | - | - | T12-250 | - | - |  | 6.600+12+12+12+12+12 | 94.2 | 0.0 | 0.0 | G40T2
Total | [10 empty] | 20.640 | 728.135 | 0.0 | 3.5 | 0.0 | 2.8 |  | 532.7 | 532.7 |  | 187.4 | 187.4 |  |  | 1042.4 | 36.0

## 1500
Summary List for 1891652500-CK3
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T20 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T12 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
9-17/F-M-CP-2 |  | Nov 25 2016 11:00AM | Dec 1 2016 4:15PM | Dec 3 2016 3:50PM | Dec 3 2016 5:25PM | 67.2 | 58.95 | 48.85 47.45 40.35 39.45 | 4.20 1.30 3.70 7.60 | 37.148 | 30.052 | 21.802 |  | 8.8 | 0.0 | 2.9 | 23T20 | 680.616 | 680.616 | T12-250 | 201.7639 | 201.7639 | 12 | 10.602+12 | 38.5 | 50.0 | 15.5 | G40T2 | C150028231 C150028233 C150028232 C150028234 C150028235 | 10 10 9 11 10
5/P-1 |  | Nov 3 2016 1:00PM | Nov 18 2016 7:00PM | Nov 18 2016 2:45PM | Nov 18 2016 6:15PM | 67.06 | 66.3 | 54.80 54.70 49.90 49.90 49.80 | 1.50 8.00 0.40 0.50 14.50 | 46.800 | 20.260 | 19.500 |  | 14.4 | 0.0 | 3.1 | 23T20 | 680.616 | 680.616 | T12-250 | 201.7639 | 201.7639 | 12 | 8.300+12 | 34.5 | 45.0 | 10.5 | G40T2 | Pending C150027543 C150027545 C150027546 C150027548 | 9 9 9 9 9
1/P |  | Oct 22 2016 11:00AM | Nov 4 2016 12:00PM | Nov 7 2016 12:30PM | Nov 7 2016 4:10PM | 67.153 | 67.8 | 58.25 56.45 55.85 55.45 55.05 54.65 54.25 53.85 53.45 | 1.30 2.40 2.00 2.70 2.00 2.00 2.00 2.00 4.40 | 52.253 | 14.900 | 15.547 |  | 9.2 | 0.0 | 4.2 | 23T20 | 680.616 | 680.616 | T12-250 | 201.7639 | 201.7639 | 12 | 4.347+12 | 27.5 | 36.0 | 23.7 | G40T2 | c150027054 c150027055 c150027058 | 12 12 12
5/P-2 |  | Nov 25 2016 11:15AM | Nov 25 2016 11:15AM |  |  | 0 | 66.3 | 0.00 | 0.00 | 0.000 | 0.000 | 66.300 |  | 0.0 | 0.0 | 0.0 | 23T20 | - | - | T12-250 | - | - |  | 7.100+12+12+12+12+12 | 117.2 | 0.0 | -100.0 | G40T2
9-17/F-M-CP-6 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 23T20 | - | - | T12-250 | - | - |  | 11.750+12+12+12+12 | 104.2 | 0.0 | 0.0 | G40T2
9-17/F-M-CP-12 | [5 empty] | 0 | 58.95 |  |  | 0.000 | 0.000 | 58.950 |  | 0.0 | 0.0 | 0.0 | 23T20 | - | - | T12-250 | - | - |  | 11.750+12+12+12+12 | 104.2 | 0.0 | 0.0 | G40T2
Total | [10 empty] | 65.212 | 241.049 | 0.0 | 32.4 | 0.0 | 10.2 |  | 2041.8 | 2041.8 |  | 605.3 | 605.3 |  |  | 426.0 | 131.0