## 1500
Summary List for J2380-KLCC P2
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T32 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T10 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
DP 9 | SGBM26 | Oct 7 2016 12:20PM | Oct 9 2016 6:00PM | Oct 11 2016 7:45PM | Oct 11 2016 8:57PM | 35.591 | 19.575 | 36.35 | 0.00 | 20.354 | 36.237 | -0.779 |  | 0.0 | 0.0 | 0.0 | 22T32 | 5138.782 | 5138.782 | T10-150 | 1052.3739 | 1052.3739 | 37 | 0.501 | -1.4 | 40.0 | -100.0 | G50T3 | 28084913 28084915 28084916 28084917 | 10 10 10 10
DP 10 | SGBM26 | Oct 1 2016 1:10PM | Oct 2 2016 3:10PM | Oct 4 2016 10:44PM | Oct 4 2016 11:50PM | 35.67 | 19.575 | 36.42 | 0.00 | -3.181 | 38.851 | 22.756 |  | 0.0 | 0.0 | 0.0 | 22T32 | 5472.108 | 5472.108 | T10-150 | 1122.7865 | 1122.7865 | 39.4 | - | 40.2 | 39.0 | -75.1 | G50T3 | 28084436 28084437 28084438 28084440 | 10 10 10 9
DP 13 | SGBM26 | Sep 28 2016 2:00PM | Sep 29 2016 7:48PM | Sep 30 2016 1:50AM | Sep 30 2016 4:10AM | 35.597 | 19.575 | 36.32 | 0.00 | -13.680 | 51.877 | 33.255 |  | 0.0 | 0.0 | 0.0 | 22T32 | 7249.849 | 7249.849 | T10-150 | 1498.3200 | 1498.3200 | 52.2 | - | 58.8 | 63.0 | -63.4 | G50T3 | 28084247 28084247 28084249 28084250 28084253 28084254 28084255 | 10 6 10 8 10 10 9
DP 11 | [5 empty] | 0 | 19.575 |  |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 0.0 | 22T32 | - | - | T10-150 | - | - |  | - | 34.6 | 0.0 | 0.0 | G50T3
DP 12 | [5 empty] | 0 | 19.575 |  |  | 0.000 | 0.000 | 19.575 |  | 0.0 | 0.0 | 0.0 | 22T32 | - | - | T10-150 | - | - |  | - | 34.6 | 0.0 | 0.0 | G50T3
Total | [10 empty] | 126.965 | 94.382 | 0.0 | 0.0 | 0.0 | 0.0 |  | 17860.7 | 17860.7 |  | 3673.5 | 3673.5 |  |  | 166.8 | 142.0

## 2000
Summary List for J2380-KLCC P2
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T32 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T10 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
DQ 42 | SGBM26 | Oct 5 2016 8:50PM | Oct 7 2016 11:05AM | Oct 7 2016 11:17PM | Oct 8 2016 2:30AM | 35.456 | 19.575 | -24.02 | 0.20 | -24.223 | 59.679 | 43.798 |  | 0.2 | 0.0 | 0.0 | 40T32 | 14974.436 | 14974.436 | T10-150 | 2315.5171 | 2315.5171 | 59.3 | - | 137.6 | 133.0 | -100.0 | G50T3 | 28084666 28084664 28084668 28084669 28084670 28084671 28084672 28084673 28084675 28084676 28084677 28084678 28084679 28084680 | 9 10 10 10 10 10 9 10 10 10 10 8 10 7
DQ 44 | SGBM26 | Sep 26 2016 6:30PM | Sep 27 2016 6:45PM | Sep 28 2016 4:35AM | Sep 28 2016 10:15AM | 35.851 | 18.575 | 36.65 | 0.00 | 5.655 | 51.296 | 12.920 |  | 0.0 | 0.0 | 0.0 | 40T32 | 13156.292 | 13156.292 | T10-150 | 2028.9137 | 2028.9137 | 52.1 | - | 40.6 | 123.0 | -100.0 | G50T3 | 28084076 28084077 28084078 28084079 28084080 28084082 28084083 28084084 28084085 28084086 28084088 28084089 28084090 | 10 10 10 9 10 10 10 9 10 10 9 10 6
DQ 40 | SGBM26 | Sep 23 2016 10:55AM | Sep 26 2016 3:30PM | Sep 27 2016 1:18AM | Sep 27 2016 3:30AM | 35.636 | 19.575 | 36.44 | 0.00 | -4.561 | 45.697 | 24.136 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11716.928 | 11716.928 | T10-150 | 1802.0193 | 1802.0193 | 46.4 | - | 75.8 | 90.0 | -100.0 | G50T3 | 28083999 28084000 28084001 28084003 28084005 28084006 28084008 28084009 28044010 28084013 | 9 10 10 8 8 6 10 10 10 9
DQ 43 | SGBM26 | Sep 21 2016 11:15AM | Sep 21 2016 10:10PM | Sep 22 2016 2:36AM | Sep 22 2016 5:00AM | 35.397 | 19.575 | 36.40 | 0.00 | -5.598 | 40.995 | 25.173 |  | 0.0 | 0.0 | 0.0 | 40T32 | 10580.588 | 10580.588 | T10-150 | 1622.8921 | 1622.8921 | 41.9 | - | 79.1 | 90.7 | -100.0 | G50T3 | 28083702 28083703 28083704 28083705 28083706 28083707 28083708 28083709 28083710 28083711 | 9 10 8 10 10 9 10 8 8.5 8.2
DQ 37 | SGBM29 | Sep 15 2016 10:40AM | Sep 19 2016 4:50PM | Sep 20 2016 12:40AM | Sep 20 2016 3:50AM | 35.568 | 18.575 | 36.37 | 0.00 | 1.374 | 46.994 | 17.201 |  | 0.0 | 0.0 | 0.0 | 40T32 | 12070.456 | 12070.456 | T10-150 | 1857.7477 | 1857.7477 | 47.8 | - | 54.0 | 115.0 | -305.6 | G50T3 | 28083540 28083541 28083542 28083544 28083547 28083548 28083550 28083551 28083552 28083553 28083555 28083556 | 10 10 10 9 10 10 10 10 10 9 10 7
DQ 39 | SGBM26 | Sep 6 2016 5:05PM | Sep 7 2016 3:00PM | Sep 8 2016 1:20AM | Sep 8 2016 5:00AM | 35.425 | 19.575 | 36.42 | 0.00 | 1.425 | 42.000 | 18.150 |  | 0.0 | 0.0 | 0.0 | 40T32 | 10858.360 | 10858.360 | T10-150 | 1666.6787 | 1666.6787 | 43 | - | 57.0 | 96.0 | -100.0 | G50T3 | 28083023 28083024 28083025 28083027 28083028 28083029 28083032 28083035 28083036 28083040 | 10 9 10 10 10 9 10 10 10 8
DQ 31 | SGBM26 | Sep 2 2016 5:35PM | Sep 3 2016 3:25PM | Sep 4 2016 12:34AM | Sep 4 2016 3:00AM | 35.711 | 18.575 | 36.60 | 0.00 | -8.605 | 44.316 | 27.180 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11413.904 | 11413.904 | T10-150 | 1754.2520 | 1754.2520 | 45.2 | - | 85.4 | 98.0 | -100.0 | G50T3 | 28082800 28082801 28082802 28083803 28082804 28082805 28082806 28082807 28082808 28082809 | 10 10 10 9 10 10 10 9 10 10
DQ 29 | SGBM29 | Jul 28 2016 9:30AM | Jul 29 2016 5:35PM | Jul 29 2016 11:20PM | Jul 30 2016 2:45AM | 35.946 | 18.575 | 36.76 | 0.00 | 3.761 | 46.785 | 14.814 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11994.700 | 11994.700 | T10-150 | 1845.8059 | 1845.8059 | 47.5 | - | 46.5 | 106.0 | -92.4 | G50T3 | 28080699 28080700 28080701 28080702 28080703 28080704 28080705 28080706 28080707 28080708 28080709 28080710 | 10 9 8 6 10 10 10 9 8 6 10 10
DQ 23 | SGBM26 | Jul 26 2016 2:30PM | Jul 27 2016 1:50PM | Jul 28 2016 9:58PM | Jul 29 2016 1:15AM | 35.945 | 19.575 | 36.75 | 0.00 | -3.750 | 39.695 | 23.325 |  | 0.0 | 0.0 | 0.0 | 40T32 | 10227.060 | 10227.060 | T10-150 | 1567.1636 | 1567.1636 | 40.5 | - | 73.3 | 85.0 | -100.0 | G50T3 | 28080579 28080580 2808081 28080582 28080583 28080584 28080584 28080586 28080587 | 10 8 10 10 10 10 10 8 9
DQ 24 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 25 | SGBM26 | Jul 22 2016 9:00AM | Jul 26 2016 12:00PM |  |  | 36.001 | 18.575 | 36.79 | 0.00 | -8.911 | 44.912 | 27.486 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11540.164 | 11540.164 | T10-150 | 1774.1550 | 1774.1550 | 45.7 | - | 86.4 | 0.0 | -100.0 | G50T3
DQ 27 | [5 empty] | 0 | 16.575 |  |  | 0.000 | 0.000 | 16.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 52.1 | 0.0 | 0.0 | G50T3
DQ 28 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 18 | SGBM26 | Jun 27 2016 5:50PM | Jun 29 2016 12:50PM |  |  | 35.862 | 18.575 | 36.66 | 0.00 | -6.843 | 42.705 | 25.418 |  | 0.0 | 0.0 | 0.0 | 40T32 | 10959.368 | 10959.368 | T10-150 | 1682.6012 | 1682.6012 | 43.4 | - | 79.9 | 0.0 | -100.0 | G50T3
DQ 19 | SGBM26 | Jul 18 2016 10:25AM | Jul 20 2016 4:15PM |  |  | 35.901 | 18.575 | 36.75 | 0.00 | -10.749 | 46.650 | 29.324 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11969.448 | 11969.448 | T10-150 | 1841.8253 | 1841.8253 | 47.4 | - | 92.1 | 0.0 | -100.0 | G50T3
DQ 20 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 21 | SGBM26 | Jul 29 2016 8:00PM | Aug 2 2016 3:20PM |  |  | 36.01 | 18.575 | 36.77 | 0.00 | 4.773 | 42.737 | 13.802 |  | 0.0 | 0.0 | 0.0 | 40T32 | 10984.620 | 10984.620 | T10-150 | 1686.5818 | 1686.5818 | 43.5 | - | 43.4 | 0.0 | -100.0 | G50T3
DQ 22 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 32 | SGBM26 | Sep 5 2016 3:45PM | Sep 6 2016 4:20PM |  |  | 35.798 | 18.575 | 36.58 | 0.00 | -8.516 | 44.314 | 27.091 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11388.652 | 11388.652 | T10-150 | 1750.2714 | 1750.2714 | 45.1 | - | 85.1 | 0.0 | -100.0 | G50T3
DQ 33 | SGBM26 | Sep 19 2016 6:00PM | Sep 20 2016 3:40PM |  |  | 35.773 | 18.575 | 36.52 | 0.00 | 5.416 | 0.000 | 13.159 |  | 0.0 | 0.0 | 0.0 | 40T32 | 9343.240 | 9343.240 | T10-150 | 1427.8425 | 1427.8425 | 37 | - | 41.3 | 0.0 | -100.0 | G50T3
DQ 34 | SGBM26 | Sep 10 2016 10:30AM | Sep 14 2016 6:30PM |  |  | 35.445 | 18.575 | 36.44 | 0.00 | -7.855 | 43.300 | 26.430 |  | 0.0 | 0.0 | 0.0 | 40T32 | 11085.628 | 11085.628 | T10-150 | 1702.5042 | 1702.5042 | 43.9 | - | 83.0 | 0.0 | -100.0 | G50T3
DQ 35 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 36 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 38 | SGBM29 | Aug 25 2016 4:50PM | Aug 27 2016 12:50PM |  |  | 35.711 | 19.575 | 36.60 | 0.00 | 1.595 | 50.416 | 17.980 |  | 0.0 | 0.0 | 0.0 | 40T32 | 12929.024 | 12929.024 | T10-150 | 1993.0882 | 1993.0882 | 51.2 | - | 56.5 | 0.0 | -107.7 | G50T3
DQ 41 | SGBM26 | Sep 8 2016 4:45PM | Sep 9 2016 12:50PM |  |  | 35.533 | 19.575 | 36.42 | 0.00 | -3.684 | 39.217 | 23.259 |  | 0.0 | 0.0 | 0.0 | 40T32 | 10100.800 | 10100.800 | T10-150 | 1547.2606 | 1547.2606 | 40 | - | 73.1 | 0.0 | -100.0 | G50T3
DQ 45 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 46 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - |  | - | 58.4 | 0.0 | 0.0 | G50T3
DQ 30 | SGBM16 | Aug 10 2016 1:00AM | Aug 27 2016 4:32AM |  |  | 0 | 18.575 | 0.00 | 9.00 | -9.000 | 8.217 | 27.575 |  | 9.0 | 0.0 | 0.0 | 40T32 | - | - | T10-150 | - | - | 0 | - | 86.6 | 0.0 | -100.0 | G50T3
Total | [10 empty] | 779.925 | 603.396 | 0.0 | 9.2 | 0.0 | 0.0 |  | 207293.7 | 207293.7 |  | 31867.1 | 31867.1 |  |  | 1895.9 | 936.7

## 2200
Summary List for J2380-KLCC P2
Pile Details | [5 empty] | General Details |  |  |  |  | Pile Details | [5 empty] | Steel Cage | [7 empty] | Concrete
Pile No. | Rig | Boring Start Date | Boring End Date | Concrete Start Date | Concrete End Date | Piling Platform Level (mRL) | Cut-off Level (mRL) | Hit Rock Level (mRL) | Rock Layer Thickness (m) | Toe Level (mRL) | Bored Depth - PPL (m) | Pile Length (m) | Cavity (m) | Total Rock Coring (m) | Paid Rock Coring (m) | Rock Socket (m) | Main Reinforcement Content | Main Bar Weight (kg) | T32 Weight (kg) | Helical/ Spiral Link | Helical/Spiral Weight (kg) | T10 Weight (kg) | Cage Length | Computed Cage Length | Theoretical (m3) | Actual (m3) | Wastage (%) | Grade | DO Number | Concrete Volume (m3)
DR 14 | SGBM29 | Aug 2 2016 10:55AM | Aug 3 2016 5:40PM | Aug 4 2016 2:25AM | Aug 4 2016 6:10AM | 36.029 | 18.575 | 36.78 | 0.00 | 10.781 | 45.048 | 7.794 |  | 0.0 | 0.0 | 0.0 | 48T32 | 13848.197 | 13848.197 | T10-150 | 1960.7959 | 1960.7959 | 45.7 | 9.074 | 29.6 | 130.0 | -100.0 | G50T3 | 28080956 28080957 28080958 28080959 28080960 28080961 28080962 28080963 28080964 28080965 28080966 28080967 28080968 28080969 | 10 10 10 8 9 10 10 10 10 8 9 10 8 8
DR 15 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 16 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 17 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 18 |  | Sep 1 2016 8:00AM | Sep 1 2016 8:30AM |  |  | 35.918 | 18.575 | 36.59 | 0.00 | 35.918 | 0.000 | -17.343 |  | 0.0 | 0.0 | 9.0 | 48T32 | - | - | T10-150 | - | - | 5.6+12+12+12 | -16.063 | -65.9 | 0.0 | -100.0 | G50T3
DR 19 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 20 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 21 | SGBM26 | Sep 30 2016 11:20AM | Oct 1 2016 12:30PM |  |  | 35.878 | 18.575 | 36.51 | 0.00 | 1.509 | 45.469 | 17.066 |  | 0.0 | 0.0 | 0.0 | 48T32 | 13939.104 | 13939.104 | T10-150 | 1973.9940 | 1973.9940 | 46 | - | 64.9 | 0.0 | -100.0 | G50T3
DR 22 | SGBM26 | Oct 15 2016 9:50AM | Oct 22 2016 10:00AM |  |  | 35.787 | 18.575 | -10.28 | 6.50 | -16.776 | 0.000 | 35.351 |  | 6.5 | 0.0 | 5.5 | 48T32 | 16181.482 | 16181.482 | T10-150 | 2299.5469 | 2299.5469 | 53.4 | - | 134.4 | 0.0 | -100.0 | G50T3
DR 23 | SGBM29 | Oct 14 2016 10:20AM | Oct 17 2016 7:10AM |  |  | 35.788 | 18.575 | 3.57 | 2.00 | 1.566 | 0.000 | 17.009 |  | 2.0 | 0.0 | 7.2 | 48T32 | 12484.589 | 12484.589 | T10-150 | 1762.8246 | 1762.8246 | 41.2 | - | 64.7 | 0.0 | -100.0 | G50T3
DQ 26-R | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 11 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 12 | [5 empty] | 0 | 18.575 |  |  | 0.000 | 0.000 | 18.575 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | - | 70.6 | 0.0 | 0.0 | G50T3
DR 13 | SGBM29 | Aug 20 2016 2:30PM | Oct 19 2016 3:00PM |  |  | 35.939 | 18.575 | 36.69 | 0.00 | 15.687 | 0.000 | 2.888 |  | 0.0 | 0.0 | 0.0 | 48T32 | - | - | T10-150 | - | - |  | 4.168 | 11.0 | 0.0 | -100.0 | G50T3
Total | [10 empty] | 90.517 | 211.365 | 0.0 | 8.5 | 0.0 | 21.7 |  | 56453.4 | 56453.4 |  | 7997.2 | 7997.2 |  |  | 803.6 | 130.0